Programme Completion Review
Title: Safeguarding Resource and Support Hub (RSH)
Final Programme Spend £ (full life): £10.4m	Review Date:	June 2025
Programme Code: [AMP ID#] 300788	Start Date: 18/06/2019	End Date: / 30/04/2025

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Programme Score	A	A	A+	A+	A+	A+
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/47791777.odt
DevTracker Links to logframe:	https://iati.fcdo.gov.uk/iati_documents/D0000956.xls

A. Summary and Overview
Description of the programme and what it has achieved
The Resource and Support Hub (RSH) Programme is a UK Foreign, Commonwealth and Development Office-funded programme that seeks to support organisations working in the international development sector to strengthen their safeguarding measures against sexual exploitation, abuse, and sexual harassment (SEAH). It has a strong focus on supporting small, local Civil Society Organisations (CSOs), particularly those operating in the ‘global south’.

RSH was established in response to evidence gathered which indicated the SEAH safeguarding support landscape was fragmented, with no centralised body of contextualised and dedicated resources for less-resourced organisations and CSOs. The programme was therefore designed around three key outcomes that are outlined in the theory of change (shown later):
[note] ‘Scoping Report, Centre of Safeguarding Excellence’ (August 2018)
Improving dialogue on safeguarding against SEAH amongst organisations in the aid sector to facilitate shared learning and raise awareness;
Building the safeguarding capacity of less-resourced CSOs, including mainstreaming safeguarding within organisations and shifting organisational culture; and
Generating evidence on what works in safeguarding against SEAH in the aid sector and making it accessible and contextualised to less-resourced CSOs, contributing to the global evidence base.

RSH ran between December 2019 and April 2025 with a phased approach to delivery, with a global platform running alongside national hubs which mobilised and closed at different periods (see image 1). The total spend over its lifecycle was just over £10.4m. Over its lifetime, RSH consisted of a global online hub providing a “one-stop-shop” of tools, guidance and resources on safeguarding against SEAH, including a consultant directory, webinars and e-learning available in more than 10 languages. Alongside this, there have been eight national hubs across Africa (Ethiopia, Nigeria and South Sudan), Middle East and North Africa (Jordan, Yemen and Syria, as well as additional resource provided in response to the Türkiye-Syria earthquake) and South Asia (Pakistan and Bangladesh). These provided support to CSOs through dedicated online platforms of contextualised resources, tools and an ‘Ask An Expert’ service and direct support via training, webinars and mentorship. Two web-only ‘language hubs’ were also created gathering translated French and Swahili resources. An Eastern European Hub was funded separately by the Disasters Emergency Committee from April 2022-October 2023, in response to the war in Ukraine. This provided direct services and support, working with three national hubs in Moldova, Poland and Romania, but is not included within this review. The Nigeria and Ethiopia hubs both secured additional, separate funding from FCDO Posts in late 2023. These investments enabled both hubs to continue some operations alongside undertaking pilots for a national CSO to take over leadership of the national hubs, supported by the global platform.

The programme had a two-phase approach; phase 1 inception over two-years for up to £4m, increasing to £10m for phase 2 over the subsequent 3 years, subject to satisfactory performance. The initial three main components (see Annex A for the initial Business Case ToC) or ‘pillars’ consisted of:
1. Providing a ‘one-stop shop’ for guidance and training: Coordinating the range of tools and resources already available on safeguarding against SEAH initiatives and convene key actors who can support and collaborate with organisations to bring about the necessary change.
2. Facilitating access to quality assured support services: For RSH to provide a portal to quality assured, locally tailored services and information (potentially delivered through the regional Hubs) to help particularly smaller organisations in FCDO countries/regions with less resource to increase their SEAH safeguarding capability and meet international standards
3. Building evidence and boosting innovation: Through funding and/or championing research, RSH to capture and further develop evidence on what works for safeguarding against SEAH and the impact of standards/measures already in place, as well as best practice on engaging with and supporting survivors to determine their needs and priorities.
Phase 1 began in December 2019, with the global online hub going ‘live’ in May 2020, after the inception period, providing a library of tools and guidance on safeguarding against SEAH, a list of quality-assured PSEAH consultants and a range of primary products, including webinars and e-learning. This was followed by the creation of initial national hubs in Ethiopia, Nigeria and South Sudan to provide contextual guidance and support for local organisations, including translation of resources into multiple languages. Following successful demonstration of the RSH concept, the programme was extended in October 2021 for phase 2, allowing it to continue launching national hubs in MENA and South Asia regions. A no-cost programme extension was also agreed in February 2024 to March 2025. This was to provide time for the South Asia Hub to complete its planned programme of work, which was impacted by COVID-19 and national registration challenges, with a scaled-back global team to focus on responsible programme exit, reporting, lessons learning and evaluation. Due to UK ODA pressures, the programme saw a 20% reduced budget in FY 2023/24 with RSH reprofiling delivery scope to meet this, limiting impact on outcomes. A final no-cost extension to April 2025 was agreed in 2025, to enable transition to the new programme ‘RSH2’.

The programme consistently scored A to A+ across the programme lifetime, consistently exceeding expectations. The programme has scored an A+ for its PCR reflecting the impact and achievement against the overall output targets, and excellent partner performance, despite various challenges in relation to COVID-19, challenging operating contexts and reduced funding scopes. The programme has built up an excellent reputation in the sector as a go-to for accessible, tailored and contextualised resources and support, laying a solid foundation for the next phase of programming which commenced in May 2025 to run to 2030 under RSH2.

Major lessons learned, evidence generated and recommendations
The third key outcome pillar of RSH is to generate evidence on ‘what works’ in building organisational capability to safeguarding against SEAH in the sector and making it accessible and contextualised to less-resourced CSOs, to contribute to the global evidence base. As such, over the lifetime RSH produced a wealth of evidence. The 2021 Global Evidence Review of Sexual Exploitation and Abuse and Sexual Harassment in the Aid Sector and its 2025 update, stands out as a major contribution. These evidence-based reviews, published on the RSH Global website, map existing gaps in SEAH prevention and response and offer recommended priorities to the sector for future research.

The major finding from the Independent FCDO-funded Evaluation by Alinea International was: “The RSH programme successfully demonstrated that targeted, locally adapted safeguarding capacity-building can strengthen organisational practices among less-resourced CSOs. Its focus on marginalised groups marked significant progress in inclusive programming. High value for money was achieved through efficient delivery, broad reach, and effective mentorship-based models, particularly where senior leadership drove organisation-wide cultural change. The programme also embedded GEDSI (gender, equity, disability, and social inclusion) considerations effectively and contributed meaningfully to sector evidence. However, systemic and structural barriers continue to constrain sustained impact. Challenges included limited integration with government and sector-wide systems, infrastructure disparities that undermined digital access, and poorly communicated exit plans that affected trust. Translation barriers and technical language limited the uptake of key RSH resources by CSOs, and informal and formal peer networks were not sufficiently embedded for long-term sustainability. Short timeframes further restricted the level of impact the RSH hubs could have and ultimately sustain.”

Key lessons and recommendations for future programming:
The Alinea Evaluation provided key lessons learned based on its findings and conclusions from RSH. These have been developed into key recommendations for FCDO / future programming. These are summarised below alongside recommendations provided by FCDO as part of this PCR:
- Contextualisation and inclusion are essential for relevance and equity: RSH successfully demonstrated that effective safeguarding materials and approaches must be rooted in the local context. Deep cultural and linguistic adaptation, led by local experts and shaped through participatory design, is more impactful than surface-level translation. Likewise, inclusive design, from the outset, ensures meaningful engagement of marginalised groups. This requires proactive targeting, dedicated accessibility budgets, and partnerships with local organisations. The RSH demonstrated highly effective and intentional integration of GEDSI considerations into both its design and implementation, achieving meaningful reach to marginalised populations while adapting to diverse contextual challenges across regions and contributed meaningfully to sector evidence. Future programmes should consistently embed contextualisation and inclusion in design and delivery.
- Relationship-based and adaptive delivery strengthen capacity building: Face-to-face mentorship and relationship-based engagement consistently led to stronger, longer-lasting capacity outcomes than just digital-only models. These approaches allow for real-time problem-solving, trust-building, and contextual responsiveness. Infrastructure disparities (especially in rural and low-resource settings) also mean digital components must be complemented by accessible offline options. Future programming should also ensure digital platforms are as user-friendly as possible to support access to the breadth of resources and tools. Programming should invest in blended, adaptive delivery models tailored to varying levels of connectivity and access.
- Leadership and organisational culture drive sustainable safeguarding: Genuine integration of safeguarding requires visible, sustained leadership commitment, not just policy compliance. Organisational culture change is most effective when senior leaders actively champion safeguarding, rather than delegating it to individuals. Building in leadership accountability mechanisms is key to driving and measuring cultural transformation over time.
- Coordination and political economy understanding enhance systemic impact: For safeguarding initiatives to have lasting, sector-wide influence, they should seek to align with national systems, donor frameworks, and coordination mechanisms. RSH’s comprehensive participatory Country Assessments were critical in designing effective tailored offers. Furthermore, political, cultural, and institutional dynamics can significantly affect programme implementation. Country Assessments are most successful when they include political economy and GEDSI analysis and dedicate resources to stakeholder coordination and adaptive delivery.
- Nationally developed and embedded and careful translations ensure effective contextualised materials: RSH’s approach to contextualisation was strong; localised and developed with national and technical expertise. In some cases, barriers to understanding persisted due to some translations lacking sufficient contextual nuances and some containing too technical (and therefore inaccessible) language. Plain language, participatory and adaptation approaches are key to communicate to wide user needs (at varying capability levels). A depth over breadth (quantity) approach can support in future programming (now that baseline documents are in place) to ensure resource is maximised effectively to produce most critical resources.
- Systemic and structural barriers must be addressed alongside individual capacity: While individual and organisational capacity building is important, its impact is often affected by systemic constraints such as lack of funding access, institutional gatekeeping, and exclusion from networks. RSH’s collaboration with national partners and networks from the outset was critical to building truly relevant, contextualised resources and support. Training offers which are paired with interventions which seek to address these structural barriers, by enhancing programme coordination, support more equitable participation and long-term change are more successful in enabling sector-wide transformation. This should include support to embed CSOs in national, peer-learning networks beyond programme lifecycles and more strategic engagement with national governments /institutions and wider strategic partners (e.g. UN / international bodies).
- Sustainability requires institutional embedding, early transition planning and receptive structural systems. RSH’s interventions saw strong internal organisational capability building and commitment post-support, demonstrated via continued policy implementation and safeguarding integrated into core operational frameworks. However, institutional embedding and memory varied based on leadership structures, staff turnover and funding and resource constraints. In addition, broader systemic fragilities outside of programme control, including national governance weaknesses, political instability, and shrinking civic space, threaten durability of PSEAH practices. These issues undermine longer-term impact. Early evidence from RSH’s locally owned pilots, demonstrate the potential for sustainable local ownership despite ongoing systemic challenges. Trust and sustainability are also best preserved when programmes have responsible exit strategies, communicated clearly from the outset. Planning for transition beyond hub lifecycles such as developing and engaging local handover/further investment options early, establishing durable peer-led communities of practice, stakeholder engagements and comms on ongoing offers (e.g. online resources) helps to prepare users and sustain impacts. Sustainability planning is therefore key to strong delivery, including longer programme cycles, responsible exit /transition strategies developed and embedded from the outset alongside peer support and knowledge retention, as standard practice.

How this report was conducted
The PCR principally draws upon the findings of the Alinea International Independent Evaluation commissioned by FCDO in the final year of RSH’s lifecycle. This evaluated the performance of the programme to determine how far RSH achieved expected results, analysed the value for money and captured key lessons and learning. Guided by OECD-DAC criteria, the Evaluation explored outcomes, effectiveness, relevance, efficiency, impact, sustainability, and coherence. The PCR was drafted by the FCDO Programme team and also drew from existing RSH materials, data and evidence (e.g. quarterly reports, logframe, annual user surveys, evidence pieces, previous ARs) and a selection of final discussions with some core RSH programme staff. The PCR focused on assessing the overall achievements at outcome and output levels (as per the logframe), value for money and lessons of RSH as it concluded.

This PCR also covers the work of RSH Nigeria phase 2 period, where it was a standalone contract, from October 2023 to March 2025, with Social Development Direct, funded by Post (FCDO Nigeria) directly. The contract aligned objectives to the Global RSH programme, and therefore sits as a component to the programme. The total spend over the duration of this contract was around £434K which is included in the £10.4m total. The contracts outcomes and indicators are aligned directly with the RSH global programme and these are therefore reported alongside each other in the PCR (Nigeria results in blue/shaded).

Actions to be taken following approval of this report:
- The programme team will upload it to DevTracker, a public platform used to share information about development projects funded by the UK government. This ensures transparency and accountability, allowing stakeholders, researchers, and the general public to access the report and understand the outcomes, challenges, and lessons learned from the project.
- The programme team will distribute the PCR to all implementing partners involved in the project. This serves two purposes:
  - Knowledge sharing: Highlighting key lessons learned, best practices, and challenges encountered during implementation.
  - Actionable feedback: Clearly outlining any follow-up actions required from the partners.
- The programme team will also disseminate this to wider key stakeholders for knowledge sharing (as above) and share with the new RSH2 implementing partners to support to inform delivery of the new phase of the programme, under its new contract.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Initial two-year phase approved for up to £4m, to increase to £10m over the subsequent 3 years, subject to satisfactory performance.	£10.4m (£10m for the core programme and £0.4m provided separately via FCDO Nigeria)
Timeframe	December 2019 – December 2024	December 2019 – April 2025
Outcomes	Aid organisations and less-resourced CSOs in particular are better equipped and able to develop and implement contextualised strategies to safeguard against SEAH. / Indicator 1: Capacity of RSH users to safeguard against SEAH. / Indicator 2: RSH contributes to a strengthened and sustainable enabling environment to support organisations to better safeguard against SEAH.	Indicator amended to: Less-resourced CSOs and other relevant actors across the aid sector are better equipped and able to develop and implement contextualised strategies to safeguard against SEAH. / Final result achieved: All outcome indicator targets achieved or exceeded with strong evidence that the capacity of RSH users to safeguard against SEAH was improved and users confirming greater collaboration and more supportive relationships to address SEAH.

Overall assessment of programme outcomes, sustainability and VfM

All programme outcomes were achieved or exceeded across the lifetime, as measured against the final targets for December 2024, the agreed timeframe, and the budget allocated. The final logframe target towards meeting the impact of improved prevention of, and response to, sexual exploitation, abuse and sexual harassment in the aid sector was achieved with 84% of all surveyed users, against a target of 75%, ‘Strongly Agreed’ or ‘Agreed’ they improved their knowledge, skills, understanding and practice on safeguarding against SEAH.

The programme met and exceeded its logframe outcome of less-resourced CSOs and other relevant actors across the aid sector are better equipped and able to develop and implement contextualised strategies to safeguard against SEAH.

Outcome indicator 1: Capacity of RSH users to safeguarding against SEAH through a) mentored organisations that have demonstrated improved organisational safeguarding culture & capacity and b) RSH users surveyed better able to apply international standards and better safeguard against SEAH to the local contexts in which they operate.

(a) 100% of organisations taking part in the final Hub phase in South Asia mentorship programme have demonstrated improved organisational safeguarding culture & capacity, against a milestone target of 75%, evidenced through an improvement from a baseline Organisational Capability Assessment (OCA). This was further validated within the Alinea Evaluation. The target was consistently exceeded across the programme lifetime.

(b) 84% of all surveyed users ‘Strongly Agreed’ or ‘Agreed’ that engaging with RSH has improved their understanding of how to apply international safeguarding standards in their context (as a breakdown, 84% for respondents from NGOs/CSOs and Organisations of Persons with Disabilities (OPDs), with strong responses from key target country audiences with 89% for Pakistan, 86% for Bangladesh and 79% for Nigeria). This exceeds the 70% target, which was consistently exceeded across the programme lifetime.

Outcome indicator 2: RSH contributes to a strengthened and sustainable enabling environment to support organisations to better safeguard against SEAH through a) CSOs and other relevant actors reporting greater collaboration and more supportive relationships to address SEAH and b) evidence of RSHs sustainable legacy at national and global level.

(a) 73% of all surveyed users ‘Strongly Agreed’ or ‘Agreed’ that RSH has provided a safe and collaborative space, where users feel comfortable to share experiences, and/or challenges regarding SEAH safeguarding (as a breakdown, 77% of respondents from NGOs/CSOs and OPDs, with strong responses from key target country audiences with 84% from Bangladesh, 77% from Pakistan and 74% from Nigeria). This is well above the target of 55% of users, and was a sustained strong outcome across the programme lifetime.

(b) Strong evidence demonstrated RSH’s sustainable legacy at national and global levels. The RSH Africa Legacy Study found evidence that highly engaged users in the Africa Hubs have continued to share their learnings and additional organisations have benefitted from RSH after the closure of the Hubs. This highlights the ripple effect which RSH has had in sustaining an enabling environment to support organisations to better safeguard against SEAH. The MENA and South Asia exit strategies were subsequently designed by incorporating learning from the Africa legacy Study. Successes and challenges of sustainability activities were shared and reflected upon in the final 6 Hub contexts (MENA and South Asia). RSH also worked with strategic stakeholders at a global and national level to look at champions for promoting the resources. The widespread work of the Common Approach to Protection from Sexual Exploitation, Abuse and Harassment (CAPSEAH) has also provided a platform for RSH to leverage key messages and resources and align CSOs with international best practice.

The Alinea Independent Evaluation found the RSH programme has made significant progress at the outcome level, largely achieving its expected results by strengthening safeguarding practices among less-resourced CSOs through improved dialogue, enhanced capacity, and access to contextualised evidence. This was particularly evident in its culturally sensitive and targeted capacity-building efforts, which meaningfully enhanced organisational practices among previously underserved CSOs. Particularly among CSOs that participated in the mentorship programme or accessed the Ask an Expert service, where support was more tailored and hands-on. More specifically, it found the RSH made significant progress towards each of the three primary outcomes of improved dialogue, capacity and evidence. However, less-resourced CSOs still face structural barriers to connecting with safeguarding networks, sustaining internal changes, and accessing evidence. Three key findings were highlighted within this:

Key Finding 1: Across most regions, the RSH was successful in fostering dialogue around the issue of SEAH and contributing to changes in organisational culture to mainstream protection against SEAH.

The evaluation confirmed RSH users saw noticeable changes in how safeguarding and SEAH were understood and integrated into organisational culture and processes. In the MENA region, for example, respondents noted that safeguarding responsibilities were no longer siloed within specific departments or individuals but were becoming shared across the entire organisation. In Nigeria, organisations described a shift from safeguarding being the responsibility of a few individuals to a more embedded, organisation-wide approach. In some contexts, particularly where the mentorship programme was implemented, CSOs were able to build valuable peer connections. For example, in Bangladesh, RSH-supported activities helped facilitate stronger intra-CSO communication through informal networking. However, some CSOs across regions reported a disconnect between these smaller networks and formal global or regional safeguarding bodies, pointing to structural challenges, such as lack of funding, limited visibility, or exclusionary governance structures of existing networks.

Key Finding 2: Many CSOs now demonstrate improved organisational capacity to safeguard against SEAH and have noticeably contributed to greater awareness of SEAH in the environment in which they are operating.

Findings highlighted the clear and meaningful improvements in capacity among CSOs with many demonstrating stronger institutional safeguarding systems, enhanced staff awareness, and more structured approaches to prevention and response, marking a significant step forward in their ability to address SEAH effectively and sustainably within their organisations and communities. However, while RSH has improved CSO capability, translating knowledge into practice remained uneven, particularly in environments where safeguarding is still viewed as external or unfamiliar.

Key Finding 3: The RSH Global Hub has made significant progress towards producing evidence and learning related to SEAH in the aid-sector, however, there is further scope to improve the national or regional contextualisation of this evidence base.

The Evaluation found that the RSH made valuable contributions to the global and regional evidence base, with evidence outputs developed in collaboration with National and Regional Hubs. It found strong evidence of RSH investing significant resources into producing localised evidence pieces, shared via the Global Hub and with national CSOs. However, some feedback indicated that, the evidence-based tools were sometimes difficult to use or insufficiently localised. Continued effectiveness and equity of support depends on deep(er) contextualisation, broader translation, and targeted dissemination to ensure evidence reaches and serves its key audience of less-resourced organisations.

The evidence demonstrates that RSH succeeded in building capability of organisations in the sector, particularly CSOs, to safeguard against SEAH as well as helping them change and improve organisational culture and practices. The approach (logic, evidence and assumptions) to achieving outcomes and impact were found to be valid. Further assessment of the programme’s overall sustainability is provided against Output 4.

Value for Money:
The Alinea Evaluation found the RSH demonstrated good VfM overall, marked by efficient resource utilization, high budget execution rates, the capacity to adapt to challenges, and a strong commitment to equity. High VfM was achieved through efficient delivery, broad reach, and effective mentorship-based models, particularly where senior leadership drove organisation-wide cultural change. In particular, the Evaluation highlighted the programme demonstrated highly effective and intentional integration of gender, equity, disability, and social inclusion (GEDSI) considerations into both its design and implementation, achieving meaningful reach to marginalised populations while adapting to diverse contextual challenges across regions and contributed meaningfully to sector evidence. Further analysis is provided in section D.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
A Monitoring Plan was developed during inception phase in 2020 through a process of internal consultation. This described the theory of change (ToC), outcomes and indicators, adapted from the Business Case ToC (Annex A). The ToC was designed not as a theory of how the RSH programme would be implemented but a theory of how the programme would instigate and contribute to a series of changes. Therefore, the ToC does not focus on activities and processes of delivery, but rather on the change pathways upon which the programme is based. In addition, all elements of the ToC and each of the pathways were created to be relevant to the work of RSH at country, regional and global levels. Recognising the RSH programme would not have direct control over whether outcome level changes are achieved – underpinning assumptions were set out in the Plan, including that donors and well-resourced INGOs are able to independently apply knowledge from RSH to improve collaboration with less-resourced CSOs, while senior staff engaging with RSH are positioned to drive internal organisational change. Additionally, that sector networks will seek become more inclusive SEAH dialogue spaces, with flexible research agendas to address evidence gaps, and public sharing of new evidence which is generated.

RSH developed a supporting inclusion-focused Ethical Framework covering the vision, approach, values and principles which describe how the RSH put values into practice including driving delivery of the ToC. The reflects the programmes strong GEDSI consideration and integration, discussed further in the Equity of section D.

The ToC remained largely valid, but with some tweaks to the outputs and outcomes at the end of inception, as Phase 2 began in 2021 (see final ToC visual below). These changes were to reflect learning to date, placing greater emphasis on less-resourced CSOs and delivery focused through the national hubs and changes in environment. The impact and overall objectives of the programme remained the same. Specific updates were:
- Updated wording in the problem statements to flag the importance of contextual guidance and evidence.
- A new output on stakeholder engagement to highlight its importance in creating an environment that enables conversation and action on safeguarding amongst less-resourced CSOs.
- Updating the outcome on capacity to recognise the need for political will and support from partners to create an environment in which less-resourced organisations can improve their safeguarding practice.
- The intermediate outcome and outcome on evidence were changed to reflect the challenges in engaging with international evidence, partly due to the COVID-19 pandemic, and the pivot towards delivering and disseminating contextualised evidence that amplifies the voices of less-resourced CSOs.
The Logframe was significantly updated through a process of stakeholder consultation, following approval for phase 2 of RSH from December 2021 and recognising the changing priorities, summarised as maximising impacts from phase 1, pivoting focus to national hubs, expanding and deepening the user base and strategic partners. Reflecting this, key changes to the logframe were:
- The Impact and Outcome 1(b) to only be reported on at the end of the programme, recognising a need to not ‘over-survey’ users, and preserve translation budgets. Instead, other indicators across outputs and outcomes were given indications of progress towards these indicators (outcomes 1(a), 2(a), outputs 1.1(a), 2.2, 3.3).
- Some indicators reduced in comparison to the baseline figure, in particular the impact milestone for 2024, recognising the expansion of RSH into some difficult contexts, creating challenges with engaging organisations and users and providing direct support due to physical/connectivity access issues and active conflicts (e.g. Syria and Yemen).
- Indicators related to the sustainability of the programme were added, recognising the importance of this for phase 2 in order to ascertain the long-term impact of RSH or alternative models for maintaining the support. These are reflected in outcome 2(b) and a new output 4.

Other changes in 2023:
- Output 2 updated to increase targets (given they were consistently being exceeded), to move resources produced to 3 and to add monitoring of communication strategies.
- Output 3 indicators were updated to capture the building of a database of verified local safeguarding consultants and indicator 3.3 was adjusted to include a review of a sample of RSH products and to measure user satisfaction.

## C: Detailed Output Assessment

Output Number and Title	RSH hubs facilitate dialogue and knowledge sharing with a diverse range of stakeholders and strategic partners
Output Score	A+
Impact weighting (%)	20%		Impact weighting revised since last AR?	n/a

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1.1a: Number and types of peer-to-peer learning and exchange sessions hosted by RSH with an engaged group of users / 1.1b: Evidence that users in these spaces feel able to share openly		Output developed for ‘phase 2’ starting in AR 2023 / 1.1a: 67 / 1.1b: Examples from sessions and positive poll results	1.1a 220 (disaggregated by type) / 1.1b Examples from sessions and positive poll results	1.1a: 1,024 peer-to-peer national expert board meetings, roundtables, WhatsApp group communities of practice, webinars, mentor supervision sessions and trainings/ other events / 1.1b: Based on evaluation poll results of 8 webinars, 83% of all respondents (417/503) felt comfortable sharing thoughts and questions during the Q&A sessions / Exceeded target
1.2: Number and quality of strategic partnerships (with aligned/ complementary values, vision and mission)		1.2: 10 (quality of partnership demonstrated through reach, uptake and sustainability)	1.2: 55 / (quality of partnership demonstrated through reach, uptake and sustainability)	1.2: 77 / Exceeded target
Nigeria Hub: / a. Number and types of peer-to-peer learning and exchange sessions hosted by RSH with an engaged group of users / b. Evidence that users in these spaces feel able to share openly		Q1: / 2 / At least 70%	Q5: / 24 / At least 70%	36 / 92% / Exceeded target
Nigeria Hub: / Number and quality of strategic partnerships (with aligned/ complementary values, vision and mission).		Q2: 3	Q5: 6	7 / Exceeded target

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
The output was brought in as a key metric for ‘phase 2’ of the programme, as it moved to implementation and the Hubs ‘going live’. Across the lifetime of the programme the target was consistently met or exceeded. Before this metric was introduced, output 1 included indicators around the procurement process and initial programme activities. It was later revised to include indicators on user numbers and consultants. Following the RSH Annual Review 2022, it was agreed that RSH would continue to monitor the number of users, but would also monitor the dialogue between partners, engagement across countries, how people were using the resources and if they find them useful. As a result, output 1 indicators were revised to capture peer to peer learning and exchange sessions and strategic partnerships; the indicators on user numbers and consultants were moved to output 2.

Overall, the programme was found to have been successful in fostering dialogue around the issue of SEAH, contributing to changes in organisational culture to mainstream and protect against SEAH (Alinea Evaluation 2025). The programme supported sector-wide coordination both at national level in convening the range of key sector stakeholders on PSEAH and internationally through knowledge-sharing, coordination and their leadership in coordination and hosting of CAPSEAH.

1.1a: Number and types of peer-to-peer learning and exchange sessions hosted by RSH with an engaged group of users
RSH exceeded the first indicator of this output. The global programme achieved 1,024 peer-to-peer learning and exchange sessions, including 3 national expert board meetings, 7 roundtables, 6 WhatsApp group communities of practice, 9 webinars, 459 mentor supervision sessions and 46 trainings/ other events, against a final logframe target of 220. The stand-alone RSH Nigeria Hub achieved 36 peer-to-peer learning and exchange sessions against a final logframe target of 24.

1.1b: Evidence that users in these spaces feel able to share openly
Peer-to-peer learning contributed to improved accountability practices, organisational learning and provided the opportunity for users to engage and share knowledge. For example, in July 2023 the Bangladesh Hub hosted a webinar on Safer Programme: what works in emergencies. The 2024 Annual User Survey found 81% of NGOs/CSO respondents agreed or strongly agreed that “[the] RSH has supported improved collaboration and opportunities to share experiences among organisations in the aid sector”. 80% of attendees from local CSOs responded positively, indicating strong demand for information and learning, and an appetite to engage openly with other users.

The Alinea Evaluation found that many CSOs reported peer-to-peer learning provided them with trusted spaces to exchange good practice with peers, troubleshoot challenges and refine safeguarding implementation approaches. In Ethiopia, peer learning was central to the mentorship scheme, with cohort members engaging in multiple rounds of group learning, role-play exercises, and ongoing mutual support. RSH Nigeria demonstrated sustained peer learning, both through the mentorship structures and the ongoing role of the National Expert Board (NEB) actors. For example, the NEB supported RSH Nigeria to sign an MoU with the Nigerian Police force to weave in safeguarding training to ensure officers were aware of SEAH, how to protect people from harms and abuses and the role they could and should play in supporting people and other organisation partners. The NEB also continued to convene review meetings and serve as peer resource persons even after the formal mentoring concluded.

There is evidence that RSH successfully fostered both formal and informal peer learning networks. However, the strength, sustainability, and degree of formalisation of these networks varied across regions and were often reliant on facilitation by RSH. The Alinea Evaluation noted that peer learning promoted adaptive learning cultures in some settings (e.g. Nigeria, Ethiopia), while in others (e.g. South Asia), network durability was more fragile and vulnerable to staff turnover and resource constraints. In MENA, ongoing political instability limited the opportunity for sustained peer collaboration, particularly across borders.

1.2: Number and quality of strategic partnerships (with aligned/ complementary values, vision and mission)
The programme exceeded the milestone for the second indicator by 40%, achieving 77 strategic partnerships. The Nigeria Hub achieved 7 strategic partnerships against a final logframe target of 6. These strategic partnerships were formed to help organisations build connections, share learning, raise awareness and contribute to collective knowledge.

This reflects the RSH’s sustained effort to build partnerships with a diverse range of partners. For example, RSH Bangladesh Hub participated in monthly calls with the Bangladesh PSEA network, which provided an opportunity to complement each other’s efforts to enhance safeguarding efforts within the sector. The issues of child safeguarding, mainstreaming safeguarding into recruitment processes and disability inclusion were identified as areas where the PSEA network would seek support from RSH.

RSH is now well-established in the international sector, collaborating closely with strategic partners (such as sitting on numerous key sectoral steering committees and boards e.g. CHS Alliance, DEC Safeguarding Leads Group and Safeguarding Funders Collaborative) as a key voice in the dialogue space. For example, RSH have collaborated with CHS Alliance in their development of investigators training. This coordinated approach further improves support for the implementation of SEAH safeguarding practices in the sector, for example co-delivery of training with the DEC and CHS Alliance, and cross-communication of tools and resources. Due to this established presence as a well-respected platform, RSH was chosen to develop and host the consultation of the FCDO-coordinated international efforts to agree the first Common Approach to Protection from Sexual Exploitation, Abuse and Harassment (CAPSEAH) for humanitarian, development and peacekeeping work. The week following the launch of CAPSEAH, which included an event hosted and run by RSH, saw 582 users register for the RSH e-learning, demonstrating the value of having the RSH platform and brand strongly linked to this best practice, global framework.

Although RSH helped to build partnerships, especially peer connections and strategic links at global level, the Alinea Evaluation noted that some less-resourced CSOs still faced barriers to joining wider safeguarding networks and reported a disconnect between smaller, informal networks and formal global or regional safeguarding bodies. For example, a CSO representative from Syria noted the lack of opportunities to engage with international bodies. Alinea found barriers highlighted were in relation to broader structural challenges such as lack of funding on PSEAH, limited visibility and some exclusionary governance structures of broader existing networks and coordination spaces. This suggests that strategic partners may still operate at a high-level and out of the reach of smaller CSOs in the sector. Though these are structural issues, and therefore not directly for RSH to resolve, it indicates that further efforts and lobbying could support to link national CSOs better to international networks.

The Alinea Evaluation also found the RSH’s core mandate of capacity-building for smaller CSOs ‘often placed it one level removed from national or donor governance structures where formal sector alignment typically occurs. This limited its visibility and participation in cross-agency or government-led safeguarding reforms.’ RSH was ‘often disconnected from national safeguarding policy development and donor-led safeguarding frameworks’. This was noted across national hub settings which Alinea interviewed.

Engagement with governments was noted as a continued challenge across the programme lifetime and RSH regularly assessed options to engage with governments more closely to support to increase impact through creating a more enabling environment for CSOs (and noted in AR 2023 and 2024). RSH worked to engage strategically where appropriate, to raise the voices of CSOs and the importance of PSEA in the workplace. For example, RSH engaged in Bangladesh with the government department responsible for CSO registrations, as CSOs were required to submit evidence of safeguarding policies. In other cases, RSH chose to operate in more discrete, indirect way due to topic sensitivity. The aims of local ownership has also been to further this, and facilitate national acceptance and accessibility by government, donors and less-resourced CSOs and to contribute to further extend safeguarding practices in countries, beyond the funding lifecycle of the programme.

Lessons learned through this output, and recommendations for future programming
- A key learning is the value of in-person peer to peer learning. As noted in AR 2024, stakeholder feedback suggests that some regions prefer face-to-face contact because it helps to build trust, facilitate dialogue and encourage close connections. It can also encourage take-up of the online RSH resources and materials.
- Further engagement with national governments could increase the impact of RSH initiatives, by creating an enabling environment for CSOs.

The Alinea independent evaluation recommended:
- Peer learning networks can drive meaningful organisational change and foster knowledge sharing. However, their long-term success and sustainability relies on consistent facilitation, clear governance, and integration into institutional practices. Without ongoing support, these networks can dissolve when key champions move on. Future programmes should therefore consider including peer learning components with explicit governance structures, succession planning, and graduated facilitation withdrawal.
- Systematically support CSO network engagement. Future programming could provide small grants to support CSO participation in formal networks, deliver targeted training on network engagement strategies, facilitate direct introductions to key coordination mechanisms, advocate on behalf of CSOs for network inclusion, and track network participation as a key programme outcome indicator.
- Expand RSH networks through strategic partnerships. Future programming could consider establishing formal partnerships with local think tanks and research institutions for evidence contextualisation, seek strategic alignment with UN bodies and international PSEAH networks to increase CSO visibility, create collective advocacy platforms that amplify smaller CSO perspectives in global safeguarding discourse, and ensure evidence generated through RSH translates into policy action at national and international levels.

Output Number and Title	The RSH online hubs are regarded as a 'go to', quality resource for the sector providing positive user experience, and expanding the user base to new geographies and languages
Output Score	A+
Impact weighting (%)	25%		Impact weighting revised since last AR?		No

Output Indicator		Starting Target		Final Logframe Target	Final Result Achieved
National and Global online hubs operating and being used regularly. / 2.1a: Number of visitors accessing RSH online hubs. / Definition: Cumulative number of unique visitors to the RSH website. / 2.1b: Number of hub visitors from identified priority countries, based in hub countries		Initial milestone for phase 1: 125,000 visitors. / Output developed for ‘phase 2’ in AR 2023: / 2.1a 260,000 / 2.1b 65,000		2.1a 1,000,000 / 2.1b 300,000	2.1a 1,102,152 / 2.1b 408,998 (with visitors from Ethiopia being the highest) / Exceeded target
2.2: Evidence of RSH user level of satisfaction with the online hubs' usability and ease of access to relevant content.		2022 AR: Evidence of feedback provided to RSH, and action plan in place for implementing recommendations		Evidence feedback provided to RSH, and action plan in place for implementing recommendations	Positive evidence from feedback on usability of the website via pop-up questions on the website, interviews and user surveys / Exceeded target
2.3: Evidence that the communications strategies are in place and informed by ongoing internal learning and reflection.		Evidence that the communications strategy is monitored and updated at regular 6-month intervals based on learning and exchange across the programme		Evidence that the communications strategy is monitored and updated at regular 6-month intervals based on learning and exchange across the programme.	Global communications strategy and regional comms strategies developed and implemented aligned with safeguarding goals, reviewed every 6 months to integrate learning / Target met
Nigeria Hub: Hub operating and being used regularly. / a. Number of visitors accessing RSH Nigeria / b. Number of hub visitors from Nigeria		Q1: / 1,000 / At least 40%		Q5: / 11,000 / At least 40%	17,395 / 51% / Exceeded target
Evidence of RSH user level of satisfaction with the online hubs' usability and ease of access to relevant content.		Q2: 70% (from pop-ups) rate 4 or 5 out of 5, supported by spontaneous qualitative feedback​		Q5: 70% (from pop-ups) rate 4 or 5 out of 5, supported by spontaneous qualitative feedback​	90% (4.5/5) positive response for ease of access – 135 responses. / Exceeded target
Evidence that the communications strategies are in place and informed by ongoing internal learning and reflection.		Q1: Evidence that the communications strategy is monitored and updated at regular 6-month intervals based on learning and exchange across the programme.		Q5: Evidence that the communications strategy is monitored and updated at regular 6-month intervals based on learning and exchange across the programme.	Communications Strategy developed and implemented aligned with safeguarding goals, reviewed every 6 months to integrate learning. Target met

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
As the programme developed, the RSH successfully secured itself as a 'go to', quality resource for the sector. Evidence gathered across ARs and Annual User Surveys provided extensive positive user experiences, as noted below. The reputation built up by RSH at international level saw the programme expand the user base to new geographies and languages. Two web-only ‘language hubs’ were also created gathering translated French and Swahili resources. An Eastern European Hub was funded separately by the Disasters Emergency Committee (DEC) from April 2022-October 2023, in response to the war in Ukraine. The DEC also provided separate funding to create a specific resource to respond to the Türkiye-Syria earthquake. The Nigeria and Ethiopia hubs both secured additional funding from FCDO posts in late 2023 to continue operations alongside undertaking pilot approaches of a national partner CSO in each country taking over to lead national hub operations, supported by the global platform, in an affiliate model.

The early stages of the programme encountered challenges reaching the target audience of less-resourced CSOs, with concerns the online resources might exclude very small and rural organisations who don’t have online access. Recognising this, a new consortium partner was identified – the International Council of Voluntary Agencies (ICVA) – with particular expertise and ability to reach out across organisations in the Global South. Three new regional communications roles were implemented to improve outreach and increase visitors to the hubs. Other outreach actions included national radio adverts (Nigeria), providing more physical resources, and creating communities of practice on WhatsApp.

2.1a Number of visitors accessing RSH online hubs. Definition: Cumulative number of unique visitors to the RSH website. 2.1b Number of hub visitors from identified priority countries, based in hub countries
RSH met or exceeded all the targets for this output over the lifecycle of the programme. For the global programme, 1,102,152 (as of April 2025) overall visitors accessed RSH online hubs against a target of 1,000,000. The programme has met its target of reaching priority countries with the Ethiopia hub having the highest number of visitors, followed by Nigeria as well as visitors from MENA and South Asia. For the stand-alone RSH Nigeria Hub, 17,395 visitors accessed the Nigeria Hub against a final logframe target of 11,000. 51% of the visitors to the Nigeria online Hub were from Nigeria. This exceeds the final logframe target of 41%.

2.2 Evidence of RSH user level of satisfaction with the online hubs' usability and ease of access to relevant content
Feedback on the use of the global online hubs' usability and ease of access to relevant content has been positive overall. For example, from December 2022 to mid-October 2023, pop-up questions on the RSH website asked whether the RSH met user needs, scoring 4.39 out of a possible 5 from over 900 responses, and how useful users found the library, scoring 4.68 out of 5 from 41 responses. Pop-up questions from mid-October 2023 to December 2024 asked whether users were satisfied with the RSH website, scoring 4.42 out of 5 (210 responses), and how easy the website was to use, scoring 4.20 out of 5 (128 responses).

For RSH Nigeria Hub, users scored a strong 4.5 out of 5 against a pop-up question on ease of access (90% positive responses). This is against a final logframe target of 70% positive responses. The Hub made continuous improvements to the site based on user feedback related to usability and ease of access including the resolution of module access issues.

Although many users indicated that the online hubs were easy to navigate with good access to translated, relevant and country specific resources, some user feedback highlighted that searching for relevant content was challenging due to the large number of resources. Also, some users noted challenges accessing content due to poor internet connectivity. The Alinea Evaluation also found that while digital platforms successfully extended global access, connectivity challenges created participation barriers at sub-national levels. Blended approaches with substantial face-to-face components were consistently preferred for deeper engagement and sustainable learning outcomes. Additionally, platform diversity successfully extended reach but required sustained technical support for effective utilisation. The multiplicity of engagement modalities represented a strategic strength, but implementation revealed the importance of ongoing user support for meaningful engagement with digital resources.

Based on user feedback, RSH conducted continuous improvements such as website usability adjustments and exploring agile and creative ways to make content more accessible. For example, strengthened guided web search functions and a ‘Progressive Web App’, a version of site where users can download materials offline. RSH also developed ‘Impact Stories’ case studies, an updated global Hub menu and more interactive content like quizzes and games – see for example, Safeguarding Challenge.

As noted above, RSH also expanded its user base to new geographies and languages. For example, the Eastern European RSH Hub operated under the RSH framework and implementing the same activities as the other RSH Hubs but was funded by the DEC. The Hub operated from April 2022 to October 2023, with 3 national Hubs in Moldova, Poland, and Romania. DEC also funded the Turkey-Syria Earthquake Appeal hub, which was a short, 6-month operation in 2023.

RSH has provided a wide range of resources that were easily accessible to users and free to download in over 10 languages, applicable in settings in the development and humanitarian sectors. The Alinea Evaluation noted that the commitment to language accessibility was widely seen as a significant strength of the RSH model. Translation into national languages was frequently cited as a crucial enabler of effective use and understanding of safeguarding materials.

2.3 Evidence that communications strategies are in place and informed by ongoing internal learning and reflection
Communications strategies were put in place and informed by ongoing internal learning and reflection for MENA, Africa and South Asia. These strategies were based on the Global strategy but adapted based on validation workshops with respective regional hub teams and internal lessons sharing by the Global Communications Team. The comms strategies were updated regularly to reflect learning, and the Global Communications Teams oversaw all the regional digital activities with direct access to all relevant data to inform strategy. The process was supported by consortium partner, ICVA, with their extensive networks across the Global South.

For the RSH Nigeria Hub, a communications strategy was developed, implemented and reviewed regularly to incorporate feedback from webinars, training sessions, community of practice deep dive sessions and targeted email responses to refine topics, formats, and outreaches, and inform key messaging. Nigeria Hub resources were adapted for accessibility (translated contextualised resources to local languages - Hausa, Igbo and Yoruba) and refined webinar topics based on engagement trends. On performance tracking, metrics like newsletter open rates and webinar registration demonstrated improved alignment with audience needs. Webinar attendance steadily increased from 37% to 57% (a 54% increase) while newsletter subscribers have steadily increased from 1,540 to 3,063 (a 50.3% increase).

Lessons learned through this output, and recommendations for future programming
- Future RSH programming should review and refresh the web platforms to ensure they are curated in the best way possible to support finding relevant documentation, including recommending similar documents. A simplified and intuitive resource organisation system can improve accessibility, with continuous platform improvements informed by quarterly user feedback surveys.
- Data could be further disaggregated to identify types of organisations accessing online hubs/materials. This disaggregation, integrated into routine monitoring processes and reported on regularly, can support to inform programme design and outreach strategies.

The Alinea Evaluation recommended:
- Invest in comprehensive digital platform support to enhance user engagement and effectiveness. Future RSH programmes should consider providing platform navigation training with a focus on mentees, mentors, and consultants. This could also be complemented with a dedicated helpdesk services that include local language support, and user experience testing with participants of varying levels of technical literacy.
- Stakeholder feedback suggests that some regions prefer face-to-face training. Future programming should continue to invest in hybrid in-person and digital delivery models. These should balance digital scalability with relationship-building potential i.e. with quarterly in-person workshops and mentoring sessions, annual peer exchange events and opportunities for network formation and collective problem-solving. Face-to-face engagement should be a priority for less-resourced organisations in contexts with limited digital access.
- Design infrastructure-responsive blended learning approaches to ensure equitable access and engagement. Connectivity assessments should be included within all Country Assessments. Downloadable offline content packages are key to accommodate users with limited internet access, and future programming should promote these offers more strongly. To enhance inclusivity, future programming could collaborate with communications experts from the ‘Global South’ to identify more accessible outreach strategies, leveraging alternative media platforms, engaging with existing local networks and organisations (such as women’s rights organisations), and supporting the development of communities of practice, as demonstrated through successes in RSH Nigeria.

Output Number and Title	RSH users have increased access to SEAH-related, contextualised resources, guidance and services (including blended learning)
Output Score	A++
Impact weighting (%)	40%	Impact weighting revised since last AR?	n/a

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
3.1 Number of primary products produced by RSH (translated, contextualised, and total overall products not including translations) disaggregated by type and hub country.	Baseline (end of phase 1): 159 primary products / Starting target November 2022: 209 primary products	November 2024: 390 primary products	November 2024: 453 primary products / Exceeded target
3.2 Number of RSH users engaging with RSH developed and published primary products and tailored services / 3.2a Number of (cumulative) times RSH primary products are downloaded from the online hub / 3.2b Number of (cumulative) users attending RSH-hosted events / 3.2c Number of (cumulative) learners who have completed at least one module of e-learning / 3.2d Number of RSH users accessing RSH specialised or tailored support via the global or national hubs	Phase 1: / a) 6,000 / b)2,450 / c) 588 (added end of phase 1) / d) 137 / Starting target November 2022: / a) 40,000 b) 2,915 c) 700 d) 217	November 2024: / a) 270,000 b) 10,400 c) 9,000 d) 3,475	November 2024: / a) 286,047 / b) 11,670 / c) 11,189 / d) 3,913 / Exceeded target
3.3 Evidence that primary products are relevant to the target audience, provide practical guidance for end-users and are contextualised to the needs of less-resourced civil society organisations.	Evidence of high RSH user satisfaction and positive feedback on the practicality, relevance and contextualisation of primary products, alongside positive interviewee feedback from survey and interview respondents.	a) FCDO review sample of primary products to assess they meet standard based on; clear communication, contextualisation, technical accuracy and; accessibility. / b) 70% of surveyed users report that they find RSH products very or extremely relevant. / c) 70% find them very or extremely user friendly. / d) 70% of e-learners find e-learning modules extremely or very relevant. / e) 70% of e-learners find e-learning modules extremely or very user friendly.	a) RSH products assessed – met high standard based on all criteria. / b) 79% / c) 80% / d) 90% / e) 88% / Significantly exceeded target
3.4 Database of quality-assured local and/or regional safeguarding consultants from developing countries updated at the national hub level and accessible to users	Baseline (end of phase I): / 26 quality assured local and / or regional SPs from developing countries in place by end Nov / November 2022: 40 quality assured local and regional service providers (cumulative)	75 quality assured local and regional service providers (cumulative)	92 / Exceeded target
N3.1 Nigeria Hub: / Number of primary products produced by RSH	Q1: 1 product	Q5: 8 products	36 products; 5 how to notes, 1 template, 1 bitesize, 11 blogs, 5 podcasts, 2 infographics, 4 impact stories, 7 webinars. / Significantly exceeded target
N3.2 Nigeria Hub: Number of RSH users engaging with primary products and tailored services / N3.2a Number of (cumulative) times RSH primary products are downloaded from the online hub / N3.2b. Number of (cumulative) users attending RSH-hosted events / N3.2c. Number of (cumulative) learners who have completed at least one module of e-learning / N3.2d. Number of users accessing RSH specialised or tailored support	Q1: / 150 / 88 / 10 / 0 (47 for Q2)	Q5: / 2,250 / 622 / 140 / 170	5,817 / 1,198 / 1,125 / 555 / Significantly exceeded target
Nigeria Hub: Evidence that primary products are relevant to the target audience, provide practical guidance for end-users and are contextualised to the needs of less-resourced CSOs	70% of surveyed users report that they find RSH products very or extremely relevant. / 70% find RSH products very or extremely user friendly. / 70% of e-learners find e-learning modules extremely or very relevant. / 70% of e-learners find e-learning modules have increased their capability to Safeguard against SEAH	No change from starting	91.4% / 82.9% / 90% (97 out of 108 responses) / 95% (103 out of 108 responses) / Significantly exceeded target
Nigeria Hub: Database of quality assured local and/or regional consultants updated at national hub level and accessible to users	Q1: 14	Q5: 16	20 (1 organisation and 19 consultants) / Exceeded target

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
The programme has exceeded all of its targets for this indicator, with access to SEAH-related, contextualised resources, guidance and services (including blended learning) at the core of what the programme has delivered. All products produced by RSH over the years were demand-driven, informed by user requests and need. The inception phase of the programme did not anticipate the level of need for primary produced products and tools, with the initial aim to primarily gather existing resources. However, as the inception phase concluded, evidence demonstrated the need to create a range of sector-wide and contextualised products as well as simplified and concise resources.

This indicator was therefore developed as part of ‘phase 2’ implementation stage in 2021. In phase 2, focus moved to the opening of the national and regional hubs and delivery, away from global hub level. This enabled more contextualised products to be produced which suited specific local contexts, languages and direct support services e.g. mentorship schemes. COVID-19 impacted the programme timelines including country assessments and therefore launches were delayed in Nigeria and South Sudan hubs. The other hubs were impacted due to safety concerns during the pandemic, which meant delivery was largely moved to online-only during 2020-2021.

The MENA hubs began in 2021, with the platform launching in January 2022 after country assessments for Jordan, Syria and Yemen were completed. This allowed for synergies between the regions to be assessed – leading to the decision to host a single platform hub rather than three separate ones for this region. This was largely due to both the regional development and humanitarian approach in MENA and the unifying Arabic language, unlike other regional hub countries. This regional focus provided a strong opportunity to reach a wider audience and created good economies of scale.

Over the lifetime, RSH has produced a broad range of primary products, both for global, broad use and specific contextualisation. This included translations, webinars, blogs, infographics and tip-sheets. The hub has greatly exceeded the target for users engaging with primary products, demonstrating their value. At the FCDO hosted Wilton Park CAPSEAH Dialogue Event held in April 2025, RSH was recognised as part of the key global tools and initiatives that are effective and essential to the PSEAH architecture.
[note] Stakeholders from across the HDP sectors (e.g. UN, IFI, NGO, governments, victim/survivor representatives) met to discuss the impact of the ODA landscape on PSEAH resourcing, and the needs and challenges at global, country and organisational levels.

The independent Alinea Evaluation found that the RSH National and Regional Hubs significantly contributed to less-resourced CSOs in-country having access to SEAH-related, contextualised resources, guidance and services. The evaluation confirmed that over its lifetime, RSH undertook significant work to contextualise tools and resources across all regions. More specifically, the Evaluation found that translation of RSH tools and resources a significant contributing factor to contextualisation, though with areas for improvement for future programming (noted below).

3.1 Number of primary products produced by RSH (translated, contextualised, and total overall products not including translations) disaggregated by type and hub country
The programme exceeded this final logframe output, with 453 final products produced as of November 2024. This broke down as; Global: 137, Africa: 4, Bangladesh: 30, Ethiopia: 48, MENA: 52, Nigeria: 94, Pakistan: 20, South Sudan: 43, Syria: 6, Swahili Hub: 2, French Hub: 10, Jordan Hub: 5 and Yemen Hub: 2. Disaggregation shows that there has been a good diversity of resources produced from different hubs, though some later-opened hubs produced less ‘new’ primary products, instead focusing on translation of existing resources into relevant languages (AR 2023). In producing sector-specific guidance, RSH made steps to improve engagement with PSEAH practices. Stakeholder interviews for this PCR highlighted that this was particularly important in areas with less PSEAH attention historically (e.g. creating specific guidance on PSEAH for agriculture and defence), where limited resources existed prior to that.

3.2 Number of RSH users engaging with RSH developed and published primary products and tailored services
Targets were exceeded across all sub-targets for this output. RSH saw a consistent and high level of downloads of products from the online platforms. Tailored webinars proved to be a popular offer across regions, providing a strong platform for users across national and regional settings to engage with one another, as well as bringing in national and international expertise. This became a key offer in the aftermath of COVID-19 when a pivot to virtual offers became more commonplace. Global level webinars and events were well attended, and RSH established itself as a strong community of practice in the international landscape, regularly convening a broad range of users, wider than the target of CSOs including donors, networks, the UN and large INGOs (Alinea Evaluation, AR 2024). This platform enabled a critical link between the broader international sector and national/smaller CSOs.

The e-learning modules grew in popularity over the lifetime with over 11,000 users completing at least one module in the final logframe record. This was one of the key offers translated into more than 8 languages, providing a free, accessible basic training for users across the sector on SEAH safeguarding. In autumn 2023 a ‘Safeguarding Challenge’ interactive e-learning was also launched and rolled out, providing a ‘gamified’ version, in response to user feedback for a more interactive learning offer. RSH Global Hub also successfully worked with 10 international NGOs seeking to include core safeguarding against SEAH training across their organisation, to develop an MOU to integrate the RSH Safeguarding Matters course into their own internal learning management systems.

The Ask an Expert service received mixed uptake over the programme lifetime, this was noted in AR 2021 and an average of just 54% of respondents to the 2024 Annual User Survey confirming they were aware of it (57% Nigeria, 54% Pakistan and 50% Bangladesh). The level of need still appeared to be consistent in user testing, with those who had used the service providing positive feedback (including that the support was timely, focused and flexible) and those who had not used it, largely sighting lack of awareness rather than not relevant (just 13%). This suggests that further outreach by the National Hubs may have been required to improve awareness of the service.

Mentorship schemes ran across all national hubs, providing more in-depth support to organisations. Over the lifetime 255 organisations took part in mentorship (Nigeria, 64, Ethiopia 17, South Sudan, 40, Jordan, 20, Syria, 50, Yemen, 25, Pakistan, 20 and Bangladesh, 19). In Syria, bespoke investigations training was provided, co-funded with the Disasters Emergency Committee. The mentorship offers within the programme hubs contributed a critical role in contextualising learning and resources to local realities. This additional layer of contextualisation, delivered through direct, person-to-person engagement, was often what made the tools and training materials most relevant and actionable. Alinea’s Evaluation findings highlighted the unique strength of the mentorship model: the ability to embed safeguarding guidance within the local linguistic, cultural, and operational contexts of participating organisations. Whilst requiring the highest staff-time investment, this proved to be one of the most popular offers, with demand outstripping capacity. The RSH Final 5 Year Results Report shared that interviews with mentors and mentee organisations found that participants praised its structured, hands-on approach and the accessibility of tools like Complaint Response Mechanisms (CRMs) and risk assessment templates, which enhanced their understanding of safeguarding and compliance standards. However, some mentees highlighted challenges such as language barriers and limited internet access, suggesting more in-person sessions and tailored materials in native languages like Bangla and Urdu.
[note] Nigeria figures include the first phase of the hub under the full global contract, and the additional phase under the separate contract.

There is also critical evidence of a positive “ripple-effect” of RSH in galvanising wider PSEAH efforts and capability building beyond organisations directly involved. RSH staff noted in PCR interviews that those supported through the mentorship programme tended to stay well engaged with RSH and the PSEAH agenda afterwards. As part of its evidence and learning strand, RSH completed an Africa Legacy Study of the Africa RSH National Hubs (Ethiopia, South Sudan and Nigeria) to assess whether the impact and achievements had been sustained after closeout. The study found strong evidence that RSH users improved their knowledge, skills and practice on PSEAH. Each Hub ran at least two six-month mentoring programmes, mentoring 91 CSOs with 100% improvement of safeguarding capability. Training of RSH cohorts, particularly through the mentorship programme, led to this wider ‘ripple effect’, with organisations who were not directly engaged with the RSH Hub also benefiting (as demonstrated by their awareness and use of RSH materials).

CSOs provided evidence including safeguarding policies and practices being strengthened, CSOs cascading information to national sectors and communities, improved organisational cultures and mentees going on to provide consultancy to other CSOs. One mentee noted they had become the full-time Safeguarding Lead for their CSO, as a result of the RSH mentorship, leading work to embed safeguarding champions in each of the CSO’s 30+ programmes. This demonstrates the longer-term effects which RSH has, after support takes place. Evidence highlighted that engaging leadership early as part of the mentorship programme had been key to building a stronger culture of safeguarding in CSOs, as ‘bringing leadership on board’ enabled safeguarding focal points to take forwards more concerted work (Africa Legacy Study 2024).

3.3 Evidence that primary products are relevant to the target audience, provide practical guidance for end-users and are contextualised to the needs of less-resourced civil society organisations.
Over the lifetime, it was noted that there was scope to improve the quality of the drafts across products in a number of areas, to make drafts of future products as strong as possible. The 2023 AR highlighted this, noting that of FCDO’s review of a sample of primary products there was some variation in the quality with some lacking clear contextualisation, missing important information, or not clearly being relevant to the target audience. Feedback from end users from Yemen and Jordan stated that some materials were not well contextualised to the Arab context. Some other products struggled with translation, with some feedback highlighting they were not well translated into local nuances.

As part of monitoring this target, FCDO began to QA a sample of products during 2023 and 2024. These continued to improve over time, FCDO feel strongly that RSH products meet a high standard based on all criteria of clear communication, contextualisation, technical accuracy and accessibility.

The 2024 Annual User Survey highlighted the tools, templates, and examples provided were not only tailored to their national contexts but, in many cases, also adapted to their specific regions and target populations. This approach was particularly helpful for CSOs that were newer to safeguarding concepts, enabling them to better understand the materials and apply them meaningfully in their work. 82% of respondents across all regions in the 2024 Survey reported finding the RSH tools and resources to be either “Extremely relevant” or “Very relevant.”

For the final year target, 79% of survey respondents found RSH products very or extremely relevant (83.9% from NGOs/CSOs and OPDs, 91.4% for Nigeria, 88.6% for Bangladesh and 73.7% for Pakistan). 80% of survey respondents find RSH products to be extremely or very accessible and user friendly (79.5% for NGOs/CSOs and OPDs respondents, 82.9% among respondents for Nigeria, 79.5% for Bangladesh and 73% for Pakistan). The final two sub-targets were strongly exceeded with 90% of e-learners finding e-learning modules extremely or very relevant and 88% of e-learners finding the modules user friendly or very user friendly.

The Evaluation and ongoing data analysis by RSH (e.g. Annual User Survey) confirmed that the programme has attracted a wide range of users, beyond the target audiences of national and less-resourced CSOs, with a diverse user base across the sector (e.g. private sector orgs, INGOs, national and international institutions). Across regions, the commitment to language accessibility has been a significant strength of the RSH model with translation into national languages cited as a crucial enabler of effective use and understanding of safeguarding materials. Digital learning platforms developed also further extended the reach of the RSH (globally and nationally). In some regions, however, the effectiveness was also constrained by infrastructure and connectivity issues.

The RSH Country Assessments were instrumental in contextualising the priority SEAH challenges, identifying key networks and local actors, and determining the tools and resources needed in each country. The RSH programme grounded its model with a localised approach from the outset and the Alinea Evaluation found that national, regional, and global RSH staff reported that the Country Assessments were key in guiding programming. For example, early engagement at national level for the country assessments in the South Asia Hub ensured that CSOs felt engaged from the outset with a sense of co-ownership; “Not something outside. Something that’s ours.” The Alinea Evaluation noted that no follow-up Country Assessments were conducted during Hub cycles or after closure, meaning potential shifts in local operating contexts went unrecorded, which could have impacted delivery.

The 5 Year Result Report and Alinea Evaluation identified some wider areas for improvement. These include the need for more accurate and specialised language translations, greater opportunities for in-person engagement (particularly through national hubs) and a deeper understanding of local operating contexts in certain settings. In the MENA region, for example, mentees reported that early tools did not reflect the regional or cultural context well enough, but rather translated core/general tools (AR 2023). This highlighted the need to adapt guides, where possible, to local cultures in order to properly express certain terms etc. In relation to translations, the nuance and meaning of key safeguarding concepts were sometimes lost without deeper contextualisation. In addition, that some tools remained overly technical or “jargon heavy” making them difficult for those new to safeguarding to engage with effectively. Findings from the 2024 RSH Annual User Survey supported these reflections. Reflections on this point to the need for quality over quantity of resources, which should be reflected as part of future programming targets.

3.4 Database of quality-assured local and/or regional safeguarding consultants from developing countries updated at the national hub level and accessible to users
The programme exceeded expectations for the number of quality-assured Consultants (three stage QA), totalling 92 against a target of 75. The Alinea Evaluation found that the RSH worked in a way that prioritised national level expertise and worked with significant numbers of national consultants. The Year 5 Results Report found that of the 31 respondents from the 2024 Annual User Survey who confirmed they had worked with an RSH Safeguarding Consultant, 93% were satisfied or very satisfied with their support. Feedback requested better guiding assistance of the service, filtering options and possible review ratings, to support uptake. Anecdotal feedback shared as part of PCR interviews highlighted that another ‘ripple effect’ of the RSH has been through providing this platform for national and regional consultants has enabled greater growth and development to them, in engaging more deeply on safeguarding and moving into more SEAH safeguarding specific roles, rather than as within wider portfolios. The Africa Legacy Study by RSH, also found evidence of a sustained improvement in and expansion of locally available safeguarding expertise in the Hub countries, with a shift away from relying on international organisations/consultants for safeguarding expertise as well as demand from other sectors (e.g. protection and education) for safeguarding support.

Lessons learned through this output, and recommendations for future programming
- Engaging with key national actors and stakeholders from the outset was critical to building truly relevant contextualised resources and support including PSEAH networks, CSOs, local organisations and FCDO country offices.
- Greater focus on the make-up of the Consultants Directory could make this even more beneficial to target working with wider partners – targeted database of areas of gaps and needs. More advertising.
- Depth over breadth (quantity). Translating materials into relevant, contextualised ways requires careful, nuanced work. As such, future programming should recognise this, and the value that those products have once created, therefore considering prioritising a smaller but critical number of resources and tools over proliferation of quick / direct translations of core materials. Future programme monitoring approaches could reflect this with a focus on quality/depth and uptake rather than just quantity.

The Alinea Evaluation therefore recommended:
- These findings point to the critical importance of not only translating resources but also contextualising them for diverse linguistic, cultural, and operational environments. Without this, safeguarding materials risk remaining inaccessible to the less-resourced CSOs and communities they are intended to support.
- Comprehensive cultural context assessments are critical. Ideally, six-month pre-implementation to identify potential resistance to safeguarding concepts, engage traditional and religious leaders in programme design, map existing protective cultural practices to build upon, and develop culturally sensitive introduction strategies with extended timeframes for community acceptance.
- Establish participatory translation and adaptation processes.  RSH implementers could create regional working groups of CSO representatives to review materials through iterative cycles, invest in local subject matter experts who understand linguistic and cultural contexts rather than direct translation services, and consider allocating specific programme budgets for contextualisation activities including user feedback incorporation. Future programmes can explore opportunities to make resources more user-friendly and adapt the delivery modality to allow for greater in-person interactions.
- Implement systematic plain language approaches. Future RSH programmes could conduct user testing with safeguarding ‘novices’ to ensure they are user-friendly and contextualised well. Advice included developing illustrated glossaries with local examples, creating materials at various complexity levels and seek to address abstract policy language.

Output Number and Title	Measures in place to sustain RSH achievements at global and national level
Output Score	A
Impact weighting (%)	15%		Impact weighting revised since last AR?		n/a

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
4.1 Responsible exit strategies are identified for all national hubs and learning shared back for future hub exit strategies		Ethiopia Exit Strategy developed and implemented	Learning feedback from Africa exit into MENA and South Asia strategies / MENA and South Asia hubs exit strategies implemented.	All exit strategies developed. MENA exit strategy developed with learnings integrated from the Africa Hub closures. South Asia exit strategies developed, adapted based on lessons in the Africa Legacy paper. / Target met
4.2 Evidence of 'what works' (related to RSH activities) to strengthen organisational capacity to safeguard against SEAH is developed, consolidated and disseminated.		Published report on Africa Mentoring approach and lessons learnt	Five additional products published including MENA and South Asia, sustainability study for Africa and the Global Evidence Refresh	Five products completed. / Target met
Nigeria Hub: Responsible exit strategy in place and learning shared		Q2: Exit strategy developed	Q5: Exit strategy developed and implemented.	Exit strategy developed and implemented. / Target met
Nigeria Hub: Evidence of 'what works' (related to RSH activities) to strengthen organisational capacity to safeguard against SEAH is developed, consolidated and disseminated		Q5: 1 product developed and shared on what works to strengthen safeguarding capacity, based on RSH learning and research	Same as starting	3 products: 1 Bitesize Learning on organisational culture, shared via Hub, newsletter and a webinar. 1 learning brief and 1 infographic. / Target exceeded

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
This indicator was developed after the 2021 AR which highlighted the need for an indicator specifically relating to evidence produced through the programme, one of the three outcomes in the theory of change. The RSH changed its approach to the evidence pillar outcome to focus less on influencing existing research to include safeguarding elements and instead looking towards the national hubs to provide evidence on what works to improve capacity on SEAH safeguarding and how to make the programme sustainable in the longer term.

All targets have been consistently met for this output. Internal learning across the lifetime (Annual User Survey, Legacy Studies etc) backed up by findings from the Alinea Evaluation, found that the programme successfully strengthened the safeguarding capacity and capability of CSOs and organisations it supported, helping to generate strong local ownership. Alinea found that RSH contributed significantly to the institutionalisation of safeguarding practices and promoted peer learning within CSOs. Staggering the opening of the hubs enabled continuous learning to inform future cycles, which increased the chances of each hub cycle being stronger than the last.
Across all regions, Alinea Evaluation and survey evidence demonstrate that CSOs who engaged directly with RSH mentorship, training, or online learning platforms strengthened their internal safeguarding capacities. Those who took part in mentorship, continued to engage with RSH and their cohort, many establishing communities of practice (Pakistan, Nigeria etc) to stay engaged on the PSEAH agenda (as highlighted in Output 3 on the ‘ripple effect’). However, a key risk identified during the programme lifetime was the challenge of training single personnel within CSOs, given staff-turnover, impacting the retention of safeguarding capability within that organisation. Additionally, most CSOs lacked dedicated budget lines for safeguarding activities once RSH funding or project-based resources ended.

Evidence has highlighted that engaging leadership early as part of the mentorship programme had been key to building a stronger culture of safeguarding in CSOs, as ‘bringing leadership on board’ enabled safeguarding focal points to take forwards more concerted work (Africa Legacy Study 2024). In response to early findings on this, the RSH worked to focus on and engage leadership within the CSOs more directly, alongside safeguarding leads, including through the mentorship programme.

For example, in South Asia Hub, specific tools and events were developed, and the mentorship programme included early in-person training for all mentee organisations leadership and their safeguarding focal points. As a result, all organisations reported improved systems and policies in their organisations and committed to cascading learning and knowledge to their downstream partners. Through creating commitment and leadership buy-in to safeguarding, CSOs became positive champions in their own contexts, reaching more organisations and improving the awareness of safeguarding beyond the RSH; a key success of the mentorship model. In Pakistan, one CSO cascaded training to 85 organisations at community level, including in a Women’s Empowerment Assembly, alongside successfully lobbying the Education minister to advocate for all schools to have a safeguarding focal point.

RSH conducted a learning review on the sustainability of the mentorship programme as a follow up to a recommendation from the 2023 annual review. The report provided detailed reflections on the programme alongside evidence to inform approaches to improve sustainability and impact of mentorship interventions. As a result, RSH increased resources and support to mentors, including direct training and co-facilitation of sessions with an RSH mentor, pre-training before commencing mentorship, refresher trainings and cross-Hub peer learning with mentors from other countries.

The research also found evidence of unintended positive outcomes, such as increased funding opportunities for some CSOs, as a result of mentorship and capacity building from RSH.

4.1 Responsible exit strategies are identified for all national hubs and learning shared back for future hubs
Over the lifetime of the programme, RSH made strong efforts to produce detailed exit strategies. Earlier opened hubs developed these later in their 2-year cycle and it was noted that earlier exit / transition planning was needed, to ensure that users were better prepared for closure / handover timelines. Establishing clear exit plans much earlier in the hub lifetime, ideally within their first year, helps facilitate planning at a much earlier stage. For example, MENA exit strategy was developed 5 months before the closure of the Hubs and integrated learnings directly from the Africa Hub closures into the strategy. The South Asia exit strategies were developed 8 months before the closure giving more time for stakeholder engagement. Both strategies made adaptations based on the lessons included in the Africa Legacy paper.

The programme also developed a longer-term sustainability plan as it progressed, informed by the feedback and evidence generated. This resulted in a model which would see a national hub to become locally-owned by a national CSO, who would then take forward the shaping of the offer and delivery within the national setting, supported by the global team, as a ‘local affiliate model’. This was successfully launched as pilots in Ethiopia and Nigeria (as noted further below), though still in early days at the end of the programme.

Furthermore, the model of having National Expert Boards provided national and local technical advice, expertise and peer learning to national hubs which help ensure policy consistency and relevance. Alinea found that this approach contributed greatly to fostering institutional resilience beyond the programme’s closure. In Nigeria, for example, the NEB model supported long-term institutionalisation “Even without external funding, our team has continued community awareness-raising activities.” The Nigeria Country Assessment noted that several NEB mentors continued to informally advise CSOs beyond the programme’s end.

Despite these efforts, it was recognised that long-term sustainability was undermined by structural barriers but also internal challenges due to sustainable funding beyond the FCDO funding cycles, transition planning challenges from inconsistent communication around programme exit and localisation ambitions.

A key lesson from this programme has been that the two-year hub cycle was often too short (first highlighted AR 2022). The programme was always set up to have options for funding from other donors to co-fund, with each national hub funded through this programme for a two-year cycle, with the aim to seek national/ wider funders, subject to need and appetite. Despite strong exit strategies and fundraising strategies, there were mixed successes for this over the programmes lifetime. As the 2-year fund cycles approached, RSH sought investment from other donors and institutions to either continue the same model for national / regional support, or to support the hub to be handed over to a local affiliate partner (LAP). Unfortunately, despite widespread and clear ongoing demand (demonstrated by user feedback and the sustained uptake of the online resources), due to the ongoing challenges of funding within the development sector as well as regional conflicts, RSH only saw limited investments. However, when the national hubs ceased in-person delivery and operations, all online hubs have remained active with all online resources still available for the duration of the programme, managed by the Global Hub. This ensured ongoing sustainability of the programmes resource and tools without additional investment.

In two of the hubs, however, Nigeria and Ethiopia, additional funding was found, in both instances by the FCDO posts to pilot the LAP model. In each, a CSO was assessed and approved – Hiwot in Ethiopia and WRAHP in Nigeria. These two CSOs had both undertaken the full mentorship programmes with RSH and demonstrated proven strong national and context-specific networks with which to work through. Both pilots are in the early stages of delivery at this time (Hiwot launching in April 2024 and WRAHP in April 2025) but have had strong ownership and delivery so far.
Alinea carried out a case study deep dive of Hiwot/ RSH Ethiopia and explored the implementation of the RSH localisation model in Ethiopia, highlighting how Hiwot Ethiopia has sustained, adapted, and scaled safeguarding services post-transition. After assuming leadership in April 2024, Hiwot has trained over 70 CSOs, 400 staff, and 21 government representatives. Alongside maintaining key elements of the RSH model, Hiwot have adapted this to suit the local context including through implementing field mentoring and site visits to address practical issues like poorly placed complaints boxes, blended learning combining online modules with simplified in-person sessions and printouts for low-literacy audiences and ongoing support via phone, email, and document reviews. Their strong reputation nationally has enabled ongoing strategic partnerships e.g. PSEA Network and CHS Alliance have reinforced visibility and aligned Hiwot with national safeguarding agendas. Hiwot have also taken steps to address sociocultural barriers, specific to Ethiopia; Patriarchal norms, stigma, and low awareness undermine uptake of safeguarding guidance but Hiwot has addressed this by simplifying materials, promoting peer learning, and supporting leadership engagement (Alinea 2025).
[note] This case study provides supplementary evidence to the independent Evaluation Alinea carried out on RSH.

Alinea’s review found that the Ethiopian localisation model offers a valuable foundation for national safeguarding leadership and provides important lessons for other contexts such as Nigeria and WRHAP. The transition to Hiwot Ethiopia has maintained momentum, relevance, and credibility for safeguarding in Ethiopia, demonstrating that local leadership can sustain and adapt technical programmes when supported with appropriate resources, partnerships, and political will. The longer timelines for Ethiopia and Nigeria direct delivery have further deepened the impact of the RSH, both in terms of sustainability and localisation.

The ongoing shrinking global funding landscape has also impacted the LAPs, with both struggling to secure additional funding to continue safeguarding trainings, mentoring and capacity building, despite ongoing requests for services and web uses. Given the downturn in the global aid resources and availability, it is likely to get more challenging to secure funding also locally in the near future. This has further impacted the resources which the LAPs can funnel towards PSEAH / Hub efforts; in Ethiopia, without dedicated funding Hiwot have been unable to implement dedicated staffing and technical access to the Hub, limiting their ability to update tools and resources or expand the platform yet, since transition.

A key finding from the Alinea Evaluation was that in places where a LAP was not rolled out, the financial uncertainty after the two-year cycle impacted how the programme was able to communicate its potential end / roll over, and this confused users who were unclear what the offer would look like after the two-year period, and saw some users dis-engage. This was a challenge given the RSH team were networking and engaging to secure additional funding from wider donors/ stakeholders, to continue hub delivery in-country, it was therefore not clear what the final timeline would look like. This points to the need for a clearer exit / transition plans to be in place from the very outset of each hub, alongside earlier engagements with potential co-funders or clear comms to all users on what the exact offer and timeline is for the hubs e.g. to identify a LAP. Embedding sustainability and transition/exit strategies from the outset is crucial.

4.2 Evidence of what works (related to RSH activities) to strengthen organisational capacity to safeguard against SEAH is developed, consolidated and disseminated
The proliferation of evidence and learning shared by RSH in relation to their activities has been central to sustaining the programme and hubs achievements at global and national level. Primary research, whilst requiring significant resource has proved to be a critical output of RSH’s work alongside supporting CSOs directly. Alinea found that the RSH Global Hub has made significant progress towards producing evidence and learning related to SEAH in the aid-sector. The Evaluation found that the RSH made important contributions to the global evidence base, with evidence outputs often developed in collaboration with National and Regional Hubs and disseminated via the Global Hub online platform. All research and evidence produced by RSH was shared via the RSH website and through various dissemination efforts by the implementation team. There is also strong evidence of the RSH National and Regional Hubs investing significant resources into producing localised evidence pieces that are shared via the RSH Global Hub and with national CSOs.

The Evaluation recognised that RSH’s key publications demonstrate how the RSH has been able to gather and generate important and valuable evidence that supports addressing SEAH in the aid sector. The production of knowledge products, particularly the 2021 Global Evidence Review of Sexual Exploitation and Abuse and Sexual Harassment in the Aid Sector and its 2025 update, stands out as a major contribution. These reviews map existing gaps in SEAH prevention and response and offer priorities for future research. The Global Evidence Review has received widespread international interest, and this was used as a key reading piece to inform the Wilton Park Event in April 2025.

Alongside this, five key products have been completed and published. The final products are wider ranging, informed by regional and national areas of need for inquiry; (1) Africa Legacy Study (2) Learning Research: Implementing RSH in the MENA region (3) The state of safeguarding policy implementation within African organisations, including child safeguarding (4) The Localisation Agenda in Pakistan (5) RSH conference learning report. For Nigeria, 1 Bitesize Learning from RSH Nigeria’s safe organisational culture mentoring pilot programme informed by RSH learning and research was completed and published alongside a webinar to disseminate the findings to a range of stakeholders. Two additional learning products were developed, a Learning Brief on the investigations mentorship programme and an Infographic of insights from the basics mentorship programme.

The Alinea Evaluation found stakeholders praised the quality and utility of the materials. However, the report suggests that to maximise its contribution to the global evidence base, the RSH should continue investing in localisation and translation to ensure that its evidence outputs, not just tools, are truly accessible and applicable to the diverse contexts in which less-resourced CSOs operate. Furthermore, the evidence generation was not always based on systematic reviews or cross-country comparisons, and learning tended to remain siloed by region or activity. While the evidence is publicly accessible, its reach among CSO users remained limited; it was noted by some that the Global Hub website is difficult to navigate.

Lessons learned through this output, and recommendations for future programming
The 2025 Alinea Evaluation highlighted that the better communication on exit plans and timelines would have supported ongoing user engagement and truly responsible exit strategies –
Sustainability requires early planning and embedded systems: Trust and sustainability are best preserved when programmes communicate exit strategies clearly from the outset on the programme lifecycle and hub lifecycles with users to be clear when direct support would cease, seek to rollover, move to a LAP model etc. A clear programme approach to transition, including options for locally owned hubs is essential to ensure that from the outset, a process is mapped out, as planned for RSH2. Abrupt or poorly planned transitions can damage credibility and outcomes. Staggering Hub opening was key to enable continuous learning and improvement for future hubs.
- Implement mandatory senior leadership engagement protocols. Programmes should consider establishing dedicated CEO/Executive Director workshops within the first 3 months of programme launch, create quarterly leadership accountability reviews, and encourage senior management to personally champion safeguarding integration through visible actions and resource allocation rather than just through focal points.
- Implement systematic staff turnover mitigation strategies. Implementers should establish train-the-trainer programmes aiming for approximately 3 safeguarding champions per organisation, develop comprehensive knowledge management systems with documented procedures, create mentorship succession planning protocols, and provide transition support when key safeguarding personnel leave organisations.

D: Value for Money
VfM performance compared to the original VfM proposition in the business case

Key cost drivers and performance
The main cost drivers in the RSH programme were programme fees (85%) and programme expenses (12%). The latter category includes activities, travel and Monitoring, Evaluation and Learning (MEL) costs. The programme delivery was predominantly based on use of expertise (research, consultancy, training, mentoring etc.) and therefore the large share of programme fees reflects this modality.

As the programme was adaptive and demand-led, there were natural variances in spend as activities changed in response to user need. Several budget amendments were agreed over the programme lifecycle, and due to Covid-19 adaptions where online delivery platforms were utilised more than in-person, a portion of the expenses budget items were moved to the programme fees.

The programme delivered within the scope of the budget, with only no-cost extensions provided to deliver, alongside securing additional, separate investments. The large numbers of users accessing the hub, substantially exceeding milestone targets and achieving within the original budget, show the economy and efficiency of the programme and its effectiveness in reaching a large audience. The programme monitored costs and forecast spend figures closely over its lifecycle. Performing well against its target indicators. A value for money framework with specific metrics was not developed, which could have provided further rigour and consistency to measuring VfM and enhance the narrative and proposition of the programme.
Economy
The programme delivery was economical, based on analysis of the programme data, Alinea findings and evidence gathered from key stakeholders interviews for this PCR. The costs of delivering the activities for this programme provided good value compared to the outputs delivered. The programme focused on providing high-quality outputs, such as online safeguarding resources, e-learning, mentorships, and peer-to-peer learning at a reasonable cost. Operating and other budget costs were carefully monitored, and the budget execution (or burn rate) for the programme quarterly periods have been high, consistently above 90% along months and quarters, and reaching 97-99% annuals. This was an indication of good financial management. Daily fee rates were broadly in line with wider ODA programmes, and many on the lower end of the range.
Efficiency
A cost analysis was undertaken as part of the Alinea International External Evaluation, which found that The RSH programme has demonstrated good value for money through its efficient use of resources, adaptability to challenges, and commitment to equity. The programme met or exceeded its output indicators. Programme funding and activities were monitored closely against agreed workplans to ensure good control and oversight. The regional and national hubs delivered effectively for the beneficiary CSOs and the wider networks of safeguarding practitioners, within relatively lean cost structures. The programme’s adaptive and demand-led approach to delivery also made it more cost-effective. For example, at the start of the programme, due to the Covid pandemic, all activities had to go online, which reduced the costs associated with travel and in-person events. Alinea found that travel costs represented 2% of overall programme expenditure which was very low for a 5-year programme operating in multiple countries and regions. Several stakeholders referred to a ripple effect (or a learning curve) where ‘adaptations in the initial years contributed to more efficient methods and greater outreach in the later phases of the programme’. Additionally, the staggered approach to setting up national hubs enabled lesson learning to inform and create further efficiencies of future hubs. However, as noted elsewhere the two-year hub cycle has been recognised as not long enough, so creating challenges for sustainability.
Effectiveness
Overall, the programme has received strong positive feedback on its services and products. In the Annual User Survey 2024, around 85% of respondents agreed or strongly agreed that ‘Engaging with [the] RSH has improved my understanding of how to apply international safeguarding standards in my context.’ and a similar proportion in 2022 and 2024 felt that RSH had improved their ‘ability to implement safe programmes and support a safe organisation’. The Alinea International External Evaluation noted that CSOs who participated in the mentorship programme were especially likely to attribute the development of formal safeguarding SEAH, and protection policies to their engagement with RSH. The RSH also prioritised national level expertise, and delivery through national consultants. Alinea found that this reduced costs but critically, helped build the national rosters of safeguarding consultants in the RSH countries, representing a good example of cost-effectiveness, alongside contributing to sustainability.
Equity
The full suite of resources and support have always been free to use for all and offered in more than 10 languages, demonstrating its strong commitment to equity. Programme data and stakeholders and user feedback recognised RSH’s strong commitment to equity. RSH has worked to target less advantaged groups (including rural/remote or less-resourced CSOs, OPDs, WLOs/WROs, and organisations representing LGBTQI+) to build local capacity, formed partnerships for disability-inclusive interventions, for example, working with Sightsavers on visually impaired technologies and learnings, translated materials into local languages and adapting the contexts, and conducting specific research and communication pieces on vulnerable groups, such as research around the Hijra community in Bangladesh.
RSH developed a supporting inclusion-focused Ethical Framework to underpin delivery covering the vision, approach, values and principles which describe how they put these values into practice including driving delivery of the ToC. The reflects the programmes strong integration of GEDSI consideration. The Alinea Evaluation highlighted this, noting the RSH demonstrated highly effective and intentional integration of GEDSI considerations into both its design and implementation, achieving meaningful reach to marginalised populations while adapting to diverse contextual challenges across regions and contributed meaningfully to sector evidence.
Alinea reiterated the importance of prioritising and enhancing equity and inclusion in future programming, recommending: 1) Conduct detailed political economy analyses of GEDSI barriers, create graduated implementation approaches to build acceptance over time, developing alternative delivery mechanisms when direct approaches face resistance, engaging traditional and religious leaders in GEDSI dialogue; and 2) Invest in comprehensive accessibility infrastructure e.g. translation and sign language interpretation services, consulting and partnering with disability organisations to develop assistive technologies and culturally appropriate aids and seeking feedback on these through quarterly feedback collection from marginalised groups.
Assessment of whether the programme continues to represent value for money
The programme represented excellent value for money in providing tools and guidance to increase the knowledge and understanding of SEAH across the aid sector; it has consistently produced better results than anticipated for a relatively small budget. The programme has significantly exceeded several of its outputs, particularly in increasing access to safeguarding resources with over one million users accessing the online platforms, and engagement demonstrated via the ‘ripple effect’ of the mentoring programme. RSH has created new resources that can be used as global goods for public use, that would not have been possible without UK funding. This demonstrates that the programme has worked efficiently to deliver its outputs and outcomes.
E: Risk
Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The FCDO risk rating for this programme remained Moderate for the duration of its lifetime, reflecting the programme’s work on a sensitive, highly technical subject and across a range of geographies, many with high risks. Risks were largely kept within appetite (cautious) and managed carefully by the RSH core team working with downstream and consortium partners and closely with the FCDO. The programme actively monitored risk through an internal FCDO risk register (with risk appetite set against each risk category) alongside regular and thorough oversight and risk management practices in place with the supplier. Social Development Direct and Options provided ad-hoc or monthly updates to FCDO, as necessary from their own programme risk register. More detailed risk reports were provided and discussed quarterly, providing key risks to flag, mitigation updates and new or emerging risks. Risk discussions also formed part of the quarterly monitoring framework reviewed by the Executive Steering Committee.

Although RSH operates globally, across an array of different contexts, there were a number of key trends in risk exposure and context. Significant risks which impacted the programme over its lifetime were:
- External Context: Driven by political instability, climate impacts and conflict and humanitarian crises. Crises and political instability disrupted operations, requiring adaptations or pauses in delivery and heightened monitoring. COVID-19 across the programme and climate impacts in South Asia also impacted delivery and necessitated programme adaptations.
- Programme Delivery: Sustainability remained a long-term concern, including risks of knowledge loss when hubs closed. This was tracked closely across the programme with staggered hub roll-out to inform lesson learning and focusing on suitability impacts beyond programming. The persistent challenges in reaching remote or marginalised groups were noted and tracked closely, particularly in South Asia and MENA hubs with focused efforts to work with local partners with contextualised knowledge.
- Staffing and Cost Pressures: Periods of high staff turnover and difficulty recruiting qualified personnel impacted delivery quality. The rise of the global cost of living also sometimes strained budgets, affecting consultancy rates and technical recruitment.

A summary of the risks against each risk category is provided below.
Risk Category	Risk Appetite	Risk assessment summary over lifetime (key trends and drivers)
Strategy and Context	Receptive	The programme covered a broad geographical footprint, each with their own contextual impacts, closely managed by RSH. The decision to work in areas of higher risk e.g. protracted crises reflected regions judged higher risk to SEAH within the sector. In particular: / Crises and political instability in MENA, Bangladesh, Ethiopia, Nigeria and Pakistan, disrupted operations and communications, requiring adaptations or pauses in delivery, engagement with expert networks and heightened monitoring. Activities were (re)scheduled around key elections. Some delivery (e.g. Ethiopia and MENA Hub) were designed with ongoing regional conflict in mind, with adaptive, mixed methods of digital and face-to-face support provided. / COVID-19 across the programme (especially 2020-21) and climate impacts in South Asia also impacted delivery, limited travel and necessitated programme adaptations and delaying of in-person travel, activities and engagements. / RSH conducted Country Assessments to map risks and carefully design activities including providing crisis responses where necessary by advertising specifically tailored online resources, with generic rapid-response activities and resources kept up to date to be rolled out as needed. / The UK Government maintained its strong commitment to Safeguarding against SEAH through the 2020 UK SEAH Safeguarding Strategy which commits to strengthening sector-wide capacity and capability to meet and drive-up global standards. This underpinned the programme, so that whilst ODA cuts necessitated programme budget reductions, commitment to the programme remained a priority. DEC funding to Eastern Europe Hub marked a new model for reactive delivery, and engaging wider stakeholders on PSEAH.
Policy and Programme Delivery	Receptive	Key delivery risks related to access and inclusion for uptake of resources, sustainability and technical expertise to deliver: / Sustainability of RSH, especially national hubs, remained a long-term concern, with risks of knowledge loss as hubs closed. This was mitigated through responsible exit strategies for each national hub informed by lesson learning from previous exits, and regular meetings between the programme team to discuss sustainability approaches and identify future stakeholders and funding streams. Developing and piloting the local affiliate partners (LAP) models had further strengthened localisation and sustainability, with local ownership taking the lead of national hub activities in Ethiopia and Nigeria. / There were persistent challenges in reaching remote or marginalised groups, especially in Yemen, Syria, and Pakistan. Efforts were focused in working with local partners/networks with contextualised knowledge, developing remote/offline resource offers (including on the RSH App) and training of trainers offers. Carefully selected and engaged technical expertise through both the consortium and national / regional experts ensured RSH was able to deliver the programme’s sensitive aims and objectives. Country Assessments were developed with extensive national consultation were developed to inform delivery to ensure interventions were contextualised, tailored and sensitive to local needs. / Humanitarian crises affected both staff and beneficiaries particularly regarding MENA, Bangladesh and Ethiopia. RSH ensured regular outreach to CSOs and collaboration with local NGOs and humanitarian networks, including provision of resources in local languages. / FCDO contract amendment timelines and processes also impacted delivery and activities, highlighting the need for early engagement with FCDO’s Commercial Department and clear timelines for partners.
Finance and Fiduciary	Minimal	Risks remained low in relation to poor financial management, VfM or fraud. Strong financial management and oversight was implemented in accordance with FCDO's PrOF rules/procedures, including maintaining constructive financial oversight through standard monitoring and evaluation procedures. Reports were shared with FCDO monthly to mitigate risks of delayed / incorrect payments. Value for money assessments were conducted as part of annual reviews and quarterly assurance meetings reviewed finances in deep dive. Social Development Direct and Options undertook due diligence with all partner /downstream organisations to ensure funds were properly spent and accounted for.
Reputational	Minimal	Key risk tracked related to lack of demand for services provided under the programme and low engagement from target countries and organisations. FCDO and RSH ensured continued, effective comms and stakeholder outreach strategies to stimulate demand e.g. identifying key local networks. National stakeholders such as the National Executive Boards, PSEA and IASC networks in country also supported this. Adding International Council of Voluntary Agencies (ICVA) as a consortium partner in 2022 (which has strong networks) improved and expanded outreach. RSH closely monitored and evaluated data to assess uptake of resources and to ensure they were reaching target groups.
Safeguarding	Minimal	Key safeguarding risks tracked were in relation to the programme being insensitive to or retraumatising victim-survivors. This was mitigated through the RSH’s Ethical framework and ‘do no harm’ principle and through expert consultation including from within the consortium of partners to develop Country Assessments and delivery plans. The programme employed strong technical expertise, through national expertise and the consortium, who were skilled in delivery which carefully centralised a locally contextualised survivor-centred approach. Products were developed and reviewed in consultation with technical experts and key user groups, including FCDO, to ensure unintended harms were minimised. Climate and Environment risks, in line with the Paris Climate Agreement were judged low.
People	Minimal	High turnover and difficulty sourcing qualified staff, especially in South Asia, heightened risks of delays to and quality delivery. RSH worked with stakeholders in country to help identify local expertise, prioritising regional/ national expertise and associate roles in many cases. RSH and FCDO had a strong focus on staff wellbeing and resilience, including maintaining a positive, open, diverse and inclusive environment, and promoting good values and behaviours. This helped tackle psychological risks to staff placed by working on safeguarding against SEAH. All RSH contracts included a Child and Vulnerable Adults protection policy and Safeguarding Framework with all staff inducted and trained on this. Careful Due Diligence applied to all RSH staff, consultants etc.
Public Service Delivery and Operations	Cautious	COVID-19 impacted approaches to delivery but duty of care of all staff and users was always prioritised to ensure safety and wellbeing. FCDO Programme staff were not based in fragile locations as part of programme oversight and delivery. RSH and FCDO took a strong risk-based approach for any travel (staff or partner), prioritising the security and safety of people, mitigating robustly through a clear duty of care process, monitoring risks and seeking approval for any high residual risks. An asset register was monitored and updated quarterly by RSH to track and ensure the security of assets and information.

Lesson learned
A key lesson from the programme was the value of a ‘live’ approach to risk management from the very start of the programme and each national Hub development. RSH undertook detailed country assessments for each region ahead of launching national hubs, which provided a strong approach to understanding the risk profile of each national setting including key contextual risks (e.g. such as conflict, natural disaster and inequalities) and opportunities, to inform national strategies. These risks were then fed into the ongoing risk management approach and monitored over the hub lifetime, including for swift escalation. Appropriate mitigation measures were kept in place for all risks and FCDO were kept up to date on any rising risks and mitigation/control progress.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.
The global programme was managed via a consortium led by Options Consultancy, with Social Development Direct (SDDirect) as technical and delivery lead and including Terres Des Hommes, International Council of Voluntary Agencies (ICVA), Clear Global, and Sightsavers. The consortium partners were selected based on their expertise and ability to add value to the RSH programme activities. ICVA had access to a network of organisations across the Global South, ClearGlobal supported work on the translations of RSH resources in local language, SightSavers assisted with visually impaired technologies and learnings, and Terres Des Hommes led with website management.
The programme was managed within FCDO by a Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO). Technical advice was provided by Senior Social Development and Humanitarian advisers. The stand-alone contract RSH Nigeria Hub was delivered by SDDirect, as a component to this programme. There was productive working relationship between FCDO and delivery partners who provided quality and timely reporting and engagement, proactive dialogues and strong financial and risk management.
Commercial
During the design phase, an open and consultative approach was adopted by DFID(FCDO) (to inform programme design) and the suppliers (to develop their proposal), ensuring the right expertise was engaged early to inform the direction of the programme. A successful early market engagement (EME) event was held by DFID to source ideas and receive feedback from a wide range of stakeholders. In selecting partners for the consortium, the suppliers engaged widely with NGOs and contractors, considering a number of factors in assessing expertise including: technical expertise in safeguarding against SEAH; connections to the civil society organisation (CSO) sector; and expertise in specific fields like child safeguarding. The suppliers adopted a consultative approach to designing and developing the bid, holding several full consortium meetings to harness the breath of expertise across consortium members.
Options Consultancy were assessed against the FCDO Supplier Code of Conduct in November 2020. Their compliance was reviewed annually since then, with no issues of concern identified. RSH met or exceeded all of the KPIs set out in the contract. Since its inception, the global programme contract underwent a number of contract amendments with substantial amendments in 2021, to extend the end date to December 2024 and increase the budget (in meeting inception phase milestones) and; in 2024, to extend the contract end date once again to 31 March 2025 to support final activities which were impacted by ODA budget restrictions, COVID-19 and regional political instability challenges. A final, short no-cost contract extension was required in 2025 for 2 months to bridge the contract to the new RSH2 contract mobilised in May 2025. The stand-alone RSH Nigeria contract had minor contract amendments to update the KPIs in July 2024 and to extend the contract and increase the budget in October 2024 in line with its proposed budget, in meeting key milestones.
AR 2022 noted that the multiple contract amendments to the global programme over the years caused some disruption and delay to delivery. Business planning within FCDO resulted in higher workload and pressure on the FCDO Commercial department at points. A key lesson was that earlier engagement with the FCDO’s Commercial Department and clear timelines for the partners on amendments was key and should prevent delays.
Financial
RSH has demonstrated sound financial reporting. Monthly financial reports detail any variances and progress against quarterly and annual forecasts. Before payments were processed, these were examined by the FCDO's PRO and SRO, and any issues investigated. The programme spent very close to its full budget and provided accurate forecasts. Additionally, the programme demonstrated flexibility in responding to FCDO requests by quickly supplying financial reports when necessary and adjusting budgets as needed. As explained in Section D, overall, the project shows strong value for money, reaching a sizable number of people at a comparatively low cost.
Asset disposal
RSH maintained a detailed asset register to track and manage all programme assets distributed across RSH Hubs. RSH agreed a tailored asset disposal approach with FCDO based on context and need identified through a selection process. Appropriate measures were put in place to ensure that all assets followed the information and data protection process. All personal data was deleted, and any programme records and data were either deleted or filed with restricted access if relevant to be kept under legitimate interest.
Programme-level approach to monitoring and evaluation
Monitoring and Evaluation
RSH submitted timely quarterly narrative and financial reports, and provided reflections and updates on progress, including against KPIs and indicators and live updates on key risks. The quality of the reports was consistently strong, covering all relevant issues and providing a thorough understanding of the programme's performance during that period. As part of the quarterly KPIs, RSH also provided regular more detailed monitoring and evaluation analyses reports. The RSH team met with FCDO at least monthly and more regularly when needed to discuss live issues and risks within the programme. These provided FCDO with live updates from partners and allowed for unexpected challenges, such as humanitarian crises, to be responded to quickly. Logframe updates were provided every six months to track progress including any indicators off track.
The governance arrangements for RSH included an Executive Steering Committee (ESC), Consortium Advisory Group (CAG) and National Expert Boards (NEBs):
- The ESC, chaired by FCDO Head of Safeguarding Unit, provided strategic oversight of RSH’s work to discuss progress and assess risks. It met biannually and was comprised of the RSH team, FCDO and senior representatives from each consortium member.
- The CAG provided independent advisory support and direction of key activities. Whilst this brought value in the early phase, following an internal review in 2023, this was discontinued. The review recognised the greater focus on localisation and regional responses to safeguarding SEAH, and as many CAG members were part of the NEBs, this was adding greatest value. All former CAG members remained close associates of the programme as ‘friends of RSH’, with smaller, focused groups convened as needed for particular consultations, pieces of work or challenge points. This marked a sensible approach to both evolve the relationships and to make the best use of expertise links.
- The NEBs served as multi-sectoral advisory bodies for the national / regional hubs. They supported to guide and strengthen safeguarding efforts, provide strategic advice and foster inclusive communities of practice where stakeholders could engage in dialogue around PSEAH. For example, in Nigeria the NEB helped scale up SEAH efforts by expanding stakeholders beyond less-resourced CSOs e.g. media and academia.
FCDO conducted formal Annual Reviews of the programme, with AR 2022 carried out by independent evaluators for additional rigour. FCDO’s Safeguarding Unit and post-staff visited RSH’s direct delivery in national hubs over the course of the programme too. FCDO commissioned Alinea International to carry out an independent end-line Evaluation in the final year of RSH’s lifecycle, to evaluate the performance of the programme, determine how far the programme achieved expected results, analyse the value for money and capture key lessons and learning.
Evidence
User engagement and evidence-informed decision-making have been a key component of the programme. The programme established a high-quality evidence base, with products and services systematically developed, consolidated and disseminated to a diverse range of users. There have been several major pieces of evidence over the programme lifecycle that demonstrate 'what works' in relation to RSH activities to strengthen organisational capacity to safeguard against SEAH (see Output 4 for more details). For example, the Africa Legacy Study (2024) looked at the sustainability of RSH’s impact in Ethiopia, Nigeria and South Sudan, and the Global Evidence Update (2025) provided a snapshot of the status of the evidence base regarding SEAH within the aid sector, as an update to the previous Global Evidence Review 2021, and to serve as an advocacy tool to inform any future research and learning priorities for the aid sector.
The RSH effectively conducted extensive data collection over the lifetime via website pop-ups, feedback forms, webinar pop-ups, KIIs and FGDs and the Annual User Survey. These reached a wide range of users and key stakeholders and captured user experiences and feedback to inform delivery. Stories of Change were also captured to provide depth in evidence of learning and capability building achieved by the RSH.
Learning
The capacity of the programme to adapt, learn, and evolve has been one of its key strengths. Over the lifecycle of the programme, RSH has been demand-led and evidence based, using the feedback received from users to make changes to the programme. The representatives of different hubs met on a regular basis to share lessons across the different contexts. RSH also produced several learning briefs, including on RSH Nigeria’s Safe organisational culture mentoring pilot programme and Implementing RSH in the MENA region. Each national exit strategy has also reflected learning from wider close-outs.
The Alinea Independent Evaluation included case study evaluations of RSH to demonstrate (i) how the RSH model can be adapted to better respond to the evolving priorities and risks in Fragile and Conflict Affected Sates (FCAS) (ii) how South Asia CSOs that participated in the mentorship programme have applied the learnings from RSH to strengthen their policy and practice against SEAH and (c) how RSH’s localisation model has been implemented through its partnership with Hiwot in Ethiopia.

Date of last narrative financial report	April 2025	Date of last audited annual statement	December 2023

Annex A: Original Business Case ToC