## Annual Review Template

Title: Sinaan (Formerly Green Urban Growth Programme)
Programme Value £ (full life): £39,000,000		Review date: / November 2025
Programme Code: 300797	AMP start date: 15/11/2023	AMP end date: 01/09/2030

Summary of Programme Performance
Year	2024	2025
Overall Output Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300797/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300797/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Green Urban Growth (GUG) Programme, rebranded as Sinaan (“Equity”), is a key UK Aid programme supporting climate resilience and green growth which will help shape Somalia’s urban future. With cities expanding rapidly due to climate displacement, migration, and natural growth, urban centres face mounting pressure on governance, service delivery, and infrastructure. Sinaan addresses these challenges by bridging immediate humanitarian and development needs with long-term systemic transformation. The Programme delivers inclusive, climate-resilient, and conflict-sensitive interventions, combining quick-win projects that build trust and visibility with deeper reforms to strengthen governance and resilience.

The Programme is structured around three outcomes: improving urban planning and investment decisions, building a pipeline of climate-resilient, bankable projects, and mobilising finance, including climate finance. Its blended approach focuses on five priority cities, namely, Baidoa, Dhusamareb, Bossaso, Burao, and Wajaale, while piloting scalable models in Mogadishu, Hargeisa, and Garowe that integrate nature-based solutions and green infrastructure. Designed to be modular and adaptive, Sinaan embeds climate resilience, gender inclusion, and conflict sensitivity across all interventions. Partnerships are central to the Programme’s approach. By working with the Federal Government of Somalia, Federal Member State ministries, municipal governments, and civil society, Sinaan strengthens ownership and accountability. Coordination is further anchored through the Programme Steering Committees (PSC), which ensure coherence with donor and government priorities, and the Somali Cities Initiative, which provides a platform for peer learning, municipal reform, and policy dialogue across all donor investments.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
This annual review marks a significant pivot for Sinaan, moving from an extended inception phase into active implementation. The previous review was awarded a ‘B’ rating due to delays stemming from internal strategic reviews, contracting processes, and procurement bottlenecks. Those issues have now been effectively resolved.
Across the output indicators for this first AR the focus was on implementation of start-up activities given the implementation period up to the November AR date is less than 6 months. The activities are therefore a combination of preparatory and assessment work, stakeholder engagement and some project identification. Across all these indicators Sinaan has met expectations.

Output	Score
Output 1: Enable Capacities: Stakeholders have increased capability to respond to plan for urban growth and adapt effectively to climate risks and impacts	A
Output 2: Identification and facilitation of donors, diaspora, private sector actors, investors etc. in support of programme objectives	A
Output 3: A pipeline of inclusive, climate resilient bankable projects and transformative initiatives with credible funding proposals developed by public and private actors to attract finance and foster partnerships.	A
Output 4: Evidence produced to test, learn and provide proof of concept for scale, and to strengthen programme delivery, adaptation and sustainability.	A
Output 5: People with improved access to climate-resilient urban infrastructure and services – World Bank programme	A

Programme Performance & Partner Delivery
The programme’s inception period started in January 2025 after an initial delay in signing the contract of several months due to internal reviews of the future Somalia portfolio. The inception period focused on developing key strategies – gender mainstreaming, inclusion and climate, alongside a comprehensive city diagnostic tool. The latter was used to identify potential cities from the long list provided in the business case. This diagnostic tool was important in providing robust evidence for choosing particular cities. This was complemented by both an internal and external independent political economy analysis which was overlayed on the diagnostic tool to help refine city selection. This work in particular has been important in demonstrating to the Somali authorities the reasons for focusing on certain cities over others – this has required balancing political realities and security and access issues with where Sinaan can find quick win opportunities. The programme team handled these difficult discussions well and has built a credible team of international and Somali experts who can work closely with government on these issues.
The programme has had to adapt after the recent decision to cut ODA from 0.5 to 0.3 of GNI which was announced early on during the inception period. The team responded flexibly developing a modular approach where the programme can scale up or down, piloting projects in some cities, depending on the resources available. Given the delays in decision making as to whether the programme would move to implementation and then changes in timeframes from an initial 9 months to an extension till March 2027, the programme has proven its ability to mobilise quickly responding to need and adapt accordingly.
The Programme is now fully mobilised, with a defined implementation strategy and resources concentrated on the five cities listed above, supported by high-visibility pilots in Mogadishu, Hargeisa, and Garowe.
Beyond this there are key factors that justify an A rating at this stage. First, the Programme has demonstrated strong responsiveness and adaptability. The shift to a blended approach, combining structured diagnostics with opportunistic engagements, represents a pragmatic adaptation to Somalia’s complex operating environment. This approach ensures that Sinaan can simultaneously deliver tangible quick wins at the neighbourhood level while also pursuing systemic, long-term reforms such as policy and regulatory changes. It reflects a balance between immediate impact and transformational outcomes.
Second, the Programme has delivered significant progress since its inception, overcoming earlier delays. Core diagnostics across municipalities have been completed, a governance framework for Programme Steering Committees agreed and established, municipal technical working groups established, capacity assessment at the state, national and municipal level completed, and a pipeline of climate-resilient bankable projects defined, co-created in consultation with the municipal mayors, private sector and state ministries.
Third, the Programme has achieved early traction in implementation. Visible neighbourhood-level engagements in Baidoa, Bossaso, and Burao are underway, building confidence among municipal counterparts, communities and signalling momentum to previous interventions by development partners. The programme has met with Presidents of both Puntland and Galmudug states indicating strong buy in at state level alongside building a close and effective working relationship with the Ministry of Interior Affairs in Somalia and Ministry of Urban Development and Local Government in Somaliland.
Finally, the Programme has mainstreamed cross-cutting strategies, namely, climate resilience, gender and social inclusion, and conflict sensitivity, into its design and early delivery. This integration is already visible in project selection and municipal engagement processes, demonstrating a holistic approach to urban resilience that aligns with both UK priorities and Somali needs. This has since led to the development of co-design clinics with local community groups which will help guide the design of interventions in each city.
The implementing partner has delivered well across all these areas as set out above, and in particular has been managing some of the tricker political dynamics. It has also increased its understanding and its ways of working across Somalia and Somaliland, adjusting accordingly.

FCDO Management
The programme team have navigated the changes in funding context and priorities (outlined below) by working closely with the implementing team, engaging directly with the Director of the programme to discuss changes and provide timely updates. This has required close and collaborative working between FCDO and the Sinaan team, identifying and shifting the approach as more clarity emerged on funding and timelines.
A key role for FCDO is in supporting Sinaan to bring in other partners, in particular the WB and also other funded programmes that the UK has an interest in such as Danwaadag. This will enhance Sinaan’s impact but also directly speaks to a key outcome which is mobilising financing where other partners become critical to delivering this. A key vehicle for this is the Somali Cities Initiative which was established during the early design phase of the Sinaan programme as a platform that applied a spatial lens to interventions happening in Somalia – the unit of analysis being the city. The platform provides an opportunity for sharing initiatives, learning and collaboration. It is co-chaired by the WB’s Task Team Leader for Urban and the FCDO SRO for Sinaan, with the secretariat run by DT Global. A key objective is to enhance and encourage co-ordination across the international community, bringing together UN agencies, MDBs and development co-operation teams from other embassies. Given the number of interventions happening at a city level across Somalia it is important that this group not only seeks to map what is being done where and by whom but also to forge strong linkages between interventions. This speaks to the UK’s focus on bringing partners together to focus on a specific geographic area and leveraging each other’s inputs for greater impact. Future plans for the initiative will seek to bring in government counterparts for specific thematic sessions and in particular the Mayors.

Relevance of Sinaan to the Context
Urbanisation
The pressure of urbanisation is becoming acute, in a country that is the fastest urbanising country in East Africa – an urban population of 7.4m. This process of urbanisation is in large part unplanned, driven by push and pull factors, across conflict, food insecurity and climate. We are continuing to see this leading to the displacement of populations from rural areas as they seek access to resources and services and as their existing livelihoods, for example in agriculture, are impacted by changing climate patterns.
The pace of urbanisation is having knock-on effects of environmental degradation and poor management of natural resources. Municipal governments are not able to deal with this due to weak political, economic and social systems, lack of clear land use and urban plans, and access to finance for investment. Yet this urbanisation trajectory is set to continue with Somalia projected to have an urban population that exceeds 60% by 2060.
The rationale for Sinaan is to intervene in these processes now to support a long term resilient economic growth pathway for these urban centres, , that builds in resilience to conflict and climate from the start. In this way, Sinaan will support urban resilience that enables humanitarian resources to be focused on those who need it most, providing space to take a longer-term approach to addressing the underlying drivers of vulnerability and building resilience, both climate and economic.

Climate & Nature
The Sinaan programme will continue to be one of the UK’s major vehicles for supporting climate resilience in Somalia working closely with the UK’s other key resilience partners, Danwaadag and the BRICS consortia. In particular supporting cities and states to identify climate adaptation and mitigation projects and consider options for financing that are more viable than accessing the vertical climate funds. Cities and states are not accredited to these funds and therefore there is a need to focus on access to other sources of finance – private sector and impact investors in particular. Sinaan is central in delivering this given its role in developing projects and providing early-stage funding to start work with small amounts of CDEL investment drawing in potential private sector actors to finance projects in the long term.
A key focus of Sinaan is to build broader urban resilience, which both addresses protracted and unplanned urban displacement, but also ensures the pattern of intensive urbanisation addresses climatic shifts, avoiding locking in, to future climate vulnerability and facilitating sustainable economic development, addressing the challenges of urbanisation outlined above.
The programme will also contribute significantly to the UK’s nature objectives with a focus on deploying nature-based solutions across all cities, in particular where low cost nature and ecosystem restoration interventions can address, for example, flood risks and urban heat island affects. This focus on nature is coming out strongly in interventions in Baidoa and Burao where urban greening, ecosystem restoration of parks and waterfall areas which can combat increasing flood risks are being scoped. A longer-term focus is being taken in Bosasso where afforestation along the coastline is being considered, in particular mangrove development which can provide a critical pathway to reducing coastal erosion and storing carbon. Across all these interventions modelling different ways of delivering nature-based solutions that also build community resilience, cohesion and bridges dynamics between IDP and host communities will be key.

Migration
The movement of people to cities can often be a stepping stone to outward migration from the country, in particular when livelihoods and services cannot to be accessed in the major cities people tend to move to. Evidence has shown that people are moving to cities and city governments are not coping with this influx, alongside managing the increasing stress from climate change and lack of finances to provide services, making them less hospitable places to stay. Therefore, if Sinaan can support cities to deliver services, bring in new financial flows and plan to reduce climate stresses such as urban heat stress, environmental degradation and flooding, people will be inclined to stay – where they do not want to return to rural homes, which some will still do – and therefore not migrate onwards. Furthermore, Sinaan can play a pivotal role in supporting residents in cities to have a stronger sense of accountability with local government, and build community cohesion, making Somali cities vibrant places to live with economic opportunities.
Sustainability of the State
The issue of government counterparts being able to finance their own development and budget fully are not new, however over the last year this has become an increasing focus for the international community and in particular for where the UK can provide support. This is in part because Somalia will graduate from World Bank IDA grants in three years so the issue is becoming more pressing. This will require Sinaan to focus more on the financing element of the work, across both mobilising private flows of finance to support service delivery and climate projects, and supporting revenue generation at the local government level.
National Plans
The most recent NDC 3 plan, which was submitted by Somalia to the UN earlier this year, outlines the need to focus on a few key priority sectors to tackle climate change. Two of these – water resource management and climate resilient infrastructure and urban resilience – Sinaan will be directly delivering on. Furthermore, the mitigation activities outlined in the plan include solid waste management and clean energy – areas where Sinaan has identified potential for longer term transformational projects in some cities. Therefore, Sinaan will be working across both adaptation and mitigation targets with the Somali governments’ climate and environment plans.
Changing funding context
The Sinaan programme has navigated the funding uncertainty and future reduced budget well, alongside managing the high expectations of Somali stakeholders. Despite the challenges and stop/start orders given to the team the programme successfully navigated this to move from inception to implementation, delivering city diagnostics, establishing Programme Steering Committees, and developing a pipeline of bankable, climate-resilient projects that directly address Somalia’s urban service delivery gaps and climate resilience and adaptation needs. In particular the programme has been successful in building relationships and trust at both municipal and state level and has the potential to support the development of forums for consensus building at the sub-national level across key stakeholders.
Shift to Portfolio Approach – Economic Development & Somaliland
A key part of the programme’s future work will be to deliver a transition period for the UK’s economic development work in The Somali region. A new portfolio programme will be delivered over the next year with a key focus on supporting Somalia to be self-sustaining with a focus on own source revenue, mobilising finance and building climate resilience and infrastructure development that supports future growth and revenue streams. The Sinaan programme is able to deliver across these key areas at the sub-national level over the next year. It is already beginning to identify projects that can support revenue generation, private sector investment and partnerships and approaches to financing climate adaption and resilience projects. Sinaan is beginning to illustrate approaches to bringing together local government and the private sector to focus on delivery through improving local state actors to have capacity to do this. In this way Sinaan can be showcasing for the broader economic development portfolio programme how to bring these actors together, whilst also navigating the political dimensions of this.
Finally, an important priority going forward is ensuring that Sinaan is making relevant links and supporting the development of the Somaliland portfolio. In particular it will need to maintain and build stronger connections with the Somaliland Development Fund. This will be important so that Sinaan and SDF can leverage each other’s investments and technical assistance to maximise impact. Furthermore, Sinaan will be able, through its interventions at city level. identify potential regulatory or enabling environment issues that are blockers to moving forward climate resilient development in Somaliland.

Major lessons and recommendations for the year ahead

Major Lessons:
Flexibility is essential in a volatile aid and political context. The reduction of UK ODA from 0.5% to 0.3% of GNI created uncertainty, affecting planning and engagement. Sinaan’s adoption of a modular, hybrid implementation approach—balancing structured diagnostics with visible, quick-win projects proved effective in sustaining momentum under shifting funding and political landscapes.
Political economy engagement yields results. Federal-state tensions around city selection (notably MoIFAR’s concern over exclusion) highlighted the importance of political inclusivity. By ensuring strong political economy analysis, stakeholder management and in particular adding Dhusamareb as an additional city, which balances clan dynamics, Sinaan secured federal endorsement and maintained balance across regions.
Working across Somalia and Somaliland. Sinaan is one of the few programmes in the UK Somalia portfolio that is implementing across Somalia and Somaliland. This has meant getting to grips with different government systems, and different levels of responsibility between national and city level, as these vary. This has not necessarily been straight forward, and the programme has had to learn how to approach this with some initial missteps that have now been overcome. Additionally working in Puntland has also meant working with a different set of regulations and laws than some other Somali parts. The team need to continue navigating this carefully whilst also seeking to foster learning across all the cities despite the political challenges that may exist.
Managing expectations is critical for credibility. Mayors and municipal teams expected immediate project rollouts, especially after USAID’s withdrawal. Sinaan learned to balance these pressures by sequencing interventions: fast-tracking consultations and quick wins while transparently communicating longer timelines for feasibility studies and PPP structuring.
Partnerships and coordination prevent duplication. Somalia’s urban sector has overlapping donor programmes (World Bank SURP-II, UN-Habitat, IOM Danwadaag). By re-activating the Somali Cities Initiative and engaging in systematic mapping, Sinaan identified complementarities and opportunities for joint pipelines, reducing duplication.
Capacity gaps remain a bottleneck. Municipalities and line ministries often lack institutional frameworks and skilled staff to absorb technical assistance. Planned capacity needs assessments were pivotal in shaping training and institutional strengthening.
Need to focus on self-revenue-generating projects. A critical lesson emerging from early project development is that the lack of predictable capital expenditure severely limits municipalities’ ability to plan and implement infrastructure projects at scale. Therefore, a strategic focus on revenue-generating and green growth projects will prove to be far more impactful. Investments that both enhance climate resilience and create sustainable revenue streams allow municipalities to finance operations, reinvest in infrastructure, and reduce dependency on external aid.

Recommendations:
Accelerate delivery of quick wins. Move beyond diagnostics to implement small-scale, visible projects (e.g. nature-based solution (NbS) pilots, SWM interventions, solar mini-grids) in 2025-26 to build trust with communities and demonstrate early results.
Strengthen PSCs and Somali Cities Initiative. Formalise and operationalise the Programme Steering Committees in Somalia and Somaliland, ensuring Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) (Mogadishu) and Ministry of Urban Development and Local Government (MoUD&LG) (Hargeisa) lead strategic oversight. Use the Somali Cities Initiative, co-chaired by FCDO and WB, for peer learning, scaling, and donor alignment.
Integrate financing strategies early and communicate how private sector can support climate investments. Advance PPP structuring and blended finance approaches in parallel with feasibility studies to crowd in private and climate finance. This will help position Sinaan as a co-financing platform rather than a standalone bilateral programme and also advance dialogue and demonstration projects with the private sector that revenue generating climate projects are viable.
Deepen federal-municipal linkages and share learning on how to operate at the sub-national level. Continue leveraging political economy analysis (PEA) to manage federal-state dynamics and ensure that city investments remain inclusive across FMS, particularly in historically underserved regions like South-west and Galmudug. Alongside this share learning with the rest of the UK Somalia network on operating at a sub-national level and how to deliver more locally led development.
Institutionalise capacity building. Translate upcoming capacity assessments into tailored municipal and ministerial training programmes linked directly to project pipelines (e.g., PPP contracting, climate screening, financial management).
Municipal finance. Through the initial scoping visits with cities, managing municipal finances and local taxation has come up repeatedly. This should be an area for further exploration in the coming year as it delivers on the British Embassy Mogadishu’s focus on supporting self-financing of the state.
Communicate progress proactively. Develop and disseminate evidence-based communication products (learning briefs, results stories, PSC updates) to demonstrate early impact to FCDO, HMG, Somali stakeholders, and communities, critical for sustaining confidence amid shrinking aid budgets.
Plan for international engagement – World Urban Forum 2026. The team should start planning for representation at the next WUF – the UN’s bi-yearly conference bringing together urban development stakeholders to showcase best practice in urban development. This is important to demonstrate to other partners internationally how to support urban climate resilient economic development in an FCAS context. The team will need to work alongside UN counterparts to plan this and ensure strong Somali representation – both from Mayors and private sector.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the Programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme continues to be on track to meet intended outcomes and impact and the evidence set out in the business case underpinning the identified interventions and projected outcomes still holds. The programme remains one of the key climate programmes for the UK’s Somalia support alongside supporting the objectives of self-sustainability of the state, at a sub-national level including mobilising finance. The Theory of Change sets out how the programme seeks to achieve this.

The Theory of Change (ToC) was refined to position Sinaan as a vehicle to catalyse transformational change in Somalia’s urban sector by enabling municipal governments, communities, and private sector actors to co-create inclusive, climate-resilient development pathways. It aims to demonstrate how UK Aid can drive inclusive, climate-smart urban transformations by piloting scalable models and investing in resilient infrastructure and ecosystem services.

The ToC assumes that:
IF Sinaan takes a systems-based approach to improve government decision-making, processes, and capacities in urban development at different levels (Federal Member State, district, and city), it can enhance urban planning, land use control, investment decisions, minimise conflict, and increase resilience to climate change.
AND attract new, coordinated finance for green infrastructure and ecosystem projects from development partners, international finance institutions (IFIs), the private sector and other relevant stakeholders in target cities.
THEN Somalia's cities will transition from crisis-driven to becoming more inclusive and resilient. They will be able to cope with rapid urbanisation and climate shocks, harness green growth opportunities that contribute to poverty reduction, and build longer-term resilience.
Change pathways identified in the ToC include:
- Enabling capacities: Building municipal technical, financial, and planning capabilities for urban development.
- Delivery and buy in for green growth activities: Engagement with stakeholders to generate programme support and test, learn and refine approach to build pathways to scale, and to strengthen sustainability.
- Mobilising inclusive Green Infrastructure Finance / co-financing: Securing public, private, and climate finance through bankable project pipelines and investment partnerships.
- Social Value Delivery: Mainstreaming gender equality, youth empowerment, and IDP inclusion into programme design and infrastructure delivery.
Cross-cutting this ToC are Value for Money (VfM), Transparency and International Climate Finance (ICF) metrics, ensuring the Programme not only delivers results but does so accountably, equitably, and in alignment with global climate and social inclusion commitments.

Theory of Change

To deliver this ambition the theory of change (ToC) identifies the need to work systematically across different levels of governance – federal, city and district – but in particular strengthening municipal capacity, to form improved systems of decision making which will consider from the outset long term plans for investment and inclusive economic growth. Alongside focusing on mobilising finance and identifying private sector actors to develop partnerships for service delivery.

Working at a city level requires working with mayors but also national government stakeholders, private sector and informal and formal groups, including ensuring strong engagement with women led organisations and businesses, responding to the complexity of how Somali cities function across sectors, service delivery, vulnerable groups, political lines and administrative boundaries.

The programme’s early actions in the implementation phase have illustrated that the assumptions in the ToC of needing to work in this way across multiple actors and levels of government is key. The programme has had to navigate early on the dynamics between federal, state and municipal level whilst also working to build consensus with the municipalities, community groups and the private sector.

The governance arrangements of the programme therefore have to support navigating these dynamics, with programme steering committees in place for both Somalia and Somaliland, that provide strategic oversight, co-chaired by the SRO and DG or Minister of the relevant line Ministry. For Somalia this is MoIFAR and for Somaliland it is the Ministry of Urban Development and Local Government. The PSC brings together all levels of government, FGS, FMS and the Mayors as well as being open to having other international partners, and other relevant line ministries take part. Reporting into the PSC are the TWGs that are established with each municipality and chaired by the relevant FMS ministry, this grouping in particular is to support building capacity and embedding the programme in municipal structures. Running alongside this are specific community climate action hubs which draw together issues of conflict, inclusion and climate and bring in underrepresented voices and different community groups. These different structures do not operate separately but interact with each other to build a holistic approach to bringing together different stakeholders and to ensure buy in for implementation on the ground. This approach seeks to ensure support for perhaps more bottom-up approaches to delivery but does ensure top down directives and frameworks are utilised and adhered to.

Therefore, Sinaan is supporting municipal structures and building local government capacity, the intended consequence of this is not to replace other local structures but to strengthen those that have direct accountability to local people. The ToC, at present, focuses more on the dynamics between FGS and FMS with cities but as the programme moves forward bringing out how the programme is interacting at the city level with local groups and local clan structures will be needed. An important learning from this programme in the coming year will be to map how it is navigating these dynamics and taking an approach that builds forums for consensus making.

The programme has adapted to generate both transactional gains, quick wins that build trust, visibility, and momentum, and transformational change, which requires deeper institutional reform and long-term investment. This speaks to the pathways of change identified above, supporting both capacities whilst also getting buy in to the importance of climate resilient green growth investments, both of which can take time.

As the programme was partly paused during inception as internal decisions were made on the future portfolio of Somalia UK Aid programming, there was some delay in refining the ToC further. The programme team will be working with the SMP programme after the AR to run a ToC workshop to further test this ToC. Please see MEL section for further details.

Describe where the Programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
Where the Programme is On Track
Outcome 1: Urban Planning, Land Use, and Investment Decisions: Sinaan is on track in establishing solid foundations for improved urban planning across Somalia and Somaliland cities. City diagnostics and consultations have been completed in all priority municipalities, namely, Baidoa, Dhusamareb, Bossaso, Burco, Wajaale, Garowe, and the Benadir Regional Authority (BRA), with validation secured at federal, regional, and state levels. The establishment of Programme Steering Committees (PSCs) in Somalia and Somaliland has created a governance framework that strengthens alignment between municipal investment decisions and national priorities, while also embedding accountability.
Building on this foundation, the Programme is advancing the preparation of City Investment Plans (CIP), structured around a clear Table of Contents that includes city profiles, strategic goals, investment priorities, funding strategies, project portfolios, and implementation frameworks. Sinaan will pilot CIPs in Baidoa and Bossaso, as they already have relatively recent city spatial or strategic plans developed by the Semeyanta Programme, which can be updated and built upon. Based on the success of the CIP pilot, Dhusamareb and Wajaale will follow, where no major initiatives have yet been undertaken.
Outcome 2: Pipeline of Bankable, Climate-Resilient Projects: Early-stage pre-feasibility and design work has been completed to implement a range of transactional projects between October 2025 and March 2026. They are:
1. Integrated Solid Waste Management in Burao, Garowe,
2. Nature bases solutions and ecosystem restoration Burao, Wajaale, Gabiley and Hargeisa corridor,
3. Improvement in municipal resource mobilisation in Burao,
4. Development of a public park for women and children and a city nursery in Garowe,
5. Urban regeneration and flood management of the Gerbooda Waterfall Project in Baidoa,
6. Waterfront development and mangrove afforestation with tree nursery in Bossaso,
7. Rehabilitation of the meat market for women traders in Dhusamareb
8. Municipal renewable energy generation in Wajaale and Dhusamareb
Detailed feasibility studies and pilot designs are underway for the following transformational projects:
1. City-wide energy demand assessment and design of a pilot in Burao and Baidoa.
2. Mangrove afforestation project in Bossaso.
3. Improvement of water supply in Wajaale
4. Feasibility study for SEZ in Wajaale.
This reflects good progress towards building a pipeline of bankable projects that combine service delivery with fiscal sustainability.
Outcome 3: Mobilisation of Finance: Progress under Outcome 3 demonstrates strong traction in positioning Sinaan as a platform for unlocking blended and private capital for climate-resilient urban infrastructure. Building on the Programme’s strategic focus on revenue-generating projects, private sector financing solutions are being advanced for the purchase and installation of solar-powered equipment, particularly where reliable revenue streams can support extended purchase agreements or loan repayments. Finn Church Aid (FCA) Investments is designing a financing product that channels funds to microfinance institutions, enabling them to provide microloans to households and small businesses investing in solar-powered appliances. In parallel, FCA Investments will also capitalise solar equipment suppliers, allowing them to extend credit for higher-value solar generation equipment and productive-use technologies.
At a larger scale, local banks and Shuraako Capital have signalled readiness to lend to businesses purchasing solar generation equipment, ranging from small-scale systems to very large installations. This emerging ecosystem of financing partners, including Shuraako Capital, FCA Investments, local commercial banks, and international impact investors creates a robust foundation for scaling investment in renewable energy and related infrastructure. Importantly, risk mitigation instruments are also being explored through the Multilateral Investment Guarantees Agency (MIGA), the African Guarantee Fund (AGF), and the African Trade and Investment Development Insurance (ATIDI), which can de-risk private sector participation and crowd in new financing.

Where the Programme is Off Track:
Institutional Capacity Gaps. Many municipalities and line ministries continue to face significant absorptive capacity constraints, limiting their ability to implement large-scale infrastructure projects or manage complex PPP arrangements. While comprehensive capacity needs assessments are only scheduled for late 2025, this means institutional strengthening is trailing behind project design. To overcome this challenge, Sinaan has proactively embedded capacity-building components into its delivery process at the project level. The establishment of Municipal Technical Working Groups (MTWGs) is a crucial step, enabling learning-by-doing, adaptation, and the preservation of institutional memory among municipal staff, ensuring that skills and knowledge are extended beyond individual projects.
Donor Coordination Risks. Despite progress achieved through the Somali Cities Initiative, the risk of duplication with other ongoing urban programmes (e.g., World Bank SURP-II, UN-Habitat, IOM Danwadaag) persists. To mitigate this, Sinaan is actively strengthening coordination mechanisms through joint consultations, investment pipeline mapping, and PSC oversight to ensure complementarity, leverage co-financing opportunities, and avoid overlapping interventions.

Planned Actions for the Year Ahead:
Accelerating quick-win implementation. Sinaan intends to advance the delivery of visible pilots in 2025-26, including nature-based solutions, small-scale solar energy projects, and solid waste management interventions. These will provide tangible early results, build confidence with municipalities and communities, and help manage expectations by demonstrating that the Programme is moving from planning to implementation.
Operationalising the PSCs to strengthen programme governance. FCDO intends to launch the programme in Mogadishu in November 2025 formally. However, the Programme Steering Committees (PSCs) have already been established with the first meeting scheduled in October-November in Mogadishu and Hargeisa. The PSC will ensure that they provide strategic oversight, accountability, and alignment with federal and state-level ministerial priorities. The Somali Cities Initiative will be leveraged as a peer-learning platform to drive municipal reforms, share lessons, and support the scaling of successful pilots across cities.
Rolling out capacity assessments and training. Sinaan will complete and act on capacity needs assessments across municipalities and line ministries, starting in November 2025. Based on the findings of the ongoing capacity assessment, tailored training modules will be developed in areas such as PPP contract management, financial systems, and climate screening. Embedding training within the delivery of pilots will strengthen institutional readiness and ensure learning is retained.
Co-design Clinics established to embed inclusion and conflict sensitivity. To ensure the programme is considering inclusion and issues of conflict into how projects are developed co-design clinics will be implemented as participatory and iterative processes, rather than one-off consultative events. These clinics will serve as platforms where communities and municipal teams will jointly shape the design of projects from inception to finalisation. Each co-design cycle will begin with pre-design focus group discussions to capture local priorities, cultural preferences, and user needs that inform the initial concept development. This will be followed by interactive visual design sessions involving women, youth, and internally displaced persons (IDPs).
Strengthening MEL and communications. Over the next year, Sinaan will enhance its Monitoring, Evaluation, and Learning (MEL) systems to capture and track triple nexus outcomes, namely, climate resilience, gender and social inclusion, and peacebuilding. New digital tools for project identification, prioritisation, risk monitoring, and implementation progress tracking will support this. These tools, being developed with technical assistance, will include an automated scoring system for project prioritisation, a real-time online risk monitoring platform, and a traffic-light reporting tool for implementation progress.
On the communications side, Sinaan will prioritise proactive storytelling and outreach to demonstrate results and maintain stakeholder confidence. Planned actions include:
1. Producing a general Sinaan video (3-5 minutes) to introduce the Programme’s vision, approach, and early impact.
2. Once Project Identification Documents (PIDs) are finalised, develop baseline videos for selected projects, capturing stakeholder perspectives through interviews. Planned coverage in the pilot stage includes: Burao waste management, Garowe waste management, Baidoa Gerbooda waterfall, and Dhusamareb meat market for women traders.
3. Launching a weekly newsletter to share partners’ contextual updatesalongside Sinaan updates.
4. Development of the Sinaan website, serving as the central platform for sharing reports, updates, and knowledge products with Somali stakeholders, FCDO, HMG, and development partners.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
There are a number of factors – internal to the UK government’s approach to UK aid - that have impacted the delivery of the Sinaan programme this year and affect how it will proceed in the coming year. The first is the cut in funding for UK aid and also wider cuts in aid across the humanitarian and development sector. Secondly in response to the changing funding landscape and the need to consider how to deliver development differently, in the Somalia context the UK is moving to a portfolio programme approach to delivering development which allows more flexibility in delivering interventions. Thirdly strategic priorities have been set for the UK’s development support in Somalia; the UK will continue support to Somalia through a broad humanitarian focus with climate and migration being key areas we will deliver on. These factors have been discussed in the summary section above.
Over the last year FCDO has had to consider the future of the programme given these factors as well as its role in supporting Somali priorities and it’s fit within the wider country portfolio. It has been agreed that Sinaan should continue as it is well placed to deliver on both UK and Somalia government priorities to address climate change and also facilitate private sector investment. Furthermore, Sinaan will be able to provide forums for consensus building that help drive locally led development, supporting the UK’s objectives in finding opportunities for state building from the bottom up. It is important to recognise that Sinaan is not delivering business as usual but has adapted to these changing priorities and the constraints on funding accordingly. The key factors and issues that FCDO has considered when making the judgement on Sinaan continuing are set out below.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Enable Capacities: Stakeholders have increased capability to respond to plan for urban growth and adapt effectively to climate risks and impacts
Output number:		1	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
1.1 Change in knowledge and skills of municipal authorities to develop, implement and manage sustainable urban development of people and organisations, supported by TA (across disaggregation)	Municipality implementation readiness checklists provide a baseline assessment of where each municipality is on a capacity scale (e.g. screening at the municipal level of people, systems, processes, incentives and so on) to inform bespoke TA for each municipality. / Once carried out the baseline will be used to update this milestone. / 1 day training with thematic experts (SWM, NbS) on project structuring, contracting and monitoring 20 participants (prioritising relevant women)	A – met expectations / Readiness checklists have been developed for each city to assess capacity and inform future technical assistance. / 2 Trainings have been delivered on solid waste management and nature-based solutions.
1.2 Number of tools, assessments, planning exercises and mapping developed by municipal authorities to understand conflict, gender, and climate contexts	4 municipalities develop tools, conduct assessments, planning and mapping exercises to understand conflict, gender, and climate contexts	A – met expectations / Specific tools that have been developed including a project monitoring tool which encompasses gender, climate and conflict issues as part of project identification in 4 municipalities.
1.3 Number and quality of strategic investment plans for target cities developed by municipalities	Pilot City Investment Plans developed, and projects identified	A – met expectations / City investment plans developed for two cities and climate resilient infrastructure and green growth projects identified across the cities.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Across all three indicators the output scores an A.
Indicator 1.1 - The Programme has progressed beyond planning to operationalisation, finalising the assessment tool, securing mayoral endorsement for TWGs, and scheduling assessments within a tight timeframe. This milestone is a progress milestone towards deploying capacity assessments at this stage – its focus was the development, review, and refinement of a comprehensive capacity assessment tool, which will be deployed across selected municipalities to systematically identify institutional and technical gaps. This tool is designed to assess readiness in areas such as governance, service delivery, financial management, and climate resilience, ensuring that forthcoming technical assistance (TA) is tailored to the specific needs of people and organisations within local governments.
The actual assessments and training modules will be rolled out between October and December 2025. The groundwork ensures that capacity building will be targeted, inclusive, and sustainable. Assessments at federal level and at regional level will be conducted in parallel to ensure alignment between municipal and federal/state capacity building interventions.
Solid Waste Management trainings involving municipal stakeholders and the private sector have taken place in Burao and Garowe. TWG sensitisation workshops on NbS were also delivered where it’s been identified as a knowledge gap for most cities.
Additional to this a list of additional sensitisation and training modules will be developed based on the culmination of the training needs assessment proposed in October

Indicator 1.2 - Tools have been successfully developed and aligned with Sinaan’s strategic frameworks, and institutional mechanisms (TWGs, PSCs) are in place for rollout.
While application at municipal level is scheduled in the coming months, the readiness to deploy a set of tools across at least four municipalities demonstrates strong progress towards the milestone and positions the Programme to deliver results that are scalable, inclusive, and sustainable. These tools seek to embed conflict sensitivity, gender equality, and climate resilience into municipal planning and investment decisions. Central to this was the development of an Excel-based automated project prioritisation tool, designed to help municipalities review and refine long lists of potential projects against agreed criteria such as climate resilience, VfM, gender inclusion, private sector leverage, and political feasibility. Training sessions are planned with Municipal Technical Working Groups (MTWGs) and Sinaan staff to ensure effective use of the tool, supported by a step-by-step user manual for replication and sustainability.
Complementing this, an online platform for real-time risk monitoring is being piloted, integrating key risk categories (political, fiduciary, safeguarding, security, climate/environmental) in line with FCDO frameworks. Dashboards will provide the Programme Steering Committees (PSCs) and FCDO with up-to-date reporting and accountability. In parallel, a progress monitoring tool is being designed to track milestones, budgets, safeguards, and outputs, supported by traffic-light reporting to give early warnings of delays or cost overruns. Training for municipal focal points will ensure that data entry and interpretation remain embedded within local institutions.

Indicator 1.3 – The team has moved quickly to identify potential projects. During the review period, Sinaan successfully identified and prioritised projects that will form the backbone of the forthcoming City Investment Plans (CIPs). Extensive diagnostics, municipal consultations, and validation at federal and state levels were conducted in Baidoa, Dhusamareb, Bossaso, Burao, Wajaale, and the Benadir Regional Authority. These processes confirmed priority investments across renewable energy, water and sanitation, solid waste management, urban markets, ecosystem restoration and regeneration. The CIP covers city profiles, strategic goals, investment priorities, funding strategies, project portfolios, and implementation frameworks.
The Programme has begun piloting CIPs in Baidoa and Bossaso, where relatively recent city plans exist and can be updated. These pilots serve as test cases for refining the CIP methodology before replication in cities such as Dhusamareb and Wajaale, where no major planning initiatives have been undertaken. The piloting process ensures that the plans are not only technically robust and bankable but also responsive to municipal realities, providing space for institutional learning and adaptation. By embedding Climate Resilience, GESI, and Conflict Sensitivity strategies into the CIP design, Sinaan ensures that each plan reflects the Programme’s triple nexus approach. The piloted CIPs in Baidoa and Bossaso demonstrate practical progress toward full plan development and provide a replicable model for scaling.
The next phase will consolidate identified projects into formalised CIPs, enabling municipalities to mobilise finance, coordinate donors, and deliver climate-resilient infrastructure with greater ownership and sustainability.
Progress has also been advanced through the integration of Sinaan’s three cross-cutting strategies. They are the Climate Resilience Strategy, the Gender Equality and Social Inclusion (GESI) Strategy, and the Conflict Sensitivity Strategy. Together, these strategies provide a triple nexus framework, ensuring that municipal planning processes not only strengthen resilience to climate shocks but also address systemic gender and social inequalities, while embedding a “do no harm” approach to conflict. By situating tool development within this strategic framework, the Programme ensures that municipalities are equipped with practical instruments to understand and act on conflict, gender, and climate dynamics in their planning and investment decisions.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There are currently no major changes to this output given programme started in July this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This is the first annual review for the programme since the close of the inception period in June 2025. There are no key lessons or recommendations for this output, at this stage.

Output Title	Identification and facilitation of donors, diaspora, private sector actors, investors etc. in support of programme objectives
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR.

Indicator(s)	Milestone(s) for this review	Progress
2.1 Depth and breadth of engagement and buy-in from potential partners and public / private investors for financing and programme delivery	Stakeholder mapping completed and document developed with targeted stakeholder approach / All four cities soft launch undertaken and additional engagements in Mogadishu, Garowe, and Hargeisa with range of stakeholders	A - met expectations. / Extensive stakeholder engagement has taken place across all the cities and launches. This has included adding an additional city – Dhusamareb to the list of cities.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
This output scores an A. After 4 months there is good political, municipal, donor, and private sector buy-in, coupled with tools for pipeline screening and PPP readiness, demonstrates that the Programme is well-positioned to translate engagement into committed finance and delivery partnerships in the coming year.
Since the start of implementation in July 2025, Sinaan has prioritised stakeholder mapping and structured engagement, explicitly identifying public and private actors critical for financing and delivery. A key milestone was achieved through the completion of stakeholder mapping and development of a targeted engagement strategy, which has guided outreach across federal, state, municipal, and private sector stakeholders. High-level political support has been secured through kick-off meetings with the Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR), regional administrations including the Ministry of Urban Development and Local Government (MoUD&LG) in Somaliland and the Ministry of Planning, Economic Development and International Cooperation (MoPEDIC) in Puntland, as well as senior ministers across the Federal Member States. These engagements have established a strong political anchor for programme delivery and reinforced alignment with national and subnational priorities. Furthermore, the team met with the Presidents of Puntland and Galmudug States securing buy in for the programme at the highest levels.
Through this early political engagement, the team was able to ascertain MoIFAR’s concerns about the selection of cities and work with them to understand their issues and address them. This in particular has meant considering clan dynamics and in particular the location of cities, ensuring a balance across clans is maintained. There has been some challenge on this but the programme has constantly reviewed these dynamics and through flexibility in programme design an additional city was added – Dhusamareb in Galmudug State which provides a stronger balance across Somalia, in particular with clan dynamics. Before adding this additional city the team also consulted with other partners to understand where they were working to avoid duplication, ability to operate in the city and municipal capacity.
This understanding of clan dynamics will remain key to the programme not just in relation to where it works but the variety of stakeholders engaging in the programme, including the private sector. The programme deployed two political economy analysis assessments to support city selection and a key learning from this process has been the need to keep this updated and live. This will become more critical as the programme seeks to potentially expand city selection, if strong results are delivered by March 2026.
At the technical level, a project screening checklist was developed to assess bankability and PPP readiness, ensuring that projects in the pipeline are structured to attract external financing and align with ICF KPI 12. In parallel, Sinaan initiated soft launches in all five priority cities, complemented by additional engagement in Mogadishu, Garowe, and Hargeisa with municipal leaders, civil society, private operators, and financiers. These consultations have built early buy-in while managing expectations in a fragmented donor landscape.
Importantly, the Programme has revitalised the Somali Cities Initiative as a coordination platform co-chaired by FCDO and the WB, to reduce duplication with existing programmes such as the World Bank’s SURP-II, while maximising complementarities and co-financing opportunities.
Indicator 2.2 - Number and type of public and private sector partnership models/ collaborations secured – this will be reviewed in March next year as the programme is only just starting project development, therefore assessment of building private sector collaborations will need more time to be developed.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There are currently no major changes to this output given programme started in July this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This is the first annual review for the programme since the close of the inception period in June 2025. There are no key lessons or recommendations for this output, at this stage.

Output Title	A pipeline of inclusive, climate resilient bankable projects and transformative initiatives with credible funding proposals developed by public and private actors to attract finance and foster partnerships.
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR.

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of scoping and funding proposal developed in each city by public and / or private actors in the pipeline of ‘investible' projects to attract finance and foster partnerships (Delivery KPI Outcome Ind 2.2 and 2.3)	Development of Investment Briefs and Pitch Decks	A – met expectations / A long list of potential projects has been scoped across both smaller scale investments and longer-term projects.
3.2 Number of community climate action hubs meeting objectives as outlined in plans (for climate training, women's economic collectives, conflict mediation etc.) with evidence of them feeding into investments.	Technical Working Group has established ToRs for the climate action hubs in 2 cities	A – met expectations / ToRs for 2 climate action hubs have been developed for 2 cities.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
This output scores an A. Indicator 3.1 – the Programme has progressed well beyond concept development. By combining more transactional quick win small projects with potential transformational projects identified.
Sinaan is also progressing well in one of its key deliverables – developing a credible pipeline of projects and has also initiated financial structuring discussions. This positions the Programme not only to attract investment but also to demonstrate how blended finance and partnerships can be mobilised to deliver inclusive, climate-resilient urban infrastructure in Somalia.
Sinaan has made substantial progress in establishing a pipeline of scoped and investible projects and translating them into Investment Briefs and Pitch Decks for financiers and development partners. Early-stage pre-feasibility and design work has been completed for a set of transactional projects scheduled for implementation between Oct 2025 and March 2026, including: (i) Integrated Solid Waste Management in Burao and Garowe; (ii) dual nurseries for greening along the Burao–Wajaale–Gabiley–Hargeisa corridor; (iii) municipal revenue mobilisation improvements in Burao; (iv) development of a public park for women and children and a city nursery in Garowe; (v) urban regeneration of the Gerbooda Waterfall in Baidoa; (vi) waterfront development and city nursery in Bossaso; (vii) rehabilitation of the Dhusamareb meat market for women traders; and (viii) renewable energy generation pilots in Wajaale and Dhusamareb.
At the same time, detailed feasibility studies and pilot designs are underway for projects that will form the next generation of large-scale investments: (i) city-wide energy demand assessments and design of pilots in Burao and Baidoa; (ii) mangrove afforestation in Bossaso; (iii) improved water supply systems in Wajaale; and (iv) a feasibility study for a Special Economic Zone (SEZ) in Wajaale. These initiatives are supported by early engagement with financing partners such as Shuraako Capital, FCA Investments, local banks, international impact investors, and risk mitigators including MIGA, AGF, and ATIDI.
Indicator 3.2 - Progress was made in laying the foundations for Community Climate Action Hubs as locally driven platforms for resilience, inclusion, and peacebuilding. A key milestone was the development of Terms of Reference (ToRs) for the hubs in two pilot cities (Burao, Baidoa), facilitated by the Municipal Technical Working Groups (TWGs). These ToRs establish the mandate of the hubs as focal points for climate training, women’s economic collectives, and conflict mediation initiatives, with an explicit link to municipal investment planning. The next stage will focus on operationalising activities within the hubs and documenting how this feed into the Programme’s investment pipeline, thereby linking community action to systemic urban resilience.
The process has been participatory, involving municipal leaders, civil society representatives, and women’s groups to ensure that hubs are not only technically relevant but also socially inclusive. By embedding the hubs within the TWG structure, the Programme ensures that community-level perspectives can feed directly into project identification and design, including renewable energy, waste management, and market rehabilitation pilots. This approach enhances ownership, accountability, and sustainability, while aligning local priorities with Sinaan’s broader outcomes on climate resilience, gender equality, and conflict sensitivity.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There are currently no major changes to this output given programme started in July this year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This is the first annual review for the programme since the close of the inception period in June 2025. There are no key lessons or recommendations for this output, at this stage.

Output Title	Evidence produced to test, learn and provide proof of concept for scale, and to strengthen programme delivery, adaptation and sustainability.
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR.

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number and impact of targeted evidence and learning products generated for influencing, demonstration effect or programme adaptation (Delivery KPI Outcome Ind 3.1 and 3.2)	Documentation of baseline situation of Sinaan cities (videography and spatial assessment)	A – met expectations / Baseline documentation of situations on the ground in each city has been completed.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
The output scores an A. Progress has been made in developing baseline evidence products. A key milestone has been the initiation of documentation of the baseline situation across Sinaan cities. This has included the design and commissioning of videography products to capture lived realities of urban communities, as well as the roll-out of a GIS-based spatial assessment to provide robust evidence on land use, infrastructure gaps, and climate vulnerability.
A key purpose of developing evidence and learning products is firstly to support influencing and demonstration effect by presenting complex technical findings in formats that are accessible to decision-makers at municipal, federal, and donor levels. Second, they provide a strong foundation for programme adaptation, ensuring that transactional quick-win projects and longer-term transformational initiatives are grounded in accurate and locally validated data.
Although full completion of the baseline documentation is ongoing, early outputs are already shaping programme delivery. Videography products are being used to strengthen community engagement and visibility, while spatial data layers are directly informing feasibility studies and investment strategies. The combination of visual, narrative, and technical evidence has not only enhanced the Programme’s legitimacy but also demonstrated early value-for-money and positioned Sinaan as a convening platform for evidence-based urban resilience planning in Somalia.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There are currently no major changes to this output given programme started in July this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This is the first annual review for the programme since the close of the inception period in June 2025. There are no key lessons or recommendations for this output, at this stage.

Output Title	People with improved access to climate-resilient urban infrastructure and services – World Bank programme
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR.	Revised down from 30% to take account of Sinaan activities starting

Indicator(s)	Milestone(s) for this review	Progress
5.1 Urban roads rehabilitated or upgraded, including drainage (Kilometres) / 5.2 / Pavements constructed (Kilometres)	37km / 37km	A – expectations met / The projected km roads were constructed across the major Somali cities. / A – expectations met / The projected km pavements were constructed across the major Somali cities.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
This output scores an A. The delivery of this output is through £9.1 million of CDEL to the World Bank’s US$195 million urban resilience “Nagaad Project” in Somalia via the Multi Partnership Fund vehicle (MPF) for the Somalia Urban Resilience Project (SURP-II).

The purpose of the SURP-II is to deliver sustainable urban infrastructure and development in Somalia, working in particular at municipal level. SURP-II comprises four components designed to strengthen resilience and governance in key cities. It supports participatory decision-making processes to identify key urban investments that advance urban resilience in six strategically important cities across five FMS and the Benadir Regional Administration (BRA). These include the cities of Mogadishu (BRA), Garowe (Puntland State), Baidoa (Southwest State), Kismayo (Jubbaland State), Dhusamareb (Galmudug State), and Beledweyne (Hirshabelle State). The UK contribution through CDEL funds to SURP-II is directly funding climate resilient infrastructure projects.

This year marked the final disbursement of UK funding to the SURP-II programme with a target to spend all funds by March 2025. There was a slight delay to spend due to considerable security constraints during the Ramadhan period in Somalia which saw an increase in conflict and therefore inhibited access and progress on construction. Despite this the WB have been able to spend all funds and delivered roads and drainage across Kismayo, Garowe, and Baidoa.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
There were no changes to this output in the last year. Our funding to the WB’s SURP II programme came to an end this year and there are no further plans to fund work under the programme. Instead, an important partnership has been developed between the WB, FCDO and the Sinaan programme.
The Sinaan team and the WB SURP team are working closely together to share potential projects for future financing, sharing feasibility and design work where there is the possibility to leverage each other’s investments and technical assistance. This will be particularly important in cities where there is some overlap – Baidoa, Garowe and Hargeisa. In particular in Somaliland the Sinaan team has greater flexibility as to where it works and given the WB is starting work in Hargeisa decided to focus on other cities where the WB currently is unbale to extend financing too. Through this approach the Sinaan team can lay foundational work and develop projects that the WB could pick up with their larger investment funds at a later date. This approach is also helping where Sinaan can pick up support to cities that are currently outside the scope of the SURP II programme in Somalia such as Bossaso.
The Sinaan and FCDO teams are often invited to take part in WB urban and climate infrastructure planning events and learnings. This year this has included contributing to the co-design of an urban climate resilience planning training programme which will be rolled out to all cities and being invited to take part in the WB’s Mayor Forum which brings together the SURP II cities.
This close co-ordination and collaboration with the WB team is critical as part of wider work to engage with the WB’s investments in Somalia and to enhance the impact of the Sinaan and SURP II activities.
To note the WB and FCDO co-chair the Somali Cities Initiative which Sinaan provides the secretariat function to. This provides a platform for bringing together donors and other partners to share learning and present projects for supporting climate resilient and inclusive urban development in Somalia. This is a key way for both the WB and FCDO to illustrate joint leadership in this sector.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
A lesson learned from the support to the WB is the importance of sharing learning from how the WB established their project with the cities and have built capacity. This will be important for the Sinaan programme to learn from in the coming year as it builds out its capacity work and starts implementing projects with the cities.
## D: VALUE FOR MONEY (1 page)
The Programme's approach to Value for Money (VfM) is integrated into its strategic and operational design, moving beyond financial compliance to actively drive efficiency and maximise impact. In the inception period, the Programme team developed a VfM strategy that utilises the ' 5 E's' framework— Economy, Efficiency, Effectiveness, Cost-Effectiveness, and Equity —to systematically measure and enhance performance. This approach to VfM is operationalised through the Adaptive Management principles embedded in the Monitoring, Evaluation, and Learning (MEL) system.
Although, it is still early into programme implementation to provide evidence and examples against all metrics, Sinaan is optimising efficiency, a critical component of its Value for Money (VfM) framework, by combining internal performance (staff/budget control) with external risk mitigation (security planning) to ensure high throughput of expected deliverables.
Operational efficiency has been achieved through:
1.     Optimising staff and financial resources: The Programme is ensuring that inputs are maximally converted into outputs by deploying highly skilled personnel including short term technical experts (STTAs) to fill in staffing gaps and continuously quality checking their expected outputs. This is reinforced by streamlining work plans and budgets and proactively addressing variances in spending and delivery, ensuring that human and financial resources are used to their maximum potential.
2.     Tracking and mitigating cost drivers: The Programme is actively tracking and responding to potential efficiency losses resulting primarily from high procurement costs associated with flight bookings and field missions. For instance, the Programme has negotiated a long-term arrangement with travel agents to minimise cost of flight changes due to issues like change in visa regulations and availability of government counterparts for consultation. To maintain fiscal efficiency (Economy and Efficiency), staff are explicitly encouraged to plan missions in good time and combine missions whenever possible to leverage better value on security charges. This demonstrates a practical, procedural focus on reducing unnecessary overhead.
3.     Proactively managing risk: The Programme has hired a local security manager to manage security risk and conduct risk assessment closer to the context. This has minimised inefficient spending on security risks that can potentially halt or complicate field activities. The security manager supports staff through scenario planning that help them navigate potential security threats. This risk-aware approach ensures that operational activities continue with minimal disruption, thereby preserving financial efficiency and preventing sunk costs or delays caused by unexpected security issues. Also, the Programme has floated a request for proposals for security services at city level through a competitive tendering process. This will facilitate simultaneous advancement of project support in each city.
The Programme is deploying the VfM framework by formally integrating its principles into its overarching Monitoring, Evaluation, and Learning (MEL) system. This is done through structured tracking of the '5 E's'- Economy (cost of inputs), Efficiency (inputs to outputs), Effectiveness and Cost Effectiveness (outputs to outcomes relative to total cost incurred), and Equity (fair distribution of benefits). This provides a comprehensive methodology for tracking performance.
The Programme is designed to treat its pilot projects as "development experiments," where VfM data is not just reported, but used to trigger immediate course corrections. This linkage is critical for operating in Somalia's fluid context. For instance, Efficiency analysis, which tracks how well inputs are converted to outputs, will be used in quarterly reviews to identify why there are project delays or high procurement costs. The results of this analysis will inform targeted actions, such as adjusting work plans or strengthening technical assistance (TA) support for municipalities. By utilising VfM data as the foundation for learning, Sinaan will ensure continuous improvement, making every pound spent more impactful.
E: RISK [½ to 1 page]

Overview of risk management

The Sinaan programme currently holds an overall risk rating of “major”, with all residual risks remaining largely within the Somalia Network’s defined risk appetite.

Sinaan continues to demonstrate a mature and responsive approach to risk management, effectively navigating a range of strategic, operational, and contextual risks. The risk of early programme termination relating to FCDO’s resourcing limitations poses a significant challenge. Other major risks – such as contextual volatility, delivery in fragile contexts, and reputational concerns – are being addressed through adaptive programming, strong partner engagement, and robust oversight mechanisms.

The programme risk management framework is sound, supporting continued delivery in complex environments. Since Sinaan moved from mobilisation to implementation in June 2025, risk management has been integrated into monthly governance processes. FCDO and DT Global continue to maintain regular engagement to identify and address emerging risks, supported by regional steering committees for in-country escalation and mitigation.

FCDO also maintains a comprehensive risk register covering contractual, financial, and political risks. The Sinaan risk register on Aid Management Platform (AMP) was last updated in October 2025. The most significant challenge has been underspend, driven by delayed programme approval and optimistic timelines. To mitigate this, FCDO and DT Global conduct monthly budget and forecast reviews to ensure accurate financial planning and delivery

Key risks and mitigation measures in place are highlighted in the table below:

Risk Description	Mitigation Strategy	Residual Risk
Policy & Programme Delivery: / Uncertainty in terms of availability of resources to finance the implementation of agreed outputs. / Budget confirmation delays, / CDEL funding limitation in outer years / Impact of UK Somalia strategy review outcome may delay and/or jeopardises the delivery of key elements of Sinaan.	Engage with internal prioritisation, planning, and budgeting processes. / Closely track spending and watch the budget ensuring programming ambitions are matched with available resources. / Consider phased implementation and resource optimisation strategies to enhance efficiency and scalability. / Design programmes with sustainability in mind, including capacity building and institutional strengthening. / Identify and develop exit strategies that allow for seamless transition or integration into ongoing initiatives by other development partners. / Engage potential partners early to explore co-financing, technical support, or programme assimilation opportunities.	Major
Strategy & Context: / Political stalemate, acute insecurity, and delayed political transition in some FMS undermine delivery and impact. These included high tensions related to the Ethiopia-Somaliland MoU issue and between the Federal Government and Federal Member States, especially Jubaland, given disputes around elections and were likely to worsen.	Frequent PEA and security updates. DT Global to inform FCDO/SRO of any significant change in context and discuss implications for Sinaan strategy or HMG campaign goals. / Ensure the best possible response to strategic challenges mobilising the full technical and diplomatic capability of the mission.	Major
Strategy & Context / Increasing insecurity, unrest/conflict and terrorism spreads, destabilising hitherto stable areas. / Increased AS activity including in Mogadishu, security architecture and intensifying risk of security vacuum (AUSSOM funding) and clan conflicts reduce access for Sinaan partners and inhibiting delivery particularly south west and central south Somalia regions.	DT Global/FCDO to undertake activities (stakeholders’ and /community engagements) to influence dialogue, understanding and shared incentives among the districts/local government/municipalities , Federal Member States(FMS) and national/federal government.	Major
Financial & Fiduciary: / Fiduciary irregularities leading diversion of programme funds or misuse of FCDO funding for unintended purposes.	FCDO to review and assess exposure to fiduciary risks at all levels of the delivery chain. / FCDO to ensure the implementing partner (DT Global) establishes strong governance and internal control mechanisms. / Review DT Global’s financial management and anti-fraud procedures. / Regular monitoring, including spot-checks. Use of third-party monitoring and verification services provided by FCDO’s cross-office Somali Monitoring programme (SMP). / Payment upon receipt of services. Ensure all suspicions of irregularity are reported and promptly escalated to internal control.	Moderate
Policy & Programme Delivery: / Political interference in the selection of cities and prioritisation of investments.	FCDO/DT Global to maintain open and regular contact with key political players at national and local level – including early identification of key political stakeholders. / Adopt a transparent and objective criteria for selection of cities and investments. / Set up governance mechanisms (decision-making and advisory boards) necessary for the effective oversight of the programme. Ensure political representation in decision-making.	Moderate
Safeguarding: / FCDO interventions raise safeguarding concerns around potential to harm beneficiaries, staff and implementing partners personnel resulting in ethical violations and reputational damage.	There were no reported cases regarding safeguarding. / FCDO will regularly monitor and ensure that Sinaan implementing partners adhere to the safeguarding standards in concordance with FCDO’s “zero tolerance” policy on safeguarding. / Delivery partners must be made aware of and adhere to the safeguarding principles. / DT Global has established a Programme Security Plan (PSP), tailored to the Somalia/Somaliland context. This includes detailed Standard Operating Procedures (SOPs) for travel, communication, field site operations, and incident management. / Environmental safeguarding policies are in place, with the publication of environmental performance reports done regularly. / Safeguarding against sexual exploitation, abuse, and harassment, policies are in place and DT Global is monitoring organisational adherence to the policy.	Moderate

Update on Partnership Principles
The FCDO does not provide direct development assistance to the Somali authorities. However, SInaan implementation will remain consistent with the British Embassy’s assessment and guidance on government engagement.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance of partners and FCDO:

The Sinaan Programme, a five-year initiative valued at £25 million (running from 6 January 2025 to 31 July 2030), successfully transitioned from its inception phase (Jan–June 2025) to the implementation phase during this review period, having met all agreed inception milestones.

Implemented by DT Global under the Global Development Delivery Framework (GDD), the inception phase was marked by strong collaboration between DT Global and FCDO, including weekly coordination meetings and co-development of reporting mechanisms. Funds were disbursed in line with milestone schedules. Communication outputs—such as PowerPoint presentations and the final inception report—were delivered on time and met FCDO’s quality expectations.

By July 2025, the programme commenced implementation activities, transitioning from diagnostic work to consolidated investment planning. Five primary cities were formally selected for intervention: Baidoa, Dhusamareb, Bossaso, Burao, and Wajaale, based on criteria including vulnerability, readiness, and alignment with green growth objectives.

By 30 September 2025, eleven Project Information Documents (PIDs) had been co-created by municipal authorities and the Sinaan Implementation Team across the five cities and Garowe. These PIDs now serve as the basis for procurement preparation and early implementation.

Despite ongoing challenges posed by reductions in Official Development Assistance (ODA), the programme has maintained momentum. This resilience is attributed to strong financial forecasting, close coordination between FCDO and DT Global, and the flexible nature of the programme’s delivery mechanism.

FCDO also continues to maintain a collaborative relationship with the World Bank under the Somalia Urban Resilience Project – Phase II (SURP II). Regular meetings and participation in the Nairobi monitoring mission have strengthened coordination. The World Bank’s inclusive approach and strong linkages with Somali government officials have enabled FCDO to engage effectively with ministerial and municipal stakeholders, as well as other MPF donors. The Bank’s country team continues to provide essential oversight and capacity support to ensure successful project delivery.

Financial Performance:

The £25 million Sinaan budget is spread over five years (January 2025 – July 2030) as detailed in the approved business case. In July 2025, Sinaan successfully transitioned from its inception phase (January–June 2025) to full implementation, having met all agreed milestones. With this shift, the programme moved from diagnostic assessments to consolidated investment planning.

Initial delays in contract signing, due to internal reviews of the Somalia portfolio and reduced UK ODA commitments, impacted the programme’s timeline - with the extension of the original 6-month inception phase window to March 2027. Despite these challenges, Sinaan has mobilized rapidly, adapted to contextual constraints, and realigned strategically with evolving priorities.

As of October 2025, £1.24m - 26% of Sinaan’s allocated budget - had been spent. The table below summarizes Sinaan’s financial position:

Budget Category	Forecast / FY2025/26 (£)	Actual Spend / (£)	Spend (%)
3000797- 401 Urban Planning and Green infrastructure
CDEL (ICF)	1,897,944	35,881	2%
RDEL (ICF)	2,821,858	1,200,716	43%
TOTAL	£4,719,802	£1,236,597	26%

DT Global has demonstrated strong flexibility by aligning its budget with FCDO’s annual allocations and ODA availability, planning activities in close consultation with the FCDO programme team.
The organization maintains robust financial systems that uphold high standards of donor fund management and ensure transparent tracking of commitments. Monthly budget and forecast reviews between FCDO and DT Global strengthen financial planning and delivery, providing assurance of accountability and compliance.

Between July and September 2025, Sinaan intensified efforts to mobilize private and climate finance, partnering with FCA Investments and Shuraako Capital to design blended-finance structures for renewable energy pilots in Dhusamareb and Wajaale. These initiatives aim to unlock sustainable investment and accelerate the transition to clean energy in Somalia.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

The Monitoring, Evaluation, and Learning (MEL) Strategy has been developed to ensure accountability and drive continuous learning focusing on data collection, management, and analysis to inform programmatic decisions. It will use a combination of quantitative and qualitative data to capture evidence and will include independent reviews at key milestones.
The MEL system is fundamentally designed around the principle of Adaptive Management. It will move beyond simply tracking outputs to critically analysing why certain outcomes are (or are not) being achieved. This is particularly crucial given Somalia's fluid and rapidly evolving operating context. Learning is institutionalised through deliberate activities such as quarterly learning events, after-action reviews for major activities, and an annual portfolio review that informs course corrections for the upcoming year. This ensures that field-level experiences and pilot project results are immediately fed back into the Programme, allowing the programme to quickly recalibrate its approach—a necessary function of the new "blended strategy" that combines structured diagnostics with opportunistic engagements.
A major focus of the Year 1 MEL plan is data collection for baselining and ensuring Data Quality and Integrity. Given the challenges in collecting reliable data in fragile and remote settings, the strategy includes stringent verification processes. The MEL Manager and Thematic Leads will perform a Quality Assurance function, actively cross-checking and triangulating evidence from different sources. This will include deploying a combination of remote monitoring techniques, targeted field visits (security permitting) for on-ground implementation verification, and the use of third-party validation exercises. Furthermore, capacity building is prioritised: training and mentorship will be provided to local data originators and implementing partners to enhance their data collection skills and promote the use of simple, user-friendly technology solutions for consistent data capture. This proactive approach aims to mitigate security, political instability, and data integrity risks, all of which are critical concerns in the operating environment.
As mentioned in the Theory of Change section, given the pause in activities and changing timelines for delivery the Sinaan team need to further refine the ToC and log frame. It has been agreed that the SMP team will work with the Sinaan MEL team to do this after the AR process has been completed. This is especially important as the original plan was to have a separate MEL contractor sense check and provide oversight to the MEL work, but it was no longer possible to contract an independent MEL team due to funding cuts.
Digital and AI application
The Sinaan team are also considering opportunities for the use of digital technology and AI within programme delivery and to also help collect data and improve learning. In particular the team are exploring explore how Sinaan interventions can monitor carbon credits while simultaneously transforming the data into actionable intelligence. For example, looking to integrate digital dashboards that link emission reductions and energy-use efficiency across our portfolio cities.

In addition, Sinaan are using satellite and drone imagery surveys for land and physical assessments that inform project design, covering topography, hydrology, and floodplain mapping to improve the accuracy of site planning and engineering layouts.

Finally, the programme exploring the use of AI-enabled sensors to monitor solar energy production, waste collection volumes, and maintenance performance.

Date of last narrative financial report	Sinaan (October 2025)	Date of last audited annual statement

Annex 1: Progress Update on Recommendations from Previous Sinaan annual review report (November 2024)

The table below summarises progress made against recommendations from the November 2024 Sinaan Annual Review report.

Recommendation	Progress
Sinaan programme will require focused linkages with the rest of the BEM economic development portfolio and the HHEART team to ensure it is delivering resilient development which incorporates long term needs of women and girls, IDPs and takes account of climate risks and future financing	The Sinaan programme has made strong linkages with the urban resilience programme in the HHEART team’s portfolio – Danwaadag, joining up on potential projects in Baidoa where both programmes operate.
Agree a set of success criteria during the inception phase (working with the MEL contractor), to assess the programme’s ability to scale up and bring together aspects of FCDO Somalia’s economic development portfolio. This will incorporate ongoing assessment of the economic and security context, the agreed break points in the contract, at the end of the inception phase, and the mid-term review to be delivered by the MEL team at the three-year point.	The MEL contract was not taken forward and changes in UK aid funding meant the programme is no longer looking to scale up and take on other aspects of the economic development portfolio. However, the Sinaan team have a MEL framework in place, and this will be refined to reflect its role in the emerging economic development portfolio and how it is mobilising finance and supporting revenue generation,
Review changes to the pollical, economic and security situation across Somalia to ensure delivery in proposed cities is viable and adjust plans accordingly.	Sinaan undertakes continual assessments of the political, economic and security situation and this has informed the cities chosen for the programme and operations.
DT Global/FCDO to work with partners during Sinaan’s inception phase to develop a governance structure with the right representation and level of oversight of the programme that includes all key stakeholders.	A governance structure has been established with Programme Steering Committees for Somalia and Somaliland and Technical Working Groups at municipal level. Climate Action Hubs are in the process of being set up which will draw in community groups as well as municipal staff to work collaboratively.
FCDO/DT Global should continue to build awareness around the programme’s aims and objectives with other donors, such as Denmark, Norway and the World Bank, who have similar urban infrastructure programmes to ensure effective join up.	FDCO and Sinaan have worked well to connect with other donors – in particular working closely with the WB – and connecting with donors working in similar locations such as Sweden in Somaliland.
Sourcing for a Sinaan programme MEL supplier must be completed in a thorough and timely manner given the range of the supplier’s range of responsibilities (such as revising and finalising the current draft log frame, theory of change, developing an overall monitoring and learning plan, the ICF indicators and the Value for Money (VFM) strategy and approach) in the inception phase.	Due to cuts in UK Aid the MEL contract was not taken forward. Instead, FCDO has sought support from the SMP programme to provide extra review and challenge on Sinaan’s MEL approach.
Draw up a set of options for alternative delivery of the objectives of Sinaan if the contract for the implementing partner is not approved. There is potential that due to the internal review of the future of the Somalia portfolio that the programme does not move ahead. Therefore, a set of options should be developed in anticipation for this scenario. Options could include increasing financing through the World Bank, combining this with delivery through centrally managed programmes and/or moving into a purely knowledge development and thought leadership role without direct delivery.	This is no longer applicable as the programme was approved and is now in implementation.

Annex 2: Acronyms

AGF	African Guarantee Fund
AI Artificial Intelligence
AMP	Aid Management Platform
AR	Annual Review
ATIDI African Trade and Investment Development Insurance
AR	Annual Review
ATMIS	African Union Transition Mission in Somalia
BC	Business Case
BEM	British Embassy Mogadishu
BRA	Benadir Regional Administration
BRICS	Building Resilient Communities in Somalia Programme
CDEL	Capital Expenditure
CIP City Investment Plan
DG Director General
FCA	Finn Church Aid
FCDO	Foreign Commonwealth and Development Office
FGS Federal Government of Somalia
FMS	Federal Member State
FY	Financial Year
GDD	Global Development Delivery Framework
GESI	Gender Equality and Social Inclusion
GIS	Geographic Information Systems (GIS)
GUG	Green Urban Growth (now called Sinaan)
ICF	International Climate Finance
IDA	International Development Association (IDA)
IFIs	International Finance Institutions
ICF	International Climate Finance
IOM International Organization for Migration
KPIs	Key Performance Indicators
IP	Implementing Partner
ICF	International Climate Finance
MDBS	Multilateral Development Banks
MEL	Monitoring, Evaluation, Learning
MIGA Multilateral Investment Guarantee Agency
MoIFAR	Ministry of Interior, Federal Affairs and Reconciliation
MoPEDIC	Ministry of Planning, Economic Development and International Cooperation
MoUD&LG	Ministry of Urban Development and Local Government
MTWGs Municipal Technical Working Groups
NbS Nature Based Solution
NDC National Determined Contributions
ODA	Official Development Assistance
PEA	Political Economy Analysis
PIDs	Project Identification Documents
PPP Public Private Partnership
PSC	Programme Steering Committee
PSP Programme Security Plan
PRO	Programme Responsible Owner
RDEL	Resource Expenditure
SEZ	Special Economic Zones
SMP Somalia Monitoring Programme
SOPs	Standard Operating Procedures
SRO	Senior Responsible Owner
SSC-K	Sool, Sanaag and Cayn - Khatumo
STTA	Short-Term Technical Assistance
SURP	Somalia Urban Resilience Project
SWM	Solid Waste Management
TA	Technical Assistance
ToRs	Terms of Reference
TOC	Theory of Change
UK	United Kingdom
UN	United Nation
VfM	Value for Money
WB	The World Bank
WUF World Urban Forum