## Updated TOC
PROJECT NAME | Evidence for Health (E4H) Federal, Khyber Pakhtunkhwa, and Punjab
Date revised: 20/06/2024

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, i.e. is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality e.g. use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets disaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed i.e. consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Logical Framework
PROJECT NAME | Evidence for Health (E4H) Federal, Khyber Pakhtunkhwa, and Punjab
Date revised: 18/04/2025
IMPACT | Impact Indicator 1 |  | Baseline (2019) | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumptions | Definitions | Computation method for MMR and U5MR annual targets |  | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - November 2026)
Reduced burden of illness and preventable deaths among poor and vulnerable populations, particularly women and children | Maternal mortality ratio (MMR) | Planned | Pakistan: 186 KP: 165 Punjab: 157 | Pakistan: 144 KP: 124 Punjab: 118 | Pakistan: 133 KP: 115 Punjab: 110 | Pakistan: 123 KP: 108 Punjab: 102 | Pakistan: 112 KP: 100 Punjab: 95 | Pakistan: 112 KP: 100 Punjab: 95 | Reduction assumption derived using Pakistan's 2030 target from its National Health Indicators and Targets (Endorsed by the Inter-Ministerial H&P Strategic Forum on 4 April 2018) at the national level. Pakistan-level rate of decrease applied to obtain KP and Punjab estimates. For computation method, see column M. Log frame assumes E4H will only have a contributory effect on targets. Achieving milestone targets will be dependent on the full health sector ecosystem in Pakistan (both public and private sectors), especially the service delivery environment. | The maternal mortality ratio (MMR) is defined as the number of maternal deaths during a given time period per 100,000 live births during the same time period. |  | Baseline | Updated baseline (2023) | Milestone 2 | Milestone 3 | Milestone 4 | Target, Y5 | 2030 goal* | Annual expected reduction (2019-2030 target) | % decrease per year
|  | Achieved |  |  | Pakistan: 155 (UN interagency estimate for 2023) MMR data at the provincial level is not available. | Pakistan: 155 (UN interagency estimate for 2023) MMR data at the provincial level is not available. |  |  |  |  | MMR (PMMS) | 186 | 143.8182 | 133.2727 | 122.7273 | 112.1818 | 101.6364 | 70 | 10.5455 | 6.9%
|  |  | Source | [7 empty] | KP | 165 | 123.9 | 115.3509 | 107.3917 | 99.9817 | 93.0829
|  |  | Baseline: Pakistan Maternal Mortality Survey 2019, national, KP, and Punjab, for the three years preceding the survey Milestone data source: subsequent Pakistan Maternal Mortality Survey OR Pakistan Demographic & Health Survey, which are expected every 4-6 years. If only one survey follows the 2017-2018 PDHS, MMR values will be interpolated for intervening years OR reports and data produced by UN Maternal Mortality Estimation Inter-Agency Group (WHO, UNICEF, UNFPA, World Bank, UNDESA/Population Division) will be utilised. | [7 empty] | Punjab | 157 | 117.9 | 109.7649 | 102.1911 | 95.1399 | 88.5753
| Impact Indicator 2 |  | Baseline (2017/2018) | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Reduction assumption derived using Pakistan's 2030 target from National Health Indicators and Targets (Endorsed by the Inter-Ministerial H&P Strategic Forum on 4 April 2018). Pakistan-level rate of decrease applied to obtain KP and Punjab estimates. For computation method, see column M. Log frame assumes E4H will only have a contributory effect on targets. Achieving milestone targets will be dependent on the full health sector ecosystem in Pakistan (both public and private sectors), especially the service delivery environment. | The number of children who die by the age of 5 years, per 1000 live births. | U5MR (PDHS) | 74 | 58.32 | 54.4 | 50.48 | 46.56 | 42.64 | 25 | 3.92 | 6.6%
| Under-five mortality rate (<U5MR) | Planned | Pakistan: 74 KP: 64 Punjab: 85 | Pakistan: 58 KP: 48 Punjab: 64 | Pakistan: 54 KP: 45 Punjab: 60 | Pakistan: 51 KP: 42 Punjab: 56 | Pakistan: 47 KP: 39 Punjab: 52 | Pakistan: 47 KP: 39 Punjab: 52 |  |  | KP | 64 | 48.2 | 45.0188 | 42.0476 | 39.2724 | 36.6804
|  | Achieved |  |  | Pakistan: 58.5 (UN interagency estimate for 2023) U5MR: is not available at the provincial level. | Pakistan: 56 (UN interagency estimate for 2024) U5MR: is not available at the provincial level |  |  |  |  | Punjab | 85 | 64.1 | 59.8694 | 55.918 | 52.2274 | 48.7804
Source
|  |  | Baseline: Pakistan Demographic and Health Survey 2017-2018, national, for the five years preceding the survey. Rate for KP and Punjab is that of 10 years period preceding survey (no 5 year period estimates available) Milestone data source: subsequent Pakistan Demographic & Health Survey, which are expected every 4-6 years. If only one survey follows the 2017-2018 PDHS, U5MR values will be interpolated for intervening years OR reports and data produced by the UN Inter-Agency Group for Child Mortality Estimation | [7 empty] | *2030 goal derived from National Health Indicators and Targets (Endorsed by the Inter-Ministerial H&P Strategic Forum on 4 April 2018)
| Impact Indicator 3 |  | Baseline (2021) | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Decrease assumption calculated using IHME data for Pakistan for the period 2010-2019. The average annual decline was computed. This decrease was applied for each milestone year. Pakistan-level rate of decrease applied to obtain KP and Punjab estimates. For computation method, see column M. Log frame assumes E4H will only have a contributory effect on targets. Achieving milestone targets will be dependent on the full health sector ecosystem in Pakistan (both public and private sectors), especially the service delivery environment. | The disability-adjusted life year (DALY) is a time-based measure that combines years of life lost due to premature mortality (YLLs) and years of life lost due to time lived in states of less than full health, or years of healthy life lost due to disability (YLDs). One DALY represents the loss of the equivalent of one year of full health. The DALY rate is expressed per 100,000 population. | Computation method prevalence of communicable diseases |  |  |  | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - November 2026)
| Prevalence of communicable disease (per 100,000) | Planned | Pakistan: 22,564 KP: 21,895 Punjab: 22,939 | Pakistan: 20,624 KP: 20,545 Punjab: 21,525 | Pakistan: 19,978 KP: 19,902 Punjab: 20,851 | Pakistan: 19,331 KP: 19,279 Punjab: 20,199 (These targets were calculated using a broader group of diseases (communicable, maternal, neonatal, and nutrition). However, the indicator requires only communicable diseases to be considered, which is why the target appear high. | Pakistan: 18,685 KP: 18,676 19,566 | Pakistan: 18,685 KP: 18,676 19,566 |  |  |  | 2010 | 2015 | Baseline (2021) | Updated baseline (2023) | Milestone 2 | Milestone 3 | Milestone 4 | Target, Y5 | Annual reduction (2010-2019) | % decrease per year
|  | Achieved |  |  |  | DALYS (Communicable diseases) Pakistan: 6,569 KP: 6,208 Punjab: 6,304 (These results are based only on communicable diseases) |  |  |  |  | Prevalence rate attributed to communicable diseases (HIV/AIDS and sexually transmitted infections; Respiratory infections and tuberculosis; Enteric infections; Neglected tropical diseases and malaria; Other infectious diseases) | 29675.84 | 25164.79 | 22564 | 20624.4073 | 19977.8764 | 19331.3455 | 18684.8145 | 18038.2836 | 646.5309 | 3.13%
|  |  | Source | [7 empty] | KP |  |  | 21895 | 20545 | 19901.9415 | 19279.0107 | 18675.5777 | 18091.0321
|  |  | Baseline: Institute for Health Metrics and Evaluation, Global Burdens of Disease 2021. Prevalence for communicable causes, with maternal and neonatal causes and nutritional deficiencies removed so that the indicator is truly focused on communicable disease. Milestone data source: Institute for Health Metrics and Evaluation, Global Burden of Disease for Pakistan. Milestone 3, YR3: The gap between targets and results is mainly because they were calculated using different data. The targets used a wider set of diseases (communicable, maternal, neonatal, and nutrition), while the results only include communicable diseases, so they cannot be directly compared. | [7 empty] | Punjab |  |  | 22939 | 21525 | 20851.2675 | 20198.6228 | 19566.4059 | 18953.9774
OUTCOME | Outcome Indicator 1 |  | Baseline (2023) | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumptions | Definitions | Computation method for annual targets for IHR CC Index |  |  | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - November 2026)
Improved health sector resilience and responsiveness to emerging disease threats and other shocks (e.g., climate change events) & Improved coverage, equity, quality, and efficiency of healthcare services | International Health Regulations (IHR) Core Capacity Index Score (%) | Planned | Pakistan: 42.7% KP: 40.4% Punjab: 43.2% | NA | Pakistan: 49% KP: 46% Punjab: 49% | Pakistan: 54% KP: 52% Punjab: 55% | Pakistan: 60% KP: 57.7% Punjab: 60.5% | Pakistan: 60% KP: 57.7% Punjab: 60.5% | Change assumptions: The national target for IHR is derived from DCP3 five-year coverage targets for the year 2026/"Towards UHC through PHC: Pakistan Investment Case for 2021-2026". This national target value is treated as a Milestone for Y4 of the programme. To obtain annual milestones, we interpolated between the 2023 and 2026 target value. The KP and Punjab-specific target is currently not available. In the absence of KP-specific targets, annual milestones were derived by applying the Federal %-pt expected increase per year to the KP baseline value. Y1 will have no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation. | International Health Regulations Core Capacity Index is the average percentage (%) of attributes of 13 core capacities that have been attained at a specific point in time. The 13 core capacities are: (1) National legislation, policy and financing; (2) Coordination and National Focal Point communications; (3) Surveillance; (4) Response; (5) Preparedness; (6) Risk communication; (7) Human resources; (8) Laboratory; (9) Points of entry; (10) Zoonotic events; (11) Food safety; (12) Chemical events; (13) Radio nuclear emergencies. |  | Baseline 2023 |  | Milestone 2 | Milestone 3 | Milestone 4 | Target, Y5 | 2026 goal* | Annual expected increase
|  | Achieved |  |  | Pakistan:42.7% KP:40.4 % Punjab:43.2 % | Pakistan: 47.83% (15 core capacities) KP: 43.0% Punjab: 55.6% Pakistan: 48.21% (19 core capacities) KP: 43.2% Punjab: 46.7% |  |  |  |  | National | 42.7 |  | 48.4667 | 54.2333 | 60 | 65.7667 | 60 | 5.7667
|  |  | Source | [7 empty] | KP | 40.4 |  | 46.1667 | 51.9333 | 57.7 | 63.4667
|  |  | Baseline: 2023 Joint External Evaluation of the IHR Core Capacities of the Islamic Republic of Pakistan. Score for core 15 capacities. NAPHSII has been completed and provincial scored have been derived from NAPHSII. Milestone data source: Following the completion of Pakistan's 2023 JEE, the milestones will be sourced from the subsequent National Action Plan on Health Security. Data will be sourced annually through IHR Technical Committees. Milestone data source (YR3): In 2025, the IHR monitoring report will be developed through a consultative process and using JEE internal assessment tool. Milestone data source (YR4): In 2026, IHR monitoring Report co-developed by IHR secretariat and NIH using JEE internal assessment tool. | [7 empty] | Punjab | 43.2 |  | 48.9667 | 54.7333 | 60.5 | 66.2667
| Outcome Indicator 2 |  | Baseline (2021) | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Change assumptions: The national target for the UHC SCI are derived from "Towards UHC through PHC: Pakistan Investment Case for 2021-2026"/DCP3 five-year coverage targets for the year 2026. To obtain annual milestones, we interpolated between the 2021 and 2026 target value The KP and Punjab-specific target is currently not available. In the absence of KP-specific targets, annual milestones were derived by applying the Federal %-pt expected increase per year to the KP and Punjab baseline values. Y1 will have no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation. | The Universal Health Coverage Service Coverage Index is a composite measure capturing progress toward the implementation of UHC. It is composed of individual indicator scores aggregated across four areas = (RMNCH • Infectious • NCD • Capacity). The IHR core capacity index is one part of the Capacity component of the UHC index. UHC scores are computed annually by the ministry at national, provincial, and district levels using the estimation approach described in the 2017 Global UHC Monitoring Report. The primary data sources used for indicators of service coverage include Pakistan Demographic & Health Survey (PDHS), Pakistan Social & Living Standards Measurement Surveys, Multiple Indicator Cluster Surveys, National and Provincial Bureau of statistics reports, JEE Report 2016 and WHO Global Monitoring Reports. | Computation method for annual targets for UHC SCI
| Universal Health Coverage Service Coverage Index Score | Planned | Pakistan: 52.0 KP: 49.8 Punjab: 53.8 | NA | Pakistan: 55.6 KP: 53.4 Punjab: 57.4 | Pakistan: 56.8 KP: 54.6 Punjab: 58.6 | Pakistan: 58 KP: 55.8 Punjab: 59.8 | Pakistan: 58 KP: 55.8 Punjab: 59.8 |  |  |  | Baseline 2021 | Updated baseline 2023 | Milestone 2 | Milestone 3 | Milestone 4 | Target, Y5 | 2026 goal* | Annual expected increase
|  | Achieved |  |  | Pakistan: 53.9 KP: 51.1 Punjab: 55.4 | Pakistan: 54.7% KP: 53.5% Punjab: 55.2% |  |  |  |  | National | 52.02 | 54.412 | 55.608 | 56.804 | 58 | 59.196 | 58 | 1.196
|  |  | Source | [7 empty] | KP | 49.82 | 52.212 | 53.408 | 54.604 | 55.8 | 56.996
|  |  | Baseline: UHC Index at District, Provincial & National Level. Milestone data source: Subsequent, annual MNHSR&C updates to the UHC Service Coverage Index, broken down by component informed by various sources Milestone data source (YR3): On the completion of NAPHS II in 2028, the next round of JEE will be carried out by the WHO, Government and other partners not only to monitor progress but also to make recommendations for future actions. Milestone data source (YR4): UHC Service Coverage Index (SCI) report 2026 will be developed. | [7 empty] | Punjab | 53.8 | 56.192 | 57.388 | 58.584 | 59.78 | 60.976
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
Strengthened integrated health security sub-systems | % of approved TAs that are delivered in accordance with the specified deliverables | Planned | 0% | Fed: TAs approved = 1 KP: TAs approved = 2 | Fed, KP, and Punjab: 95% | Fed, KP, and Punjab: 70% | Fed, KP, and Punjab: 80% |  | Y1 will have no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation. As a result, Y1 captures the minimum number of TAs that should be approved for the first year of implementation. Milestones assume that over time, more aspects related to TA delivery will be under the direct control of the programme (e.g., political turbulence related to 2024 elections will subside etc.), hence performance against approved TAs will improve. Milestone 3, Y3: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs. Milestone 4, Y4: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs.
|  | Achieved |  | Fed: 2 TA mini projects approved (NAPHS, Framework of Action for Climate Resilient Health System) KP: 2 TA mini projects approved (Provincial action plan on HS, Workshops on climate resilient health systems) | Fed = Achieved (100%) KP = Achieved (100%) Punjab = Achieved (100%) | Overall = 97% Fed = Met (95%) KP = Met (100%) Punjab = Met (95%)
Source
E4H programme reporting/M&E The indicator has been calculated based on the percentage of completion of deliverables, taking into account three key performance dimensions: adherence to timelines, compliance with quality standards, and achievement of agreed deliverables according to the TORs of TAs.
| Output Indicator 1.2 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| Priority IHR governance reforms advanced (policy, plans, legal frameworks, monitoring and evaluation frameworks, financial management, accountability) | Planned | JEE 2023 in-process, with planned update/revision of NAPHS (II) KP: Public Health Act 2017 exists Punjab: Infectious Diseases and Control Act 2020 | Fed: NA KP: NA Punjab: NA | Fed, KP & Punjab: NAPHS II with provincial chapters developed and approved by the Inter-Ministerial Health and Population Council Fed, KP & Punjab: In-depth review of IHR-related legislations completed (200 legislations) | Federal: The annual IHR monitoring report developed and finalised through Embedded E4H TA. MOV: Approval by M/o NHSR&C and Dissemination to Stakeholders: Evidence of use of the report includes activation of IHR Coordination KP: KP Public Health Act 2017 Revised. MOV: Revised law approved by the KP Department of Health Punjab: Punjab Infectious Disease Act 2020 Revised MOV: Revised law approved by the Punjab Health and Population Department | Federal: IHR Coordination Secretariat at NIH tracked NAPHS II activities. MOV: Quarterly NAPHS II implementation progress reports documenting the status of activities, including AMR-related actions, achievements, challenges, and follow-up actions. KP: Revised Public Health Act approved by DOH, vetted by the Law Department and submitted to the Cabinet for approval. MOV: Official documentation evidencing Law Department vetting. Punjab: Draft Public Health Security Act presented to the Health Minister. MOV: Presentation material, consultation and communication record, revised draft of the Public Health Security Act submitted to the Health Minister. | Successful implementation of NAPHS II components for which government received E4H support. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 3: Y3: political stability and continuation of senior leadership making timely decisions at Federal, KP and Punjab levels. Milestone 4: Y4: Strong institutional commitment exists for implementing NAPHS II priorities.
|  | Achieved |  |  | Federal: National Action Plan with provincial chapters approved by the Inter-Ministerial Health and Population Council. Federal, KP & Punjab: In- depth review of the IHR –related legislations completed. | Federal: The IHR Monitoring Report 2025 was developed, its completion was informed by a two‑day national consultation with IHR TWGs where One Health stakeholders validated progress across all 19 capacities. KP: The KP Public Health Act was endorsed by the DoH and submitted to the Law Department for legal review, feedback, and further approval. Punjab: The draft Punjab Health Security Act was submitted to the Minister of Health and Population Department (H&PD).
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
| Output Indicator 1.3 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| IHR coordination mechanisms established and operationalised | Planned | Fed: National IHR Task Force notified but not fully functional​​ Fed: 19 technical groups for JEE 2023 formed KP and Punjab: weak or non-existent provincial IHR coordination and decision-making mechanisms | Federal: NA KP: NA Punjab: NA | Federal: New National IHR coordination mechanism in alignment with NAPHS II developed and notified KP & Punjab: Provincial IHR coordination & decision-making mechanisms developed and notified | Federal: IHR coordination mechanisms functional (including the Steering Committee of the pandemic fund). MOV: Convening of the Steering Committee to improve effectiveness of the Pandemic Fund (25% of actions completed). KP: IHR coordination mechanisms are functional at the provincial level, with evidence of tracking the progress of implementing priority NAPHS II activities in KP. MOV: Minutes of the IHR coordination meeting in KP with implementation of a minimum of 25% actions agreed. Punjab: The IHR Technical Working Group/Taskforce is functional, with evidence of tracking progress of implementing priority NAPHS II activities in Punjab. MOV: Minutes of the IHR coordination meeting in Punjab with implementation of a minimum of 25% actions agreed. | Federal: Improved implementation of the Pandemic Fund activities through regularly convening and monitoring of the Pandemic fund coordination mechanism. MOV: Pandemic Fund TWG convened with action tracker to monitor implementation of the Annual Work Plan 2026–27. KP: *IHR coordination mechanisms strengthened and institutionalised in line with the revised Public Health Act, with AMR and other priority public health risks integrated. MOV: Government notifications, meeting records and action trackers evidencing strengthened coordination and integration of priority risks. Punjab: *Provincial IHR Taskforce formally continued and convened at least once to review, endorse and advance TWG recommendations and ensure sustainability. MOV: Documentation (minutes/action tracker) of Taskforce meeting held in Punjab with at least 50% recommendations of the TWG endorsed. | IHR coordination mechanisms are fully functional at the Federal level, in KP, and Punjab. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month).x Milestone 2, Y2: The 'functionality' of coordination mechanisms is intentionally covered under M3/Y3 in light of current constraints faced in getting mechanisms approved and notified. Full functionalisation, in this case, may not be possible until Y3. Milestone 3: Y3 IHR remains a priority for the government. Milestone 4: Y4 Continued prioritisation of IHR obligations in national and provincial agendas.
|  | Achieved |  |  | Federal, KP and Punjab: National and Provincial IHR coordination mechanism established and operationalised | Federal: The Pandemic Fund Steering Committee meeting was convened on 29 May 2025 with implementing partners, chaired by Mo NHSR&C. KP: IHR coordination mechanism meeting was held on 10 November 2025, the minutes documented the evidence of completion of actions. Punjab: The provincial IHR taskforce meeting was convened on 01 January 2026 which marked a key milestone in operationalising the provincial coordination mechanism and provided a platform for reviewing the status of IHR-related activities and identifying priority actions. The first TWG meeting was held in March 2026, where the members of the group highlighted progress on the sustainable and effective way forward for the coordination mechanism.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
40% | Enhanced capacities for IHR | Planned | Capacities prioritised by E4H: ​(a) Legal (4/10); ​(b) IHR Coordination (6/15); (c) HR (7/20)​; (d) Health Emergency Management (HEM) | Fed: NA KP: NA Punjab: NA | Federal: Development of Multi-sectoral Health workforce Strategy along with a robust M&E plan KP: Provincial HRH strategy enhanced with incorporation of surge response capacity, with implementation initiated Punjab: Provincial HRH strategy inception report developed and approved | Federal: Surge Capacity Training Design for Managers and Health Facility Staff at the district level to Enhance Pandemic Response and Preparedness at the district level. MOV: Training design approved by the M/o NHSR&C & shared with provinces; Later training to be mainstreamed, including commensurate government funding into the Sustainable Training Mechanism/ PHDC & DHDC in KP & Punjab. KP: At least one Simulation Exercise started for the training of trainers by the E4H teams in one District, with evidence of integration into the overarching Sustainable Training System for government ownership and funding. MOV: Training Report and IHR trainings are included in the Sustainable Training System plan. ​Punjab: At least one Simulation Exercise started by E4H-trained teams in one District, with evidence of integration into the overarching Sustainable Training System for government ownership and funding. MOV - Training Report and IHR trainings and advocacy plans for sustainability are included in the Sustainable Training System plan. | Federal: IHR monitoring function established within NIH through the IHR Secretariat to ensure continuity. MOV: IHR Monitoring snapshot co-developed by IHR Secretariat and NIH and hosted on knowledge management repository. KP: Khyber Medical University (KMU) faculty capacitated to deliver surge capacity training, with the module embedded in MPH and CPD programmes. MOV: ToT report, approved training materials, and KMU records confirming use of modules through MPH and CPD programmes. Punjab: Institutional capacity strengthened through at least two capacity-building workshops on IHR conducted for senior and mid-level managers in H&PD/DGHS. MOV: IHR capacity-building workshop reports, training materials, participant records, and H&PD endorsement letter. | Total score of prioritised competencies improved (TBD once capacities agreed with FCDO and TPM) | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 2, Y2 (Fed): Since the multi-sectoral health workforce strategy TA timeline spans six months, ending in Feb-2025, we are unable to include the term 'approval' in the milestone, as this would not come until the next year. Milestone 4, Y4 Capacity-building interventions are institutionalised within government systems.
|  | Achieved |  |  | Federal and KP: Multi-sectoral Health workforce Strategy along with a robust M&E plan developed. Punjab: Provincial HRH strategy inception report developed and approved. | Federal: A multisectoral surge capacity training package was developed and senior officials and technical experts were oriented through a national workshop held on 22 January 2026. The Provincial health departments will integrate the package into existing in-service and capacity-building programmes through PHDCs and DHDCs. KP: Simulation exercises for Cremean Congo Hemorrhagic Fever (CCHF) outbreak response were held in Peshawar from 29-31 December 2025. Punjab: A standardised simulation exercise package was developed, and exercises were conducted in Nankana Sahib and Muzaffargarh districts on Dengue and Monkeypox outbreak preparedness and response mechanisms.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumptions
Strengthened evidence-based decision-making practices | % of approved TAs that are delivered in accordance with the specified deliverables | Planned | 0% | Fed: TAs approved = 2 KP: TAs approved = 2 | Fed, KP, and Punjab: 95% | Fed, KP, and Punjab: 70% | Fed, KP, and Punjab: 80% |  | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestones assume that over time, more aspects related to TA delivery will be under the direct control of the programme (e.g., political turbulence related to 2024 elections will subside etc.), hence performance against approved TAs will improve. Milestone 3, Y3: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs. Milestone 4, Y4: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs.
|  | Achieved |  | Fed: 2 TA mini projects approved (MTR of NHV, Update to PSHF) KP: 2 TA mini projects approved (Health data governance mechanism, Policy brief for PHA) | Fed = Partially achieved (85%) KP = Partially Achieved (87%) Punjab= Achieved (100%) | Overall: 97% Fed = Exceeded (100%) KP = Exceeded (100%) Punjab = Exceeded (100%)
Source
E4H programme reporting/M&E The indicator has been calculated based on the percentage of completion of deliverables, taking into account three key performance dimensions: adherence to timelines, compliance with quality standards, and achievement of agreed deliverables according to the TORs of TAs.
| Output Indicator 2.2 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| Multisectoral and sectoral policies are evidence-informed and aligned to sub-sectoral strategies/plans | Planned | Fed: National Health Vision 2016-25 and National Action Plan 2018-23 under implementation​ KP​: KP Health Sector Strategic Plan (2019-2025) exists, but aligned district plans for implementation have not been developed Punjab: Punjab Health Sector Strategy (2019-2028) exists but needs alignment with the new developments in the province | Fed: NA KP: NA Punjab: NA | Federal: Mid-term review (MTR) of NHV 2016-25 completed and NHPP 2024-34 developed and approved​ KP: MTR of KP Health Sector Strategic Plan (HSSP) completed and revision of HSSP commenced ​ Punjab: Review of the Health Sector Strategy of Punjab (2019-2030) completed and endorsed | Federal: National Digital Health Hub for reporting was developed in collaboration with other development partners and provincial governments. MOV- Approval of the Unified Data Governance Framework approved by the M/o NHSR&C with consensus on institutionalisation in the data Centre/HPSIU. KP: District Health Office(s) restructuring initiated to enhance governance for strengthening Primary Healthcare and ensuring effective reform implementation MOV: Inception report endorsed by the Department of Health (DOH), KP Punjab: Punjab Health & Population Strategy 2025-34 developed through targeted TA from E4H. MOV: Draft Punjab Health & Population Strategy | Federal: The Pakistan Immunisation Sustainability and Transition Roadmap (PISTR) 2026–2035 developed to support local vaccine production by 2035. MOV: The costed PISTR roadmap submitted to M/o NHSR&C and DRAP for review and feedback, prior to its submission to the Prime Minister of Pakistan Office. KP: Restructured DHO Model with clear mandates, governance arrangements, financing/accountability mechanism presented to DGHS. MOV: Revised organogram presented to the DOH and agreement letter/minutes received. Punjab: Gender-responsive and safeguarding-informed governance framework for Nursing Centres of Excellence co-developed with the PIU. MOV: Draft governance framework aligned with ADB DLI-8A and submitted to the PIU. | PISTR document developed to support vaccine and financial self-reliance by 2035. Transition plan co-developed and endorsed by HSRU for effective and sustainable implementation and oversight of the GGRR. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestones 2, Y2 (Punjab): The development and approval of the new Health Sector Strategy for 2025-2035 is covered under YR 3. For Y2, the review will be completed, and the review report will be endorsed by the government. Milestone 4, YR4: Sustained government commitment to health sector reforms;
|  | Achieved |  |  | Federal:: Mid-Term review of NHV 2016-25 completed; findings and recommendations disseminated. KP: MTR of KP Health Sector Strategic Plan (HSSP) completed. Punjab: Review of Health Sector Strategy of Punjab completed. | Federal:: Data sharing agreement was presented at the IMH&PC and the UHC Country Platform meeting to establish a central platform for consolidating multiple health data streams into a unified national dashboard. KP: The restructuring of district helath office initiated. Punjab: The draft Health & Population Strategic Plan 2026-31 was submitted to the Minister of H&PD.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
| Output Indicator 2.3 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| Evidence on policy and programmatic reforms is generated, synthesized, and used to drive performance and accountability | Planned | Evidence-informed National Health Vision 2016-25 and provincial health sector policies and strategies are available/exist, and a reform towards PHC is needed. | Fed: NA KP: NA Punjab: NA | Federal:, KP, Punjab: at minimum two analytical documents (e.g., policy briefs, assessments) developed by geography with dissemination at high-level policy forums and evidence of use by government | Federal: Budget Analysis 2025/26 Brief and Burden of Disease Analysis Report at National and Provincial Levels. MOV: Analytical documents approved by the M/o NHSR&C KP: District health capacity on facility-level budgeting enhanced to improve PHC financing in at least one district. MOV: Notification of the facility level budgeting by the KP Finance Department. Punjab: Operational review of the Clinic on Wheels Initiative to inform scale-up supported by the E4H Programme. MOV: Operational Plan Recommendations on Clinic on Wheels endorsed by H&PD | Federal: UHC SCI estimation completed and institutionalised through coordination with the provincial health departments/HCCs and vertical Programmes. MOV: UHC Monitoring Report 2026 endorsed by the M/o NHSR&C and development partners, uploaded to the NDHH, capacity building materials and participant (M/o NHSR&C) records for UHC SCI estimation. KP: Facility-level budgets for all ten districts incorporated into the FY 2026–27 provincial budgets, informed by the FLB-EMP and supporting budget analysis. MOV: FY 2026–27 provincial budget book/budget documents showing incorporation of facility-level budgets for all ten districts. Punjab: Patient referral processes strengthened and digital information exchange between primary and secondary care improved through EMR–HMIS interoperability. MOV: Validated and H&PD/HISDU-endorsed Patient Referral Management SOPs, with evidence of adoption and EMR–HMIS interoperability. | Successful generation of evidence for government-led implementation of key priorities at the Federal and provincial levels. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 3: Y3: Availability of information from reliable surveys and health information systems. Milestone 4, Y4: Government stakeholders actively use analytical outputs (snapshots, briefs) for planning and decision-making.
|  | Achieved |  |  | Federal:: The findings of NHV MTR along with 9 policy briefs (2016-2025) have been developed and disseminated KP: 7 policy briefs developed and disseminated at high level policy forums based on CHVA and KP Health Foundation outsourcing evaluation. Punjab: 2 policy briefs developed: Provincial Health Accounts Policy Sehat Sahulat Sustainable Financing Model Policy | Federal:: The budget analysis snapshot was developed and endorsed by the Ministry. KP: Facility-level budget and expenditure management policy was piloted in Peshawar and subsequently scaled up to additional nine districts. Punjab: Through operational review of clinic on wheels, current operations were assessed to identify service gaps, and a geo-optimised deployment strategy was developed.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
20% | Strengthened holistic health sector coordination mechanisms at national, provincial, and district levels | Planned | The Federal UHC Health Sector Coordination Mechanism is functional. ​ Provincial and district UHC coordination and governance plans exist but have limited functionality in KP and Punjab. | Fed: NA KP: NA Punjab: NA | Federal: Minimum 1 meetings of Inter-Ministerial Health and Population Council​ KP: Health data governance mechanism established and functional, with evidence of data-driven decision-making initiated KP: Donor Coordination Mechanism established and operationalized Punjab: Donor Coordination Mechanism established and operationalized Punjab: Strategy for Health Data Information and Decision making developed | Federal: UHC Country Platform convened to endorse the Global Health Initiatives' Strategic findings and build consensus on future actions. MOV: Endorsed Global Health Initiatives Report by the UHC Country Platform. KP: The District Health and Population Management Team (DHPMT) is functional and strengthening PHC in at least one district by December 2025. MOV: Minutes of the DHPMT progress review meeting with evidence of implementation of prioritised actions for PHC​. Punjab: Institutionalisation of the Donor Coordination mechanism to focus on PHC strengthening with support of the UHC Delivery Unit embedded within the Health and Population Department. MOV: Regular Donor Coordination Sessions are convened, and the Portal is functional and updated. | Federal: Inter-ministerial coordination meeting on health and population reforms strengthened through the Council, with agreed PHC/UHC priorities and actions. MOV: Council-endorsed recommendations and actions on PHC/UHC reforms with assigned responsibilities, timelines, and follow-up on implementation progress. KP: EMR piloted in one district and presented to the DOH for scale-up, with institutionalisation through HISDU. MOV: EMR pilot report, EMR handover documentation to the Department of Health for scale-up, and HISDU documentation demonstrating institutionalisation of the EMR system. Punjab: *Partner coordination strengthened through at least one joint engagement with ADB, the World Bank or UN agencies, resulting in aligned PHC/UHC technical support. MOV: Joint engagement records and evidence of aligned and complementary technical assistance for Punjab’s PHC/UHC priorities. | National and Provincial health coordination mechanisms are fully functional (at least one inter-ministerial meetings held. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 3: Y3: Government and partners willing to share information for decision-making. Milestone 4, Y4: National and provincial coordination platforms remain functional and regularly convened.
|  | Achieved |  |  | Federal:: Two meetings of the Inter-Ministerial Health and Population Council were held. KP: Health data governance mechanism developed and operationalized. Donor and Development Partners Coordination Mechanism has been established and operationalized. Punjab: Donor Coordination Mechanism established and operationalized. Operational Roadmap and Conceptual Framework developed. | Federal:: A joint meeting of the IMH&PC and the UHC Country Platform was held on 16 December 2025, chaired by the Federal Health Minister and GHI report endorsement was documented in the minutes. KP: DHPMTs were functionalised in four NHSP prioritised districts (Peshawar, Abbottabad, Kohat and Swat). DHPMT DTRC meetings helped establish regular, structured review processes for DAP implementation. Punjab: H&PD notified the Punjab Family Planning Partners Coordination Forum and E4H is working with H&PD to expand it into a Health & Population Partners Coordination Forum.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
Strengthened sub-system practices to implement UHC | % of approved TAs that are delivered in accordance with the specified deliverables | Planned | 0% | Fed: TAs approved = 1 KP: TAs approved = 2 | Fed, KP, and Punjab: 95% | Fed, KP, and Punjab: 65% | Fed, KP, and Punjab: 80% |  | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 2, Y2: Milestones assume that over time, more aspects related to TA delivery will be under the direct control of the programme (e.g., political turbulence related to 2024 elections will subside etc.), hence performance against approved TAs will improve. Milestone 3, Y3: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs. Milestone 4, Y4: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs.
|  | Achieved |  | Fed: 2 TA mini projects approved (Pak UHC Monitoring Report, National Health Support Programme year one assessment) KP: 2 TA mini projects approved (Coordination mechanism for donors & development partners, Sustainable training system) | Fed = Achieved (100 %) KP = Achieved (100%) Punjab = Achieved (100%) | Overall: 97% Fed = Achieved (100%) KP = Achieved (100%) Punjab = Achieved (100%)
Source
E4H programme reporting/M&E The indicator has been calculated based on the percentage of completion of deliverables, taking into account three key performance dimensions: adherence to timelines, compliance with quality standards, and achievement of agreed deliverables according to the TORs of TAs.
| Output Indicator 3.2 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| Strengthened health workforce as a means to primary healthcare (PHC) for UHC | Planned | Fed: Density of the essential health workforce (doctors, nurses, MWs, CMWs, LHVs) is 1.8/1000 population KP and Punjab: Non-standardized training systems for health workforce cadres are present. | Fed: NA KP: NA Punjab: NA | Federal: Regular monitoring of health national workforce statistics with development of snapshot, with evidence of use (e.g., development of resulting transformation plan etc.) KP: Sustainable Training System established and operationalized (e.g., TORs developed, team onboard) Punjab: Sustainable Training Framework developed | Federal: Revamping of the Nursing Council Secretariat, including formation of three committees (management, education, and quality assessment). MOV: Revamping Report and Notification of Committees KP: Validated and functional HRMIS used by DHPMTs for performance management and institutionalised through integration with the sustainable training database, in line with the Essential Package of Health Services Human Resource norms. MOV: Analytics generated and used by district management. Punjab: Training of trainers using the integrated training curriculum for community health inspectors within the broader context of the Sustainable Training System, with demonstrable government buy-in. MOV: Endorsement of Curriculum from the Provincial Health and Development Centre (PHDC)/ Health and Population Department (H&PD) | Federal: Regulatory reforms for nursing and midwifery institutionalised through the PNMC Act 2026. MOV: The Pakistan Nursing and Midwifery Act 2026 approved by the Parliament, assented to by the President of Pakistan, and notified in the Official Gazette. KP: Standardised HRH framework and service rules for priority cadres developed to support equitable workforce planning, deployment and management. MOV: Final HRH framework and priority-cadre service rules, with evidence of submission to the Health Department or competent authority for approval. Punjab: Frontline maternal health capacity strengthened to improve prevention and management of post-partum haemorrhage (PPH), supporting quality PHC and contributing to reduced maternal mortality. MOV: Standardised PPH training package aligned with UNICEF and at least 50 master trainers and 4,000 skilled birth attendants trained across Punjab province. | Essential health workforce with enhanced capacities available at the provincial and district levels. Training systems/initiatives are standardized and coordinated, promoting efficiencies and consistent workforce quality. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 3: Y3: The milestones are based on the assumption that TAs for systems development will be embedded within government structures and there will be institutional uptake of TA outputs. Financial Resources available for the sustainable in-service training systems. Milestone 4, Y4: Government ownership ensures sustained implementation of workforce reforms and training systems.
|  | Achieved |  |  | Federal:: National health workforce statistics snapshot developed with evidence of use. KP: Sustainable training system mechanism developed with phased implementation. Punjab: Sustainable training framework developed | Federal:: Revamping of the PNMC secretariat report (along with the transition plan) shared with M/o NHSR&C and PNMC. The report proposed an organogram for the Secretariat positions. KP: HR records were validated across 13 DHQ hospitals and six DHO offices and analytics are being routinely used in DHPMT meetings. Punjab: District level ToTs were conducted to institutionalise skilled, digitally enabled 173 community health inspectors across 16 districts.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
| Output Indicator 3.3 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
| Improved practices for ensuring high-quality PHC | Planned | Islamabad Health Regulatory Authority (IHRA) at the Federal level and Health Care Commissions (HCCs) in Punjab and KP are partially functional KP and Punjab: No plan/unified vision or structured system for quality of care across province, district, and key health stakeholders (QOC fragmented) | Fed: NA KP: NA Punjab: NA | Federal:: Roundtable discussion of IHRA, HCCs and stakeholders held to identify common strategic priorities​, share learnings and develop way forward KP: Unified QOC Strategic Plan developed and approved | Federal:: Health Technology Assessment undertaken at the PHC level in collaboration with the National Institute for Clinical Excellence (NICE). MOV: Assessment Report of the Health Technology Assessment, including options for institutionalisation. ​ KP: PHC Quality Assurance Mechanism institutionalised in one district in line with Quality of Care Strategic Plan. MOV: Notification of Quality Assurance Mechanism and progress report. Punjab: MSDS compliance assessment conducted through E4H support, and a roadmap for addressing recommendations developed, prioritised, and institutionalised by the HCC. MOV: Recommendations derived for enhancing the quality of care in public and private facilities and submitted to the Punjab HCC. | Federal: Revised National Health Support Programme (NHSP) Federal PC-1. MOV: Revised NHSP Federal PC-1 document, submitted to M/o PD&SI with the approval of M/o NHSR&C. KP: *Inter-provincial collaboration on healthcare regulation strengthened through at least one coordination meeting of Provincial Healthcare Commissions. MOV: Meeting records documenting participation, lessons shared, agreed priority actions and follow-up commitments. Punjab: Evidence-informed referral integration model developed to support structured linkages between private sector GPs and public sector healthcare facilities. MOV: Draft referral model and implementation package submitted to PHCC with documented feedback received and incorporated. | IHRA and HCCs are functional and operating in alignment with global best practice (components for which the government received E4H support) Implementation of Quality Assurance Mechanism in prioritised districts. | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestones 2, Y2 (Punjab): No TA is planned on QoC in YR 2. The milestone for YR 3 will be added once the TORs for the TA are developed. Milestone 3: Y3: Funds secured for KP and Punjab provinces for quality of care initiatives. Milestone 4, Y4: Quality of Care (QoC) mechanisms remain institutionalised and functional.
|  | Achieved |  |  | Federal:: Roundtable of HCC and IHRA with agreement on next steps. KP: QoC strategic plan developed and approved | Federal:: Health technology assessment report was developed by NICE. KP: Quality of Care (QoC) committees were notified in four districts (Peshawar, Abbottabad, Kohat and Swat). DAPs in the four priority districts actively monitored through functional DHPMTs and DTRCs, with QoC committees meeting convened regularly to oversee RMNCH service delivery. Punjab: The implementation of MSDS was assessed in 71 healthcare establishments across five districts.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline | Milestone 1, YR1 (February 2023 - December 2023) | Milestone 2, YR2 (January 2024 - December 2024) | Milestone 3, YR3 (January 2025 - December 2025) | Milestone 4, YR4 (January 2026 - December 2026) | Target (by December 2026) | Assumption
40% | Improved governance for UHC implementation | Planned | Federal: Ad hoc discussion of PHC for UHC at central levels KP and Punjab: UHC Steering Committee structures non-functional (see linkages to Output 2.4). No strategy for comprehensive UHC execution in place, slowing UHC progress | Fed: NA KP: NA Punjab: NA | Federal:: Effective coordination among health insurance initiatives with common strategic direction​. KP: UHC Implementation Roadmap developed . Punjab: UHC Implementation Roadmap developed​. Punjab: Punjab UHC Delivery Unit operationalised for strengthening EPHS implementation. | Federal:: Meeting of National Advisory Committee and Interministerial Health and Population Council held for the endorsement of National Health and Population Policy for the next 10 years. MOV: Approved Minutes of the Meeting. KP: District Action Plan (DAP) developed in at least two districts with E4H support and alignment with NHSP. MOV: DAP approved by UHC technical committee and evidence of submission to steering committee.​ Punjab: Punjab Community Health Inspector Implementation Plan developed with the involvement of the UHC Delivery Unit. MOV: Endorsed by Health and Population Department. | Federal: National Health and Population Policy (NHPP) 2026-35 submitted to the Federal Cabinet to strengthen governance for UHC implementation. MOV: NHPP 2026-35 submitted and approved by the Prime Minister/Cabinet of Pakistan office. KP: DAPs co-developed for six new districts, with the rolling planning process institutionalised through DGHS oversight, capacity transfer to DHOs, and a structured handover for sustainable implementation. MOV: DGHS-endorsed DAPs, capacity transfer records through planning workshops, and documentation outlining DGHS oversight and the rolling planning process. Punjab: Evidence generated and shared with H&PD to strengthen disability-inclusive PHC policy and practice, supporting equitable access and UHC. MOV: Final policy brief submitted to H&PD/P&D. | Federal: TBD KP and Punjab: UHC Roadmaps developed, launched, and progressively implemented based on selected/agreed priorities | Milestone 1, Y1: no score corresponding to this indicator, given that the majority of the period consists of inception (6 months), with only 3 months of implementation for KP and Federal, with Punjab inception just commencing (1 month). Milestone 3: Y3: UHC still remains a priority for the government with the availability of funds. Milestone 4, Y4: UHC remains a government priority, with sustained commitment to implementation of reforms and coordination platforms.
|  | Achieved |  |  | Federal:: NAC held and also endorsed E4H supported MTR and NAPHS work KP: UHC Implementation Roadmap developed, with evidence of implementation initiated. Punjab: Punjab UHC Delivery Unit operationalised | Federal:: NAC was convened on 2 July 2025 to provide technical oversight for national level programmatic reforms. A joint meeting of the IMH&PC and the UHC Country Platform was held on 16 December 2025, chaired by the Federal Health Minister, ensuring high level commitment and improved coordination. KP: DAPs developed for four NHSP priority districts (Peshawar, Abbottabad, Kohat and Swat). Punjab: The H&PD developed provincial CHI framework.
Source
(1) E4H programme reporting and M&E; (2) Official government notifications/approvals/meeting minutes

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
LOGFRAME |  |  |  |  | THEORY OF CHANGE
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE | ID | TOC ELEMENT | DETAILS OF CHANGE | AUTHOR | DATE
Changes documented to E4H logframe from September 2023 |  |  |  |  | Changes documented to E4H TOC from February 1, 2024
0 | General reformatting | Reshaping of logframe to better align with standard practice (e.g., change from long term goal language to impacts, removal of "measures of success" and replacement with milestones etc.) | Kaja J | 18/03/2024 | 1 | TOC stages | Stages of TOC reframed so we more actively show the flow from inputs to impacts, including contribution to the next stage | Kaja J | 18/03/2024
1 | Impact statement | Amended to be better aligned to business case, with focus on preventable rather than premature deaths | Kaja J | 18/03/2024 | 2 | Impact | As with logframe, amended to be better aligned to business case, with focus on preventable rather than premature deaths | Kaja J | 18/03/2024
2 | Impact Indicators 1 & 2 | Added KP and Punjab point estimates for baseline year, as well as targets computed based on national rate of change | Kaja J | 18/03/2024 | 3 | Activities | Updated to reflect latest domains of priority for the programme | Kaja J | 18/03/2024
3 | Impact Indicator 3 | Amended from DALYs to prevalence rate for easier understanding; maternal and neonatal disorders and nutritional deficiencies removed from communicable disease computation (so that only core communicable diseases are retained). Targets computed based on national rate of change | Kaja J | 18/03/2024 | 4 | Assumptions | Assumptions tweaked, with addition of assumption related to Federal-provincial tensions and collaboration | Kaja J | 18/03/2024
4 | Milestone 4, Y4 adjustment | Y4 adjusted from Jan-Dec, to Jan-Nov 2026 in alignment with recently communicated change to end of programme date | Kaja J | 18/03/2024 | 5 | Activities | Defined final domain (links to logframe indicator 3.4) as "improved governance for UHC implementation." | Kaja J | 2024-03-05
5 | Target column | Target year adjusted to Nov 2026 or by Nov 2026, in alignment with recently communicated change to end of programme date | Kaja J | 18/03/2024 | 6 | TOC overall | Updated in consultation with FCDO and TPM (latest version featured in "Updated TOC" tab) | Dr Mahwish Hayee | 14/06/2024
6 | Outcome Indicator 1 | Data updated to reflect 2023 JEE, with provincial-level estimates. Fully vetted provincial scores will not be available until NAPHSII is completed | Kaja J | 18/03/2024
7 | Outcome Indicator 2 | Data updated to include Punjab estimates | Kaja J | 18/03/2024
8 | Output Indicators 1.1, 2.1, and 3.1 | Indicators amended so that they are no longer composites (simplification). Targets amended | Kaja J | 18/03/2024
9 | Output Indicators 1.2, 2.2, 3.2 | Previous indicators removed/deleted and replaced with subject-matter/output-specific indicators | Kaja J | 18/03/2024
10 | Output Indicators 1.2, 1.3, 1.4; 2.2, 2.3, 2.4; 3.2, 3.3 | Related to #9, new indicators defined, along with corresponding baselines and targets, and milestones for Y2 and tentative for Y3. No milestones for Y4 given that logframe requires annual update and Y4 TA priorities are too distant/uncertain | Kaja J | 18/03/2024
11 | Output Indicator 1.4 milestones | Confirmation of Punjab province milestone following workplan completion and TA prioritisation in April | Kaja J | 2024-03-05
12 | Output Indicator 2.2 baseline and milestones | Definition of Punjab province baseline and milestone following workplan completion and TA prioritisation in April | Kaja J | 2024-03-05
13 | Output Indicator 3.2 baseline and milestones | Federal milestone re-defined (multisectoral HRH strategy moved to output 1.4), with a focus on monitoring health workforce. Provincial level milestones aligned to development of sustainable training systems and their implementation in Y3. | Kaja J | 2024-03-05
14 | Output Indicator 3.3 baseline and milestones | Baseline for KP and Punjab added. Y2 milestone for KP revised to focus principally on the QOC Strategic Plan work, which will ultimately unify the additional TAs being delivered to KPHCC and KPHF. No specific milestone for Punjab added based on current years' workplan -- in its place, an additional milestone was added to output indicator 3.4 | Kaja J | 2024-03-05
15 | Output Indicator 3.4 baseline and milestones | Indicator defined (previously indicator was TBD) as "improved governance for UHC implementation." Federal, KP, and Punjab baselines and milestones defined. | Kaja J | 2024-03-05
16 | Output Indicator milestones 3.2, 3.3, 3.4 for Y2 | In discussion with FCDO, removed 4 milestones for Y2: Ind 3.2 - KP & Punjab: Plan for skill and non-skills-based training developed; Ind 3.3 - Punjab: no specific TA on QOC in Y2; in lieu of that, two milestones added under indicator 3.4; Ind 3.4 - Federal: Effective coordination among health insurance initiatives with common strategic direction AND Punjab: UHC Implementation Roadmap developed | Dr Mahwish Hayee | 14/06/2024
17 | Output Indicator milestones 3.4 for Y3 | In discussion with FCDO, removed 1 milestones for Y3: Federal: Benefit packages updated based on evidence (tentative/TBD) | Dr Mahwish Hayee | 14/06/2024
18 | Impact indicator milestones | In discussion with FCDO, removed annual milestones at the impact level only to keep the baseline and the target | Dr Mahwish Hayee | 14/06/2024
19 | Achievement against Output indicators 1.1, 2.1, 3.1 | Based on Annual Review, achievement for first year of the programme added for indicators 1.1, 2.1, 3.1 | Salman Mahmood | 20/06/2024
20 | Milestones against output indicators: 1.3, 1.4, 2.2, 2.4, 3.2, 3.3, 3.4 | Based on the feedback received from FCDO (BZ), changes were made to the milestones for YR2 and YR3, including adding language on evidence of use/uptake/implementation where feasible | Salman Mahmood and Kaja J | 25/06/2024 and 27/06/2024
21 | Impact Indicator milestones | Following conversation with FCDO, impact indicator milestones restored, though assumptions about reduction further caveated -- contribution rather than attribution | Kaja J | 25/06/2024
22 | Outcome Indicator 1 and 2 | The latest IHR score and the UHC service coverage index have been updated. | Dr Mahwish Hayee | 19/06/2025
23 | Milestones against output indicators: 1.2, 1.3, 1.4, 2.2, 2.3, 2.4, 3.2, 3.3, 3.4 | Based on the feedback received from FCDO, milestones have been set for programme year 3 at the provincial level with related MOVs | Dr Mahwish Hayee | 19/06/2025
24 | Assumptions in indicator 1.2, 1.3, 2.3, 2.4, 3.2, 3.3, 3.4 | The assumptions have been revised for YR3 milestones. | Dr Mahwish Hayee | 19/06/2025
25 | Achievement against Impact indicators 1 and 2 | Achievements for second year of the programme added against impact level indicators. | Dr Mahwish Hayee | 19/06/2025
26 | Achievement against Output indicators 1.1, 1.2, 1.3, 1.4 2.1, 2.2, 2.3, 2.4, 3.1, 3.2, 3.3, 3.4 | Based on Annual Review, achievements for second year of the programme added. | Dr Mahwish Hayee | 19/06/2025
27 | Assumptions in indicator 1.1, 2.1, 3.1 | Based on the comments received from FCDO, the assumptions have been updated to reflect the Government ownership and up take. | Kaif Gill | 30/06/2025
28 | Source in Output Indicators 1.1, 2.1, 3.1 and Outcome Indicator 1 and 2 | Defined the delivery of TAs based on the specific TORs for the work stream and are calculated based on timeliness and quantity. The baseline information and milestone data source for year 3 has been updated. | Kaif Gill | 30/06/2025
29 | Outcome Indicator 1 and 2 | The latest IHR score 2025 and the UHC service coverage index 2025 have been updated. | Kaif Gill | 2026-12-06
30 | Achievement against Impact indicators 2 and 3 | Achievements for E4H programme year 3 added. | Kaif Gill | 2026-12-06
31 | Data Source Impact indicator 3 | Justification for target calculation added. | Kaif Gill | 2026-12-06
32 | Assumptions for output level indicators | The assumptions have been revised for YR2 milestones. | Kaif Gill | 2026-12-06
33 | Achievement against Output indicators 1.1, 2.1, 3.1 | Based on Annual Review, achievements for third year of the programme added. | Kaif Gill | 2026-12-06
34 | Achievement against Output indicators 1.2, 1.3, 1.4, 2.2, 2.3, 2.4, 3.2, 3.3, 3.4 | Progress for third year of the programme added. | Kaif Gill | 2026-12-06
35 | Assumptions in indicator 1.1, 1.2, 1.3, 1.4 2.1, 2.2, 2.3, 2.4, 3.1, 3.2, 3.3, 3.4 | The assumptions have been updated to reflect the Government ownership and up take. | Kaif Gill | 21/7/2026
36 | Milestones for year 4 against output indicators: 1.2, 1.3, 1.4, 2.2, 2.3, 2.4, 3.2, 3.3, 3.4 | Milestones have been set for E4H programme year 4 at the provincial level with related MOVs. | Kaif Gill | 21/7/2026