BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Evidence for Health (E4H)
Directorate/ Post	Islamabad	Contact names	Dr. Bilal Zafar / Maryam Masud
Original programme budget	£35 million	Country or region targeted	Pakistan
Cost extension value (if applicable)	Not applicable	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Minister
New increased or reduced programme budget (if applicable)	Not applicable	Original programme start and end dates	14/01/2022 to 10/01/2027
Latest AR programme score	A	New programme end date (if applicable)	10/07/2028
		Programme ID	300801

Detailed information
Programme summary	Evidence for Health (E4H) is a health system strengthening technical assistance programme designed to build effective, inclusive, and resilient health systems. It works in direct partnership with the federal government and the provincial governments of Punjab and Khyber Pakhtunkhwa (KP). / The business case was approved in January 2022 by Minister Lord Ahmed, with an addendum in October 2022 to reflect minor material scope changes and explicitly position the programme to (a) address flood-related challenges in the human development sector and (b) adopt a holistic MERL (Monitoring, Evaluation, Research and Learning) approach through partnership with the World Bank’s National Health Support Programme (NHSP). While the overall programme cost remained unchanged, the technical partnership budget was reduced from £8m to £5m, reallocating funds to increase the MERL component from £3m to £6m. / Notable achievements to date, include: / Conducted the National Health Vision Mid-Term Review, which led to the approval of Pakistan’s first joint National Health & Population Policy (2025–34). / Developed the National Action Plan for Health Security (NAPHS) with UKHSA, USAID, and WHO, enabling £14.1m Pandemic Fund and £33m USAID grant for International Health Regulations compliant health security. / Drove health reforms through technical assistance: training 20,000 community health workers, boosting efficiency of 900 mobile clinics, and leveraging £288M in partner investments to fast-track Universal Health Coverage. / Completed the first joint strategic review of Global Health Initiatives (GFATM, GAVI, PEI), producing a roadmap for integration under the Lusaka Agenda.
Changes		The programme areas of work have not been materially amended since October 2022. / The proposed change is an 18-month extension into FY 2028 to align contract end dates with the approved business case (10 January 2027). Currently, KP & Federal contract ends on 15 February 2027 and Punjab on 28 November 2027; both beyond the business case timeline, creating commercial non-compliance. Approving this addendum will resolve the mismatch and enable better forward planning for the programme and its contracts. / This extension is critical to sustaining momentum and ensuring the sustainability of gains achieved under E4H. It will enable the programme to preserve both operational and technical progress, leveraging strong ministerial support from the Government of Pakistan, deep provincial engagement, and a proven track record of high‑quality delivery. / Without this extension, essential technical assistance to advance reforms, scale data systems, and leverage domestic resources will be disrupted. This includes disruption to our global partnerships including the World Bank and UK’s central investments in Global Health Initiatives.. These risks reversing progress, weakening partnerships, and undermining health outcomes - eroding gains and reducing the impact of UK investments / The extension will not deviate from the original Business Case; all workstreams will continue. Adjustments to the theory of change include delivering further ambition in all areas, a bigger focus on demography, a longer timeframe for embedding systemic reforms. / VfM assumptions from the original business case remain valid and broadly unchanged with further evidence gathered over reporting year 2025/2026. / Trade-offs considered: / Redirecting financial resources toward new programming which needs to be designed; instead of maintaining existing high-impact programs. / Exploring alternative implementation approaches, such as direct delivery by the UK government. / Given the programme’s sustained performance, strategic relevance and commercial compliance requirement, an 18‑month extension time offers the best value for money.
Implementation		Implementation will use existing delivery channels: all contracts will be extended under current terms of reference. The technical partnerships component will pivot to demography, converging with work from the near concluding Delivering Accelerated in Family Planning (DAFPAK) programme by December 2026 (TBC). / No major management changes: the current SRO-led structure remains. Adaptive programming stays central, backed by quarterly reviews and proportionate MEL oversight by Integrity to validate progress and evaluate impact.
Budget		Original budget: £35 million / Spent to date: approximately £8.3 million / Funding is affordable within Pakistan ODA allocation and does not exceed the current SR period. The proposed extension leverages efficiencies from existing contracts and avoids costs of programme restart.
Impact		Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk		Existing risk management processes (quarterly risk reviews, escalation protocols) will continue. / Frequent government leadership changes, shifting donor priorities, and unclear expectations pose risks to continuity and delivery. E4H mitigates these through rapid reorientation, strong institutional linkages, clear focal points, and regular performance reviews. Recruitment challenges are addressed through partner consultant networks and rigorous hiring processes; while safeguarding and fiduciary risks are managed through strict policies, training, and financial monitoring. These measures keep residual risks moderate.
Results/Monitoring and Evaluation		E4H will launch additional programming based on health sector needs and evidence, leveraging partnerships with the World Bank and other partners. / By mid-2026, a phased transition roadmap will be developed to embed reforms in government systems while addressing priorities such as integrated primary health care, sustainable population growth (as DAFPAK closes), and PHC financing. Collaboration with the World Bank, Pandemic Fund, UKHSA, and Global Fund Accelerator will drive systemic reforms while aligning with the UK’s modern partnership agenda. / The theory of change remains valid; however, it will undergo further review to ensure alignment with the modern partnership agenda. This includes strengthening the existing Monitoring, Evaluation, and Learning (MEL) framework through an updated logframe and enhanced reforms tracking.