## Annual Review Template

Title: Evidence for Health (E4H)
Programme Value £ (full life): £35 million		Review date: / 31 Jan 2026
Programme Code: 300801	AMP start date: / 14 Jan 2022	AMP end date: / 10 Jan 2027

Summary of Programme Performance risk
Year	2022	2023	2024	2025
Overall Output Score	C	A	A	A
Risk Rating

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300801/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300801/documents

A. SUMMARY AND OVERVIEW
Description of programme

1. The Evidence for Health (E4H) programme is the UK Government’s flagship health initiative in Pakistan, focused on strengthening health systems through improved governance, evidence-based decision-making, institutional capacity building, and leveraging domestic and partner investments in health at both federal and provincial levels. With a core emphasis on Universal Health Coverage, Health Security, and Evidence-Based Decision Making, E4H is committed to building resilient and equitable health systems. The programme provides technical assistance (TA) and implements a robust Monitoring, Evaluation, Research, and Learning (MERL) framework to support the Federal Ministry of National Health Services, Regulation and Coordination (MoNHSR&C) and the provincial health departments of Punjab and Khyber Pakhtunkhwa (KP).
2. The period under review (Jan 2025 – Jan 2026) marks the programme’s consolidation phase, transitioning from foundational systems strengthening to deepening institutional capacity, enhancing accountability for results, and integrating learning across provinces. E4H builds on previous UK investments in health systems strengthening and serves as a key pillar of the UK-Pakistan Health Partnership, launched in February 2023. This partnership has marked a shift from traditional aid-based support to a collaborative model grounded in mutual interests.
3. Delivered through a consortium of Palladium International and Oxford Policy Management, E4H provides specialist expertise in three thematic output areas of 1.) health security and International Health Regulations (IHR), 2.) evidence-based decision-making, and 3.) Universal Health Coverage (UHC), leveraging global best practices and partnerships with academia, international programmes, multilaterals including World Bank and the UK’s National Health Service (NHS). The UK support provides embedded teams of technical experts working within government health departments to strengthen policy and systems and help ensure sustained uptake of reforms within Pakistan’s complex political and economic landscape.
4. Now entering its third year of implementation, E4H has made significant progress across its three active funding components - Federal and KP, Punjab, and Monitoring, Evaluation, Research and Leaning (MERL), with the fourth Technical Partnerships component not yet mobilised. The programme has met strong demand from health authorities, delivering 74 government-prioritised Technical Assistance (TA) workstreams across policy and implementation. Of these, 44 TAs are completed and 30 remain active.
5. This reporting year, 48 completed and ongoing TAs are the focus of this Annual Review: 12 at the federal level, 18 in KP, and 18 in Punjab, reflecting a strategic shift after strengthening national policies and strategies towards provincial and district levels implementation support.
6. The E4H team ensures all TAs are delivered in line with agreed Terms of Reference and government expectations. Strategic oversight is provided by steering committees chaired by the Secretary of Health. A full summary of all TAs and their status is available in Annex B.
7. E4H’s contributions this year have focussed on development and approval of first National Health and Population Policy since 2011 devolution with consensus of the provinces, Primary Health Care reforms including District Health office restructuring, improved public sector financial and human resource management, supporting quality of care, implementation of National Action Plan for Health Security and leveraging World Bank and partners funded (£288m) National Health Support Programme (NHSP) to improve Universal Health Coverage. The total volume of TA workstreams supported thus far represents a hugely ambitious programme of reform and support to policy development, system strengthening, and quality monitoring across all three outputs.
8. As recommended in the last Annual Review, the programme is now shifting its focus from provincial to district-level reforms in Primary Health Care (PHC), Health Security, Quality of Care, and Health Care Financing. The transition is ensuring balancing the volume and sustainability of TA workstreams, ensuring quality across diverse interventions, maintaining national coverage alongside provincial engagement, and clearly defining the scope of federal support, leadership, and optimal engagement.
9. The MERL component, delivered by Integrity, jointly supports the E4H and NHSP programmes by providing independent verification and ensuring financial transparency down to the district level reinforcing accountability in UHC implementation. Built on Third-Party Verification (TPV), programme evaluation, research, and learning exchange, this component plays a critical role in monitoring outputs, validating Disbursement-Linked Indicators (DLIs) under NHSP to enable payments within the Program-for-Results (PforR) framework, and generating evidence to identify achievements, challenges, and gaps. Early and midline evaluations for both E4H and NHSP were completed during the last AR period, offering key insights to refine and adapt the programmes for improved results.
10. The fourth Technical Partnerships component has not yet been mobilised, and options are being actively considered. E4H’s programme components are summarised below.

Component	Description
TA contract for KP & Federal Government	Total budget: £12m. Implementation commenced in September 2023. Consortium of Palladium (lead) with Oxford Policy Management (OPM).
TA contract for Punjab	Total budget: £12m. The inception phase ended in April 2024, and implementation commenced in May 2024. Consortium of Palladium (lead) with OPM
MERL contract	Total budget: £6m. The inception phase ended in April 2024, and implementation commenced in May 2024. Integrity leads the contract.
Technical Partnerships	Total budget: £5m. Not yet mobilised. Design options are being considered and will be mobilised by July 2026.

About changes to UK ODA
A significant prioritisation in light of the Ministerial decisions related to the Official Development Assistance (ODA), the new Modern Development principles, and the UK-Pakistan cooperation portfolio strategy has required programmatic pivoting and adaptations to implement the new BHC-I Pakistan Portfolio Development Strategy. This Annual Review highlights that the programme has reallocated resources under a revised plan, with expected changes to targets. The programme is now considering a comprehensive Health Systems Strengthening (HSS) approach that also integrates sustainable population growth challenges; previously addressed through the BHC-I funded DAFPAK programme, which will close earlier than planned in 2026. The recent merger of the Health and Population Welfare Departments in Punjab further reinforces this strategic alignment and pivot.

Summary supporting narrative for the overall score in this review

1. E4H is on track to deliver against milestone output targets for this year, despite delays caused by changes to the UK’s ODA allocation. The programme has reached a mature phase of delivery, with strong government demand and embedded TA teams well positioned to respond. Relationships with federal and provincial counterparts have strengthened, enabling credible and priority TA support. Progress includes improved federal-provincial coordination through the National UHC platform, endorsement of the first National Health and Population Policy, reforms at primary health care, improvements in quality of care, institutional capacity building and strengthened public sector financial management. The shift toward district-level support and stronger linkages with the World Bank’s NHSP marks a strategic evolution in delivery. While evidence on outcomes and impact remains limited due to the absence of regular national health surveys, the programme continues to consolidate its role in contributing to strengthen Pakistan’s health system.
2. Demand for the programme’s support continues to be strong and ambitious at all three component levels (Federal, KP and Punjab) as demonstrated by the high number of TAs also supported by the government counterparts contacted for this review. The counterfactual was consistently stated that although reforms would have been undertaken, they would have been less effective, less well coordinated, slower and fewer. The review also focuses on questions around links to education and climate, overall coverage and targeting, downstream delivery and reaching marginalised groups.
3. The programme’s third-party monitoring and independent MERL component provides useful and credible assurance of progress, deliverables and uptake of the TA inputs, providing confidence in the scoring assessment and contributions of workstreams to the overall Theory of Change.
4. The E4H programme achieves an A. It has shown strong performance across all three outputs, achieving most of its milestones and making significant progress on last year’s Annual Review recommendations despite delay in implementation due to funding decisions. Despite a challenging operating environment marked by government transitions and political instability, the programme has clearly strengthened Pakistan’s health system infrastructure in areas like Health Security, Evidence-based decision-making, and Universal Health Coverage. (The archive of initiatives carried out in 2025 is in Annex B). Under the leadership of the Government of Pakistan, E4H played an enabling role in achieving key results. Examples identified by the government for the review team include.
5. National Health and Population Policy (2026 2035).
Since devolution in 2011, aligning federal and provincial health priorities has been challenging, with the last consensus document (National Health Vision 2015) lacking effective implementation. Meanwhile, health challenges have intensified, driven by rapid population growth, health security risks, malnutrition, and climate vulnerabilities. With E4H technical assistance, the Federal Ministry of Health led a structured, evidence-based, and politically sensitive process to develop Pakistan’s first unified National Health and Population Policy (NHPP 2026–2035). Endorsed by all provincial health ministers, NHPP establishes a coherent national framework for Universal Health Coverage and health security, monitored through the National UHC platform. Drawing lessons from the pandemic, the policy emphasizes the importance of national alignment, cross-provincial learning, and international engagement in a devolved context, ensuring consistent standards while allowing provincial flexibility. This approach mirrors global best practice in federated systems (Canada, Australia), balancing national coordination with local adaptation to strengthen resilience and equity. NHPP now provides a unified framework guiding provincial health strategies, with implementation monitored through the National UHC platform with first following up meeting planned in April 2026.
Primary Health Sector Reforms in Punjab
E4H is supporting the Chief Minister’s health reform agenda through the Delivery Unit in the Punjab Health and Population Department. Early evidence of impact is emerging through increasing focus on monitoring and evaluation to improve access to essential health services, including the recent integration of the Population Welfare Department with Primary Health Care.
Modernising Nursing and Midwifery Policy Framework (2025-34)
Based on findings from a WHO-supported survey of over 500 nursing and midwifery schools, the Ministry of NHSR&C supported by E4H and in collaboration with the UK NHS developed Pakistan’s first comprehensive Nursing and Midwifery Policy Framework (2025–34) to address outdated regulations and fragmented governance. The Government has adopted all recommendations, and a new Nursing and Midwifery Ordinance approved by the President introduces a modern regulatory architecture for advanced practice, high-quality training, and stronger public protection across the country. Alongside legislative reform, E4H is strengthening the Nursing and Midwifery Council[1] Secretariat to ensure robust governance and accountability. ADB is supporting nursing and midwifery education with considerable financing in both Punjab and Sindh ($300m) with opportunities of further collaboration.
[1] Regulatory Authority for Nursing and Midwifery Profession in Pakistan
Reforming Minimum Service Delivery Standards for Better Care
Punjab Healthcare Commission (PHCC) pioneered MSDS, the first quality-of-care standards in Pakistan, later adapted by other provinces. While over 70,000 public and private facilities are registered with PHC, licensing and regular checks remains limited due to resource constraints. E4H supported PHCC in assessing MSDS compliance across 71 facilities in South and Central Punjab; only 6% achieved full compliance, with primary health care facilities performing weakest and private facilities generally better than public ones. Expanded assessment revealed persistent gaps in patient safety and efficiency, highlighting that the current MSDS framework is too complex for low-resource settings. These findings are now being considered by the PHCC and Health Department to drive a shift toward simplified, modular standards and targeted support for health care facilities to enable sustainable quality improvement and greater equity in rural care.
Clinic on Wheels – Healthcare at the Doorstep
  The Government of Punjab launched Clinic on Wheels to deliver essential health services to urban slums and peri-urban communities, deploying 911 mobile clinics that provide outpatient care, ultrasounds, free medicines, immunisation, and screening for hepatitis, malaria, and TB reaching over 9.4 million people in just a year. Initially, deployment was inconsistent, with routes driven by limited evidence and no real-time data to guide coverage. E4H TA introduced a data-driven solution using geotagging, mapping, and population-need analysis to prioritise underserved areas, prevent duplication, and optimise routes. Integrated dashboards now track clinic performance in real time, strengthening equity, accountability, and resource efficiency in this large-scale provincial programme.
Supporting Improved Coverage of Community Health Workers in Punjab
Punjab faced a 49% coverage gap of community health workers in peri-urban, rural, and newly urbanised areas under the Lady Health Worker (LHW) Programme. To address this, the province introduced a new cadre of Community Health Inspectors (CHIs), hired through third-party contracting to deliver doorstep primary healthcare where LHWs do not operate. Piloted in four underserved districts, the model’s success led to a province-wide scale-up of 20,000 CHIs across all 36 districts. To enable rollout, E4H refined the training curriculum, trained 155 master trainers in 18 districts, and developed a digital literacy module for geotagging, household mapping, and integration with existing information systems.
Facility-Level Budgeting (FLB) in KP
E4H’s work on Facility-Level Budgeting (FLB) builds on earlier assessments by the BHC-I Subnational Governance Programme and the World Bank-supported Expenditure Management Policy. E4H operationalised this policy in the health sector by piloting FLB at district level in Peshawar, addressing decades of centralized budgeting that caused stockouts, weak planning, and poor accountability. The pilot enabled facilities to access clear allocation data, track spending and performance, and plan predictably. At the Government’s request, the model has now expanded to four additional districts, with a focus on institutionalizing FLB for sustainability. Recognized in the Chief Minister KP Good Governance Roadmap, this reform demonstrates how starting small and scaling strategically can translate complex public financial management (PFM) policy into practical service delivery improvements.
Fixing HR Data for Smarter Workforce Planning in KP
For years, KP’s health department relied on incomplete paper-based HR records, making it hard to track staff positions or plan services. With E4H support, over 17,000 workforce records across four districts were validated and digitised, giving managers accurate data on vacancies, staffing gaps, and gender distribution. Human Resource Management Information System (HRMIS) focal persons were trained to maintain the system, ensuring data stays current. This upgrade is improving transparency, enabling fair deployment especially in underserved areas and strengthening workforce planning, is now scaled up to another 10 districts through E4H support on request of DoH.
Development of District Action Plans (DAP) to Advance Universal Health Coverage
E4H technical assistance enabled four KP districts to develop costed, phased District Action Plans (2025–2028), aligning implementation with NHSP Disbursement Linked Indicators (DLIs) to advance Universal Health Coverage. This approach effectively leveraged the World Bank’s £288m NHSP funding to strengthen UHC, prioritizing essential maternal and newborn health services. Building on strong results, the initiative is now being scaled up to six additional districts at the request of the Department of Health and the World Bank. This aligns with KP’s Good Governance Roadmap and fulfils last year’s annual review recommendation to work at the district level.
Building a Sustainable Health Workforce Training System in KP
Previously fragmented, KP’s health training lacked standard curricula and impact measurement. To fix this, the Department of Health, with E4H support, launched the Sustainable Training System (STS) under the Provincial Health Services Academy as the province-wide platform for workforce development. A training Alliance of government, academia, and partners now oversees implementation, endorsed the 2025–26 Training Plan, and drives curriculum and digital innovation. STS now hosts all new trainings such as Facility-Level Budgeting, HRMIS, and International Health Regulations supported by a digital dashboard and structured governance, ensuring a coordinated, government-led, and sustainable approach.
Integrated Care for Children with Special Needs in Punjab
E4H supported screening of 38,000 children in special education schools exposed major unmet health needs. With E4H support, Punjab institutionalised an integrated care system introducing treatment protocols, referral pathways, Electronic Medical Record (EMR) dashboards, and district committees. Over 8,000 children have received services, 5,000 are under treatment. This government-led model ensures coordinated, inclusive care and stands as a replicable approach for equity in health planning.
Public Health Act Revisions
KP and Punjab updated their Public Health Acts to align with IHR (2005), strengthening legal provisions for surveillance, vaccination, antimicrobial resistance, and epidemic response, including calibrated measures like lockdowns. The reforms embed the One Health approach, define cross-sector roles, and provide a legislative foundation for the National Health Security Plan, addressing gaps flagged in the independent IHR assessment.

Major lessons and recommendations for the year ahead
Lessons learned
Strategic Collaboration Amplifies Impact:
Effective collaboration with government on reform agendas combined with strong partnerships with the World Bank’s National Health Support Programme (NHSP) and the Pandemic Fund significantly enhanced the reach and impact of E4H’s technical assistance. Joint planning and alignment with these major initiatives enabled resource pooling, reduced duplication, and accelerated delivery of high-priority reforms such as Universal Health Coverage (UHC), International Health Regulations (IHR) governance, and health security preparedness. This experience underscores that coordinated, multi-partner engagement is essential for systemic change and resilience in Pakistan’s health sector.
Gap-analysis and co-design secure ownership:
Using structured gap-analysis frameworks and co-created Technical Assistance (TA) plans with federal, provincial, and district stakeholders has proven highly effective. Inclusive planning and clear communication foster mutual accountability and ensure reforms are government-led and sustainable.
Embedded Expertise Accelerates Reform and Builds Ownership:
Embedding technical assistance within government departments strengthens analytical capacity, improved responsiveness, and fostered greater government ownership of reforms. This approach combines technical expertise with collaborative support, helping institutions design and implement reforms effectively. By working within government systems, it provides strategic leverage to identify high-impact priorities while ensuring sustainability. Flexible and context-driven, the model balances ambition with feasibility, embedding reforms in national structures and creating opportunities for long-term capacity development and resilience
Evidence-Based Pilots Enable Scalable Reform
Practical, field-focused pilots such as emergency preparedness simulations and Facility-Level Budgeting deliver tangible results, expose system gaps, and accelerate adoption. When sequenced with prior diagnostics, these interventions create transparent, scalable reforms, demonstrating progressive realism: ambitious yet feasible change grounded in evidence.
Data governance requires protocols, not just technology
Establishing a unified national data governance mechanism showed that technical design alone is insufficient. Sustained coordination, clear data-sharing protocols (formal agreements with provinces), and confidentiality safeguards are essential for interoperability and compliance.
Continuity and Structured Frameworks Drive Sustainable Reform
E4H’s consistent engagement during periods of shrinking Official Development Assistance (ODA) preserved momentum on critical reforms such as effective Federal and Provincial regular coordination on key health issues and International Health Regulations (IHR) governance. Coupled with multi-year frameworks earlier developed such as five-year National Action Plan for Health Security (NAPHS), this continuity supported by investments from both government and development partners provided predictability, strengthened resilience, and enabled measurable improvements. This underscores the value of long-term partnerships built on trust, progressive realism, and mutual accountability.
Strong regulation underpins Public Private Partnerships (PPP) and outsourcing success
Persistent gaps in private-sector data and Minimum Service Delivery Standards (MSDS) compliance highlight the need for capable regulatory institutions and enforceable standards as service delivery models evolve

Recommendations:
Transition Planning and Programme Pivoting
To ensure a smooth and sustainable transition, E4H should develop a phased plan bto avoid an abrupt exit and embed reforms within government systems. This plan will pivot the programme to adapt to reduced Official Development Assistance (ODA) and emerging priorities, including integrated primary health care (PHC), enhanced domestic financing, and sustainable population growth, particularly as the flagship DAFPAK programme concludes in 2026. The approach should align with the UK’s modern partnership agenda, grounded in progressive realism and mutual accountability. A transition roadmap should be completed by Q1 2026 under BHC-I guidance, with E4H leading planning and pivot design in close coordination with federal and provincial health authorities, while also factoring in UK support through GFA and UKHSA.
Bundling Technical Assistance for Greater Impact
To maximise impact and value for money, E4H team should bundle related technical assistance streams such as governance, legislation, and capacity-building using the practiced TA Identification Tool to create integrated provincial packages. This prioritisation should be implemented in all new TA workstreams in close collaboration with provincial health departments and partners, including GFA and UKHSA by Q1 2026.
Advancing Equity Through Knowledge Sharing
Equity should be promoted through strategic knowledge-sharing in underserved provinces rather than direct technical engagement. E4H should further leverage the Health Planning & Systems Improvement Unit (HPSIU) at the federal level to disseminate best practices, guidance, and tools developed under the programme to other provinces in addition to KP and Punjab. This approach ensures national coherence without overstretching resources and builds on existing examples, including support provided to provincial Health Sector Reform Units. By institutionalising these knowledge products and fostering peer learning, E4H can strengthen capacity across provinces while maintaining efficiency and sustainability throughout next implementation year.
Strengthening Health Security and International Health Regulations (IHR) Reforms
E4H should further support the implementation of IHR (2024) reforms by strengthening the National Institute of Health (NIH) and corresponding provincial focal points, while working closely with UKHSA and other partners to align efforts with Pandemic Fund-financed activities. This should include improving inter-provincial coordination and harmonising governance mechanisms throughout 2026.
Scaling Facility-Level Budgeting (FLB) in KP
E4H should complete the province-wide rollout of Facility-Level Budgeting (FLB) in Khyber Pakhtunkhwa and consider conducting implementation research comparing FLB and non-FLB districts to demonstrate gains in transparency and efficiency by Q2 2026. The findings would inform inter-provincial learning, strengthen resource planning, and enhance accountability mechanisms.
Institutionalising Digital Health and Regulatory Data Flows
Digital health and regulatory data flows should be institutionalised by strengthening interoperability between federal and provincial systems, in line with the recent UHC interministerial agreement on regular data sharing. This should also include integrating data from private health facilities to address a major gap in the current system. Key priorities include digitizing licensing processes and operationalizing compliance with Minimum Service Delivery Standards (MSDS) for health facilities to ensure quality of care. Additionally, telehealth pilots should be explored to expand access, improve efficiency, and enhance service delivery by Q2 2026.
Driving Efficiency and Sustainable PHC Financing for Equity
To secure sustainable financing for primary healthcare (PHC) and promote equity, E4H should focus on efficiency and effectiveness of existing service delivery models, informed by E4H MERL’s “Rethinking PHC for Pakistan” research. This includes developing and supporting cost effective service models, institutionalizing Delivery Units for stronger implementation, and consolidating the UHC Country Platform for joint planning and resource mobilization. Exploring innovative financing mechanisms while protecting vulnerable populations from catastrophic health expenditure is critical. E4H should also engage Finance Departments in addition to Health Departments to align health priorities with fiscal strategies, leverage cross-office expertise (Governance and Economic Reforms teams), and embed health financing within broader reform agendas. Importantly, the government should consider its evolving role as a strategic purchaser rather than direct provider, ensuring integration in PHC and quality of care while learning from existing models.
Strengthening In-Country Leadership of Delivery Partners for Strategic Guidance
In a complex and evolving operating environment, strong in-country programme leadership is critical to provide robust strategic guidance, ensure timely decision-making, and maintain effective coordination. While quarterly visits and the deployment of a Senior Technical Specialist have enhanced engagement, sustained senior leadership presence at the country level is essential to steer strategy, build trusted relationships with key government stakeholders and partners, and respond proactively to emerging challenges. This approach will help safeguard delivery and reinforce alignment with national priorities for long-term impact.
Strengthening Collaboration and Joint Advocacy
E4H should strengthen and expand its partnerships with the World Bank and other development partners, while collaborating closely with the Global Financing Accelerator (GFA) and UKHSA to drive health system reforms. This collective effort should prioritize addressing systemic challenges such as unsustainable population growth, malnutrition, declining GHI funding, and fiscal transition risks. Leveraging the existing UHC Country Platform as the central coordination mechanism will be critical for mobilizing resources and influencing policy effectively.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The E4H programme aims to support progressive, equitable health systems that are more resilient to emergencies, pandemics and climate change – in a policy context of UHC-aligned health care services for all. It seeks to strengthen capacity for evidence-based planning and decision making. Systemic impacts will be achieved through the pursuit of three core programme outputs:

1. Strengthened integrated health security sub-system practices.
2. Strengthened evidence-based decision-making practices.
3. Strengthened sub-system practices to implement UHC.

At its core, the ToC maps the stepwise transformation of inputs into long-term health system impacts by addressing strategic health systems gaps. These efforts emphasise equity, gender, and climate resilience as cross-cutting issues, reflecting E4H’s commitment to building a strengthened and adaptive health system at both provincial and federal levels. The E4H log frame was updated in 2024 to align with the revisions made to the ToC. Changes reflect predicted progress based on targets computed with national data and baseline and milestones for the newly mobilised Punjab component. No change was made to the ToC or Logframe in 2025 as ToC assumptions remain valid in light of ODA shrinkage and evolving UK-Pakistan priorities.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
33. Despite a challenging operating environment, E4H remains firmly on track to deliver its expected outcomes and impact, consistently meeting nearly all output milestones and demonstrating strong value for money. Government counterparts at federal and provincial levels have acknowledged E4H’s catalytic role, noting how its evidence, analysis, and embedded engagement have shaped critical decisions in service delivery, financing, surveillance, quality of care, human resources, and sector governance. Landmark reforms such as Pakistan’s first evidence-based National Health and Population Policy, alignment of provincial health strategies in Punjab and KP, and improvements in efficiency and effectiveness of domestic and partner financing, including World Bank NHSP and the Pandemic Fund reflect E4H’s technical contributions. The programme has also advanced quality of care across public and private sectors and initiated reforms in Global Health Initiatives through close collaboration with the Global Fund Accelerator (GFA) technical assistance.
34. Health remains a priority sector for provincial governments and is central to Chief Ministers’ reform agendas. E4H has effectively leveraged this political commitment to drive systemic improvements and enhance the efficiency and effectiveness of domestic investments. As a trusted technical partner, E4H has translated progressive realism into actionable reforms and accountability models.
35. Looking ahead, the programme will pivot to address emerging priorities driven by ODA shrinkage and evolving UK-Pakistan development partnership objectives. Planned actions include developing a phased transition roadmap by mid-2026 to ensure reforms are fully embedded in government systems, while adapting to priorities such as Integrated Primary Health Care (PHC), Sustainable Population Growth (as DAFPAK closes in 2026), and strengthening PHC financing. E4H will deepen collaboration with the World Bank, Pandemic Fund, UKHSA, and GFA to jointly advocate for systemic reforms addressing unsustainable population growth, malnutrition, fiscal transition risks, and reduced GHI funding. These actions position E4H to maintain momentum and deliver on its objectives while aligning with the UK’s modern partnership agenda and principles of mutual accountability and progressive realism.

Outcome Indicators	Baseline (2023)	Progress (2024/25)	Progress (2025/26)
International Health Regulations (IHR) Core Capacity Index Score (%)	Pakistan: 42.7% / KP: 40.7% / Punjab: 43.4%	Pakistan: NA / KP: NA / Punjab: NA	Pakistan: 48.21% / KP: 43.2% / Punjab: 46.8%
Universal Health Coverage Service Coverage Index Score	Pakistan:52.7 % / KP: 51.1% / Punjab: 53.8%	Pakistan: 53.9% / KP: 51 % / Punjab: 55.4%	Pakistan: 54.7% / KP: 53.5% / Punjab: 55.2%

E4H’s two expected outcomes: strengthened health sector resilience and responsiveness to emerging disease threats and climate shocks, and improved coverage, equity, quality, and efficiency of health services are showing measurable progress. Latest monitoring reports indicate Pakistan’s Universal Health Coverage Service Coverage Index (UHC-SCI) has increased from 53.9 in 2024 to 54.7 in 2025, reflecting incremental gains in essential service coverage and equity. Similarly, the International Health Regulations Core Capacity Index (IHR-CCI) rose from 42.7% to 48.21%, signalling enhanced surveillance, preparedness, and response capacities. These improvements demonstrate a more resilient and responsive health system aligned with global benchmarks, progress to which E4H’s technical support, alongside partners, has contributed. (Refer to Annex E for detailed linkages between technical assistance streams and the health system building blocks they strengthen, demonstrating contribution to achieving outcome indicators.)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

36. E4H remains on a strong performance trajectory and highly relevant within the UK-Pakistan modern partnership. With the time remaining under this business case, including consideration for a no-cost extension, the programme will consolidate gains, institutionalise supported reforms, and complete a phased transition embedding delivery within government systems. Health’s central role in building human capital, driving productivity, educational attainment, and workforce participation makes sustained reforms in primary health care, health security, and quality of care critical to achieving inclusive growth and macro-stability under the UK–Pakistan modern partnership principles. E4H’s embedded technical assistance, mutual accountability, and progressive realism continue to deliver strong value for money. Looking ahead, E4H will also advance the sustainable population growth agenda by improving access to and coverage of family planning (FP) services, a priority for both governments. These actions position the programme to consolidate impact and maintain momentum on key health system reforms strongly aligned with the UK–Pakistan modern partnership.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened integrated health security sub-systems
Output number:	1	Output Score:	A
Impact weighting (%):	40	Weighting revised since last AR?	No

Indicator(s)	Milestones for YR3 / (January 2025 - / December 2025)	Progress
1.1: % of approved TAs that are delivered in accordance with the specified deliverables	Fed, KP, and Punjab: 97%	Overall score A / Fed = Met (95%) / KP = Met (100%) / Punjab = Met (95%)
1.2: Priority IHR governance reforms advanced (policy, plans, legal frameworks, monitoring and evaluation frameworks, financial management, accountability)	Federal: The annual IHR monitoring report developed and finalised through Embedded E4H TA. / KP: KP Public Health Act 2017 Revised. / Punjab: Punjab Infectious Disease Act 2020 Revised	Overall score: A / Federal = Met / The annual IHR monitoring report has been developed and approved and a meeting is being convened with different sub-committees within the NIH. / KP = Met / The Public Health Act revised and approved by the KP Department of Health. / Punjab = Partially Met / The Punjab infectious Disease Act was revised and submitted for department’s approval.
1.3: IHR coordination mechanisms established and operationalised	Fed: IHR coordination mechanisms functional (including the Steering Committee of the pandemic fund). / KP: The IHR coordination mechanisms are functional at the provincial level, with evidence of tracking the progress of implementing priority NAPHS II activities in KP. / Punjab: The IHR Technical Working Group/Taskforce is functional, with evidence of tracking progress of implementing priority NAPHS II activities in Punjab.	Overall score: A / Federal = Exceeded target / The Steering Committee for the Pandemic Fund was convened on 29 May 2025, and 100% actions have been completed. / KP = Met / The IHR coordination mechanisms have been notified, meetings minutes confirm implementation of 25% of actions agreed. / Punjab = Met / The IHR TWG/Taskforce has been notified, meeting meetings confirm tracking progress of NAPHS II activities and implementation of 25% actions agreed.
1.4: Enhanced capacities for IHR1.4: Enhanced capacities for IHR	Fed: Surge Capacity Training Design for Managers and Health Facility Staff at the district level to Enhance Pandemic Response and Preparedness at the district level. / KP: At least one Simulation Exercise started for the training of trainers by the E4H teams in one District, with evidence of integration into the overarching Sustainable Training System for government ownership and funding. / Punjab: At least one Simulation Exercise started by E4H-trained teams in one District, with evidence of integration into the overarching Sustainable Training System for government ownership and funding.	Overall score: A / Federal = Partially Met / Surge Capacity Training design developed and approved by the M/o NSR&C and shared with provinces for integration into Sustainable Training System; approval will be done by March 2026. / KP = Met / Simulation Exercise trainer conducted in 1 district with evidence of integration into the Sustainable Training System / Punjab = Met / Simulation Exercise trainer conducted in 1 district with evidence of integration into the Sustainable Training System

37. Indicator 1.1: This is a process-level indicator. This year, a total of 2 Federal and 7 Provincial TA workstreams were delivered (listed in Annex B) to support and strengthen integrated health security subsystems. Beyond completion percentages, quality assurance mechanisms such as compliance checks against agreed Terms of Reference by the third-party verification firm, were used to ensure TA deliverables meet technical and policy standards. The indicator scores A.
38. Indicator 1.2 (Priority IHR governance reforms advanced): In Year 1, E4H worked with the government to develop National Action Plan for Health Security (NAPHS) and its provincial chapters, grounded in Joint External Evaluation (JEE) 2023 recommendations, followed by an in-depth review of IHR-related legislation in Year 2. This analysis identified outdated provisions and the absence of comprehensive public-health Acts in KP and Punjab. In response in Year 3 (2025), E4H supported both provinces to revise their Public Health Acts through an iterative, government-led consultative process with Health Departments, legal teams, and multisectoral stakeholders, strengthening mutual accountability as provinces now lead the revisions through their own approval channels. Once approved, these legal arrangements will be mobilized through implementation plans, capacity-building for enforcement, and integration into provincial health strategies to ensure reforms translate into tangible improvements in public health governance. The updated Acts, termed as Health Security Acts, provide a modern legal mandate based on pandemic learnings for surveillance, immunisation, coordinated One Health (human, animal, and environment) response, integrating laboratory networks, remaining up to date with biosecurity and biosafety, while addressing public health emergency management as a core function of a strengthened health system. As a first in the country, the Federal Ministry of Health, with E4H support, developed a nationwide IHR monitoring report, enabling national tracking of real-time progress on IHR core capacities, supporting continuous assessment between JEE cycles, and embedding routine accountability in the IHR domain. The indicator scores A.
39. Indicator 1.3 (IHR coordination mechanisms established and operationalised): As recommended in the Year 2 Annual Review, IHR coordination mechanisms (previously identified as a critical gap in JEE 2023 and NAPHS) are now functioning as action-oriented platforms at federal, KP, and Punjab levels. At the federal level, the IHR Steering Committee convened the first Pandemic Fund Steering meeting, orchestrated by the Ministry and attended by all key development partners, endorsed a prioritised action plan, and oversaw the implementation of all agreed actions, exceeding the minimum 25% completion. In KP and Punjab, IHR technical working groups were formally notified and, for the first time, brought together One Health stakeholders from health, livestock, agriculture, environment, food safety, and disaster management around a single NAPHS action matrix neatly divided into the sub-groups of ‘prevent, detect, respond’. These TWGs convened meetings, used NAPHS priority actions as a shared results framework, and jointly tracked and unblocked implementation, with both provinces achieving the 25% completion benchmark.
Over time, these platforms are expected to accelerate decision-making, enable smoother processing of IHR-related policies and laws, and ensure that reforms move in a sequenced, government-led manner aligned with NAPHS. Collectively, this marks a significant step toward institutionalising multisectoral governance and coordination for health security. The indicator scores A.
1. Indicator 1.4 (Enhanced capacities for IHR): Building on the NAPHS and its provincial chapters, HR capacities for IHR implementation were strengthened through a two-pronged approach not previously used for emerging disease preparedness in Pakistan. At federal level, the Surge (having enough trained people, supplies and systems to respond to emergencies) Capacity Training Package was finalised, and shared with provinces for integration into Sustainable Training Systems. In KP and Punjab, simulation exercises were conducted in two districts and master trainers were certified, creating a trained cadre that can be rapidly deployed during public health emergencies.
2. The shift toward simulation-based training has begun to strengthen the health system’s ability to prevent, detect and respond to emerging public health threats. This approach has also improved the value for money of preparedness investments, building a scalable and replicable surge-capacity model across federal and provincial levels. These improvements are expected to enhance the provinces’ operational readiness for future pandemics meaningfully.The indicator scores A.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Year 4 milestones (January–November 2026) are yet to be finalised. The Output 1 logframe will be revised to reflect the programme’s planned pivot and transition strategy, as outlined in the main recommendations.
Output 1: Progress on recommendations from the previous AR (if any), lessons learned this year and recommendations for the year ahead.

All recommendations from the E4H Annual Review 2024 have been tracked, with progress either completed or actioned and ongoing as outlined in Annex C. While these recommendations were not structured by output, several have been integrated directly into 2025 TA workstreams and logframe indicators, particularly those relating to strengthening IHR coordination mechanisms, in-service systems, anchoring reforms within government-led structures, and focusing on district-level approach (such as simulation exercises). These actions have contributed to the full achievement of Output 1 milestones this year.
Lessons learned in 2025:

1. Sustained, strategic engagement is critical when Official Development Assistance (ODA) declines. As major development partners withdrew, the risk of losing momentum on International Health Regulations (IHR) reforms increased significantly. E4H’s continued presence, routine engagement, and targeted advocacy ensured health security priorities stayed on the policy agenda, proving that consistent technical stewardship is essential in a constrained financing environment.
2. Practical, field-focused interventions deliver stronger results than policy dialogue alone. Simulation exercises on novel pathogens in KP and Punjab were highly impactful, exposing emergency preparedness gaps and driving renewed commitment to surge-readiness. These exercises show that experiential learning accelerates reform adoption far more effectively than desk-based efforts.
3. Co-creation remains vital for sustainability. Joint development of KP and Punjab Public Health Acts strengthened government ownership and demonstrated that collaborative design fosters mutual accountability and willingness to lead subsequent legal and administrative steps.
4. Trusted relationships and responsiveness are equally important. Despite interest from multiple partners, the Government of KP requested E4H to lead the Public Health Act revision, reflecting the value of credibility, agility, and alignment with government priorities—hallmarks of effective technical assistance.
5. Finally, multi-year, sequential planning ensures continuity and coherence. The five-year National Action Plan for Health Security (NAPHS), introduced in E4H’s first year, provided predictability and balanced investments across Prevent, Detect, and Respond domains. This approach not only delivered measurable improvements in IHR performance but also strengthened federal–provincial coordination and alignment, creating a unified platform for health security reforms.
Recommendations for the year ahead

Establishing a National IHR Authority:
E4H should explore with the Government of Pakistan to implement the recommendations of the IHR assessment (2024), especially the recommendation to establish an IHR authority as a national oversight body with a legal mandate, to be developed through an act of parliament.
Advocating for Increased IHR Financing:
E4H should advocate for greater resource allocation in the IHR space, and this should be highlighted at both national and provincial forums while closely working with provincial health and finance departments.
Sustaining Fleming Fund Investments:
With the closure of the Fleming Fund ( FF), antimicrobial surveillance risks leaving a critical gap in Pakistan’s health security architecture. E4H team should closely work with UKHSA and DHSC with support of BHC I Health Team to identify potential high impact areas of collaboration to sustain FF investments by Q1 2026.
Strengthening Coordination with Global Health Security Partners:
E4H should maintain close coordination with the Pandemic Fund Secretariat, WHO, FAO and ADB, and continue to strengthen national and provincial IHR governance mechanisms for effective delivery of NAPHS priorities and scaling up core capacity benchmarks to maximise synergies and avoid duplication.

Output Title	Strengthened evidence-based decision-making practices
Output number:	2	Output Score:	A
Impact weighting (%):	20	Weighting revised since last AR?	No

Indicator(s)	Milestones for YR3 / (January 2025 - / December 2025)	Progress
2.1: % of approved TAs that are delivered in accordance with the specified deliverables	Fed, KP, and Punjab: 97%	Overall score A / Fed = Exceeded (100%) / KP = Exceeded (100%) / Punjab= Exceeded (100 %)
2.2: Multisectoral and sectoral policies are evidence-informed and aligned to sub-sectoral strategies/plans	Fed: National Digital Health Hub for reporting was developed in collaboration with other development partners and provincial governments. / KP: District Health Office(s) restructuring initiated to enhance governance for strengthening Primary Healthcare and ensuring effective reform implementation / Punjab: Punjab Health & Population Strategy 2025-34 developed through targeted TA from E4H.	Overall score A / Fed= Met The Unified Data Governance Framework was developed and approved by the M/o NHSR&C in the UHC Country Platform convened on 16 Dec. / KP= Partially Met The District Health Office restructuring TA is underway, and the inception report has been submitted and endorsed by the Department of Health. / Punjab = Met / The draft Punjab Health and Population Strategy has been developed and submitted to the Health Department for approval.
2.3: Evidence on policy and programmatic reforms is generated, synthesized, and used to drive performance and accountability	Fed: Budget Analysis 2025/26 Brief and Burden of Disease Analysis Report at National and Provincial Levels. / KP: District health capacity on facility-level budgeting enhanced to improve PHC financing in at least one district. / Punjab: Operational review of the Clinic on Wheels Initiative to inform scale-up supported by the E4H Programme.	Overall score A / Fed= Met / The Budget Analysis Brief and Burden of Disease Analysis Report have been developed and approved. / KP= Exceeded / Facility level budgeting notified and completed in 4 districts. / Punjab = Met / The Clinic on Wheels Operational Plan has been developed and endorsed by the H&PD.
2.4: Strengthened holistic health sector coordination mechanisms at national, provincial, and district levels	Fed: UHC Country Platform convened to endorse the Global Health Initiatives' Strategic findings and build consensus on future actions. / KP: The District Health and Population Management Team (DHPMT) is functional and strengthening PHC in at least one district by December 2025. / Punjab: Institutionalisation of the Donor Coordination mechanism to focus on PHC strengthening with support of the UHC Delivery Unit embedded within the Health and Population Department.	Federal = Met The UHC Country Platform was convened on 16th December 2025, and the Global Health Initiatives Report was presented and endorsed by all stakeholders. / KP = Met DHPMTs have been notified, and minutes of the progress review meetings confirm evidence of implementation of PHC prioritised actions. / Punjab = Met / The donor coordination mechanism is functional, and regular sessions are being convened.

Briefly describe the output’s activities and provide supporting narrative for the score.

1. Output 2 supports the generation and use of evidence to inform policy, planning, financing, and coordination across federal and provincial health systems. It plays a central role in enabling prioritisation across competing areas, improving resource allocation during fiscal constraints, and linking federal reforms with downstream implementation in districts. The output complements and reinforces both Output 1 (health security) and Output 3 (UHC). Across the programme, 16 TAs contributed to Output 2 in 2025, all of which achieved their milestones, this output scores A.
2. Indicator 2.1: This year, five federal workstreams and 11 provincial workstreams have been actioned (Annex-B) and completed. The impact of work undertaken in Output 2 is becoming more visible as the programme matures, with the implementation of the generated evidence and plans. This indicator scores A.
3. Indicator 2.2 (Multisectoral and sectoral policies are evidence-informed and aligned to sub-sectoral strategies/plans): This indicator focuses on ensuring policies are evidence-based and aligned with sub-sectoral strategies/plans. At the federal level, the Digital Health Hub TA delivered a national data governance framework, an operational plan, and a data-sharing agreement, all endorsed by the UHC Country Platform including provinces, marking a major step towards consolidating health information systems across the country. In KP, the restructuring of District Health office was initiated in line with the government’s 5-year Good Governance Reform Roadmap. In Punjab, the draft Punjab Health & Population Strategic Plan 2026–31 was developed, establishing the first unified strategic framework following the merger of the Health and Population Departments. All milestones under 2.2 were met. This indicator scores A.
4. Indicator 2.3 (Evidence on policy and programmatic reforms is generated, synthesised, and used to drive performance and accountability): Federally, the budget analysis and Burden of Disease assessment were completed by the embedded E4H team, providing critical inputs to resource prioritisation and ministerial planning. E4H supported the implementation of KP’s Facility-level Budgeting and Expenditure Management Policy (FLB-EMP) by piloting Facility-Level Budgeting in Peshawar district thereby allocating funds directly to health facilities and replacing the traditional top-down approach. This initiative was aligned with the World Bank’s National Health Support Programme (NHSP) and formally endorsed by the DoH for expansion to four additional districts, an early example of sustained institutional uptake. In Punjab, E4H supported the Chief Minister’s PHC agenda by completing an operational review and evidence-based planning for the Clinic-on-Wheels initiative (approximately 900 mobile clinics) embedding geographic targeting, digital integration, and performance accountability to improve equitable access for underserved communities and advance progress towards UHC. All Year 3 milestones under 2.3 were achieved. The indicator scores A.
5. Indicator 2.4 (Strengthened holistic health sector coordination mechanisms at national and provincial levels): Coordination mechanisms at federal and provincial levels were strengthened under this indicator, in line with the previous Annual Review recommendations. Federally, the UHC Country Platform was convened to endorse the National Health and Population Policy (NHPP), Global Health Initiative (GHI) findings and agree on priority next steps, reinforcing coherence across global health investments. In KP, District Health & Population Management Teams (DHPMTs) were fully activated for PHC oversight at the district-level in five pilot districts, and the Peshawar District Action Plan finalised as a model for district-level PHC governance under the NHSP. In Punjab, donor coordination mechanisms were operationalised through a dedicated coordination platform and portal, enabling improved visibility across multiple financing streams and strengthening alignment with UHC and health systems priorities. All milestones under 2.4 were met. This indicator scores A.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Year 4 milestones (January–November 2026) are yet to be finalised. The Output 2 logframe will be revised to reflect the programme’s planned pivot and transition strategy, as outlined in the main recommendations.

Output 2: Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.
All recommendations from the E4H Annual Review 2024 have been tracked, with progress either completed or underway as outlined in Annex C. While these recommendations were not structured by output, several have been integrated directly into 2025 Output 2 TA workstreams and logframe indicators, particularly those relating to supporting learning and best practice through evidence generation, enhancing government capacity for public private partnerships, supporting operational improvements at the district level without compromising strategic oversight. These actions have contributed to the full achievement of Output 2 milestones this year.

Lessons learned in 2025:
1. The FLB reform builds on BHC-funded SNG PEFA findings that highlighted the need for facility-level expenditure tracking. With E4H support, KP piloted FLB in Peshawar, expanded to four districts, and achieved greater transparency in BHU/RHC spending and repair allocations. The pilot now informs provincial resource planning and has driven KP’s decision to roll out FLB province-wide under the Good Governance Roadmap showing that consistent, well-sequenced BHC support delivers scalable, catalytic reforms.
2. The Clinic on Wheels (COW) initiative involved substantial government investment (including a fleet of 900 vehicles) but suffered from fragmented and inconsistent deployment. With minimal TA, E4H introduced evidence-based deployment through mapping, geotagging, and population-need analysis, ensuring more equitable coverage of underserved areas, preventing duplicate visits, and reducing the waste of government resources. Integration with HISDU dashboards further strengthened planning and accountability. The lesson is that strategic, low-cost technical inputs can dramatically optimise large-scale government programmes.
3. Pakistan lacked a unified data governance system. E4H supported the Ministry to establish one, linked to provinces and backed by an AI-enabled knowledge repository. Ongoing provincial dialogue on data-sharing protocols ensures interoperability and confidentiality, demonstrating that technical design must be paired with sustained coordination.
4. E4H’s first-of-its-kind GHI assessment mapped governance, financing, and sustainability risks across major initiatives (Polio, Gavi, Global Fund). Findings are informing Pakistan’s exit planning through the Global Financing Accelerator and shaping high-level forums like NAC and UHC Country Platform for managed transitions.
Recommendations for the year ahead:
Aligning with Punjab’s Health Reform Agenda
The E4H Punjab programme is closely aligned with the Health Department’s reform agenda, including Community Health Inspectors, Clinic on Wheels, and the Sustainable Training System (STS), and should maintain active engagement to stay ahead of upcoming initiatives. With the Department prioritising outsourcing of service delivery, support will be needed for strategic purchasing and managing private sector partnerships. Opportunities for capacity building and technical assistance should be identified by Q1 2026, with a strong focus on strengthening primary healthcare.
Designing Sustainable Financing Models for PHC
E4H should design and pilot innovative, efficiency-driven financing models to sustain primary healthcare and manage the transition resulting from declining ODA and reduced GHI funding for programmes such as EPI, HIV/AIDS, TB, and malaria while working closely with GFA. Future TAs should prioritise developing domestic financing instruments to reduce donor dependency and optimise local resources. Linking these fiscal solutions to district-level delivery will strengthen transparency, accountability, and effective spending at the BHU and RHC levels.
Strengthening Partnerships for UHC and Health Security
E4H should strengthen and deepen collaboration with multilateral and regional partners—such as WHO, UNICEF, the World Bank, and ADB to ensure Pakistan’s UHC and health security priorities are fully aligned with global frameworks. By leveraging these partnerships, Pakistan can mobilise additional financing, reduce programme fragmentation, and build a more resilient health system. The UHC Country Platform should serve as the central regular coordination mechanism, bringing together all development partners and, where feasible, the Global Health Initiatives to promote joint planning, efficient resource use, and coherent national leadership in advancing health reforms.
Institutionalising Data Analytics for Evidence-Based Decision-Making
E4H should continue the essential support to the Health & Population Department (H&PD) for data analytics and data informed decision-making through the embedded Delivery Unit support and look at avenues on how this support can be institutionalised and strengthened in the future as per needs and demands of H&PD. Strengthen the Delivery Unit’s capability from routine analytics to applied public health analysis and policy advisory, positioning it as a core H&PD function with clear value to decision-making and a pathway for institutionalisation beyond the programme by Q2 2026.

Output Title	Strengthened sub-system practices to implement UHC
Output number:		3	Output Score:		A
Impact weighting (%):		40%	Weighting revised since last AR?		No
Indicator(s)	Milestone 3 of YR3 (January 2024 - / December 2025			Progress
3.1: % of approved TAs that are delivered in accordance with the specified deliverables	Fed, KP, and Punjab: 97%			Overall score A / Fed = Achieved (100%) / KP = Achieved (100%) / Punjab = Achieved (100%)
3.2: Strengthened health workforce as a means to primary healthcare (PHC) for UHC	Fed: Revamping of the Nursing Council Secretariat, including formation of three committees (management, education, and quality assessment). / KP: Validated and functional HRMIS used by DHPMTs for performance management and institutionalised through integration with the sustainable training database, in line with the Essential Package of Health Services Human Resource norms. / . / Punjab: Training of trainers using the integrated training curriculum for community health inspectors within the broader context of the Sustainable Training System, with demonstrable government buy-in.			Overall score A / Federal = Met / The revamping report of the Nursing Council Secretariat is complete and Ordinance by President has been promulgated. / KP = Met / HRMIS analytics have been generated in 4 districts and DHMPTs have been trained on its use. / Punjab = Met / The curriculum has been developed and endorsed by the H&PD and training of trainers for the community health inspectors has been completed for 17 districts.
3.3: Improved practices for ensuring high-quality PHC	Fed: Health Technology Assessment undertaken at the PHC level in collaboration with the National Institute for Clinical Excellence. / KP: PHC Quality Assurance Mechanism institutionalised in one district in line with Quality-of-Care Strategic Plan. / Punjab: MSDS compliance assessment conducted through E4H support, and a roadmap for addressing recommendations developed, prioritised, and institutionalised by the HCC.			Overall score A / Federal = Not Applicable / The Health Technology Assessment work was picked up by UK’s NICE through DBT support, initial findings report has been shared with the Federal Ministry of Health. E4H delayed this workstream to avoid duplication. / KP = Met / The PHC Quality Assurance Mechanism has been integrated into the District Action Plans and DHMPT agendas for implementation / Punjab = Met / The final comprehensive MSDS compliance assessment report has been completed containing recommendations for enhancing quality of care and shared with the Punjab HCC.
3.4: Improved governance for UHC implementation	Fed: Meeting of National Advisory Committee and Interministerial Health and Population Council held for the endorsement of National Health and Population Policy (NHPP) for the next 10 years. / KP: District Action Plan (DAP) developed in at least two districts with E4H support and alignment with NHSP. / Punjab: Punjab Community Health Inspector (CHI) Implementation Plan developed with the involvement of the UHC Delivery Unit. / .			Overall score A / Federal = Met / The NAC meeting was conducted on 2 July and the IMH&PC meeting was held on 16 December; the NHPP was endorsed in both. / KP = Exceeded / District Action Plans have been developed in 4 districts in alignment with NHSP. / Punjab = Achieved / The Punjab CHI Implementation Plan has been developed and endorsed by the H&PD.

Briefly describe the output’s activities and provide supporting narrative for the score.

1. This output tracks TA that strengthens the governance, quality, and delivery of Universal Health Coverage (UHC), with a focus on workforce development, regulatory quality, and district-level implementation. In 2025, the output continued to play a central role in supporting provinces to advance PHC reforms, strengthen institutional capacity, and operationalise quality and governance mechanisms essential for UHC. Across the three components, 23 TAs contributed to Output 3 and met their Year 3 milestones. The output scores an A.
2. Output 3.1: This year, 5 federal workstreams and 18 provincial workstreams have been actioned (Annex-B) that have met the logframe milestones and are on track for completion by March 2026. This indicator scores A.
3. Output 3.2 (Strengthened health workforce as a means to PHC for UHC): The passage of the Pakistan Nursing and Midwifery Council Ordinance (2025) provided a mandate to modernise governance. Building on this, E4H supported institutional strengthening through revamping the Nursing Council Secretariat, establishing three functional management committees to improve governance, clarify accountability, and strengthen the regulatory framework for education and practice ensuring a more capable, well-regulated workforce. In KP, E4H validated and operationalised the HRMIS in four districts, generating reliable, disaggregated HRH data. It then reactivated and trained District Health and Population Management Teams (DHPMTs) to use these analytics for local planning and workforce allocation. This sequential approach, first improving data quality, then enabling its use has created a clear pathway for transparent, efficient, and equitable staff deployment at district level.
4. In Punjab, the first Training-of-Trainers for Community Health Inspectors (CHIs) was completed across 17 districts after finalizing the CHI curriculum with UNICEF. This sets the stage for scaling up under the Chief Minister’s PHC reform agenda and the Primary and Secondary Healthcare Services Act 2025, aiming to deploy skilled CHIs in LHW-uncovered areas. Clear job descriptions are in place, and Health Department, with E4H support, is preparing master trainers to train 20,000 new CHIs. E4H established the training foundation, designed the ToT model, certified master trainers, and set quality standards, while the government will lead cascade training to ensure accountability. The indicator scores an A.
5. Output 3.3 (Improved practices for ensuring high-quality PHC): Under this indicator, improved practices for ensuring high-quality PHC were supported across all delivery tiers. Nationally, the Health Technology Assessment (HTA) TA work is now led by BHC Department of Business and Trade team (DBT) which is drawing on UK NICE expertise to strengthen evidence-based decision making in close collaboration with E4H team.
6. The Quality-of-Care Strategic Plan, developed with E4H support in Year 2, has now been fully embedded in KP government planning. The government has cascaded this framework to districts, and with E4H’s support, quality assurance mechanisms have been formally integrated into the district action plans and agendas of District Health and Population Management Teams.
7. In Punjab, compliance assessments for Punjab Health Care Commission’s (PHCC) Minimum Service Delivery Standards (MSDS) were conducted for 71 public and private facilities. Category I hospitals outperformed Category IIA hospitals, while RHCs and BHUs had the weakest compliance. Private facilities generally performed better than public ones, and the quality-of-care analysis indicated medium-to-high overall performance with good equity and patient-centeredness, though safety and efficiency were weaker. The assessment also revealed that MSDS is complex and challenging to implement in resource-limited settings and that structural compliance alone does not consistently lead to better outcomes. These findings are now driving a shift toward simplified, modular standards and targeted support for primary-level facilities to enable sustainable quality improvement and greater equity in rural care. The indicator scores an A.
8. Output 3.4 (Improved governance for UHC implementation): At the federal level, the National Advisory Council (NAC) convened in July to review reforms and provide strategic direction with participation of all provinces and DG Health Services or officers of similar designations. Embedded E4H advisers supported convening of the Inter-Ministerial Council endorsement of the National Health and Population Policy (NHPP) 2025–35, helping to secure whole-of-government ownership. The policy sets out a 10-year roadmap to reform and modernise the health and population sectors. It sets out a liberalised, resilient, high-quality health system and integrates health, population welfare, nutrition, and health security into one national agenda. This has prompted provinces to plan to develop their policies and strategies in line with the newly approved NHPP and is further supported by E4H in KP and Punjab.
9. In KP, the indicator target was exceeded: District Action Plans were finalised and adopted in four districts (vs. the planned one), linked to NHSP implementation, providing districts with a concrete, costed roadmap to translate provincial UHC commitments into services on the ground. In Punjab, the provincial Community Health Inspector Implementation Plan was completed and adopted, providing a structured blueprint for province-wide rollout of the Chief Minister’s flagship PHC outsourcing initiative. It included clear guidelines on vendor management, public-private partnerships, and performance-based payment mechanisms, which will enhance the quality of PHC services being provided at the community level. The indicator scores an A.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Year 4 milestones (January–November 2026) are yet to be finalised. The Output 3 logframe will be revised to reflect the programme’s planned pivot and transition strategy, as outlined in the main recommendations.
Output 3: Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.
All recommendations from the E4H Annual Review 2024 have been tracked, with progress either completed or underway as outlined in Annex C. While these recommendations were not structured by output, several have been integrated directly into 2025 Output 3 TA workstreams and logframe indicators, particularly those relating to focusing on “high priority” reforms aligned with the National Health and Population policy, enhancing quality of care regulation and service delivery, and supporting district-level PHC delivery to advance UHC. These actions have contributed to the full achievement of Output 2 milestones this year.
Lessons learned in 2025:

1. Earlier FCDO TA (2020) on improving health service delivery identified LHW-uncovered areas and recommended using PPPs to recruit community health workers; hence, the PPP pathway for CHI recruitment was used. This concept was subsequently adopted and piloted by the Government in 2025, illustrating how well-sequenced support translates into government-led innovations.
2. For the CHI cadre, E4H first delivered the standard Master Trainer course, as agreed with the Department. When an additional request emerged for training on the digital tools, E4H responded with flexibility and agility, quickly developing and delivering a tailored digital module within the required timeframe. This responsiveness enabled a smooth rollout.
3. The MSDS TA highlighted persistent gaps in data availability and quality from the private sector, along with clear differences in compliance between public and private facilities. Public-sector BHUs and RHCs consistently showed lower compliance and weaker quality-of-care indicators. With the Primary and Secondary Healthcare Act 2025 now in place and BHUs already outsourced, there is a timely opportunity for E4H to support the PHCC in strengthening regulation and licensing of outsourced PHC facilities to ensure consistent, enforceable standards across the system.
Recommendations for the year ahead:
Institutionalize Transparency and Performance-Driven Management:
E4H should further support Health Sector Reform Unit to institutionalize transparency and performance-driven management under the Chief Minister’s Good Governance Reform Roadmap. This alignment should begin immediately and remain ongoing through 2026. Responsibility: E4H team in collaboration with the KP Department of Health.
Strengthen Strategic Partnerships:
Building strategic partnerships remains essential. E4H should strengthen collaboration with other donor agencies, such as World Bank-funded projects like NHSP/HCIP, to reinforce government reforms and institutional capacity. Exploring partnerships focused on Primary Health Care (PHC) strengthening will enable transformative change aligned with national priorities. These efforts should be initiated in Q1–Q2 2026. Responsibility: E4H Team.
Advance PHC Integration Reforms:
Advancing PHC reforms should remain a core focus. E4H should prioritize EPHS-aligned RMNCH integration at the district level, linking service delivery improvements to routine accountability through District Health and Population Management Teams, District Technical Review Committees, and Quality-of-Care review cycles. Efforts should aim to standardize PHC services and reduce fragmentation by embedding consolidated oversight and problem-solving within existing provincial and district systems, rather than relying on ad hoc project monitoring. Responsibility: E4H Team in consultation with Provincial Health Departments.
Simplify and Operationalize MSDS
Finally, E4H should work closely with the Health Care Commission to simplify and operationalize Minimum Service Delivery Standards (MSDS) for resource-constrained facilities. This includes strengthening mechanisms and legislation to secure routine data from private and outsourced facilities, including for notifiable diseases, and conducting follow-up assessments to examine changes in MSDS compliance after outsourcing BHUs and RHCs. These actions should be implemented during Q2–Q4 2026. Responsibility: E4H Team in consultation with Provincial Health Care Commissions.
## D: VALUE FOR MONEY (1 page)

VfM performance compared to the original VfM proposition in the business case
VfM remains central to E4H’s delivery approach, ensuring optimal use of resources while achieving health system reform objectives. The E4H programme revised its VfM Framework in June 2024. The finalised framework consists of 10 indicators across five ‘E’ themes of economy, efficiency, effectiveness, cost effectiveness, and equity with qualitative and quantitative data sources.
Key cost drivers and performance
With the E4H KP and Federal in its third year of implementation phase and Punjab in its second year of implementation, the key cost remains consultant team costs. The table below shows the percentage of the total programme budget and reimbursable costs that were allocated to Technical Assistance (TA).
Components	% TA of total budget	% TA reimbursables of total budget	% of remaining other costs including core team, KPI, operating reimbursables etc
KP & FED	57%	4%	39%
Punjab	62%	3%	35%

A quick snapshot of percentage of TAs cost by output as per components is as follows:
Cost of TAs by Output	Output 1	Output 2	Output 3
% of TA cost / for KP & Federal	20%	44%	36%
% of TA cost for Punjab	7%	52%	41%

TA spending remains balanced across Outputs, with the largest share under Output 2 (strengthened evidence-based decision-making), reflecting E4H’s core focus on evidence generation and policy translation.
### Economy
1. From an economy perspective, E4H continued to drive down unit costs while protecting quality. Blended fee rates fell year-on-year i.e. £263 in KP & Federal (vs £271, ~3% lower) and £254 in Punjab (vs £283, ~10% lower) and remained below the senior-national ceiling of £308.28, evidencing an efficient mix of senior, mid and junior expertise deployed across Outputs. Delivery choices also generated direct savings: embedding personnel within ministries and departments (with no office overheads charged) yielded £22,854 in KP & Federal and £180,000 in Punjab during the first three quarters of 2024/25.
2. The programme minimised discretionary spending through strategic consolidation and contracting. For example, the National Advisory Committee meeting held on 2 July 2025 served as a single platform to disseminate multiple workstreams including Global Health Initiative findings, the National Health and Population Policy, the Blueprint for the Pakistan Health Information, Knowledge and Practice Hub, and the Pakistan Multisectoral Health Workforce Strategy to more than 80 high-level stakeholders simultaneously. This approach avoided the venue, logistics, and facilitation costs associated with hosting multiple events, saving an estimated £9000. Organised at the federal level, it ensured participation from national and provincial stakeholders, enabling more effective information flow from national to provincial tiers. In Punjab, consultants supporting the UHC Roadmap and TA identification were engaged on lump-sum, deliverable-based contracts, improving cost predictability and sidestepping higher cumulative day-rate expenditure while maintaining responsiveness. Overall, tighter rate control, an optimised grade mix, and lean delivery/contracting models lowered average costs and delivered better value for money on the economy dimension.
### Efficiency
1. E4H demonstrated strong performance on efficiency by maintaining timely delivery and process discipline across a lean operational structure. The programme consistently met the FCDO benchmark of two technical reviews per deliverable (ToRs and KPIs), even where multiple iterations were needed to ensure quality.
2. The Quality Assurance (QA) team and core teams played a pivotal role in improving turnaround times and maintaining workflow discipline through standardised templates, red-flag tracking, and rapid review cycles. Where consultant capacity gaps emerged, QA provided direct surge support (including restructuring drafts, addressing analytical gaps, and coaching consultants) to sustain delivery momentum as per FCDO programme team’s guidance.
3. These systems reduced delays, improved consistency across outputs, and strengthened quality without expanding management overheads. The result is an agile, high-performing delivery mechanism that achieves significant output volume through a compact and cost-efficient structure.
### Effectiveness
1. In 2025, E4H deepened the integration of Value for Money principles within its technical assistance delivery, with a strong emphasis on effectiveness, sustainability, and institutional ownership. At the federal level, the programme transitioned from a fragmented, consultant-driven model to a fully embedded technical support approach within the Ministry of NHSR&C. This shift enhanced coordination, reduced transaction costs, and strengthened institutional learning while ensuring the timely delivery of key outputs such as the UHC Monitoring Report, HRH Snapshot, Budget Analysis Brief, and IHR Monitoring Report. Embedded expertise has also enabled regular convening of the UHC Country Platform and IHR coordination meetings, establishing institutional mechanisms for governance and policy dialogue that will endure beyond programme timelines.
2. By consolidating expertise and embedding it directly within government structures, E4H accelerated delivery, improved quality assurance, and enhanced alignment with ministerial priorities. This model not only strengthened ownership but also ensured that technical outputs informed real-time decision-making, demonstrating how adaptive and demand-driven support translates into more sustainable system change.
3. In KP, effectiveness was demonstrated through strategic adaptability. The TA on IHR governance and revision of the Public Health Act maintained momentum despite external dependencies by aligning with WHO on a consortium model, preventing duplication, and ensuring complementarity. Similarly, E4H reoriented catalytic support to strengthen district-level capacities directly linked to NHSP Disbursement-Linked Indicators (DLIs) and Annual Review recommendations, enhancing the connection between service delivery performance and systemic reform.
4. In Punjab, the programme applied the same adaptive management ethos. The TA on Minimum Service Delivery Standards (MSDS) expanded beyond its original Terms of Reference at the request of the Punjab Health Care Commission with potential impact of improving quality of care in approximately 70,000 registered health facilities , highlighting the responsive approach undertaken by E4H. Likewise, the Clinic-on-Wheels TA revised its geographic focus from flood-affected areas to Rawalpindi, Faisalabad, DG Khan, and Bhakkar to improve feasibility and equity impact.
5. Across all provinces, these examples illustrate how E4H’s flexible, government-led, and results-oriented approach ensured that technical assistance remained relevant, high quality, and directly responsive to evolving national and provincial priorities. The programme’s ability to adapt rapidly, maintain strategic coherence, and deliver institutionalised outputs underscores strong performance on the effectiveness dimension of Value for Money.
### Cost Effectiveness
The following case study can help gauge the effectiveness of one of the TAs under the programme: Cost-Effective Scale-Up of CHI Training: TA for the Community Health Inspector (CHI) programme, which is also marked as a milestone for FY 25/26 in the FCDO Country Business Planning (CBP) document, was designed for province-wide coverage. Through strategic sequencing, E4H delivered Training of Trainers (ToTs) in 16 districts - training 173 Master Trainers, while UNICEF covered the rest. This approach ensured timely delivery, avoided duplication, and maximized resource efficiency. Strong early performance led the Health & Population Department to request E4H to consolidate ToTs in the remaining 20 districts, leveraging existing systems and lessons learned. This demonstrates high value for money: minimal TA costs catalysed government-led scale-up, streamlined implementation, and optimized large-scale investments.
### Equity
1. Equity is a defining principle of E4H and is systematically embedded across its technical assistance design, planning, and delivery frameworks. Rather than treating equity as a standalone theme, the programme integrates it into policy, data systems, institutional processes, and frontline delivery, ensuring that reforms address gender, poverty, and geographic disparities in access to health services.
2. At the policy and governance level, E4H has institutionalised equity within the country’s health planning architecture. Embedded technical support to the Ministry of NHSR&C has driven the development of equity-focused outputs such as the HRH Snapshot 2025 and the UHC Monitoring Report, both of which incorporate gender and One Health lenses and produce district-level Service Coverage Index (SCI) estimates. These analyses have directly informed the National Health and Population Policy (2026–35) and the revised NHSP PC-I, which now integrate equity indicators, district targeting frameworks, and equity-sensitive resource allocation guidance.
3. At the service delivery and community level, E4H-supported innovations have directly expanded access for underserved populations. In Punjab, the Clinics-on-Wheels initiative extended primary healthcare services to peri-urban, low-income, and flood-affected communities, particularly targeting women and children. Lady Health Supervisors and Lady Health Workers are being trained to use new dashboards and micro-planning tools, enabling household mapping of missed clients and improved follow-up of referrals. Similarly, the programme has strengthened HISDU’s analytical capacity to generate disaggregated data, highlight service gaps, and guide planning at provincial and district levels.
4. E4H supported screening of 38,000 children in special education schools exposed major unmet health needs. With E4H support, Punjab institutionalised an integrated care system introducing treatment protocols, referral pathways, Electronic Medical Record (EMR) dashboards, and district committees. Over 8,000 children have received services, 5,000 are under treatment. This government-led model ensures coordinated, inclusive care and stands as a replicable approach for equity in health planning
5. In Khyber Pakhtunkhwa, district action plans are being developed, district system strengthening is underway, and quality-of-care mechanisms are being developed for the NHSP prioritised low-SCI and high-vulnerability districts, linking TA support directly with service delivery improvement in hard-to-reach areas and ensuring timely responses to outbreaks and essential service continuity for vulnerable populations. Other initiatives such as the Human Resource Management Information System (HRMIS) validation and strengthening across ten districts in KP, is helping identify female workforce thereby enabling evidence-based planning for equitable workforce distribution.
6. By linking policy, data, and delivery, E4H has closed the loop between high-level commitments and last-mile action. This has improved access, quality, and continuity of care for marginalised women, children, and remote populations, directly advancing Pakistan’s progress toward Universal Health Coverage (UHC) and reducing inequities across geography, gender, and income.
Assessment of whether the programme continues to represent value for money
Overall, investment in reforming, strengthening, and regulating Pakistan’s health system continues to deliver strong value for money (VFM). Without these interventions, progress would be slower, less integrated between federal and district levels, and poorly coordinated across financing and programming streams from multiple stakeholders and the Government of Pakistan. Technical Assistance (TA) under the programme has improved the efficiency and effectiveness of domestic resources and partner investments, including those from the World Bank, by aligning priorities, reducing duplication, and enhancing accountability. In its final planned year, E4H’s strategic focus on supporting the transition to a new partnership model, building accountability for quality and efficiency in health service delivery, and simplifying the health system financing landscape is assessed to offer the highest VFM. Additionally, investing in a robust evidence base for E4H outcomes will strengthen the VFM case for successor programmes and inform other health sector partners, ensuring future investments deliver measurable impact.

E: RISK

The overall risk rating for the programme is ‘Moderate’. The FCDO E4H team manages a comprehensive risk register for the programme, assesses risks under the FCDO risk framework and specifies detailed mitigation measures to ensure all risks sit within risk appetite. There is an agreed risk escalation mechanism in place with all partners; but currently there are no risks beyond the FCDO and BHCI set appetite. Monthly check-ins with all partners reviews risk mitigation and learning. Since the technical partnerships component hasn’t been mobilised, no Due Diligence Assessment (DDA) has been carried out under the programme and hence there are no risks associated with DDA. The main risks of the programme and the appetites against each category are outlined below.

Risk Category	FCDO Appetite	BHC Islamabad Appetite	Programme Risk Appetite
Strategy and Context	Receptive	Eager	Receptive
Policy and Programme Delivery	Receptive	Eager	Receptive
Public Service Delivery and Operations	Cautious	Receptive	Cautious
People	Cautious	Cautious	Cautious
Safeguarding	Cautious	Cautious	Cautious
Financial and Fiduciary	Cautious	Receptive	Cautious
Reputational	Cautious	Cautious	Cautious

1. Strategy and context risk: Frequent government leadership changes across all geographies have been a constant risk for the programme, combined with ODA funding and changes to the health donor landscape, affecting commitments to the delivery of the programme. To address this, the embedded E4H team provides rapid re-orientation, works closely with the federal and provincial steering committee structures, and upholds standard operating processes with government partners. The residual risk is moderate.
2. Policy and Programme Delivery Risk: There is a risk that unclear expectations around TA support beyond the Steering Committee can lead to gaps between government needs and project delivery. By clearly identifying government focal points for each TA workstream and regularly sharing success metrics, the E4H teams secure buy-in, and align expectations for achievable results. The residual risk remains moderate.
3. Public Service Delivery and Operations: Frequent turnover of government officials can disrupt relationships and delay MERL activities. To reduce this risk, E4H and NHSP focus on building strong ties with institutions rather than individuals. Institutional linkages help maintain continuity and ensure progress, even when personnel change mitigating the risk. The residual risk is moderate.
4. People risk: E4H’s key people risk is recruiting qualified consultants with the right expertise which has been made difficult by ongoing brain drain and uncompetitive pay due to low framework rates. To manage this, the team taps into Palladium, OPM, and Integrity’s extensive consultant databases and follows a rigorous, competitive hiring process. Quality assurance, clear expectations, and outreach to experienced professionals help mitigate the risk, which remains moderate.
5. Safeguarding risk: Implementing partners have safeguarding policies and a joint reporting mechanism in place. All partners have provided safeguarding training to all employees, ensuring all safeguarding cases are processed in alignment with the FCDO framework. Reported safeguarding incidents in the reporting period were escalated to Reporting Concerns for assessments, investigations and recommendations are being followed and tracked. The residual risk is moderate.
6. Financial and Fiduciary risk: To safeguard against any fraud and the mismanagement of funds that may be relate to favouritism in hiring of consultants, the E4H programme team frequently monitors the IPs to ensure their financial systems are in a good place for sound management of development funds. FCDO's policy on fraud, corruption and anti-bribery has been shared with IPs who also receive regular training refreshers from the FCDO finance team. The residual risk is moderate.

Update on Partnership Principles

1. The Partnership Principles Assessment (PPA) sets out FCDO’s assessment of commitments made by the Government of Pakistan to four principles: (1) reducing poverty and progress towards achieving the Sustainable Development Goals; (2) respecting human rights and international obligations; (3) strengthening financial management and reducing the risk of funds being misused through weak administration or corruption; and (4) strengthening domestic accountability. We continue to promote FCDO objectives, partnership principles and international obligations with all our government partners and use the PPA to inform our bilateral aid talks with the GoP. This programme does not provide direct on-budget support. However, it does support the strengthening of health systems and works with the GoP to strengthen policies, procedures and guidelines. The experience of this programme corroborates the findings of the PPA with regard to SDG progress and rights.
2. Our overall judgment is that the Federal Government of Pakistan is demonstrating a credible commitment to two of the four partnership principles namely: poverty reduction and financial management. However, there are causes for concern in certain areas of human rights where the trajectory of progress has been downward. Progress towards the attainment of the SDGs and poverty reduction is proceeding at a slow pace with the rapid population growth creating more pressure. On public financial management and anti-corruption, the direction of travel is broadly neutral, although some evidence indicates improvements. There has been mixed progress towards strengthening domestic accountability with a reduction in civic space and media freedom.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Performance and Delivery against planned timeframe
1. The E4H programme is now in its third year of implementation for KP & Federal component and in the second year of implementation for Punjab and for the MERL component. Palladium (in consortium with OPM), manage both contracts related to KP & Federal level and have performed effectively aligning TAs with the demands of the government and aligned with review recommendations, focusing within the remit of the programme outputs. Integrity has progressed well in terms of developing and implementing a workplan suited for the needs of E4H and NHSP programmes, for this year.
2. All IPs share regular financial and programme management reports with the E4H PMT on a timely quarterly basis, as agreed. The programme’s financial management and controls continue to perform effectively. However, during the July to September 2025 quarter, some underspend variances occurred due to delays in finalising the TA workplans owing to uncertainties around the ODA budget and a strategic shift toward district-level TA, aligned with last year’s AR recommendations. FCDO programme team introduced a new mechanism in August 2025, that refined the process of forecasting, resulting in bringing the variance within set thresholds of under 5% variance in October 2025. Key Performance Indicators (KPIs) are being met with reports submitted on time.
Commercial Performance
1. Both implementing partners have demonstrated good performance throughout the Annual Review (AR) period, consistently meeting agreed targets. A key area identified for improvement across all Palladium contract has been the limited in-country presence of senior leadership. To address this, a Senior Technical Specialist has been deployed by the supplier for on-ground leadership, and Programme Director Dr Jabulani Nyenwa has begun quarterly visits to Pakistan. However, following the AR, this setup may need rethinking as strategic, sustained leadership on the ground is essential to effectively manage evolving needs.
2. All technical assistance (TA) targets are assumed to have been met across Khyber Pakhtunkhwa, Punjab, and the federal level by January 2026. Integrity also delivered all agreed outputs within the stipulated timelines. Annual contract amendments are progressing forward, with phase one of key personnel changes contract amendments now completed; and phase 2 contract amendments related to perform as reflecting the programme’s transition from inception to full implementation. These revisions once finalised will enable necessary adjustments to workplans and budgets, ensuring alignment with evolving programme needs.

Financial performance
Overall, the programme has spent £4.82 against the allocated budget of £5.7m in FY2025/26. The spend percentage of the programme is 72.82% as of December 2025.The team expects to spend its full allocation, based on forward plans, by March 2026. At the start of this financial year, the programme experienced a slow start due to the evolving district-level implementation approach and delays in budget confirmations. Programme is expected to spend major amount of £1.59m the last quarter as most TA teams have now been approved and onboarded, allowing activities to progress at pace.
The summary on financials is outlined below:
FY 2025-26	FY 2026/27
E4H KP& Federal / Allocation: £2,500,000 / Spend: £1,834,490	E4H KP& Federal / Allocation: £3,000,000
E4H Punjab / Allocation: £2,500,000 / Spend: £1,806,213	E4H Punjab / Allocation £3,500,000
MERL E4H / Allocation: £700,000 / Spend: £510,059	MERL E4H / Allocation: £500,000
Total allocation: £5,700,000 / Total spend to date: £4,150,762	Total allocation: £7,000,000

All IPs provided quarterly progress reports which include a detailed and accurate section on financial progress. In addition to the quarterly progress reports, the programme management team (PMT) reviewed finances monthly through expenditure reports and accruals submitted. The regular reporting and progress reviews enabled the programme to remain on track. Palladium and Integrity submitted internal audit reports in October 2025.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
1. E4H has embedded a robust Monitoring, Evaluation, Research and Learning (MERL) system to drive evidence-based decision-making, accountability, and adaptive programming. Delivered through Integrity, MERL covers both E4H and the World Bank-supported NHSP, institutionalizing systematic monitoring and independent verification since April 2024. Third-party verification exercises across all active components have strengthened credibility and data integrity, while operational research such as the ongoing ‘Rethinking Primary Health Care’ study aims to generate actionable insights for policy and delivery.
2. MERL includes four core functions: (1) six-monthly field verifications and DLI checks; (2) demand-led operational research to identify health system gaps; (3) evaluations to inform adaptive programming; and (4) learning platforms/events for cross-programme knowledge exchange. Despite budget constraints delaying some evaluations, mid-term review for NHSP was completed, with most recommendations acted upon. Recent lessons emphasise building institutional capacity through training and documentation and leveraging technology by digitizing assessment tools and integrating them into health platforms.
3. A joint E4H–World Bank learning event on Universal Health Coverage (UHC) was held in March 2025, creating a platform for sharing best practices and fostering networks among federal, provincial stakeholders, and partners. Post-event feedback underscored the need for regular national learning events to promote cross-provincial exchange and structured collaboration, highlighting that such convenings address a critical gap in the health sector.
4. Asset monitoring and control
The E4H PMT conducted the detailed review of assets in October 2025. The report observed that the IPs are following FCDO’s asset management guidelines. The full report is available and is attached as Annex D.

Date of last narrative financial report	KP/Federal: 10 January 2026 / Punjab – 12 January 2026 / MERL – 12 December 2025	Date of last audited annual statement	Palladium: 1 July 2024 to 30 June 2025 - received on 15 October 2025 / Integrity: 1 July 2024 to 30 June 2025 - received on 15 October 2025

Annexes:
Annex A: List of Acronyms
Annex B: Full status of TAs
Annex C: AR recommendations status
Annex D: full asset spot check report
Annex E: TA mapping

## Annex A: List of Acronyms
AIDS	Acquired Immunodeficiency Syndrome
AMP	Aid Management Platform
AR	Annual Review
BC	Business Case
BHCI	British High Commission Islamabad
BMGF	Bill and Malinda Gates Foundation
BRAVE	Building Resilience and Addressing Vulnerability to Emergencies
CDC	Centre for Disease Control
CHI Community Health Inspectors
CHAP	Climate Health Adaptation Plan
CHVA	Climate and Health Vulnerability and Adaptation Assessment
CHW	Community Health Worker
CPD Continued Professional Development
CM	Chief Minister (of Pakistan)
CoP 29	Conference of the Parties 29
DAC	Development Assistance Committee
DAFPAK	Delivering Accelerated Family Planning in Pakistan
DALY	Disability-Adjusted Life Year
DARE	Data and Research in Education
DCP	Disease Control Priorities
DEV Tracker	Development Tracker
DGHS	Directorate of General Health Services
DLRs	Disbursement Linked Results
DoH	Department of Health
DRAP	Drug Regulatory Authority of Pakistan to separate
E4H	Evidence for Health
EPHS	Essential Package of Health Services
FCDO	Foreign, Commonwealth and Development Office
Fed	Federal
FLB Facility Level Budgeting
GAVI	Global Alliance for Vaccination
GEMFA	Global Evaluation and Monitoring Framework Agreement
GFATM	Global Fund for Aids. TB and MALARIA
GFF	Global Financing Facility
GHI	Global Health Initiatives
GoP	Government of Pakistan
GP	General Practitioners
H&PD Health and Population Department
HCC	Healthcare Commission
HIS	Health Information System
HMIS	Health Management Information System
HRH	Human Resources for Health
HRMIS	Human Resource Management Information System
HSSP	Health Sector Strategic Plan
IDSR	Integrated Disease Surveillance and Response
IHSDP	Improve Health Service Delivery in Pakistan
IMDP	International Multi-Disciplinary Programme
IHRA	Islamabad Healthcare Regulatory Authority
IHR	International Health Regulations
IPs	Implementing Partners
JEE	Joint External Evaluation
KMU	Khyber Medical University
KP	Khyber Pakhtunkhwa
KPI	Key Performance Indicators
LHW	Lady Health Worker
LTTA/STTA Long Term Technical Assistance/ Short Term Technical Assistance
M&E	Monitoring and Evaluation
MERL	Monitoring, Evaluation, Research and Learning
MIS	Management Information System
MPH	Master of Public Health
MSDS	Minimum Service Delivery Standards
MSHWS	Multi-Sectoral Health Workforce Strategy
MTR	Mid Term Review
NAPHS	National Action Plan on Health Security
NICE National Institute for Health and Care Excellence
NDHH National Digital Health Hub
NHPP	National Health and Population Policy
NHSP	National Health Support Programme
NHS	National Health Services
NHV	National Health Vision
ODA	Official Development Assistance
OECD	Organisation for Economic Cooperation and Development
OPM	Oxford Policy Management
PC-1	Planning Commission-I
PFM	Public Financial Management
PHA	Provincial Health Accounts
PHC	Primary Healthcare
PM	Prime Minister (of Pakistan)
PMDC	Pakistan Medical and Dental Council
PMT	Proxy means test
PNWC	Pakistan Nurses and Midwives Council
P.P.	Percentage Points
PPA	Partnership Principles Assessment
PPP	Public Private Partnership
QoC	Quality of Care
QoD	Quality of Delivery
SC	Steering Committee
SDGs	Sustainable Development Goals
SNG2	Sub National Group 2
SRO	Senior Responsible Owner
TA Technical Assistance
TB	Tuberculosis
TOC	Theory of Change
ToR Terms of Reference
UHC	Universal Health Coverage
UK United Kingdom
UK-PK	United Kingdom - Pakistan
UKHSA	UK Health Security Agency
UNICEF	United Nations Children's Fund
USAID	United States Agency for International Development
VfM	Value for Money
WB	World Bank
WHO	World Health Organisation
WRAP	Water Resource Accountability in Pakistan
Y2	Year 2
Y3	Year 3