Title: Africa Regional Climate and Nature (ARCAN) programme
Programme Value £ (full life): £250 million.		Review date: 29 July 2025
Programme Code: 300808	AMP start date: 12 January 2022	AMP end date: 31 March 2028

Summary of Programme Performance

Year	2022	2023	2024	2025
Overall Score	A	A	A	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-300808 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007484.xlsx

## A: SUMMARY AND OVERVIEW

Programme Description

ARCAN is a regionally managed FCDO programme designed to address the interconnected challenges of climate change, nature loss, and resilience in Africa through a coordinated, transboundary approach across five key pillars: water, nature, clean energy, weather and climate information, and adaptation finance. In 2024/25, ARCAN spent £41 million. This included increasing investments in projects delivering on priority UK climate and nature objectives, including clean energy, better climate and weather forecasting and reducing deforestation. The programme is central to delivering the UK’s International Climate Finance (ICF) commitments. With anticipated reductions in ODA following the 2025 Spending Review, and the reduction in ODA by other donors, ARCAN will need to adapt its delivery model, placing greater emphasis on partnerships and strategic alignment with evolving UK development priorities.

Summary supporting narrative for the overall score in this review

This Annual Review (AR) assesses progress made between April 2024 and March 2025. Rather than scoring the programme solely against output performance, this AR scores ARCAN against three ‘performance areas’, each with its own weighting.

Performance Area	Weighting	Score
Contribution to meaningful change: progress towards long term outcomes.	30%	A
Delivery: quality and timeliness of activity and output delivery. Each ARCAN project is scored individually, with its contribution to the ARCAN score weighted by the value of FCDO’s commitment.	60%	A
Actionable learning: the programme is effectively using evidence and learning to remain on track.	10%	B
Annual Review Score		A

Overall ARCAN has scored a ‘A’ in this Annual Review.

The programme scored an A on the contribution to meaningful change (30%), reflecting good progress across its portfolio. Programmes are advancing toward their intended outcomes, with notable achievements in clean energy access – SEFA has connected 5.7 million people since 2020 – and in mobilising or influencing over $16 billion in climate-related finance. CIWA has strengthened governance of shared water resources and influenced $6.4 billion in investment. FFF restored or protected 111,000 hectares of forest and farmland in 2024, supporting locally led adaptation. Progress in protecting the Congo Basin forests has been slow but the UK is playing a leading role in reform. WISER exceeded expectations for supporting countries to act on weather and climate information, with a significant scale-up planned in 2025. These achievements demonstrate ARCAN’s growing impact in building resilience to climate change, protecting nature and energy access across Africa.

ARCAN scored an A on delivery (60%) due to good overall progress across its seven implementing partners, with five of seven projects either meeting or exceeding their targets for the 2024/25 reporting year. Highlights include:

- SEFA achieving record levels of project approvals and new electricity connections.
- WISER demonstrating strong institutional uptake of weather and climate information services, supporting over 165 institutions.
- CIWA supporting six relevant transboundary institutions, including the Nile River Basin and in the Southern African Development Community (SADC) to improve flood risk and early warnings.
- AAAP made steady progress influencing public investments in climate-resilient infrastructure.
- FFF surpassed its targets for supporting forest and farm producer organisations.
- CAFI progress on implementing some activities aimed at reducing pressure on forests, including 163,189 households benefitting from cleaner cooking to date. CAFI is also pioneering new ways of protecting the forest including launching a $100m private sector investment facility. However, progress on implementing policies to reduce deforestation remains slow.
The programme scored a B on actionable learning (10%) primarily due to gaps in the quality of evidence generated as well as consistency and utilisation of learning processes.

Previous Annual Review Recommendations:

Recommendations from 2024	Progress
Improve donor Coordination	FCDO strengthened coordination with donors across AAAP, CIWA, FFF, and SEFA and led CAFI’s presidency in 2024-25.
Cross-Cutting Engagement	FCDO advisers have increased collaboration across sectors, including a joint humanitarian-climate mission.
Locally-Led Adaptation	A new ARCAN project was developed to support locally-led adaptation, but stopped due to ODA cuts.
Safeguarding	The Common Approach to Protection from Sexual Exploitation, Abuse and Harassment has been promoted and discussed with all implementing partners.
Fraud and Risk Management	FCDO reminded partners of their obligations to prevent fraud, loss, and aid diversion.

Major lessons and recommendations for the year ahead

ARCAN has made good progress across its portfolio but faces challenges in sustaining impact amid reduced donor funding and the difficult context for private sector finance in Africa. In response, the programme must prioritise sustainability of outcomes and refocus to deliver on new FCDO development priorities with a smaller budget.

Key Lessons

1. Sustainability Risks: Many ARCAN outcomes rely heavily on donor funding to be sustained. With expected reductions in ODA (UK and other donors), there is a pressing need to enhance African ownership and capacity to deliver outcomes.
2. Private Sector Finance Challenges: Mobilising private investment has proven more difficult than anticipated in the BC due to worsening macroeconomic conditions globally and especially Africa. This affects all ARCAN projects, particularly SEFA and SRMI.
3. Learning System Gaps: While foundational MEL systems are in place, implementation has been uneven. Evidence products have not always been timely or actionable, limiting their influence on programming.
4. Synergies and Policy Influencing Underutilised: Opportunities for cross-programme collaboration (e.g., between WISER, FFF and CIWA) and for combining UK programming and policy influencing to achieve change have but not been fully realised.

Priority Recommendations for 2025/26

1. Reassess ARCAN delivery model, considering (by October):
  1. Outcomes of 2025 Spending Review and midline evaluation.
  2. Reduction of donor support across some delivery areas.
  3. Implications around private sector mobilisation.
  4. Support for partnerships with countries and regional institutions.

1. Strengthen MEL (by end 25/26)
  1. Ensure MEL products are demand-led and co-developed between FCDO and implementing partners.
  2. Allocate time and resources for implementing and tracking recommendations.
  3. Complete Transformational Change Assessments (by end of 2025)
  4. Push partners on GESI targeting and reporting.
2. Enhance Sustainability (ongoing in 25/26)
  1. Advocating for capacity building, knowledge transfer and institution strengthening across projects.
  2. Use transformational change assessments to develop a plan for sustaining outcomes for all projects beyond ARCAN support.

1. Enhance Synergies and Policy Influencing Across ARCAN (throughout 2025/26)
  1. Facilitate joint learning between programmes with overlapping goals, focusing on WCIS (WISER), Water (CIWA) and agriculture (FFF).
  2. Clearer articulation of how ARCAN funded partners are supporting on wider multilateral initiatives in Africa – such as SEFA and SRM to Mission 300.
  3. Seek opportunities for combining our programming with FCDO policy expertise and diplomacy to advance climate and nature objectives e.g. water sector.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The ARCAN Theory of Change (ToC) (see diagram in Annex) is based on achieving change across five pillars (weather and climate information systems, nature, transboundary water management, energy transition, and climate finance), delivered by seven implementing partners (IPs). The outcome indicators were updated after the last AR to better align with the Business Case targets and to make it easier to assess progress of each IP.
Evidence from the first phase of the midline evaluation (March 2025) and implementing partner results suggest the TOC remains generally valid. However, some of the assumptions are being tested, particularly on political momentum to tackle global climate change given the loss of US support and engagement; levels of private sector finance given worsening investment climate globally and in Africa; and continued availability of climate resources given the planned reductions in UK, US and other donor ODA.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The initial allocation for ARCAN in FY 24/25 was £24.3m, rising to £38.6m. Additional money was used to support climate action across Africa by driving systemic change in finance, energy, water, resilience, and land use. While the methodology to assess this transformation is still being finalised, early evidence across the ToC is promising. Highlights include CIWA’s use of satellite data and new coordination groups to improve groundwater management; CAFI’s support for forest governance reforms and ecosystem service payments; FFF’s work to build sustainable, income-generating producer organisations; AAAP’s integration of adaptation into $9 billion of investments; SEFA and SRMI’s efforts to de-risk renewable energy projects; and WISER’s co-produced early warning systems that are scaling across vulnerable urban communities. These examples suggest ARCAN is on track to deliver lasting, scalable impact, with a full assessment due by the end of 2025.

ARCAN is well aligned with the Foreign Secretary’s priorities on climate and nature but over the coming year we will consider how to embed sustainability and better support partnerships across the portfolio. As part of this evolution, ARCAN will also need to strengthen its equity focus – particularly in CAFI and WISER, which were rated as “not quite” meeting expectations on gender and disability inclusion – and ensure that lessons from the current phase inform more inclusive and resilient programming going forward.

Previous Annual Review Recommendations:

Recommendations from 2024 Annual Review	Progress
Remove reference to greenhouse gas emission attribution in the ARCAN Theory of Change outcomes, in line with the original Business Case, and remove this impact indicator.	Completed.
MEL Unit to prioritise support to ARCAN projects to strengthen reporting on the ICF indicator 15 on transformational change.	In progress. Transformational change methodology has been developed and starting to be rolled out to projects.
FCDO and MEL Unit to develop a plan to facilitate relevant lesson learning and collaboration between projects, focusing on weather and climate information systems.	Ongoing. ARCAN wide lesson learning event on weather and climate information services held in March 2025.
Workshop how the energy pillar interventions create impact and value to the wider society and economic development to inform assessment of their outcomes.	Changed. This was taken forward through impact case studies for SEFA and SRMI conducted by the FCDO energy lead.

Lesson learnt and recommendations for next year:
- Refresh the Theory of Change in early 2026 following the mid-term evaluation findings and confirmation of implication of ODA budget reductions.
- Complete the transformational change assessment of all ARCAN projects, and use this to prioritise efforts to increase the likelihood of sustainability and scale of the most promising interventions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
ARCAN is strongly aligned with the UK’s objective of ‘ensuring a liveable planet free from poverty’. It key to delivering our strategic priorities for climate and nature including:
1. Climate resilience by increasing coverage of early warning and preparedness (WISER), and mainstreaming climate adaptation into investments (AAAP, CIWA);
2. Green growth by developing an investable pipeline and leveraging investment for clean energy (SRMI, SEFA);
3. Nature by halting and reversing forest loss (CAFI, FFF);
4. Cross-cutting priorities of agriculture and water security (FFF, CIWA);
The concept for a project to support nature-based solutions for adaptation was developed in 2025 but stopped due to budget cuts.
ARCAN is vital to meeting the UK’s International Climate Finance (ICF) commitments. All except one of the projects are making good progress towards their objectives. Well performing projects working in priority sectors have received additional support.
## C. DETAILED SCORING

Performance area	Contribution to Meaningful Change
Score:	A
Impact weighting (%):	30%	Weighting revised since last AR?	Yes, Increased from 20% to 30%.

See Annex 1: Detailed Scoring for assessment against results framework indicators.

Summary of programme’s Contribution to Meaningful change

Each ARCAN project has indicators in line with their main contribution to the ARCAN Outcomes. These have limitations: a) in most cases, including SEFA, SRMI, CIWA and CAFI, historical targets have not been updated by partners to reflect the changed delivery context or changes in project focus; b) the time between enabling activities and real world impact were underestimated; c) and the indicators do not capture the broad range of progress toward outcomes. The Contribution to Meaningful Change assessment against the indicators considers this context.

Summary of progress by outcome

Outcome: Increase in protection of natural resources
CAFI	Good historical progress on area of land under improved policies, plans, management or protection measures, but continued slow progress on area of forest under sustainable management (no data for 2024).
FFF	Strong progress on area of forest and farms supported.
Outcome: Transition of energy sector towards zero carbon power
SEFA	Strong progress on increasing access to electricity (primarily through small scale solar), but slower than expected progress on renewable capacity installed due to fewer large projects resulting from the challenging investment climate
SRMI	Progress made on supporting governments with the enabling environment for renewables, but slower progress on renewable capacity supported due to the challenging investment environment.
Outcome: Strengthened resilience of population
FFF	Better than expected progress on the number of people supported to cope with the effects of climate change.
CIWA	Good progress on number of transboundary water institutions supported.
WISER	Exceeding targets for strengthening use of weather and climate information (WCIS) by institutions. Lower than expected number of people accessing/using WCIS due to delays in data collection.
Outcome: Mobilisation of climate and natural resources related investment
SEFA	Mobilisation of investment good in the context, but lower than original targets.
CIWA	On track for 24/25 but moderately off-track against cumulative target
AAAP	More public finance influenced than expected, but less private finance.

Overall, the Contribution to Meaningful Change performance area has scored an ‘A’. ARCAN has made good overall progress towards all its Outcomes, with some exceptions.

ARCAN is making variable progress on increasing in protection of natural resources. FFF has protected or restored 235,000 hectares of forests and farmland, with strong progress in 2024. CAFI has almost met its target to facilitate land use plans for 10 million hectares. However, it has only put 146,279 hectares under sustainable land use, well behind the cumulative target of 300,000, representing continued difficulties in delivery.

Good progress is being made on the transition of energy sector towards zero carbon power. SEFA is doing well at increasing access to electricity, connecting 5.7m people since 2020, including nearly 1m in 2024, significantly over its target. Progress is slower than expected on installed capacity, but SEFA still expects to reach its close to its 3,000 MW target by 2030. SRMI has supported six countries to launch seven procurement processes for energy infrastructure, a high proportion of all similar procurement processes launched across Africa, although they lack proper targets for this work.

ARCAN is making good progress on supporting institutions to strengthen the resilience of populations to climate change. CIWA is making solid progress on improving the management of water resources, strengthening 10 more transboundary institutions in 2024/25. Its analysis is achieving significant impacts, but often years after the work. WISER is meeting or exceeding its targets to strengthen organisational access and use of weather and climate information (WCIS) but delays in data collection means it cannot yet report on the number of individuals reached.

ARCAN is successfully mobilising and influencing climate and nature finance, with much more success mobilising public rather than private sector finance. AAAP has ensured that adaptation is addressed in $9 billion of mainly public infrastructure investments, with half of which was achieved in 24/25, putting it on track to meet its 2025 target. However they are influencing much less private finance than expected. CIWA has influenced $6.4 billion of investment for water resources in Africa, with a further $11 billion in the pipeline, meeting its 24/25 milestone. Since 2020 SEFA has mobilised $800m in co-investment, primarily from the multilaterals/public sector. This is impressive given the much harder environment for private sector investment than when the original ambitious target of $1.8bn was set in 2020.

Describe any changes to this assessment during the past year, and any planned changes as a result of this review.

The indicators and targets were revised over the year to focus on overall achievements of partners against their own targets. Previously the indicators were focused on assessing UK attribution against the International Climate Finance indicators. The shift has enabled a more meaningful analysis of progress against partner expectations, of progress towards Business Case targets, and a fuller picture of UK influence. In 2025 we will prioritise evaluative work to understand of how ARCAN can maximise the sustainability and scale of these outcomes.

 Progress on recommendations from the previous AR:

Recommendations from 2024	Progress
Improving Indicators and GESI Disaggregation:	Ongoing. Indicators were revised and priorities, with a greater focus and clarify around real-life verses expected results, and the attribution of the ARCAN programmes.
Deepening Understanding of ARCAN’s contribution to meaningful change	Ongoing. The ARCAN MEL unit is currently carrying out evaluation case studies on sustainability and scale (FFF); sustainability (AAAP); Value for money of Nature Based Solutions (AAAP); Influence (CIWA); Gender and Social Inclusion (CAFI); and sustainability and resilience (WISER).
Outcome Milestones and Qualitative Reporting	Ongoing. Priority outcome targets have been aligned with Business Case goals and agreed with partners. Qualitative reporting has improved through new indicators and case studies, though data disaggregation remains weak.
Communications with UK Embassies	Exceeded. Over 25 tailored updates were shared with UK embassies, far surpassing the target of two. These included country-specific briefings, regional updates, engagement in country.

Lesson learnt and recommendations for next year:
- Mobilising private sector finance is proving much more difficult than originally anticipated in the ARCAN Business Case and in partner targets. This could reflect an optimism bias in target setting, and worse than expected macro-economic climate resulting in much less private sector investment in Africa than expected. All relevant ARCAN partners (AAAP, CIWA, SEFA) are struggling to secure private sector investment. As part of the planned revision of the Theory of Change, the team should relook at assumptions and approach around the role of the private sector, and consider the implications for sustainability of interventions.
- ARCAN has made some good progress towards its outcomes. However, the sustainability of many of its achievements are still heavily dependent on donor financing and expertise, which is at risk with reduced donor budgets (from the US, UK and others). As part of the TOC review, ARCAN will need to review its priorities and approach given the changed ODA context, including how to increase African delivery and ownership.

Performance area	Delivery
Score:		A
Impact weighting (%):		60%	Weighting revised since last AR?	Decrease from 75% to 60% (the weighting of Delivery is planned to decrease each reporting year as the relative importance of delivering outcomes and learning increases)

See Annex 1 for results reported against ARCAN results framework indicators. All results are for total project performance, and are not pro-rata to the UK contribution.

Summary of Performance against Delivery

ARCAN project	Share of Delivery Score	Score
Cooperation in International Waters in Africa (CIWA) (World Bank)	12%	A
Central Africa Forest Initiative (CAFI) (UNDP)	22%	B
Forest and Farm Facility (FFF) (FAO)	5%	A
Weather and Climate Information Services in Africa (WISER Africa)	28%	A
Sustainable Risk Mitigation Initiative (SRMI, part of ESMAP)	11%	A
Sustainable Energy Fund for Africa (SEFA) (AfDB)	10%	A+
Africa Adaptation Acceleration Programme (AAAP) (GCA)	12%	B
Overall Score		A

ARCAN project		Cooperation in International Waters in Africa (CIWA) (World Bank)
Score		A
	Project Weighting %:		12%	Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

CIWA scored an ‘A’ for 2024/25, meeting or moderately exceeding 7 of 10 active indicators and not meeting expectations of 3 indicators. While some targets were not met due to strategic shifts or World Bank guidance, CIWA continued to strengthen existing interventions and made progress toward transformational change in transboundary water governance. Despite operating in a challenging context–including conflict, climate shocks, and humanitarian crises–CIWA demonstrated resilience and adaptability.

The programme’s Theory of Change (ToC), centred on the ‘three Is’–institutions, information, and investments–was revised in 2024. The World Bank shifted focus from quantity to quality of outputs, deepening existing initiatives. CIWA made notable progress in institutional strengthening, supporting ten transboundary institutions and enhancing analytical tools and data systems in six others. It also advanced regional information systems, including flood and drought monitoring in the Nile Basin and groundwater data platforms in SADC.

Although investment finance influenced (CIWA 1) remained unchanged, CIWA 2 reported 310,000 new expected beneficiaries from projects in the Horn of Africa and SADC. CIWA also expanded its work on biodiversity, gender, and climate resilience, including support to South Sudan and the Okavango Basin. These efforts reflect a growing focus on inclusive, pro-poor, and climate-smart water management.

Describe any changes to this output during the past year, and any planned changes as a result of this review

CIWA adopted a revised ToC and results framework (CIWA 2.0), introducing more qualitative indicators and aligning more closely with ARCAN and UK climate finance priorities. New indicators distinguish between direct and indirect beneficiaries and better capture institutional strengthening and resilience outcomes. CIWA also improved integration of cross-cutting themes like gender, biodiversity, and conflict sensitivity.

Progress on recommendations from the previous AR

Recommendations from 2024 AR	Progress
Strengthen measurement of climate outcomes and ICF KPIs	Completed.
Improve GESI-related MEL and disaggregation	Completed.
Shape implementation of biodiversity framework	Completed but ongoing.
Understand and support private finance mobilisation	Partially completed.
Strengthen in-country linkages with other ARCAN programmes	Completed but ongoing.
Share CIWA lessons with other World Bank programmes	Partially completed.
Support CIWA 2.0 development	Completed.
Demonstrate UK leadership in donor coordination	Completed.

Lessons Learned

CIWA has already met many cumulative targets from previous years. However, some 2024 milestones were poorly defined under the old framework. The new CIWA 2.0 results framework addresses this with a more qualitative approach. Limited progress on finance mobilisation and beneficiary numbers reflects the upstream nature of CIWA’s work and a shift toward smaller, more bankable projects. The programme is also expanding beyond infrastructure to include sectors like tourism and livelihoods.

Recommendations for the Year Ahead
1. Support CIWA’s monitoring and reporting at impact level and engage with ARCAN MEL Unit on CIWA 2.0 Indicator 5 to inform the 2025/26 results framework.
2. Foster collaboration with other ARCAN partners like WISER and FFF.
3. Deepen understanding of private sector finance mobilisation through AC meetings and strategic pipeline discussions.
4. Share CIWA lessons with other World Bank programmes, including dissemination of the MDTF learning paper.
5. Prioritise support to national-level institutions and focus on short-to-medium term outcomes.
6. Translate regional mandates into national-level activities to enhance regional learning and cooperation.

ARCAN project		Central Africa Forest Initiative (CAFI) (UNDP)
Score		B
Project Weighting %:	22.2% of share of Delivery score		Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

In 2024, CAFI made progress in several key areas, including meeting its targets for institutional improvements and land under improved planning or protection policies. It also exceeded its 2026 target for improved cookstove distribution in the DRC, reaching over 163,000 households and creating more than 1,000 jobs through clean cooking and agroforestry initiatives. CAFI expanded its private sector engagement, launching a $100 million investment facility and piloting Payments for Environmental Services (PES) mechanisms. Forty projects were active during the year, with four new implementing organisations accredited.

However, CAFI fell short on most other milestones, particularly on direct beneficiaries, where it remains significantly off track. Gender sensitivity also declined, with only 22% of projects classified as gender responsive. A GESI case study is planned for 2025 to address this. While deforestation appears to be stabilising, forest degradation is increasing, driven by insecurity and land tenure challenges. CAFI has responded with risk mitigation measures such as land rights mapping and FPIC protocols.
[note] Central African Forest Initiative Annual Report 2024 p.35 URL: https://mptf.undp.org/sites/default/files/documents/2025-06/2024_cafi_annual_report_english_final.pdf

At the country level, CAFI continued to support national reforms and policy dialogue. In the DRC, 83 of 117 recommendations from the 2023 Letter of Intent review showed progress, though forestry-related milestones remain delayed. In Cameroon, a new LoI was signed, but project approvals were slow. In Gabon, activities resumed following the 2023 coup, but delivery challenges persist. The Republic of Congo made progress on forest monitoring and agroforestry, while the Central African Republic launched a new climate finance fund.

Despite challenges, CAFI improved its MEL systems, including public access to its Metrics Hub and spatial monitoring tools. However, data gaps remain, particularly around validated land use plans and accurate beneficiary reporting. Overall, while CAFI demonstrated commitment to reform and innovation, delivery remains uneven, justifying a B.

Progress on recommendations from the previous AR
Recommendations from 2024 Annual Review	Progress
UK Presidency and Strategic Coordination	Ongoing. The UK has effectively used its CAFI presidency to drive delivery improvements and align efforts with the Congo Basin Forest Action (CBFA) programme. The UK presidency has been extended to Spring 2026.
GESI Case Study	Not completed in 2024. Delivery is now being scoped for 2025 by the ARCAN MEL Unit.
Improving MEL Systems	Progress has been limited due to staffing changes. Some engagement has taken place on sustainable land management indicators and civil society engagement, but broader MEL improvements are pending.
Support to FONAREDD MEL Capacity	Not prioritised in 2024 due to limited resources. Potential support may be scoped in 2025 if capacity allows.
Joint Working with CBFA	Done. Regular coordination is in place between CAFI, CBFA, regional programmes, and embassy climate advisers to ensure a joined-up HMG approach to the Congo Basin Forests.
Improving Communication Between Secretariats and Donors	Ongoing. Productive engagement with the CAFI Secretariat and consistent CRP meetings by FONAREDD have supported improved communication.
Risk Management	Ongoing. A risk register was developed in 2024, though its use remains limited. The UK is advocating for stronger risk and conflict sensitivity measures in the upcoming CAFI mid-term review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Significant changes were CAFI’s focus on private sector and piloting PES mechanisms. PES were tested in the PIREDD Plateaux project in DRC which will provide up to $600,000 for people implementing sustainable land use practices. A PES toolkit and monitoring platform is under development using remote sensing, with a launch delayed until 2025. Five projects are set to use the new tool, demonstrating the potential of PES in the region.

Lessons learned this year:

There are knowledge sharing and learning synergies between CAFI and other ARCAN- and FCDO-supported programmes. This includes FFF on community forestry interventions and the energy pillar in relation to CAFI’s energy-related projects. CAFI co-ordinates well with UK-funded forest programmes, including FGMC, IFSLU, and the Congo Basin Forest Action Programme, particularly due to having a climate adviser role in the region.

In 2024 FCDO successfully engaged senior staff and Ministers in HMG, countries of the Congo Basin and donor countries on the opportunities and challenges for CAFI and more widely across the Congo Basin, for example at a conference at Wilton Park, ahead of COP30 in 2025.

Recommendations for the year ahead:

Continue to use the UK presidency of CAFI to set clear direction for the Fund, drive for improvements on efficiency, project delivery, accountability, MEL and to build trust among donors and partners. Our role has been extended from 2025 to 2026, continuing to offer the UK outsized influence over CAFI.

We will take action to improve gender sensitivity, including pushing CAFI to push implementing organisations to do better and focussing an upcoming evaluative case study in 2025 solutions to improving CAFI’s gender sensitivity.

1. Focus on quantified data and results driven programming:
  1. CAFI should implement the CAFI PES policy and tools over the course of 2025 to deliver on the region’s expectations and showcase at COP30.
  2. CAFI should review methodologies for calculating the number of direct beneficiaries reached, and the 2026 target for direct beneficiaries reached.

Begin preparations for new phases of LoIs starting in 2026; ROC, Gabon and DRC.

ARCAN project		Forest and Farm Facility (FFF) (FAO)
Score		A
Project Weighting %:	5%		Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

The Forest and Farm Facility (FFF) is a multi-donor initiative that supports forest and farm producer organisations (FFPOs) to strengthen livelihoods and climate resilience through sustainable forest management. Managed by a consortium of FAO, IIED, IUCN, and Agricord, FFF is currently in its second phase (2018–2026), with ARCAN funding focused on African countries. In 2024, FFF achieved its highest-ever disbursement of US$16.3 million, nearly doubling the previous year. The programme has made strong progress across its three outcome areas, particularly in policy advocacy, enterprise development, and climate adaptation. It has substantially exceeded its targets for policy influencing in favour of FFPOs; number of FFPOs supported; and people supported to cope with the impacts of climate change. Progress on area of forest and farmland protected by FFF support is slightly behind the 2024 milestone but the 2026 target is on track.

FFF has played a key role in influencing policy and legal reforms that benefit FFPOs, such as securing land tenure agreements in Madagascar. It has also significantly exceeded targets for supporting FFPO enterprises, especially in Togo, with 45% of supported businesses adding value to their products and 33% led by women. In the Gambia, FFF-backed women’s groups have adopted organic farming and biofertiliser production, boosting incomes and reducing input costs. The number of people benefiting from sustainable land management and climate adaptation has surged, with a threefold and 32-fold increase respectively since 2022, demonstrating FFF’s growing impact on resilience and livelihoods.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second year of FFF reporting under ARCAN. Covid and personnel issues caused problems with delivery at the start of phase 2, but there has been significant progress over the last two years. FFF operates on cumulative targets rather than annual targets. As per suggestions in the previous annual report, two indicators (number of female lead enterprises and number of forest and farm producers receiving improved social or cultural services) were dropped or merged in this year's results.

For the remainder of Phase 2 of the FFF the focus should be on sustainability, ensuring any remaining funds are directed embedding learning and activities began under FFF. The focus should also be on ensuring that lessons are learned from what has worked in the first two phases of the FFF, and ensuring these lessons are made available to other development actors and used to enhance any development of a potential third phase of the FFF.

Lessons learned this year:

Fieldwork undertaken in 2024/25 (Madagascar and Zambia) has confirmed that scaling and replicating the agro-forestry business model supported by FFF is very challenging. There are also questions around the sustainability of agro-forestry initiatives unless there is a clear and well established market in country for the projects produced. There are clear opportunities to exploit synergies between FFF and other ARCAN projects working with communities on resilience activities (WISER).

Progress on recommendations from the previous AR:

Recommendations from 2024 Annual Review	Progress
Outcome Milestones and Monitoring	Progress is underway. The MEL Unit has worked on refining indicators and targets, though it’s unclear if regional sub-targets for Africa have been formally requested. Further follow-up is planned.
Governance and Risk Management:	Some progress has been made. FAO is working on developing a risk appetite framework, which is expected to strengthen overall programme governance.
M&E Systems Assessment	In progress. The ARCAN MEL Unit has begun assessing FFF’s data systems to improve monitoring and evaluation.
No-Cost Extension and Budget Plan:	Completed. All donors have agreed to the extension and revised activity and budget plan.
Cross-Programme Synergies	Initial steps taken. A learning event in March 2025 brought together FFF, WISER, CIWA, and AAAP to explore collaboration on climate resilience. Engagement has also occurred at country level, notably Madagascar.

Recommendations for the year ahead:

1. FCDO to continue engaging in the delivery of Phase 2, working with other donors in pushing to embed sustainability across outcomes. We will also engage in the development of phase 3.
2. The FFF have suggested that their M&E systems could be improved to better showcase the FFF’s results. This should be a priority for them as the end of phase evaluation goes on and the second phase comes to an end.
3. The FFF aims to trial a new finance mechanism in 2025, which combines FFF, private finance, and agricultural credit union financing. While it is late in phase 2 to be trialling new approaches, this one is aligned with FCDO aims to leverage greater amounts of climate finance. As such, this move should be encouraged.
4. The FFF should make sure it protects where possible its current staffing levels to ensure the programme can end Phase 2 strongly. Recruitment is under way for a new FFF Lead within the FAO, but until that can be completed the existing lead will work with the current team to deliver results. It is vital that there are no further significant staffing gaps if the FFF is to deliver a strong finish by end of 2026.

ARCAN project		Weather and Climate Information Services in Africa (WISER Africa)
Score		A
Project Weighting %:	28%		Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

In FY24/25, WISER 3 made strong contributions to building resilience and adaptive capacity in climate-vulnerable communities across Africa. The programme achieved significant progress in institutional engagement, capacity building, and behavioural change, with 136 organisations reporting improved access to weather and climate information services (WCIS) and 165 using WISER-generated evidence in decision-making. WISER also embedded gender equality and social inclusion (GESI) through co-production approaches, such as ResAlert’s intersectional “Missing Voices” methodology, which helped tailor early warning systems to the needs of marginalised groups.

While institutional uptake and policy integration of WCIS exceeded expectations, individual-level access and use fell significantly short of targets, but this is due to delays in data collection rather than underperformance. WISER did report substantial increases in reach, including over 166,000 individuals with improved access and 35,000 using WCIS to inform decisions. While these numbers remain below expectations, this is due to shifting the timelines of midline/endline project evaluations, in some cases linked to agreeing uplifts in project funding, rather than any indication that projects are reaching fewer people than anticipated. We expect reported numbers to significantly increase in the next reporting period. Projects like ECREA and DARAJA demonstrated strong local impact, and midline evaluations that have been completed, such as in Senegal, showed increased awareness and use of WCIS. Overall, WISER continues to deliver meaningful results, with growing evidence of its role in enhancing preparedness and resilience at both institutional and community levels.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

At COP29, the UK Minister for Development announced a £30 million uplift for WISER Africa over three years, prompting a significant scale-up of the programme. This includes extensions to successful projects like DARAJA, ECREA, and ResAlert, and a major expansion of the small grants component to support locally led innovation. A key strategic shift is the launch of four new regional projects: ActionFirst (focused on near-term weather and disaster risk management), PASS (seasonal forecasting), CLICK (long-term climate information and adaptation), and BDRM (sustainable financing for WCIS). These projects are designed to strengthen leadership and capacity at all levels while aligning with global initiatives like the UN’s Early Warnings for All.

In parallel, a global evaluation of WISER, completed in October 2024, highlighted the need to strengthen evidence on sustainability and resilience-building. In response, WISER has begun developing a Story of Change on anticipatory action in urban Africa and plans further analysis in FY25/26 in collaboration with FCDO, the ARCAN MEL provider, and the Met Office. These efforts aim to ensure that WISER’s expanded portfolio delivers long-term, transformative impact across Africa.

Progress on recommendations from the previous AR:

Recommendations from 2024 Annual Review	Progress
Scaling Up WCIS and Cross-Sector Collaboration	In progress. WISER has made strong progress in scaling up weather and climate information services following the funding uplift. Regional projects are in contracting, core grants like DARAJA and ECREA are delivering impact, and the Technical Assistance and Partnerships (TAP) resource has been strengthened. Staffing gaps at the Met Office have been addressed, and collaboration with sectors such as agriculture, disaster risk finance, and urban resilience is expanding.
Improving Value for Money and Synergies	In progress. WISER has actively explored synergies with other ARCAN programmes. A March 2025 learning event facilitated collaboration with FFF, CIWA, and AAAP. Regional projects are designed to align with broader resilience goals, and examples like ECREA’s integration of agri-met services into district planning show practical cross-sector impact.
Responsiveness to FCDO Posts	Completed (but ongoing work needed). WISER has improved engagement with FCDO Posts through tailored annual updates and regional sessions, enabling Posts to influence scale-up planning and align activities with local priorities.
Measuring Resilience and Transformation	In progress. Progress has been made on KPI 4 (resilience) and KPI 15 (transformation). Six projects were assessed for transformational outcomes, with four showing partial evidence. Resilience gains include increased WCIS use, community co-production, and strengthened institutional capacity.
Advancing GESI Standards	Done.(but ongoing work needed). WISER continues to embed gender equality and social inclusion (GESI) through local partner capacity building and inclusive design. A network of GESI champions is active, and the “Missing Voices” approach in Senegal has improved accessibility of early warning systems for marginalised groups.

Lessons learned this year:

There are strong synergies between WISER and other ARCAN projects such as FFF, AAAP, and CIWA, highlighted during a March 2025 learning event, with further opportunities for collaboration and knowledge-sharing, including with FCDO-funded programmes like CLARE. Embedding co-production insights and strengthening long-term stakeholder partnerships will enhance impact, especially during the WISER uplift. Media partnerships are also key to increasing WCIS visibility and reach. While recent successes in securing funding–such as through ECREA and DARAJA–are promising, the increasingly constrained funding landscape makes sustainability, including financial and other dimensions, a critical focus and risk area.

Recommendations for the year ahead:

1. Partnerships: WISER should actively seek partnerships with existing initiatives, including FCDO-funded ones, to improve WCIS access and use. This could enhance efficiency and impact, especially in areas like anticipatory action and climate-resilient infrastructure.
2. Risk & Financial Management: WISER should enhance risk management and financial monitoring, focusing on accurate forecasting and partner collaboration. It should also build partner capacity in safeguarding and fraud reporting.
3. GEDSI Integration: WISER should strengthen intersectional GEDSI approaches (beyond gender) in project design, delivery, and MEL. This includes promoting leadership, empowerment, and inclusive WCIS service provision, especially in new regional projects.
4. Stakeholder Engagement: WISER should improve engagement across the WCIS value chain, including unexpected stakeholders. It should also enhance feedback mechanisms to ensure adaptability and responsiveness.
5. Media & Communication: WISER should improve media engagement and communication planning, involving the Met Office, FCDO, and partners. This includes giving FCDO posts advance notice of noteworthy activities.

ARCAN project	Sustainable Risk Mitigation Initiative (SRMI, part of ESMAP)
Score	A
Project Weighting %:	11%	Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress is reported is against the 2024 World Bank year (from August 2023 to July 2024). SRMI forms part of the wider ESMAP programme, which focuses on building capacity and helping to accelerate new projects in the energy sector across developing and emerging markets. Outputs from SRMI form part of ESMAP’s wider contribution to Mission 300, a landmark initiative launched by the WB and AfDB to expand energy access and rapidly scale up investment in the sector in Africa.

Overall SRMI made reasonable progress against 2023/24 indicators. It supported six countries to improve their enabling environment for renewable energy in 2023/24, exceeding the milestone of three. Three renewable energy projects were prepared for investment, meeting the milestone. SRMI is providing extensive transaction advice to African governments and leading a capacity-building programme across 12 countries. This includes training officials and utility companies through a leading African RE investment centre in Cape Town, meeting the 2023/24 milestone for this activity. SRMI closely missed two milestones for supporting new risk mitigation instruments (two rather than three) and knowledge products shared (one rather than two). The project did not provide any support to countries to develop roadmaps including maximising socio-economic benefits derived from renewable energy, substantially missing the milestone of three.

Private sector investment in energy infrastructure depends on a stable and predictable environment, which has been lacking since 2020 due to macroeconomic instability and limited public sector capacity in energy planning and regulation. These challenges have significantly altered expectations set out in the ARCAN Business Case, with increased risks, reduced returns, and a greater need for public sector support. As a result, many original milestones are now outdated. SRMI has made some changes to its work which are not reflected in the SRMI logframe. We have agreed that this year to substantially update the monitoring framework to reflect donor results expectations.

Financial innovation has become increasingly important due to systemic issues like unbankable utilities and foreign exchange risks. SRMI is collaborating with DFIs such as IFC and MIGA to improve access to guarantees. Technical assistance remains vital, supporting both project-level implementation and national energy planning, with success stories like Burkina Faso highlighting the transformative potential when political will aligns with infrastructure development.

The final FCDO contribution to SRMI was in 2024. We will remain active in engaging with the project and shaping its outcomes, including through FCDO’s wider engagement with ESMAP.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, the scope of SRMI’s activities has expanded significantly, prompting planned changes to its monitoring framework. The review recommends broadening SRMI’s monitoring to capture the full range of its work, including capacity building, transaction advice, project-level support, country-level roadmaps, and technical assistance for grid modernisation and reinforcement. Additionally, there will be a focus on assessing the influence of SRMI advisers embedded within the wider ESMAP programme. To better reflect the complex and adaptive nature of the programme, both implementing partners will continue developing case studies and impact stories as a more suitable alternative to traditional theory of change approaches, which are often too linear for this context.

Progress on recommendations from the previous AR:

Recommendations from 2024 Annual Review	Progress
FCDO should work with ESMAP and SRMI to better understand: / (i) SRMI’s influence on IDA-funded ESMAP projects, (ii) its contribution to ESMAP’s overall strategy, and (iii) how it balances upstream enabling work with project-level support.	Progress has been made on understanding SRMI’s contribution to ESMAP and we have clarified that it is working almost exclusively upstream in reaction to the challenging enabling environment for on-grid renewables.
FCDO and the ARCAN MEL Unit should engage SRMI and ESMAP to improve assessment of SRMI’s progress, including: / (i) refining the ARCAN results framework, (ii) linking upstream work to project finance leverage, and (iii) incorporating milestones and results into the 2025–30 ESMAP Business Plan.	Not yet done.
FCDO lead adviser should propose quarterly MEL calls for all donors, led by ESMAP’s MEL lead.	Not done. There are regular calls between the FCDO adviser and the SRMI team.
FCDO should consider future involvement in SRMI in light of wider HMG investments in ESMAP, as ARCAN’s final payment is in 2024.	FCDO’s final contribution to ESMAP was in 2024. We continue to be engaged with SRMI to shape its outcomes.
FCDO should deepen engagement with SRMI and ESMAP to understand SRMI’s strategic role, project delays, and the balance between upstream and downstream activities.	Strong progress has been made. FCDO now has a detailed understanding of SRMI’s work, including transaction advice, capacity building, and financial de-risking. Improved reporting and renewed momentum are evident as post-COVID delays ease and World Bank loans are approved.

Lessons learned this year:

Expectations need to be adjusted for both outputs and outcomes. FCDO has made significant progress understanding the challenges, and changing mandate, of SRMI this year. Economic uncertainty is likely to continue and condition not remain similar in the RE sector.

Recommendations for the year ahead:

FCDO’s final planned contribution to SRMI occurred in 2204. However the ARCAN Energy Adviser will continue to engage and we will continue to assess the progress on this component in subsequent ARCAN ARs.

The energy transformation roadmaps featured in SRMI’s results framework are government-owned and serve as key reference points for initiatives like Mission 300. A key action for SRMI and ESMAP is to ensure that support for these planning efforts is well-coordinated, avoiding duplication and enhancing overall effectiveness.

Expectations need to be adjusted for both outputs and outcomes. FCDO and the ARCAN MEL Unit should engage SRMI and ESMAP to improve assessment of SRMI’s progress and update the results and indicators.

ARCAN project	Sustainable Energy Fund for Africa (SEFA) (AfDB)
Score	A +
Project Weighting %:	10%	Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score

SEFA’s activities in 2024 reflect strong performance and adaptability, justifying an A+ score against the project outputs. SEFA has already substantially exceeded its 2025 target for new energy connections, reaching 5.7 million people through concessional investment (3.3 million target) largely driven by post-COVID recovery platforms like the Off-Grid Recovery Platform and the Africa GoGreen Fund.

SEFA is on track to meet the overall target for committing $105 million concessional finance by 2025, already exceeded the targets for green baseload and energy efficiency respectively. It has substantially exceeded the 2030 target for the number of people in direct employment as a result of its investments (over 14,000 jobs compared to a target of 2,000). It is on track to meet cumulative milestones for technical assistance projects/programmes for energy efficiency and has already exceeded the green baseload target, but is not on track against the green mini-grids target.

SEFA’s approach under its current SEFA 2.0 model has enabled faster disbursements and results, supported by a strong pipeline and new donor engagement. Innovative approaches, including equity tenders and renewable energy certificates, are helping address viability gaps and public sector constraints. SEFA’s complementary role to SRMI and its catalytic impact across Africa’s energy landscape further support the high score. Ongoing impact studies will enhance future monitoring and learning.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, SEFA’s 2025 annual work plan was approved by the Donor Council, with no significant changes made to the output. Planned changes as a result of this review include streamlining SEFA’s indicators to better reflect the trust fund’s activities and achievements. This will involve incorporating SEFA’s own KPIs–such as approvals, disbursements, innovations, and the use of intermediaries to leverage impact–into the results framework. Additionally, outdated milestones based on the 2019 Strategic Framework will be updated to ensure relevance by the next annual review, and redundant indicators will be removed.

Progress on recommendations from the previous AR:

Recommendations from 2024 Annual Review	Progress
FCDO should engage with SEFA on the anticipated shift in portfolio allocations outlined in the draft 2025 workplan, and regularly assess SEFA’s pipeline, disbursement capacity, and project risks.	Complete: FCDO has had strong engagement with SEFA, including fieldwork and hosting the Governing Council in February 2025. This has improved visibility into SEFA’s diverse portfolio.
FCDO should engage in the mid-term review of SEFA 2.0, focusing on the scalability of its consultant-heavy delivery model and the implications of SEFA taking on procurement responsibilities.	Complete. The mid-term review was presented but is ongoing. SEFA’s rapid scale-up–approving $130 million in 2024 and building a similar pipeline for 2025–has highlighted capacity constraints. The team continues to rely on consultants, and in-sourcing procurement has helped speed up delivery but requires additional resources.
FCDO is considering secondments to SEFA, funded through the Climate Compatible Growth Programme, to support delivery capacity.	Ongoing. An FCDO funded secondment into SEFA should commence will commence 2025.

Lessons learned this year:

- As with ESMAP, SEFA’s delivery is playing a key role in helping to prepare and develop new projects that will contribute to Mission 300 goals on energy access and stimulating new investment in the sector.
- SEFA is building a strong portfolio of approvals, but disbursements are slow due to a lack of legal capacity in AfDB.
- Disbursement delays are longer for technical assistance than concessional investment, reflecting government ownership of the procurement process. SEFA and SRMI have sought to speed TA delivery by bringing technical procurement in-house, but there is a balance to be struck given the importance of country “ownership”.
- Ambitions for financial innovation (guarantees and risk instruments), are in jeopardy as grant funding is cutback by conventional donors. New, blended finance models may be required to finance this work.

Recommendations for the year ahead:

1. Continue to champion SEFA and explore how we can best support its contribution to Mission 300 alongside other vehicles with UK funding such as ESMAP, BII and PIDG
2. Actively engage with the mid-term review findings, including any potential option analysis for SEFA 3.0, particularly consideration of the funding gap and the possibility of SEFA becoming a blended finance vehicle.
3. Monitor cash-balance indicators for emerging capacity constraints and disbursement issues.
4. Monitor the impact of FCDO-supported secondments into SEFA starting in 2025.
5. Develop better understanding of the portfolio’s expected vs actual results.
6. Actively engage in conversations about scaling up the SEFA model, protecting SEFA’s ambitions, and focussing resource of impactful activities.
7. Review our assumptions around the volume of private sector investment available for renewables in Africa, and consider our policy/programmatic response.

ARCAN project	Africa Adaptation Acceleration Programme (AAAP) (GCA)
Score	B
Project Weighting %:	12%	Weighting revised since last AR?	Yes

Briefly describe the output’s activities and provide supporting narrative for the score.

In 2024, AAAP, implemented by the Global Center on Adaptation (GCA), continued to deliver across its four pillars, with the Infrastructure and Nature-based Solutions (NbS) workstream (Pillar 2) showing the strongest results. The programme influenced $4.6 billion in public investment projects, contributing to climate-resilient infrastructure for an estimated 16.6 million people–72% of the annual target–with 42% of beneficiaries being women. They have therefore not met expectations. AAAP struggled to mobilise private sector finance and saw limited uptake of technical assistance outputs, such as GCF concept notes and methodologies. Of the three active output indicators, one was substantially not met (number of GCF proposals supported); one was moderately not met (number of infrastructure resilience advisory packages developed) but very close to targets; and one was moderately exceeded (Number of Masterclasses held).

In response, AAAP made institutional improvements, including launching a new business line to strengthen engagement with non-MDB financial institutions. Early partnerships, such as with CRDB Bank in Tanzania and the IMF’s Resilience and Sustainability Facility, aim to mainstream adaptation into national financial systems, though these efforts are still in early stages and difficult to quantify. GCA also enhanced its internal evaluation and learning functions through AAAP 10, focusing on evidence-based decision-making and continuous learning. These changes reflect a strategic shift in approach, with AAAP 2.0 set to begin in 2026, aiming to improve the programme’s long-term impact and accountability

Progress on recommendations from the previous AR:
Recommendations from 2024 AR	Progress
Identify synergies across ARCAN partners	Completed. FCDO hosted an Annual Learning event in March 2025 focused on WCIS and climate resilience, facilitating knowledge exchange.
Conduct country visits to assess AAAP’s contributions	Completed. Visits to Tanzania and Senegal provided valuable insights into stakeholder needs, programme ownership, and opportunities for improved coordination and communication.
Improve access to GCA support	Completed. GCA’s AAAP 2.0 model introduces ‘Country Platforms’ aligned with National Adaptation Plans, supporting a more country-led approach.
Strengthen knowledge transfer and sustainability of capacity building	Partially completed. Discussions have taken place, and a joint case study is underway to explore this further.
Advocate for support to challenging sectors	Completed. The 2025 Work Program includes support for water-related areas, including urban water resilience.

Lessons learned this year:
AAAP progress on private finance has substantially not met expectations, however a lack of numbers reported does not entirely equal a lack of progress made. GCA reports expanding its engagement with the private sector being a strategic priority towards which multiple initiatives have been initiated over the past year, including e.g. the MIGA project with the World Bank. Under AAAP’s Infrastructure Pillar, several ongoing initiatives with the private sector are anticipated to be approved in the next reporting next year. Similar challenges are evident in the Adaptation Finance Pillar efforts on the uptake of TA products. This signals some discrepancy between AAAP’s ambition level at the time of milestone-setting and these investments’ preparation and approval timelines.
[note] GCA reports that despite demand for its support under Pillar 4 being expected to increase still, lengthy approval timelines related to internal processes of both multilateral funds and national bureaucracies lead to results currently lagging behind targets. GCA’s proposed solution to expand its portfolio to include new types of TA and/or focus on non-accreditation related pathways (e.g. enhancing efforts towards facilitating private finance solutions domestically) is expected to contribute to enhanced results under AAAP 5 over the next year.

Recommendations for the year ahead:

1. As part of the strategic reorientation of Pillar 4, AAAP to consider possibilities to leverage its high-level access and political capital to increase access to climate finance on the supply side, e.g. influencing climate funds to improve application processes, addressing known barriers.
2. AAAP to strengthen mainstreaming of adaptation at the systems-level in IFIs in addition to/leveraging its work with the IMF's RSF.
3. FCDO, the ARCAN MEL Unit and GCA (Research for Impact team) to assess the possibility of reincluding AAAP in ARCAN’s upcoming ICF KPI reporting (included re ICF KPI 1, 11 and 12 in 2023 with a substantial adjustment factor; excluded in 2024) following results measurement realignment having been completed.

Performance Area	Actionable Learning
Score				B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, increase from 5% to 10%

Briefly describe the output’s activities and provide supporting narrative for the score.
The ARCAN programme was designed as an adaptive programme, able to allocate funds taking into account need and performance. The ARCAN Monitoring Evaluation and Learning (MEL) unit, led by Ecorys, was established to generate evidence to inform this approach and support effective management. The ARCAN MEL unit complements MEL of implementing partners by consolidating information across the ARCAN portfolio, addressing gaps and strengthening partner MEL processes as needed.
There has been mixed progress towards this output this year. Several implementing partners have strengthened their MEL systems, but there have been delays in the ARCAN MEL unit outputs. The products were fewer and less impactful than anticipated. Quality of outputs has been an ongoing issue. This was partly due to significant staff changes in the ARCAN MEL unit mid-2024, and a decision to re-orient the MEL unit approach to be more flexible and demand driven to maximise the use of their work. The unit is now fully staffed with a new approach to identifying MEL activities. There are signs that this is already increasing the value and use of ARCAN MEL unit products. Although the MEL unit work is now back on track, the B reflects the delays and challenges over the last year.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Indicators and milestones will need to be updated to reflect the change in the MEL Unit work programme and approach.

Progress on recommendations from the previous AR:

Recommendations from 2024 Annual Review	Progress
Improve co-creation and tracking of recommendations	In progress. Recommendations from the previous year were tracked, improving prioritisation and follow-up. However, further co-creation with FCDO, the MEL Unit, and implementing partners is needed.
Identify and act on synergies between ARCAN projects	In progress. A learning event on WCIS was held, but deeper collaboration has been limited. The MEL Unit is shifting to a more demand-led learning approach.
Encourage cross-partner learning events	In progress. Some sharing has begun, but systematic communication about events across IPs is still lacking.
Share ARCAN learning across FCDO.	In progress. Learning has been limited due to a reduced work plan but is expected to scale up with upcoming evaluations. A cross-FCDO MEL group has been established and is sharing learning on climate finance indicators.
Strengthen MEL implementation through partners	Partly achieved. Many partners are improving MEL systems, including with support from FCDO and the MEL Unit.

Learning over the past year:
There has been significant learning on how to design and implement external MEL units to maximise their impact and effectiveness, including the value of:
- Ensuring products and events are addressing specific MEL questions, jointly agreed by all relevant stakeholders, to maximise their use. Products generated through an activity-based plan have been less valuable.
- Ensuring effective use of appropriate international experts to add-value to well established implementing partners.
- Facilitating close links between the MEL Unit and relevant FCDO experts, and using this relationship to develop and steer jointly agreed priorities.
- Ensuring clear Terms of Reference for each MEL product, complemented with clear expectations for and assessment of the quality of products and events.
Recommendations for the year ahead:
1. FCDO and the ARCAN MEL Unit should complete the shift to a mostly demand led workplan. The indicators and future milestones will need to be revised to reflect this revised workplan and approach.
2. Resources and time should be factored into Terms of References and workplans/objectives to enable MEL Unit recommendations to be co-created with relevant FCDO leads and, when appropriate, ARCAN implementing partners, to maximise their value and use.
D: VALUE FOR MONEY

Key cost drivers and performance

There are no significant changes to the Business Case estimates on return on investment. The biggest allocation is allocated to the bilateral WISER programme (28%) for weather and climate information services, and nature and energy take the next 48% of the total budget. This is partially consistent with the business case which allocated the most resources to those areas with highest mitigation potential (forest and energy), both of which also have substantive adaptation benefits.

VfM performance compared to the original VfM proposition in the business case

The current VfM performance of the ARCAN programme broadly aligns with the original proposition, which emphasised adaptive management, evidence-based decision-making, and maximising the impact of each £1 spent. Strong progress has been made in economy and efficiency, with most programmes demonstrating good budget execution. However, gaps remain in cost-effectiveness data, equity outcomes, and the ability to flexibly scale interventions. Limited VfM analysis has been done so far. The the upcoming VfM Deep Dive will provide a more robust assessment across the portfolio.

D.2.1 Economy:

The ARCAN programme demonstrates sound economic management, with administrative and management costs generally within global benchmarks. For example, SEFA’s administration costs were 3.3% and CIWA’s were 6%, both aligning with international standards. Programmes like WISER and FFF also reported cost-saving measures such as pooled procurement and in-kind contributions. However, some programmes, such as AAAP, reported relatively high staff costs (26%), which may warrant further scrutiny. Overall, the programme has maintained cost discipline while navigating a challenging macroeconomic environment in sub-Saharan Africa.

D.2.2 Efficiency:

Efficiency across the portfolio is mixed. CIWA and FFF reported strong budget execution rates (90% and 89% respectively), while SEFA and SRMI showed lower execution due to legal and operational delays. Leveraging ratios vary significantly: AAAP reported an exceptional 1:1100 ratio of financing influenced to GCA costs, though this is skewed by a few large infrastructure projects. WISER demonstrated operational efficiency through timely delivery and cost reductions (e.g., voice message costs reduced from £7.50 to £5.20). However, evidence of flexible scaling between interventions remains limited, and the mid-term evaluation is expected to provide further insights.

While most development initiatives were evaluated based on VfM principles—emphasizing economy, efficiency, equity, and effectiveness—the CAFI programme prioritised long-term environmental sustainability over immediate cost-effectiveness.

D.2.3 Effectiveness:

Effectiveness is evident in several areas as seen in the Delivery assessment above. However it is clear that we need in a number of areas a revised results framework to ensure the targets fully reflect the work and expectations we have for the components, particularly in influencing large-scale investments and delivering technical assistance. CIWA exceeded its beneficiary targets by 64%, and SEFA surpassed its electricity connection targets. AAAP’s influence on IFI project approvals remains high (90%), and its cost per beneficiary is low (EUR 0.76). However, attribution challenges persist, especially in linking upstream influencing activities to downstream resilience outcomes. Some programmes, like SRMI, lack comprehensive cost-effectiveness data, limiting the ability to assess impact fully.

D.2.4 Equity:

Equity performance varies across the portfolio. WISER stands out for its intentional and visible inclusion of marginalised groups, while FFF has made progress in engaging smallholder farmers, women, and indigenous communities. CIWA has begun integrating GESI into project design, though systemic shifts in governance remain limited. SEFA and SRMI show weaker performance on equity, with limited evidence of social inclusion or benefit distribution. AAAP reported 34% female beneficiaries–below its 50% target–though it achieved gender parity among staff. The GESI review carried out by Ecorys in 2025 will be essential to understand CAFI’s performance on equity and improvements to be made.

Assessment of whether the programme continues to represent value for money

The ARCAN programme continues to represent good value for money, particularly through its strategic investments in high-impact sectors like energy, climate finance, and weather services. While the scale of funding is modest relative to regional infrastructure needs, targeted investments–such as SEFA’s support for the Renewable Energy Certificate scheme–have the potential for transformative impact. The programme’s structured learning processes, adaptive management, and alignment with national priorities enhance its relevance and sustainability. However, improvements are needed in tracking cost-effectiveness, equity outcomes, and the scalability of interventions. The upcoming VfM Deep Dive and mid-term evaluation will be critical in refining these assessments and ensuring continued value for UK taxpayers.

E: RISK

Overview of risk management (including safeguarding)

The overall risk rating of the ARCAN programme is major. The risk appetite for the programme was last reviewed in February 2025. Over the last year, two risks (one Financial and Fiduciary and one Policy and Programme Delivery risk) have sat outside of appetite. We have major delivery risks (in appetite) under Policy & Programme Delivery, Strategy & Context, and one (out of appetite) Financial & Fiduciary, but this risk is being treated.

The risk trends have been mainly focused on our internal programme management gaps and delays to recruitment processes. These have been resolved with staff being onboarded to support ARCAN. Further risks have developed around ODA reductions impacting the existing and planned initiatives. To mitigate risks within our control, we are proactively aligning our activities with the Africa Approach and adjusting our plans through scenario-based planning.

All ARCAN implementing partners have received the latest FCDO Fraud and Safeguarding letters and have acknowledged receipt of these. Safeguarding risks have been captured within the project level risk registers as well as the overarching ARCAN risk register. We have worked with partners to minimise sexual exploitation and abuse and sexual harassment (SEAH) risks by conducting spot checks on field visits, discussed reporting processes with multilateral and bilateral partners and ensuring staff training is undertaken. Safeguarding mitigating measures are followed up on and reviewed regularly. We will continue to promote the Common Approach to Protection from Sexual Exploitation, Abuse and Harassment (CAPSEAH), which is voluntary and non-binding, to all our partners to sign and commit to where possible. A new APEX-wide Safeguarding Action Plan has also been developed and rolled out across programme teams, focusing on 5 core areas; Culture and Awareness, Programme Management, Case Management, Stakeholder Engagement and Awareness, and Social Safeguards.

Social and environmental risk monitoring has developed within ARCAN over the last year. A Social and Environmental Safeguards Field Visit Guide has been developed and was tested on field visits, although further testing is needed. The Departmental Safeguarding Champions and APEX Social Development Adviser have reviewed and updated the Social and Environmental Safeguard risks on the ARCAN risk register, strengthening both the risk descriptions and mitigation measures.

Our major risks highlighted through the partner due diligence processes were around the delivery chains and flow of funds not being clear to FCDO for the large multi donor funds within ARCAN (SRMI, FFF, CAFI, CIWA and SEFA). We have worked closely with the implementing partners to map their projects. This continues to be a risk, but the mobilisation of the MEL Unit, continued field visits, donor coordination mechanisms (SRMI/ESMAP, FFF, CAFI, CIWA and SEFA) and demonstrations of financial need being submitted before payments, have meant this risk have been kept within appetite albeit one that is an ongoing challenge. We review our overarching and nested risk registers (we have one per implementing partner) every quarter and discuss risk management with partners as part of our standard reporting. We encourage partners to escalate risks outside of appetite when they arise.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

ARCAN delivers through multilateral institutions (the World Bank, African Development Bank, FAO and UNDP), one NGO (Global Center on Adaptation), the UK Met Office and a monitoring, evaluation and learning (MEL) contract.

Project Funding Overview

Project Name	Partner	Total Value (£)	Disbursed to Date (£)	Notes
SRMI	World Bank via ESMAP MDTF	18,000,000	18,000,000	Fully disbursed
CAFI	UN MPTFO / UNDP	36,830,000	29,830,000	Majority disbursed
WISER	UK Met Office	46,800,000	13,230,440	Budget increase agreed in 2025.
CIWA	World Bank MDTF	19,880,000	17,530,000	Near full disbursement
FFF	UN FAO	8,000,000	6,000,000	75% disbursed
AAAP	Global Center on Adaptation	20,000,000	7,442,145	Moderate disbursement
SEFA	African Development Bank	16,500,000	15,097,280	Nearly fully disbursed
ARCAN MEL	Ecorys	4,046,042	1,226,864	Early-stage disbursement

SRMI, managed by the World Bank under the ESMAP MDTF, receives pooled donor funding, with FCDO represented on the ESMAP Board. While the World Bank’s financial systems are robust, FCDO receives limited, high-level reporting, primarily through annual reports. Delivery chain mapping remains weak, though some progress has been made. Engagement with the SRMI team is mostly technical, with programme management handled centrally by ESMAP. Coordination between FCDO and the ESMAP team has supported policy implementation on fraud and safeguarding, but more regular updates are needed to strengthen oversight.

CAFI, managed by the UNDP Multi-Partner Trust Fund Office, demonstrates strong financial transparency through the Gateway. FCDO is the third-largest donor and currently holds the CAFI Presidency, giving it significant influence. Funds are disbursed based on Steering Committee priorities and tracked by project, country, and theme. Real-time tools like the PES Management Tool and adherence to M&E guidelines ensure spending aligns with intended results. CAFI’s governance and reporting structures are well-established, with all financial data publicly accessible via the MPTF Gateway.

WISER, implemented by the UK Met Office, has scaled up significantly, with its budget increasing to £46.8 million. In response, the Met Office has strengthened programme management and financial oversight, including improved delivery chain risk mapping. Despite a £1 million underspend in FY24/25, the FCDO team has responded proactively, planning a financial management capacity-building workshop with downstream partners in Kenya to improve forecasting, reporting, and compliance. Since then the MO have taken a more proactive approach to risk adjusting their forecasts. WISER maintains timely reporting and strong collaboration with FCDO, with inclusion and risk management embedded in its operations.

The Forest and Farm Facility (FFF), led by FAO, is supported by multiple donors including FCDO, which committed £8 million to Phase II. Reporting has improved, with clearer articulation of risks and lessons learned, though gaps remain in logframe reporting and outcome attribution. FAO has responded positively to FCDO feedback, and collaboration continues to ensure strong financial oversight and sustainability planning.

The World Bank’s CIWA programme benefits from regular FCDO engagement and joint work on an updated Theory of Change and delivery chain mapping. While reporting remains high-level, recent collaboration has improved visibility into project-level implementation.

The Africa Adaptation Acceleration Programme (AAAP), implemented by GCA, maintains strong financial reporting and responsiveness. FCDO has good visibility of delivery chains and procurement, and GCA has made progress on due diligence and internal communications.

SEFA, managed by the African Development Bank, continues to demonstrate strong engagement with FCDO, sharing project documentation and maintaining transparency despite capacity constraints. Financial planning is supported by a clear pipeline and responsiveness to donor requests.

The ARCAN MEL contract with Ecorys has faced staffing and quality challenges, prompting a new team and a shift to a more demand-led work plan. Recent changes show promise in improving quality and relevance of the MEL outputs. Prior to this some pieces of work required significant edits and engagement from FCDO.

Organisation / Initiative	Last Narrative Financial Report	Last Audited Annual Statement
SRMI	24 January 2025	9 September 2024
CAFI	31 May 2025	31 December 2024
Met Office	15 May 2025	19 August 2024
FAO	Page 53 of 2024 Annual Report	Not applicable
CIWA	9 December 2024	9 December 2024
AAAP	8 May 2025	1 April 2025
SEFA	17 March 2025	16 June 2025
Ecorys	Milestone-based contract (no breakdown)	31 December 2023

Assets

Asset management practices vary across ARCAN programmes. The Met Office adheres to HMG policy, maintaining a detailed and regularly updated asset register with accountability measures in place. FFF follows FAO’s corporate asset guidelines, with assets tracked in its ERP system and disposal requiring donor approval. CIWA and SEFA do not directly own assets; instead, assets are held by recipients or beneficiaries, with oversight through procurement plans or contractual clauses. SRMI, under World Bank MDTF rules, does not provide asset lists to donors. CAFI lacks a fund-level asset overview, with asset recovery policies varying by implementing agency; the CAFI Board is considering improvements from 2025. No FCDO-funded assets have been purchased under AAAP.

FCDO ARCAN programme governance structures

The ARCAN programme is governed through a multi-tiered structure. At the strategic level, when required the ARCAN Board provides oversight and includes senior civil servants from FCDO and DESNZ, senior climate advisers, and Senior Responsible Owners (SROs) from ARCAN and its sister programmes in MENA and Asia. This Board has not met in the last year. Day-to-day delivery and risk management are overseen by a Programme Management Committee, chaired by the Programme Responsible Owner (PRO) and comprising the SRO, lead advisers, and programme managers, which meets monthly. Additionally, a MEL Working Group, convened by the MEL provider, brings together project leads and partner representatives to support monitoring, evaluation, and learning. The ARCAN SRO also meets with counterparts from other regional and research climate programmes to ensure coordination, particularly around contracting and reporting.
G: MONITORING, EVALUATION AND LEARNING

Monitoring, evaluation and learning (MEL) is undertaken by a mixture of:
- MEL contract, led by Ecorys (the ‘ARCAN MEL Unit’). Responsible for developing, collating, communicating and quality assuring results, and conducting robust evaluation of the portfolio.
- ARCAN project advisers and other FCDO technical specialists, who work directly with Ecorys and implementing partners to understand progress.
- Project partners, through their own monitoring and evaluation.
Details of progress of the ARCAN MEL Unit over the last year, and implementing partner MEL systems, is set out in the ‘Actionable Learning’ output.
FCDO has continued the regular monitoring of implementing partners, including regular quarterly meetings (e.g. WISER), attending or chairing steering committee meetings or donor groups (e.g. chair of CAFI Board, attending CIWA, SRMI and SEFA donor committee meetings), and reviewing annual or quarterly reports of all partners. Monthly FCDO programme management coordination meetings ensure key lessons and challenges are shared across the ARCAN team.
Field Visits, Engagement with Stakeholder and Beneficiaries

FCDO programme staff and advisers have had extensive engagements with programme stakeholders during the review period including x field visits. This has included:

Date	Project	What
Feb 2024	CAFI	Field visit to Cameroon to meet prospective program partners.
March 2024	CAFI	Field Visit to Equateur province to see a regional development ‘integrated REDD+’ program with WWF and FAO.
June 2024	CAFI	Kinshasa – cookstove production facility and PROMIS health clinic visit
October 2024	CIWA	CIWA Male Champions for Women’s Empowerment meeting in Maseru, including a closed session with champions to observe training by CIWA GESI lead, and an open session at the WaterNet Symposium to observe efforts to improve awareness of and interest in the initiative itself and the concept in general.
October 2024	Ecorys consultant	Visit to RoC to complete co-ordination project interim review
November 2024	CIWA	CIWA Advisory Committee Meeting in Senegal which included field visit to Diama Dam/ Senegal River Basin as well as meetings with donors, partners, and the World Bank to shape programme priorities for climate-resilient water management in Africa.
November 2024	WISER	Joint meetings with partners in Nairobi alongside Met Office, including Kenya Meteorological Department, IGAD Climate Predictions and Applications Centre (ICPAC), WMO and others.
November 2024	AAAP	Meeting with AAAP country partners in Senegal to better understand GCA institutional approaches, in particular in relation to the Dakar-Saint Louis highway and more generally.
January 2025	WISER	Visit to the Early Warnings for Southern Africa (EWSA) project in Katlehong in Johannesburg, meeting with community partners, local government and South African Weather Service. Attendance at the ActionFirst regional workshop for Southern Africa in Pretoria.
March 2025	WISER	Visit to ICPAC in Nairobi to meet all East African project partners. Field visit to the Enhancing Climate Resilience in East Africa (ECREA) project in Nakuru, Kenya. Meeting local partners and government, attending farmers training workshop and farm visit.
May 2025	AAAP	Field monitoring of AAAP in Tanzania including attending climate finance masterclass. This informed the sustainability case study and facilitated engagement from across BHC Tanzania on climate maps.
May 2025	FFF, SEFA, WISER	Joint climate/humanitarian visit to Madagascar to monitor FFF, WISER and SEFA activities.

Recommendation:
It would be valuable to consider a more strategic approach to FCDO monitoring, field visits and ARCAN MEL Unit work, considering how these can be linked and mutually support each other. This would include identifying clear ARCAN wide and Implementing Partner MEL priorities, and consider how to use the different monitoring mechanisms (such as quarterly review meetings, IP report reviews, steering committees, ARCAN MEL unit studies, FCDO field visit) to maximise UK understanding and influence.
Evidence
The ongoing ARCAN MEL Unit case studies complement evaluations conducted by implementing partners, including SEFA Mid Term Review, and ESMAP (SRMI Umbrella Fund) and FFF evaluations. The WISER case study will build on its 2024 WISER evaluation (across all regions) which highlighted challenges around sustainability.
The ARCAN MEL Unit is currently undertaking a mid-term evaluation, to be published by the end of 2025. The first phase bought together available evidence on ARCAN programmes, and tested the Theory of Change against an AI assisted review of new global evidence since the programme started. It confirmed that the latest global evidence backed up ARCAN priorities and approaches. It highlighted gaps in evidence, primarily around sustainability and potential for scale, which are being addressed by planned Phase 2 studies.
Gender Equity and Social Inclusion

 The ARCAN programme has taken steps to integrate gender equity and social inclusion (GESI) into its strategy, including within its Theory of Change and some operational components. Over the past year, significant strides were made in mainstreaming GESI, particularly through initiatives led by CIWA, AAAP, WISER, and FFF. These included the development of gender frameworks, training programmes, and inclusive planning tools that addressed gender gaps in water governance, climate adaptation, and disaster risk management. Notable achievements include CIWA’s Male Champions for Women’s Empowerment initiative, WISER’s inclusive early warning systems, and FFF’s support for women-led enterprises and governance in forest and farm producer organisations. These efforts have not only improved access to services and information for women and marginalised groups but also demonstrated tangible impacts on resilience, livelihoods, and community empowerment.

Despite these advances, challenges remain in achieving consistent and transformative GESI integration across the ARCAN portfolio. Monitoring and reporting of GESI indicators are still uneven, with many programmes focusing primarily on gender while neglecting other dimensions of social inclusion such as disability, age, and displacement. Programmes like SEFA, SRMI, and CAFI show limited evidence of systemic institutional change or responsiveness to local community needs. The lack of clear definitions and consistent reporting frameworks further hampers the ability to assess progress and impact. While some tools, like the UN-REDD gender marker, offer a starting point, their limited scope and inconsistent application highlight the need for more robust, inclusive, and context-sensitive approaches to ensure that GESI commitments translate into meaningful and lasting change on the ground.

 Progress on recommendations from the previous AR:

Recommendations from 2024 AR	Progress
FCDO PM Team should continue integrating GESI in monitoring activities.	Partially completed.
FCDO PM Team should encourage greater ambition among IPs including by supporting them to build on their GESI policies, frameworks, and action plans.	Partially completed. CIWA refreshed their GESI strategy; AAAP improved disaggregation in reporting.
FCDO PM Team should decide and communicate a GESI baseline across programmes, e.g. gender disaggregation for all/direct beneficiary numbers, gender disaggregation for training.	Partially completed. All reviewed programmes have at least one indicator capturing GESI dimensions.
FCDO PM Team and ARCAN MEL Unit to work with IPs towards a stronger and more explicit application of the equity in VFM dimension to decision-making.	While some progress has been made, such as embedding equity in programme design and piloting a VfM Scorecard, gaps remain in disaggregated data, consistent reporting, and evidence of how equity influences outcomes.

Recommendations for the year ahead:

1. Support capacity building for implementing partners, particularly in upstream-focused programmes, to strengthen their ability to implement and report on GESI.
  [note] Including by enhancing outcome-level monitoring beyond participation metrics to assess resilience, empowerment, and systemic change; improving disaggregation and intersectionality by expanding data collection beyond gender; ensuring this data informs adaptive programming.
2. Developing clearer VfM dimensions, improved data collection, and targeted support to ensure equity considerations inform programming.

Leverage learning across programmes by facilitating cross-programme exchanges on effective GESI practices.
[note] Practices include WISER’s impact-based forecasting and Missing Voices approach, and FFF’s support for women-led enterprises.

Within FCDO ARCAN team, share and potentially roll out GESI-FCV-Climate risk framework delivered by the Women, Peace, and Security Helpdesk.
[note] Flag most severe risks identified for each programme and signpost methodology for identifying and assessing similar future risks.