ARCAN Annual Review 2025/26 Annex.

ARCAN Theory of Change diagram

Reporting against Results Framework.

Performance area	Contribution to Meaningful Change
Score:	A
Impact weighting (%):	30%	Weighting revised since last AR?	Yes. Increased from 20% to 30%.

Indicator(s)	Milestones for this review	Progress
Outcome indicator 1: Increase in protection of natural resources
Hectares under sustainable land management practices (contributes to ICF KPI 17). Programme: CAFI	Linear progress toward 2028 milestone (317,478)	N/A, indicator data not provided in CAFI M&E framework – 2024. / DRC: 146,279 ha / RoC: no new data in 2024 – cumulative total remains: 472 ha
Hectares of land under improved policies, plans, management or protection measures. Programme: CAFI	Linear progress toward 2026 milestone (10,000,000)	Milestone met, 2026 target almost achieved. / 9,906,741 ha (no data on how much of this is under validated policies, plans, management or protection measures)
Number of ha of the forest and farmland managed by FFPOs where FFF support has contributed to either protection, restoration or sustainable forest and farm management to improve climate change mitigation or adaptation (contributes to ICF KPI 17). Programme: FFF	Cumulative 2026 milestone: 336,000 ha (based on average of 42,000 for 8 countries) / 2024/2025 milestone: Linear progress (year 7 (78%) out of 9) towards 2026 = 262,080 ha	Milestone not met, 2026 target on track / Cumulative: 235,089 ha / 2024/2025 progress: 111,298 ha / Progress is slightly behind the 2024 milestone – currently 70% towards the 2026 target.
Outcome indicator 2: Transition of energy sector towards zero carbon power
MW of new renewable power capacity installed (contributes to ICF KPI 7). Programme: SEFA	Linear progress (year 5 (83%) out of 6) towards 2025 milestone (1,500) / Cumulative 2025 milestone: 1,500 MW / Cumulative 2030 milestone: 3,000 MW / 2024/2025 milestone: not set	2025 cumulative milestone likely not to be met based on 2024 progress. / Cumulative results: 243 MW from concessional investments / 2024/2025 progress: 199 MW from concessional investments
Number of successful tenders launched (that were supported by SRMI). Programme: SRMI	No milestone was set for the 2024/2025 reporting period	2024 progress: 19 countries being supported in SSA to launch tenders
Outcome indicator 3 - Strengthened resilience of population
Number of people directly supported in coping with the impacts of climate change (contributes to ICF KPI 1). Programme: FFF	Cumulative 2026 milestone: 145,117 people (+6,000 per year) in line with a reasonable trajectory since 2022 / 2024/2025 milestone: 133,117 people (+6,000 per year) in line with a reasonable trajectory since 2022	2026 Milestone substantially exceeded / Cumulative: 301,280 people / 2024 progress: 174,163 people
Number of relevant transboundary institutions strengthened to improve regional cooperation. Programme: CIWA	Cumulative 2024/2025: 20 institutions (with evidence of improvement) / 2024/2025: Evidence of improvement across supported institutions	Milestone met / Cumulative: 20 / 2024/2025 progress: Further strengthening of 10 groups of institutions, each with a qualitative explanation of how the institution was strengthened
Number of people that a) access and b) use WCIS to inform their decision-making. Programme: WISER	Cumulative 2024/2025 milestone: Access: 280,219 people / Cumulative 2024/2025 milestone: / Use: 102,421 people	Milestone not met / Cumulative total 2024/2025: / Use: 35,638 people / Access: 166,812 people / 2024/2025 progress: / Use: 35,638 people (variance of - 66,783) / 2024/2025 progress: / 166,773 people with access were reported (Variance: -113,407)
Number of institutions/organisations that a) access and b) use weather and climate information services or evidence/analysis supported by WISER in their decision-making. Programme: WISER	Cumulative 2024/2025 milestone : / Access : 65 institutions/ organisations / Use : 79 institutions/ organisations	Milestone substantially exceeded / 2024/2025 progress: / Access: 87 institutions/ organisations / Use: 147 institutions/organisations / Cumulative total 2024/2025: / Access: 136 institutions/ organisations / Use: 165 institutions/ organisations
Outcome indicator 4 - Mobilisation of climate and natural resources related investment
Total volume of investment (US$) mobilised by SEFA commitments (contributes to ICF KPI 11 and 12). Programme: SEFA	Linear progress (year 5 (83%) out of 6) towards 2025 milestone ($1,800,000,000 investment mobilised by SEFA commitments) / Cumulative 2025 milestone: US$1.8 billion investment mobilised. / Cumulative 2030 milestone: US$3.1 billion investment mobilised / 2024/2025 milestone: not set	2025 cumulative milestone likely not to be met based on 2024/2025 progress. / Cumulative results: US$809 million co-investment mobilised. This was from concessional investments. / Six projects contributed to cumulative results, with the majority of investment mobilisation from GBL projects including the Gabon Kinguélé Aval HPP, Africa Renewable Energy Fund II, and Egypt Kom Ombo Solar PV IPP. / 2024/2025 progress: - US$28.6 million from concessional investments
US$ investment finance for cooperative management and development of international water resources projects influenced by CIWA. Programme: CIWA	US$14 billion potential investment finance + US$7 billion mobilised investment finance (US$21 billion in total) / 2024/2025: 0	On track in 2024/2025 ARCAN reporting year (reflecting no expected change), but the cumulative milestone is moderately off track / Cumulative: US$11.03 billion potential investment + US$6.365 billion mobilised investment (US$17.4 billion in total) / 2024/2025 progress: change in potential investments: US$23.6 million mobilised in community groundwater investments through the Untapping Resilience and SADC-GMI projects
US$ in approved investment projects reflecting adaptation solutions brokered or adaptation finance solutions influenced. Programme: AAAP	Linear progress towards 2025 milestone (US$12 billion in total by 2025) / 2024/2025 milestone (Cumulative): / a) $ 8,100,000,000 (public) / b) $ 871,000,000 (private)	a) Milestone exceeded (public) / Cumulative: $ 9.1 billion / 2024/2025: $4.6 billion (all public) / 19 IFI investment projects make up 4.6 billion in investments influenced throughout the reporting period. / b) Milestone not met (private) (see Section 4.7)
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] This Milestone was agreed with FFF following a proposal from FCDO which was based on the average annual increase observed for this indicator over the first few years of Phase 2.
[note] There is uncertainty attached to this value: In Annex 9 of the FFF annual report, the disaggregated data (per country) for 2024 totals more (309,560) than the Africa cumulative total provided here.
[note] The cumulative target had been set at 12 since 2021 but CIWA had already supported 20 institutions by 2023 (as reported in CIWA’s 2023 annual report).
[note] CIWA’s 2024 Annual Report provides a list of 10 examples of institutional strengthening, some of which pertain to multiple institutions. In total, 21 distinct entities are mentioned.
[note] milestone for previous FY was 0 so this is the first time WISER 3 is reporting progress on this indicator
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] Under the previous results framework, the annual targets remained the same since 2022 (as presented in CIWA’s 2023 Annual Report).

Outcome indicator	Assessment	Relative contribution to meaningful change
Increase in protection of natural resources / Outcome indicator 1	ARCAN is making a credible contribution to the protection of natural resources through FFF and CAFI, although current data limitations prevent a full assessment. FFF has enabled sustainable management practices across 235,089 hectares of forest and farmland, with 2024 progress (111,298 ha) slightly below the linear milestone but broadly on track to meet the 2026 target. This reflects steady support to FFPOs across 8 countries on forest protection, restoration (including the planting of 32,400 indigenous tree seedlings on 13.5 ha of degraded land in 2023–2024 in Menengai, Kenya), and climate-smart practices (such as mulching, crop association and rotation, minimum tillage, agroecology and organic farming that increases soil health). Under CAFI, there are 9.9 M hectares of land under improved policies, plans, management or protection measures. This includes 239,204 ha of land under local land use plans in the DRC which increases community engagement and ownership. However, there have been significant delays and postponements in the delivery of forestry-related milestones that have limited CAFI’s impact. . Furthermore, CAFI is one of several programmes where delivery risks and downstream MEL constraints have limited visibility of change to date. Overall, ARCAN is supporting progress in natural resource governance, though more robust implementation tracking is needed to assess outcome-level impact at scale.	Moderate / Strong quantitative progress by FFF; CAFI results pending. Policy influence evident. Gaps in implementation tracking.
Transition of energy sector towards zero carbon power / Outcome indicator 2	ARCAN’s contribution to the zero-carbon energy transition remains modest in terms of reported outcomes, though there is evidence of foundational progress supported by SEFA and SRMI. In 2024, SEFA reported 199 MW of new renewable capacity from concessional investments, bringing the cumulative total to 243 MW - significantly below the 2025 milestone of 1,500 MW. While delivery is constrained by legal and institutional bottlenecks, SEFA has made stronger progress on new connections and continues to strengthen its MEL systems, including the addition of institutional indicators. SRMI is contributing to enabling environments through regulatory and tender preparation support across several countries. Although data on tenders launched or MW generated is not yet available, this may reflect timing issues in MEL reporting. The MEL Unit has begun working with both IPs to develop outcome pathways, which should improve visibility on how upstream interventions are expected to deliver long-term decarbonisation outcomes. Further progress will require stronger alignment between MEL systems and the evolving delivery context.	Low to moderate / Foundational progress underway via SEFA and SRMI. Output progress stronger than outcome-level mobilisation or decarbonisation.
Strengthened resilience of population / Outcome indicator 3	ARCAN is contributing meaningfully to climate resilience at individual, institutional, and regional levels, with strong progress by FFF and CIWA, and emerging results from WISER. FFF has exceeded its 2026 cumulative milestone ahead of schedule, supporting over 301,000 people - more than double the target - to adopt climate-smart practices, restore landscapes, and access livelihood support. The Gambia Business Incubation hub for instance is supporting women vegetable-growers across five administrative regions to develop organic farming practices that simultaneously provide value addition to their produce. CIWA met its 2024 milestone by strengthening transboundary water institutions in 10 additional settings, demonstrating sustained collaboration and embedded institutional support. WISER has not yet met its outcome targets on individual access and use of weather and climate information, but notable progress has been made at institutional level: 165 institutions reported using WCIS since 2023/24 against a milestone of 79. Across these programmes, ARCAN is helping to embed resilience capacities, though better outcome tracking and attention to access and equity will be key to deepening this contribution.	High / Exceeded targets on individual resilience (FFF); strong institutional gains (CIWA). WISER making progress.
Mobilisation of climate and natural resources related investment / Outcome indicator 4	ARCAN is contributing to the mobilisation of climate and natural resource investments, but progress towards 2025 milestones is uneven and difficult to verify in full. SEFA reports US$809 million in cumulative co-investment, though this is lower than the US$837.6 million mobilised in 2023. Many projects remain in early stages and face regulatory delays, which has limited disbursement. CIWA reports a cumulative total of US$17.4 billion in potential and mobilised investment influenced, but only US$23.6 million was added in 2024. These results largely reflect upstream support for pipeline development rather than confirmed capital flows. AAAP continues to make steady progress towards its 2025 target of US$12 billion in investments influenced, mainly through public finance, but progress towards its goal of unlocking access to US$1 billion in adaptation finance is less advanced. Overall, while ARCAN is helping to lay the groundwork for long-term investment, improvements in indicator definitions and finance tracking are needed to assess progress more clearly.	Moderate / Investments influenced but mostly in pipeline stage. SEFA and CIWA delivery slow; AAAP progress steady but partial.

ARCAN project	Cooperation in International Waters in Africa (CIWA) (World Bank)
Score	A
Project Weighting %:		12%	Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Program development objective: To strengthen the cooperative management and development of international waters in Sub-Saharan Africa to facilitate sustainable climate-resilient growth.
CIWA 1 (Outcome): $ investment finance for cooperative management and development of international water resources projects influenced by CIWA / CIWA 2.0: PDO Indicator 1: US dollars influenced for cooperative management and development investments	Cumulative: / US$14 billion / potential + US$7 / billion mobilised / (US$21 billion in / total) / 2024/2025: 0	On track in 2024/25 (reflecting no expected change) but the cumulative milestone is moderately off track Cumulative: US$11.03 billion potential + US$6.365 billion mobilised (US$17.4 billion in total) / 2024/2025 progress: change in potential investments: US$23.6 million mobilised in community groundwater investments through the Untapping Resilience and SADC-GMI projects.
CIWA 2 (Outcome): Number of people expected to directly benefit from improved water resources management and development in target basins through projects supported by CIWA / CIWA 2.0: PDO Indicator 2: Number of people benefiting from improved water resources management and development investments	Cumulative: 45 / million / 2024/2025: 5 / million	Milestone substantially exceeded overall, but off track for 2024/25 / Cumulative: 66 million from potential investments and 19.875 million from mobilised investments (85.875 / million people in total) / 2024/2025 progress: No change from potential investments but around 310,000 new expected beneficiaries from the investments mobilised through / the Untapping Resilience and the SADC-GMI projects.
Intermediate Result 1. Regional Cooperation and Integration Strengthened
CIWA 3 (Output): Number of relevant transboundary institutions strengthened to improve regional cooperation / CIWA 2.0: 1. Institutions / strengthened to improve regional / cooperation	Cumulative: 20 (with / evidence of / improvement) / 2024/2025: / Evidence of / improvement across / supported / institutions	Milestone met / Cumulative: 20 / 2024/2025 progress: Further strengthening of 10 groups of institutions, each with a qualitative / explanation of how the institution was strengthened
CIWA 4 (Output): Number of strategic analyses and knowledge products used to illustrate the evidence base for cooperation, needs, and challenges / CIWA 2.0: 3. Knowledge products to / illustrate the evidence base for cooperation, needs, and challenges.	Cumulative: 148 / 2024/2025: 20 new analyses	Milestone not met / Cumulative: 135 / 2024/2025 progress: 7 new products
Intermediate Result 2. Water Resources Management Strengthened
CIWA 5 (Outcome): Number of relevant transboundary institutions using improved analytical tools, knowledge products, data, forecasting, and/or capacity for improved water and climate risk management or investment operation coordination / CIWA 2.0: 1.c. Institutions using improved analytical tools, knowledge products, data, forecasting for improved water and climate risk management or investment coordination	Cumulative: 13 institutions in at least 7 basins (with evidence of improvement) / 2024/2025: Evidence of improvement across supported institutions	Milestone met / Cumulative: 13 / 2024/2025 progress: 6 examples of institutions supported in this area (ENTRO, NELSAP-CU, NILE-SEC, NBI, INMACOM and Volta Basin Authority, and SADG-GMI)
CIWA 6 (Output): Number of stakeholders (including in communities and private sector) trained in improved biodiversity conservation or natural resource management activities	Cumulative: 50 / 2024/2025: 50	N/A / Indicator not included in CIWA 2.0 results framework
Intermediate Result 3. Water Resources Development Strengthened
CIWA 7 (Output): Number of investment opportunities with regional benefits that have been advanced through CIWA support / CIWA 2.0: 7. Investments with regional benefits that have been advanced through CIWA support	Cumulative: 47 / 2024/2025: 3	Milestone met / Cumulative: 47 / 2024/2025 progress : 3 examples (first batch of Ethiopian water schemes implemented through the World Bank’s Groundwater for Resilience programme influenced by CIWA’s Untapping Resilience project,12 subgrants for national groundwater investment influenced by the SADC-GMI project, and the World Bank’s Regional Climate Resilience Program for Eastern and Southern Africa 2 Project)
CIWA 8 (Outcome): Number of relevant transboundary institutions with an improved approach to sustainable investment planning and bankable investment preparation	Cumulative: 10 (with evidence of improvement) / 2024/2025: 0	N/A / Indicator not included in CIWA 2.0 results framework
CIWA 9 (Output): Design or preparation of new World Bank operations that were informed by CIWA activities / CIWA 2.0: 6. World Bank projects informed by CIWA	N/A - no milestone was set for the 2024/25 ARCAN reporting period	N/A / Cumulative: 17 / 2024/2025 progress: 1, Regional Climate Resilience Program for Eastern and Southern Africa 2 Project (RCRP2)
Intermediate Result 4. Stakeholder Engagement and Coordination Strengthened
CIWA 10 (Outcome): Number of basins with improved engagement of civil society, private sector, and academia; percentage of engagements where improved stakeholder engagement explicitly supports the incorporation of gender issues into the design and implementation of water management and development activities / CIWA 2.0: 1.a. Institutions with improved engagement of civil society, private sector, and academia	Cumulative: 8 basin institutions (60% explicitly incorporate gender issues) (with evidence of improvement) / 2024/2025: Evidence of improvement across a selection of supported basin institutions	Milestone partially met, but no information on % incorporating gender / Cumulative: At least 8 institutions / 2024/2025 progress: 4 relevant CIWA operations contributing to this indicator: 1) collaboration between SADC-GMI and three universities; 2) Sahel project expanding civil society organisation diagnostic to Guinea and Senegal, and facilitating the participation of the Burkinabe Youth Transboundary Water Parliament in World Water Week; 3) youth internship and young professional programmes hosted by the NBI centres, and community engagement in flood-prone areas in Kenya, Ethiopia, South Sudan, and Sudan; 4) stakeholder engagement for early warning systems through the South Sudan Transboundary Waters Support Program, including with academia
CIWA 11 (Outcome): Number of basins with increased water resources management and development information in the public domain / CIWA 2.0: 1.b. Institutions with increased water resources management and development information in the public domain	Cumulative: 6 (with evidence of improvement) / 2024/2025: Evidence of improvement in a number of supported basins	Milestone met / Cumulative: 6 / 2024/2025 progress: 2, continued support to the SADC region (ongoing support to the SADC Grey Literature Archive and SADC Groundwater Information Portal) and the Nile Basin (ENTRO produced flood forecasts and a flash flood early warning system, NILE-SEC produces a bi-weekly drought monitoring bulletin, NBI produced the Nile Basin Water Quality Database)
CIWA 12 (Output): Number of women in high or medium- skilled and/or management positions trained / CIWA 2.0: 2.b. Number of women in / high- or medium-skilled and/or management positions trained in transboundary WRM data use, information, or decision support systems	Cumulative: 250 / 2024/2025: 137	Milestone moderately exceeded / Cumulative: 258 / 2024/2025 progress: 145 women participated in trainings (28 through WDR, 45 through SADC-GMI, and 72 through NCCR)
Key institutional improvements within CIWA
CIWA 13: Examples of institutional improvements within CIWA to increase impact and effectiveness	Agreement of CIWA 2.0 theory of change and results framework by December 2024	Milestone met / CIWA introduced the CIWA 2.0 theory of change and reported against the new results framework in its 2024 Annual Report
[note] Under the previous results framework, the annual targets remained the same since 2022 (as presented in CIWA’s 2023 Annual Report).
[note] According to CIWA, the target of 45 million people counts both mobilised and potential investments
[note] The target set for 2024 was already exceeded by results reported by CIWA in the 2023 Annual Report
[note] The cumulative target had been set at 12 since 2021 but CIWA had already supported 20 institutions by 2023 (as reported in CIWA’s 2023 annual report).
[note] CIWA’s 2024 Annual Report provides a list of 10 examples of institutional strengthening, some of which pertain to multiple institutions. In total, 21 distinct entities are mentioned.
[note] CIWA did not report the cumulative total in 2024 so the figure of 135 is obtained by adding 7 to the cumulative total of 128 reported in 2023.
[note] 1) Salinity guideline produced through Untapping Resilience project; 2) analysis with the Rift Valley Institute on conflict and fragility considerations produced through the Untapping Resilience project; 3) a regional integration roadmap produced through the Untapping Resilience project; 4) analysis of water point failure with UNDP; 5) an updated civil society organisation diagnostic through the Sahel project; 6) groundwater legislation assessment for Nigeria, France, and Spain produced through the Sahel project; 7) Water Security Assessment for Lake Chad.
[note] The cumulative target had been set at 11 since 2021 but CIWA had already supported 13 institutions by 2023 (as reported in CIWA’s 2023 annual report).
[note] CIWA did not report the cumulative total in 2024 so the cumulative total of 13 reported in 2023 is assumed to be unchanged.
[note] Indicator not included in CIWA 2.0 results framework but will be reported as a discrete disaggregation under indicator 2 ‘Number of people who participate in CIWA-funded activities’.
[note] CIWA did not provide a quantitative result for this indicator in 2024 but mentioned support to two regional investments that were supported in the reporting period.
[note] The RCRP2 project was not specifically listed in CIWA’s 2024 Annual Report but confirmed as a new investment by the CIWA team following the monitoring synthesis workshop held on 29/04/2025.
[note] The cumulative target had been set at 6 since 2021 but CIWA had already supported 10 institutions by 2023 (as reported in CIWA’s 2023 annual report).
[note] CIWA did not set a milestone for this indicator which was first introduced in its 2023 Annual Report.
[note] Cumulative total confirmed by CIWA following the monitoring synthesis workshop held on 29/04/2025.
[note] This project was not listed in CIWA’s 2024 Annual Report, but the CIWA team confirmed that 2023/24 progress is 1 following the monitoring synthesis workshop held on 29/04/2025.
[note] The cumulative target had been set at 7 since 2021 but CIWA had already supported 8 institutions by 2023 (as presented in CIWA’s 2023 Annual Report).
[note] CIWA did not provide a quantitative result for this indicator in 2024, instead highlighting relevant activities implemented during the reporting period. It is therefore assumed that at least the previous cumulative total of 8 basins has been achieved.
[note] The cumulative target had been set at 5 since 2019 but CIWA had already supported 6 basins by 2023 (as presented in CIWA’s 2023 Annual Report).
[note] Note that the old indicator counts basins while the new indicator counts institutions.

ARCAN project		Central Africa Forest Initiative (CAFI) (UNDP)
Score		B
Project Weighting %:	22.2%		Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestone(s) for this review	Progress
Hectares under sustainable land management practices (contributes to ICF KPI 17)	2026 target: / DRC: 326,286 ha / RoC: 2,160 ha / 2024 milestones: Linear progression toward 2028 targets	N/A, indicator data not provided in CAFI M&E framework – 2024. / DRC: 146,279 ha / RoC: no new data in 2024 – cumulative total remains: 472 ha
Hectares of land under improved policies, plans, management or protection measures.	2026 target: 10M ha / 2024 milestone: Linear progression toward 2026 target.	Milestone met, 2026 target almost achieved. / 9,906,741 ha (no data on how much of this is under validated policies, plans, management or protection measures) / (9.99M ha according to the CAFI Metrics Hub)
CAFI 1 (Output): Number and ratio of direct beneficiaries compared to the total population of the area of intervention	DRC / 2026 target: The overall target is approximately 11% of the DRC population, i.e., 9.6M direct beneficiaries. / 2024 milestone: Roughly on track towards 2026 target assuming linear progress. / RoC / 2026 target: 500 direct beneficiaries (PROREP). / 2024 milestones: Roughly on track towards 2026 target assuming linear progress. / Gabon / No milestone set for 2024/25 ARCAN reporting year	Milestones not met, 2026 targets off track. / CAFI programme total: 301,700 direct beneficiaries of CAFI-funded non-reproductive health projects, plus 3,193,965 direct beneficiaries of contraceptive methods, including 435,441 young women who benefit from long-acting contraceptive methods in 11 DRC provinces. / DRC: 300,073 direct beneficiaries / RoC: 310 beneficiaries identified and selected and 100 supported & granted with secure access to land for agroforestry plantations. / Gabon: N/A – no milestone set for 2024/25 reporting year (also to note, there is no related data to report this year)
CAFI 2 (Output): Percentage of gender blind/ sensitive/ responsive programs	2024 Milestones: / • No active CAFI-funded program is gender-blind. / • At least 20 % of active CAFI-funded programs are highly gender sensitive, i.e., they meet 3 out of 4 criteria. / • At least 50 % of active CAFI-funded programs are gender responsive with 4 out of 4 criteria met.	Milestones substantially not met. / Of the 31 active projects: / 3 projects are gender blind (meet 0 of the criteria) / 4 projects meet only 1 of the criteria / 12 projects meet 2 of the criteria / 6 projects meet 3 of the criteria / 6 projects are gender responsive
CAFI 3 (Output): Progress against Letter of Intent (LoI) milestones	DRC / 2026 target: 90 milestones for 2021-2026 / 2024 milestone: On track to reach 2026 target. / RoC / 2026 target: 52 milestones for 2019-2025 / 2024 milestone: On track to reach 2026 target. / Gabon: / 2025 target: 26 milestones for 2017-2022 / 2024 milestone: On track to reach 2025 target. / For all milestones: Taking into account funding and context.	Not met. Milestones are progressing but there are significant delays and postponements. / DRC: 2024 annual report points to the 2023 Annual Review of the CAFI-DRC Partnership held in March 2024, whose report was validated and published: 44 of the 90 milestones are currently in progress or achieved but FONAREDD 2024 Draft annual report: 55% of the 75 2021-2024 milestones have been achieved (15) or are in progress (26). 25 milestones have been delayed and 9 postponed. / RoC: no 2024 data available - annual reviews of national LoI milestones were not conducted in 2024 and no data was provided in the CAFI 2024 annual report / Gabon: no 2024 data available - annual reviews of national LoI milestones were not conducted in 2024 and no data was provided in the CAFI 2024 annual report / Cameroon: Additionally, CAFI and Cameroon signed an LoI in October 2024 – currently in an engagement phase. Two large scale projects have been approved including USD 20 million to Cameroon's Coffee & Cocoa Development Fund. The ambition is to mobilise USD 2.5 billion over a ten-year period to support Cameroon’s transition to a green economy, promote deforestation-free agriculture, and advance the country’s sustainable development efforts.
CAFI 4 (Output): Number of improved stoves distributed/sold (and total number of households) and in which territory, sector, group and village	DRC / 2024 target: 119,000 stoves (global as of 2026) including: / Energy prog: 87,000 stoves / RoC: / 2026 target: 4,200 stoves / 2024 milestone: On track to reach 2026 target.	Milestones partially met, 2026 DRC target exceeded. / DRC: 163,189 households have to date benefitted from cleaner cooking solutions in the DRC including improved cookstoves (145,426), liquid gas petroleum stoves and briquettes. / Of the 145,426 improved cookstoves distributed under FONAREDD activities, 134,285 were distributed by the energy programme and 11,141 by PIREDDs. / RoC: Launch for expression of interest to identify local artisans to produce improved cookstoves and launch their businesses.
CAFI 5: Examples of institutional improvements within CAFI to increase impact and effectiveness	Progress being made on strengthening the Metrics hub and developing independent verification of land use projects and management tool for PES projects; New indicator agreed to track average disbursement rates.	Milestones met. / CAFI further developed the Metrics Hub in 2024, including its feature to estimate CO₂ sequestration resulting from various measurable interventions. CAFI has also began to implement sample-based visual verifications of the progress reported for land use activities using spatial data reported by implementing organisations. / CAFI also finalised the PES framework which lays out the strategic pillars for national and regional deployment, ranging from political and financial advocacy to standardisation, planning tools, applied research and performance tracking. 5 projects are set to use this framework in 2025. / CAFI state that for the first time in 2024, compliance to the 2023 CAFI Monitoring Evaluation and Learning Guideline has allowed an analysis of the CAFI outcomes towards which projects spend. The Consolidated Annual Financial Report provides the expenditure delivery rate per project. The overall expenditure rate was 63.21% at the end of 2024.
[note] The data presented brings together the data specific to several indicators from the CAFI results framework (A.P.2; A.P.3 and A.P.4; A.P.5; E.P.4; E.P.5; F.E.1a.) synthesised to obtain a single indicator for Sustainable Land Management. The data included in this table show the total number of hectares, combining sustainable land management practices and including both specifically georeferenced data and non-georeferenced data.
[note] CAFI. (2025b) CAFI 2024 Annual Report Annex: Reporting against the M&E framework – 2024.
[note] Also no data on how many of this is under validated policies, plans, management or protection measures.
[note] CAFI. (2025c) CAFI Annual Report 2024. The number of direct beneficiaries of contraceptive projects is not disaggregated further than this eg. by country.
[note] FONAREDD. (2025) Rapport Annuel Consolide 2024. Relates to non-reproductive health projects only.
[note] CAFI. (2025b) CAFI 2024 Annual Report Annex: Reporting against the M&E framework – 2024.
[note] Specifically, gender is reflected explicitly in any of the 4 following criteria: i) gender analysis in the project document context; ii) implementation of activities; iii) monitoring. iv) allocation of budget
[note] Data comes from CAFI 2024 Annual Report Annex: Gender Assessment 2024n.
[note] Due to the political transition of August 2023 and subsequent reshuffling of ministerial positions, the closing of the Letter of Intent is postponed to 2025 (2024 CAFI Annual Report (narrative report).
[note] CAFI explained that there has been no annual review of milestones for the LoIs in 2024. No reliable data is available beyond what is in the annual report, which only contains information for the DRC. Annual reviews of DRC, RoC and Gabon LoI milestones are expected in 2025.
[note] FONAREDD. (2024) Rapport de la revue annuelle 2023. Partenariat entre La République Démocratique Du Congo et l’Initiative pour la Forêt d’Afrique Centrale (CAFI).
[note] FONAREDD. (2025) Rapport Annuel Consolide 2024.
[note] CAFI. (2025c) CAFI Annual Report 2024.
[note] FONAREDD. (2025) Rapport Annuel Consolide 2024.p.43.
[note] CAFI. (2025c) CAFI Annual Report 2024. The total number of clean cooking solutions is not disaggregated between LGP stoves and briquettes – only improved cookstove figures are provided in the FONAREDD (2025) report.
[note] FONAREDD. (2025) Rapport Annuel Consolide 2024.p.46.
[note] CAFI. (2025c) CAFI Annual Report 2024.
[note] CAFI. (2025c) CAFI Annual Report 2024.
[note] UN Multi-Partner Trust Fund Office (MPTF). (2025a) Central African Forest Initiative Consolidated Annual Financial Report of the Administrative Agent. May 2025.

ARCAN project		Forest and Farm Facility (FFF) (FAO)
Score		A
Project Weighting %:	4.8%		Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Outcome 1: More enabling policy and legal frameworks for FFPOs delivered through more FFPO-inclusive governance and cross-sectoral processes
FFF 1 (Outcome): Number of policy/legal documents, processes or decisions that have changes made in favour of the interest of FFPOs through direct FFPOs engagement at 1) national level; 2) at international level	Cumulative 2026 (end-of-programme) target: 26 policy changes (24 sub-national/national policy changes (based on an average of 3 per country); 2 regional/global level policy changes) / 2024/2025 Milestone: Linear progress (year 7 (78%) out of 9) towards the 2026 target = 20 policy changes	2026 target substantially exceeded. / Cumulative: 84 policy changes (70 national; 14 international) / 2024/2025 progress: 28 policy changes (21 national; 7 international)
Outcome 2: Increased entrepreneurship, access to markets and finance through gender equitable value chains delivered through new capacity to provide business incubation within FFPOs.
FFF 2 (Outcome): Number of FFPO enterprises based on environmentally sustainable resource use that are providing benefits and returns to their members	Cumulative 2026 target: 8 (1 apex FFPO per country) / 2024/2025 Milestone: Linear progress (year 7 (78%) out of 9) towards 2026 = 6 apex organisations supporting FFPO enterprises	2026 target substantially exceeded. / Cumulative: 720 FFPO enterprises (supported by 44 apex FFPOs covering each African country), of which 234 are women-led. / 2024/2025 progress: an additional 65 FFPO enterprises since 2023 (supported by 44 apex FFPOs)
FFF 3 (Outcome): Number of FFPO enterprises that have new or enhanced value addition activities	Cumulative 2026 target: 200 enterprises (25 enterprises (10 women led) per country) / 2024/2025 Milestone: Linear progress (year 7 (78%) out of 9) towards 2026 milestone = 156 enterprises	Milestone and 2026 target partially met. / Cumulative: 325 enterprises (26 in Gambia, 3 in Ghana, 51 in Kenya, 3 in Liberia, 86 in Madagascar, 22 in Tanzania, 101 in Togo and 33 in Zambia; not disaggregated by gender for any country) / 2024/2025 progress: 140 enterprises
Outcome 3: Improved delivery of landscape scale mitigation, adaptation and climate resilience for climate change through direct engagement of FFPOs and integration with inclusive livelihood approaches
FFF 4 (Outcome): Number of ha of the forest and farmland managed by FFPOs where FFF support has contributed to either protection, restoration or sustainable forest and farm management (to improve climate change mitigation or adaptation)	Cumulative 2026 target: 336,000 ha (based on average of 42,000 for 8 countries) / 2024/2025 Milestone: Linear progress (year 7 (78%) out of 9) towards 2026 = 262,080 ha	Milestone not met, 2026 target on track. / Cumulative: 235,089 ha / 2024/2025 progress: 111,298 ha / Progress is slightly behind the 2024 milestone – currently 70% towards the 2026 target.
FFF 5 (Output): Number of people who have benefitted directly from that protection, restoration and sustainable forest management (including on-farm agroforestry systems) disaggregated data	Cumulative 2026 target: 340,000 people (based on 2026 target) / 2024/2025 Milestone: Linear progress (year 7 (78%) out of 9) towards 2026 milestone = 265,200 people	Milestone not met, 2026 target on track. / Cumulative: 234,333 people / 2024/2025 progress: 67,913 people / Progress is slightly behind the 2024 milestone – currently 69% towards the 2026 target.
FFF 6 (Output): Number of people directly supported in coping with the impacts of climate change	Cumulative 2026 target: 145,117 people (+6,000 per year) in line with a reasonable trajectory since 2022 / 2024/2025 Milestone: 133,117 people (+6,000 per year) in line with a reasonable trajectory since 2022	2026 target substantially exceeded. / Cumulative: 301,280 people / 2024/2025 progress: 174,163 people / In Annex 9 the disaggregated data (per country) for 2024 totals more (309,560) than the Africa cumulative total provided above.
FFF 7: Examples of institutional improvements within FFF to increase impact and effectiveness	2024/2025 Milestone: Robust TOR for the evaluation is approved and procurement completed; new grants agreed in 10 countries; work started to enhance risk monitoring.	Milestone met. / 2024/2025 progress: Evaluation ToR / drafted and inception report completed. / Not yet commenced. New grants / agreed; work started to enhance risk / monitoring. / In 2024, FFF issued 88 letters of / agreement and 117 direct beneficiary / grants, covering 12 countries. (FFF / 2025b). / Progress has been made on / implementing the FAO Environmental / and Social Framework (ESF); new ESF / implementation guidelines and risk / assessment procedures are being / developed, and grievance mechanisms / included in all contracts.
[note] The corresponding 2024/25 ARCAN reporting year for FFF covers the period January 2024 – December 2024.
[note] The cumulative totals provided in this column for 2024 are those presented in Annex 9 as the ‘Africa total.’ The starting year for cumulative results is 2018 running to 2024.
[note] The 2024 totals are provided by subtracting the 2023 cumulative total found in last year’s FFF Annual Report (presented in the ARCAN MEL Unit Monitoring Synthesis Report of June 2024) from this year’s cumulative total.
[note] This milestone was agreed with FFF following a proposal from FCDO which was based on the average annual increase observed for this indicator over the first few years of Phase 2.
[note] As agreed by FCDO and FFF, this indicator has been added since last year’s M Synthesis report to enable measurement of improving project management and, to some extent, measure the institutional capacity building of the IP – this indicator is used across all ARCAN IPs. Each year’s milestone for this indicator will be agreed with FCDO and FFF on an annual basis.

ARCAN project		Weather and Climate Information Services in Africa (WISER Africa)
Score		A
Project Weighting %:	28.2%		Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Progress at Outcome Level
WISER 1: number of policies, plans, resource allocation or other decisions developed or revised to incorporate weather and climate information services and/or evidence supported by WISER	Cumulative: 20 examples of new or revised policies, plans, resource allocation or other decisions incorporating weather and climate information	Milestone exceeded / Cumulative total: 22 policy documents or resource allocation decisions have integrated WCIS / 2024/2025 progress: 22 policy documents or resource allocation decisions have integrated WCIS / NB: Milestone for previous FY was 0 so this is the first time WISER Africa is reporting progress on this indicator
WISER 2: Number of institutions/organisations using weather and climate information services or evidence/analysis supported by WISER in their decision-making / (ARCAN RF: Outcome-level indicator)	Cumulative: / Use: 79 institutions/organisations	Milestone substantially exceeded / Cumulative total: / Use: 165 institutions/ organisations / 2024/2025 progress: / Use: 147 institutions/organisations
WISER 3: Number of people (women, men, PWDs, young people and older people and other groups identified as marginalised) that use WCIS to inform their decision-making / (ARCAN RF: Outcome-level indicator)	Cumulative: / Use: 102,421 people	Milestone not met / Cumulative total: / Use: 35,638 / 2024/2025 progress: / Use: 35,638 people (variance of - 66,783) / Programme level disaggregated data / Data are from 2 projects: ResAlert and WISER Kenya (DARAJA). / Male = 17,684 / Female = 17,954 / People with disability = 2,343 / Project level data / Age: / ResAlert / Children (0-14 years) = 13,915 / Youth (15-24 years) = 7,632 / Adult (25-64 years) = 12,602 / Elderly (65+ years) = 1,349 / WISER Kenya (DARAJA) / 18-30 years = 71 / 31-59 years = 69 / 60+ years = 0 / NB Milestone for previous FY was 0 so this is the first time WISER is reporting progress on this indicator
WISER 4: Number of people (women, men, PWDs, young people and older people and other groups identified as marginalised) with access to weather and climate information services through a range of channels (IO1) / (ARCAN RF: Output-level indicator)	Cumulative: 280,219 people	Milestone not met / Cumulative total: 166,812 (39 people were reported for the previous FY) / 2024/2025 progress: 166,773 people with access were reported (mostly through ECREA PICSA training for farmers, ResAlert beneficiaries, and EWSA directly engaged end users). / Variance: -113,407 / Programme level disaggregated data: / Data from 4 projects: ECREA, ResAlert, EWSA, WISER Kenya (DARAJA). / Male = 81,795 / Female = 85,157 / People with disability = 3,597 / Project level data: / Age: / ECREA / Under 35 yrs = 82,503 / Over 35 yrs = 36,378 / ResAlert / Children (0-14 years) = 19,879 / Youth (15-24 years) = 10,903 / Adult (25-64 years) = 18,003 / Elderly (65+ years) = 1,927 / WISER Kenya (DARAJA) / 18-30 years = 71 / 31-59 years = 69 / 60+ years = 0 / EWSA: no age data reported (data collection approach not consistently used).
WISER 5: Number of organisations and institutions with increased access to weather and climate information services (IO2) / (ARCAN RF: Output-level indicator)	Cumulative: 65 organisations	Milestone exceeded. / Cumulative total: 136 (49 were reported for the previous FY) / 2024/2025 progress: 87 organisations / Variance: +71
WISER 6: Number of users (institutions/organisations, women, men, PWDs, young people and older people and other groups identified as marginalised) in the WCIS value chain that have increased awareness of the value of using WCIS in decision-making. (IO4) / (ARCAN RF: Output-level indicator)	Cumulative: 35,004 users	Milestone substantially exceeded. / Cumulative total: 45,641 / 2024/2025 progress: 45,641 users / Variance: +10,637 / Project level data (only ResAlert has reported against this indicator) / Male = 22,652 / Female = 22,989 / People with disability = 3,012 / Age: / Children (0-14 years) = 17,891 / Youth (15-24 years) = 9,813 / Adult (25-64 years) = 16,203 / Elderly (65+ years) = 1,734 / NB Milestone for previous FY was 0 so this is the first time WISER is reporting progress on this indicator
Progress at output level
Output 4: Improved enabling and policy environment for better delivery and sustainability of weather and climate information services
WISER 7: Amount of public funding WISER attracts for the increased generation, uptake and use of weather and climate information Output 4.1 / (ICF KPI 11) / (ARCAN RF: Outcome-level indicator)	£0	Milestone substantially exceeded / Cumulative total: £788,329 (£280,925 were mobilized during previous FY) / 2024/2025 progress: £507,404 / Daraja and ECREA have leveraged additional funding (£493,000 from German Federal Foreign Offices for year 1 of the DARAJA Sudan Emergency and Weather and Early Warning Service and £14,404 from ENABEL to scale ECREA activities to the southern part of Rwanda) / NB: we are discussing with Met Office how to ensure this indicator is as meaningful as possible; as leveraging further funding is largely dependent on other development partners, implementing partners are often reluctant to commit to milestones. We will review ahead of the next annual review.
WISER 8: Number of evidence/knowledge products produced by organisations supported by WISER to influence use of services and analysis in decision-making / Output 4.2 / (ARCAN RF: Output-level indicator)	6 knowledge products	Milestone exceeded / Cumulative total: 16 / 2024/2025 progress: 16 / NB Milestone for previous FY was 0 so this is the first time WISER 3 is reporting progress on this indicator
WISER 9: Examples of institutional improvements within WISER to increase impact and effectiveness / (ARCAN RF: Output-level indicator)	Drafts shared of (a) a plan for how to collect evidence on resilience under WISER and (b) 1 Story of Change on resilience.	Milestone met / A draft note on Evidencing Resilience through WISER was submitted alongside the WISER annual report. This includes a plan for strengthening WISER’s evidence base on resilience. This note also included a Story of Change on Strengthening resilience to weather-related hazards through anticipatory action in urban Africa.
[note] In this table, cumulative totals are results reported in 2024/25 since the year 2023/24

ARCAN project	Sustainable Risk Mitigation Initiative (SRMI, part of ESMAP)
Score	A
Project Weighting %:	10.8%	Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Outcome: Increased prioritisation and investment in renewable energy, energy efficiency and access, enabling a just and inclusive energy transition
SRMI 1 (Outcome): / Number of client governments who received supporting to prepare and run RE tenders, / From the SRMI capacity-building partner (IRENA) or transaction advice.	N/A – a milestone was / not set for the 2024/25 / ARCAN reporting year	2023/2024 progress: Following World Bank Approval of country lending programmes by end-2023, SRMI is now supporting 19 countries to build technical capacity and prepare for running RE tenders. The delivery partner for this capacity building/ training is IRENA.
Outputs
Output 1: Governments / supported to improve / their enabling / environment for / renewable energy / SRMI 2: Number of / countries supported / (BETF) – including / inclusive VRE / integration, / generation and / transmission / planning, policies, / regulations, and / strategic advice	Cumulative (including / baseline data): 24 / 2023/2024 milestone: 3	Milestones substantially exceeded. / Cumulative results: 27 countries supported. The SRMI team, is embedded in the World Bank’s flagship Energy System Programme, ESMAP, and provides transactional advice across sub -Saharan Africa and beyond. / 2023/2024 progress: 6 countries in sub-Saharan Africa received direct SRMI support. SRMI’s share of transaction advice is much greater than anticipated, supporting 7/10 government transactions in the region.
Output 2: “Commercially viable” renewable energy projects are prepared for investment . / SRMI 3: Provision of technical assistance and advice to WB client governments. Indicator = Number of countries supported (RETF) – including transaction advisory [TA], feasibility studies [FS], E&S assessments [E&S], generation and transmission plan [Plan], VRE integration	Cumulative (including baseline data): 8 / 2023/2024 milestone: 3	Milestones met. / This is an impressive achievement in the current investment climate, where most projects were few RE projects are commercially viable without significant support from concessional finance and/ or DFIs. / Cumulative results: 8 bankable RE projects have been prepared for investment. / 2023/2024 progress: 3 RE projects prepared for investment
Output 3: New risk mitigation instruments developed, or offering improved access, to sub Saharan African entities. / SRMI 4: Number of countries where new risk mitigation instruments deployed	Cumulative (including baseline data): 4 / 2023/2024 milestone: 3	Milestones not met / Cumulative results: 3 new risk mitigation instruments developed. / 2023/2024 progress: 2 new risk mitigation instruments developed / SRMI works to influence the availability of risk instruments offered by others. SRMI’s result will be the improved access to instruments for SSA governments and entities. SRMI also fund-raise for bespoke project interventions, bridging the viability gap, and can evidence success particularly in West Africa. E.g. Sao Tome CAPEX buy-down and liquidity guarantee.
Output 4: Renewable energy scale-up supports socio-economic development and action on gender / SRMI 5: Country-level planning for the energy transformation. / Indicator = Number of countries developing roadmaps including maximising socio-economic benefits derived from renewable energy development with a focus on women’s empowerment and skill development	Cumulative (including baseline data): 10 / 2023/2024 milestone: 3	Gender: Being assessed as part of wider ESMAP programme. Removing from SRMI indicator. No longer applicable. / (5) Country roadmaps - Substantially not met expectations. / SRMI has directly supported 8 governments to produce roadmaps. / 2023/2024 progress: 0 roadmaps developed / No new engagements, continued support to Botswana, Namibia, Mali.
Output 5: Knowledge on renewable energy developed and shared / SRMI 6: Number of renewable energy knowledge and guidance products developed	Cumulative (including baseline data): 5 / 2023/2024 milestone: 2	Strong progress has been shown in 2024 on knowledge-sharing and capacity building through knowledge-sharing events and facilitating networks of expertise in the region to support capacity building however the milestone of knowledge products has not been met. / Cumulative results: 4 knowledge and guidance products developed and shared. / 2023/2024 progress: 1 knowledge and guidance product developed and shared
Output 6: Public sector capacity-building supported at client governments. / SRMI 7: Number of countries completing the capacity building programme from Q1 2024-Q1 2025.	Cumulative milestone not set. / 2024 milestone: 12, with evidence of follow up and increased capacity by participants	Milestones met. / Following the approval of WB government loans at end-2023, SRMI launched their concept note for a 2-year capacity building programme. The first cohort of 12 countries has now completed year one. / Cumulative results: 12 countries / 2024 progress: 12 countries sent a broad range of senior energy officials, regulators and utility companies - to the hybrid training facilitated by in partnership with GIZ, IRENA and the Power Futures Lab. / The training, supports public sector planning, coordination and the building of technical capacity and senior networks.
Contextual Delivery Indicators
Context 1: Volume of mobilised finance influenced for renewable energy projects: / a) public (government, WB, climate finance) / b) private	No 2023/2024 milestones set.	This indicator was originally intended to monitor mobilisation of private sector finance, but is now almost entirely DFI and climate finance. Sharp falls in FDI flows to Africa, outside extractives and mining, are consistent with this outcome. / a) Cumulative result: $3,720 million / 2023/2024 progress: $1,094 million / The largest volume of public finance influenced is expected from Ethiopia ($522.63 million), Namibia ($138.5 million), and Somalia ($100 million). / 2022/2023 progress: $200 million / b) Cumulative: $2,222 million / 2023/2024 progress: $1,084 million / The largest volume of private finance influenced is expected in Namibia ($940 million). / 2022/2023 progress: $365 million
Context 2: Expected increase in renewable energy capacity (MW) due to SRMI supported projects committed: / a) Photovoltaic (PV) / b) Wind / c) Geothermal	No 2023/2024 milestones set.	Expected results as follows if all SRMI projects materialised only x% will reach financial close and be built: / a) Cumulative: 1,647 MW / 2023/2024 progress: 404 MW / The largest expected increase in renewable energy capacity for PV includes Namibia (200 MW), Liberia (70 MW), and the Gambia (50 MW). / 2022/2023 progress: 235 MW / b) Cumulative: 300 MW / 2023/2024 progress: 200 MW / The expected increase in renewable energy capacity for wind is from Namibia (200 MW). / 2022/2023 progress: 100 MW / c) Cumulative: 20 MW / 2023/2024 progress: 20 MW / The expected increase in renewable energy capacity for geothermal is from Ethiopia (20 MW). / 2022/2023 progress: 0 MW
Context 3: Expected increase in storage (MWh) due to SRMI-ESMAP supported projects committed	No 2023/2024 milestones set.	Expected results as follows if all SRMI projects materialised only x% will reach financial close and be built: / Cumulative: 1610 MWh / 2023/2024 progress: 636 MWh / The largest increase in storage (MWh) is expected from Kenya (150 MWh), Namibia (90 MWh), Somalia (90 MWh), and Guinea Bissau (80 MWh). / 2022/2023 progress: 140 MWh
Context 4: Number of people expected to benefit from electricity access due to projects supported by SRMI-ESMAP instruments	No 2023/2024 milestones set.	Expected results as follows if all SRMI projects materialised only x% will reach financial close and be built: / Cumulative: 21,563,400 people / 2023/2024 progress: 2,435,400 people / The majority of expected people to benefit from electricity access due to projects include Somalia (1,820,000) and Liberia (494,000). / 2022/2023 progress: 3,495,000
[note] Information based on FCDO Reporting_January 29 2025 sent by FCDO on 28.04.25 and SRMI SSA Country pipeline downstream support spreadsheet sent by FCDO on 28.04.25.
[note] 176 Results based on SRMI-FCDO Results spreadsheet sent by FCDO on 28.04.25
[note] Ibid
[note] Ibid
[note] Ibid
[note] ESMAP (2024) ESMAP Progress Report FY24, Energizing Renewables / Sustainable Renewables Risk Mitigation Initiative, p61
[note] Results based on SRMI-FCDO Results spreadsheet sent by FCDO on 28.04.25
[note] Draft ARCAN Results Framework - 11th December2024 sent by FCDO on 28.04.25
[note] Outcome indicators for SRMI, based on expected results, will be used as contextual indicators for 2024/25. This is because actual results are not tracked, and 'delivered results' will not be received until the end of the ARCAN programme. The outcome indicators are more useful as indicators of context, which can be used to inform implementation over time, rather than indicators to track progress year-on-year.
[note] The starting year for cumulative results is SRMI FY21 running to FY24.
[note] Results based on SRMI-FCDO Results spreadsheet sent by FCDO on 28.04.25
[note] Ibid
[note] Ibid
[note] Ibid
[note] Results based on SRMI-FCDO Results spreadsheet sent by FCDO on 28.04.25
[note] Ibid
[note] Ibid
[note] Ibid5
[note] Ibid
[note] Ibid
[note] Ibid
[note] Ibid
[note] Ibid
[note] Ibid

ARCAN project	Sustainable Energy Fund for Africa (SEFA) (AfDB)
Score	A+
Project Weighting %:	9.9%	Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Outcome 1: Increase access to sustainable energy / Outcome 2: Increase adoption of renewable energy
SEFA 1 (Outcome): People with new electricity connections (number) / Based on actual results from concessional investments.	Cumulative 2025 milestone: 3.3 million people / Cumulative 2030 milestone: 7.5 million people / 2024 milestone: not set	2030 cumulative milestone likely to be substantially exceeded. 2025 milestone already exceeded. / Cumulative results: 5,7mn people connected from concessional investments. (Early results are due to SEFA stepping in to support utility-scale projects that were on the brink of failure after COVID.) / Cumulative results for number of people with new electricity connections have been driven by the COVID-19 Off-Grid Recovery Platform (940,438 connections, 4.7 million people connected) and the African GoGreen Fund (203,082 connections, 1 million people connected). / 2024 progress: 938,120 people connected from concessional investments
SEFA 2 (Outcome): New renewable power capacity installed (MW) / Based on actual results from concessional investments.	Cumulative 2025 milestone: 1,500 MW / Cumulative 2030 milestone: 3,000 MW / 2024 milestone: not set	Not met expectations. Indicated should be revised to focus on expected installation from pipeline. / Cumulative results: 243 MW from concessional investments. The 2025 milestone (unrevised from 2019), is no longer a relevant benchmark for actual installed capacity, but remains relevant for future (expected) capacity, for which SEFA’s pipeline of approvals is still on track with x MW expected? / 2024 progress: 199 MW from concessional investments
SEFA 3 (Outcome): Energy savings from new investments (GWh/year) / Based on actual results from concessional investments.	Cumulative 2025 milestone: 730,000 GWh/year / Cumulative 2030 milestone: 1.35 million GWh/year / 2024 milestone: not set	Redundant indicator as SEFA is targeting new energy access not switching to cleaner energy – remove for 25/26
SEFA 4 (Outcome): Direct employment (number), of which 50% are women / Based on actual results from concessional investments.	Cumulative 2025 milestone: 1,000 of which 50% women / Cumulative 2030 milestone: 2,160 of which 50% women / 2024 milestone: not set	Substantially exceeded the milestones originally set in 2019. This is due to SEFA’s post-COVID role supporting the viability gap on shovel-ready projects in North Africa. / Gender monitoring has not been carried out but is presumed not to be met as jobs primarily in construction and heavily male dominated industry – suggest remove gender target. / Cumulative results: 14,165 jobs from concessional investments / 2024 progress: 4,880 jobs from concessional investments
SEFA 5 (Outcome): Total volume of investment mobilised by SEFA commitments ($m) / Based on actual results from concessional investments.	Cumulative 2025 milestone: US$1.8 billion / Cumulative 2030 milestone: US$3.1 billion / 2024 milestone: not set	Across ARCAN the optimism for private sector capital mobilisation has been overtaken by global events. As a result, SEFA’s (2019) targets for mobilisation now look redundant. Almost all the RE investment in Africa is now concessional finance or climate finance. / Not met expectations / Cumulative results: US$809 million co-investment mobilised from concessional investments / 2024 progress: - US$28.6 million from concessional investments
Promoting and delivering sustainable energy solutions through more investments
SEFA 6 (Output): Technical Assistance projects/programmes (number) / a) Green Mini-Grids (GMG) projects and programmes deployed / b) Green Baseload (GBL) projects and programmes deployed / c) Energy Efficiency (EE) projects and programmes deployed. Note that “energy efficiency” is not very relevant in SSA, and is therefore not relevant to SEFA’s activity. SEFA have begun to classify other activities under this indicator to address the reporting ask. (e.g. EVs and CC).	a) Cumulative 2025 target: 9 / Cumulative 2030 target: 15 / 2024 milestone: 0 / b) Cumulative 2025 target: 9 / Cumulative 2030 target: 15 / 2024 milestone: 3 / c) Cumulative 2025 target: 6 / Cumulative 2030 target: 10 / 2024 milestone: 0 / Note: 2024 targets taken from SEFA 2024 workplan	2025 milestones for green baseload projects are being met, which is an impressive result in the new investment environment. / Green mini-grid projects are off target, as expected, reflecting the deteriorating viability of off-grid opportunities in recent years. / a) Cumulative results: 2 GMG TA projects and programmes deployed / 2024 progress: 0 GMG projects and programmes deployed / No additional TA was provided to GMG projects in 2024. Lending is expected in 2025 for the Africa Mini-Grid Acceleration Programme II. This leaves the total of GMG TA projects and programmes deployed at two. / b) Cumulative results: 14 GBL TA projects and programmes deployed / 2024 progress: 3 GBL projects and programmes deployed / Three new GBL TA projects and programmes were approved in 2024 (compared to three in 2023). These include AESTAP Regional / Multinational, Axian Energy Green Project Preparation Facility, and AESTAP Nigeria. Total GBL TA projects and programmes deployed are now 14, exceeding the 2025 target. / c) Cumulative results: 5 EE TA projects and programmes deployed / 2024: 0 EE TA projects and programmes deployed / No additional TA was provided to EE projects in 2024. This leaves the total of EE TA projects and programmes deployed at five.
SEFA 7 (Output): Finance committed by SEFA ($) / a) Green Mini-Grids projects and programmes deployed / b) Green Baseload projects and programmes deployed / c) Energy Efficiency projects and programmes deployed	a) Cumulative 2025 target: $105 million / Cumulative 2030 target: $175 million / 2024 milestone: $25 million / b) Cumulative 2025 target: $143 million / Cumulative 2030 target: $238 million / 2024 milestone: $39 million / c) Cumulative 2025 target: $30 million / Cumulative 2030 target: $50 million / 2024 milestone: $34 million / Total expected in 2024 Annual workplan: $98 million approval target was 75% of pipeline, or $73.5 million	Cumulative milestones on track to be met, with green baseload and energy efficiency finance already exceeded. / a) Cumulative results: $79 million committed to GMG projects and programmes / 2024 progress: $18 million committed to GMG projects and programmes / $18 million for GMG projects in 2024 (compared to $27 million in 2023). This is lower than the $25 million target in 2024. The Off-Grid REC Accelerator Project ($6 million) is expected to be finalised in H1 2025. / b) Cumulative results: $151 million committed to GBL projects and programmes / 2024 progress: $54.74 million committed to GBL projects and programmes / $54.74 million for GBL projects in 2024 (compared to $22.3 million in 2023). This exceeded the target of $39 million. / c) Cumulative results: $78 million committed to EE projects and programmes / 2024 progress: $35 million committed to EE projects and programmes / $35 million for EE projects in 2024 (compared to $21 million in 2023). This exceeded the target of $34 million. / A significant amount of finance was committed by SEFA in 2024, with a total amount of $79 million approved in the reporting period, exceeding $73 million in 2023 and the 2024 approval target of $73.5 million. By December 2024, total approvals had reached $107.7 million.
SEFA 8 (Output): Case studies demonstrating SEFA’s contribution to accelerating the energy transition	2 case studies agreed by March 2025	Pending: Finalised case studies (drafted by ARCAN MEL unit with support from SEFA)
Key institutional improvements within SEFA
SEFA 9 (Output): Examples of institutional improvements within SEFA to increase impact and effectiveness	SEFA Mid Term Review is shared with donors and recommendations on strengthening SEFA’s disbursements, operational model and MEL approach (including updated targets) are agreed by March 2025	Pending: Finalised Mid-Term Review Report due in June 2025
[note] SEFA 1 is calculated by multiplying total connections (1,143,520) by an average household of five (based on SEFA guidance in the 2023 Monitoring Handbook). SEFA (2024) Semi-annual report, July-December 2024, p10
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] Ibid
[note] SEFA Strategic Framework set a MWh/year unit based target but the 2022 and 2023 Annual Reports outline GWh/year reporting. It is assumed that GWh/year is SEFA unit of measurement.
[note] Ibid
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] SEFA (2024) Semi-annual report, July-December 2024, p10
[note] SEFA 2.0 reported actual results to date are from concessional investment operations since the tracked results are direct outputs rather than outcomes of SEFA’s intervention. SEFA (2024) Semi-annual report, July-December 2024, p10
[note] SEFA (2024) 2024 Annual Workplan and Budget, p5
[note] SEFA (2024) Semi-annual report, July-December 2024, p19-20
[note] SEFA (2024) Semi-annual report, July-December 2024, p19
[note] SEFA (2024) Semi-annual report, July-December 2024, p15
[note] Ibid
[note] SEFA (2024) Semi-annual report, July-December 2024, p24
[note] SEFA (2024) Semi-annual report, July-December 2024, p23-24
[note] SEFA (2024) Semi-annual report, July-December 2024, p18
[note] This figure is $24 million according to SEFA 2024 Annual Workplan and Budget.
[note] SEFA (2024) Semi-annual report, July-December 2024, p12
[note] SEFA (2024) Semi-annual report, July-December 2024, p21
[note] This figure is $35 million according to the SEFA 2024 Annual Workplan and Budget.
[note] SEFA (2024) Semi-annual report, July-December 2024, p1
[note] SEFA (2024) Semi-annual report, July-December 2024, p18
[note] SEFA (2024) Semi-annual report, July-December 2024, p17
[note] SEFA (2024) Semi-annual report, July-December 2024, p12
[note] Ibid
[note] SEFA (2024) Semi-annual report, July-December 2024, p22
[note] SEFA (2024) Semi-annual report, July-December 2024, p21
[note] SEFA (2024) Semi-annual report, July-December 2024, p1
[note] ARCAN Results Framework March 2025
[note] Ibid
[note] Ibid

ARCAN project	Africa Adaptation Acceleration Programme (AAAP) (GCA)
Score	B
Project Weighting %:	12%	Weighting revised since last AR?	Yes

Delivery Indicator(s)	Milestones for this review	Progress
Pillar 2: Infrastructure and Nature-based Solutions
AAAP 1 (Outcome): $ in approved investment projects reflecting adaptation solutions brokered or adaptation finance solutions influenced a) public / b) private	Cumulative: / a) $ 8,100,000,000 / b) $ 871,000,000	a) Milestone exceeded (public) / Cumulative: $ 9.1 billion / 2024/2025 progress: $4.6 billion (all public) / 19 IFI investment projects make up 4.6 billion in investments influenced throughout the reporting period. / b) Milestone substantially not met (private) / Cumulative: $0 as reported
AAAP 2 (Outcome): Number of expected beneficiaries targeted through approved investment solutions informed by GCA	Cumulative: 66,000,000 expected beneficiaries targeted through approved investment solutions informed by GCA / 2024/2025: 23,000,000 expected beneficiaries (40% women)	Milestone moderately not met / Cumulative: 63,400,000 expected beneficiaries reported to have been targeted through approved investment (direct) or enabling (indirect) solutions informed by GCA. / 2024/2025 progress: 16,600,000 expected beneficiaries (42% women)
AAAP 3 (Output): Number of infrastructure resilience advisory packages developed (disaggregated by sub-sector including PPPs)	Cumulative: 17 advisory packages / 2024/2025: 10 advisory packages	Milestone moderately not met / Cumulative: 16 advisory packages / 2024/2025 progress: 9 advisory packages, of which 2 concerning Energy; 7 Transport.
AAAP 4 (Output): Number of Masterclasses delivered to enhance and embed capacity for designing, planning, and financing climate resilient infrastructure, and % of participants reporting strengthened capacity or empowerment as a result of the course.	Cumulative: 7 masterclasses / 2024/2025: 5 masterclasses / 152/160 participants (i.e., 95%) report experience of strengthened capacity, skills, and/or empowerment for adaptation action	Milestone moderately exceeded / Cumulative: 8 masterclasses / 2024/2025 progress: 6 masterclasses / GCA delivered 6 masterclasses on Climate-Resilient Infrastructure PPPs in 2024, in Kenya (2x), Senegal (2x), the Netherlands and Uganda. / % participants: 30/30, i.e. 100% of the participants of the Climate Adaptation Changemakers School Masterclass (Nairobi, Oct 2024) report experience of strengthened capacity, skills, and/or empowerment for adaptation action. No % reported for the other Masterclasses.
Pillar 4: Adaptation Finance
AAAP 5 (Outcome): $ in approved investment projects reflecting adaptation solutions brokered or adaptation finance solutions influenced / a) public / b) private	Cumulative: $ 900,000,000 (public and private combined) / 2024/2025: $ 600,000,000 / (public and private combined)	Milestone substantially not met / Cumulative: $ 338,000,000 in approved investment / 2024/2025 progress: $ 0 in approved investment / As in 2023, concerns the AfDB’s African Financial Alliance on Climate Change support to the Tanzania Agriculture Development Bank ($66 million) and the AfDB/GCF Staples Crops Processing Zones project ($272 million)
AAAP 6 (Outcome): Number of entities directly accessing climate finance	N/A	N/A / Cumulative: 1 entity / 2024/2025 progress: 0 entities / GCA continued to support Direct Access Entities (DAEs) through its Technical Assistance Program (TAP) to access GCF, GEF and AF funds throughout 2024.
AAAP 7 (Output): Number of GCF concept notes, funding proposals, and accreditation analyses supported to access climate finance	Cumulative: 27 GCF concept notes/ proposals/ accreditation analyses supported / 2024/2025: 15 GCF concept notes/ proposals/ accreditation analyses supported	Milestone substantially not met / Cumulative: 12 GCF concept notes/ proposals/ accreditation analyses supported / 2024/2025 progress: 0 GCF concept notes/ proposals/ accreditation analyses supported
Cross-cutting
AAAP 8 (Outcome): Number of GCA solutions and methodologies scaled, mainstreamed, or replicated by external stakeholders	Cumulative: 70 GCA solutions and methodologies / 2024: 27 (Pillar 2 only)	Milestone substantially not met / Pillar 2: / Cumulative: 43 GCA solutions and methodologies. / 2024/2025 progress: an additional 19 GCA solutions and methodologies scaled, mainstreamed, or replicated since 2023 (all Board-approved MDB or Multilateral Climate Fund investments / projects mainstreaming GCA solutions) / Pillar 4: N/A / Combined values: Cumulative: 43 GCA solutions and methodologies / 2024/2025 progress: 19 GCA solutions and methodologies
AAAP 9 (Outcome): # policies and development strategies endorsed by government that are informed by GCA research and support	N/A – no milestone was set in the 2024/25 ARCAN reporting year	N/A As this is a recent focus of work under AAAP, milestone targets will not be set until the ARCAN 2025/26 reporting year.
Key institutional improvements within AAAP
AAAP 10 (Output): Examples of institutional improvements within AAAP to increase impact and effectiveness	Evidence of diversification of AAAP support to non-MDB organisations	Throughout 2024, AAAP has strengthened its support to and cooperation with the private sector as well as non-IFI financial institutions. In addition, GCA has been working on enhancing its internal learning and evaluation function, with the aim to strengthen continuous learning and evidence-based decision-making within AAAP.
[note] 2023 value does not align between AR 2023 (2 bln) and AR 2024 (2.4 bln), with the value for 2022 not seeming to correspond by deduction (2.3 bln in 2023 AR; 2.1 in AR 2024 (deducted)).
[note] See ‘Delivery Assessment’ narrative.
[note] Beneficiaries targeted through approved investment (direct) solutions informed by GCA.
[note] 2023 results: Annual Report 2024 includes 5 packages (1 Energy, 1 PPP, 3 Transport) reported in 2023; Annual Report 2023 and Pillar-Level Results Overview Pillar 2 in Annual Report 2024 report only 1. Cumulative result 2024 based on 2023 results Annual Report 2023 is 7 (2022 (6) + 2023 (1)) + 9 (2024) = 16. 9 packages in results summary Annual Report 2024 are not reflected in pillar-level results overviews.
[note] Not reflected in pillar-level results overview.
[note] % of masterclass participants that report experience of strengthened capacity, skills, and/or empowerment for adaptation action overall, i.e. across all 6 masterclasses is not reported upon.
[note] Same amount as reported in 2023. $ 300,000,000 in Monitoring Synthesis June 2024 based on rounded amount of $ 0.3 bln in AAAP Annual Report 2023, narrative text AAAP Annual Report 2023 similarly states $ 338,000,000.
[note] AAAP Annual Report 2024 narrative (p. 71) does mention GCF concept notes supported by GCA; yet these are not reflected in the result summary and pillar-level results overview as these are to be approved still and therefore not reported as part of the Annual Report’s results.r.
[note] Sum of two sub-indicators: i) ‘number of approved investment projects reflecting adaptation solutions brokered’ (the number of projects valued in AAAP 1) and ii) ‘number of instances where a GCA solution has been brokered with evidence of being under implementation’, i.e. the sum of MDB and non-MDB projects. GCA reports the latter to be less common as most of its influence occurs through MDB projects, but as there are examples of this type of project as well, they are tracked separately.
[note] AAAP Annual Report (and subsequent feedback) do not specify whether cumulative milestone of 70 in 2024 is for Pillar 2 and Pillar 4 only.
[note] GCA Results Framework Guidance Note: ‘This can be policies and strategies from countries, MDB, International Organizations…These can be counted when the government approved, launched, or started implementing the policy/strategy’.
[note] With this only recently being a primary focus of work under AAAP, no milestone available currently but 2024 results are to inform milestones setting going forward.
[note] Output indicator in AAAP AR 2024: ‘# GCA interventions and engagement to provide inputs to strengthen policies and development strategies’, does not specify whether these have indeed been endorsed by government.

Performance Area	Actionable Learning
Score				B
Impact weighting (%):		10 %	Weighting revised since last AR?	Yes. Increased from 5% to 10%.

Indicator(s)	Milestones for this review	Progress
1. Portfolio learning is documented and shared with internal and external audiences / Number and quality of documents and studies capturing portfolio learning, having met quality standards	2024/2025 Milestone: 4 documents capturing lessons and recommendations / (1 deep dive evaluation, 1 midline evaluation, 1 learning synthesis and 1 learning brief)	(i) Milestone partially met: Midline evaluation in progress; Learning synthesis 2024 delivered; June 2024 Monitoring Synthesis; Deep Dive evaluation of CAFI PAC delivered; CIWA Zambia Story of Change delivered
2. Learning mechanisms and forums are in place to facilitate internal learning and establish IP synergies / Number of learning-oriented meetings and events with internal and external audiences, with positive feedback on their value	2024/2025 Milestone: / (i)Internal: 7 learning fora (each IP) / (i) External: 4 ARCAN MEL Committee, 2 MEL working group, 1 annual learning event with 70% participants report positive feedback	(i) Milestone exceeded: all IPs instigated or participated in learning in at least one forum / (ii) Milestone partially met: 2 full ARCAN MEL committee meetings held (May 2024, March 2025,). One learning event held (March 2025). Post survey feedback indicates 100% positive feedback. MEL working group meetings have not been held during the period under review due to lack of demand.
3. Evidence and lessons generated by the portfolio inform internal (ARCAN) and external (UK government) multilateral and bilateral programming / Examples where ARCAN evidence and lessons have informed decision-making	2024/2025 Milestone: / Internal: / 2 IPS; %x FCDO ARCAN team / External: 0	(i) Milestone partially met: A recommendations tracker has been established as part of the ARCAN MEL dashboard to track progress on recommendations. The tracker currently contains a total of 52 recommendations, 25 of which were made prior to the development of the tracker. Of the remaining 27, 22 are for the attention of FCDO and 5 for the attention of the MEL unit. However, the tracker requires updating to indicate the status of recommendations and which ones have been acted on.
[note] ARCAN Learning Synthesis 2024
[note] https://arcan.masae-analytics.com/recommendations_tracker_view