Evaluation Report for Programme Name:
Africa Regional Climate and Nature Programme (ARCAN) mid-term evaluation

Response to ARCAN mid term evaluation

Background / The Africa Regional Climate and Nature Programme (ARCAN) is a regionally managed FCDO programme delivering UK International Climate Finance objectives by addressing transboundary climate change, nature loss and resilience challenges in Africa. It works primarily through large multilateral and regional platforms. ARCAN aims to support African countries to be more climate resilient, low carbon and environmentally sustainable, and increase political commitment to tackling climate change. It works across five pillars (nature, water, finance, energy and information), through seven implementing partners: / the Central African Forest Initiative (CAFI), supporting forest governance and policy reform in the Congo Basin; / the FAO’s Forest and Farm Facility (FFF), strengthening forest and farm producer organisations and climate‑resilient livelihoods; / the World Bank’s Cooperation in International Waters in Africa (CIWA), advancing transboundary water and groundwater governance; / the Africa Adaptation Acceleration Programme (AAAP), implemented by the Global Centre on Adaptation and African Development Bank (AfDB), to increase adaptation across investments and policies; / the AfDB’s Sustainable Energy Fund for Africa (SEFA) which uses concessional finance and risk mitigation to catalyse private investment in clean energy; / the World Bank’s Sustainable Renewables Risk Mitigation Initiative (SRMI) to strengthen capacity, reduce risks and improve the enabling environment for renewable energy investment; and / the UK Met Office WISER, which strengthens availability and use of weather and climate information services. / The ARCAN mid term evaluation was conducted in 2025 by the ARCAN MEL unit, independently contracted by FCDO and delivered by Ecorys, as ARCAN’s lead MEL contractor. It consists of an initial document review and interviews with FCDO staff (Phase 1) and subsequently, six case studies designed to address priority evidence gaps (Phase 2). These case studies focused on: / Gender, Disability and Social Inclusion (GEDSI) within CAFI / Forest and Farm Producer Organisations businesses support in Kenya by FFF / Impact of CIWA’s engagement in the Horn of Africa / AAAP’s approach to sustainability; and maximising Value for Money from Nature Based Solutions. / SEFA’s role in mobilising investments / The ARCAN components for CAFI, FFF, AAAP, SEFA, SRMI, and CIWA are closing at the end of March 2026. As such, although originally designed as a mid-term evaluation, the case studies ended up being stand-alone studies to inform FCDO’s final assessments of progress and ongoing implementing partner delivery. The WISER component was not covered by the evaluation case studies, with the Phase 1 findings (evidence gaps on contribution to resilience and approaches to sustainability) addressed by technical assistance rather than an evaluation. / Recommendations from evaluations: / The mid term review learning summary highlighted general lessons for ARCAN and beyond around: / The importance of local partnerships, meaningful co-creation and political economy analysis and addressing the enabling environment for sustainability; / The need to be realistic about challenges, investor risks and additionality associated with raising private sector capital; / The importance of taking a comprehensive approach to the role of GEDSI to deliver outcomes; and / The potential to strengthen meaningful measurement of impact and transformational change, particularly in relation to assessing critical policy and enabling environment outcomes. / Findings have been discussed internally within FCDO and shared externally, including with the implementing partners. Specific findings from each study were primarily designed for implementing partners and were presented as recommendations to inform partner programme delivery. They are summarised in the table below. / Overall summary: / The mid-term evaluation phases 1 and 2 provided evidence and supported a better understanding of successes and challenges within the large and complex ARCAN programme. Successes include SEFA’s innovative financial model securing private finance within a high-risk financial context; AAAP’s high quality analysis and innovation on adaptation; FFF and WISER’s strong partnerships and approach to co-creation with local organisations; and CAFI, CIWA and SRMI’s essential but long-term work on the enabling environment and political commitment. The case studies were focused on evidence gaps and highlighted the importance of increasing the focus on sustainability (including strengthening and broadening local partnerships and establishing realistic theories of change), inclusion and meaningful measures of impact.

Evaluation Report Title: ARCAN mid-term evaluation

Recommendations:	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
Recommendation 1: CAFI to address recommendations to better reflect GEDSI across its portfolio (CAFI GEDSI case study).	Accepted	The CAFI case study findings and recommendations were presented to and discussed with the CAFI secretariat and CAFI Board, who broadly accepted and welcomed the findings. FCDO will continue using its position as a donor and on the Board to support implementation.
Recommendation 2: FFF to address recommendations to increase sustainability and inclusion of enterprise partnerships, including broadening value chains, establishing more inclusive selection processes and strengthening monitoring, coordination with other partners and learning (FFF case study).	Partially accepted	The evaluation study has been shared and discussed with the FFF team, with findings broadly accepted. The ARCAN FFF component is not receiving any additional funding from March 2026, limiting the potential for FCDO to continue engaging in the implementation of the recommendations.
Recommendation 3: CIWA to address recommendations to strengthen the capture and use of relevant learning internally and externally, and re-look at sustainability and cost recovery assumptions (CIWA case study).	Partially accepted	The study has been shared and discussed with CIWA, who acknowledged and appreciated the findings. The ARCAN CIWA component is not receiving any additional funding from March 2026, limiting the potential for FCDO to continue engaging in the implementation of the recommendations.
Recommendation 4: AAAP to address recommendations to increase focus on implementation of their analytical work on nature-based solutions (NBS) and strengthen comprehensiveness of cost-benefit analysis (AAAP NBS study).	Accepted	The study was shared and discussed with AAAP, who accepted and welcomed the findings. The ARCAN AAAP component is not receiving any additional funding from March 2026, limiting the potential for FCDO to continue engaging in the implementation of the recommendations.
Recommendation 5: AAAP and funders to address recommendations to further strengthen and expand local partnerships, increase focus on national financing and planning and tracking sustainability, to maximise impact. FCDO to consider value for money analysis of domestic v consultant-led different delivery models and consider more long-term strategic partnerships with financial and other national institutions (AAAP sustainability study).	Mainly accepted	The study was shared and discussed with AAAP, who accepted and welcomed the findings. The ARCAN AAAP component is not receiving any additional funding from March 2026, limiting the potential for FCDO to continue engaging in the implementation of the recommendations. / The recommendations around how to maximise sustainability and strengthen and diversity local partnerships were shared and discussed across FCDO and will be particularly relevant to maximising impact with reduced ODA budgets. At this time there is no budget for an additional value for money study.
Recommendation 6: SEFA and funders to strengthen understanding and communications around renewable energy prospects in Africa with investors and the general public, including pension funds (SEFA case study).	Accepted	The study was shared with SEFA, who noted that they had already been addressing some of the findings. The ARCAN SEFA component is not receiving any additional funding from March 2026, limiting the potential for FCDO to continue engaging in the implementation of the recommendations. The recommendations and study have been shared with FCDO teams working on energy.