Annual Review Template

Title: The Growth Gateway Programme
Programme Value £ (full life): £76.09 million		Review date: / 29th August 2025
Programme Code: [AMP ID#] 300812	AMP start date: 24th January 2019	AMP end date: / 31st March 2026

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A+	A+	A++	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	D0002842.odt
DevTracker Link to results framework:	Available from 04/09/25

A. SUMMARY AND OVERVIEW
Description of programme

The Growth Gateway (GG) Programme delivers development impact through increased two-way trade and investment between the UK and Low-Income and Middle-Income Counties (LICs, MICs) that promotes sustainable and inclusive growth as well as mutual economic benefits. It delivers this through three active components:

- A main component delivered via a consortium headed by Boston Consulting Group (BCG) incorporating a free-to-access online digital service, a Business Advisory Service and a portfolio of in-country interventions.
- Support to the World Bank’s Resilient and Inclusive Supply-Chain Enhancement (RISE) Partnership via it’s Extractives Global Programmatic Support Trust Fund Phase 3 (EGPS 3) and the International Finance Corporation’s Donor Committee for Enterprise Development (DCED).
- Deployment of technical assistance from the British Geological Survey (BGS).

This review will primarily focus on the programme component led by the consortium supplier as it accounts for the majority of delivery (95% of budget spend), but the review will also carry out light touch assessments on the World Bank’s RISE (0.5% of budget spend) and British Geological Survey partnerships (4% of budget spend).

BCG Led Component

Business Advisory Service

The Business Advisory Service (BA) identifies high potential businesses which may be seeking to attract investment from, or export to, the UK. The service helps direct businesses to existing guidance and support or provides them with tailored advice. So far, GG has engaged with over 1,300 businesses and, in doing so, surfaced a set of recurring business needs relating to market entry guidance, investor readiness, and navigating regulatory requirements. Recognising these patterns, the programme has invested in a suite of digital resources, ranging from sector and market insights to investor-readiness guides, and significantly upgraded GG’s public-facing digital services with a new GOV.uk campaign website.
GG is transitioning out of providing direct, tailored advice to businesses, and instead will utilise targeted digital signposting, which offers stronger VfM as well as extended reach and greater consistency of offer. The one-to-one BA service will therefore be wound down early in the coming year (Year 5).
Interventions

GG interventions explore and unlock high potential trade and investment opportunities, in close collaboration with Posts (UK Embassies and High Commissions) in target countries. Typically, project funds are used to pay for expertise to work with businesses to identify and refine their business models and secure investment, or to work with Governments to improve rules and frameworks for investment. GG also deploys non-ODA in partnership with DBT to identify commercial opportunities for UK companies, which also deliver development outcomes.

GG runs an annual consultative planning process to identify and select interventions with Posts. For the FY 25/26, we have strengthened the programme’s Strategic Fit Assessment to standardise and simplify early engagement with Posts. This year, the programme delivered 22 interventions across 20 countries in Africa and Asia, contributing to climate transitions, poverty reduction, inclusion and economic transformation goals, while strengthening key UK bilateral and multilateral partnerships. Interventions utilised Overseas Development Aid (‘ODA’) and blended ODA/non-ODA funding and are listed below.
[note] The strategic fit assessment assesses how well each intervention aligns with key HMG priorities. Namely, driving GG outcome-level results, matching the GG delivery offer, sector prioritisation, leveraging supplier capabilities and GG differentiators, and optimising value for money, price, and budget fit.

Table 1 BCG Led Interventions for FY 24/25
Intervention	Geographic Scope	Detail	ODA/ non-ODA split (%)
Green Services Deal Accelerator (GSDA)	Africa	Support to growth-stage African firms to fast-track inclusive, green investments through investor-readiness and deal packaging	100% ODA
Green Special Economic Zone (SEZ) Ph3	Cambodia	Design and mobilisation of £1b green infrastructure pipeline in Cambodia's SEZ, supporting climate-smart industrial policy	83% ODA/ 17% Non-ODA
National Adaptation Plan (NAP) Ph3	Philippines	Pipeline development in two provinces focused on climate resilient investment opportunities	87% ODA/ 13% Non-ODA
SMME Just Energy Transition Partnership (JET-P) Ph3	South Africa	Support to Small Medium and Micro Enterprises (SMMEs) in green sectors which support the transition from coal through investor-readiness and deal acceleration	100% ODA
ASEAN industrial Policy - Phase 2	ASEAN	Regional policy framework development on clean energy, innovation and digital integration	80% ODA/ 20% Non-ODA
ASEAN Regional Value Chains	ASEAN	Facilitating ASEAN supply chain localisation and value capture in regional green industries	100% ODA
Sustainability Impact Assessment of Blueprint 2025	ASEAN	Assessment of ASEAN’s Blueprint 2025 to inform inclusive, resilient industrial policy	100% ODA
Critical Minerals	Multiple	Pipeline scoping and stakeholder engagement for priority minerals across LICs and MICs	100% ODA
Critical Minerals Ph2 & National Development Strategy Ph1	Kyrgyzstan	Strategy design and diagnostics to position critical minerals sector within national plans	100% ODA
JET plan Ph3	Mozambique	Designing delivery tools and pipeline planning for Mozambique's JETP implementation	100% ODA
Adaptation & Resilience priority projects pipeline	Pakistan	Developing project portfolios to mobilise finance for agricultural climate resilience in Pakistan	100% ODA
Women Economic Empowerment in Africa Tech	Africa	Targeted support to women-led African ‘climate-positive’ firms through readiness, pitch tools and investor access	100% ODA
Critical Minerals	South Africa	Mapping value chain gaps and policy barriers in South Africa’s critical minerals sector	100% ODA
Financial Services Accelerator (FSA) PMO	ASEAN	Supporting cross-programme strategy, prioritisation and governance for ASEAN financial policy work	100% ODA
Trade Finance Pilot (x 4)	Vietnam, Philippines, Malaysia, Indonesia	Diagnostics and structuring to inform UK-linked green trade finance pilots	100% ODA
SMME JET-P	Indonesia	Foundational delivery design and pipeline diagnostics for JET-P SMMEs	100% ODA
Services	Ghana	Business environment and investment climate diagnostics for tradable services	100% ODA
Critical Minerals	Tanzania	Pipeline structuring, permitting reform and investor policy dialogue in Tanzania	100% ODA
Clean Energy Supply Chain Collaboration	Egypt, South Africa, Morocco, DRC, Brazil, Mexico, Argentina, Turkey, Malaysia, Indonesia, Thailand & Singapore	Coordinating cross-country action to unlock investment in clean energy supply chains	100% ODA

Some friction points around the Post buy-in process emerged this year and in response, detailed departmental guidance has been written to outline the buy-in process including highlighting the resource requirements

World Bank RISE & International Finance Corporation DCED

The RISE partnership develops the midstream and downstream segments of mineral value chains to ensure diversified, sustainable, and inclusive pathways for clean energy products. It does this by promoting improved governance, transparency and business environments for extractive sectors to catalyse responsible investment and improve development impacts from natural resources.

In the current year under review, £400,000 was spent with details of what has been delivered outlined in section F below.

The programme also provides funding for annual membership to the International Finance Corporation’s (IFC) Donor Committee on Enterprise Development (DCED).
In the current year under review, only £37,000 was spent, with details of what has been delivered outlined in section F below.
British Geological Survey

The British Geological Survey (BGS) provides expert advice on geological data acquisition, management and interpretation, as well as bespoke support to sister Geological Survey organisations, and their associated ministries. This supports governments to develop mining codes and better understand their mineral reserves. During the review period, GG worked with BGS to provide this type of support in India, Democratic Republic of Congo (DRC), Rwanda, South Africa, Tanzania, Zambia, Zimbabwe and the Philippines covering:

High-level overviews of the geological potential for critical minerals.
Targeted work with partner country geological surveys to develop their skills and capacity.

BGS deliverables are outlined in the table below; all are 100% ODA funded

Table 2 BGS Interventions for FY 24/25
Geographic Scope	Deliverables
India, South Africa, Philippines	Initial scoping and learning visits, expected to lead to country work plans.
Rwanda	Report on the critical raw materials landscape in Rwanda.
Tanzania	Technical assessment of the Geological Survey Tanzania and relevant geological data. / Desk-based Tanzania critical minerals report
Zambia	Skills analysis and technical training (archival training, laboratory training, critical minerals) delivered to GSD Zambia / Finalisation of the Critical Minerals Brochure
Zimbabwe	Capacity assessment of ZGS and delivery of training course on critical mineral resources.

Budget

This review covers GG’s fourth year of delivery (financial year 2024/25). At the start of FY24/25, the programme was allocated £10.2m with an additional £5.6m allocated in late 2024. From this funding, £15.2m was ODA (of which £9m, 59% was International Climate Finance eligible), and £570k was non-ODA. In FY24/25, Gateway used £3.5M in blended ODA and non-ODA, with Non-ODA contributing to £0.55M (16%) of the blended funding. An additional £4.18m (or an additional 30% on top of the £15.8m allocated from central Business Case) was contributed by Posts from their bilateral ODA budgets, bringing total programme funding for FY 24/25 to £19.9m.

This Review only covers ODA and blended ODA/non-ODA activities. GG non-ODA activities are reported via the FCDO’s Centre For Delivery (CfD) Annual Review.

Summary supporting narrative for the overall score in this review

The programme has delivered above its outcome and output targets, which were scaled up as a result of additional funding received part way through the year, and a deliberate attempt to increase ambition. Increased focus on programme activity with the most direct relevance to logframe targets eventually drove this over performance. The programme has also delivered its strongest value for money (VfM) performance to date, with a rise in all outcome-level results per pound spent. Furthermore, in a step change improvement from last year, and following recommendations of the last Annual Review, 100% of interventions integrated Women Economic Empowerment (WEE). The programme pivoted BA to its new ‘digital first’ approach and launched a refreshed Campaign Page in response to previous performance challenges. It has also worked hard to secure Post buy-in and to maintain strong and consistent communication with key stakeholders, including Department for Business and Trade (DBT).
 Major results by programme theme include:

Green and inclusive deals: Through its Deal Accelerator interventions GG has facilitated and closed deals worth £304m, generating £43 of closed deal value for every £1 spent. ‘Green’ deals represent 60% of the total. Furthermore, 40%+ of the 437 high potential businesses supported to date have reached commercial discussions, representing a near term deal pipeline of more than £1.2bn.

In addition, the programme has developed a pipeline of investments against multi-year transformative projects which will drive green and inclusive transformations within LIC/MICs. Within this additional £2.4bn pipeline, £846m of deals are now in advanced commercial stages. (That is, the total pipeline is valued at £3.6b)

UK climate leadership: GG work on Adaptation and Resilience (A&R) has the potential to benefit 5m+ people at severe risk from climate change. The programme is supporting partner governments to develop fully costed and investable project pipelines, advancing investor engagement on £1.9bn (out of the £2.4bn large and complex project pipeline) of transformative climate projects. In Philippines and Pakistan these pipelines build from their formal National Adaptation Plans, developed with the support of GG in previous years.

Economic diplomacy: The programme has supported 15 major initiatives adopted by partner governments that support economic development, climate action, job creation and the UN Sustainable Development Goals (SDGs). For example, the Cambodia Green Special Economic Zone (SEZ), has supported several SDGs including SDG 8 and SDG 9 through the development of a Green Special Economic Zone (SEZ) and investment pipeline in infrastructure and key growth sectors, SDG 13 by promoting low-carbon design, Environmental Social Governance standards, and green project structuring, SDG 7 was addressed through renewable energy targets within the SEZ and the development of clean energy infrastructure, and SDG 17 by facilitating cross-government collaboration and leveraging public, private, and development finance for sustainable infrastructure. The programme has also helped to ensure 49 Market Access Barrier (MAB) reform plans are accepted or progressed, helping to open new markets.

FCDO and DBT country officers rated their engagement with GG as strong (10 out of 12) based on alignment against priorities, engagement, and application of the work.

Inclusivity and jobs: To date, GG has created 20,529 jobs with the potential for a total of up to 60,000 from work under way. Many interventions focused on job creation for vulnerable and/or underrepresented groups.

The programme has embedded WEE in the design and delivery of all interventions in FY24/25 ranging from tailored deal acceleration support to 11 women-led and women-centric businesses in Africa, to detailed recommendations on gender-responsive design. Furthermore, GG developed systems-level tools, frameworks and learnings on WEE and inclusion that have been shared with governments, investors, businesses and FCDO Centres of Expertise (COEs). In particular, this should be further captured as the FCDO’s Green and Inclusive Growth COE is developed.

- UK growth: The programme has been able to mobilise more than £162M in UK-linked deals to date through direct support to UK businesses and investors. This includes major transactions such as OX Delivers’ £42.8m raise that accelerates clean transport and logistics with direct UK backing, a UK venture capital fund raise of £31m, and additional smaller deals including InspiraFarms (sustainable agritech) and Africa Originals (UK entry trade deal in consumer goods).
- GG has successfully initiated work in the critical minerals sector, including mapping and analysis to identify opportunities and constraints to investment, as well as developing HMG roadmaps for UK partnerships.

Major lessons and recommendations for the year ahead

Key lessons include:
  - New work in the services sector has confirmed initial assumptions about the sector’s high job creation potential, and suitability for GG intervention. The programme should scope opportunities to scale up work in services-focused programming, including targeted support for enabling environments, digital infrastructure, and investment facilitation while taking care to deconflict from other HMG programmes.

  - Long-term, sustained interventions deliver better impact over time. This year has been an important year for capturing learnings on this theme. It is the first year that longer, multi-year interventions formed the majority of programme allocation with 80% of FY24/25 programme spend dedicated to follow-on and longer phases of existing interventions. Impact and value for money have improved as a result.

  - GG has established notably high levels of engagement and trust with investors, HMG affiliates such as British International Investment, businesses (both Fortune 100 firms and SMEs), and business associations, which appears to be an important part of the long-term success and VfM of the programme. The programme needs to leverage these relationships to ensure strong delivery in its final phase.

  - Programme experience this year has shown that deal acceleration interventions need to be carefully tailored to circumstance. Early-stage companies, especially women-led, need bespoke, sustained support, often including peer networks and pitch development. Growth-stage firms benefit from investor-aligned materials and targeted investor matching. Technical support for capital raising must also be carefully timed, so that businesses can access help at the most impactful point.

  - There is strong demand for guidance and insights that draw from interventions and business advisory inbox responses. Utilising these resources is cost effective, particularly for earlier-stage or nascent businesses that may not yet be deal-ready. Feedback from users indicates that the quality and relevance of digital insights is high, and that it helps shape later stages of support or engagement.
  - Women’s Economic Empowerment (WEE) and inclusion can be more comprehensively integrated into the design and delivery of programmes than is commonly assumed in private sector development projects. For the first time, GG was able to ensure 100% of interventions included effective WEE and inclusion, significantly increasing results measured by inclusion. The programme should generate specific transferable lessons.

  - GG adds to evidence that early consideration of sustainability (such as agreeing handover plans) is effective and better VfM.

  - Close collaboration across HMG (especially Posts) is instrumental for sustainability. Structured engagement mechanisms with Posts - such as joint planning, dedicated working groups, and post-led knowledge handovers - support impact, relationships, and sustainability. The GG team developed Post Buy-In guidance note which sets out principles to ensure collaboration with post is efficient and effective; this note may have value beyond GG to other Centres of Expertise (see Programme Management section below for more discussion)

Several structural challenges emerged, which informed programme learning and adaptations going forward:
- Managing trade-offs between near-term vs. sector/systemic impact:
  Firm-focused deal acceleration drives near-term results, while longer-term, multi-phase interventions are critical for transformative investment, policy reform, and building institutional capacity. As such, the programme team has taken a portfolio approach, closely calibrating the mix of intervention types and impact pathways across the programme; the mix needs to be kept under review.
- Alignment with complementary programmes: As engagement with complementary FCDO programmes has deepened, it has been important to clearly delineate GG’s offering and activity from adjacent programmes (e.g. Manufacturing Africa). In some cases, this has meant revisiting the programme’s geographic footprint.
- Securing climate investment amid structural gaps:
  While demand for climate investment is high, mobilising it is a challenge due to weak enabling environments, fragmented pipelines, and limited investor confidence in project bankability. GG is responding by codifying investable models - such as national investment pipelines and blended finance readiness.
- Balancing development impact with commercial viability:
  There is sometimes a trade-off between development impact and commercial attractiveness. To navigate this, the programme ensures there are clear criteria and thresholds that must be met across both lenses, supported further by inclusion of clear indicators in the logframe.

- Critical Minerals is a high priority that GG can support for furthering economic development and global green transition objectives. Funding both BCG and BGS, plus RISE provides the programme with a good portfolio of activity deploying expertise across Asia and Africa. Developing a dedicated critical minerals strategy for the programme, with its own budget, and clear alignment to the logframe will help further define that component of the programme.
- Business to business learning has value but must be targeted: the Business Advisory team contracted a specialist coffee importer to run development sessions for a handful of 'high potential' African businesses. However, the companies were ultimately deemed not suitable for the UK market. Learning has been shared with the newly forming Import Accelerator including having a tighter focus on priority sectors and geographies, well defined company size to work with, defined value proposition to these companies, plus closer alignment with UK market specialists.
In summary, GG has demonstrated that sustained, green and service sector-focused, and investor-engaged interventions can yield strong development and commercial outcomes. Deep local government partnerships and adaptive delivery models have maximised impact and value for money.

Recommendations for the year ahead

Key recommendations for the year ahead are:
Scale successful models across geographies
Several interventions have shown success that can be extended or replicated in new contexts. GG’s SMME support in South Africa has already been scaled from Mpumalanga to additional provinces and adapted to Indonesia, while the trade finance registry model piloted in Vietnam and the Philippines has potential for broader regional uptake.

Ensure intervention alignment with the future Green and Inclusive Growth Centre of Expertise (GIG COE)
Intervention activity should take account of the emerging design and focus of the GIG COE to enable continuation of service and results flows. GG should be available to start intervention activity which GIG COE will continue, but only where it meets the criteria for expansion set out in the original Business Case and aligns clearly with GIG COE objectives. The maturity of many workstreams within GG are delivering strong results, with other workstreams approaching maturity – these investments need to be carefully protected in the transition to the GIG COE.

Increased focus on deal tracking through a ‘deal hub’ to drive maximum impact towards closure
The programme tracks deal pipelines generated through BA and interventions. Increased focus through a dedicated ‘deal hub’ on providing the right support to each deal, including leveraging FCDO’s Growth Investment Partnership GIP Toolkit, should help ensure the maximum number of deals reach closure in the lifetime of the programme. Options for specialist deal support via a ‘hub’ should be explored.

Ensure that the impact of any changes in HMG resourcing are fully understood, reported, and mitigated
As the programme transitions to its final phase, reductions in number and seniority of HMG personnel dedicated to GG will reduce. This is likely to create risks to the GG programme in terms of supplier management, increasing focus on risk awareness (open and systemic engagement) at the delivery partner level.

Programme management and Monitoring, Evaluation and Learning (MEL)
Embed handover planning at programme and intervention levels
In this final phase of the programme, sustainability of digital resources, commercial pipelines, and relationships with stakeholders should be a core focus. GG needs to further embed sustainability while preparing for programme transition. This includes planning handovers for business engagement and MAB tracking to DBT and transitioning programme-wide learnings, playbooks and frameworks to the GIG and Trade Centres of Expertise.

1. Institutionalise strategic engagement with UK capital deployment institutions
   While GG has engaged British International Investment (BII), UK Export Finance (UKEF), and others on a regular basis, the final phase of the programme presents an opportunity to formalise knowledge-sharing. Periodic teach-ins and targeted strategy sessions could feed directly into these institutions’ strategy review processes, helping to mainstream GG learnings into UK investment approaches.
2. Create structured partnerships to embed and scale GG learning and resources
   Institutional partnerships with African/Asian universities, business schools, and incubators could serve as longer-term vehicles for continuing GG’s delivery approach. This would allow ongoing implementation and adaptation of investment and policy tools in market, while also providing a pathway for UK-funded knowledge to remain locally anchored. This approach should also be considered as part of the design of the GIG COE.
3. Pair deal acceleration with ecosystem strengthening
   Standalone support to firms must be matched by efforts to address systemic gaps (such as investor-readiness infrastructure, local capital architecture, and social attitudes facing women entrepreneurs). Future interventions should build in ecosystem-wide changes alongside direct support, making future deal flow more viable and sustainable.

An independent evaluation is strongly recommended this year to assess the effectiveness, provide accountability, and generate lessons. This remains an incomplete recommendation from last year. An independent evaluation can be used to critically evaluate VfM, deepening learning and informing potential areas of focus for the GIG COE.

Consider the level of ambition in the existing log frame and whether more ambitious targets are required for the following year
In light of very positive results this year, and the impact that targeted efforts can have, what more could be done with increased targets in the coming year. A light touch review of the targets will be carried out in year 5.

Communication and dissemination
1. Build a comprehensive, targeted dissemination and training calendar as part of the comms strategy
   GG should define a targeted dissemination calendar that includes both internal briefings and wider-facing knowledge-sharing sessions with clear audience segments relating to the broader comms strategy. Sessions should be targeted at FCDO Posts, Whitehall departments, and CoEs, with a view to institutionalising the programme’s most effective approaches.
2. Building a stronger narrative for programme successes
   The programme and its suppliers should explore and build compelling ways to showcase the programme’s successes which demonstrate VfM, building a coherent narrative to describe the programme’s impact, including the centrality of direct investment mobilisation for sustainable economic development. Innovative new channels for sharing GG’s impact and VfM should be explored.
B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change has not been revised but following the previous Annual Review, several changes were made to the Logframe to improve the tracking of programme outcomes. Improvements have been made to Output Indicator 4.1 and Outcome Indicator 2.1, updating the definition of MABs to ensure better alignment with DBT’s use of the term, for onward tracking, action and resolution.
Several new indicators have also been added, including:

Output Indicator 3.4: Average Intervention Development Impact (DI) Score –has been introduced at the output level.
[note] GG uses a six-dimension DI score to evaluate the development impact of the businesses that the programme supports. Each business is scored on each dimension to indicate the relevance and impact, and this is then summed to get an aggregate view.

- Output Indicator 5.2: Average Posts’ Engagement Score - This new indicator tracks the programme’s ability to contribute to Posts’ objectives.
- Outcome Indicator 1.3: Value of large-scale and/or complex trade & investment projects supported that have secured commercial interest / a MoU - This indicator, which will begin to be tracked in Year 5, has been added to capture where GG has supported long-term transformational projects towards project maturity.
Overall, these changes sharpen focus on systemic impact and highlight the role the programme plays in broader HMG-wide objectives. The programme should continue to make improvements to this end, including:
1. Reviewing logframe indicators to ensure that they capture downstream impacts and areas where the programme has directly strengthened the wider business ecosystem, including but not limited to indirect jobs.
  [note] Direct jobs are those created as an immediate effect of investment supported by the programme. Indirect jobs are those estimated to be created as a result of wider economic impacts.
2. Redefining indicators previously used to assess engagement with Business Advisory to ensure they work with the revised digital tools and resources.
3. Reviewing programme targets to ensure that they remain ambitious but realistic, to help achieve impact and VfM.
4. Incorporating sub-indicators to systematically track sustainability of interventions and efficacy of handover processes.
5. Incorporating quantitative data to support the qualitative narrative provided for intervention DI scoring where possible.
6. Better capturing the additional impact of Post buy-in where Post uses their own business case, outside of the Post engagement score.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Table 3 Outcome Targets and Actuals
[note] Outcomes are tracked cumulatively in terms of % achievement vs targets.  Annual performance also exceeded expectations by even higher proportions.
Outcome		Y4 target	Y4 actual (cumulative)	% Diff.	Y4 actual (Y4 only)
1.1	Total value of facilitated T&I deals (£M)	290	304	+5%	90
1.2	# MABs identified with reform plan accepted	45	49	+8%	20
1.3	Value of large-scale and/or complex trade & investment projects supported	N/A	N/A	N/A	N/A
2.1	Jobs expected to be created / supported by T&I deals	19,900	20,529	+3%	6,976
2.2	Dev. impact score of supported opportunities (out of 6)	3.0	4.6	+53%	+0.6
3.1	Extent to which GG has helped HMG and private actors in pursuit of UK economic & foreign policy interests (out of 5)	3.0	4.0	+33%	N/A

GG has performed well against outcome targets for FY 24/25, adapted to varying levels of funding. It has also had to contend with a volatile geo-political environment, and staffing challenges both in the GG central HMG team and at Post. Significant progress has been made on integrating WEE and deal acceleration in particular, with early progress on large, complex projects, advancing a pipeline valued at over £2.4bn. While these contributions will be formally captured in the FY25/26 logframe, current momentum demonstrates the programme’s capacity to structure strategic, high-value opportunities aligned with long-term UK and partner priorities.

- The maturity of GG’s T&I pipeline is expected to yield further outcome-level results in the coming year. The lag between support and deal closure remains a structural factor in outcome timing. Longer-term interventions and ongoing central team engagement will allow the programme to track and support businesses through this journey. As per the recommendations above, mature and maturing workstreams will need to be carefully protected in the transition to the GIG COE to ensure benefit realisation.
- GG will continue to prioritise growth-stage firms and structure support around investment facilitation, co-investor engagement, and technical packaging to further increase conversion into closed deals. DI scoring methodology will continue to ensure consistent alignment with the programme’s development impact objectives. The programme will focus more on the conversion of existing identified MABs through to acceptance (and, in some cases, reform itself) as part of follow-on phases of interventions, while selectively deepening the MABs identified in newer interventions.
The programme outcome-level achievements are summarised below:

Outcome 1: Increase in trade and investment in the UK and low- & middle-income countries, with more firms involved.

Outcome 1.1: total trade and investment deals facilitated

The programme has facilitated 35 trade and investment deals to date, totalling £303.6m. More broadly, 40%+ of deals supported throughout the programme have now reached commercial discussions, representing a pipeline of £1.2bn+. This reflects a more targeted and tailored approach to deal support, including through deal accelerator programmes as well as a natural progression of deals over the programme’s lifetime. Conversion rates outperformed standard benchmarks. Key success factors for the progress against this indicator are i) careful selection of high-priority opportunities (sector, geography, maturity of business etc.); ii) detailed understanding of buyer/investor needs; iii) expertise in delivering investment readiness support and navigating the investment landscape; iv) the length of time over which workstreams have been allowed to mature; v) strong knowledge and connections in focus country. Going forward, it would be beneficial to disaggregate the total T&I value by gender, to not only better understand the impacts of WEE objectives on Small, Medium and Micro Enterprises (SMMEs) but to also interrogate the challenges faced specifically by women-owned businesses.

The review recommends the programme should collect data disaggregated by gender on the value of all deals closed.
Outcome 1.2: number of market access barriers that have reform plans accepted

Of the 189 Market Access Barriers (MABs) identified by the programme, 49 (26%) have been accepted for reform by partner governments, against a target of 45. These have been verified and evidenced by intervention-level MEL reporting. All accepted MABs have been captured and formally handed over to government counterparts and HMG Posts, and embedded in the reform roadmaps, implementation charters or regional regulatory frameworks of partner stakeholders.
A key success factor has been early, close engagement with partner governments and embedding reform plans within government strategies, rather than independently identifying market access barriers and then bringing them to partners. GG has also significantly strengthened its collaboration with DBT teams to ensure that MABs are included in the Department for Business and Trade’s Market Access Service system (DMAS) and definitions are aligned. The programme has identified a number of barriers that hinder trade and investment but do not meet the formal classification of market access barriers. Tracking non-MAB barriers would highlight real-world challenges that businesses face beyond formal policy issues and is recommended for inclusion in GG. Assessing long-run impact of reforms in terms of sustained economic benefits and improved market functionality is also recommended (potentially with the Department for Business and Trade).

20.The review recommends tracking the identification and resolution of non-MAB barriers and exploring options to track the long-term real economy impact of identifying and resolving MABs.
Outcome 1.3 – Value of large-scale and/or complex trade & investment projects
While this is a new indicator for the next reporting year, data is already being gathered on the status of the current pipeline. Going forward, GG will focus on progressing these large-scale projects from concept to bankability, including investor packaging and supporting policy reform where required.

21. The review recommends ensuring the methodology to assess the likelihood of deal closure is sufficiently rigorous, utilising analysis from ex-post assessments where deals have (or have not) closed and that there is provision in place to continue tracking the deals beyond project lifespan.
Outcome 2: Trade and investment between the UK and low- & middle-income countries is more likely to deliver development impact and climate adaptation & mitigation
Outcome 2.1: number of jobs expected to be created/supported by trade and investment deals
Deals facilitated by GG are expected to create 20,529 jobs with creation of quality, sustainable and inclusive jobs an increased focus this programme year. Job quality is assessed within each intervention’s Development Impact (DI) framework where contributions to decent work, income improvement, skill development, and inclusive participation are assessed. Sustainability often relates to the longevity of roles in green or resilient sectors, while quality encompasses access for underrepresented groups, improved working conditions, and income enhancement. The South Africa SMME JETP model on green SMEs was expanded to Indonesia, also focusing on JETP related SMME opportunities. On the Cambodia Green SEZ intervention, sector prioritisation intentionally targeted labour-intensive, climate-aligned industries. In the Philippines NAP, infrastructure and services interventions are designed to support climate-resilient livelihoods at a subnational level. The programme does not currently quantify and report the quality of jobs created.
22. The review recommends ensuring the programmes tracks data that captures the quality and productivity of the jobs created as well as wider inclusivity and sustainability dimensions to record against the logframe.
Outcome 2.2: development impact score of supported opportunities (out of 6.0)
GG achieved an average Development Impact (DI) score of 4.6 out of 6.0 for supported high-potential businesses (HPs), against a target of 3.0. The higher than expected result is accounted for by a more intentional screening approach, particularly across the South Africa SMME Just Energy Transition portfolio and the Green Services Deal Accelerator (GSDA) intervention, which have helped shift the programme toward greener, higher-impact firms (businesses showing measurable contributions to climate adaptation or resilience increased from 42% to 60%, while climate mitigation gains rose from 32% to 60%). WAfTech and GSDA contributed notably to this result, with supported firms scoring highly on gender equity, environmental performance, and inclusive job potential. These businesses were selected and supported using a structured methodology that integrates DI criteria into business diagnostics and investment readiness tools.

23.The review recommends both utilising the same set of Sustainable Development Goals (SDGs) for DI scoring and reviewing the current DI score target to determine if it’s sufficiently ambitious
Outcome 3: UK relations with LICs and MICs are more likely to deliver on UK economic and foreign policy interests.

Note: Economic diplomacy results are delivered through non-ODA spend as well as through secondary benefits of ODA. The primary use of ODA spend by GG is focused on achieving poverty reduction and development impact goals.

Outcome 3.1: Extent to which the programme has helped HMG and private actors in pursuit of economic and foreign policy interests
GG serves as a strategic partner for the UK’s economic diplomacy agenda, contributing to improved bilateral relationships in priority geographies. This year, the programme achieved a score of 4.0/5.0 on economic diplomacy, reflecting GG’s role in supporting UK foreign and economic policy interests through technical assistance and investment-related reform (eg. Cambodia GSEZ, Philippines NAP, Mozambique ETS) including adoption of national policies or strategies (eg. Kyrgyzstan, ASEAN). The programme’s diplomatic value has been enhanced by the seniority of its relationships, including regular engagement with ministers, permanent secretaries, and senior officials across key partner governments. Active coordination with over 10 FCDO Posts has ensured GG’s work is aligned with diplomatic objectives and contributes to the UK’s reputation as a delivery-focused and trusted technical partner. While the economic diplomacy score is effective in capturing some impact, adding further quantitative metrics would be a positive step towards capturing the wider scope of impact particularly when assessing the impact of blending ODA and non-ODA where the benefits are not clear.

24.The review recommends expanding and refining measures of economic diplomacy to better capture soft power benefits of interventions in addition capturing the UK growth benefits.
Details of independent evaluation outlined in MEL section.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Given the programme’s continued high performance against the logframe targets and alignment with HMG objectives, there is good evidence that the programme should continue with its planned activities into Y5. Post-GG planning should be a key feature over the next year to ensure continuity of impact.

C. DETAILED OUTPUT SCORING

Output Title	The UK Government trade and investment service offer to low- and middle-income countries is better promoted to businesses and coordinated with UK Government representatives in country
Output number:		1	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative total)	Progress	Y4 actual (Y4 only)
No. of relevant firms reached by outreach campaigns and events	9,000	9,183 (+2%)	1,183
No. of substantive business engagements with GG services	23,000	25,125 (+9%)	7,383

Briefly describe the output’s activities and provide supporting narrative for the score.
Substantial volume of business engagement through events and services:
The programme substantively engaged with 25,125 firms through digital, hybrid (webinars and roundtables), and in-person channels. Over the year, GG delivered a balanced mix of 10 virtual, 9 in-person, and 2 hybrid communications events designed to engage stakeholders on specific opportunities. The programme engaged 1,141 (cumulatively 9,183) businesses across 8 external events over the year to drive awareness of the programme. Examples of events include the WAfTech Investor Engagement Forum, an industry roundtable for GCPA, and targeted Cambodia SEZ outreach sessions. Feedback was generally positive, however at a Wilton Park Conference on Green and Inclusive Growth many women business leaders and owners discussed being 'over-mentored and under-funded'. This was echoed by a number of women entrepreneurs participating in GG who were interviewed as part of this Annual Review.
Digital offering upgraded:
GG significantly enhanced its digital offering this year, introducing a new Campaign website serving as a single platform to extend outreach and support high quality lead generation. The team also published investor toolkits (e.g. GSDA) and gender-lens materials (e.g. WAfTech) that are already in active use by businesses and wider stakeholders.

Over the past year, the programme has seen 6,106 unique users across online tools and guidance pages and has supported over 1,100 enquiries through its inbox service, which heavily leveraged digital knowledge resources to respond to requests. GG’s digital landing and guidance pages continue to attract strong international interest, with ~30% of users from Africa and Asia—while most users (~65%) remain from the UK, highlighting sustained domestic engagement. A low bounce rate of 22.2% across our guidance pages, suggests users are actively engaging.
[note] Bounce rate is the percentage of visitors who leave the site after visiting only one page and is calculated by counting single page visits and dividing it by total visits.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output on the number of UK Government user engagements with GG services was discontinued in 2023-24 and is thus not recorded in this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress: The programme has invested in a comprehensive revamp of the GG website, which will enable easier access to programme materials and better promote GG’s offer across HMG, businesses and partner governments.

Recommendations for the year ahead:
1. Continuously update the repository with latest knowledge products to maximise reach to stakeholders, responding to their needs.
2. Optimise the design of both the resources and the website to enhance usability and accessibility, responding to user feedback.
3. Promote across relevant comms materials and outreach to become a single point of entry for engaged businesses
4. Socialise resources internally across relevant posts and wider HMG teams for onward sharing
5. Prioritise gathering feedback from users on this service to ensure it is as efficient as possible.
6. Create a sustainability plan to ensure continuity of service, that the digital repository provided by the website is not lost when the campaign term, or the programme ends.
7. Collect regular feedback from women business owners to understand their unique requirements and adapt support accordingly to ensure it is useful and does not result in 'over-mentoring', including through tailoring support to their individual requirements and knowledge levels, and ensuring regular follow up. This can fold into GG’s existing work to further refine their models of providing support to businesses, especially with regard to securing investment finance.

Output Title	Businesses in UK and low- & middle-income countries are supported to engage in trade and investment with positive climate and development impact and significant secondary UK commercial potential
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	Yes, was 35%

Indicator(s)	Milestone(s) for this review (cumulative)	Progress	Y4 actual (Y4 only)
2.1 Inbox response rate (%<10days)	70%	90% (+20% pp)	-2%
2.2 Number of high potential (HP) businesses supported	370	437(20%)	181
2.3 Number of green high potential (HP) businesses supported	188	229 (+22%)	100
2.4 High potential business satisfaction rate	72%	93% (+21pp)	+3%

Briefly describe the output’s activities and provide supporting narrative for the score.
Growing late-stage pipeline of businesses, many in commercial discussions:
GG has surpassed targets for supporting HP (high potential) businesses and its pipeline of businesses has grown substantially in the last year through focused interventions, including deal accelerators (GSDA, WAfTech, SA SMME, Indonesia SMME) and other targeted efforts to advance late-stage project opportunities (Cambodia, Mozambique).

Successful launch of deal accelerator model:
GSDA was the first full-scale implementation of the deal accelerator model, providing end-to-end advisory, including pitch development, sector scoping, and investor matching. GSDA was highly successful, resulting in 4 deals (20% of businesses supported) worth £64m, generating £43 in closed deals for every £1 spent.
Support under the SA SMME intervention has already led to 5 deals with more expected, and the WAfTech and the shorter, first phase Indonesia SMME interventions have built promising pipelines that are expected to yield deals soon.
Women’s Economic Empowerment mainstreamed in firm selection and support
Over the programme period, 179 HP businesses were assessed against Women’s Economic Empowerment (WEE) criteria; 63% of these met at least one of the 2X WEE criteria (further details outlined in section D), demonstrating a strong pipeline. In addition, over 200 women-led or women-benefitting businesses received tailored dissemination resources through the WafTech intervention. GG also embedded WEE targeting into firm selection, scoring, and support delivery, leveraging the 2X framework, with WAfTech and GSDA accelerators supporting 17 women-led and women-centric firms alone on investment readiness. This support was typically pitch-deck development and helping entrepreneurs to build confidence to meet with investors which - while positive - was not enough to counter the challenges faced by women, including feelings of competition, and lack of investor trust in women.
Enhanced investor engagement and central team management:
Through strong collaboration between the central business advisory team and interventions, GG has developed a comprehensive management system for investor engagements. This enables different intervention teams to identify (and add to) a list of the most relevant investors.
Business advisory (BA) service transitioning to digital-first approach
GG's business advisory service received 224 enquiries this year, down from 331 the previous year. Although the BA service successfully built a pipeline of African businesses looking to export to the UK, this did not yield deals, nor build the expected relationships required to support this activity on an ongoing basis. With this blocker in place, the service could not provide the value for money the programme desired, and BA 1-2-1 support was discontinued.

Over the course of the programme, the BA team has developed digital resources and standardised guidance that enables rapid and efficient signposting.  Therefore, GG is transitioning to a "digital-first" approach, where inbox business enquiries are directed to a form on gov.uk that provides direction and links to relevant guidance. This approach will ensure that the service and outreach goals of GG's business advisory offering is retained, while minimising cost and maximising value for money by reducing the need for a dedicated inbox response team. Future improvements are planned to further optimise user navigation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Not applicable.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In response to last year’s annual review GG has developed a plan for building a central register of UK firm engagements across the business advisory and intervention portfolios. This will enable better attribution and monitoring of UK business benefits across deal pipelines and policy advisory work.

Recommendations for the year ahead:
Retain a two-pronged approach to business support:
-digital-first offer to reach a wide number of early-stage businesses
-tailored support to accelerate deals through accelerators and other formats
1. Extend central team management into a ‘deal hub’ for the final phase of GG
2. Typically, the programme has used structured handovers from intervention teams to BA to provide tailored investor outreach for firms. As BA is now closed, and the programme is focusing on pipeline development and closure, a new model should be defined before the end of 2025.
3. Expansion of the deal accelerator model in Africa through follow-on phases to GSDA, WAfTech, SA SMME and Ghana services, plus ongoing activity in Asia (Philippines, Cambodia, Indonesia, Vietnam) means the central team should consider creating a ‘deal hub’ to drive maximum impact towards deal closure.
4. Work should be done to understand the specific challenges facing women and interventions should be tailored to meet these challenges. A short summary report should be published on the findings before the end of the year. The team should consider a short report and/or learning session on GG’s experience of using the ‘2X’ gender inclusion criteria in the programme.
5. Draft a plan for hosting and maintaining digital products beyond the programme close, and detailed learning reports on priority themes

Output Title	Commercial opportunities and partners identified, for trade and investment between the UK and low and middle-income countries with positive climate & development impact and significant secondary UK commercial potential
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress	Y4 actual (Y4 only)
3.1 Number of commercial opportunity spaces in priority markets and sectors identified and shared	338	382 (+13%)	104
3.2 Number of commercial partners in priority markets and sectors identified and shared	4,400	5734 (+30%)	2,108
3.3 Number of proposals for sectoral and systemic changes that would drive large-scale trade and investment identified and shared	9	21 (+133%)	15
3.4 Average Intervention Development Impact Score (out of 12)	8	8.1 (+1%)	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

Commercial Opportunity Spaces:
There has been strong performance on identifying and sharing commercial opportunity spaces owing to several new interventions, partly funded through additional, unexpected funding (Clean Energy Supply Chain, Ghana services, WAfTech, Kyrgyzstan, ASPIRE). These began delivering fast, strong impact, accounting for surpassing the target.

GG’s newer interventions are designed with a more granular pipeline lens, yielding richer commercial scoping. In late-stage interventions, analysis focused on deep-dives in specific subsectors or geographic areas.
Systemic change proposals:
Multiple interventions this year contributed to partner efforts that will drive large-scale trade and investment through system-level change. This included work in ASEAN to develop regionally harmonised trade finance registries in four countries, as well as support to the Global Clean Power Alliance (GCPA) initiative through the identification of four major proposals for multilateral action to improve participation of LICs and MICs in global clean energy supply chains.
DI score of interventions
The DI score has been high due to interventions such as WAfTech, GSDA and Cambodia SEZ performing particularly well, with high scores supported by the depth of their inclusion frameworks, policy linkages, and institutional ownership.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A new output indicator 3.4 has been introduced assessing the mainstreaming of six DI criteria into the design and delivery of interventions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress has been made on a new output-level DI score (Indicator 3.4), enabling the programme to monitor DI integration across the full intervention portfolio. This is aligned with the scoring framework already in place for firm-level support and allows GG to better assess the extent to which its interventions embed inclusive, green, and productive impact criteria. The new indicator is helping inform intervention selection and design in the 2025 portfolio and has surfaced valuable insights into delivery models that are more effective at driving DI outcomes. It has already been used in FY24/25 where an intervention DI dashboard was first created, and interventions were scored in MEL reports.

A milestone management tracker has also been introduced that ensures timely sign-off, improves delivery transparency, and accelerates issue resolution. Suppliers are now fully embedded in the intervention design process, focusing on their areas of specialisation, to ensure the greatest value is obtained from each consortium partner.

Recommendations for the year ahead:
1. Focus on later stage interventions, going deeper within existing opportunity areas
2. Explore options to bring workstreams 3.1 (commercial opportunity development) and 3.3 (systemic change) together, including in deal accelerator work.

Output Title	Knowledge products and policy & business environment insights identified and shared to help unlock opportunities for T&I between the UK and low- & middle-income countries
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress	Y4 actual (Y4 only)
4.1 No. of market access barriers identified and shared with government or related advocacy groups in the UK and low- & middle-income countries who have the capacity to act on them	173	192 (+9%)	79
4.2 No. of knowledge base products, tools and resources produced and / or facilitated	188	231(+22%)	87

Briefly describe the output’s activities and provide supporting narrative for the score.

MAB identification:
Good progress has been made on identifying MABs with specific reforms through engagement and partnerships with governments. Examples include:
- Cambodia Green SEZ: GG supported the identification of 9 business environment barriers tied to the design and delivery of a climate-aligned SEZ. These spanned regulatory gaps in zoning and permitting, fiscal incentive inconsistencies, and coordination challenges across subnational agencies.
- ASEAN ASPIRE: Supported ASEAN’s blueprint for industrial transformation by identifying 5 key policy and regulatory barriers hindering SME participation in regional green supply chains. These included weak coordination mechanisms for standards adoption, unclear guidelines on sustainable sourcing, inconsistent regulatory incentives for localisation, and the lack of harmonised SME financing frameworks.
- Ghana Trade in Services: GG worked with the Ministry of Trade and Industry and local private sector to identify 7 regulatory and institutional barriers affecting trade in services, particularly within business process outsourcing and digital services. These included the absence of a coherent national services export strategy, restrictive licensing and data localisation requirements, limited international recognition of professional qualifications, and gaps in digital trade policy.

Production of high-quality, sustainable knowledge products:
Knowledge product development was considered in intervention planning and delivery, deliberately moving the programme away from generic diagnostics and responding more effectively to stakeholder needs (including partner governments, businesses, and investors).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following last year’s annual review, the definition of market access barriers in output indicator 4.1 has been updated to ensure that it is better aligned with DBT use of the term, for onward tracking, action and resolution. This update clarified that market access barriers are those caused by "specific government policies, regulations, processes or lack thereof…that impede overseas businesses from participating in trade or investment".

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Following last year’s review, GG updated its definition of MABs to better align with DBT’s DMAS system. The programme now distinguishes between regulatory market access barriers (those suitable for handover to DBT) and broader investment climate constraints. This ensures clearer terminology, smoother handovers to DBT, and better reporting on T&I-related constraints. GG also plans to introduce a taxonomy to facilitate clearer tracking and coordination.

Recommendations for the year ahead:
1. Focus MAB reform activity on conversion to "acceptance" and beyond, where reform has genuine transformational impact. Reporting via a quarterly MABs report on acceptance confirmation, valuation where applicable, ensuring DBT have visibility.
2. Interventions that built in review cycles with users, such as WAfTech and GSDA, produced highly actionable, well received products. GG should institutionalise light-touch feedback mechanisms to inform iteration and improve usefulness.

Output Title	UK Government actors (central, regional, in-country teams and GIP teams) are supported to promote two-way trade and investment with MICs and LICs and facilitate cooperation on topics of wider UK national interest
Output number:		5	Output Score:	A++
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress	Y4 actual (Y4 only)
5.1 No. of senior level engagements between UK Government actors and LIC and MIC governments facilitated by GG	39	65 (+67%)	40
5.2 Average Country Office Engagement Score (out of 12)	9	10 (+11%)	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

GG has played a significant role in enabling Posts to advance senior government-to-government engagement on priority topics:
GG facilitated over 50 interactions between UK Posts and senior officials in LIC and MIC governments. These engagements were structured touchpoints that advanced mutual economic priorities, technical coordination, and strategic relationships.

Strategic alignment with GIP and UK commercial objectives:
GG worked closely with Posts and GIP delivery partners, including DBT, BII, and UKEF, to shape intervention design and unlock follow-on support. For example -
- In South Africa, the programme’s green SME pipeline was structured in alignment with UK-linked green finance tools, providing a downstream deployment channel for BII and development finance institution resources.
- In ASEAN, GG’s technical advisory fed directly into DBT-led economic diplomacy efforts under AIPBI and regional trade platforms.
- In Cambodia, GG worked closely with Post to co-develop the SEZ MoU, a strategic platform which now underpins UK engagement on green infrastructure.
- In Mozambique, close collaboration with Post and central FCDO teams helped align the Just Energy Transition work with broader UK regional priorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A new indicator 5.2 regarding average country office engagement has been introduced for 2024-25. As Posts play a central role in articulating UK priorities in partner countries, this indicator ensures interventions are designed in strategic alignment with Posts'. The indicator is measured collaboratively with Posts who provide feedback on three key dimensions of engagement, specifically: Alignment with Posts objectives (TOR stage), Involvement of Posts in decision making (implementation) and Utility to Posts (wrap-up and post-intervention phase).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Senior-level engagement facilitated by GG across several key interventions (Cambodia, ASEAN, Philippines, SA) has led to strong performance against indicator 5.1.

Recommendations for the year ahead:
Explore how sufficient capacity and resourcing can be made available at Post for the duration of intervention promotes effective delivery.
D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The programme has a comprehensive VfM strategy reported on in quarter and annual programme reports. Over the last programme year, GG has been evaluated during its internal MEL process as reaching “strong” or “good” performance on 78 out of 95 VfM elements scored across 20 interventions. As a programme, GG delivers strong value for money across its portfolio.

Economy
Day rates have remained consistent throughout the programme and continue to be the primary cost driver for GG. Programme day rates were agreed at the outset of the programme and have been benchmarked as competitive against other programmes within the FCDO.

GG utilises a notable proportion of senior consultant expertise, which is judged to be good value for money in this case. Although more costly in absolute terms, GG is unique in that it is able to deliver substantial diplomatic value, with regular programme engagement with ministers, permanent secretaries, and senior officials across key partner governments. Senior BCG consultants are key to this, taking an outsized role in GG's activities. Success of these inputs is underscored particularly by outcome 3.1. The indicator matched its Y3 performance and exceeded its annual target again on supporting the UK’s economic and foreign policy interests, contributing to improved bilateral relationships in priority geographies.

Economy and financial management are scored quarterly as part of GG’s programme management Key Performance Indicators (KPIs). The programme consistently performs strong against this system.

See also recommendation 43 below on plans for further examining fee rates and seniority.
Efficiency

GG continues to innovate on intervention designs to drive efficiencies. Learnings from Y3 confirmed the importance of a portfolio approach to ensure strong aggregate performance across the breadth of logframe indicators. Looking ahead to Y5, lessons continue to shape both intervention design and prioritisation, including:

MEL reviews from Y4 being used to update VfM benchmarks across intervention types to guide selection and design.

- Embedding VfM more systematically in the prioritisation of “longer and thinner” interventions, which have shown higher return relative to cost by enabling systemic change, deeper policy uptake, or more advanced deal flow.
- Factoring in cumulative VfM across multi-phase workstreams (e.g. Mozambique JETP, Cambodia SEZ, Philippines NAP), to better understand and optimise how impact builds over time and can be applied to future years.

Effectiveness

To date, for every £1m spent on the programme, it has supported 11+ high-potential businesses, facilitated £7.31m in trade and investment deals (with an additional ~£31.4m in commercial discussions), progressed £21m in large/ and complex projects to advanced commercial stages and enabled ~500 jobs. That same investment has also identified ~5 MABs, of which at least 1 has been accepted for reform, created 5 knowledge products, and facilitated 605 substantive engagements. Targeting of growth-stage businesses and tailoring of support to each business contributed significantly to these strong returns.

A residual challenge relates to the lag between support and deal closure in outcome timing. This is to be expected somewhat, and the programme’s new indicator 1.3, tracking the value of large-scale projects that have secured commercial interest, will seek to incorporate upcoming deals in the logframe. This indicator represents opportunities with near-term momentum that could close within 1-2 years.

Tracking the conversion rate of these deals into actual investments will be useful information for informing expectations of graduation on the remaining deals with commercial interest in the GG pipeline. Tracking real jobs created would also be useful information to collect to appraise wider, long-term VfM.

The proposed evaluation of GG, and ongoing ex-post assessments of activity, offer further opportunities to understand the sustainability of interventions after they have finished.

Equity

Over the past year, GG has sought to embed WEE into the design and delivery of all interventions in FY24/25, with women's economic participation a core component of the new Development Impact indicator. WEE is now treated as a minimum requirement in programme design, with clear principles set out by intervention archetype—sectoral, deal acceleration, and enabling environment.

Within GG, WEE is considered from ToR development to MEL, with options to involve CSOs, map risks along value chains, and generate sex-disaggregated data. The frameworks refined this year are now replicable across future workstreams, ensuring WEE remains a strategic, measurable, and context-sensitive priority. GG has developed systems-level tools, frameworks and learnings on WEE and inclusion that have been shared with governments, investors, businesses and FCDO COEs.

Progress followed recommendations in the previous AR, and evidence across interventions of how deliberate intervention design and targeted implementation strategies can achieve more meaningful equity outcomes than just selecting sectors with downstream inclusive potential.

In FY 24/25, GG more than doubled its targeted ambition on Women’s Economic Empowerment (WEE), expanding its assessment from 65 to approximately 179 high-potential (HP) firms – a nearly threefold increase in scale. Despite this substantial growth, 63% of firms still met the strong WEE criteria, maintaining the programme’s high base of 60% on gender inclusion from FY 23/24.

This increase was largely driven by interventions with intentional WEE screening, notably:

- South Africa JETP SMME: targeting women-owned and - led businesses, often in green sectors.
- WAFTECH identified, supported, and showcased 11 investable, women-led or women-serving digital startups
- GSDA : applied WEE lenses as part of enterprise selection of 15 supported companies

64% of GG’s 179 high potential firms met at least one of the 2X WEE criteria, while:

- 22% offered products that specifically benefit women
- 21% had >30–50% female workforce and a commitment to gender equality
- 21% were women-founded
- 17% were majority women-owned

These interventions consistently prioritised businesses with inclusive hiring practices, gender-sensitive leadership, and sectoral influence, helping to maintain and slightly improve strong WEE performance despite the expanded high performing business base. This demonstrates that GG has moved from WEE integration in selected interventions to more systematic application of WEE metrics across the high performing business pipeline, reinforcing its commitment to gender-responsive economic development. The team will consider whether there is value in a more detailed case study of how WEE been integrated across the programme, possibly as part of the planned evaluation.

Cost-effectiveness

Breadth of impact is a defining feature of the programme. GG seeks impact across commercial, development, and economic diplomacy objectives, unlike many comparator programmes that deliver against a narrower mandate. Given the wide-ranging nature of GG's work, some of the more transformative outcomes are not readily captured in logframe metrics, for example:

The Cambodia SEZ catalysed a green investment platform now advancing over £270m in strategic infrastructure investment and has established institutional partnerships formalised through a G2G MoU

In the Philippines, GG helped develop a multisectoral, resilience-focused adaptation pipeline, expected to benefit millions of vulnerable people over the long term

Although there are spillover benefits with the breadth of GG's delivery, a wide mandate may sometimes incentivise overcommitting and create inefficiencies. Evidence from interventions have highlighted the importance of engagement from key stakeholders for effective outcomes (i.e., the engagement of posts and government partners). This has been a challenge in Pakistan where the main supplier faced difficulties in engaging senior stakeholders within the government.

The programme has adapted to this and narrowed its focus somewhat over the past year as aforementioned, to shift to fewer, deeper interventions designed for stronger outcome-level VfM, particularly through sustained delivery or targeted deal acceleration. This approach seeks higher return on outcomes relative to cost by enabling systemic change, deeper policy uptake, or more advanced deal flow.

Attribution still remains difficult to ascertain however - to fully understand the effectiveness of GG’s role in facilitating commercial deals. As highlighted last year, an independent evaluation is strongly recommended to fully assess the effectiveness of the programme.

Assessment of whether the programme continues to represent value for money

There is strong evidence that the programme continues to deliver good VfM, given performance against the logframe and some of the more transformative work that GG has supported over the past 12 months.

Looking ahead, the programme should also explore simple, compelling ways to showcase the programme’s successes and demonstrate the VfM the programme is generating in an easy-to-understand and accessible format. This will be enhanced by carrying out an independent evaluation to further strengthen the attribution of key outcomes as well as defining critical insight for the GIG. There is an ongoing stakeholder mapping exercise to identify new channels for sharing GG’s impact and VfM that will be valuable in this pursuit.

E: RISK

Overview of risk management

Overall risk rating remains at Moderate. This is within FCDO’s risk appetite.

Table 4 Risk Appetite by Category
Category	Level
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Public Service Delivery & Operations	Cautious
People	Cautious
Safeguarding	Cautious
Financial & Fiduciary	Cautious
Reputational	Cautious

Key risks this year have included budget uncertainty, staff movement within the HMG team (partly to resource the new Green Inclusive Growth COE) and delivery teams and geopolitical crises in countries of operation.

The programme has effectively adapted to uncertainties in the budget and responded rapidly to absorb additional budget. Budget uncertainty is an ongoing risk which has the potential to impact the programme’s ability to confidently implement long term, multi-year projects which can build consistency, effectively utilise learning and strengthen relationships leading to greater impact. The programme has mitigated this by implementing a responsive and flexible delivery model as well as extensively modelling budget scenarios. Central staff turnover has been managed well through leadership, strong knowledge sharing and robust onboarding processes as well as a high degree of flexibility and resilience from team members. However, it should be noted that the new Programme SRO is one grade lower than the predecessor, whose slot was transferred to the new Green Inclusive Growth Centre of Expertise programme to aid development and transfer of learning. This has placed additional pressure on the delivery team. Moreover, difficulties have arisen from staff turnover within intervention teams at Post leading to a loss of momentum in some cases. These challenges have been managed through revisions to ways of working including adapting meeting cadence and working closing with suppliers to reduce the time burden of reviewing deliverables.

Emerging geopolitical crises have interrupted workstreams through the redeployment of staff at Post and cancelling or postponing field visits. This risk has been managed by close observation and communication with Post as events unfold as well as the implementation of mitigation strategies by delivery partners such as shifting to desk based reviews were possible.

The above risks are moderate and well within the tolerance level of the programme. Additionally, there is a robust risk management process internally and externally with the delivery partners to manage these risks in the coming year and indicated below:

- Formal quarterly reviews of programme level risk registers between BCG and HMG to manage both imminent and recurring risk.
- Ad hoc notifications to of significant risks in real-time, as well as weekly opportunities to address high priority risk issues in weekly PMO meetings.
- Specific risk registers for significant interventions to ensure that the unique nature and scale of these risks are appropriately considered and managing these risks is appropriately resourced.
- Regular reviews of intervention level risk registers to ensure that they are up to date.
- BCG has specific safeguarding, anti-fraud/anti-bribery and corruption policies which are applied on all projects. All consortium partners and contractors undergo screening, covering both BCG due diligence and to ensure they meet FCDO Code of Conduct requirements.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Overall central management of the programme has been effective but there were some friction points around the Post buy-in process. In response, detailed guidance has been written to outline the buy-in process including highlighting the resource requirements. New sign off processes have also been implemented to ensure that Post has sufficient resourcing and access to finance systems before buy-in is approved. Feedback has been provided to the FCDO’s Centre for Delivery to highlight some of the wider structural issues within the buy-in process.
In response to recommendations in the previous annual review, the programme is now tagged as ‘significant’ against the Gender marker and ‘not targeted’ against the disability marker.

Boston Consulting Group

GG’s contract with the Boston Consulting Group led consortium started in August 2021, this reporting period covers the fourth full year of implementation.
GG is designed to continuously improve the way the programme is delivered, the results that are achieved, and the systems and processes to support this. The following programme management measures were undertaken this year to apply this approach:
- KPI scoring: The current KPI scoring regime was recognised as having some flaws, specifically around the definitions linked to the marking system, which in theory could result in satisfactory and good performance being penalised through fee retention. The scoring regime was reviewed, and a new KPI scoring system has been introduced in the contract amendment, whereby scores exceeding 400 (“Supplier delivering efficiently and effectively. Very few or no improvements needed”) do not have any retention applied to them.
- Cabinet Office indicators: The previous Cabinet Office performance indicators were outdated. Three alternative logframe output indicators were proposed as replacements. The Social Value Cabinet Office indicator was also regarded as unsuitable, as it focuses on UK social impact; an alternative indicator was developed and is under review by HMG.
- Milestone tracking: A new milestone tracker has been introduced helping ensure accurate budgeting.
- International Climate Finance (ICF) Reporting: GG reports its ICF contribution both in terms of contribution to ICF indicators, as well as ICF spend. In terms of the contribution to ICF indicators, the programme reports against the following 3 indicators:
  - ICF Technical Assistance KPI 1: Number of countries supported by International Climate Finance technical assistance
  - ICF Technical Assistance KPI 2: Number of individuals and organisations informed by International Climate Finance technical assistance
  - ICF Technical Assistance KPI 3: Number of climate policies informed by International Climate Finance technical assistance

53% of spend qualified as ICF across the supplier led interventions. To identify ICF spend on GG the programme uses an ICF Attribution Tool, based on a version used successfully on other FCDO programmes.
Overall delivery of the programme is on track and the supplier continues to adapt and remain agile despite budget uncertainties. Quarterly narrative and financial reports were submitted on time (with justification where delayed) and the quality has been good. The supplier has also met all contractually agreed financial commitments and provides timely input for all FCDO programme compliance requests such as KPI input, risk scores; asset registers and asset disposal documentation. The Programme has consistently scored strongly on a series of 15 management KPIs assessed quarterly. KPI scores are moderated by HMG to ensure accurate reflection of performance, and there have been no issues regarding poor performance.

Some progress has been made against the recommendation from last year’s annual review to achieve greater financial clarity and assurance on VfM, including through agreement to make clear the intervention team during the terms of reference formation.

43.This review recommends increasing the transparency of interventions costs including providing named intervention team members with clearly outlined levels of seniority, hours and associated hourly rates, as with comparator programmes.
Comms and digital

A high-level review of GG’s communications strategy was initiated to capture lessons from the year and to enhance the targeting, quality and efficiency of engagement efforts. As a result, significant progress has been made on scaling up and expanding the programme’s communications and knowledge sharing efforts including the publishing of case studies and a redesign of the programme’s campaign page.

However, several comms deliverables required multiple rounds of revision before final approval, leading to a lower score on management KPI 2.2 (Reports and annual work plans are concise, well-written in Plain English, and need no more than 1 round of FCDO comments to finalise). To address this, the supplier will prioritise improving the quality and clarity of first drafts and programme teams will continue to monitor and provide feedback.

Interventions

GG’s intervention model remained focused on delivering transformational change - whether through policy, investment pipeline design or direct support to projects and businesses.

There was significant buy-in from key stakeholders in partner governments across the portfolio of interventions including in Kyrgyzstan and the Philippines. However, securing stakeholder engagement in Pakistan was more challenging, leading to unsatisfactory delivery and subsequent retention of milestone payments. The issue also highlighted the importance of milestone definitions for timely resolution.
44.This review recommends ensuring that ToRs include both robust stakeholder management plans and clearly defined, quantifiable milestones. Where possible, the review also recommends utilising in country staff on supplier intervention teams or subcontracting in country experts where this is not possible.

Concerns were also raised regarding the management of contractors within the Lead Supplier’s Consortium where perceived lack of oversight and insufficient financial management led to Post missing a deadline for budget transfer meaning payment of the Consortium Partner invoice was covered through GG’s central budget.
45. This review recommends the Lead Supplier ensure that communication between Post and its suppliers follows clear process to avoid any potential confusion and risk to relationships.

Going forward, central teams and Post should ensure that all milestones in the ToR are well defined and trackable. Interventions would also benefit from always having Lead Supplier staff based in country or where that is not possible, regionally, in order to rapidly respond to needs and draw on local expertise when engaging key stakeholders. This advice should be formalised in the Post Buy-In guidance.

British Geological Survey
A Memorandum of Understanding (MoU) was signed with the British Geological survey in 2023.
Overall delivery of the projects are on track and the partner continues to adapt and remain agile despite budget uncertainties. Quarterly narrative and financial reports were submitted on time and the quality has been good.
Key highlights from the deliverables include:
- Following bespoke training by BGS staff in Zambia, there is significant evidence of improvement within the partner laboratories including cleaning and tidying of laboratory spaces. Laboratory activities are now carried out using health & safety equipment, showing a positive change in work culture and practices.
- In Tanzania, the work of BGS was picked up and cited in national newspapers with the former Mining Permanent Secretary (Kheri Mahimbali), noting the collaboration with the BGS will enable the Ministry of Minerals to deliver their ‘Vision 2030’ through improving local capacity in critical minerals.
- A successful visit to the Philippines took place, with a total of 8 BGS staff involved over 2 weeks. The visit encompassed attendance at two conferences in Baguio (a UK-Philippine conference on Sustainable Mining, and the Philippine Mine Safety and Environment conference) as well as meetings with a wide number of government, industry and public sector stakeholders facilitated by British Embassy colleagues.

A report on “Critical Minerals and the role of the Geological Survey in Zimbabwe” has been written and a full draft was shared with the British Embassy in Harare at the start of April 2025.

BGS were invited to launch a 4th Pillar of the UK-India Net Zero Innovation Centre, supported by the British High Commission. The initiative will focus on collaborative research and innovation on CCUS between the BGS and the Indian Institute of Technology Bombay.

Attendance at Mining Indaba in South Africa and meetings with a variety of stakeholders relevant to wider BGS work on critical minerals in Africa. This included engagement with BCG and FCDO colleagues around potential future delivery of GG projects.

In response to risk due to conflict and infectious disease outbreaks two of the projects due to be delivered in the Democratic Republic of Congo and Rwanda were desk based which led to an underspend against the budget
World Bank RISE
The World Bank’s EGPS 3 results framework (which covers RISE outputs) is nested under the GG logframe to facilitate ease of results reporting. RISE results are not currently contributing to the overall investment and other outcome level targets (this will be reviewed for feasibility - as part of recommendation 46 below.

Table 5 GG Outcome Indicators and RISE output
RISE outcome indicators against GG	RISE output and activity reported to date
1.1 Total value of trade and investment deals that GG contributed to: / Volume of investments made by RISE-partners’ based companies. / Number of RISE-Participant countries receiving investments in sustainable energy products’ supply chains. / Amount (US$ million) of trade, private and development finance leveraged by RISE activities. / Amount (US$ million) of investments in human capital formation facilitated by RISE (US$ million).	RISE contributes to trade and investment through reform roadmaps, investment facilitation and investment de-risking. Confirmed investment facilitated by RISE as of August 2025: / Argentina: Mining and Transport teams-initiated preparation of an infrastructure and critical minerals project in lithium-rich provinces Jujuy and Salta (US$120m incl. $30m for mining). / Peru, World Bank (WB) Mining (IEEXI) started preparations of a US$220m project to strengthen the mining sector, including geological data management - a prerequisite for developments mid- and downstream. / Malawi: WB Mining team working closely with WB energy team, IFC and Multilateral Investment Guarantee Agency on the energy mining nexus and in form of WBG supported Mpatamanga Hydropower Storage Project (US$1.54bn). / Burundi: RISE supported advisory work for strengthening mining sector regulatory and legal framework as well as studying potential for the Musongati Nickel project to unlock Burundi’s participation in the Nickel belt (DRC-Burundi-Tanzania) value chain development. / DRC: Strong focus on mining within the transformative WBG supported Inga 3 Development Program (US$250m). RISE supported study on Copper Belt (Zambia-Southeast DRC) trade and value-chain additions for Southern Africa in early stage.
1.3 No. of market access barriers identified, with clear reform plan accepted: Number of individual RISE-participants benefitting from country specific or regionally focused market intelligence and analytics on developing sustainable and resilient supply chains of clean energy products financed by RISE. Percentage reduction of supply controlled by the three top producing countries in selected energy products’ supply chains attributable to RISE activities. / Number of RISE-Participants designing and implementing inclusive economic diversification strategies and legal and regulatory reforms underpinning competitive and sustainable downstream value addition projects. Number of RISE-Participant countries adopting measures to improve the business environment and governance as a result of RISE activities. Number of RISE-Participant countries adopting higher ESG standards as a result of RISE activities. / Number of feasibility studies on strategic and integrated investments in cross-boundary “multiuser” decarbonized ancillary energy and transport infrastructure.	The Zambia roadmap identified the following market barriers (Burundi and Malawi roadmaps are forthcoming): / High Non-Tariff Measures (NTMs): Technical trade barriers, price controls, and complex import procedures increase border protection rates, making the import regime costly and challenging. / Regulatory Bottlenecks and Overlaps: Overlapping regulations, discretionary powers for new rules, and multiple border agencies without streamlined procedures create administrative inefficiencies and unpredictability for investors. / Electricity Supply Instability: Despite competitive electricity prices, frequent power outages and reliance on expensive imported energy increase operational costs, deterring manufacturing investment. / Access to Finance for MSMEs: High interest rates (~25%), lack of collateral, limited financial products, and low financial literacy hinder micro, small, and medium enterprises' (MSMEs) participation in ETM supply chains. / Policy and Regulatory Instability: Fluctuating contract terms, unpredictable tax regimes, and unclear investment mandates undermine investor confidence and discourage long-term investments. / Weak Trade Facilitation and Logistics Infrastructure: Poor road quality, inefficient border crossings, and slow domestic transport increase time and costs for manufacturers and exporters. / Skills and Labor Productivity Gaps: Zambian firms face lower labor productivity compared to regional competitors, and there is a high reliance on expensive expatriate technical and managerial skills. / Weak Procurement Governance in Mining Supply Chains: Local suppliers face high costs of capital, payment delays, and governance issues, including demands for kickbacks, which discourage their participation in ETM value chains. / Limited Adherence to ESG Standards: Local businesses’ limited compliance with environmental, social, and governance (ESG) standards restricts their access to global supply chains that demand transparent, sustainable sourcing. / High Tariffs on ETM-Related Products: Zambia’s tariffs on ETM goods, such as copper wire and fittings, are higher than the Sub-Saharan Africa average, which impairs export competitiveness and integration into global value chains.
2.1 No. of jobs expected to be created or supported within 3 years: / Number of skilled labour employed by investment leveraged by RISE activities, disaggregated by gender. / Value-added (US$ million) and number of jobs (disaggregated by gender) created by RISE initiatives in low- and middle-income countries.	Investment carried out based on the Zambia roadmap will lead to an expansion of infrastructure and as a result and increase in skilled workforce and higher employment—up to 500,000 jobs in mining alone. / Job creation outcomes will also be detailed within further RISE roadmaps including Malawi, Burundi, Peru and Argentina and more. Furthermore, the RISE grants during the second year will focus on the design and implementation of job-related grants.
2.2 ​Average development impact score of 'high potential' trade and investment opportunities supported by GG: Number of technical assistance and capacity building programs and government officials trained by RISE activities. Number of workers trained (1,000) disaggregated by gender. / Quantifiable reduction in gender inequality in projects funded by RISE / Estimated volume of global GHG emissions reduced as a consequence of RISE activities. / Quantifiable reduction in gender inequality in projects funded by RISE	RISE activities are supporting the technical assistance and capacity building of government officials in addition to improving gender equality and reduction of GHG. In the upcoming annual reporting process, the RISE team aims to update on outputs related to technical assistance, capacity building, gender equality, and climate-related work aligned to the RISE Results Framework.

46.This review recommends a revision of how RISE results are tracked and recorded.

Donor Committee for Enterprise Development DCED, hosted by IFC

GG pays for the UK’s membership to the DCED. The UK has been a founder-member of the DCED since 2004 and FCDO officials are members of 5 main Working Groups: Business Environment, Results Measurement, Green Growth, WEE, Private Sector Engagement and Market System Development. Engagement with DCED has proven useful in influencing the UK’s own and other donors’ policies; in programme design and donor coherence. For example, in October 2024, DCED convened a global seminar on Growth, Employment and Resilience, where the FCDO played an active part in raising the profile and approaches to these topics that are now shared with multiple governments and stakeholders. Additionally, DCED updated its standard for measuring job creation and recognising job-displacement – a statistical approach which is used in FCDO’s results measurement.

DCED provides annual financial and progress reports outlining progress and updates across the DCED working groups. Their work is proceeding according to agreed timelines and quality.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring Evidence and Learning
Monitoring, Evaluation and Learning is substantially integrated into the programme’s approach, with a dedicated MEL function led by a specialised consortium partner, Tetra Tech. This MEL function assesses the potential and achieved impact of the Core Team workstreams and each intervention on an ongoing basis, feeding back performance information and related learnings to ensure there is continual improvement in programme delivery.

Importantly, GG targets were formally rebased this year to reflect both the ambition and strong performance of the programme to date. Rebasing targets mid-cycle is unusual and reflects the programme’s innovative approach. Incremental targets were adjusted from actual baseline performance from Y3, rather than from the target for Y3, giving additional stretch in line with trending performance.

Good progress has been made in MEL against last year’s annual review recommendations:
- Expanded reporting on progress towards outcomes, sustainability, and longer-term tracking. Following Annual Review recommendations, the intervention MEL Reports now capture more extensively the sustainability of key results and effects. This includes looking at how different stakeholders (Posts, businesses/investors, national governments) are set up to take forward recommendations, knowledge products, or connections developed by GG. Interventions completed in FY23/24 that have not had a follow-on activities in FY24/25 are also tracked through a dedicated ex-post assessment involving interviews with selected Posts and businesses.
- Updated MEL report templates include expanded narrative sections to capture learnings across a number of important topics. A small number of case studies have been completed, with more in development, to complement quantitative scoring, with the aim of deepening insights on what drives progress across interventions.

- Reporting on the impact of non-ODA funding and disaggregation of UK’s secondary benefits. Also following Annual Review recommendations, reporting has started on the contribution of non-ODA funding to UK commercial and diplomatic objectives. Firstly, UK focused results from the Logframe were identified and disaggregated from benefits to countries. The results of both fully non-ODA funded interventions as well as blended ODA / non-ODA funded interventions were then presented. This quantitative overview was complemented with more qualitative narratives and stories that highlight the value of the non-ODA funding for the UK, particularly when delivered in tandem with an ODA funded programme. Work to increase the proportion of non-ODA results captured in the logframe is ongoing, and is further recommended above.
- GG is increasing its engagement with Department for Business and Trade to improve on our ODA/non-ODA work. Two examples of related MEL work include:

    - Reviewing how our interventions bring in DBT expertise to facilitate UK business engagement including in how we pursued our activities in Cambodia, Philippines - bringing in UK businesses to facilitate market engagement on strategic, large-scale projects and positioning UK expertise in these projects.
    - Drafting a report on our learnings from non-ODA and ODA blending and assessing how non-ODA has enabled the programme to further benefit to UK businesses and investors.
- Reporting on UK Growth. In alignment with the new UK Government’s growth imperative, a simple framework was developed to identify and report key contributions to the UK growth agenda for each intervention. GG’s reporting framework below shows the programme’s contribution to the UK growth agenda by securing T&I deals, building UK-focused longer-term pipelines, addressing market barriers, and strengthening government-to-government partnerships. This framework may have value in other related programmes and initiatives.
- Light-touch check on interventions’ progress and lessons for adaptation. A flexible approach to assess progress against Logframe indicators at the midpoint of interventions was introduced. The process was rolled out for all the interventions of over six months to enable a collaborative review, feedback, and development of lessons that could inform adaptations in the final stage of the intervention. This allows MEL to be more useful for implementation, by creating a quicker feedback loop from evidence into programming.
- Women’s Economic Empowerment is now embedded across all new interventions through Terms of Reference design and MEL tracking. Most, if not all interventions are anticipated to have a minimum score of '1' to show that WEE has been an intentional objective. Continued refinement of the WEE approach is underway, with discussions ongoing with on how to continue embedding WEE deliverables in the coming year.
- Dissemination has occurred through internal reviews and centre-led learning products - including 3 disseminations sessions - on mobilising climate action with partner governments, on GG's perspective in accelerating investment to services sub-sectors in Africa, and on driving women's economic empowerment in Africa's dynamic tech sector.

There are further adjustments that would improve the MEL approach. This review recommends:
1. Defining learning priorities for the last year of the programme with a view of creating targeted thematic and operational learning products.
2. Providing outcome level contributions at the ToR stage for new interventions (where appropriate), to improve outcome results targeting
3. Employing outcome harvesting techniques to trace the impact of multi-phase interventions and identify key assumptions, conditions, and factors of success to inform the GIG Theory of Change.
4. Outlining how the programme will support Post to track the impact of interventions long-term including monitoring deals after the closure of the programme. (See also VFM section for discussion of ex-post studies of intervention impact)
5. Improving handover to the GIG and Trade CoE by defining any potential monitoring gaps and providing learning logs for all interventions going forward.
6. Stronger understanding of pricing variations across interventions in order to better determine if VfM is being achieved and where improvement could be made. Work is being carried out in year 5 to align intervention outputs with the pricing menu which was provided in response to recommendations from a previous annual review.
7. Determining the best way to capture downstream impacts, such as tracking the quality of jobs and number of indirect jobs whilst avoiding endogeneity and double counting
8. Consideration of how cultural and social attitudes prevent women from engaging with markets and determine if there’s scope within the programme’s work to shift these attitudes.

Evaluation
Last year’s annual review highlighted that an independent review should be carried out to assess the deep impact and value for money of the programme. In response, GG engaged with the FCDO evaluation unit’s Evaluation, Quality Assurance, & Learning Service 2 (EQUALS) programme to refine the scope and focus of the evaluation. Drawing on this insight, an independent external evaluation was initially planned for FY24/25. However, uncertainty around budget meant the evaluation was postponed. In addition, an application was submitted to review the programme internally through the FCDO’s Strategic Impact Evaluation and Learning (SIEL) programme. This application was not successful as SIEL primarily employs experimental or quasi experimental evaluation techniques which do not align with the programme’s delivery model.

The planned independent evaluation is expected to commence in year 5 in collaboration with Manufacturing Africa.