## Annual Review 2020/21

Title: AT2030 – Life Changing Assistive Technology for All
Programme Value £ (full life): £19.8m		Review date: 05/12/2021
Programme Code: 300815-101	AMP start date: 28/01/2019	AMP end date: 01/10/2024

Summary of Programme Performance
Year	1	2
Overall Output Score	A+	A+
Risk Rating	Moderate	Cautious

DevTracker Link to Business Case:
DevTracker Link to results framework:

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The WHO estimates[1] that one billion people are in need of assistive technology (AT), e.g. wheelchairs, hearing-aids, prosthetics and orthotics, eyeglasses and digital products. However, 90% do not have access and 80% of those without access live in low- and middle-income countries (LMICS). AT2030, is delivered by a consortium led by the UK based Global Disability Innovation (GDI) Hub, is a global programme testing ‘what works’ to improve access to AT. The programme invests in and supports solutions to scale with a focus on innovative products, new AT service delivery models and global capacity support. The programme will reach 9 million people directly and 20 million people indirectly[2] to enable a lifetime of potential through life-changing AT. AT2030 is an innovative disability inclusion programme, pivoting to build on successes to focus on reaching the maximum number of people with AT and its associated services. Programme flexibility is essential - making a series of investments in new approaches, contexts and/or technologies to ‘fail fast and scale successes’ for a higher rate of return, reaching more people with AT.
[1] https://at2030.org/static/at2030_core/outputs/-Scoping-Report_2019-compressed-192.pdf
[2] This is an increase from 2020 Annual Review estimates - from 5 million to 9m people reached directly and from 9m to 20m people reached indirectly (earlier target numbers published in the 2020 AT2030 Annual Review)

AT2030 contributes towards the Foreign Commonwealth and Development Office’s strategic priority on science and technology, through supporting innovations to reach scale and develop an evidence base on ‘what works’. Supporting the Leave No-one Behind agenda, current and future FCDO and external programmes can draw on evidence and lessons learned to more effectively support people with disabilities - one of the poorest and most marginalised populations. The programme contributes to sharing UK expertise and UK leadership in innovation and AT through supporting UK based academic institutions (such as University College London (UCL) and Loughborough University); and to diplomacy and development through growing international partnerships and advocacy based on a deepening evidence base to support policy development.

- The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021.
- Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID.
- Throughout the business planning process, the FCDO has strived to ensure that every penny of the ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money.
- The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.
- The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This reporting period covers the period from April 2020 to March 2021 to fit with the programme’s reporting period. The AMP deadline is still December however it is intended that next year the review will be completed in a more timely manner[3]. In a challenging period requiring budget reprofiling and associated programme adjustments, all AT2030 impact, outcome and output indicators have reached their targets and 18 out of 23 have exceeded targets. Overall, in this Annual Review AT2030 scored an A+, exceeding expectations. Already the programme has reached 5m people directly and 16m people indirectly[4]. Six ‘life stories’ (see Hakim’s story in Box 1 below) were developed during the period and provide a qualitative interpretation of the programme’s impact.
[3] This year the deadline could not be brought forward due to a combination of staff absence due to Covid-19, annual leave and competing priorities.
[4] AT2030 has already reached over 5m people directly and 16m people indirectly, substantially exceeding Logframe targets of 2.4m and 3m respectively to end March 2021

Box 1: Hakim’s Life Story: Innovative AT Provision in Refugee Settlements (Humanity & Inclusion (HI))
Hakim is a 30-year-old male refugee from South Sudan staying in one of the six villages that make up Omugo Refugee settlement. Following a stroke and lack of quality medical and rehabilitative care he has severe impairments that made walking and self-care extremely difficult. Prior to his engagement with HI through AT2030 Hakim told his psychosocial worker,
“I do not think this life is worth living. I am better off dead….With these impairments, I cannot take care of myself, I cannot bathe, I cannot participate in meetings, I cannot move around easily to visit friends. I am always at home. People in the communities call me all sorts of names”
His main caregiver is his 80 year old mother who struggles to lift and move him to bathe and dress. Through an early intervention with HI, Hakim received psychosocial and physiotherapy which improved his mobility and independence and he no longer had suicidal tendencies.

Through the innovative technology that HI started under the AT230 programme - a 3D Printing through Emergency Tele Rehabilitation Access (3D PETRA) project, aimed at the provision of orthoses to improve the way people walk, it became possible to correct impairments of the feet and hands - such as Hakim’s. People with weakness in their lower limbs could have orthosis printed at HI offices in Arua to enable them to walk better. With only a structured sensor connected to an iPad, Hakim was scanned and a copy of his leg and foot were taken. The scan was modified on a computer bya prosthetics and orthotics (P&O) consultant, then printed by a 3D Technician. During Covid, ‘TELE REHAB’. while observing the set Standard Operating Procedure, 3D PETRA activities like fitting orthoses and modifications continued remotely with the P&O consultant interfacing with field teams via online platforms like Teams and Zoom. Hakim was provided with a Dynamic Ankle Foot Orthosis. The physiotherapist gave him gait training sessions and continued strengthening exercises to enable him to walk better with the orthosis.

Hakim is now able to walk around the village to meet friends. When sick, he can walk by himself to the hospital and he is now able to fully participate in community meetings.
“My life has greatly changed ever since HI started working with me… I never knew I could walk independently for
more than a kilometre. The orthosis you provided me has greatly improved my walking.”

     P&O 3D Printer	Final Adjustments to Hakim;s prosthetic	Hakim’s initial fitting
.
Pictures: Humanity & Inclusion
At outcome level, the programme is ahead of plans. By the end of the review period, AT2030 had supported six AT product innovations, 20 ventures, seven service delivery models towards reaching scale [5], and supported 22 countries or organisations to implement AT2030 funded ideas (findings, research or new methodologies). AT2030 substantially exceeded expectations against 11 out of 16 output indicator targets. Examples include the number of published influencing papers to address critical research questions; strategic tools developed to increase AT capacity[6]; number of partnerships formed to support AT capacity, match funding; and Country Capacity Assessment recommendations being delivered or completed through a series of pilot studies. Examples include the number of published influencing papers to address critical research questions; strategic tools developed to increase AT capacity[7]; number of partnerships formed to support AT capacity, match funding; and Country Capacity Assessment recommendations being delivered or completed through a series of pilot studies. See example in Box 2 opposite.
[5] Logical Framework Definitions around ‘Scale’ - The AT2030 Logical Framework (logframe) includes three indicators which target ‘scaling-up / on track to scale’ or ‘supported for sustainability’, with respect to: (i) AT innovations, (ii) AT ventures and (iii) service delivery models. These are defined as: SCALING-UP / ON TRACK TO SCALE: an innovation / venture that, as a result of AT2030, has experienced a projected increase in funding, user base, or proved the validity of their product/venture. SUPPORTED FOR SUSTAINABILITY: AT ventures that, as a result of AT2030, have substantively progressed with: development of their products, gathered evidence about the validity of their solutions, made links with relevant national and international partners, improved their relationship with customers or users, or implemented successful business plans. These progressions to Scale are measured and tracked by: • Reporting from ventures against definitions of scale and sustainability above (notably within Innovate Now); •	Insights monitoring by third-party research/evaluation to determine the value-add of programme support (notably within the AT Impact Fund); •	Partner reporting, with respect to service delivery models where change and uptake at the national /organisational level can be identified.
[6] The term ‘capacity’ in AT2030 relates to the development of professional skills, practical tools, organisational change or arrangements, and/or decision-making frameworks that increase the ability of the recipient or user to create greater access to AT
Box 2: Increasing the Government’s Capacity in AT in Kenya
The ‘Disability Medical Assessment Guidelines’, developed with the government by AT2030 partners CHAI in Kenya [Strategic Tool], enable policy makers and practitioners in the Ministry of Health and the Ministry of Labour and Social Protection to streamline [Capacity] rehabilitative services and increase access to AT [Impact]
[7] The term ‘capacity’ in AT2030 relates to the development of professional skills, practical tools, organisational change or arrangements, and/or decision-making frameworks that increase the ability of the recipient or user to create greater access to AT

Major lessons and recommendations for the year ahead

AT2030 is an innovative research programme and continued learning and programme flexibility is an integral part of the programme. Key lessons and recommendations are outlined in Table 1 below.
Table 1: Key Lessons and Recommendations
Lessons and Recommendations
Cross-programme lessons and recommendations
Based on progress this year and constraints due to Covid-19 and budgets, review logframe indicators
(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Learn lessons from ATIF to refine and adapt future approaches and to contribute to our understanding of the AT ecosystem (by end March 2022). / Document and disseminate findings through report(s) (by end June 2022) and a series of webinars beginning in November 2021
(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced
GDI Hub should continue to strengthen and streamline the profiling and capture of programme content for ongoing co-ordination and communications planning, leveraging match support from partner organisations where possible / (ongoing, to end programme)
FCDO SRO should focus on outreach within FCDO - connecting and collating emerging lessons (through papers, webinars, social media and podcasts etc) with relevant country based and policy teams / (ongoing, to end programme).
(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
GDI Hub should continue to build partnerships for strong programme results / (ongoing, to end programme)
(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
SRO and GDI Hub (and partners) should use Paralympic Games as a ‘communications moment’ for the programme, promoting AT2030 internally across FCDO and externally. / (August/September 2021)
There are a number of additional strong ‘communications moments’ in FYs 21/22 and 22/23 for AT2030. SRO and GDI Hub should map and make plans to promote AT2030 and AT generally (internally and externally) through ‘communications moments’. / (plans in place by end December 2021)
SRO and GDI Hub to reach out to FCDO Posts to share CCA outcomes and CIF progress with including details of partnerships in-country. / (by end FY 2021/22)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

The Theory of Change (ToC) for AT2030 is at Figure 1 below.

Figure 1: AT2030 Theory of Change

Current evidence suggests that the ToC still holds as early indications of delivery achievements (see Figure 2 below – under ‘outcomes’) are strong.

As a result, no changes to the ToC are proposed. Following the programme’s last Annual Review, the impact of recent budget adjustments and in response to good progress made in some areas, the indicators and logical framework (logframe) were revised. In the main, targets were increased to stretch the programme to continue to deliver ambitious results, despite the challenges of 2020/21. The Logframe and partner reporting system, track tracks impact and outcomes from outputs from all partners and sub-programmes on a quarterly basis. The significantly more stretching impact (reach) targets from five million to nine million people reached directly and from nine million to 20m people reached indirectly, have considerably increased the effectiveness of FCDO’s original investment, particularly under challenging circumstances. Following the in-year budget limitations introduced in April 2021, the programme was reviewed and partly reprogrammed to work within the new 2021/22 budget. This did not change programme targets however, and details will be outlined in next year’s Annual Review covering the period April 2021 to March 2022.

See Box 3. Wherever possible (in all areas except for outputs 4.5 and 4.6, the Paralympic television broadcasts) the programme is collecting and disaggregating data by age, sex, disability and geography to increase the learning from the programme and inform future (possibly targeted) interventions. In line with the ‘nothing about us, without us’ tenet, people with disabilities are not only targeted by interventions, but are also meaningfully included throughout the programme cycle, from design through to delivery and monitoring and evaluation.
Box3: AT2030 targets people with disabilities in low- and middle- income countries
“In low and middle-income countries, people with disabilities and their families are poorer than people without disabilities in nearly all socio-economic indicators. They are more likely to remain poor due to higher living costs, unpaid caring responsibilities, exclusion and entrenched stigma and discrimination….

…barriers create lasting disadvantages and a vicious cycle of poverty between schooling, employment and people’s life-chances.”

FCDO’s (was DFID’s) Strategy for Disability Inclusive Development 2018-23, December 2018

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact (reach):
Target: 5 million people (total)	Achieved: 21 million people (total)
Significantly exceeded target

The planned impact of the programme by 1st October 2023 is to reach 9 million people directly and 20 million people indirectly[8] with AT and it’s associated services, to enable a lifetime of potential through life-changing AT. AT2030 is creating and proving models of ‘what works’ to improve access to AT with a view to scale, focussing on innovative products, new service models and global capacity support (outcomes).
[8] In earlier Annual Reviews, the number of indirect beneficiaries (9m) was originally calculated on those targeted by television broadcasts of the Paralympic Games only.

AT2030 has:
- Directly reached: over 5m people with AT and AT related services to end March 2020. This includes recipients of stigma-reducing/addressing comicbooks across Kenya, people included pilots of new Eye Health programmes in Liberia and South Africa, people included in disability-focused research and applied research such as the adapted version of the WHO rATA (Rapid Assistive Technology Appraisal) survey in four informal settlements in Banjarmasin, Indonesia and Freetown, Sierra Leone; Ministry staff who received capacity building or direct advisory support during in-country Country Capacity Assessments (CCA) and follow-up pilots, and learners at disability-focused conferences and seminars delivered on the lessons and findings from the programme.
- Indirectly: over 16 million people, including through the daily national-scale broadcast of stigma reducing/addressing radio shows and social media broadcasts that showcased characters living with disabilities in Kenya, aimed at young adults; ongoing social media engagement on issues and learning from AT2030’s sub-programmes; and the populations now covered by new policies for people with disabilities

Impact (or reach) was originally expected to total of five million (direct and indirect combined) by the end of the reporting period. However, the programme reached 21 million people (total) to March 2021, four times the anticipated target.

Outcomes

New Products: development and scaling up of innovative AT products
Ideas: research, new methodologies and ideas for AT uptake and influence
Ventures: sustainable development of AT ventures
Delivery Models: development and scaling up of innovative AT service delivery models.

Figure 2, ‘Outcome Progress’ details progress (actual) against Logframe indicators (planned/forecast) at end March 2021. The ‘Target’ in this diagram, is what AT2030 expects to achieve by the end of the programme. AT2030 is exceeding expectations against all ‘planned’ outcomes.
Figure 2: Outcome Progress

Outcome Indicator 1[9]:New Products
[9] An outcome can stretch across a number of activities and outputs i.e. including from ‘InnovateNow’, the ‘AT Impact Fund’, and ‘Spark Innovation’. ‘Scale’ is assessed using realistic ambitions for progress over the venture/product/innovation’s 1-2 years of programme support. For example, AT2030 traces the impact of ventures which have gone through InnovateNow’s 12-week programme to measure progress over time; ‘Spark Innovation‘ combines an assessment of broader organisational relationships (e.g. Motivation, Humanity & Inclusion) from a baseline onwards.
Number of innovative assistive technologies scaling up / on track to scale.
Target: 5	Achieved: 8
This outcome has exceeded expectations.

During this reporting period AT2030 supported five new innovative technologies to test, trial and modify their products which are now on track to scale[10].
[10] SCALING-UP / ON TRACK TO SCALE: an innovation / venture that, as a result of AT2030, experiences a projected increase in funding, user base, or proves the validity of their product/venture.

- Humanity & Inclusion (HI) combined telerehabilitation, CAD-CAM and 3D printing, to provide and increase access to orthotic devices for use in emergencies and remote settings in Uganda. HI established a partnership MOU with the local CoRSU Hospital (further reading: here and here);
- hearX - tested an end-to-end hearing-aid solution for low-income customers in Africa. Focus countries: Kenya and South Africa (further reading here)
- WaziVision – reviewed the business model and manufacturing techniques for high quality, stylish, and durable eyewear from recycled materials in Uganda. Their glasses are 80% cheaper than alternatives on the market. Read more here
- Amparo Permanent Socket – a more durable, and compatible prosthetic better suited to the needs of amputees in developing countries. The “Amparo Permanent Socket” concluded testing, trials and modification to begin to scale. Read more here and here
- Majicast – Amparo and the University of Strathclyde developed a fitting tool that enables a mobile, relatively low cost, hands-free, repeatable, perfect socket fit, with minimal training.

Outcome Indicator 2: Ventures
Number of AT ventures supported for sustainability.
Target: 18	Achieved: 20
This outcome has exceeded expectations

The AT Impact Fund launched in April 2020 The AT Impact Fund launched in April 2020 to facilitate the growth of the AT ecosystem by combining grant capital with venture-building (bespoke and sustainability-focused) support to help AT innovators launch and scale solutions. To date, two ventures have been successfully contracted through the ATIF – hearX and WaziVision – with further investees in the pipeline for the next reporting year.

The ATIF is also developing lessons and insights into combining programme support to enable innovation with the private sector, development finance and venture building. The ATIF is establishing an operational model and is working to engage the private sector with AT investment opportunities in this nascent sector.

‘Innovate Now’, AT2030’s AT eco-system accelerator, supported 10 more ventures through a process from ‘viable early-stage innovation idea’, to building prototypes, undertaking clinical trials, responding to feedback, developing a business strategy before pitching their products and businesses to potential investors at ‘demo day’. Each venture joined a 12-week active learning program including mentoring, coaching and independent work in preparation for ‘demo day’. The entrepreneurs are continuing to make progress to sustain their businesses and develop their products for market. Ongoing progress is tracked through the programme.

The logframe target remains to be stretching but achievable at this time.

Outcome Indicator 3: Ideas
Number of entities (countries or organisations) implementing AT2030 funded ideas (findings, research, or new methodologies)
Target:1	Achieved: 29
This outcome significantly exceeded expectations.

Outcome achievements include:
- Partners in Mongolia, Associazione Italiana Amici di Raoul Follereau (AIFO), Tegsh Niigem and Universal Progress ILC, are implementing recommendations[11] from AT2030’s first ‘Inclusive Infrastructure case study’, focused on accessibility and inclusion in the built environment.
  [11] In Mongolia, the government is developing an accessibility law which will make accessibility standards required by law. While this was already in motion, AT2030’s research provided robust evidence to support the proposal. Furthermore, AT2030’s local partner is now part of the review committee for the law.
- Partners in India, including the Commissioner of Varanasi, are implementing recommendations[12] from the second Inclusive Infrastructure case study (to be published).
  [12] The Varanasi report was only recently published and the full and formalised recommendation update is pending. However, AT2030’s inclusive design advice has fed into tender documents for upcoming infrastructure projects in the city.
- Eight Government Ministries are continuing to implement recommendations from their Country Capacity Assessments (CCAs)[13]. Ministries also continue to build on four AT2030[14] pilot studies.
  [13] Excluding countries supported through AT2030’s Country Investment Fund
  [14] Ministries continuing to implement recommendations of the CCA (excluding CIF investments) and/or Ministries continuing to build on pilots supported through the project: Uganda - Ministry of Health – CCA, Ethiopia -Federal Ministry of Health – CCA, Indonesia - All Indonesia Public Health Services Association (ADINKES) - AT Technical Working Group, Indonesia -Ministry of Social Affairs – CCA, Malawi -Ministry of Health & Population – CCA, Kenya -Ministry of Health - Pilot – Wheelchairs, South Africa -National Department of Health - Pilot - School Health, South Africa -KwaZulu-Natal Provincial Department of Health - Pilot - Hub & Spoke, Liberia - School Eye Health Programme
- The National Paralympic Committee (NPC) certified 38 people as I’mPOSSIBLE[15] Educators (IPEs) who can now implement I’mPOSSIBLE Teacher Training in Ghana, Zambia, and Malawi. Read more here
  [15] Focussing on inclusion, I’mPOSSIBLE (created by the IPC) promotes the Paralympic values to challenge and change perceptions of how young people perceive persons with disabilities, working towards an inclusive society for all​
- The Assistive Technology Capacity Assessment Survey (ATA-C) was implemented in Mongolia and is implementing a number of recommendations[16] based on the results by the Ministry of Health.
  [16] Including conducting a national sample survey based on rATA questionnaire on the total and unmet needs of APs in Mongolia, and the development of a national APL (Assistive Products List)

Outcome Indicator 4: Delivery Models
Number of innovative service delivery models on track to scale
Target: 3	Achieved: 7
This outcome significantly exceeded expectations.

Two innovative service delivery models were developed and are on track to scale:
1. In South Africa, CHAI supported the piloting of the Optical Laboratory Management System (OLMS), an electronic ordering management system to improve the quality of vision services, enhance productivity, and provide management control of all aspects of production. The OMS is part of a broader initiative to strengthen the provision of eyeglasses in the public sector.
2. In South Africa, and scaling into Kenya, hearX’s smartphone based hearing diagnostic tool paired with a hearing aid is changing the way hearing diagnosis, hearing aid prescription and fitting are delivered. This makes it possible to conduct tests in the field by lay health workers.

Match Funding:
See Figure 3, ‘Match Funding’. AT2030 will deliver 100% match funding in cash or in kind. As at end of March 2021, the programme had raised over £10.5m in match funding against a target of £5.6m. A table showing the match-funding split is at Annex A.

Challenges:
The programme has ambitious targets. The impact of COVID-19 affected planned programme delivery during the reporting period – in both positive and negative ways. Travel restrictions delayed country-level work, research and data collection, and notably the 2020 Paralympic Games were delayed to 2021. However, AT2030 took the opportunity to pivot activities towards the COVID-19 challenge for example, undertaking a ‘Rapid Global Survey on Assistive Technology Use and Provision During COVID19’ (here) delivering outputs aligned to disability inclusion and access.
Figure 3: Match Funding

AT2030 faced budget adjustments in FY20/21, that resulted in an in-year budget reduction of 28% and required a significant amount of programme budget re-profiling and partner management.

Despite these significant challenges, the programme exceeded all outcome and impact targets.

Monitoring, evidence and learning – Inclusion
AT2030’s AT products and ventures are driven by the needs of people with disabilities and new service delivery models are focussed on the needs and priorities of stakeholders, including Disabled People’s Organisations (DPOs), and beneficiaries. Programme research prioritises beneficiaries and stakeholders from an ethics and inclusion perspective. Policy makers, NGOs, and DPOs are directly targeted for dissemination, learning and uptake to optimise impact and sustainability.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

AT2030 is on track to meet outcomes and impact and has exceeded expectations in this reporting year despite significant in-year budget reduction against the original 2020/21 budget forecast (although the overall programme budget remains unchanged). Ten qualitative ‘life-stories’ reflect the “life-changing impact of AT” on programme beneficiaries through AT2030 – see Box 4 below.

Budget re-profiling for 2021/22 began towards the end of the reporting period and as a result some activities have been delayed or stopped (this will be covered in the next Annual Review). It is therefore recommended that the programme is extended to end March 2024. Based on progress against impact and outcomes to date, AT2030 will review logframe targets to ensure they remain stretching but achievable year on year within budget. There will be strong focus in 2021/22 on reflection and learning across the programme for a better understanding ‘what works’ in the AT sector. This work is already underway and a summary ‘what works’ paper (or series of papers) will be published in FY2022/23.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on programme outputs, outcomes, impact (11/16 Outputs, 4/4 Outcomes and, 3/3 Impacts all exceeded expectations) and a strong value for money assessment, including a 100% match funding target, the programme continues to deliver strong results, good value for money and should continue. Disability inclusion is an important part of the Leave No One Behind agenda, and without targeting people with disabilities, it will not be possible to achieve the SDGs.
Capturing Life Stories during COVID-19: Understanding the impact on disabled people's daily lives.

Galih (hearing impariment):
“when pandemic hit there wasn’t much assessable information” creating confusion and anxiety in the deaf community.

Hari (mother of Bima who has ADHD): “when the pandemic hit all of Bima’s activities halted – his therapy, school, stimulating sessions and outside playtime…it has put us in a difficult position as parents”.
Box 4 Life changing impact of AT

AT2030 leads, the UK’s GDI Hub provide FCDO with a strategic and competitive advantage through AT science and technology innovation. This underpins the UK’s Science and Technology priorities, published in the UK Government’s 2020 Integrated Review. Increasing access to AT for people with disabilities was a commitment made by the UK Government at the DFID/FCDO co-hosted 2018 Global Disability Summit in London. AT2030 is strongly aligned to the delivery of FCDO’s (previously DFID’s) Strategy for Disability Inclusive Development, in particular the cross-cutting pillar on AT. AT will remain to be a priority in the forthcoming FCDO Strategy for Disability Inclusion (to be published in early 2022).

FCDO’s Senior Responsible Owner should explore options for extending the programme based on results to date.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Output number:		1	Output Score:	A
Impact weighting (%):		26	Weighting revised since last AR?	No

Note, the indicators above are cumulative milestone indicators
Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of innovative ATs supported	14	19 / (exceeded expectations)
1.2 Establishment of Innovate Now’s (IN) accelerator programme and number of cohorts run	Innovate Now (IN) Established / 3 cohorts	Innovate Now (IN) Established (on track) / 3 cohorts / (on track)
1.3 Number of AT Impact Fund (ATIF) Investments	3	2 (1 delayed – due to COVID[17]) / (on track to deliver outputs in 2021/22) / Note: significant progress was made across the ATIF but not captured in the current logframe
[17] COVID-19 hindered stakeholder outreach and engagement with the investment and innovation community (conflicting priorities, distracted by pressures of the pandemic, inability to travel etc.), and this constrained the identification of an available pipeline of potential investments. The approach to engagement changed thereafter, culminating in the Feb Open Call.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The programme supported 19 innovative new ATs in this reporting period, through the Innovate Now and AT Impact fund. These are significant commitments in terms of time, and level of support provided, that have produced promising results to date. The full list is at Table 2. Three new cohorts of xx entrepreneurs were onboarded in 2020/21, all of whom completed the programme.

Two investments were made under the AT Impact Fund. One was delayed due to the difficulties in engaging with potential grantees during the pandemic. This was eventually overcome through a dedicated resource to focus on outreach and the decision for an open call for applicants (which concluded onboarding new grantees during FY 2021/22). As AT is a nascent area, a significant amount of learning was required up front to develop the ATIF model and more work than originally anticipated was needed to better understand the whole AT ecosystem. A significant amount of learning from the ATIF approach, alongside early lessons from the investments, will be shared through a series of webinars and papers in 2021/22.

  1. Number of ATs supported
Exceeded expectations

Twelve (12) new innovative ATs (see Table 2) were supported during this reporting period. These comprised of innovations from two InnovateNow cohorts and two investments from the ATIF. Output 1.1 is on track to meet/exceed end of programme targets.

Table 2: Output 1.1 – Supporting Innovative ATs
Sub-Program	Organisation/ Country	AT Innovation
Innovate Now / [Kenya]	Kenya NGO Alliance Against Malaria / (KeNAAM)	Accessible, targeted mobile messaging / KENAAM is building and testing the use of mobile messaging to run marketing and awareness building campaigns around AT products and services in Kenya in formats that people with disabilities understand. It is envisaged that this could help DPOs and other clients reach people with disabilities everywhere with targeted messaging.
Innovate Now / [Kenya]	Lugha Ishara Company Limited (LI)	Education technology for deaf inclusion / ‘Lugha Ishara’ (Sign language in Kiswahili) is developing animated learning content and online classes to give the gift of language and literacy to pre-school kids born deaf. Primarily using mobile devices or computers, the technology is helping parents/guardians with no sign language knowledge, to learn together with their children at home. LI is working with corporates and Gertrude’s Children Hospital in Kenya to support children and parents from poor backgrounds access LI learning content.
Innovate Now / [Kenya]	Positive Exposure	Albinism & I App - informing, connecting & empowering / The Albinism & I App – a one-stop shop for information on albinism self-care, e-store for albinism skin and eye-care products as well as community of persons with Albinism. Persons with albinism and their families in Africa often lack access to information about self-care and self-care products. Discrimination and stigma can also cause isolation and a lack of voice in society. The app is accessible through web and mobile.
Innovate Now / [Kenya]	Taz Technologies	mPost - testing last mile delivery for ATs / People with disabilities anywhere in Kenya with access to a mobile phone can have parcels, including ATs delivered to their doorstep. Due to rapid urbanisation, pressure on resources, a lack of proper physical addresses and inaccessible postal offices, makes the delivery of parcels (including ATs) a major challenge. Mpost (a patented technology) enables mobile phone users to transform their phone number into a unique postal address for cost effective physical delivery of mails and parcels.
Innovate Now / [Kenya]	Hear(oes) on Demand (HOD)	An ‘on demand’ marketplace to source sign language interpreters / There are few verified sign language interpreters, who tend to be in high demand as events, schools, television, training programmes seek to be more inclusive. Hear(oers) on Demand are building and testing an ‘Uber’ equivalent ‘on demand’ app, to connect verified and qualified sign language interpreters with those needing their services easily and quickly. Features will include ratings and verified public resumes.
Innovate Now / [Kenya]	Riziki Source	Enabling access to jobs for persons with disabilities / Riziki Source is a social enterprise that facilitates workplace diversity, disability inclusion. The organisation works with a wide range of employers to facilitate introductions for persons with disabilities with particular skill sets (who are currently untapped for recruitment) to fill vacancies.
Innovate Now / [Kenya]	Village2nation	Accessible e-learning for employment / Village2nation is an accessible e-learning platform that combines learning-on-demand with live classes. It uses AT to make life-long learning accessible to people with visual and hearing impairments and focuses on courses with direct paths to employment - traditional or digital self-employment.
Innovate Now / [Kenya]	Errands Guy	Running errands for people with disabilities / ErrandsGuy is an eCommerce platform that seeks to connect people who are busy and require assistance in running errands, with individuals with time and skills who want to make money running errands/tasks. They offer a professional customer service to clients while providing income opportunities targeted at young Kenyans. ErrandsGuy have developed a custom platform (www.errandsguy.com) and app, (errandsguy) through which customers can access a range of services i.e. (a) individual/family errands; (b) corporate services; (c) services for SMEs and startups; and (d) services for people in the diaspora.
Innovate Now / [Kenya]	On the Table Africa	Matching talented people with disabilities with employment opportunities / On the Table Africa are a creative staffing agency with a pool of qualified, pre-screened engineering, product, marketing & design talent. Through talent matching, they advocate for people with disabilities to make up at least 20-30% of an organisation’s workforce. This workforce agility enables an organisation to be diverse, people-led and technology-supported.
Innovate Now / [Kenya]	AssistALL	Online sign language services / AssistALL interpretation services creates a direct link between sign language interpreters and the deaf in need of receiving or delivering services. A sign language interpreter aids effective communication, service delivery and service acquisition. When a service provider/receiver encounters a deaf person there is often a communication barrier. AssistAll, which can be downloaded on ‘google play’ and connects the provider/receiver to an interpreter of their choice online. This significantly reduces cost of Sign Language interpretation services and enables an interpreter to serve a greater number of clients.
AT Impact Fund / [Uganda]	WaziVision	Prescription eyewear designed, manufactured and distributed in Uganda / Wazi is the first prescription eyewear brand to offer low-cost, high-quality eyeglasses with a commercial proposition for low- and middle-income customers. ATIF is supporting Wazi to pivot to CNC digital fabrication so that the company can scale production, create an African designed and manufactured product, build a brand and marketing strategy, and develop a distribution model that can reach tiers of low- and middle-income customers. Through this work, ATIF has negotiated a partnership with Cubitts, a manufacturer of eyeglasses in the UK, to assist with the new manufacturing processes and provide scaling support.
AT Impact Fund / [South Africa & Kenya]	hearX Group	The world’s first clinical smartphone hearing solution / hearX Group offers an innovative product that makes it possible for lay-health workers to detect and diagnose hearing needs, and demonstrate how hearing aids can help, all in one sitting. ATIF is supporting hearX to test a business model for hearing aid provision in Kenya, with a subscription payment model and distribution partners. ATIF and hearX are piloting distribution and financing in South Africa and Kenya, with Azuri, a solar home system company offering access to paygo energy, and with Ilara Health, a health tech company servicing small scale pharmacies.

  1. Establishment of Innovate Now’s Accelerator Programme and Number of Cohorts Started
On track

GDI Hub and Kenyan partner Amref Enterprises onboarded five mobile technology-based projects into the Cohort 2, 12-week Innovate Now accelerator program. Cohort 2, launched on 14th July 2020, and participants joined 18 training sessions based on the Innovate Now curriculum, with 35 network mentorships, and five Live Lab introductory meetings. Cohort 3, launched on Nov 23, 2020 (here) and supported five start-ups who leveraged the power of technology to match people with disabilities to job opportunities and accessibility products to improve the work environment. Innovate Now contracted Kilimanjaro Blind Trust Africa to run the Live labs, support to develop business models and marketing strategies, and to provide support on legal compliance.

Innovate Now has continued to develop, test and refine their innovation toolkit. This included design and content creation of 80 method and information cards to continue to support the start-up entrepreneurs to apply their learning from the accelerator.

  1. Number of AT Impact Fund (ATIF) Investments
Moderately did not meet expectations (activities delayed due to Covid-19)
On track to deliver outputs in 2020/21

The ATIF planned to take three ventures through the application and portfolio process in FY 2020/21, however only two companies were deemed suitable and capable within the reporting period. Four further companies will follow in the next reporting period. The early impact of COVID-19 was a substantial barrier to stakeholder outreach and engagement within the investment and innovation community which severely constrained the identification of an available pipeline of potential investments. This issue has been overcome[18].
[18] By restructuring the team with three distinct ‘horizons’, one of which solely focused on investor and stakeholder outreach. Improvements were also made to the website and digital materials & messaging in the run-up to the Feb 2021 open call launch.

In the 20/21 reporting period, hearX and WaziVision were onboarded and are receiving capital investment and venture building support from GDI Hub, Brink and the Catalyst Fund (BFA Global). In its first global open call on 11 February 2021, 150 people joined the webinar which resulted in 90 applications from 84 organisations. Of these six were selected to take part in ‘pitch day’ where they presented their ideas and participated in a Q&A with a panel of experts. A final four were selected for investment starting in the next reporting period.

The AT Impact Fund also held an inaugural ‘Circle of Investors and Funders’ event on Tuesday 23 March 2020. 31 people were in virtual attendance, and heard from the fund’s founders, directors and investment managers. The event marked the beginning of a journey to grow the ATIF and the portfolio.

During the reporting period the ATIF iterated its service and operational design to better focus on engaging the available pipeline of potential grantees, maximise expert input from the panel of internal and external advisers, deepen the due diligence process around grantees, further develop the research and monitoring offer running parallel to the investments, and increase focus on medium- and long-term fundraising for the ATIF from third-party donors/investors. The logframe will be adapted to capture these outputs in the next reporting cycle.

The activity of the AT Impact Fund is shown in Figure 4, and Figure 5. These diagrams outline the AT Impact Fund’s target investment portfolio market and placement within the AT innovation ecosystem. Significant progress was made in the definition, development and iteration of the ATIF approach, a complex process.

Figure 4 highlights the challenges of ‘the path to scale’ in a diverse nascent area; first to understand the challenges, then to develop an AT ecosystem generally, and then for each individual investment - a complex and difficult process. The ATIF will require time to fully operationalise, i.e. to generate evidence of impact and to then crowd-in funding from the Private Sector and multilaterals, for whom this is uncharted territory. AT2030 will share evidence of their learning in late 2021/22 through to 2022/23 in a report, a series of webinars and in ongoing conversations with the Private Sector, with a view to continuing to establish and develop relationships and highlight the opportunities that investment in AT can provide. The next year of the programme will therefore include a review of the lessons and experience gained through the development of the ATIF, and the use of innovative funding mechanisms as a route to increase access to AT in LMICs (and other similar products/services), which are expected to significantly contribute to our understanding of the AT ecosystem.

Figure 4: AT Impact Fund

Figure 5: AT Impact Fund’s target investment portfolio

Table 3: VfM Indicators for Output 1
Effectiveness / Feedback from beneficiaries of the InnovateNow programme demonstrates the ‘effectiveness’ of the InnovateNow model of in-country support combined with bespoke support from experts in business development and assistive technology. For example: / ErrandsGuy’; / “It is very critical especially in shaping and bringing out the value and product development which answers to the needs of the market. My experience was really humbling that after training the mentorship period gets into perspective how to implement and measure the success of lessons by integrating them in product development”. / Cindy Adem, ‘Village2nation’; / “Think of this as a world-class crash course on building tech that people want. I went in as an absolute novice in the assistive tech space and have completely been immersed in a world that showed me what was possible in building a company that was responsive to the needs of people with hearing and visual impairments”.
Efficiency / AT2030 continues to leverage new and existing partnerships to ensure that the programme delivers outputs to the highest standard, while maintaining low costs. The existing GDI Hub partnership with Amref Enterprises has now expanded to include Kilimanjaro Blind Trust. This enabled the InnovateNow team to quickly develop networks to attract the best entrepreneurs and innovators to join the InnovateNow challenge.
Equity / AT2030 is designed to reach the most marginalised and ‘hard to reach’ populations, specifically focusing on people with disabilities. Country-level work under this output, such as the work in Kenya, has focused on people living in very poor conditions including informal settlements who have previously been overlooked for AT provision, i.e. reaching the last mile. / The ATIF is scaling AT ventures to reach people with disabilities in LMICs, specifically developing products and funding mechanisms to make ATs more accessible and affordable for the poorest populations.
Cost-effectiveness / Owing to the credible local impact and specific focus on supporting products and ventures based on their affordability for use by people with disabilities in LMICs, the programme has been able to leverage additional funding from other partners and organizations. For example, the European Disability Forum (EDF) awarded a grant prize of £15,000 to the Cohort 3 pitch day winner, and the Errandsguy also won Africa AT Innovation Progress Award as awarded by Safaricom. / The GDI Hub leverages their professional partnerships, i.e. combining expertise from UCL, Brink and the circle of investors to ensure that the selected ventures are appropriate for the market. Venture building and technical experts partner the organisations through a complex journey ensuring that capital funding is used effectively to build the business model and technical solution to scale their reach in LMICs, specifically targeting the people with disabilities, who are among the poorest and most underserved populations in developing countries.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Output 1.1, ‘Number of ATs supported’, exceeded expectations in FY 2020/21. Logframe milestone targets for this output will be considered for review in FY 2021/22. However the programme must also consider realistic targets for forthcoming years based on constrained budgets.

Due to budget prioritisations in FY 2021/22, FDCO will no longer directly fund new cohorts within InnovateNow (output 1.2). Logframe milestone targets will be reviewed accordingly. However, the GDI Hub are actively seeking new partnerships to continue to fund new cohorts of the sub-programme through match funding.

Due to limited budgets in 2020/21, anticipated to carry through to 2021/22, the ATIF has reduced the total number of ventures that can be supported from 12 to five. Logframe milestone targets will be updated to reflect this. The ATIF is a significant part of the programme and it is anticipated that the learnings and successes will attract new investment from the private sector over time, large international finance institutions and/or multilateral organisations. This important work is not yet reflected on the logframe, therefore an additional output indicator 1.4 will be considered.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead (Table 4)

Table 4: Output 1 Recommendations
(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Previous AR Recommendations	Progress
AT2030 should retain fund management expertise and source strong venture building expertise for innovators and entrepreneurs to ensure that the new AT Impact Fund (the first of its kind) can deliver against ambitious and challenging targets	Completed / AT2030 retained technical and venture building expertise for the ATIF through Brink and UCL and recently onboarded BFA Global for further venture building expertise, as well as 60Decibels for support in the generation of insights. / It has been a challenging year for the ATIF however they are on track to meet new targets (based on budget constraints – logframe to be updated)
AR Recommendations for this year
Based on updated annual budgets and achievements to date, review logframe targets by end October 2021: / Output 1.1 / Output 1.2 / Output 1.3 / Consider adding an output 1.4 on fund raising for the ATIF
Learn lessons from ATIF to refine and adapt future approaches and to contribute to our understanding of the AT ecosystem (by end March 2022). / Document and disseminate findings through report(s) (by end June 2022) and a series of webinars beginning in November 2021.

Output Title	(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced.
Output number:		2	Output Score:	A++
Impact weighting (%):		24	Weighting revised since last AR?	N/A

Note, the indicators in the table above are cumulative milestone indicators
Indicator(s)	Milestone(s) for this review	Progress
Number of peer reviewed / journal and conference papers published	5	18 / substantially exceeded target
Number of influencing papers, answering critical research questions published	14	44 / substantially exceeded target
Number of downloads/views for articles/papers above.	8,400	17,045 / substantially exceeded target

Briefly describe the output and provide supporting narrative for the score.
This has been a particularly strong output for AT2030 during the reporting period. Across all indicators in this output, AT2030 has substantially exceeded expectations. The programme continues to produce high quality academic and influencing papers, notably feeding into WHO’s Global Report on AT to be published in early 2022/23. The number of downloads and views have far exceeded expectations, testament to the programme’s outreach efforts.

Output 2.1: Number of peer reviewed / journal and conference papers published
Substantially exceeded expectations

The boxes below, highlight examples of work completed under this output. A full list, including links to the papers and articles is at Annex B.

During the reporting period a substantial amount of research and analytical work was completed, framed around three main research themes of enquiry.
1. the Economics of AT around a mission-led framework;
2. the Return on Investment for AT, and;
3. What Works to Overcome Stigma
.
Box 7 Theme C: What Works to Overcome Stigma

Leonard Cheshire (LC), with the United Disabled Persons of Kenya (a Disabled People’s Organisation) finalised work on the ‘Overcoming Stigma towards Assistive Technology’ (OSAT) Project. It aims to conduct and evaluate stigma and discrimination reduction interventions to engender the uptake of AT. Their work was accepted for publication in the ‘International Journal of Environmental Research and Public Health’ – date late 2021.
Box 6 Covid Pivot

Pivoting to respond to Covid-19, programme partner Maynooth University Assistive Living and Learning Institute (MU ALL), published three peer-reviewed manuscripts on ‘COVID response and AT’, and on ‘opportunities for AT use and provision during the COVID pandemic’ - including results from their rapid global survey.

Box 5 Theme A: The Economics of AT Around a Mission-led Framework

UCL-IIPP (UCL Institute for Public Purpose) and GDI Hub published New Economics of Assistive Technologies: A call for a Missions Approach paper which sets out a framework for action around AT through a public sector-led, mission-oriented approach.
“A mission-oriented approach will use tools such as market-shaping and stakeholder co-creation to set an agenda by which AT innovation and access can be positioned as a meaningful step in tackling societal challenges. Through a missions approach the value of AT will be properly captured and society can come closer to addressing issues surrounding healthy ageing, enabling human capability and equity.”
IIPP continued to build on their Input-Output analysis which seeks to identify the impact AT may have within the broader production and innovation ecosystems through input-output linkages in their supply chains, shaping market structure, increasing employment, and ultimately, benefiting the user. IIPP also submitted a WHO Background paper for publication, “Systematic Review of Economic Evaluations of Assistive Technology Globally” which has been accepted for publication in the RESNA Special Issue (Rehabilitation Engineering and Assistive Technology Society of North America) in late 2021.

Co-funded by AT2030 (notably including the co- ordination of the report), WHO leads the coordination of the Global Report on AT (GReAT) through an Editorial Committee (EC - five-chapter editors supporting a lead editor), established during this reporting period. First and second drafts of the report were completed for Expert Advisory Group (EAG) and UNICEF review.

On 15th February, the Editor-in-Chief at the Assistive Technology Journal RESNA, formally invited programme partners to submit papers for the ‘AT2030 Special Issue’ of the Journal, sponsored by UNICEF. This edition will be made open access is expected to be published in Q4 2021/20, although a number of peer reviewed articles were drafted during this reporting period

Work began on ‘Assistive Technology in the Humanitarian Context’, an AT2030 applied research project. Led by Dr Maria Kett (UCL), this work was delayed due to Covid-19 restrictions. The research aims to improve understanding of the need for AT in Humanitarian Settings, compiling evidence of current provision and practice, and case study examples of “what works” as well as providing recommendations for action by key stakeholders in the humanitarian space. This project is now expected to conclude in Q3, 2021/22.

Maynooth University (MU) ALL Institute: Assisting Living & Learning (ALL) engaged in discussions and a review of existing AT innovation hubs in Kenya to determine the factors that promote technologies coming to market, and the barriers faced specifically by organisations producing or promoting ATs. This will inform AT2030’s (an others’) approach to AT innovation investments going forward.

Output 2.2: Number of influencing papers answering critical research questions published
Substantially exceeded expectations

31 additional papers against a target of seven ‘influencing papers, answering critical research questions published’ were published. Two examples are detailed in boxes 8 and 9. See Annex C for the full list of publications in this reporting period.

Box 8 Gender and disability in informal settlements during COVID-19: What we have learnt so far
How are women, in particular disabled women, affected by COVID-19 in informal settlements in the global South? Little has been documented about the lived experiences of women, particularly disabled women, in informal settlements in the global South. More information and critical analysis is needed to understand the intersectional impact of the pandemic.

Emerging research shows ‘(…) a combination of population density and inadequate access to water and sanitation, (…) makes standard advice about social distancing and washing hands implausible [in informal settlements] (Wilkinson, 2020; p.1), posing specific risks for female dwellers, in particular those who are disabled.

From previous health crises, we know that informal settlements tend to be gravely affected and that global health policies have been slow at recognising the gender and disability dimensions of health emergencies. Evidence from the West African Ebola outbreak (2014-2016) shows that women (and gender more broadly) remain largely invisible at every point of the international health response (Smith, 2019). Disabled people in particular, faced lack of access to food and health services, increased discrimination and lack of information about the epidemic.

Working with the Federation of the Urban and Rural Poor (FEDURP), Sierra Leone Research Centre, the Indonesian NGOs Kota Kita and Kaki Kota to understand the lived experiences of disability in informal settlements, we know that:
1. Decreased livelihoods have resulted in lack of access to food: Maria, a female community leader from the largest informal settlement in Valparaíso, explained,
    1. “It is not the virus we are worried about, it is unemployment. It is the number of people that are losing their jobs, which are already informal, and children that are not getting their meals because they are not going to school. Some people don’t have anything to eat.”
2. Effects of quarantine and social distancing measures on informal care systems and networks: A few days after the first case of COVID-19 was registered in Freetown, the Head of FEDURP, explained:
    1. “Social distancing is just not possible here, we would need to expand to all the city (sic) if we were to be two meters apart from each other.”
3. Disabled people have told FEDURP that if social distancing is enforced more strictly, they are at the risk of losing everyday support they receive from neighbours and friends.
4. High rates of gender-based violence against disabled women and girls: Disabled women are disproportionally affected by gendered violence (United Nations High Commissioner for Human Rights, 2012), which has increased dramatically as confinement puts more pressure on households. This makes it even more important that the data collected in health crises is disaggregated in gender, sex, disability, age and race, in order to identify groups that are particularly vulnerable and need more support.
5. Difficulties accessing water and sanitation heighten health crisis: Dwellers are spending more time in the settlement and children are not in school which means that the management of water – already difficult to ration – is even harder in a context where hygiene is key. In Freetown’s settlements, paid water points are even more difficult to access for older and disabled women, who tend to have lower income. Physical access is also an issue, as is sexual violence against women, in particular disabled women and girls, by water controllers.
The cases have highlighted women’s roles as carers of children, older people and increasingly, of the ill, in setting up community kitchens, managing scarce water resources, with less access to income and vulnerability to gender-based violence, especially if they are disabled.

Box 9 Policy Brief - Powering Inclusion: Artificial Intelligence and Assistive Technology
“Design constraints imposed by disability result in novel universal technologies”
AT2030 convened an expert roundtable to highlight the potential of using AI for AT and to establish a list of ‘grand challenges’ to drive forward innovation in the AI & AT sector ahead of the launch of the newly formed International Research Centre on Artificial Intelligence under the auspices of UNESCO (IRCAI). Participants included industry leaders, innovators, entrepreneurs, policymakers, and AT users. The session focused on the opportunities and barriers around four areas: ‘AI & Communication’, ‘AI & Mobility’, ‘AI & Improving Information’, and also on more general ‘cross-cutting themes’, requirements that must be considered when developing new technologies in this space.
Conclusions
AI presents many opportunities to both enhance AT and to improve access to AT. Better data on the scale and nature of the need globally is vital in making sure that opportunities are realised. The importance of taking a user-led approach to designing new technologies was equally notable. The roundtable focused on harnessing the power of AI to create a more accessible world. AI innovations such as image recognition, speech-to-text, and autonomous spatial guiding systems are technologies that can benefit society as a whole. By designing with accessibility in mind, we can all benefit from the creation of more intuitive, feature-rich and impactful products; Innovation for disability is innovation for everyone.

Recommendations for Policymakers
Policymakers should consider how data, knowledge and learning can be shared effectively between different countries in order to maximise benefits;
Policymakers should consider the ethical implications of using AI, particularly where AI is used to recommend who gets access to AT and/or which technology they are offered;
- Policymakers should work with industry and users to develop guidelines to ensure transparency in AI based decision making;
- Policymakers should ensure digital inclusion: make digital technologies and contents fully accessible to all people.

Output 2.3: Number of downloads/views for articles/papers above
Substantially exceeded expectations

AT2030 has been monitoring the number of downloads, views and citations for all programme research papers through metrics taken from researchgate, AT2030.org, journal analytics (which are typically shown next to publications) and partner websites (as part of Quarterly reporting). As at end March, this indicator substantially exceeded expectations with 17,045 Downloads and views, against a target of 840.

AT2030 has worked to strengthen impact measurement mechanisms for research outputs by developing an AT2030 project through the ‘ResearchGate’ platform and on AT2030.org. Through ResearchGate’, programme partners are able to store and share all academic publications produced across the programme. ‘ResearchGate’ enables the programme to track reach, including the number of downloads and citations which simplifies indicator reporting processes. It is one of the leading networking sites for scientists and researchers to share papers, ask and answer questions, and find collaborators. Several management improvements were also made to the development of content pipelines to track and profile media and content generated by all partners. This supports the project website, AT2030.org as a mechanism to disseminate and track the uptake of project research, lessons and ideas. For example, a ‘content pipeline’ was created to aggregate all the material being generated across the programme, and link this to downstream communications work to promote, post and track content. This is ensuring that content pieces are not just produced but become publication and communication assets for AT2030. This also addressed past challenges with ensure that programme material is all available on AT2030.org.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

This Output presented strong value for money this reporting period. Examples are shown in Table 5 below. Changes to travel costs have fallen as a result of Covid-19, while due to in-year budget reductions, the percentage of management costs to delivery costs as a proportion have increased slightly.

Table 5: Output 2 VfM examples
Effectiveness / There has been coordination across all programme partners around data, databases and tools to estimate demand and supply of AT (for example, the LSHTM-UCL-WHO collaboration on the AT Need Mobile App which uses survey data generated by the Musculoskeletal impairment paper reported in the previous period ). In addition, programme partners have together supported the WHO World Report on AT (to be published next year), strengthened impact measuring tools and identified new research and academic conference opportunities to disseminate lessons and evidence. AT2030’s research partners leverage established partnerships with NGOs and world-class academic institutions, composed of diverse and complimentary skills, to deliver high quality outputs. / Some research strands quickly pivoted to provide rapid evidence on the needs of people with disabilities during the Covid-19 pandemic and enhance our understanding of impact of Covid on people with disabilities and the supply and demand of AT.
Efficiency / Dissemination of research findings is a key element of programme outcomes attainment and is supported by dedicated communications capacity. Due to the size, reputation and reach of partner networks – including world-class universities, industry bodies and global NGOs – this function is highly efficient. For example UCL’s dissemination network includes programme partners, GATE Network, European Assistive Technology Information Network (EASTIN), Association for the Advancement of Assistive Technology in Europe (AAATE) , Rehabilitation Engineering and Assistive Technology Society of North America (RESNA), The Global Alliance of Assistive Technology Organisations, CHI Conference on Human Factors in Computing Systems, among others.
Equity / As for all of AT2030, all of the research is aimed at better understanding the needs, access and unmet needs of people with disabilities, one of the most marginalised populations globally. The programme has conducted research on people with disabilities and AT informal settlements in Indonesia and Sierra Leone to better understand the needs of some of the most marginalised populations of people with disabilities. These studies typically include participant data disaggregated by gender (e.g. https://at2030.org/bridging-the-divide/ and https://at2030.org/the-social-network/), and have to a limited extent highlighted findings on the different use and impact of mobile technology for visual and mobility impaired men and women.
Economy / Inputs for the programme are largely person time, with low programme goods purchases. A large proportion of human resource capacity across the programme is procured through academic partners, and therefore costs are based on academic salary scales. This is much cheaper than comparable quality professional levels procured through consultancy. For example, a senior researcher costs approx. £210 per day through AT2030’s grant structure compared to a (discounted and long-term) service level charge-out rate of £462 for the same level of expert.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

AT2030 has and is producing a substantially larger amount of content (academic and grey literature) than originally anticipated. This poses opportunities to increase impact, but also presents challenges for the coordination of this volume of content from a communications perspective. This can be accessed through the AT2030 website. Coupled with a reduction to programme resources and proportionate reduction in management capacity, achieving streamlined communications across this work has been particularly challenging. Nevertheless, further effort to strengthen and streamline the profiling and capture of programme content is continuing, leveraging programme match-support from GDI Hub and UCL to address current gaps.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Table 6: Output 2 Recommendations
(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced. https://at2030.org/impact-stories/
Previous AR Recommendations	Progress
GDI Hub should implement strong cross-partner communication objectives as outlined in the AT2030 communications plan. This will enable better understanding of how the research links together across programme outputs and outcomes. There is potential for the cross-fertilisation of knowledge to generate new ideas, partnerships and innovations	GDI Hub have made strong progress this reporting period on targeting a wide range of stakeholders: implementing a series of webinars; blogs; a bi-weekly newsletter to programme partners and; podcasts, to disseminate emerging lessons from the research and across programme themes. / In particular the webinars and bi-weekly newsletters have enabled programme partners to connect across workstreams, for example a new partnership formed in this period was bringing UNCIEF into the WHO-led Procurement work, which has created a substantial multiplier effect for the impact of AT procurement tools, with these now entering the UNICEF practice as well as utilising the UNICEF AT Advocates Network. / GDI Hub and the AT2030 programme have significantly increased their social media presence to advocate for change, to share insights and lessons, and raise awareness of specific issues, challenges and opportunities. / More work needs to be done to share these and future outputs and communications with targeted FCDO partners.
AR Recommendations for this year
Based on excellent progress and reflecting a reduced budget, review the Logframe indicators for this output / (by end October 2021).
GDI Hub should continue to strengthen and streamline the profiling and capture of programme content for ongoing co-ordination and communications planning, leveraging match support from partner organisations where possible / (ongoing, to end programme)
FCDO SRO should focus on outreach within FCDO - connecting and collating emerging lessons (through papers, webinars, social media and podcasts etc) with relevant country based and policy teams / (ongoing, to end programme).

Output Title	(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
Output number:		3	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of partnerships supported to increase AT capacity.	6	62 / substantially exceeded expectations
Number of strategic tools developed to increase AT capacity	32	50 / substantially exceeded expectations
Number of case studies produced (including from: Inclusive Infrastructure and Sport against Stigma).	0	14 / substantially exceeded expectations
Value of matched funding provided through partnerships	£ 5,600,000	£10,581,847 / substantially exceeded expectations

To note, the indicators in the table above are cumulative milestone indicators.

Briefly describe the output and provide supporting narrative for the score.
This output has proven to be a particular area of strength for AT2030 leads, the GDI Hub. AT2030 has substantially exceeded all expectations during the reporting period. With 62 partnerships contributing to programme delivery the programme excels at working with a variety of organisations to maximise its outputs.

The programme has already developed 50 strategic tools (34 in this reporting period, including the InnovateNow toolkit, the AT data repository and ATA-c portal) and a series of case studies (14 as at the end of the reporting period) to reach a variety of audiences with the outputs of the programme, to increase the likelihood of uptake of the learning.

GDI Hub has nearly doubled the amount of match funding expected during this period. This is mainly due to the investment made to develop partnerships throughout the programme.

3.1 Number of partnerships supported to increase AT capacity
Substantially exceeded expectations

The number of partnerships formed through AT2030 have been significantly greater than originally anticipated during programme design. The programme now has 62 partnerships, summarised in Figure 6 below. 16 of which are UK based partnerships. Over the year ahead the programme will continue to build relationships with the private sector, multilaterals and international financial institutions through the growth of the ‘ATIF Circle of Investors’, with national Government departments through CCAs, implementation of CIF grants and the inclusive infrastructure portfolio. Ongoing reviews of GDI Hub’s Stakeholder Mapping will ensure timely and effective links are made providing a growing impact. In this period the AT2030 programme team had discussions with FCDO offices in India, Sierra Leone, Kenya and the Africa ST&I Team. The FCDO SRO will prioritise in-country outreach in AT2030 ‘priority countries’ in 2021/22 when the reprofiled areas of activity are better understood.
Box 10: Exemplifying the value of Partnerships
GDI Hub, UCL, IRCAI/UNESCO, European Disability Forum, and the Jožef Stefan Institute (JSI) launched a global call for evidence into Artificial Intelligence and Assistive Technology and hosted and international roundtable. The roundtable brought together 35 international experts to discuss and agree the top 10 challenges around artificial intelligence and assistive technology. As a result of the roundtable, UNESCO/IRCAI, UCL/GDI Hub, EDF, UCL STEaPP and the Jožef Stefan Institute published the Powering Inclusion: AI and AT Policy Note.

In 2021/22 onwards, country level work will continue predominantly through: innovation acceleration, inclusive infrastructure case studies, and the parasport against stigma project. Likely focus countries, where outreach will be prioritised include Kenya, Ghana, Zambia, Malawi, India, Indonesia, Sierra Leone, Nepal.

Figure 6: Partnerships by country

Figure 7: Partnerships by Type

3.2 Number of strategic tools developed to increase AT capacity
Substantially exceeded expectations

AT2030 added a further 15 ‘strategic tools’ against a target of 3. Annex D details the full list of strategic tools developed. Many of these tools are at an early stage of implementation. AT2030 is monitoring their use and application and for future Annual Reviews, will provide a short summary report of their impact.

Examples include:
- InnovateNow: The Innovation Toolkit and the InnovateNow Accelerator Programme Curriculum are core parts of the InnovateNow model, allowing innovators to access the course and support resources even after completion of the 12-week programme. The toolkit will be moved online in 2021/2022.
- Launch of the (WHO) ATA-C tool portal (9th November 2020), including the Implementing Manual. ATA-C is a system-level tool to evaluate a country’s capacity to finance, regulate, procure and provide assistive technology. Its development was informed by testing and implementation in Bahrain, Bolivia (Plurinational State of), Ethiopia, Indonesia, Iraq, Liberia, Malawi, Mongolia, Nigeria, Rwanda, Sierra Leone, Tajikistan, Uganda and Viet Nam.
- Joint UCL/WHO AT data repository is online and is growing. This work includes a global systematic review of all population-level studies with a measure of Assistive Products as an outcome. The AT Data Repository allows policymakers to interact with the data in a way that is most accessible to them, will help answer specific questions, provide contextual information and links to external data sources. Access here
- Completion of ‘Product Narratives’, published in multiple languages, provide a market shaping and strategic approach to increase access to AT (eyeglasses, hearing aids, prosthetics, wheelchairs, and ‘digital’ products) to inform the approach of governments, donors, NGOs and other funders in the AT space.
- At country level, Kenya’s Disability Medical Assessment Guidelines were developed by CHAI. Further details of the case study that this tool supports are here.

3.3 Number of case studies produced (including from Inclusive infrastructure and Sport Against Stigma)
Substantially exceeded expectations

Case studies were designed to engage audiences through different formats. A full list is at Annex E. Examples include:

Table 7: Case Studies
Project / [Location]	Case Study	Links
Inclusive Design and Accessibility of the Built Environment / [Ulaanbaatar, Mongolia]	Research on accessibility and inclusion in the built environment. / Part of a series of six global case studies to understand global priorities for inclusive design. / Results were disseminated at the Development Agencies meeting in Mongolia on 14th October, organised by the UN, and with the British Embassy in Mongolia. The report is available in English and Mongolian / By GDI Hub, Associazione Italiana Amici di Raoul Follereau (AIFO), Tegsh Niigem and Universal Progress ILC	Full report / (87 pages) / Summary / (8 pages) / Overview of Inclusive Infrastructure / (web page)
Catalysing AT access: / Scaling rehabilitative services and increasing access to AT / [Kenya]	Expanding access to rehabilitative and AT services in Kenya / At the request of Kenya’s Ministry of Health, a comprehensive situational analysis was conducted that involved a mapping of service capacity in 238 public health facilities – 47 county referral hospitals and 191 sub-county hospitals. The case study describes the pathway towards national scale up by developing a “National Strategy for Scaling Rehabilitative Services and Increase Access to Assistive Technology”. / Findings were shared with all government stakeholders via a series of video conferences and a follow up two-week workshop / By CHAI and AT2030 programme	Full Report (6 pages)
The Liberia Evidence Lab: A new scalable model to deliver School Eye Health / [Liberia]	Expanding access to eyeglasses for better outcomes in school / The case study highlights how school eye health programs can be successfully scaled in under-resourced and under-capacitated contexts, and ultimately supported through a sustainable financing mechanism. School eye health is an entry point and critical building block to comprehensive national eye health coverage. Through a pilot of the school eye health model, approximately 50,000 children received eye screenings across three counties in Liberia. / By EYElliance, CHAI and the AT2030 programme	Full Report / (7 pages)
A unified approach to fund and provide AT services / [Indonesia]	A new coordinating mechanism is catalysing access to AT / An assessment of the country’s AT sector highlighted the need for increased coordination among stakeholders. A cross-ministerial technical working group (TWG) was set up in 2019 to address the issues that inhibit access to assistive products. One of the TWG’s first commitments was increasing budgets and developing policy for provision of AT by local governments. A new AT funding scheme – currently named DAK-Fisik Social for AT – will cover the cost of assistive products and services for people with disabilities in Indonesia. / By CHAI and the AT2030 programme	Full report / (5 pages)

3.4 Value of matched funding provided through partnerships
Substantially exceeded expectations

AT2030 includes an ambitious 100% match-funding target. The programme leveraged a total of £10,581,847 in cash or in-kind resources against a target of £5,600,000 by the end of the reporting period. The form of match contributions is varied, and key additions in the reporting period include:
- German Government funding to support 'A rapid, remote-support model to strengthen access to community-level assistive technology in response to COVID-19 disruption' via the WHO. Read more here;
- Loughborough University directed co-funding into the project budget, including additional staff time on the project and the provision of external expert and consultancy advice.
- Match-funding from USAID to support work in Tajikistan on the review of the assistive product specifications (APS's);
- Match funding secured from the International Paralympic Committee to support approximately 75% of the cost of the broadcast contracts for the Paralympics;
- Co-funding from Global Observatory on Local Democracy and Decentralization and the The European Disability Forum (EDF) through the Innovation to Inclusion (i2i) project to support InnovateNow.
- Substantial government budget unlocked to support AT provision through DAK FISIK (Indonesia) in 2020/2021.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Output 3 has accelerated faster than anticipated and therefore has represented strong value for money. Examples are included in Table 8.

Table 8: Output 3 VfM examples
Economy and cost effectiveness / The 100% match-funding target is delivered by working through a wide and diverse range of partnerships - with NGOs, academic institutions and the private sector. / AT2030’s ‘internal skills market’ has driven down the cost of service provision, as expertise can be leveraged through existing programme partnerships instead of buying in expensive consultancy, which has equally driven up programme capability. For example, the provision of world-class research frameworks from UCL, Maynooth University and LSHTM are used within country-based pilots delivered by CHAI and WHO.
Efficiency / GDI Hub’s coordination and collaboration function ensures that partners avoid duplication and identify possible programme efficiencies. For example, the Training on Assistive Products (TAP) modules for training on AT developed by WHO under AT2030 have been used at the country-level by partners CHAI as part of their Country Implementation Fund (CIF) work.

Describe any changes to this output, and any planned changes as a result of this review.
Output 3 is an excellent example of how the AT2030 programme has built and leveraged partnerships to deliver high quality products at an affordable cost, substantially exceeding all outcome target expectations.

Logframe targets were reviewed upwards as a result of last year’s Annual Review and as the output has again substantially exceeded expectations, demonstrating GDI Hub’s strengths in this area, logframe targets for forthcoming years of the programme will be re-evaluated. However, budget reductions against original spend forecasts for the forthcoming two years will need to be factored into this.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Table 9: Recommendations
(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
Previous AR Recommendations	Progress
Based on programme outcomes and outputs that have exceeded expectations in this reporting period, further investment in building partnerships should continue to yield strong results. / An ongoing review of key stakeholders for and across sub-programmes will ensure that important partners are identified early and appropriately to explore new opportunities. GDI Hub should talk to this at quarterly FCDO/AT2030 Quarterly Reviews	GDI Hub has excelled in developing new partnerships in this reporting period, building on last year’s strong progress. These partnerships have substantially increased the number of tools developed, case studies produced and match funding achieved – beyond expectations. This good work should continue. / GDI Hub update FCDO regularly, during bi-weekly meetings and quarterly reviews.
AR Recommendations for this year
Based on excellent progress and reflecting a reduced budget, review the Logframe indicators for this output / (by end October 2021).
GDI Hub should continue to build partnerships for strong programme results / (ongoing, to end programme)

Output Title	(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
Output number:		4	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Note, milestone targets are cumulative
Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of country capacity assessments (CCA)	10	10 / met expectations
4.2 Number of countries delivering CCA action plans	3	7 / exceeded expectations
4.3 Number of countries with direct investment in AT matched to be sustainable (also links to significant numbers of ‘reach’).	2	4 / exceeded expectations
4.4 Number of 'one-stop-shop' pilots at the country level	2	2 / met expectations
4.5 Number of 52min daily digests of the Japan Paralympic Games produced.	0 / Target changed last year due to postponement of 2020 Paralympic Games to 2021	0 / (Good progress – output indicator is on track)
4.6 Paralympic Games broadcasts across a number of Africa Countries	0 / Target changed last year due to postponement of 2020 Paralympic Games to 2021	0 / (Good progress – output indicator is on track)

Briefly describe the output and provide supporting narrative for the score.
Overall, this output has exceeded expectations. AT2030 completed 10 Country Capacity Assessments (CCAs), meeting target expectations, through the complex facilitation of multiple stakeholders including across multiple country Government departments for each CCA. During this reporting period, there was evidence that seven countries were already delivering against their CCA action plans (against a target of four, exceeding expectations). This is also encouraging evidence that that CCA recommendations are being operationalised as part of a long-term commitment from Governments and will therefore sustainably impact directly on the lives of people with disabilities.

Further, the programme exceeded expectations in gaining direct investment from Governments to deliver CCA action plans in four countries (against a target of two). This was achieved through strong partnerships developed by delivery partners and Governments during the CCA process and ongoing advocacy. One-stop shop pilots were delivered in two countries, Tanzania and Tajikistan.

The Paralympic Games were postponed until September 2021 and therefore logframe targets for output indicators 4.5 and 4.6 were also postponed until FY2021/22.

4.1 Number of country capacity assessments
Met expectations

Country Capacity Assessments (CCAs) are in-depth studies aimed at understanding a country’s capacity to finance, procure and provide AT. They provide evidence and the process provides support for policy makers to identify actions to strengthen AT service delivery to meet population needs.

CCAs studies include stakeholder workshops with multiple in-country Government Departments and NGOs involved in AT policy, production and supply. AT2030 met expectations for delivery of CCAs against a stretching target. Co-designed by AT2030 partners CHAI, and Government partner organisations, each country produced descriptive reports with actionable recommendations. Some country Governments have made their reports publicly available - on request (see Table 10).

Table 10: Country Capacity Assessment – cumulative progress
Reporting period	Countries	Output	Lead Partner	Link to output (where available)
2020/21	All – CCA Lessons Learned Report / All – ‘Country Capacity Assessments- supporting country governments to address Assistive Technology access.’	Report / Webinar	GDI Hub	Report / Webinar recording
2020/21	All – refined ATA-C tools / All – CCA and ATA-C guidance		WHO
2020/21	Dominican Republic / Vietnam / Bolivia	CCAs	WHO
2020/21	Informal settlements: Sierra Leone / Informal settlements: Indonesia	CCAs	GDI Hub
2019/20	Ethiopia / Liberia / Malawi / Nigeria / Rwanda / Sierra Leone / Uganda	CCAs	CHAI

GDI Hub facilitated a Disability Innovation Live webinar entitled ‘Country Capacity Assessments- supporting country governments to address Assistive Technology access.’ Participants heard from the creators of the ATA-C tool (tested and refined through the programme to measure AT supply and demand) and from teams that implemented the Country Capacity Assessments, with country specific information from Ethiopia. Over 200 people joined the webinar from 72 countries.

4.2 Number of countries delivering CCA action plans
Substantially exceeded expectations
Six counties delivered actions against their CCA action plans (in addition to four countries from earlier periods). To build on the CCAs, GDI Hub developed and operationalised the ‘Country Investment Fund’ (CIF), which supports the implementation of CCA recommendations. Following an open application process, the CIF is working in four countries; Liberia, Nigeria, Rwanda and Sierra Leone.

Two countries, not receiving CIF support, are implementing CCA action plans:
- Malawi: The Malawian CCA led to the development of a new policy that provides a directive to deliver assistive products and services sustainably through the health system. The CCA in Malawi identified policy gaps in the delivery of AT and rehabilitation services. The Ministry of Health prioritised the development of a National Medical Rehabilitation Policy (NMRP) to ensure that all people access quality medical rehabilitation services at all levels of the healthcare system in Malawi. In March 2020, a task force, which included 14 representations from Ministry of Health - Clinical Services and Policy and Planning Directorates, Ministry of Gender, and the Community Development and Social Welfare Office held consultations with stakeholders including public, private and NGOs, across the country to gain input and feedback on the draft policy.
- Ethiopia: In response to recommendations in Ethiopia’s CCA, the Ethiopian Ministry of Health officially launched the National Rehabilitation and AT Services Guideline, developed under the AT2030 programme. The guidelines are important for the ensuring quality and safety of ATs in Ethiopia.

4.3 Number of countries with direct investment in AT matched to be sustainable (also links to significant numbers of ‘reach’)
Exceeded expectations
The CIF was designed and operationalised during this reporting period. This included the formation of an advisory board (including an FCDO representative) to interrogate and assess proposals for further in-country investment to implement recommendations from CCAs. 14 applications were received and four were awarded CIF grants. Maynooth University are conducting the accompanying research component.

Commencing in January 2020 and led by AT2030 partners, CHAI, Liberia, Nigeria, Sierra Leone and Rwanda began designing and implementing a range of CCA recommendations. These are scheduled to complete in the 2021/22 reporting year. CCA recommendations are at Annex F.

4.4 Number of 'one-stop-shop' pilots at the country level
Met expectations
AT2030’s ‘one-stop-shops’ are part of the effort to develop new models of integrated AT service provision. In collaboration with Ministries of Health and local partners, the WHO is piloting this model in Tanzania and Tajikistan. A ‘one-stop-shop’ typically provides a single point of contact and ‘how-to’ information on issues related to AT services, including procurement of assistive products, training of workforce, and the establishment of referral mechanisms.

Owing to the covid-19 pandemic and related travel restrictions during 2020/21 no further work on the in-country ‘one-stop shop’ model could be progressed in this reporting period. However, WHO maintained relationships and will re-visit this work stream as soon as is feasible. Progress remains on-track in respect of logframe indicators, (indicators were revised in early FY 21/22 as pandemic restrictions became clear). This work stream is currently planned to conclude in the 2021/22 reporting year. A Lessons Learned report on the ‘one-stop shop’ pilots will be published in FY 2021/22. Experience and learning from the two pilots will inform roll-out of the ‘one-stop shop’ model in new countries beyond AT2030 scope (e.g. India, PNG and Iraq) with match funding.

Supporting the ‘one-stop-shops’ to operationalise AT procurement, WHO developed and launched the ‘Assistive Product Specifications (APS)’ at a Global Launch Webinar on 4th March 2020. 175 people attended the launch from 59 countries. The main aim of the APS is to ensure countries supply good quality and affordable assistive products through appropriate procurement to enable access for all who need them. Each of the 26 APS included in the compilation, includes the functional and performance requirements that should be used as a model to guide manufacturing and procurement. The APS focusses on innovative products, new service models, and global capacity to drive disability innovation for a fairer world. The priority assistive products list (APS) includes mobility, hearing, vision, communication, cognition and self-care products. These range from clubfoot braces and wheelchairs to hearing aids, alarm signallers and audio-players. Accompanying the launch was a short animation video.

4.5 Number of 52min daily digests of the Japan Paralympic Games produced
No targets within this reporting period, and paused due to Covid-19
On track

Building on lessons from London 2012 and learning from AT2030’s ‘stigma research programme’ (see Box xx), this output is intended to challenge the negative perceptions of people with disabilities. However, with the postponement of the 2020 Paralympics due to Covid-19, output targets under this indicator were deferred to FY 2021/22. Progress to deliver against this indicator is on track for FY 2021/22.

4.6 Paralympic Games broadcasts across a number of Africa Countries - no targets within this reporting period, and paused due to Covid-19
On track
The International Paralympic Committee (IPC) signed broadcasting agreements with 26 territories in sub-Saharan Africa during this reporting period. [This number grew significantly to 49 countries by September 2021/22 – this will be reported in the next Annual Review.]

In this reporting period, the programme signed contracts with the National Paralympic Committees in Malawi, Ghana and Zambia to support in depth analysis of the perceptions of people with disabilities as a result of the television broadcasts and for delivery of the aligned stigma and discrimination educational programmes. I’mPOSSIBLE in a number of schools.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The International Paralympic Committee (IPC) signed broadcasting agreements with 26 territories in sub-Saharan Africa during this reporting period. This number grew significantly to 49 countries by September 21/22 (which will be reported in next year’s Annual Review).
Box 11: Challenging stigma at the country level
Shujaaz Inc completed the ‘Stigma in Youth Project’ in Kenya. Launched in 2019, this project started the purposeful inclusion of persons with disability in Shujaaz Inc’s media campaigns. Shujaaz Inc carried out a GroundTruth study to develop a deep understanding of the issue in general as well as of how it is experienced (understood, perceived, and acted on) by young Kenyans. The study showed that there is a high level of knowledge amongst young people on disability, that young people’s attitudes towards persons with disabilities depend on their visibility in their community and that frequent and positive engagements with persons with disabilities helps to improve attitudes. This fit with the findings from Leonard Cheshire’s Stigma project. With these insights, Shujaaz Inc. successfully rolled out a targeted media campaign. Overall, the Kenyan Stigma in Youth Project reached a total of 2,816,016 young people and engaged a further 144,831 young Kenyans. Shujaaz Inc intend to continue incorporating a disability lens into their media and communications in the future.

In this reporting period, the programme signed contracts with the National Paralympic Committees in Malawi, Ghana and Zambia to support in depth analysis of the perceptions of people with disabilities as a result of the television broadcasts and for delivery of the aligned stigma and discrimination educational programmes in a number of schools.

Table 11: Output 4 VfM
Effectiveness and Efficiency / AT2030 continues to support in-country development and delivery of CCA action plans - both through the CIF, and match-funded programmes established as a result of partnerships developed through the CCA process. This work ensured that CCA recommendations are operationalised to reach people with disabilities through practical solutions.
Economy / CHAI and WHO, AT2030 delivery partners (who delivered the CCAs), used their existing in-country knowledge, experience, and understanding of the data and country information, to support countries to develop and deliver their action plans. This effective and efficient approach reduced time and resources to deliver critical outputs.
Efficiency / A new partnership– bringing UNCIEF into the WHO-led Procurement work, created a substantial multiplier effect for the impact of AT procurement tools. These tools are now part of UNICEF practices and utilise the UNICEF AT Advocates Network.

Describe any changes to this output, and any planned changes as a result of this review.
The timeline for the 2020 Tokyo Paralympic Games is a critical dependency for delivery of output indicators 4.5 and 4.6. As the Paralympic Games were postponed until 2021 due to the impact of Covid-19, so too will delivery targets for these outputs. The logframe was updated to reflect this.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Table 12: Recommendations
(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
Previous AR Recommendations	Progress
AT2030 should consider where these lessons can (a) inform inputs across the range of AT2030 sub-programmes and (b) be adapted, considering the travel restrictions now in place due to Covid-19, to ensure that it continues to deliver outputs of equal value	Despite the significant challenges posed by Covid-19, the programme has delivered strong results against expectations. / Despite Covid-19, AT2030 delivery partners adapted programme delivery, to either facilitate virtual rather than in-person meetings or, with a heavier reliance on in-country partners to deliver on the ground (within local Covid-19 guidelines), with online supervision from a distance. / The 23% reduction in programme budget slowed some activities (although logframe targets were still met). This space provided time for learning and reflection across sub-programmes which has since proved particularly timely ahead of the partial programme re-design required at the start of the 2021/22 financial year (due to further in-year budget reductions of 5% against original forecast, 28% reduction in total).
AR Recommendations for this year
Based on strong progress and reflecting a reduced budget, review the Logframe indicators for this output / (by end November 2021).
SRO and GDI Hub (and partners) should use Paralympic Games as a ‘communications moment’ for the programme, promoting AT2030 internally across FCDO and externally. / (August/September 2021) / There are a number of additional strong ‘communications moments’ in FYs 21/22 and 22/23 for AT2030. SRO and GDI Hub should map and make plans to promote AT2030 and AT generally (internally and externally) through ‘communications moments’. / (plans in place by end November 2021)
SRO and GDI Hub to reach out to FCDO Posts to share CCA outcomes and CIF progress with including details of partnerships in-country. / (by end December 2021)

D: RISK [½ to 1 page]

Overview of risk management
AT2030 is an innovative disability inclusion programme. This has enabled flexibility within the programme - to make a series of investments in new approaches, contexts and/or technologies to ‘fail fast and scale successes’ for a higher rate of return i.e. to reach more people with disabilities, and older people with AT. AT2030’s overall risk appetite and rating remains unchanged as ‘Cautious’ (equates to ‘moderate’ the language used in the previous AR).

The main trends in risk exposure and response over the reporting period were increasingly driven by the impact of COVID-19, including budget reductions and uncertainty. These risks were anticipated to impact mainly on programme delivery timelines. At end March 2021, these were not considered to be ‘severe’, as programme adaptation (using virtual methods and learning from others), and relatively moderate delays were made in most cases. Notable exceptions to this are the work aligned with the 2020 (now 2021) Paralympic Games, the earlier than anticipated conclusion of InnovateNow[19], and in-country stakeholder workshops and follow-ups (such as the one-stop-shops).
[19] Which will nevertheless likely continue with third party funding in 2022

Multiple innovative partnerships carry some reputational risks. The aim of AT2030 is to work with, and test new partnerships. Therefore, the risks of working with/through multiple and new partners, some of whom are new to working with FCDO (and the UK Government) are mitigated by thorough due diligence checks (including safeguarding), and GDI Hub led early and regular conversations and close monitoring, to ensure all partners comply with FCDO’s processes and procedures.

The programme continues to target the most vulnerable populations – people with disabilities who are often older people, to increase their access to AT. Data is, wherever possible, disaggregated by gender and analysed to understand if adaptations are required according to gender and age.

The programme manages risk through established systems to proactively monitor risk on an ongoing basis; i.e. to monitor each risk through FCDO’s risk categories and provide clear risk owners, mitigation actions and timelines. The risk categories detailed here were correct for the review period (1 April 2020 – 31 March 2021).
Figure 8: Risk

At the end of FY 2020/21, the programme team took a snapshot of the programme risk profile based on feedback from delivery partners and project managers (based on FCDO’s previous risk model). Figure 8 summarises the results of this risk assessment. Risk ratings capture an index measure of each risk’s probability and impact on programme delivery, and the diagram details risk profile before and after mitigation actions.

There are effective mitigations in place against the biggest risks – external context – and a balanced risk portfolio overall.

Risks are discussed with FCDO during regular bi-weekly meetings and more formally through quarterly reporting / reviews. No change to risk appetite is foreseen, and in the next reporting period programme management processes across delivery partners will continue to improve the visibility and responsiveness of risk management practices.
Figure 8: AT2030 Risk Profile 2020/21

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
AT2030 leads GDI Hub, regularly engage with FCDO and programme partners throughout the reporting cycle. The GDI Hub provided timely quarterly financial and narrative reports, engaged in bi-weekly catch-up calls with FCDO, provided fortnightly delivery and coordination email updates to all partners (including FCDO) - including highlights and media output – attended formal quarterly review progress meetings with FCDO, hosted quarterly AT2030 Advisory Boards and made substantial contributions to the programme Annual Review including presentation/discussion to/with FCDO.

The financial year end accounts of implementing partners are checked by the GDI Hub and provided to FCDO annually. In 2020/21 GDI Hub was also Audited as part of its commitment to FCDO, including receiving supportive auditor statements in respect of AT2030 fund usage. The programme risk register, delivery chain maps and asset register are maintained and shared with FCDO on request and at least annually.

Programme forecasts and expenditure were managed closely and have broadly been in line with budget. Underspend variance during the first half of the year, as well as budgetary pressure during 2020/21 reduced the total annual budget for the programme from £4.5m to £4.22m. Quarterly and annual programme forecasts are provided to FCDO at the beginning of each quarter and financial year with quarterly updates addressing any changes or variance. The impact of COVID-19 during 2020/21, and related budget pressures within FCDO resulted in the reduction of the AT2030 budget in 2020/21. The programme has managed this change and pressure well, and transparently with all delivery partners. This ensured that during the reporting period (and into next), the programme’s financial management has been robust. The overall AT2030 programme budget of £19.8m remains unchanged.

FCDO has supported programme leads GDI Hub throughout the performance year. With ongoing FCDO support, the programme will continue to grow, build on its successes, particularly with regard to innovative delivery instruments such as the AT Impact Fund, and deliver/disseminate a set of coherent outcomes designed to increase access to AT in developing countries. Ongoing country level co-ordination through FCDO will help to ensure that in-country programme and partner linkages are optimised.

Monitoring activities throughout the review period informed programme risk management discussions, the risk management matrix and programming decisions. Frequent narrative and discursive reviews (as described above) have ensured a high level of programme oversight and monitoring. However, due to Covid-19 travel restrictions, it has unfortunately not been possible for the FCDO SRO or Programme Manager to undertake field visits during this period. These will be prioritised as soon as the situation allows and/or alternative methods of verification considered e.g. in- country third party monitoring and/or working with FCDO colleagues in country to provide feedback on programme activities. GDI Hub provides programme-level risk reporting as part of their Quarterly Reports from all partners, which supports the strategic level risk matrix for AT2030 – shared and discussed with FCDO during quarterly reviews.

Value for Money (VfM) – Economy and Efficiency
See table 13 below.

Table 13: VfM indicators Economy and Efficiency
Economy
AT2030 has a target of 100% match-funding. Currently the programme is significantly ahead of schedule on its match funding targets / AT2030 is delivered by an established partnership of NGOs and academic institutions composed of diverse and complimentary skills. AT2030’s ‘internal skills market’ has driven down the cost of service provision, as expertise can be leveraged through existing programme partnerships instead of buying in expensive consultancy, which has equally driven up programme capability. For example, the provision of world-class research frameworks from UCL and LSHTM are used within country-based pilots delivered by CHAI and WHO. / Inputs for the programme are largely person time, with low programme goods purchases. A large proportion of human resource capacity across the programme is procured through academic partners, and therefore costs are based on academic salary scales. This is much cheaper than comparable quality professional levels procured through consultancy. For example, a senior researcher costs approx. £210 per day through AT2030’s grant structure compared to a (discounted and long-term) service level charge-out rate of £462 for the same level of expert. / Targeting improved wellbeing and livelihoods of people with disabilities, contributes to improved livelihoods and therefore poverty reduction for those at the bottom of the pyramid.
Efficiency
The coordination and collaboration function provided by GDI Hub enables partners to avoid duplication and detect possible programme efficiencies, for example, strategic tools developed through AT2030 for AT procurement are used at the country-level by CHAI (and WHO) in their CCAs. / Dissemination of research findings is supported by dedicated communications capacity and a new communications policy. Due to the size, reputation and reach of partner networks – including universities, industry bodies and global NGOs – dissemination reaches a broad and relevant audience. / The programme is delivered by established partnerships that can leverage a broader range of existing relationships to support programme delivery. / Five AT2030 partners in this reporting period fed-into the upcoming ‘WHO World Report on Assistive Technology’. / Programme leads GDI Hub coordinated and aligned related research on specific research questions to support programme outcomes (i.e. proving ‘what works’). / The development of strategic tools pairs research and idea generation with country and policy focused delivery

Date of last narrative financial report	September 2021	Date of last audited annual statement	December 2021 (forthcoming)

Annex A: Outcome 4 - Breakdown of Match Funding
Match Funding type	Split	Sources include
Cash	£ 8,691,190	International Paralympic Committee / Country Governments in: / Ethiopia / Malawi / Indonesia / South Africa / German Government (to WHO) / USAID / Queen Elizabeth Diamond Jubilee Trust (Commonwealth Eye Health Consortium) / Amparo / UCL UKRI Grants
In Kind	£ 2,168,403	GDI Hub / UCL / LUL / Maynooth University / LSHTM / CHAI: Nigeria, Liberia, Rwanda, Sierra Leone

Annex B: Output 2.1: Peer reviewed / journal and conference papers published
The list of 13 papers developed (against a target of three) during this reporting period (including those featured above) are shown below.
Peer reviewed articles / journal articles published
Paper	Platform / Journal
Estimating assistive product need in Cameroon and India: results of population‐based surveys and comparison of self‐report and clinical impairment assessment approaches	Tropical Medicine & International Health / Volume 26, Issue2, February 2021, Pages 146-158 / https://onlinelibrary.wiley.com/doi/10.1111/tmi.13523
Additive Manufacturing Techniques for Smart Prosthetics Liners	Medical Engineering & Physics Journal / Volume 87, January 2021, Pages 45-55 / https://www.sciencedirect.com/science/article/abs/pii/S1350453320301703?dgcid=rss_sd_all
Bridging the Divide: Exploring the use of digital and physical technology to aid mobility impaired people living in an informal settlement	ASSETS '20: The 22nd International ACM SIGACCESS Conference on Computers and Accessibility October 2020 Article No.: 50 Pages 1–13 / https://doi.org/10.1145/3373625.3417021
Assistive Technology Use and Provision During COVID-19: Results From a Rapid Global Survey	International Journal of Health Policy and Management / https://www.ijhpm.com/article_3954_ec965671ae00a3f198168e08a53dbf21.pdf
Developing inclusive and resilient systems: COVID-19 and assistive technology	Disability & Society / Volume 36, 2021 - Issue 1 / https://www.tandfonline.com/doi/full/10.1080/09687599.2020.1829558
COVID-19 as social disability: the opportunity of social empathy for empowerment	BMJ Global Health / 2020-5 / https://gh.bmj.com/content/5/8/e003039
The Return on Investment and Cost-Benefits of AT Provision	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Methods in Estimating Demand and Supply of AT	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Innovation Strategies and processes to improve access to AT	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Value beyond function: analysing the perception of wheelchair innovations in Kenya	ASSETS '20: The 22nd International ACM SIGACCESS Conference on Computers and Accessibility October 2020 Article No.: 37 Pages 1–14 / https://doi.org/10.1145/3373625.3417017
Inclusion and Independence: The impact of Mobile Technology on the Lives of Persons with Disabilities in Kenya and Bangladesh	IEEE Global Humanitarian and Technology Conference (GHTC), 2020, pp. 1-8. / https://ieeexplore.ieee.org/document/9342934
Disability design and innovation in computing research in low resource settings	The International ACM SIGACCESS Conference on Computers and Accessibility (26/10/20 - 28/10/20) / https://dl.acm.org/doi/10.1145/3373625.3417301
Uncovering unexpected impacts: the case of digital manufacturing of wheelchairs in Kenya	RESNA 2020 Virtual Conference, GAATO/RESNA Assistive Technology Outcomes/Impact Summit / https://www.resna.org/sites/default/files/conference/2020/GAATO/150Barbareschi.html

Annex C: Output 2.2: Influencing papers

Applying Market Shaping Approaches to Increase Access to Assistive Technology: Summary of the Wheelchair Product Narrative https://discovery.ucl.ac.uk/id/eprint/10084646/
Disability, inclusion and cities: can COVID-19 trigger change? https://www.iied.org/disability-inclusion-cities-can-covid-19-trigger-change
Gender and disability in informal settlements during COVID-19: What we have learnt so far https://at2030.org/gender-and-disability-in-informal-settlements-during-covid19.what-we-have-learnt-so-far/
The Politics of Making Disability Visible in Community-led Urban Research https://blogs.ucl.ac.uk/dpublog/2020/02/26/the-politics-of-making-disability-visible-in-community-led-urban-research/
Celebrating International Disability Day in Sierra Leone https://at2030.org/celebrating-international-disability-day-in-sierra-leone/
International Day of Persons with Disabilities in informal settlements in Sierra Leone and Indonesia https://at2030.org/international-day-of-persons-with-disabilities-in-informal-settlements-in-sierra-leone-and-indonesia/
Country Capacity Assessment for Assistive Technologies: Informal Markets Study, Sierra Leone https://www.ucl.ac.uk/bartlett/development/sites/bartlett/files/at2030_dpu_informal_merkets_study_sierra_leone_16_nov.pdf
Country Capacity Assessment for Assistive Technologies: Informal Markets Study, Indonesia https://www.ucl.ac.uk/bartlett/development/sites/bartlett/files/at2030_dpu_informal_markets_study_indonesia_final_16_nov_.pdf
Understanding the impact of COVID-19 on disabled people's daily lives https://www.youtube.com/watch?v=TGnbMIo4hU4&ab_channel=TheBartlettDevelopmentPlanningUnit
AT2030: Community led solutions - Methods & Findings Phase 1 (2019) https://www.ucl.ac.uk/bartlett/development/research-projects/2021/feb/at2030-community-led-solutions
Powering Inclusion: AI and AT. The findings of an online expert roundtable https://at2030.org/powering-inclusion:-ai-and-at.-the-findings-of-an-online-expert-roundtable/
New economics of assistive technology: A call for a missions approach https://at2030.org/new-economics-of-assistive-technology:-a-call-for-a-missions-approach/
Catalysing AT access: Scaling rehabilitative services and increasing access to AT in Kenya https://at2030.org/catalysing-at-access:--scaling-rehabilitative-services-and-increasing-access-to-at-in-kenya/
Summary of Inclusive Design and Accessibility of the Built Environment in Ulaanbaatar, Mongolia https://at2030.org/summary-of-inclusive-design-and-accessibility-of-the-built-environment-in-ulaanbaatar,-mongolia/
An AT Innovate case study: Amparo https://at2030.org/an-at-innovator-case-study:-amparo/
Digital Fabrication of Lower Limb Prosthetic Sockets https://at2030.org/digital-fabrication-of-lower-limb-prosthetic-sockets/
Exploring the experience of persons with disabilities of using mobile technology in their daily lives in Kenya and Bangladesh https://www.disabilityinnovation.com/blog/exploring-the-experience-of-persons-with-disabilities-of-using-mobile-technology-in-their-daily-lives-in-kenya-and-bangladesh
Opportunities and challenges for disability inclusion during the COVID-19 pandemic https://www.disabilityinnovation.com/blog/opportunities-and-challenges-for-disability-inclusion-during-the-covid-19-pandemic
Inclusive Education in Low Resource Settings’ Webinar in February 2021 (UNICEF-led, but aligned to the procurement workshops under AT advocate network). https://en.unesco.org/gem-report/events/2021/webinar-inclusive-education-low-resource-settings
AT Impact Fund: How we do impactful research https://www.disabilityinnovation.com/blog/at-impact-fund-how-we-do-impactful-research
Building the Assistive Technology ecosystem, one coffee at a time https://rhysjwilliams.medium.com/opening-the-doors-of-assistive-technology-one-coffee-at-a-time-181e63a3d14b
Assistive product specifications and how to use them https://apps.who.int/iris/bitstream/handle/10665/339851/9789240020283-eng.pdf
Assistive Technology: What is in a name? https://at2030.org/assistive-technology,-what-is-in-a-name?/
Celebrating Inspirational Entrepreneurs Building Tech that Matters for Africa https://at2030.org/celebrating-inspirational-entrepreneurs-building-tech-that-matters-for-africa/
An Eye for Inclusion: GDI Hub partners with NIUA for global photography competition ‘an Eye for Inclusion” https://www.disabilityinnovation.com/news/an-eye-for-inclusion-gdi-hub-partners-with-niua-for-photography-competition-an-eye-for-inclusion
Co-design workshop exploring inclusive and accessible urban environment in Varanasi, India https://www.disabilityinnovation.com/news/id-workshop-varanasi-india
New 'Innovation Action Insights' podcast launched - episode 1: https://www.disabilityinnovation.com/news/podcast
Mobile-powered employment opportunities for all; up to £20k available for Bangladesh solutions https://www.disabilityinnovation.com/news/mobile-powered-employment
Episode 2 of Innovation Action Insights podcast now live - exploring COVID-19 Innovations https://www.disabilityinnovation.com/news/episode-2-podcast
First ever global guide for assistive technology to improve the life of millions https://www.disabilityinnovation.com/news/first-ever-global-guide-for-assistive-technology-to-improve-the-life-of-millions
Episode 3 of Innovation Action Insights podcast - exploring Sustainability & Circular Economy https://www.disabilityinnovation.com/news/episode-3
New podcast - Innovation Action Insights explores Assistive Technology https://www.disabilityinnovation.com/news/new-podcast-4
What is assistive technology? LSHTM Presentation at ICED conference https://www.lshtm.ac.uk/sites/default/files/2019-11/BOGGS_LSHTM%20ICED%20PENDA%20conference%202019%20FINAL_no%20notes.pdf
What is Assistive Tech, who is it for, and what does it enable? https://www.disabilityinnovation.com/blog/what-is-at
Inclusive Design Research in a Pandemic: Working Remotely in Ulaanbaatar, Mongolia https://www.disabilityinnovation.com/blog/inclusive-design-research-in-a-pandemic-working-remotely-in-ulaanbaatar-mongolia

Annex D: Output 3.2 - AT2030 strategic tools developed to increase AT capacity
1. Disability Medical Assessment Guidelines (Strategic Tool), Kenya
2. WHO rATA Survey and Global Deployment Plan
3. Joint UCL/WHO online AT data repository
4. iN Innovation Toolkit
5. iN Accelerator Programme Curriculum
6. Access to Assistive Technology Benefits All Rate of Return Model
7. ATA-C tool portal
8. AT procurement manual
9. Guide for Writing Descriptive ATA-C Reports
10. Decision framework to Support AT Action Plan Development
11-15. Five ‘product narratives’ which provide market landscaping and strategic approach to increasing access (for eyeglasses, hearing aids, prosthetics, wheelchairs and ‘digital’ products)

Annex E: Output 3.3 – Full list of case studies
1. Inclusive Design and Accessibility of the Built Environment [Ulaanbaatar, Mongolia]
2. Catalysing AT access: Scaling rehabilitative services and increasing access to AT [Kenya]
3. The Liberia Evidence Lab: A new scalable model to deliver School Eye Health [Liberia]
4. Catalysing AT access: A unified approach to fund and provide AT services in Indonesia
5. Access to life changing spectacles for millions. A new vision for KwaZulu Natal, South Africa
6. ‘How mobile operators are driving inclusion of persons with disabilities” case study, documenting digital inclusion initiatives implemented by MNOs and providing recommendations for the digital inclusion of PWDs
7. AT innovation ecosystem design – a Kenyan case study
8. An AT Innovator Case Study: Amparo
9. Applying market shaping approaches to increase access to assistive technology: Summary of the wheelchair product narrative as an illustrative case study
10. Case study: Developing product narrative to guide sector investments behind a unified access approach
11. (4x) Video case studies to showcase role of mobile as an assistive tech for PWD in Kenya and Bangladesh

Annex F: Output 4.3 – Implementation of Country Capacity Assessment (CCA) recommendations
CHAI Sierra Leone
In Sierra Leone, the CCA identified the need for an AT data and information system that can enumerate the actual number of disabled persons within Sierra Leone, as well as their AT needs.  To address this gap, CHAI is supporting the development of the Development Health Information System (DHIS2) that will ensure routine capturing of AT service delivery information for existing national programs.

Another recommendation that came out of the Sierra Leonean CCA was the development of a national AT strategy and AT policy. In response, CHAI is leading the development of a national AT Policy Strategy, inclusive of monitoring and evaluation plans as well as an Assistive Technology Priority Products List (APL).

These documents will guide the Government of Sierra Leone, ensuring that the provision of AT, as well as Sierra Leoneans access to it, is a key priority at a national level.

CHAI Liberia
A challenge identified in the Liberian CCA, was the foundational gaps that currently hinder the ability of Liberia’s health and social systems to deliver AT.  For example, Liberia lacked a coordinated mechanism among its government that could ensure effective implementation of strategies to improve access to AT.  Under Liberia’s CIF grant, CHAI is supporting the government to establish a cross-sectoral technical working group  (TWG) for AT to increase knowledge-sharing, improve collaboration, maximise resources and ensure sustained government ownership over AT activities.

Additionally, Liberia also lacked a national assistive products list (APL) that contained adequate technical specifications for assistive products. In response to another recommendation made in the Liberian CCA, CHAI is working to develop a national priority assistive products list suitable to the Liberian context, that aims to solidify government prioritisation of select assistive products based on population demands, to guide procurement/donations, and to ensure AT is discussed during government supply planning and budgeting.

CHAI Nigeria
One of the priority recommendations within the Nigerian CCA, was to strengthen a coordinated national effort for increased access to AT.  In response to this recommendation, CHAI is working with the Federal Ministry of Humanitarian Affairs, Disaster Management and Social Development to develop a national roadmap aimed at accelerating access to AT that includes a monitoring and evaluation plan that will track progress for coordination of the sector.

Another recommendation from the CCA was to develop sustainable financing for AT procurement and provision. In response, CHAI is working with the Federal Ministry of Humanitarian Affairs, Disaster Management and Social Development as well as state governments to identify innovative financing mechanisms for AT procurement at a national level, and to develop an investment care for inclusion for priority AT into state funding mechanisms for social development.

CHAI Rwanda
For Rwanda, the CCA process identified that there is no centralised data system that can comprehensively and accurately capture information on AT needs, types, causes of disability, service, and product provision. In response, CHAI is supporting the development of a national AT data system in the form of a Disability Management Information System (DMIS) that will inform decision making and policy implementation and support improved data on AT.

Another priority recommendation from the Rwandan CCA was create a coordination mechanism that clearly delineates roles and responsibilities for AT stakeholders and can ensure the implementation of a coordinated AT strategy.  To address this recommendation, CHAI is supporting the National Council for People with Disabilities (NCPD) to revamp the technical working group (TWG) by creating a sub-committee focused on AT that will build evidence and provide guidance to the government on critical areas of policy and regulatory formulation and implementation, including, planning, financing, and M&E.