## Annual Review : 2021/22

Title: AT2030 – Life Changing Assistive Technology for All
Programme Value £ (full life): £19.8m		Review date: 08/2022
Programme Code: 300815-101	AMP start date: 28/01/2019	AMP end date: 01/10/2024

Summary of Programme Performance
Year	1	2	3
Overall Output Score	A+	A+	A+
Risk Rating	Moderate	Cautious	Cautious

DevTracker Link to Business Case:
DevTracker Link to results framework:

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The WHO estimates[1] that 2.5 billion people are in need of assistive technology (AT), e.g. wheelchairs, hearing-aids, prosthetics and orthotics, eyeglasses and digital products. However, 90% do not have access and 80% of those without access live in low- and middle-income countries (LMICS). AT2030, is delivered by a consortium[2] led by the UK based Global Disability Innovation (GDI) Hub, is a global programme testing ‘what works’ to improve access to affordable AT. The programme invests in and supports solutions to scale with a focus on innovative products, new AT service delivery models and global capacity support. By the end of the programme, AT2030 will have reached 30 million people (1 million directly (people), 8 million directly (systemic) and 21 million indirectly[3] [4]) to enable a lifetime of potential through life-changing AT. AT2030 has agreed definitions of programme ‘reach’ with FCDO – the full document is at Annex A.
[1] https://at2030.org/static/at2030_core/outputs/-Scoping-Report_2019-compressed-192.pdf
[2] Includes, Global Cooperation on AT, UCL, CHAI, London School of Hygiene and Tropical Medicine (LSHTM), Leonard Cheshire, Motivation, UNICEF, Loughborough University, Hogan Lovells, Development Planning Unit (UCL), IIPP (UCL), Humanity and Inclusion, GSMA, Eyelliance, Amref Health Africa, Amparo, Microsoft, Kota Kita, Kiran Society, Maynooth University, Associazione Italiana Amici di Raoul Follereau (AIFO), SLURC, Shujaaz, International Paralympic Committee (IPC), Tegsh Niigem, IRCAI, WHO, Brink, Catalyst Fund, 60 Decibels, ATScale, Clinton Health Access Initiative (CHAI)
[3] This is an increase from 2020 Annual Review estimates - from 5 million to 9m people reached directly and from 9m to 21m people reached indirectly (earlier target numbers published in the 2020 AT2030 Annual Review)
[4] Direct (people) - Individuals who participate in AT2030 activities and/or outputs (benefits and inclusion); Direct (systemic) - Groups who benefit from the outputs and outcomes of AT2030 relating to improved provision of AT through policy and system advances, and community- and organisational-level change, including changes in the provision of rights and recognitions and the engagement of people with disabilities in the process; Indirect - Individuals who (likely) do not have direct interaction with the programme, but who could still derive benefit from it. These people can be reasonably identified as included within community/national-level catchment.

AT2030 is an innovative disability inclusion programme, pivoting to build on successes to reach the maximum number of people with AT and its associated services. Programme flexibility is essential - making a series of investments in new approaches, contexts and/or technologies to ‘fail fast and scale successes’ for a higher rate of return, reaching more people with affordable AT.

AT2030 contributes towards the Foreign Commonwealth and Development Office’s strategic priority on science and technology, through supporting innovations to reach scale and develop an evidence base on ‘what works’. Supporting the Leave No-one Behind agenda, current and future FCDO and external programmes can draw on evidence and lessons learned across 35 countries to date, to more effectively support people with disabilities - one of the poorest and most marginalised populations. The programme contributes to sharing UK expertise and UK leadership in innovation and AT through supporting UK based academic institutions (such as University College London (UCL) and Loughborough University); and to diplomacy and development through growing international partnerships[5] and advocacy based on a deepening evidence base to support policy development.
[5] Long lists of partnerships and geographies are detailed under Outputs. Examples of international partnerships include: the International Paralympic Committee (IPC); International Society for Prosthetics and Orthotics (ISPO); the Asian Development Bank (ADB); Associazione Italiana Amici di Raoul Follereau (AIFO, or IDDC, the International Disability and Development Consortium); International Research Centre on Artificial Intelligence (IRCAI) and; the World Health Organisation (WHO).

AT2030 is registered on IATI with the Activity Identifier GB-COH-11126312, and was last updated on 31st March 2022.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This reporting period covers the period from April 2021 to March 2022, in alignment with the programme’s reporting period. In a challenging period that required budget reprofiling and associated programme adjustments, AT2030 met or exceeded expectations against 14/16 Output, 4/4 Outcome and, 2/3 Impact indictors, and delivered a strong value for money assessment, which includes a 100% match funding target. Overall, in this Annual Review AT2030 scored an A+, exceeding expectations. Already the programme has reached 28 million people[6] and captured 13 ‘life stories’ to provide a qualitative interpretation of the programme’s impact.
[6] AT2030 Reach falls into three categories as per the detailed Reach Definitions attached to the programme. In this reporting period AT2030 delivered: 862,408 in Direct Reach (People); 5,046,928 in Direct Reach (Systemic); and 22,487,343 in Indirect Reach. See Footnote (4) for short definitions of reach.

Major lessons and recommendations for the year ahead [1/2 page]

AT2030 is an innovative research programme that works with entrepreneurs, NGOs, Governments, communities and academics to develop, test and deliver new models of ‘what works’ to improve access to AT to the point they have started to reach scale or disrupt markets, with a focus on new products and service delivery models and local capacity. Continued learning and programme flexibility is an integral part of the programme. High level lessons and recommendations are outlined in Table 1 below.
Going into 2022/23 AT2030 will develop a defined approach to address ‘What Works’ to increase access to affordable AT. This piece of work will explore three programmatic datasets: (i) published outputs over the past four years e.g. reports, white papers, peer-reviewed papers etc., (ii) quarterly programmatic reports from programme leaders and (iii) and a survey with inputs from project leads on not only what works but what does not work. The draft interim findings, per cluster, will be reviewed through an in-person consultative workshop to not only validate the findings and to reach consensus regarding the research questions (as a framework to use going forward), but also to gather additional insights that may not have been captured purely from the outputs. The insights gained over the four years of the AT2030 programme, through the ‘What Works’ outputs analysis will respond result in a comprehensive report and more accessible micro-documents, such as Evidence-to-Action Insights, for ease of learning and implementation by sector stakeholders.  A robust dissemination/communication strategy will also be developed.
Table 1: High Level Lessons and Recommendations
(further detail shown under each output)
Cross-programme lessons and recommendations
Lessons	Recommendations
Given the number of beneficiaries reached by the programme, cost-effectiveness Value for Money (VfM) metrics would lend weight to the argument for continuation (or extension) of the programme	Identify and agree cost-effectiveness VfM metrics and present this indicator in the next Annual Review.
Some sub-programmes have concluded, been restructured or require more stretching annual targets	Review logframe indicators and targets by end December 2023
Gender research is a RED and FCDO priority. While the programme has produced some outputs on the differences in access between men, women, boys and girls, this could be prioritised across workstreams	Increased programme focus on gender disaggregation and understanding of the nuances between male and female barriers, challenges and access to AT. / Share the results with relevant stakeholders. / [Be able to demonstrate substantive outputs in the next Annual Review] / Introduce gender targeted AT workstreams and/or continuation of previous gender workstreams / [Implementation underway by June 2023]
(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Lessons	Recommendations
With learning from the programme, review the approach to the ‘Innovation’ cluster of programmes, to assess if this is the most effective programmatic approach for AT2030 to take to build the AT ecosystem and support innovators/ventures from early stage to scale	Review AT2030’s programmatic approach to innovation and share learning on what works. / [By end 22/23] / Where possible (with the funding available) implement any recommendations for changes to the programmatic approach / [By end June 2023]
(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced
Lessons	Recommendations
Outputs are open access and available through various research and data portals however these can be difficult to find.	Ensure research, data and evidence outputs are accessible through the AT2030 website / [By end March 2023]
(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
Lessons	Recommendations
Innovative new tools have been created/developed and tested during the reporting period which can add value through supporting innovators, ventures and ecosystem stakeholders (including governments) to inform decision making. These tools now need to be shared and socialised with stakeholders who can derive benefit from them	Widely disseminate the value and use of AT2030 tools (digital tools in particular – and how to use them), with a targeted stakeholder approach / [By end June 2023]
(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
Lessons	Recommendations
See ‘cross programme learning and recommendations’

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

The Theory of Change (ToC) for AT2030 [Revised] is at Figure 1 below.

Figure 1: AT2030 Theory of Change [Revised, April 2022]

Following the 2020/21 Annual Review (AR) the ToC was revised to better articulate Intermediate and Long-Term Outcomes. The revised ToC also highlights the ‘Inclusive Infrastructure’ Cluster (formerly a Sub-Programme) to better articulate the distinct causal pathway and global influence emerging from this work. Nevertheless, current evidence suggests that the ToC logic still holds, as delivery achievements, (see Figure 3 below –‘outcomes’), remain strong. Additionally, following progress made in achievements against targets in previous years despite challenging global circumstances, targets have again been increased to continue to deliver stretching, ambitious results. The logframe will be revised in the next performance year 2022/23 to reflect the updated ToC.
The 2021/22 Logframe and partner reporting system, tracks impact, outcomes and outputs from all partners on a quarterly basis. Since the beginning of the programme, as a result of strong results achieved against logframe targets, AT2030 set more stretching impact (reach) targets, extending the total number of people reached from 6 million (total) to 30 million (total), increasing the effectiveness of FCDO’s original investment. This breaks down as an additional 4 million people reached directly (to a total of 9 million), and an additional 12 million people reached indirectly (to a total of 21m). An extended programme end date would support the realisation of greater impact, specifically around new approaches, methodologies, ideas and lessons learned to inform increased access to affordable AT.
“Appropriate accessible and affordable assistive technology (AT), including wheelchairs, prosthetics and orthotics, spectacles, hearing-aids and digital devices, is a key enabler for change. AT is critical for inclusion and transformative for people with disabilities and older people. It is an area where UK science and innovation is world leading.

We will bridge the disability divide through mobile and digital technologies that can link excluded people to education, jobs, finance and markets and create opportunities for marginalised voices to be heard.”

FCDO Disability Inclusion and Rights Strategy

Box 1: AT2030 targets people with disabilities in low- and middle- income countries
Wherever possible the programme collects and disaggregates data by age, sex, disability, and geography to increase the learning from the programme and inform future (possibly targeted) interventions. In line with the ‘nothing about us, without us’ tenet, people with disabilities are not only targeted by interventions, but are also meaningfully included throughout the programme cycle, from design through to delivery and monitoring and evaluation (See Box 1).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Impact (reach): Significantly exceeded target
2021/22 Target: Reach 24 million people (total)
2021/22 Achieved: Reached 28.4 million people (total)

Reach	2021/22 Target	2021/22 Achieved*
Direct (People) / of which Research Participation	750,000 / 280,000	862,408 / 390,539
Direct (Systemic)	4,882,150	5,046,928
[Direct total]	[5,632,150]	[5,909,336]
Indirect	18,000,000	22,487,343
TOTAL	23,632,150	28,396,679

Note, a paper outlining AT2030’s definitions of direct (people and systemic), and indirect reach is at Annex A.

* Prior to the recent disaggregation of Direct Reach in early 2022, the programme did not have specific targets against the ‘Direct (People)’ and ‘Direct (Systemic)’ categories; the numbers provided here are imputed from the target set for the original ‘Direct Research’ total.

Impact indicators (1) and (2) on direct and indirect reach were significantly exceeded.

The Reach target increased from 15m (total) target to 29m (total) by the end of the programme, and following this review is recommended to increase again to 30m (total). This demonstrates substantial progress in increasing access to AT and its associated services. Figure 2 show performance against impact and the projected future delivery.

Some examples of this Impact progress include:
- Direct Reach (People) – 11,333 teachers (42% female, 52% male) across Ghana, Zambia and Malawi were trained by the International Paralympic Committee to use the I’mPossible Toolkit (training materials based on the Paralympic values) alongside the Tokyo Paralympics to address disability and stigma associated with use of AT in schools.
- Direct Reach (Systemic) - 95,000 people directly reached across AT2030’s engagement with national Ministries, including through interviews informing the product narratives, ministry capacity building, and direct pilot service delivery (such as the Liberia eye health pilot).
- Indirect Reach - AT2030 Stigma reducing work in Kenya delivers change through positive disability messaging in comics and social media aimed at the Kenyan youth. Supported by a research and monitoring programme, 1.2m people received radio show broadcasts addressing issues of disability stigma through this intervention.
Impact target (3) ‘Number of life stories reflecting AT life-changing impact’ was 14 at end 2021/22. AT2030 achieved 13 life stories and therefore narrowly missed this target. The final impact story for the performance year was not translated into English (from Indonesian) in time for the end of the reporting period.

Figure 2: Impact Performance

Outcomes

Figure 3 show performance against outcomes. All targets are met or exceeded. The blue line outlines targets by end of the programme. The scale of uptake of ideas, new service delivery models and new AT products are now close to or exceeding overall programme targets. Therefore, it is recommended that these targets are increased.

Figure 3: Outcome Performance

Outcome Indicator 1: New Products
2021/22 Target: scaled 9 new products
2021/22 Achieved: scaled 10 new products
This outcome exceeded expectations

This outcome captures progress scaling[7] new AT products (e.g. physical/software tools or devices) and AT-related product innovations, or existing AT products (e.g. physical/software tools or devices) and AT-related product innovations used in new ways to enable increased access.
[7] An outcome can stretch across a number of activities and outputs i.e. including from ‘InnovateNow’, the ‘AT Impact Fund’, and ‘Spark Innovation’. ‘Scale’ is assessed using realistic ambitions for progress over the venture/product/innovation’s 1-2 years of programme support. For example, AT2030 traces the impact of ventures which have gone through InnovateNow’s 12-week programme to measure progress over time; ‘Spark Innovation‘ combines an assessment of broader organisational relationships (e.g. Motivation, Humanity & Inclusion) from a baseline onwards.
[Note, these may be linked to an AT Venture, but they are differentiated as the product/service itself (the 'what'), rather than the operational and delivery service model (the 'how').]

Examples from this reporting year include:
- Koalaa’s develops and tests affordable upper limb, soft prosthetic for the Sierra Leone market (funded through AT2030’s AT Impact Fund[8]), has now fitted 21 prostheses (in Sierra Leone) during 10-day mission and as a result, a Memorandum of Understanding (MoU) has been agreed with Swiss Limb and Sierra Leone’s Ministry of Health and Sanitation (MOHS) to (i) provide training to employees of the National Rehabilitation Centre for prosthetic fitting and to roll out the ‘Limb Buddy’ service - to support patients and collect feedback; (ii) provide shared access to Koalaa’s database of users fitted in Sierra Leone, for the Ministry of Health and Sanitation, Clinton Health Access Initiative and Koalaa, to maximise the number of users on the service; (iii) provide a commitment from Koalaa to working with the MOHS to secure funding for a low-cost service for functional upper limb prostheses to people in Sierra Leone; and (iv) track outcomes, work together and publish data collected. This project was supported by research with ‘Legs 4 Africa’, ‘Leonard Cheshire’, and ‘Elizabeth Hope Foundation’, which will be published in the next reporting period.
  [8] The AT Impact Fund was launched in April 2020 to facilitate the growth of the AT ecosystem by combining grant capital with venture-building (bespoke and sustainability-focused) support to help AT innovators launch and scale solutions.
- InnovateNow[9] Venture and Cohort 4 Winner, SarafriSeat, further developed their low cost, all-terrain wheelchair, through new partnerships with the International Committee of The Red Cross in Niger and with the Inclusionaries lab to explore how employment opportunities can be facilitated for wheelchair users in low-resource settings. This work resulted in the development of the 'SafariCart' wheelchair attachment for transporting and vending goods.
  [9] ‘Innovate Now’, was AT2030’s AT eco-system accelerator, the first of its kind in Africa. Norad has funded the accelerator since January 2022 i.e. from cohort 5 onwards.
Outcome Indicator 2: Ventures
2021/22 Target: 24
2021/22 Achieved: 26
This outcome exceeded expectations

This outcome describes AT ventures that demonstrate substantive progress to critical sustainability milestones as a result of AT2030 support. Examples include: improved product development methods, development of robust evidence proving the validity of solutions, acquiring commercial, distribution and/or service links with relevant national and international partners, demonstration of funding or user base increases, or successful implementation of business plans. ‘Ventures’, describes the business organisation and surrounding ecosystem to support AT innovation.

[Note: This is distinct from Outcome 1, ‘Products’, which focuses on specific AT innovation products and their journey from development to scale. In the first half of AT2030 there is some overlap with AT Ventures supporting AT Products (with both counted in each results chain), however these metrics and chain, do and increasingly will also diverge hence the separation in Outcome types.]

Examples this reporting year include:
- Vinsighte Visis, a digital health venture (smart reading glasses) aids the visually impaired to read books conveniently by converting text to audio input has had multiple successes since graduating from InnovateNow. This includes being awarded the 1st prize (and €40,000) for the Orange Corners Nigeria Incubation program, becoming a finalist for the competitive Cisco Global Problem Solver award 2022, emerged as one of the first 10 Solv[Ed] Innovators, 2022, and emerged as the overall winner of the ICT4Inclusion challenge 2021 and Collaborate Lagos during @artoftechnologylagos. These further awards bring both investable capital, visibility, partnership, often an injections of capacity support, all further the route to scale and later-stage capital.
- ATIF and GDI Hub are working with MiracleFeet to diversify their distribution and revenue streams, exploring a new commercial model for the clubfoot brace to help to subsidise the model for low-income customers (see a short video introduction here). The social enterprise model will help to make the organisation more sustainable and scalable in LMICs. The model was piloted in Nigeria (with a view to expanding to around 66 new geographies), and Miraclefeet completed a Memorandum of Understanding (MoU) with OADCPH (African Organisation for the Development of Centres for People with Disabilities, also an ATIF recipient) to support wider distribution in West Africa. The United Nations Children’s Fund (UNICEF) are also in the pipeline of partnerships to be established (likely 22/23). MiracleFeet also completed the design of their Patient Survey, launched training for Nigerian distributors and created a new website.
- ATIF supported hearX to test a new business model in Kenya (see a short video introduction here). This included testing a subscription payment model and distribution partners to extend reach. hearX fitted 18 hearing aids with 19 customers completing a 6-week hearing aid program, completed Kenyan medical device registration and established a distribution partnership with Ilara health. They were awarded the Best IoT (Internet of Things) Healthcare Wearable Device award and published an insights article on Hearing care by community health workers using digital technologies.
- ATIF Venture Wazi completed an open call for African designers and artists. They received 115 submissions, reached over 150 artist cooperatives, universities and fashion designers across Africa and featured in 14 press releases, including interviews on CNBC and FOX Africa. See a short introduction video here. A strategic partnership was established with UK-based glasses manufacturer Cubitts, and the expanded Wazi team established a workshop in Uganda. Wazi (founded by two female Ugandan entrepreneurs) are the first company to manufacture locally designed prescription glasses frames in Africa.

Outcome Indicator 3: Ideas
2021/22 Target: 25
2021/22 Achieved:39
This outcome significantly exceeded expectations

This outcome captures the uptake of programme Ideas, findings and methodologies when there is evidence that they have been adopted by governments or organisations.

Examples this reporting year include:
- ‘Universal Progress’ and the ‘BASIIC programme’ are applying AT2030 Inclusive Design methodology in their research. This outcome was as a direct result of outreach associated with the Mongolia Inclusive Built Environment Case Study.
  Figure 4: Zambia’s National Paralympic Committee promoting the I’mPossible toolkit
- The uptake and use of the AT2030-supported I’MPossible toolkits (training materials based on Paralympic values) for teachers in Zambia and Ghana. See Figure 4.
- Five additional national governments (13 national country governments cumulative[10]) implemented Assistive Technology Capacity Assessment (ATA-C) recommendations (Bolivia, Dominican Republic, Mongolia, Tajikistan, Viet Nam)
  [10] Bolivia, Dominican Republic, Ethiopia, Mongolia, Liberia, Iraq, Malawi, Nigeria, Rwanda, Sierra Leone, Tajikistan, Uganda, Viet Nam

Outcome Indicator 4: Delivery Models
2021/22 Target: 9
2021/22 Achieved: 9
This outcome met expectations

This outcome captures the use of AT2030 frameworks and approaches to guide the design, development, deployment, operation and retirement of AT services. Models may include any of the following: (i) Communicating the service offerings and products (ii) Identifying and prioritising demand for capacity development services (iii) Determining the appropriate level and methodology for service delivery (iv) Identifying potential partnership opportunities (v) Resourcing capacity development initiatives and/or (vi) Delivering services.

Examples this reporting year include:
- ATIF Venture, OADCPH through it’s learning of what works has expanded its service delivery to Kenya through a Memorandum of Agreement with Association for the Physically Disabled of Kenya (APDK). OADCPH facilitate access to quality AT and related services through a lower cost distribution model, that includes rehabilitation professional capacity development and the provision of technical support to rehabilitation centres in Africa.
- Towards the end of previous reporting period, AT2030 partner CHAI, working alongside other national stakeholders, used previous learning to facilitate the upgrade of the Addis Ababa Prosthetic and Orthotic Center into a National Comprehensive Rehabilitation Centre. The Centre now offers a full range of services, including physiotherapy, mobility devices (crutches, braces, wheelchairs, etc), and custom-fitted prosthetic limbs and orthotic leg braces, and is also a hub for training medical professionals. This year, the government allocated approximately £720,000 to improve facilities and service delivery.
Match Funding:
See Figure 5. AT2030 will deliver 100% match funding in cash or in kind. As at end of March 2022, the programme had raised nearly £14m in match funding against a target of £13m. Examples are included in the Output section below.
Figure 5: Match Funding Progress

Monitoring, evidence and learning – Inclusion
AT2030’s AT products and ventures are driven by the needs of people with disabilities and new service delivery models are focussed on the needs and priorities of stakeholders, including Disabled People’s Organisations (DPOs), and beneficiaries. Programme research prioritises beneficiaries and stakeholders from an ethics and inclusion perspective. Policy makers, NGOs, and DPOs are directly targeted for dissemination, learning and uptake to optimise impact and sustainability.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on programme outputs, outcomes, impact (14/16 Outputs, 4/4 Outcomes and, 2/3 Impacts targets met or exceeded expectations) and a strong value for money assessment, including a 100% match funding target, the programme continues to deliver strong results, good value for money and should continue. Disability inclusion is an important part of the Leave No One Behind agenda with growing global momentum. Without deliberately targeting people with disabilities, it will not be possible to achieve the SDGs.

AT2030 leads, the UK’s GDI Hub provide FCDO with a strategic and competitive advantage as UK leaders in AT science and technology innovation, underpinning the UK’s Science and Technology priorities. Continuing to increase access to AT for people with disabilities is a commitment in FCDO’s 2022 Global Disability Summit action plan. AT2030 is strongly aligned to the delivery of FCDO Disability Inclusion and Rights Strategy: 2022 to 2030 in particular the first ‘Enabler for Inclusion’ - Assistive Technology. GDI Hub, lead delivery partners for AT2030, were awarded the world’s first ‘WHO Collaborating Centre on AT’ status based on the achievements of AT2030.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]
Output Title	(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Output number:		1	Output Score:	B
Impact weighting (%):		26	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of innovative ATs supported	23	30 / Exceeded expectations
1.2 Establishment of Innovate Now’s (IN) accelerator programme and number of cohorts run	Established (5 cohorts)	Established (4 cohorts with FCDO funding) / Narrowly missed target* / *FCDO funding for InnovateNow was stopped during the reporting year due to budget reductions. This target should have been reduced to 4, but this was missed in error
1.3 Number of AT Impact Fund (ATIF) Investments	6	5 / (A decision was taken to pivot the programme (agreed with SRO) after one investment withdrew during due diligence checks. / With the inclusion of the programme pivot (implemented before the end of Mar 22), this indicator target is considered to be met) / Nearly met

NB. the indicators above are cumulative milestone indicators

[Note: Output 1 describes the development of AT products or services themselves to a point where they have been user tested and are ready for market (i.e. Output markers). These are differentiated from outcomes, which evidences their path to scale and sustainability, through the specific Outcome markers of: investment, partnerships, agreements, successful pilot programmes etc.]

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

This output captures AT Venture support through two main instruments – the AT Impact Fund (ATIF) for mid-stage ventures and InnovateNow for early-state entrepreneurs/innovators.

The programme exceeded the number of AT supported, however faced challenges with funding for the final Cohort of InnovateNow (due to FCDO funding reductions). A fifth cohort was due to be established with match funding from Norad during 2021/22, however with delays due to the contracting process, this cohort will now begin (and complete) in 2022/23. One ATIF grantee did not pass due diligence. It was agreed with FCDO’s SRO to only onboard five investments and instead pivot the programme to provide additional venture building and capital support to the existing investments. This Output is therefore considered to be on track, albeit adjustments must be made to the logframe.

  1. Number of ATs supported
2021/22 target: 23
2121/22 achieved: 30
Exceeded expectations

11 new innovative ATs (see Table 2) were supported during this reporting period (bringing the cumulative total to 30). These comprised of innovations from the fourth InnovateNow cohort, three new ATIF investments (two investments were included in the AR for 2020/21), and support offered through University College London’s (UCL) new ‘Systems Strengthening: Local Production Systems of AT’ project.

[Note: The innovative ATs supported under InnovateNow cohort 5 (onwards), funded by Norad will not be counted in future AT2030 Annual Reviews]

Table 2: Output 1.1 – Supporting Innovative ATs
Sub-Program	Organisation/ Country	AT Innovation
Innovate Now / [Kenya]	Veezaviz [formerly Sekani]	Veezaviz (Kenya) is a social enterprise developing leading-edge technology-based solutions to address the accessibility and communication barrier for people with hearing impairments. InnovateNow supported ‘assistALL’, which provides flexible Sign Language interpretation services at lower cost.
Innovate Now / [Nigeria]	One Networking	One Networking (Nigeria) provides safer mobility enhancements for the elderly and the visually impaired such as the Visually Impaired Electronic Walking Guide (VIEW Guide) among other assistive technologies.
Innovate Now / [Kenya]	The Accessibility Institute Ltd	The Accessibility Institute Ltd (TAI) developed the first truly off-road manual wheelchair designed and made in Kenya, not only providing mobility but also helping mobility impaired people to live fully inclusive lives.
Innovate Now / [Nigeria]	Vinsighte	Vinsighte (Nigeria) is a digital health venture (smart reading glasses) that makes use of technology to aid the visually impaired to read books by converting text to audio.
Innovate Now / [Kenya]	Ace Mobility	Ace Mobility (Kenya) provides safe, reliable, and affordable mobility solutions to underserved persons like the people with disabilities, so as to improve their social and economic participation.
Innovate Now / [Kenya]	Batian	Batian (Kenya) is an e-commerce start-up helping digital workers combat eye strain with affordable eyeglasses. With feedback from InnovateNow’s ‘live labs’, the team decided to pivot to a microfinance driven e-commerce distributor for AT (FIGA), to facilitate pay as you go and consumer credits to unlock business to customer (B2C) affordability. In the reporting year, the company was not able to execute their plan however due to lack of team capacity, however continues to sell eyeglasses and frames, and plans to relaunch next year.
Innovate Now / [Kenya]	Project Circleg	Project Circleg is developing the Circleg lower-limb prosthetic system for above-knee and below-knee amputees. It is made from reinforced and certified recycled plastic, creating lightweight, high-quality and comfortable prosthetic components.
AT Impact Fund / [Togo]	OADCPH	OADCPH facilitates access to quality AT and services through a lower cost distribution model, rehabilitation professional capacity development and technical support to rehabilitation centres in Africa. ATIF is working with OADCPH to digitise the logistics and sales operations and to test and replicate the entire business model in East and Southern Africa, setting up operations via a distribution centre in Kenya.
AT Impact Fund / [Nigeria]	MiracleFeet	MiracleFeet are bringing a non-surgical AT method of treatment to LMICs which is routinely provided in advanced health systems. ATIF is working with MiracleFeet to support the diversification of their distribution and revenue streams, exploring a new commercial model for the clubfoot brace which could help to subsidize the model for low-income customers. The social enterprise model will help to diversify income and make the organisation more sustainable and scalable.
AT Impact Fund / [Sierra Leone]	Koalaa	An easy to fit, affordable, stylish and functional soft prosthetic solution, which has been made, distributed and used in the UK to date. Through a collaborative design process with local partners, Koalaa has extended the design of the prosthetic solution for the needs of upper limb users in Sierra Leone and for use across the African continent. ATIF is working with Koalaa to test and validate a business model for sustainable scale, establishing an end-to-end service from manufacturing to fitting, ongoing care and maintenance of the limb in urban and rural Sierra Leone.
Innovate Now / [Kenya]	Makerko	A 'Web of Production' Platform that connects local Makers and Users to build collaborative projects. With Makerko, users can build their portfolio, share their production capabilities, material, pricing and innovative projects. AT2030 is working with Makerko to identify and attach AT specialist skills to existing engineering capacities to enable local AT innovation and specialist third party services.

  1. Establishment of InnovateNow’s Accelerator Programme and Number of Cohorts Started
2021/22 target: 5
2121/22 achieved: 4 with FCDO funding + 1 with Norad funding
Nearly met expectations

GDI Hub and Kenyan partner Amref Enterprises onboarded six new assistive technology start-ups into the Cohort 4 InnovateNow accelerator program. Cohort 4, launched on 25 May 2021, with each start-up matched with 2 mentors and participation in a 6-week curriculum aimed at accelerated learning and gathering evidence for what works so that they can quickly navigate the start-up ‘valley of death’ (and see diagram 6 below) toward growth and scale. The accelerator provided the ventures with the foundations for success through eight development lectures including on the essentials of entrepreneurship, understanding the product user, market and product. At the close of the 6-week curriculum, the Cohort 4 Demo Day was held on 14 September with the winning project awarded to ‘The Accessibility Institute’ for their ‘Safariseat’ innovation.

Due to impacts of COVID-19, 14 start-ups that comprised Cohorts 1, 2 and 3, were also able to undergo Live Lab activities alongside Cohort 4. Activities for the live labs included consultative meetings, brainstorming sessions, and planning meetings as well as reviews and analyses of the various meetings/activities.

The remaining Cohorts (5, 6 and 7) will be funded by a third-party donor (Norad) as they take on overall financial support for InnovateNow within a new project building on the successes and lessons of AT2030.

  1. Number of AT Impact Fund (ATIF) Investments
2021/22 target: 5
2021/22 achieved: 4 (one investment withdrew during due diligence and SRO agreed to a programme pivot, i.e., to provide additional funding to existing investments that met specific criteria. Therefore, it is considered that expectations have been met for this output. This target should have been changed but this was missed in error)
Met expectations

Figure 6: AT Impact Fund Approach
The Assistive Technology Impact Fund (ATIF) uses AT2030 funding to support innovative assistive technology solutions, focusing on scaling affordable products and services for persons with disabilities in low and middle income countries (LMIC). The fund invested in ventures that improve access to mobility aids, hearing devices, and digital assistive tools.
2021/22 was the main delivery year for the ATIF. The programme completed the onboarding of the three final ventures (OADCPH, MiracleFeet and Koalaa) alongside the original two (HearX and Wazi). The ATIF also contributed to both Outcome 1 and Outcome 2, through the scaling of specific AT products alongside progressing the sustainability of specific AT ventures.
The ATIF is a research and learning instrument, and through this, AT2030 delivered the Opportunity of a Billion Webinar Series[11], published blogs on how ATIF ensures impactful research using three approaches: mixed methods, multi-perspective and regular measurements (more information is here), published an externally conducted Impact Report on ATIF venture MiracleFeet (Full report), and produced an interim report entitled ATIF Fundraising & Ecosystem Building: What did we learn? Ecosystem stakeholder interviews to support the final research report will take place in the next reporting period.
[11] Opportunity of a Billion Webinar Series: access the recording of session1 (here) and session 2 (here)

Finally, funded through ATIF and continuing within AT2030 more broadly, the AT Inclusive Tech and Ecosystem map was launched, which lays the foundation for further AT innovation mapping in future years.

As one venture failed to meet due diligence requirements, with the agreement of FCDO’s SRO, the remaining ATIF resources were refocused to support existing ventures with a small amount of further support i.e. replicating the success of the MiracleFeet Impact Report.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

It is proposed to replace OP1.2 and OP1.3 targets (which correspond to InnovateNow and ATIF respectively) with a future-proofed target focused on the ‘Number of Innovation Ecosystem development interventions’. Informed by ongoing programme learning, AT2030 will improve (and change) delivery approaches to support innovation ecosystem acceleration.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Table 4: Output 1 Recommendations
(OP1: INNOVATION) Innovation Ecosystem established with acceleration programme
Previous AR Recommendations	Progress
Based on updated annual budgets and achievements to date, review logframe targets by end October 2021: / Output 1.1 / Output 1.2 / Output 1.3 / Consider adding an output 1.4 on fund raising for the ATIF	Complete - Targets have now been reviewed (albeit late for this Annual Review) and selective uplifts proposed. / Research now tells us that fundraising for a vehicle of this type and stage is not possible until the market itself is more mature. This recommendation has been superseded by the development of GDI Hub’s Accelerator (GDIA, based on programme learning, bringing the two existing innovation vehicles into one).
Learn lessons from ATIF to refine and adapt future approaches and to contribute to our understanding of the AT ecosystem (by end March 2022). / Document and disseminate findings through report(s) (by end June 2022) and a series of webinars beginning in November 2021.	In Progress - four webinars were completed, with a fifth planned once all learning has been published. Programme learning has resulted in the development of a new approach. / Research outputs such as a final webinar, and a report arising from ATIF will launch during 2022.
2021/22 Learning	Recommendations
With learning from the programme, review the approach to the ‘Innovation’ cluster of programmes, to assess if this is the most effective programmatic approach for AT2030 to take to build the AT ecosystem and support innovators/ventures from early stage to scale	Review AT2030’s programmatic approach to innovation and share learning on what works. / [By end 22/23] / Where possible (with the funding available) implement any recommendations for changes to the programmatic approach / [By end June 2023]

Output Title	(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced.
Output number:		2	Output Score:	A++
Impact weighting (%):		24	Weighting revised since last AR?	N/A

NB. the indicators in the table above are cumulative milestone indicators
Indicator(s)	Milestone(s) for this review	Progress
Number of peer reviewed journal/conference papers published	20	34 / Substantially exceeded expectations
Number of influencing papers, answering critical research questions published	50	63 / Substantially exceeded expectations
Number of downloads/views for articles/papers above.	31,500	43,024 / Substantially exceeded expectations

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

This has been a particularly strong output for AT2030 during this reporting period. Across all indicators in this output, AT2030 has substantially exceeded expectations. The programme continues to produce high quality academic and influencing papers, notably feeding in over 100 peer reviewed papers and influencing papers to inform WHO’s Global Report on AT (and launched in the UK at the Houses of Parliament by the Rt Hon Penny Mordaunt MP in early 2022/23). The number of downloads and views have exceeded expectations, likely due to in part to outreach efforts.

Output 2.1: Number of peer reviewed journal and conference papers published
2021/22 target: 20
2021/22 achieved: 34
Substantially exceeded expectations

The boxes below, highlight examples of work completed under this output. A full list, including links to the papers and articles is at Annex B.

During the reporting period a substantial amount of research and analytical work was completed. Some of the common research themes included:
- Assistive Technology Innovation and Sustainability
- AT, Participation and the Impact of COVID-19
- Companion Papers to the Global Report on Assistive Technology

Core academic partners within AT2030 include: UCL, Maynooth University, Loughborough University, and the London School of Hygiene and Tropical Medicine (LSHTM) alongside discrete individual inputs from: the Institute of Innovation and Public Purpose (UCL), National Institute for Urban Affairs (NIUA) India, Nosaal Institute (University of Melbourne), The Hong Kong Polytechnic University, Universidad de Chile, University of Malawi, University of Nairobi, University of Pittsburgh, University of Salford, University of Sao Paulo (USP), and University of Southampton.

Box 5: “When They See a Wheelchair, They’ve Not Even Seen Me”—Factors Shaping the Experience of Disability Stigma and Discrimination in Kenya
UCL, Shujaaz Inc. and Streetwise Opera

“Disability stigma in many low- and middle-income countries represents one of the most pervasive barriers preventing people with disabilities from accessing equal rights and opportunities, including the uptake of available assistive technology (AT).”

For the AT sector this is relevant because previous studies have rarely examined how disability stigma may be shaped through factors endemic to social interactions, including how the use of assistive technology itself may precipitate or alleviate disability stigma. Through two strands of work, this gap is addressed via the identification of shared and divergent understandings of what shapes disability stigma and discrimination.

Kenyans with and without disabilities were cognisant of how religious/spiritual interpretations of disability, conceptions of impairments as “different” from the norm, and social stereotypes about (dis)ability shaped the experience of stigma and discrimination. Moreover, both groups highlighted assistive technology as an influential factor that served to identify or “mark” someone as having a disability. However, whereas participants without disabilities saw assistive technology purely as an enabler to overcome stigma, participants with disabilities also noted that, in some cases, use of assistive technologies would attract stigma from others. ATs can work as a constant visible mark of disability that can attract unwanted attention and occasionally be seen as more important than the person with disability who is using them.
Box 6: Could Assistive Technology Provision Models Help Pave the Way for More Environmentally Sustainable Models of Product Design, Manufacture and Service in a Post-COVID World?
GDI Hub, UCL and LSHTM

“We examine whether Assistive Technology (AT) provision models could look towards more sustainable approaches, and by doing this benefit not only the environment, but also address the problems that the current provision systems have.”

For the AT sector this is relevant as it identifies intrinsic links between disability inclusion and the climate crisis, and the particular vulnerability people with disabilities face in its wake. Localised circular models of production could be beneficial, facilitating context driven solutions and much needed service elements such as repair and maintenance.

There are distinct parallels between what AT provision models require to improve equitable reliable access, and strategies that could reduce environmental impact and bring economic benefit to local communities. This could allow future AT ecosystems to be key demonstrators of circular models, however further exploration is required. What is key in all respects, moving forward, is aligning AT provision with sustainability interventions.

Box 7: Meeting AT needs in humanitarian crises: The current state of provision
UNICEF, UCL, and GDI Hub

Humanitarian coordination systems increasingly recognize and aim to respond to the needs of people with disabilities within populations affected by crises, spurred on by the UN Convention on the Rights of Persons with Disabilities (CRPD) which was adopted in 2006.

For the AT sector this is relevant because there is very little evidence of AT provision in humanitarian settings, which is a specific and urgent need for many people including the elderly and people with disabilities, and an implicit requirement of Article 11 of the CRPD and World Health Assembly resolution on improving access to assistive technology. There is also little evidence of effective mechanisms for AT provision in humanitarian settings. This is despite high and growing levels of unmet AT need in crises, and despite the legally binding requirement in the CRPD. The small body of academic literature that describes AT provision in humanitarian settings paints a picture of small-scale provision, specialized to single types of impairments, and delivered by predominantly by NGOs. While gray literature from Afghanistan and South Sudan provided supplementary evidence of the types of AT providers and AT provision available in protracted crises, there are very few examples of how AT services can be scaled up (from a very low baseline) and maintained sustainably within a strengthened health system. The literature also describes more examples of provision of assistive products for mobility over assistive products for other impairments. If the paucity of literature on AT provision in humanitarian settings is a reflection of the scale of provision, this implies a deficiency in humanitarian response when it comes to providing people with AT needs with the essential products and services to which they have a right, and which will enable their access to basic, life-saving assistance.

Recommended next steps are: (1) develop an AT Provision and Coordination Framework for humanitarian systems that includes, information on met and unmet need, demand, barriers and enablers to access AT in a range of humanitarian settings; details of interagency responsibilities for AT provision and humanitarian coordination for AT provision for different models; and details of minimum standards for how interagency responsibilities should be enacted, based on evidence of best practice that considers the varied needs of all groups with AT needs. (2) Explicit incorporation
Box 8: ‘meeting AT needs in humanitarian crises’, continued and ‘Introduction to the companion papers to the global report on assistive technology’

of assistive products and services into emergency preparedness planning and humanitarian response. (3) Establish a multi-stakeholder taskforce to take forward the recommendations and to build the capacity of humanitarian actors.

Introduction to the companion papers to the global report on assistive technology
Special Issue of ‘Assistive Technology’

If accessible, assistive technology would be life changing for a billion people across the world today – and two billion people in 2050 (WHO, 2018). It would make the difference between independence and dependence, inclusion and exclusion, life and death. It holds the potential to improve and transform health, education, livelihood and social participation; fundamental human rights everyone is entitled to. And if we are lucky to grow old, the chances are that we all would use assistive technology by then. But do we care?

Despite having been on the international agenda for generations, it is estimated that only one in ten people have access to the assistive technology they need (WHO, 2018). Is it an insurmountable challenge to improve this situation? No, it is not. As the starting point is very low, every percentage is an important improvement.

States are increasingly embarking on a journey to develop or strengthen their assistive technology systems. To inspire and support this movement, and in response to the World Health Assembly resolution (WHO, 2018), WHO and UNICEF are currently developing the Global Report on Assistive Technology (GReAT) set to be launched in 2022. Based on existing and new evidence, it will provide an overview of the assistive technology scenario in the world and recommend stakeholder-specific actions to improve the access to assistive technology.

GReAT gives us a window of opportunity to do something for the sake of hundreds of millions of people in our generation who still cannot access basic assistive technology, as well as for coming generations. Aiming for including assistive technology in Universal Health Coverage, we should not stop until everywhere everyone has the assistive technology, they need to live life to the fullest.

Output 2.2: Number of influencing papers[12] answering critical research questions published
[12] i.e., not peer reviewed / journal articles. Typically published as Policy Papers, Insight Papers or other Programme Lessons
2021/22 target: 50
2021/22 achieved: 63
Substantially exceeded expectations

The boxes below highlight examples of work completed under this output. A full list, including links to the papers is at Annex C.

Box 9: MiracleFeet: The human impact of foot braces in Nigeria and Liberia
ATIF, MiracleFeet and 60 Decibels

“…based on the data and insights in this report, we can say that MiracleFeet are having an overwhelmingly positive impact on the lives of children in Liberia and Nigeria”, 60 Decibels

To better understand and evidence the impact of MiracleFeet's work for children living with clubfoot, ATIF commissioned 60 Decibels to conduct research using specifically designed tools to measure the impact of assistive technology.

- 200 parents and guardians of children receiving MiracleFeet treatment (including MiracleFeet’s clubfoot brace) in Nigeria (39%M; 61%F) and Liberia (43%M; 57%F) were surveyed using the Assistive Technology Impact Measurement survey.
- 98% of children who used the MiracleFeet brace experienced an improved quality of life. Parents and guardians of children using the brace attributed the improvement to their child’s ability to move, stand, play, and forge positive relationships.
- Parents and guardians of children undergoing Miracle Feet brace treatment are highly satisfied and loyal towards the company, with a Net Promoter Score ® (NPS) of 88 (a value which indicates high satisfaction and loyalty, putting MiracleFeet the company, in the top 20%).
In Liberia, MiracleFeet is doing an excellent job at providing clubfoot treatment to children from extremely poor, poor and low-income households. In Nigeria, MiracleFeet is overall providing clubfoot treatment to children from low-income households in Nigeria, though some work could be done to serve the extremely poor.

“He can walk by himself now and he refused for us to hold him. We can leave him at home now and he can move around.” – Mother from Liberia. The bracing intervention has also …

Box 10: MiracleFeet: Liberia and Nigeria (continued) and ‘Preventing lifelong impairment: Access to clubfoot treatment’

… improved the quality of participation and relationships. One mother from Liberia notes that their child is no longer called names which could affect a child’s social participation and self-confidence. The overall improvements in a child’s ability to walk, made possible by the MiracleFeet brace, have also led to improved social participation with fellow children.

Preventing lifelong impairment: Access to clubfoot treatment in low-and-middle-income countries
CHAI and GDI Hub (SP6)

Clubfoot affects 1 in 800 births. Left untreated, it can lead to life-long impairment, impacting participation in society, education, and employment. Most children with clubfoot can be successfully treated with the Ponseti method, a low-cost, cost-effective, and minimally invasive treatment protocol. Despite progress, less than 1 in 5 children born with clubfoot in LMICs currently receive treatment.

The report recommends:
- Policy: Advocate to global and national actors - ministries of health and donors - for the integration and mainstreaming of clubfoot treatment as an essential neonatal and child health service.
- Provision: Develop global guidance and standards on the delivery of clubfoot services and products.
- Personnel: Integrate clubfoot treatment into government led MNCH policies, plans and training curricula for health workers.
- Products: Ensure an adequate supply of all treatment materials – plaster, padding and tenotomy supplies and affordable, quality Foot Abduction Braces in LMICs.
- People: Test, validate, adopt, and scale new solutions and technologies that promote patient-centred care to improve adherence in low resources settings.

Box 11: Assistive Technology in urban low-income communities in Sierra Leone & Indonesia
UCL, GDI Hub, the Sierra Leone Research Centre, the Sierra Leone Federation of the Urban and Rural Poor, Kaki Kota and Kota Kita

According to the World Health Organization (WHO), more than a billion people need one or more assistive products (AP), but only one in ten people have access. While the prevalence of disability and need for AT – which comprise assistive products and their related services – have been documented in general terms, there is little data on low-income settlements in the global south. The findings from the surveys give an insight into disability prevalence and access to AT in five urban low-income communities in Sierra Leone and Indonesia

Mainstream* findings:
- Self-reported disability prevalence (“some difficulty” and above) and severe disability (“a lot of difficulty” and above) is high in the four ‘mainstream’* communities
- The most common impairments reported by participants regard mobility and seeing/vision
- More than half of the older population have a disability
- The findings suggest that there could be a relationship between sex and disability prevalence/access to AT
- AP coverage in mainstream* communities is low among the population in need
- AP variety is extremely low
- Most people get their AP from the informal market
- In the mainstream* communities, AT users are “satisfied” with the quality of the AP they have, and less satisfied with the maintenance and services
- Limited knowledge about APs and AT
HEPPO findings:
- Survey results showed an extremely high prevalence of severely disabled adults with a mobility impairment (29.9%).
- Very high AP coverage (71.4%) among the population in need.
- The most common APs were wheelchairs and tricycles, and most APs came from non-governmental organizations (45.4%).
- Satisfaction with current devices was relatively low

*Four of the sites were selected as ‘mainstream’ settlements of the urban poor. The intention was to understand the need for and access to AT in settlements occupied largely by low-income people without specific provisions for, or a particular visibility of, people with disabilities. The fifth settlement, (HEPPO, Freetown) was a unique case study for researching AT access in Sierra Leone. It is community organised around wheelchair users and people affected by polio.

Box 12: Groundtruth Report
Shujaaz Inc.

Contrary to the general belief that youth in Kenya know little about disability and people with disabilities, the study found that the level of awareness about disability among young people in Kenya is high; moreover, they are able to clearly distinguish between physical and mental disabilities, their causes and manifestations. The attitude and behaviours that youth exercise around Persons with Disability depend on the visibility of people with disabilities to youth and the context in which youth see them; i.e., it is important how often and under which circumstances youth interact with people with disabilities.

Recommendations for a media campaign include:
- It appears that the most effective way for young people to develop positive attitudes towards PWDs has been via normalized, frequent and positive engagements with them as part of their routine lives. Stories of people with disabilities as characters are imbedded in other stories and participate on par with other Shujaaz characters in various daily activities. Creating a separate story focusing on people with disabilities would further highlight their separation from the community.
- Each of the four youth segments in the study require a slightly different approach in the campaign, which can be emphasized via different media channels. E.g. some groups would benefit from traditional comic and radio stories supported by the engaging conversations through social media. For another group, face-to-face engagement with people with disabilities during Shujaaz monthly Konnect events is recommended.
- The campaign needs to address both fully abled and differently-abled youth. It is important to showcase to people with disabilities the way they might be a part in creating the misunderstanding that they are experiencing, and/or what their contribution can be in redefining their role in the community.
- It is important to continue insight-generation activities alongside the main media campaign to gather more nuanced details on youth attitudes, behaviours, perceptions and stereotypes about people with disabilities and disability as well as about the attitudes, behaviours and challenges of people with disabilities within their respective communal contexts.

Output 2.3: Number of downloads/views for articles/papers above
2021/22 target: 31,500
2021/22 achieved: 43,024
Substantially exceeded expectations

AT2030 has been monitoring the number of downloads, views and citations for all programme research papers through metrics taken from ResearchGate, AT2030.org, journal analytics (which are typically shown next to publications) and partner websites (as part of Quarterly reporting). As at end March2022, this indicator substantially exceeded expectations with 43,024 downloads and views, against a target of 31,500.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

AT2030 is producing a substantially larger amount of content (academic and grey literature) than originally anticipated. Data and Evidence (especially the production thereof) is a cross-cutting theme across all Clusters and GDI Hub, as a ‘Research and Practice Centre’ embed research into everything they do. Further, research to build the evidence base is disseminated in various ways i.e. academic journal articles as well as blogs, insights, influencing papers etc. as grey literature. It is proposed that the targets for this Output be increased in consultation with FCDO and programme delivery partners.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Table 6: Output 2 Recommendations
(OP2: DATA & EVIDENCE) Critical Research Questions are answered and methodologies produced. https://at2030.org/impact-stories/
Previous AR Recommendations	Progress
Review the Logframe indicators for this output, focussing on more stretching targets / (by end October 2021).	Done – with further stretch revisions to be proposed following this Annual Review.
GDI Hub should continue to strengthen and streamline the profiling and capture of programme content for ongoing co-ordination and communications planning, leveraging match support from partner organisations where possible / (ongoing, to end programme)	Ongoing – Improved communications support has been set-up. In addition, following the loss of management staff due to budget reductions GDI is rebuilding this capacity which will have a direct impact on content management.
FCDO SRO should work with GDI Hub to focus on outreach within FCDO – connecting and collating emerging lessons (through papers, webinars, social media and podcasts etc) with relevant country based and policy teams / (ongoing, to end programme).	GDI Hub and FCDO’s SRO worked together to share details of the programme with a number of FCDO Post representatives. This will continue for the remainder of the programme. / Advisers were invited to a number of the AT2030 webinars, and content has been shared through social media. This will continue for the remainder of the programme and include a more targeted approach.
Learning	Recommendations
Gender research is a RED and FCDO priority. While the programme has produced some outputs on the differences in access between men, women, boys and girls, this could be prioritised in future studies e.g. pulling together the programme’s existing learning on gender differentiation across research, evidence and data outputs and increasing focus on this in future.	Increased programme focus on gender disaggregation and understanding of the nuances between male and female barriers, challenges and access to AT. Share the results with relevant stakeholders. / [Be able to demonstrate substantive outputs in the next Annual Review]
A high volume of research, evidence and data has been produced by the programme. However, it is not always clear where the linkages are between these outputs, and with broader programme outputs, i.e. how the research is informing/has informed progress and decision making across the AT2030 programme	Make stronger links between research, data and evidence outputs and how/where they support broader programme outputs, outcomes and impact e.g. through some impact tracing and/or through the programme’s website / [By end June 2023]
Outputs are open access and available through various research and data portals however these can be difficult to find.	Ensure research, data and evidence outputs are accessible through the AT2030 website / [By end March 2023]
AT2030 has surpassed logframe targets during this reporting period	Agree stretch logframe targets / [By end December 2022]

Output Title	(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
Output number:		3	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of partnerships supported to increase AT capacity.	70	85 / Substantially exceeded expectations
Number of strategic tools developed to increase AT capacity	55	63 / Exceeded expectations
Number of case studies produced (including from: Inclusive Infrastructure and Sport against Stigma).	17	17 / Met expectations
Value of matched funding provided through partnerships	£13,000,000	£13,868,221 / Exceeded expectations

NB. the indicators in the table above are cumulative milestone indicators.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

This output continues to be a strength for AT2030 leads, the GDI Hub. AT2030 has substantially exceeded expectations during the reporting period. With 85 partnerships[13] contributing to programme delivery, the programme excels at working with a variety of organisations to maximise its outputs. See Figures 6 and 7.
[13] A partnership is described as the participation of a (registered) organisation in the delivery of one or more of AT2030's activities. The GDI Hub has sub-contracts/MOUs with some partners but not all. These partnerships include those with 'beneficiary partner organisations' such as local governments in cities where inclusive infrastructure programming occurs.

Match funding success is reported in Figure 5, Section B of this Annual Review, and all the Strategic Tools and Case Studies produced by the programme in this reporting period are listed below.

3.1 Number of partnerships supported to increase AT capacity
2021/22 target: 70
2021/22 achieved: 85
Substantially exceeded expectations

The number of partnerships formed through AT2030 has been significantly greater than originally anticipated during programme design. The programme has now involved 85 organisations globally (summarised in Figure 6), 22 of which are UK based innovation partners who are working in and with LMIC. These global partnerships also reflect the diversity of the programme in terms of organisation types from the private sector, NGOs, governments, universities and hospitals, as shown in Figure 7.

Figure 6: Partnerships by country

Figure 7: Partnerships by Type

3.2 Number of strategic tools developed to increase AT capacity
2021/22 target: 55
2021/22 achieved: 63
Exceeded expectations

AT2030 added a further 13 ‘strategic tools’ against this year’s target of five. Table 7 details the full list of strategic tools developed. Many of these tools, such as the AT innovators map, AT data repository and innovators toolkit, will continue to be developed by the programme through buy-in across the AT sector and are supported by the recommendations of the 2022 Global Report on AT.

Table 7: Strategic Tools
Tools	Link
Assistive technology innovators map across emerging markets / This AT map is the first-of-its-kind visualisation of key innovators and stakeholders in the assistive technology and disability innovation ecosystem across emerging markets. The map puts a spotlight on the different types of digital tech-driven and inclusivity-focused startups and organisations that are creating state of the art solutions for people with disabilities in Africa, Latin America, the Middle East and Asia from prosthetics to digital sign language software. As one of the most underexplored and nascent spaces in the tech-scene globally, the AT landscape is beginning to show business viability and attract funding, investment and resources.	https://at2030.org/at-innovators/map/
Joint UCL/WHO AT data repository online* / *While this was created in the previous reporting period it has been substantially developed during this reporting period. It is however not counted as one of the 13 new tools. / The aim is to reduce data gaps and increase knowledge sharing in the AT sector, supporting evidence-based decision-making at policy-level and improving access to information for AT entrepreneurs. Currently, 207 population-based studies included in the Systematic Review are represented in this repository using an interactive map and histogram.	https://at2030.org/at-data-portal/map/
8 new Training in Assistive Products (TAP) modules developed and pilot conducted. A publicly Available MOOC planned in Oct 2022 / To improve access to assistive products at community- level, through AT2030, WHO created TAP, a series of e-learning modules that will build the skills and capacity of primary healthcare workforce to safely and effectively provide basic assistive products. / Pilot / The pilot provided confidence that TAP modules have good potential to increase knowledge, in preparation for learners to begin provision of simple AP. The pilot also confirmed that learners will in most instances require supervised practice to achieve safe and effective competency in AP provision. / Health service providers recognise a high need for AP amongst service users; and see provision of simple AP as an appropriate task for nurses, primary/community health workers and related workforce. Participants also gave valuable feedback to strengthen module content, as well as to improve the platform’s usability and accessibility. Practical barriers to TAP implementation were identified including limited access to internet, tablets and printers; availability of supervisors; competing priorities; and a need for dedicated time to focus on training within busy clinic schedules. These are all factors to be considered as TAP is further developed and rolled out. / Post pilot, there has been continuation of vision screening and provision of reading glasses at Kaugere Health Clinic, as well as a collaborative initiative between the Kaugere and the National Orthotics and Prosthetics Service to provide mobility device services.	https://www.who.int/news-room/feature-stories/detail/personnel-training-in-priority-assistive-products-(tap) / Pilot: https://cdn.who.int/media/docs/default-source/assistive-technology-2/tap/tap-pngpilot-report.pdf?sfvrsn=902e5acc_2
Two Localised I’mPOSSIBLE toolkits (Zambia and Ghana) / The International Paralympic Committee’s (IPC) I’mPOSSIBLE toolkits were localised by complementing the ‘standard’ toolkit with national stories and images to make them more relatable to teachers and students on the ground in Zambia and Ghana, while promoting national Para athletes. IPC’s strategy is to empower its members and have as much ownership of the project as possible on the ground through National Paralympic Committees.	The Zambia toolkit can be found here and the Ghana toolkit here
Liberia National Priority Assistive Products List (APL) / The APL is intended to focus and prioritize resources and efforts toward products that are the most impactful and context-relevant to the country. Moving forward, the APL will guide the AT sector in product procurement and donation, service provider training, development of technical standards and service delivery guidelines, and broader advocacy and resource mobilization efforts. Its validation is evidence of the government’s commitment to increasing access to AT through strengthening governance and coordination in the sector.	https://at2030.org/liberia,-country-investment-fund-and-the-production-of-national-priority-assistive-products-list-and-national-roadmap-to-increase-access-to-at/
National Roadmap to Increase Access to Assistive Technologies (2021-2023) / This Roadmap operationalizes the visions that have been outlined in broader national policies and sets a clear plan to guide and coordinate national efforts in AT. It further supports the Government of Liberia in its advocacy and resource mobilization efforts. Validation of this Roadmap is a crucial step towards realizing the Government of Liberia’s commitment to increase access to quality AT at an affordable cost, and will ultimately increase community and economic participation for all persons with disabilities, enabling the realization of human rights.	https://at2030.org/static/at2030_core/outputs/Liberia_National_Priority_APL_V1_Dec_2021.pdf
InnovateNow Innovation Toolkit / The open entrepreneurship toolkit is a set of learning materials that can help entrepreneurs and their teams to solve problems by creating and experimenting with different strategies. There is rarely a single correct way to solve problems as an entrepreneur, so they will need to learn how to create and compare different solutions. Covering the domains of user, product, market and business development, the set of cards have been designed to be used by two or more group members to actively experiment with different solutions.	https://www.disabilityinnovation.com/toolkit

3.3 Number of case studies produced (including from Inclusive infrastructure and Sport Against Stigma)
2021/22 target: 17
2021/22 achieved: 17
Met expectations

Case studies are designed to engage audiences based on a contextualised analysis, recommendations and lessons. A full list of case studies developed to date is included in Annex E. This reporting period, AT2030 concluded the Case Studies below.

Table 8: Case Studies
Project / [Location]	Case Study	Links
Inclusive Design and Accessibility of the Built Environment / [Ulaanbaatar, Mongolia]	Research on accessibility and inclusion in the built environment. First in a series of six global case studies to understand global priorities for inclusive design. / Current understanding on accessibility and inclusion is being driven by international influences and standards and is not fundamentally embedded in architectural training or urban development programme delivery. Inclusive design can be applied across the city’s urban development and planning initiatives to integrate local perspectives and amplify the voices of people with disabilities, who have some of the best understanding of how the built environment is inequitable. Setting a comprehensive vision and action plan for a more inclusive Ulaanbaatar should be complemented by training and education in disability inclusion and inclusive design across stakeholders and the general public… improving the lives of everybody: including people with disabilities. / Results were disseminated at the Development Agencies meeting in Mongolia on 14th October, organised by the UN, and with the British Embassy in Mongolia. Among the speakers and attendees were: the British Ambassador to Mongolia, the Minister for Labour and Social Protection of the Government of Mongolia, the Italian Ambassador to Mongolia, representatives of the embassies of Canada, USA, Germany, Italy, and the UK, representatives of multi-lateral organisations including UNDP, UNFPA and GIZ and NGOs and DPOs The report is available in English and Mongolian. / By GDI Hub, Associazione Italiana Amici di Raoul Follereau (AIFO), Tegsh Niigem and Universal Progress ILC.	Full report (87 pages)
Inclusive Design and Accessibility of the Built Environment / [Solo, Indonesia]	Research on accessibility and inclusion in the built environment. Second in a series of six global case studies to understand global priorities for inclusive design. / “When resources are limited, accessible design interventions can often be limited to essential services such as accessing government services, healthcare, education, and transport. However, according to participants, a much wider variety of infrastructures are key to a fulfilling urban life including inclusive green spaces, recreational spaces, religious spaces, markets, and tourism. The assistive technologies people can access are also essential in facilitating access to the urban environment. An inclusive design approach to city planning can support all citizens to experience their city in a fair an equal way, providing a framework to integrate people’s needs and aspirations in urban development.” / Results were disseminated at an event to launch the findings from the ‘Inclusive Infrastructure’ and ’Build Capacity and Participation‘ sub-programmes of AT2030 in early 2022. GDI Hub, UCL and Kota Kita hosted an event to celebrate AT2030's programmes in Indonesia, which was attended by the Mayor of Banjarmasin and representatives of multi-lateral organisations, NGOs, DPOs and academia. The Mayor of Solo also pre-recorded a message of support. / By GDI Hub and Kota Kita.	Report / (13 Pages)
Inclusive Design and Accessibility of the Built Environment / [Varanasi, India]	Research on accessibility and inclusion in the built environment. Third in a series of six global case studies to understand global priorities for inclusive design. / At a policy level, national laws must be accompanied by local guidance and standards. National accessibility standards must also be localised to Varanasi, and having best practice examples that could be highlighted would help. At the industry scale, good design practice, design reviews and inspections must take place and construction professionals must also be aware of and champion inclusive design and take responsibility to ensure quality implementation. / Communities should convey their needs through participation in design and consultation processes, conducting accessibility audits and advocacy work where they can. However, there should be government and industry support to fund this work, people should be acknowledged and compensated for their work. Persons with disabilities should also be participating in design and decision-making processes through being provided opportunities to access employment in policy and industry professions. / The Varanasi report was launched formally in September 2021 at a multi-stakeholder consultation which was attended by city officials from Varanasi and the Varanasi Smart City Limited organisation, the Department of Disability Affairs in Varanasi, Varanasi Development Authority, Town and Country Planning Department, Department of Empowerment for Persons with Disabilities, Tourism Department, Road Safety and Traffic Department, Smart City SPV and representatives of NGOs, DPOs and sector experts. FCDO representatives from India and the UK were also in attendance including the Minister Counsellor of UK Government, Katy Budge. / The study was conducted by GDI Hub, the National Institute of Urban Affairs, Kiran Society and Varanasi Municipality.	Full Report (112 Pages)
Catalysing AT access: / Scaling rehabilitative services and increasing access to AT / [Kenya]	Expanding access to rehabilitative and AT services in Kenya / At the request of Kenya’s Ministry of Health, a comprehensive situational analysis was conducted that involved a mapping of service capacity in 238 public health facilities – 47 county referral hospitals and 191 sub-county hospitals. The case study describes the pathway towards national scale up by developing a “National Strategy for Scaling Rehabilitative Services and Increase Access to Assistive Technology”. / Findings were shared with all government stakeholders via a series of video conferences and a follow up two-week workshop. Workshop consultations and the dissemination event included people with disabilities living in Nairobi, representatives of National and Local Government including: Nairobi Metropolitan Services, Nairobi County Government and Ministry of Labour and Social Protection, representatives of NGOs, DPOs, built environment industry and academia. This supports awareness and buy-in for the final recommendations. / The result will be the finalised case study (including situation analysis and feedback) which forms a core qualitative data set.. / By CHAI and AT2030 programme	Full Report (6 pages)
The Liberia Evidence Lab: A new scalable model to deliver School Eye Health / [Liberia]	Expanding access to eyeglasses for better outcomes in school / The case study highlights how school eye health programs can be successfully scaled in under-resourced and under-capacitated contexts, and ultimately supported through a sustainable financing mechanism. School eye health is an entry point and critical building block to comprehensive national eye health coverage. Through a pilot of the school eye health model, approximately 50,000 children received eye screenings across three counties in Liberia. / By EYElliance, CHAI and the AT2030 programme	Full Report / (7 pages)
A unified approach to fund and provide AT services / [Indonesia]	A new coordinating mechanism is catalysing access to AT / An assessment of Indonesia’s AT sector highlighted the need for increased coordination among stakeholders. A cross-ministerial technical working group (TWG) was set up in 2019 to provide for this increased coordination and address the issues that inhibit access to assistive products. One of the TWG’s first commitments was increasing budgets and developing policy for provision of AT by local governments. A new AT funding scheme of £3m – currently named DAK-Fisik Social for AT – will cover the cost of assistive products and services for people with disabilities in Indonesia. / By CHAI and the AT2030 programme	Full report / (5 pages)

3.4 Value of matched funding provided through partnerships
2021/22 target: £13,000,000
2021/22 achieved: £13,868,221
Exceeded expectations

AT2030 includes an ambitious 100% match-funding target. The programme leveraged a total of £13,868,221 in cash or in-kind, against an (already stretching) target of £13,000,000. See Figure 5 in Section B. The forms of match contributions are varied. Notable additions in this reporting period include:
- £1.3m in partner direct co-funding into the project budget from the IPC, Loughborough University London (LUL) and Hogan-Lovells to support the broadcast of the 2021 Paralympics. This included extra-budget, staff time, goods, equipment, and supplies (including IT infrastructure and telecoms), and the securing of national broadcasting across Sub-Saharan Africa.
- £200,000 in partner direct co-funding into the Rwanda country investment budget (supporting the development of a National Assistive Products List (APL) and Implementation Plan) from funding secured from third party donors GIZ, CBM and UNICEF, as well as in-kind contributions from external consultancy advice and physical location support.
- £155,000 in partner direct co-funding into the Liberia country investment budget (supporting the development of a National APL) from funding secured from third party donors WHO, as well as in-kind contributions from additional staff time and physical location support.
- £184,000 in in-kind contributions (as unfunded staff time, operational costs and stock storage) as well as select revenue reinvestment, by AT Impact Fund ventures, Wazivision, Koaala, MiracleFeet, OADCPH and HearX.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Table 10: Recommendations
(OP3: CAPACITY & PARTICIPATION) Partnerships directly supported and tools and lessons learnt developed to support countries and global agencies
Previous AR Recommendations	Progress
Review the Logframe indicators for this output / (by end October 2021).	Done – with further stretch revisions to be proposed following this Annual Review.
GDI Hub should continue to build partnerships for strong programme results / (ongoing, to end programme)	Achieved – as above.
2021/22 Learning	Recommendations
The programme has performed well this year against logframe targets	Review and agree stretch logframe targets / [By end December 2022]
Innovative new tools have been created/developed and tested during the reporting period which can add value through supporting innovators, ventures and ecosystem stakeholders (including governments) to inform decision making. These tools now need to be shared and socialised with stakeholders who can derive benefit from them	Widely disseminate the value and use of AT2030 tools (digital tools in particular – and how to use them), with a targeted stakeholder approach / [By end June 2023]

Output Title	(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
Output number:		4	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of country capacity assessments (CCA)	10	12 / Moderately exceeded expectations
4.2 Number of countries delivering CCA action plans	7	10 / Exceeded expectations
4.3 Number of countries with direct investment in AT matched to be sustainable (also links to significant numbers of ‘reach’).	4	4 / Met expectations
4.4 Number of 'one-stop-shop' pilots at the country level	2	2 / Met expectations
4.5 Number of 52min daily digests of the Japan Paralympic Games produced.	13	13 / Met expectations
4.6 Paralympic Games broadcasts across a number of African Countries	30	49 / Substantially exceeded expectations

NB. the indicators in the table above are cumulative milestone indicators.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Planned delivery under this Output largely concluded in this reporting period, with targets for CCAs, Action Plans, Country Investment Fund (CIF) investments, One-stop-shops and work aligned with the 2021 Tokyo Paralympics, being largely met or exceeded. The country reach of the broadcast of the Tokyo Paralympics was a particular highlight having covered 49 countries against a target of 30. Further to this large audience reach, the parallel research (see Box 13, output 4.5 below) within the project offers important lessons and challenges for this kind of approach to parasport and stigma reduction which will inform programming (within and beyond AT2030) in the run-up to Paris, Milan and Los Angeles.

4.1 Number of country capacity assessments
2021/22 target: 10
2021/22 achieved: 12
Moderately exceeded expectations

Country Capacity Assessments (CCAs) are in-depth studies aimed at understanding a country’s capacity to finance, procure and provide AT. The process provides support for policy makers to identify actions to strengthen AT service delivery to meet population needs based on evidence. This reporting year concluded this workstream within AT2030, with future work selectively continuing on the implementation of National Action Plans with a specific focus on AT procurement. FCDO’s SRO and GDI Hub have discussed and/or shared CCA reports with FCDO Social Development Advisers in a number of the countries where CCAs have been conducted.

AT2030 has also generated catalytic impact through the wider proliferation and update of CCAs by other partners and countries – with a total of 28 countries either planning, delivering of completing CCAs following the AT2030 model in partnership with AT2030 core partner, the WHO. GDI Hub have been in negotiation with Cabinet Office for a CCA for the UK.

Table 11: Country Capacity Assessment – cumulative progress
Reporting period	Countries
2020/21	CCA Lessons Learned Report / Lessons Learned event: ‘Country Capacity Assessments- supporting country governments to address Assistive Technology access.’
2020/21	ATA-C Tool / ATA-C Implementation Manual
2020/21	Informal settlements: Sierra Leone / Informal settlements: Indonesia
2019/20 / 2020/21 / 2021/22	Bolivia / Dominican Republic / Ethiopia / Liberia / Malawi / Mongolia / Nigeria / Rwanda / Sierra Leone / Uganda / Vietnam

4.2 Number of countries delivering CCA action plans
2021/22 target: 7
2021/22 achieved: 10
Exceeded expectations

As with the development of CCA, this reporting year concludes AT2030’s workstream on CCA Action Plans, with future work progressing into the granularity of AT procurement. Nevertheless, AT2030 has now supported ten (10) counties to deliver actions against their CCAs, over the target of seven (7). This includes the impact realised through AT2030’s ‘Country Investment Fund’ (CIF)’ – an open call to support the implementation of CCA recommendations. Highlighted progress in CIF countries (Liberia, Nigeria, Rwanda and Sierra Leone), includes:
- Liberia – Under CIF, CHAI as the lead technical partner supported the Liberia Ministry of Health in the development and validation of two major national documents for access to assistive technologies: National Roadmap to Increase Access to Assistive Technologies (2021-2023) and Liberia National Priority Assistive Products List (APL), First Edition. The development of these documents will pave the way in ensuring Assistive Technology can be accessed by people with disabilities and older people living in Liberia.
- Nigeria - Under CIF, CHAI as the lead technical partner supported the Federal Ministry of Health in Nigeria to launch the first-ever National Priority APL in March 2022. The development of the APL is a milestone in the Nigerian government’s efforts to create an enabling environment for assistive technology sector players to accelerate the scale-up of appropriate and high-quality ATs for Nigeria’s more than 25 million persons with disabilities.
- Rwanda – Under CIF, CHAI as the lead technical partner supported the Government of Rwanda Ministry of Health to develop the first-ever national priority APL, a new National Rehabilitation strategy (with one section dedicated to increasing AT access) and a comprehensive data system on disability.
- Sierra Leone - Under CIF, CHAI as the lead technical partner supported The Ministry of Health and Sanitation in the development of the Priority APL and AT Policy and Strategic Plan 2021-25 in Sierra Leone. The APL in Sierra Leone aims to help improve access to appropriate, quality AT products at an affordable price that will help enhance the functioning and independence of persons with disabilities, while facilitating their participation and integration in society.

Respective CCA recommendations are in Annex F.

4.3 Number of countries with direct investment in AT matched to be sustainable (also links to significant numbers of ‘reach’)
2021/22 target: 4
2021/22 achieved: 4
Met expectations

This Output relates to the operationalisation and governance of the CIF which was completed in the previous reporting period.

4.4 Number of 'one-stop-shop' pilots at the country level
2021/22 target: 2
2021/22 achieved: 2
Met expectations

While the AT2030 pilots were completed in 2020/21, the 1-stop-shop models were shown to be good examples of catalytic impact. Similar 1-stop-shops are now being replicated by WHO in India, Iraq, Papua New Guinea, and Liberia, to date. Additionally, a final workshop in 2022 is also planned in Jordan with a focus on AT in Humanitarian Contexts to further explore integrated service provision, and to refine and adapt this model based on the lessons learned from these pilots.

AT2030’s ‘one-stop-shops’ were part of the effort to develop new models of integrated AT service provision. In collaboration with Ministries of Health and local partners, the WHO piloted this model in Tanzania and Tajikistan. A ‘one-stop-shop’ typically provides a single point of contact and ‘how-to’ information on issues related to AT services, including procurement of assistive products, training of workforce, and the establishment of referral mechanisms.

- In Tajikistan, the 1-stop-shop model included the procurement of assistive products, training of the relevant workforce (conducted in 2021, 15 primary healthcare workers as well as people from the MOH), and the establishment of referral mechanisms and other related activities. Training covered the identification of need for, referral to and provision of simple assistive products to support the following domains: mobility (walking aids, therapeutic footwear), vision (reading glasses, telescopes and magnifiers), self-care (toilet and shower chairs, absorbent products).
- In Tanzania, the 1-stop-shop model also included the procurement of assistive products, training of the relevant workforce and the establishment of referral mechanisms and other related activities. Partners in Tanzania included MoH, and HelpAge International. There were approximately 190 learners (of which 150 were community health workers who only need take the first module, plus 40 primary healthcare workers from 20 different primary healthcare centres) from two districts (one urban and one rural) in the Morogoro region. The training covered: mobility (walking aids, therapeutic footwear, rigid removable boots), vision (reading glasses, telescopes and magnifiers), self-care (toilet and shower chairs) and cognition (pill organizers).

4.5 Number of 52min daily digests of the Japan Paralympic Games produced
2021/22 target: 13
2021/22 achieved: 13
Met expectations

Building on lessons from London 2012 and learning from AT2030’s stigma research, this output is intended to challenge the negative perceptions of people with disabilities.

TV Media Sport (TVMS) led the distribution and broadcast of the 52-minute highlight packages of African centred content to 49 National broadcasters across Sub Saharan Africa. The highlights package was provided by TVMS to National broadcasters with English, French and Portuguese commentary and aimed to highlight stories of Para athletes from the region.

The highlights broadcast as well as the main broadcast reach itself (4.6) have both been supported by parallel research led by Loughborough University. This research is available here and highlights are in Box 13 below.

Box 13: Para Sport Against Stigma Research Report on the Tokyo 2020* Broadcasting in Sub-Saharan Africa (Malawi) (Parallel Research Report)
Loughborough University

The findings indicate that Paralympic broadcasting is an important vehicle in disability representation and the development of empowering disability narratives. However, Paralympic broadcast through National state TV alone is not sufficient to challenge widespread intersectional forms of disability stigma and discourses around AT use. For the Paralympic broadcast to have reach and impact in Sub-Saharan African countries with a communication/ media ecology and infrastructure such as Malawi, and to be sustainable as a social change vehicle, a range of media activities and diverse forms of distribution will be required. This should include broadcast via more accessible platforms such as radio and digital streaming, as well as community screening via community hubs (e.g., in schools).

Localising Paralympic content through Chichewa interpretations and commentary was successful. The Chichewa interpretations and commentaries were important in localising the content for Malawian audiences and making it more accessible for a wider audience share. Further, the translations provided additional audio content to the highlights package that tackled local understandings and narratives around disability discrimination, stigma and AT use.

For the broadcast to be financially and socially sustainable medium for long term cultural change, commercial independent broadcasters with the capacity to invest in the Paralympic highlights package and provide additional programming with may be more suitable than National state television broadcast channels.

Audience and community research indicate that Paralympic coverage is a useful tool for tackling negative cultural disability attitudes and showcasing the role of AT in enabling individuals with a disability to play sport and participate in civic life. The use of personal and localised stories of Para athletes were particularly powerful in capturing audiences and reducing some forms of disability stigma.

4.6 Paralympic Games broadcasts across a number of Africa Countries
2021/22 target: 30
2021/22 achieved: 49
Substantially exceeded expectations

Figure 7: Social Media Promotion from Rwanda
Figure 8: Screenshot of Sierra Leone (SLBC) Broadcast
In partnership with the International Paralympic Committee (IPC), TV Media Sport (TVMS), and Hogan Lovells, the programme substantially exceeded expectations by broadcasting free to air content from the 2022 Tokyo Paralympics to 49 Sub-Saharan African Countries (against an original target of 30).

The full list of countries and estimated audience size is shown in Annex G.

Following the successful cooperation with the Tokyo 2021 Broadcast, the French news channel TV5 Monde asked to broadcast a 5-min daily highlight package from the Beijing 2022 Winter Paralympics in the African region - this included 49 Sub-Saharan African countries. This represents the first time Winter Paralympics have been shown to that extent on the African continent.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

With the conclusion of CCA, CIF, One-Stop-Shop pilots and the Tokyo Paralympics, the Output targets for this area of work have been completed. These will be replaced with indicators to capture ongoing work within the Country Testing and Implementation Programme Cluster, focussing on procurement, e.g.:
- Number of Procurement pilots/frameworks at country level
- Number of Country Level Strategies for Disability Inclusions and AT Access (CCAs, Action Plans, NPC Partnerships).
Final indicators and targets will be agreed by GDI Hub and FCDO’s SRO.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Table 12: Recommendations
(OP4: COUNTRY TESTING & IMPLEMENTATION) Evidence from in-country pilot activity through investment to; stimulate demand, improve supply of AT for LMICs and create a more enabling market environment.
Previous AR Recommendations	Progress
Review the Logframe indicators for this output / (by end November 2021).	Done – new proposed indicators suggested.
SRO and GDI Hub (and partners) should use Paralympic Games as a ‘communications moment’ for the programme, promoting AT2030 internally across FCDO and externally. / (August/September 2021) / There are a number of additional strong ‘communications moments’ in FYs 21/22 and 22/23 for AT2030. SRO and GDI Hub should map and make plans to promote AT2030 and AT generally (internally and externally) through ‘communications moments’. / (plans in place by end November 2021)	Done – substantial social media and wider communications campaign supported the Tokyo Paralympics, driven by the GDI Hub and internally by FCDO’s SRO. / AT2030 ongoing communications planning is supported by bi-weekly newsletters highlighting events and media, as well as dedicated communications capacity.
SRO and GDI Hub to reach out to FCDO Posts to share CCA outcomes and CIF progress with including details of partnerships in-country. / (by end December 2021)	Done and Ongoing – several meetings with FCDO posts held and to be continued whenever there is relevant country-level work.
2021/22 Learning	Recommendations
With the conclusion of CCA, CIF, One-Stop-Shop pilots and the Tokyo Paralympics, the Output targets for this area of work have been completed.	Replace these with new indicators to capture work on Country Testing and Implementation focused on procurement. E.g.: / Number of Procurement pilots/frameworks at country level / Number of Country Level Strategies for Disability Inclusion and AT Access (CCAs, Action Plans, NPC Partnerships). / [By end December 2022]

D: VALUE FOR MONEY [1 page]
VfM performance compared to the original VfM proposition in the business case
Effectiveness
AT2030’s effectiveness in robust research contributed over 100 papers to the WHO/UNICEF 2022 Global Report on Assistive Technology. / AT2030’s InnovateNow sub-programme has launched more than 30 new AT innovations in three years and supported over 60 Startup founders across 4 countries through InnovateNow's Inclusive Innovation Curriculum. Feedback suggests that this knowledge had a direct impact on helping them to build AT products and business models fit for users and the market. The sub-programme also provided over 500 hours of mentoring. / Feedback from beneficiaries of the InnovateNow programme demonstrates the ‘effectiveness’ of the InnovateNow model of in-country support combined with bespoke support from experts in business development and assistive technology. For example: / Cindy Adem, ‘Village2nation’; / “Think of this as a world-class crash course on building tech that people want. I went in as an absolute novice in the assistive tech space and have completely been immersed in a world that showed me what was possible in building a company that was responsive to the needs of people with hearing and visual impairments”. / There has been coordination across all programme partners around data, databases and tools to estimate demand and supply of AT (for example, the LSHTM-UCL-WHO collaboration on the AT Need Mobile App which uses survey data generated by the Musculoskeletal impairment paper reported in the previous period). / Programme partners have together strengthened impact measuring tools and identified new research and academic conference opportunities to disseminate lessons and evidence. AT2030’s research partners leverage established partnerships with NGOs and world-class academic institutions, composed of diverse and complimentary skills, to deliver high quality outputs. / One of the biggest contributors of match funding has been from governments committing budgets to work identified by CCA and CIF action planning. This both ensures that CCA recommendations are operationalised to reach people with disabilities through practical solutions (effectiveness), and expediates the translation of AT2030 programme efforts into robust and sustainable outputs at the country-level (efficiency). / A new partnership– bringing UNCIEF into the WHO-led Procurement work, created a substantial multiplier effect for the impact of AT procurement tools such as APL (Assistive Product Lists) and APSs (Assistive Product Standards). These tools are now part of UNICEF practices and utilise the UNICEF AT Advocates Network which promotes access to AT within UNICEF programming. In the future the programme expects to see an expansion to UNICEFs role supporting global procurement of AT at a substantially reduced unit cost.
Cost-effectiveness
The 100% match-funding target is delivered by working through a wide and diverse range of partnerships - with NGOs, academic institutions and the private sector, and as programme successes have become more evident, third-part funding (from donors, governments and private companies) has increasingly contributed to this figure. As at the end of March 2022, AT2030 had raised over £13.8m in cash or kind to support the delivery programme outputs. E.g., owing to the credible local impact and specific focus on supporting products and ventures based on their affordability for use by people with disabilities in LMIC contexts, the programme leveraged additional funding from Norad, to support a further 3 cohorts of InnovateNow over the next three years. / Inputs for the programme are largely person time, with low programme goods purchases. A large proportion of human resource capacity across the programme is procured through academic partners (particularly, but not only in the UK), and therefore costs are based on academic salary scales. This is much cheaper than comparable quality professional levels procured through consultancy. For example, a senior researcher costs approx. £210 per day through AT2030’s grant structure compared to a (discounted and long-term) service level charge-out rate of £462 for the same level of expert. / Innovate Now support enabled innovators to build robust local capacity for AT manufacturing. AT's manufactured or built locally has reduced the cost by more than 50 percent in some cases.
Equity
AT2030 is designed to reach the most marginalised and ‘hard to reach’ populations, specifically people with disabilities and older people. Country-level work under this output, such as the work in Kenya, has focused on people living in very poor conditions including informal settlements who have previously been overlooked for AT provision, i.e. reaching the last mile. / The ATIF is scaling AT ventures to reach people with disabilities in LMICs, specifically developing products, services and funding mechanisms to make ATs more accessible and affordable for the poorest populations. / The programme has conducted research on people with disabilities and AT informal settlements in Indonesia and Sierra Leone to better understand the needs of some of the most marginalised populations of people with disabilities. These studies typically include participant data disaggregated by gender (e.g. https://at2030.org/bridging-the-divide/ and https://at2030.org/the-social-network/), and have highlighted findings on the different use and impact of mobile technology for visual and mobility impaired men and women. They will increase their focus on gender going forward.
Economy
CHAI and WHO, AT2030 delivery partners (who delivered the CCAs), used their existing in-country knowledge, experience, and understanding of the data and country information, to support countries to develop and deliver their action plans, including through the CIF. This reduced time and resources to deliver critical outputs. / Inclusive infrastructure case studies are delivered in-country by local partners, leveraging their existing relationships with local government and communities. This more effective and economical approach was a positive unintended consequence of Covid-19 when travel restrictions limited travel of the GDI Hub expert team to conduct or direct the research in person. As a result of this learning, the GDI Hub are continuing to support local partners virtually to deliver the remaining case studies.
Efficiency
Dissemination of research findings is supported by dedicated communications capacity. Due to the size, reputation and reach of partner networks, this function has proven to be highly efficient. For example, UCL’s dissemination network includes programme partners, GATE Network (Global Association of Assistive Technology), European Assistive Technology Information Network (EASTIN), Association for the Advancement of Assistive Technology in Europe (AAATE), Rehabilitation Engineering and Assistive Technology Society of North America (RESNA), The Global Alliance of Assistive Technology Organisations, CHI Conference on Human Factors in Computing Systems, among others. / GDI Hub’s coordination and collaboration function ensures that partners avoid duplication and identify possible programme efficiencies. For example, the Training on Assistive Products (TAP) modules for training on AT developed by WHO under AT2030, have been used at the country-level by partners CHAI as part of their Country Implementation Fund (CIF) work, and will be employed in all applicable county-level work going forward. / This year the programme was responsible for the television broadcast of the Tokyo Paralympics to 49 countries, substantially exceeding the target of 30 countries, to tackle stigma and discrimination. The broadcast is estimated to have reached more than 57 million people across sub-Saharan Africa. / As GDI Hub is affiliated to UCL, it provides an opportunity for AT2030 to tap into various other centres of excellence e.g. Institute of Innovation and Public Purpose (IIPP) etc. The programme also draws heavily from GDI Hub’s Academic Research Centre (ARC) within UCL i.e. Professor Holloway and her team of researchers, as well as LUL, LSHTM and Maynooth - all of whom have strong research capabilities, and have made significant contributions to the outputs of AT2030.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

AT2030 is an innovative disability inclusion programme. This has enabled flexibility within the programme - to make a series of investments in new approaches, contexts and/or technologies to ‘fail fast and scale successes’ for a higher rate of return i.e. to reach more people with disabilities, and older people with AT. AT2030’s overall risk appetite and rating remains unchanged as ‘Cautious’.

The programme manages risk through established systems to proactively monitor risk on an ongoing basis; i.e. to monitor each risk through FCDO’s risk categories and provide clear risk owners, mitigation actions and timelines.
Figure 9: AT2030 Risk Profile 2021/22

At the end of FY 2021/22, the programme team took a snapshot of the programme risk profile based on feedback from delivery partners and project managers (based on FCDO’s previous risk model – since updated). Figure 9 summarises the results of this risk assessment. Risk ratings capture an index measure of each risk’s probability and impact on programme delivery, and the diagram details risk profile before and after mitigation actions.

There are effective mitigations in place against the biggest risks – external context – and a balanced risk portfolio overall.

Risks are discussed with FCDO during regular bi-weekly meetings and more formally through quarterly reporting / reviews. No change to risk appetite is foreseen, and in the next reporting period programme management processes across delivery partners will continue to improve the visibility and responsiveness of risk management practices.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

AT2030 leads GDI Hub, regularly engage with FCDO and programme partners throughout the reporting cycle. The GDI Hub provided timely quarterly financial and narrative reports, engaged in bi-weekly catch-up calls with FCDO, provided fortnightly delivery and coordination email updates to all partners (including FCDO) - including highlights and media output – attended formal quarterly review progress meetings with FCDO, hosted quarterly AT2030 Advisory Boards and made substantial contributions to the programme Annual Review including presentation/discussion to/with FCDO.

The financial year end accounts of implementing partners are checked by the GDI Hub and provided to FCDO annually. In 2020/21 GDI Hub was also Audited as part of its commitment to FCDO. The auditors confirmed there were no material errors relating to the grant accounting and no significant weaknesses relating to internal controls. Programme forecasts and expenditure were managed closely and have broadly been in line with budget. Quarterly and annual programme forecasts are provided to FCDO at the beginning of each quarter and financial year with quarterly updates addressing any changes or variance. The lingering impact of COVID-19 during 2021/22, and related budget pressures within FCDO resulted in the reduction of the AT2030 budget in 2021/22 (from £6.58m to £3.25m). The programme has managed this change and pressure well, and transparently with all delivery partners. Year-end spend was £4,509 overspent (0.1% variance) against the ceiling budget for the year of £3.55m (£3.25m agreed budget + £300K uplift in Q4). The overall AT2030 programme budget of £19.8m remains unchanged.

FCDO has supported programme leads GDI Hub throughout the performance year. With ongoing FCDO support, the programme will continue to grow, and build on its successes. Ongoing country level co-ordination through FCDO will help to ensure that in-country programme and partner linkages are optimised. However, due to Covid-19 travel restrictions, it has unfortunately not yet been possible for the FCDO SRO or Programme Manager to undertake field visits during this period. These will be prioritised as soon as the situation allows. GDI Hub provides programme-level risk reporting as part of their Quarterly Reports from all partners, which supports the strategic level risk matrix for AT2030 – shared and discussed with FCDO during quarterly reviews.

Date of last narrative financial report	July 2022	Date of last audited annual statement	21 September 2022

Annex A: AT2030 Reach Definition

The AT2030 programme is designed to find out ‘what works’ in getting AT to the people that need it around the world, in order to create blueprints for scale. It is therefore foundational, explorative research and innovation; rather than being a programme which solely tries to map AT units to individuals. The Logical Framework (logframe) indicators were initially agreed in 2018 as part of an addendum to the existing FCDO Ideas 2 Impact (I2I) business case in line with the co-creation and scoping work that had been undertaken. The Log Frame was reworked in 2019 when AT2030 developed a new business case for a stand-alone programme, but the approach to developing ‘reach’ figures remains unchanged, and in line with the Global Strategy on AT.
After analysis and collaboration, including that presented in the scoping report on AT funded by FCDO (here), it was considered that the priority interventions necessary to improve access to AT were more complex and more systemic than simply providing AT; which would be a) a drop in the ocean of the problem and b) could be piecemeal and not transformational. The programme was, therefore, founded upon the hypothesis (tested in the scoping review) that interventions should need to span market shaping, innovation, systems intervention, and community participation – as well as the direct provision AT, as a first principles impact priority.
At inception it was felt important that the programme incentivised action at a systemic level.

AT2030 includes top-level impact indicators which target ‘Reach’ (Direct (People), Direct (Systemic) and Indirect). These quantitative indicators sits aside a qualitative measure of impact captured in the 2019 AT2030 Log Frame - Impact Stories. The ‘Reach’ indicators cover all aspects of AT2030 delivery, including research, product innovation, delivery pilots, media outreach, advocacy, capacity building, partnership development, match-fund mobilisation, policy reform and venture investment.
Reach Definitions

Direct Reach (People):
People who participate at an individual level in the activities and/or outputs of AT2030. This includes individuals reached by the programme in its endeavour to find out ‘what works’- is not the same as beneficiary counting, as we are interested in benefits as well as inclusion. This reach nevertheless typically refers to individuals.

Direct Reach (Systemic):
Groups who benefit from the outputs and outcomes of the AT2030 relating to improved provision of AT through policy and system advances, and community- and organisational-level change. This includes systemic changes of a defined and specific magnitude in terms of the number and manner of people affected and included. This reach typically refers to groups. This captures core success factors for the appropriate provision of AT set out in the Scoping Report 2018 and notably includes changes in the provision of rights and recognitions and the engagement of people with disabilities in the process.

Indirect Reach:
Individuals who are not directly connected with the programme but could still derive benefit from it. This (likely) does not involve direct interaction with the programme but can be reasonably identified as included within programme community/national-level catchment.

Direct Reach (People)
The participation of people with disabilities in research on issues which affect their lives is an essential element of ensuring that disability research is robust and focused on the issues of greatest importance and the participation of people with disabilities in co-designing a more inclusive world is also necessary for achieving it[14]. Innovators know that user-centered design is essential and this is also the case with research. We describe this as necessary to create the conditions for ‘socially just’ pedagogy (Goodley, 2007).
[14] Sen, A., 1999a. Freedom as development. Oxford University Press, Oxford.
People with disabilities are substantially underrepresented within research (including research on disability issues)[15]. Emancipatory research, as first identified by Oliver (1992), was based on changing the social relations of research production. In other words, for emancipatory research to be possible the balance of power within the research process would have to change, and move towards a more equal relationship between the researcher and the people with disabilities who are being ‘researched’. Disability research would have to be done with (i.e. in partnership with) people with disabilities rather than on them - as had been the case with traditional approaches. With a focus on a social model of disability, commentators such as Oliver[16] and Zarb[17] forwarded models of ‘emancipatory’ research as a response not only to the exclusion of people with disabilities from the research process, but as a necessary reaction to the oppression of people with disabilities in society and the systematic denial of their rights. In recent years Disability Emancipatory Research has been operated in practice seeking to drive participation of disabled people as research co-creators forward, but it is not without challenge in implementation and is naturally always imperfect[18][19] (Goodley, 2007; Deepak, 2019).
[15] For a summary of the main points and arguments see Abberly, Oliver, Zarb and others in ‘Disability, Handicap and Society’ (1992) Vol.7, No.2; and Barnes and Mercer, Oliver, Ward, Zarb and others in ‘Doing Disability Research’(1997), edited by Barnes and Mercer
[16] Oliver, M (1992) Changing the Social Relations of Research Production, in ‘Disability, Handicap and Society’, Vol. 7 No. 2
[17] Zarb, G (1992) On the road to Damascus: first steps towards changing the relations of disability research production, ‘Disability, Handicap & Society’, Vol. 7, No. 2. And Zarb, G (1997) Researching Disabling Barriers, in ‘Doing Disability Research’, Barnes and Mercer (Eds.) Leeds: The Disability Press
[18] Goodley, D., 2007. Towards socially just pedagogies: Deleuzoguattarian critical disability studies. Int. J. Incl. Educ. 11, 317–334. https://doi.org/10.1080/13603110701238769
[19] Deepak, S. 2019. Challenges of Emancipatory Disability Research in Developing Countries. Conference: Essere Persona: Disabilita nel Mondo - Quali Diritti, Inclusione e Riabilitazione Milan, 5-6 April 2019At: Milan
For the above reason, across research conducted within AT2030, we count the reach of participants with disabilities in recognition of the ‘basic’ (adequately reflecting perspectives) and ‘emancipatory’ (addressing social relations and rights through inclusion and research awareness) importance of research practice. This specific cohort of direct reach (i.e., research participants) will be disaggregated within the overall category and supported by future research on the emancipatory power of research inclusion within the field of disability.
In respect of supporting the physical delivery of AT products (hearing aids, wheelchairs, prosthetics etc.), which is only one part of what AT2030 does, we count people receiving or being assessed for AT and their support personnel (if applicable). Relieving pressure on carers and support persons is a well-recognised benefit of providing AT to a user, in addition to the benefit realised by the user themselves[20].
[20] Bhachu, A. S., Hine, N., & Woolrych, R. (2012). The role of assistive technology in supporting formal carers. In J. C. Augusto, M. Huch, A. Kameas, J. Maitland, P. McCullagh, J. Roberts, A. Sixsmith, & R. Wichert (Eds.), Handbook of Ambient Assisted Living: Technology for Healthcare, Rehabilitation and Well-Being (Vol. 11, pp. 283-303). (Ambient Intelligence and Smart Environments; Vol. 11). IOS Press. https://doi.org/10.3233/978-1-60750-837-3-283
With respect to the delivery of capacity building and system strengthening work within country organisations, the reach aims to capture the size of the team or organisation which is strengthened, along with qualitative feedback from participants to validate this impact.
Direct Reach (Systemic)
A core pillar of the AT2030 is to trial strengthening policy, systems and implementation to create enabling an environment for innovation and AT. A substantial component of programme delivery is aimed at the creation of this enabling environment within which people with disabilities live. While over the course of 10-15 years we would expect to see increased delivery of AT units as a longer-term result of this enabling environment, that long-term impact is beyond the scope of AT2030’s results chain.
People benefit from rights by virtue of having them (even for example when they don’t draw upon them). For example, people who have never committed a crime, are nevertheless still beneficiaries of the right to a fair trial; those who live without arbitrary encumbrances on their liberties are nevertheless beneficiaries of human rights provisions (where these exist).
For the reasons above, within Reach we count those groups of disabled people newly covered by rights and policy provisions as a result of AT2030 efforts. The methodology for capturing this reach is based on the identification of the intervention type and the nature of the output/outcome delivered. Crucially, in order to be direct systemic reach, the change created must be of a defined and specific magnitude in terms of the number of people affected and included, the way in which they are affected/included and at a level of greater specificity to general (DP) population impact. In referring to systemic change this is necessarily compliance indicator, rather than performance indicator, and while necessarily limited in the nuance it can capture, is comparable to the use of indicators and statistics within the United Nations human rights system[21].
[21] UN Office of the High Commissioner for Human Rights (OHCHR), Human Rights Indicators: A Guide to Measurement and Implementation, 2012, HR/PUB/12/5, available at: https://www.refworld.org/docid/51a739694.html [accessed 14 February 2022]
A key example here, would be the expansion of provision of AT within primary health care policy coverage – and the fact that not every single person will, at that moment, make a claim for AT, but all functionally eligible and included persons are from that point capable of making such as claim. This is distinct from broad policy catchment, as the policy shift captured here (rather than under Indirect) are immediately implementable in their passing. These changes are substantial impacts and advancements for increasing access to AT. We don’t count whole national populations despite the fact that conceivably these rights and provisions have nationwide impacts for all citizens. It is also worth noting that due to systematic and seismic underestimates in disability prevalence rates[22], even the reach that is counted here is likely an underestimate of impact. To date we have only counted those populations specifically targeted by policies in South Africa, Liberia and Kenya, which are passed along with the capability to implement (e.g. financial or practical), for example which includes:
[22] Mont D. 2007. Measuring disability prevalence: Special Protection, World Bank
- 95,000 directly reached during the programme’s engagement with Ministries including interviews informing the product narratives, ministry capacity building, and direct pilot service delivery (such as the Liberia eye health pilot), since the programme began in 2019.
- 900,000 people with disabilities that will benefit directly from the Kenya Disability Medical Assessment and Categorization Guidelines and National Strategy for Scaling Rehabilitative Services and Increase Access to Assistive Technology. This is a subset of the approximately 4m disabled people in Kenya in scope of a more inclusive policy environment, with the number here referring to those specifically provided for in the Medical Assessment Guidelines and Rehabilitative Services, as identified though the process of policy formulation. This substantial systemic impact addressed the needs for the provision of AT set out in the Scoping Report 2018, and captures the importance of domestic policy and resource mobilisation.
- 1.9m learners covered by the Integrated School Eye Health in South Africa and 400,000 learners covered by a similar School Eye Health framework in Liberia. This reach captures the number of learners provided for by the policy adopted by government as a result of the pilot, and is both a substantial impact for the programme in catalysing systemic change with a direct user group in focus, and aligned to priorities for the provision of AT set out in the Scoping Report 2018.

Another large part of AT2030’s programmes of activities are focused on awareness raising, behavioural change and project participation. This is measured through demonstrations of positive actions by people on AT and disability topics and actions which address stigma.
Work addressing and seeking to better understand stigma around disability is one such example. Additionally, where the programme works to change the way third-party entities implement AT-related work, the breadth with which AT2030 is able to engage with organisations is crucial to the sustainability of impact achieved. This also relates to the programme Outcome to see third-party entities (countries or organisations) implementing AT2030 funded ideas (findings, research or new methodologies).
For this reason, in Reach, we capture audiences actively participating and interacting with advocacy and outreach materials or workshops (for example, around positive inclusion messaging on disability and participation). NB. We do not count within reach the total audience size without evidence of interaction. For example,
- 1,569 people have participated in AT2030’s Disability Live webinars focused on sharing insights from the programme and offering an opportunity for panel engagements.
- AT2030 Stigma reducing work in Kenya delivers change though positive disability messaging in comics and social media. Programme research indicated that approximately 7.7 million Kenyans aged 15-24 years old received a range of media from the programme; however only a sub-set of this is counted as direct reach – such as the 297,655 (over a two year period) who clicked onto the online resources to get further information of the AT providers, reached out to the implementing partner on SMS, or responded to the call outs and then connected to a service and/or product provider. Also included are those receiving project materials which address stigma and support behavioural change, where these are supported by evidence showing a material and direct impact on people’s perceptions of disability and ability/willingness to engage in addressing stigma. A parallel example might be counting the number of bed-nets disbursed with evidence of their efficacy in reducing malaria.

Indirect Reach
Indirect reach is collected across the breadth of the programme, and reflects the diversity of delivery approach and domains, inclusive of policy strengthening, capacity and participation, political support, behavioural change and innovation ecosystem growth. The impact counted as indirect, in contrast to direct reach, cannot be either directly identified as specific individuals or specific groups. Examples from the programme to date include:
- 6.3m indirectly reached based on the population catchment of PWD covered by new national policies and frameworks in Liberia, Indonesia, South Africa, Kenya. NB. Not counted here are the approximately 55,000,000 total PWD population covered by the Country Capacity Assessments and Action Plans developed under AT2030, across eight counties, even though in-time benefits are likely to be realised from this.
- 1.2m radio show broadcast audience members receiving programmes which address issues of disability stigma.
- 675,000 Social Media users who viewed and clicked the #DisabiltyInnovationDay tag attached to AT2030 work, and those viewing media from our Stigma programme on social media.
- 4,000 unique users accessing AT2030 material on AT2030.org

All of the figures above are measured and tracked though:
- Partner reporting, especially with respect to service delivery models where change and uptake at the national/organisational level can be identified.
- Research and insights monitoring by partners and/or third-party research/evaluation to ascertain the value-add of programme support.
- Media analytics and event monitoring.

Annex B: Output 2.1: Peer reviewed articles / journal articles published

Previously Reported in 2019/20 Annual Review	Newly Reported in this Annual Review Period

Paper	Platform / Journal
Estimating assistive product need in x and India: results of population‐based surveys and comparison of self‐report and clinical impairment assessment approaches	Tropical Medicine & International Health / Volume 26, Issue2, February 2021, Pages 146-158 / https://onlinelibrary.wiley.com/doi/10.1111/tmi.13523
Additive Manufacturing Techniques for Smart Prosthetics Liners	Medical Engineering & Physics Journal / Volume 87, January 2021, Pages 45-55 / https://www.sciencedirect.com/science/article/abs/pii/S1350453320301703?dgcid=rss_sd_all
Bridging the Divide: Exploring the use of digital and physical technology to aid mobility impaired people living in an informal settlement	ASSETS '20: The 22nd International ACM SIGACCESS Conference on Computers and Accessibility October 2020 Article No.: 50 Pages 1–13 / https://doi.org/10.1145/3373625.3417021
Assistive Technology Use and Provision During COVID-19: Results From a Rapid Global Survey	International Journal of Health Policy and Management / https://www.ijhpm.com/article_3954_ec965671ae00a3f198168e08a53dbf21.pdf
Developing inclusive and resilient systems: COVID-19 and assistive technology	Disability & Society / Volume 36, 2021 - Issue 1 / https://www.tandfonline.com/doi/full/10.1080/09687599.2020.1829558
COVID-19 as social disability: the opportunity of social empathy for empowerment	BMJ Global Health, 2020-5 / https://gh.bmj.com/content/5/8/e003039
The Return on Investment and Cost-Benefits of AT Provision	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Methods in Estimating Demand and Supply of AT	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Innovation Strategies and processes to improve access to AT	Global perspectives on assistive technology: proceedings of the GReAT Consultation 2019, World Health Organization, Geneva, Switzerland, 22–23 August 2019. Volume 2 / https://apps.who.int/iris/handle/10665/330372
Value beyond function: analysing the perception of wheelchair innovations in Kenya	ASSETS '20: The 22nd International ACM SIGACCESS Conference on Computers and Accessibility October 2020 Article No.: 37 Pages 1–14 / https://doi.org/10.1145/3373625.3417017
Inclusion and Independence: The impact of Mobile Technology on the Lives of Persons with Disabilities in Kenya and Bangladesh	IEEE Global Humanitarian and Technology Conference (GHTC), 2020, pp. 1-8. / https://ieeexplore.ieee.org/document/9342934
Disability design and innovation in computing research in low resource settings	The International ACM SIGACCESS Conference on Computers and Accessibility (26/10/20 - 28/10/20) / https://cdn.disabilityinnovation.com/uploads/documents/Global-Inclusion-Workshop-CHI2021_accepted.pdf?v=1611665681
Uncovering unexpected impacts: the case of digital manufacturing of wheelchairs in Kenya	RESNA 2020 Virtual Conference, GAATO/RESNA Assistive Technology Outcomes/Impact Summit / https://www.resna.org/sites/default/files/conference/2020/GAATO/150Barbareschi.html
The Digital and Assistive Technologies for Ageing initiative: Learning from the GATE initiative	The Digital and Assistive Technologies for Ageing initiative: learning from the GATE initiative, VOLUME 1, ISSUE 3, E94-E95, DECEMBER 01, 2020 / https://doi.org/10.1016/S2666-7568(20)30049-0 / https://at2030.org/the-digital-and-assistive-technologies-for-ageing-initiative/
Applying market shaping approaches to increase access to assistive technology: Summary of the wheelchair product narrative	Global Report on Effective Access to Assistive Technology: Applying Market Shaping Approaches to Increase Access to Assistive Technology: Summary of the Wheelchair Product Narrative, 22- 23 August 2019 / https://discovery.ucl.ac.uk/id/eprint/10084646/ / https://at2030.org/pn-wheelchair-summary/
Intersections between systems thinking and market shaping for assistive technology: the smart (Systems-Market for assistive and related technologies) thinking matrix	International Journal of Environmental Research and Public Health, 2018, 15(12), 2627 / https://doi.org/10.3390/ijerph15122627 / https://at2030.org/systems-thinking-and-market-shaping/
Mobile phones as assistive technologies: gaps and opportunities	UCL Discovery, GReAT Summit 2019, 22-23 August 2019, Geneva, Switzerland, 22 August 2019 - 23 August 2019 / https://discovery.ucl.ac.uk/id/eprint/10084648/1/Mobile-Phones-as-Assistive-Technologies-Gaps-and-Opportunities.pdf / https://at2030.org/mobile-phones-as-assistive-technologies/
Capturing and Creating Value in the Assistive Technologies Landscape through a Mission-Oriented Approach: A New Research and Policy Agenda	WHO AT Conference, August 2019, Project: AT2030 - Life Changing Assistive Technology for All / https://at2030.org/data-and-evidence-working-paper-series/
Capturing and Creating Value in the Assistive Technologies Landscape through a Mission-Oriented Approach: A New Research and Policy Agenda	WHO AT Conference, August 2019, Project: AT2030 - Life Changing Assistive Technology for All / https://at2030.org/data-and-evidence-working-paper-series/
COVID-19 as social disability: the opportunity of social empathy for empowerment	BMJ Global Health, Volume 5 Issue 8, http://dx.doi.org/10.1136/bmjgh-2020-003039
New economics of assistive technology: A call for a missions-approach	UCL Institute for Innovation and Public Purpose https://at2030.org/new-economics-of-assistive-technology:-a-call-for-a-missions-approach/
Critical Junctures in Assistive Technology and Disability Inclusion	The Official Journal of RESNA, Volume 22, 2021, Issue Sup 1: Companion Papers to the Global Report on Assistive Technology / https://doi.org/10.1080/10400435.2021.2003658 / https://at2030.org/critical-junctures-in-assistive-technology-and-disability-inclusion/
Introduction to the companion papers to the global report on assistive technology	The Official Journal of RESNA, Volume 22, 2021, Issue Sup 1: Companion Papers to the Global Report on Assistive Technology / https://doi.org/10.1080/10400435.2021.2003658 / https://at2030.org/companion-papers-to-the-global-report-on-assistive-technology/
GREAT: Selfsustainable Assistive & Accessible Technology for Low Resource Settings	Great Summit Submission Theme 9: ‘Effective Access to AT’, Overcoming systematic global barriers to AT: a new methodology and quickstart testing through a £20m programme. / https://discovery.ucl.ac.uk/id/eprint/10084627/1/107_AUSTIN_Victoria-Overcoming-systematic-global-barriers-to-AT-a-new-methodology-and-quick-start-testing-through-a-%C2%A320m-programme.-V2.pdf / https://at2030.org/great-selfsustainable-assistive-and-accessible-technology-for-low-resource-settings/
“Give Us the Chance to Be Part of You, We Want Our Voices to Be Heard”: Assistive Technology as a Mediator of Participation in (Formal and Informal) Citizenship Activities for Persons with Disabilities Who Are Slum Dwellers in Freetown, Sierra Leone	Int. J. Environ. Res. Public Health 2021, 18(11), 5547; https://doi.org/10.3390/ijerph18115547 / https://at2030.org/assistive-technology-as-a-mediator-of-participation/
“This Is the Story of Community Leadership with Political Backing.(PM1)” Critical Junctures in Paralympic Legacy: Framing the London 2012 Disability Inclusion Model for New Global Challenges	Sustainability 2021, 13(16), 9253; https://doi.org/10.3390/su13169253 / https://at2030.org/critical-junctures-in-paralympic-legacy/
A review of innovation strategies and processes to improve access to AT: Looking ahead to open innovation ecosystems	The Official Journal of RESNA / Volume 33, 2021 - Issue sup1: Companion Papers to the Global Report on Assistive Technology / https://www.tandfonline.com/doi/full/10.1080/10400435.2021.1970653 / https://at2030.org/a-review-of-innovation-strategies-and-processes-to-improve-access-to-at-looking-ahead-to-open-innovation-ecosystems/
Could Assistive Technology Provision Models Help Pave the Way for More Environmentally Sustainable Models of Product Design, Manufacture and Service in a Post-COVID World?	Sustainability 2021, 13(19), 10867; https://doi.org/10.3390/su131910867 / https://at2030.org/assistive-technology-provision-models/
Estimating need and coverage for five priority assistive products: a systematic review of global population-based research	BMJ Global Health, 2022; 7: e007662. doi:10.1136/ bmjgh-2021-007662 / https://gh.bmj.com/content/7/1/e007662.abstract / https://at2030.org/estimating-need-and-coverage-for-five-priority-assistive-products/
Measuring assistive technology supply and demand: A scoping review	The Official Journal of RESNA / Volume 33, 2021 - Issue sup1: Companion Papers to the Global Report on Assistive Technology / https://doi.org/10.1080/10400435.2021.1957039 / https://at2030.org/measuring-assistive-technology-supply-and-demand-a-scoping-review/
Developing inclusive and resilient systems: COVID-19 and assistive technology	Disability & Society, Volume 36, 2021, Issue 1 / https://doi.org/10.1080/09687599.2020.1829558
“When They See a Wheelchair, They’ve Not Even Seen Me”—Factors Shaping the Experience of Disability Stigma and Discrimination in Kenya	April 2021 / International Journal of Environmental Research and Public Health 18(8):4272 / DOI:10.3390/ijerph18084272 / https://at2030.org/experience-of-disability-stigma/
Shifting the focus to functioning: essential for achieving Sustainable Development Goal 3, inclusive Universal Health Coverage and supporting COVID-19 survivors	Global Health Action, Volume 14, 2021, Issue 1, https://doi.org/10.1080/16549716.2021.1903214 / https://at2030.org/shifting-the-focus-to-functioning-essential-for-achieving-sustainable-development-goal-3-inclusive-universal-health-coverage-and-supporting-covid19-survivors/
Estimating Need for Glasses and Hearing Aids in The Gambia: Results from a National Survey and Comparison of Clinical Impairment and Self-Report Assessment Approaches	Int. J. Environ. Res. Public Health 2021, 18(12), 6302; https://doi.org/10.3390/ijerph18126302 / https://at2030.org/estimating-need-for-glasses-and-hearing-needs-in-the-gambia/

Annex C: Output 2.2: Influencing papers

Previously Reported in 2019/20 Annual Review	Newly Reported in this Annual Review Period

Applying Market Shaping Approaches to Increase Access to Assistive Technology: Summary of the Wheelchair Product Narrative https://discovery.ucl.ac.uk/id/eprint/10084646/
Disability, inclusion and cities: can COVID-19 trigger change? https://www.iied.org/disability-inclusion-cities-can-covid-19-trigger-change
Gender and disability in informal settlements during COVID-19: What we have learnt so far https://at2030.org/gender-and-disability-in-informal-settlements-during-covid19.what-we-have-learnt-so-far/
The Politics of Making Disability Visible in Community-led Urban Research https://blogs.ucl.ac.uk/dpublog/2020/02/26/the-politics-of-making-disability-visible-in-community-led-urban-research/
Celebrating International Disability Day in Sierra Leone https://at2030.org/celebrating-international-disability-day-in-sierra-leone/
International Day of Persons with Disabilities in informal settlements in Sierra Leone and Indonesia https://at2030.org/international-day-of-persons-with-disabilities-in-informal-settlements-in-sierra-leone-and-indonesia/
Understanding the impact of COVID-19 on disabled people's daily lives https://www.youtube.com/watch?v=TGnbMIo4hU4&ab_channel=TheBartlettDevelopmentPlanningUnit
AT2030: Community led solutions - Methods & Findings Phase 1 (2019) https://www.ucl.ac.uk/bartlett/development/research-projects/2021/feb/at2030-community-led-solutions
Powering Inclusion: AI and AT. The findings of an online expert roundtable https://at2030.org/powering-inclusion:-ai-and-at.-the-findings-of-an-online-expert-roundtable/
New economics of assistive technology: A call for a missions approach https://at2030.org/new-economics-of-assistive-technology:-a-call-for-a-missions-approach/
Catalysing AT access: Scaling rehabilitative services and increasing access to AT in Kenya https://at2030.org/catalysing-at-access:--scaling-rehabilitative-services-and-increasing-access-to-at-in-kenya/
Summary of Inclusive Design and Accessibility of the Built Environment in Ulaanbaatar, Mongolia https://at2030.org/summary-of-inclusive-design-and-accessibility-of-the-built-environment-in-ulaanbaatar,-mongolia/
An AT Innovate case study: Amparo https://at2030.org/an-at-innovator-case-study:-amparo/
Digital Fabrication of Lower Limb Prosthetic Sockets https://at2030.org/digital-fabrication-of-lower-limb-prosthetic-sockets/
Exploring the experience of persons with disabilities of using mobile technology in their daily lives in Kenya and Bangladesh https://www.disabilityinnovation.com/blog/exploring-the-experience-of-persons-with-disabilities-of-using-mobile-technology-in-their-daily-lives-in-kenya-and-bangladesh
Opportunities and challenges for disability inclusion during the COVID-19 pandemic https://www.disabilityinnovation.com/blog/opportunities-and-challenges-for-disability-inclusion-during-the-covid-19-pandemic
Inclusive Education in Low Resource Settings’ Webinar in February 2021 (UNICEF-led, but aligned to the procurement workshops under AT advocate network). https://en.unesco.org/gem-report/events/2021/webinar-inclusive-education-low-resource-settings
AT Impact Fund: How we do impactful research https://www.disabilityinnovation.com/blog/at-impact-fund-how-we-do-impactful-research
Building the Assistive Technology ecosystem, one coffee at a time https://rhysjwilliams.medium.com/opening-the-doors-of-assistive-technology-one-coffee-at-a-time-181e63a3d14b
Assistive product specifications and how to use them https://apps.who.int/iris/bitstream/handle/10665/339851/9789240020283-eng.pdf
Assistive Technology: What is in a name? https://at2030.org/assistive-technology,-what-is-in-a-name?/
Celebrating Inspirational Entrepreneurs Building Tech that Matters for Africa https://at2030.org/celebrating-inspirational-entrepreneurs-building-tech-that-matters-for-africa/
An Eye for Inclusion: GDI Hub partners with NIUA for global photography competition ‘an Eye for Inclusion” https://www.disabilityinnovation.com/news/an-eye-for-inclusion-gdi-hub-partners-with-niua-for-photography-competition-an-eye-for-inclusion
Co-design workshop exploring inclusive and accessible urban environment in Varanasi, India https://www.disabilityinnovation.com/news/id-workshop-varanasi-india
New 'Innovation Action Insights' podcast launched - episode 1: https://www.disabilityinnovation.com/news/podcast
Mobile-powered employment opportunities for all; up to £20k available for Bangladesh solutions https://www.disabilityinnovation.com/news/mobile-powered-employment
Episode 2 of Innovation Action Insights podcast now live - exploring COVID-19 Innovations https://www.disabilityinnovation.com/news/episode-2-podcast
First ever global guide for assistive technology to improve the life of millions https://www.disabilityinnovation.com/news/first-ever-global-guide-for-assistive-technology-to-improve-the-life-of-millions
Episode 3 of Innovation Action Insights podcast - exploring Sustainability & Circular Economy https://www.disabilityinnovation.com/news/episode-3
New podcast - Innovation Action Insights explores Assistive Technology https://www.disabilityinnovation.com/news/new-podcast-4
What is assistive technology? LSHTM Presentation at ICED conference https://www.lshtm.ac.uk/sites/default/files/2019-11/BOGGS_LSHTM%20ICED%20PENDA%20conference%202019%20FINAL_no%20notes.pdf
What is Assistive Tech, who is it for, and what does it enable? https://www.disabilityinnovation.com/blog/what-is-at
Inclusive Design Research in a Pandemic: Working Remotely in Ulaanbaatar, Mongolia https://www.disabilityinnovation.com/blog/inclusive-design-research-in-a-pandemic-working-remotely-in-ulaanbaatar-mongolia
	AT2030: Community Led Solutions. Assistive Technology in Informal Settlements in Sierra Leone and Indonesia https://at2030.org/at2030-community-led-solutions-assistive-technologies-in-informal-settlements-in-sierra-leone-and-indonesia/
		Exploring the experience of persons with disabilities of using mobile technology in their daily lives in Kenya and Bangladesh https://www.disabilityinnovation.com/blog/exploring-the-experience-of-persons-with-disabilities-of-using-mobile-technology-in-their-daily-lives-in-kenya-and-bangladesh
	Disability, inclusion and cities: can COVID-19 trigger change? https://www.iied.org/disability-inclusion-cities-can-covid-19-trigger-change
	Opportunities and challenges for disability inclusion during the COVID-19 pandemic https://www.disabilityinnovation.com/blog/opportunities-and-challenges-for-disability-inclusion-during-the-covid-19-pandemic / AT Impact Fund: How we do impactful research https://www.disabilityinnovation.com/blog/at-impact-fund-how-we-do-impactful-research / Gender and disability in informal settlements during COVID-19: What we have learnt so far https://at2030.org/gender-and-disability-in-informal-settlements-during-covid19.what-we-have-learnt-so-far/
	Building the Assistive Technology ecosystem, one coffee at a time https://at2030.org/building-the-assistive-tech-ecosystem,-one-coffee-at-a-time/
	The Politics of Making Disability Visible in Community-led Urban Research https://at2030.org/the-politics-of-making-disability-visible-in-community-led-urban-research/ / Assistive Technology: What is in a name? https://at2030.org/assistive-technology,-what-is-in-a-name?/
	Innovation Action Insights Episode 5 podcast – materials https://innovationaction.org/podcasts/
	Shujaaz Inc. Groundtruth Report https://www.at2030.org/static/at2030_core/outputs/Annex_A_-_SHUJAAZ_INC_DISABILITY_CAMPAIGN_DESK_REVIEW__GROUND_W0TJ7Fp.pdf / Shujaaz Inc. Final Report https://www.at2030.org/static/at2030_core/outputs/SHUJAAZ_INC_FINAL_NARRATIVE_REPORT.pdf / Assistive Technology in urban low-income communities in Sierra Leone & Indonesia https://www.ucl.ac.uk/bartlett/development/sites/bartlett_development/files/rata_report_final_20jan22.pdf / Preventing lifelong impairment: Access to clubfoot treatment in low-and-middle-income countries https://at2030.org/static/at2030_core/outputs/AT_Clubfoot_Narrative_April_2021_Final.pdf
	Understanding the mobile disability gap https://at2030.org/static/at2030_core/outputs/GSMA_Understanding-the-mobile-disability-gap_116pg_Accessible_QEXwKVP.pdf / Country Capacity Assessment for Assistive Technologies: Informal Markets Study, Sierra Leone https://www.ucl.ac.uk/bartlett/development/sites/bartlett/files/at2030_dpu_informal_merkets_study_sierra_leone_16_nov.pdf / Country Capacity Assessment for Assistive Technologies: Informal Markets Study, Indonesia https://www.ucl.ac.uk/bartlett/development/sites/bartlett/files/at2030_dpu_informal_markets_study_indonesia_final_16_nov_.pdf / Lessons learned from assistive technology country capacity assessments, 2019-2020 https://at2030.org/static/at2030_core/outputs/CCA_Lessons_Learned_-_AT_2030_template_final_OCT_2020.pdf
	Ghana Country Assessment https://at2030.org/internal/resources/Country_Assessments/
	Malawi Country Assessment https://at2030.org/internal/resources/Country_Assessments/
	Zambia Country Assessment https://at2030.org/internal/resources/Country_Assessments/
	GDI Hub at COP26 https://www.disabilityinnovation.com/news/gdi-hub-at-cop26
	A World Apart: A Global Clubfoot Journey Fuelled by One Woman’s Resolve https://www.disabilityinnovation.com/blog/a-world-apart-a-global-clubfoot-journey-fuelled-by-one-womans-resolve
	hearX – ENT UK Global https://www.disabilityinnovation.com/blog/a-world-apart-a-global-clubfoot-journey-fuelled-by-one-womans-resolve
	Assistive technology innovators across emerging markets https://at2030.org/at-innovators/map/ / Kenyan Assistive Technology Ecosystem Strengthening https://at2030.org/kenyan-assistive-technology-ecosystem-strengthening/
	Designing for resilience through circular economy https://at2030.org/designing-for-resilience-through-circular-economy/
	A Preliminary Study to Understand How Mainstream Accessibility and Digital Assistive Technologies Reaches People in Lower- and Middle-Income Countries https://at2030.org/resna-annual-conference-2021/

Annex E: Output 3.3 – Full list of case studies
Additions this Reporting Period
1. Inclusive Design and Accessibility of the Built Environment [Varanasi, India], Full Report (112 Pages)
2. Inclusive Design and Accessibility of the Built Environment [Solo, Indonesia], Full Report (13 Pages)
3. ‘How mobile operators are driving inclusion of persons with disabilities” case study, documenting digital inclusion initiatives implemented by mobile network operators and providing recommendations for the digital inclusion of people with disabilities Full report (36 pages) Full Video
4. AT innovation ecosystem design – a Kenyan case study Full Report (17 Pages)
5. An AT Innovator Case Study: Amparo Full Report (16 pages)
6. Access to life changing spectacles for millions. A new vision for KwaZulu Natal, South Africa Full Report (4 pages)
7. Applying market shaping approaches to increase access to assistive technology: Summary of the wheelchair product narrative as an illustrative case study Full Report (17 Pages)
8. Case study: Developing product narrative to guide sector investments behind a unified access approach Full Report (6 Pages)

Reported in Previous Annual Reviews
Inclusive Design and Accessibility of the Built Environment [Ulaanbaatar, Mongolia], Full report
(87 pages), Summary (8 pages), Overview of Inclusive Infrastructure (web page)
1. Catalysing AT access: Scaling rehabilitative services and increasing access to AT [Kenya] Full Report (6 pages)
2. The Liberia Evidence Lab: A new scalable model to deliver School Eye Health [Liberia] Full Report (7 pages)
3. Catalysing AT access: A unified approach to fund and provide AT services [Indonesia] Full report (5 pages)
4. Practitioner Case Study: Assistive Technology Country Capacity Assessment using WHO Assistive Technology Assessment-Capacity Tool Full report
5. - 17. Video case studies to showcase role of mobile as an assistive tech for PWD in Kenya and Bangladesh
  1. Full Video - Sumona
  2. Full Video – John
  3. Full Video – Angie
  4. Full Video - Joseph

Annex F: Output 4.3 – Implementation of Country Capacity Assessment (CCA) recommendations
CHAI Sierra Leone
In Sierra Leone, the CCA identified the need for an AT data and information system that can enumerate the actual number of disabled persons within Sierra Leone, as well as their AT needs.  To address this gap, CHAI is supporting the development of the Development Health Information System (DHIS2) that will ensure routine capturing of AT service delivery information for existing national programs.

Another recommendation that came out of the Sierra Leonean CCA was the development of a national AT strategy and AT policy. In response, CHAI is leading the development of a national AT Policy Strategy, inclusive of monitoring and evaluation plans as well as an Assistive Technology Priority Products List (APL).

These documents will guide the Government of Sierra Leone, ensuring that the provision of AT, as well as Sierra Leoneans access to it, is a priority at the national level.

CHAI Liberia
A challenge identified in the Liberian CCA, was the foundational gaps that currently hinder the ability of Liberia’s health and social systems to deliver AT.  For example, Liberia lacked a coordinated mechanism among its government that could ensure effective implementation of strategies to improve access to AT.  Under Liberia’s CIF grant, CHAI is supporting the government to establish a cross-sectoral technical working group  (TWG) for AT to increase knowledge-sharing, improve collaboration, maximise resources and ensure sustained government ownership over AT activities.

Additionally, Liberia also lacked a national assistive products list (APL) that contained adequate technical specifications for assistive products. In response to another recommendation made in the Liberian CCA, CHAI is working to develop a national priority assistive products list suitable to the Liberian context, that aims to solidify government prioritisation of select assistive products based on population demands, to guide procurement/donations, and to ensure AT is discussed during government supply planning and budgeting.

CHAI Nigeria
One of the priority recommendations within the Nigerian CCA, was to strengthen a coordinated national effort for increased access to AT.  In response to this recommendation, CHAI is working with the Federal Ministry of Humanitarian Affairs, Disaster Management and Social Development to develop a national roadmap aimed at accelerating access to AT that includes a monitoring and evaluation plan that will track progress for coordination of the sector.

Another recommendation from the CCA was to develop sustainable financing for AT procurement and provision. In response, CHAI is working with the Federal Ministry of Humanitarian Affairs, Disaster Management and Social Development as well as state governments to identify innovative financing mechanisms for AT procurement at a national level, and to develop an investment care for inclusion for priority AT into state funding mechanisms for social development.

CHAI Rwanda
For Rwanda, the CCA process identified that there is no centralised data system that can comprehensively and accurately capture information on AT needs, types, causes of disability, service, and product provision. In response, CHAI is supporting the development of a national AT data system in the form of a Disability Management Information System (DMIS) that will inform decision making and policy implementation and support improved data on AT.

Another priority recommendation from the Rwandan CCA was create a coordination mechanism that clearly delineates roles and responsibilities for AT stakeholders and can ensure the implementation of a coordinated AT strategy.  To address this recommendation, CHAI is supporting the National Council for People with Disabilities (NCPD) to revamp the technical working group (TWG) by creating a sub-committee focused on AT that will build evidence and provide guidance to the government on critical areas of policy and regulatory formulation and implementation, including, planning, financing, and M&E.

Annex G: Paralympic Broadcast Audience