## Annual Review 2024-2025

Title: AT2030 – Life Changing Assistive Technology for All
Programme Value £ (full life): £50.8m		Review date: 11 December 2025
Programme Code: [AMP ID#] 300815-101	AMP start date: 28/01/2019	AMP end date: 31/03/2030

Summary of Programme Performance
Year	1	2	3	4	5	6
Overall Output Score	A+	A+	A+	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW
Description of programme
The AT2030 programme, part of the Research and Evidence Directorate (RED)’s portfolio and delivered by the Global Disability Innovation Hub (GDI Hub) addresses the global challenge of limited access to Assistive Technology (AT), which affects an estimated 2.5 billion people worldwide. In some low- and middle-income countries (LMICs), access to essential AT—such as wheelchairs, hearing aids, prosthetics, eyeglasses, and digital solutions—remains as low as 3%[1]. AT2030 aims to unlock economic and social potential by enabling people with disabilities to access healthcare, education, and essential services, thereby supporting their participation in work, community and family life.
[1] UNICEF and WHO Global Report on AT.
AT2030 tests and develops scalable models of innovative approaches to improve access to affordable AT in LMIC countries, focusing on the development of new products, service delivery models, and strengthening global capacity. The programme is designed to be adaptive, investing in a range of new technologies and delivery contexts to identify effective solutions and scale those that demonstrate impact. This aligns with the UK Government’s priority to modernise its approach to development, putting partnerships first, and supporting the growth agenda. Over its lifetime, AT2030 is expected to benefit 18 million people directly and 40 million indirectly, contributing to greater inclusion and improved quality of life for persons with disabilities in LMICs.
This Annual Review covers the period from 1 April 2024 to 31 March 2025.
Summary supporting narrative for the overall score in this review
During the reporting year, AT2030 exceeded or met expectations against all but two impact, outcome and output indicators. A few highlights include:
- Benefited over 506,000 people directly, exceeding the cumulative target by over 370,000 people. This significant increase in engagement was due to the successful impact of the AT2030 Para Sport Against Stigma events and engagements at the Paris 2024 Paralympics.[2]
  [2] These events were referenced in the previous annual review (2023/24), but the data is for this reporting year
- Supported 13 innovative assistive technology ventures through the Attvaran Assistive Technology start-up accelerator. This initiative, delivered in partnership with University College London (UCL), the Indian Institute of Technology (IIT) Delhi, GDI Hub, and IIT Madras, enabled participating Indian start-ups to achieve an average 114% increase in grant funding following the programme’s intervention. This reflects improved capacity and readiness to access further public and private funding.
Raised £4,750,338 in match funding (funding and in-kind) through partnerships where knowledge, expertise and finances were brought into AT2030 at no additional financial cost to the programme.

Published 19 peer-reviewed journal articles which were shared widely to inform the broader global AT sector.

Collaborations with WHO and UNICEF created demand for new products through global procurement catalogues, significantly lowering the cost of goods in LMICs. For example, in Rwanda, the price of hearing aids was reduced by 94%, from $2,000 to $118, resulting in a shipment of 1,200 hearing aids as part of a pilot programme that concluded in 2024/25.

After four years of extensive research conducted across six cities worldwide, launched the Global Action and Global Comparison reports offering practical guidance on designing inclusive cities for all, including people with disabilities.

Launched the Centre for Digital Language Inclusion (CDLI) in partnership with the Royal Academy of Engineering, University of Ghana, and Talking Tipps, with significant match funding from Google. The centre is collecting non-standard speech datasets for 10 languages in 4 countries in Africa to develop Automatic Speech Recognition AI models, to support people with atypical speech.

Created 31 partnerships leveraging AT2030 experience and knowledge to increase capacity and access to AT by embedding AT within partners’ delivery models.

Major lessons and recommendations for the year ahead
Lessons:
- Disaggregation: Collecting disaggregated data across the AT2030 programme is complex and challenging due to the programme’s broad geographic spread, diverse stakeholder involvement, and varying capacities for data collection by partners and countries. Many regions where the programme operates face systemic barriers such as limited infrastructure, inconsistent data standards, and under-resourced local institutions, which hinder the reliable collection of detailed data, especially those disaggregated by gender and detailed data on types of disability.
- AT Growth Fund (ATGF): The importance of engaging the General Partner (GP, responsible for fund management) early, aligning incentives, and investing in GDI Hub–GP relationship to support co-owned fundraising, awareness and pipeline development work.
- Safeguarding: AT2030’s approach to safeguarding requires strengthening to ensure more consistent and targeted implementation. Safeguarding standards, while present, need to be more robustly embedded, contextually adapted, and actively monitored.
- Impact assessment: Reach has been included to assess the impact of the programme to date. However, on its own and as the programme matures, this is not a suitable, rigorous indicator to measure the broad degree of impact the programme has on an individual, community, national and international levels.
Recommendations:
- Disaggregation: To improve the collection of disaggregated data by gender and by type of disability, the programme management team will use a coordinated, capacity-building approach, to work alongside partners to improve data collection techniques, particularly where resources are limited, and where the cultural context is important to consider. GDI Hub should develop standardised data collection tools and guidelines - co-designed with AT2030 partners, women and people with a range of disabilities - to ensure consistency and relevance across diverse contexts. To be completed by March 2026.
- ATGF: A level of training or awareness raising will likely be necessary to build the capacity of the GP in disability inclusion and AT and to build out their associated networks. To be completed in 2025/26.
- ATGF: Alternative plans for fundraising should be put in place and, with support from FCDO and GDI Hub, the GP should take advantage of international events and plan targeted fundraising events for potential investors. To be completed by October 2026.
- Safeguarding: GDI Hub should continue to work alongside FCDO to strengthen the programme’s approach to safeguarding by drawing on best practices and lessons learned from other TIU partners. The programme will collaborate with downstream partners to ensure that safeguarding measures are contextually and culturally appropriate, with a strong emphasis on effective implementation, ongoing monitoring, and evaluation. The safeguarding policy will be re-developed in 25/26 and cascaded to all programme partners for implementation, including identifying a named safeguarding focal person for the programme. To be implemented by September 2026 (in line with Due Diligence recommendations)
- Budget reductions: In anticipation of a new spending environment, as the UK government reduces Official Development Assistance to 0.3% of GNI scenario planning should be undertaken and logframe milestones adjusted accordingly if budget reductions are confirmed. To be completed by February 2026.
- Impact assessment: The programme should assess and implement a broader range of robust indicators to better understand the impact of the programme at individual, community, national and international levels. To be implemented by 1 April 2026.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC) was updated following the approval of the Business Case Addendum (BCA), and in response to compliance audits and stakeholder feedback. These highlighted the need for adjustments to ensure project success and regulatory adherence. The updated ToC (see diagram below) was implemented in April 2024.

Figure 1: AT2030 Theory of Change (revised, March 2024)
AT2030 outcome targets are on track, reflecting the expected ToC causal linkages from inputs to outputs and to outcomes. Supporting evidence provides no cause for any changes to the assumptions that underpin the ToC or the BCA or that challenge the design of the programme. Therefore, there are no reasons to propose changes to the ToC at this time.
In line with the ‘Leave No One Behind’ agenda, AT2030 is a programme with disability at the centre. While it is on track to meet Gender Equality and Public Sector Equality Duty commitments, it could make improvements, particularly around gender and disability type data disaggregation, and the ability to compare results, including across geographies.
It has been noted that there have been challenges in terms of the disaggregation and comparability of data by gender and by type of disability across every programme workstream. However, GDI Hub are continuing to make improvements, including in more difficult LMIC contexts. They will develop innovative standardised data collection tools and guidelines to enable the comparison of data across workstreams and to draw conclusions and recommendations aimed at women, people with different disabilities and different AT needs, and across geographies. These will be developed with women with disabilities, and people with a range of different disabilities in different LMIC contexts. These tools, once tested, will enable AT2030, and other disability AT research, innovation or intervention programmes, and governments, to collect standardised data across the sector.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Impact Indicator	1 & 2
Title	Direct Reach (1) and Indirect Reach (2)

Table 1: Breakdown of reach
Reach	Achievements in 2024/25	(Cumulative) Target / By 31 March 2025	(Cumulative) Achieved / By 31 March 2025
Direct (People)	506,852	1,328,145	1,699,997
Direct (Systemic)	838,321	8,792800	8,858,622
[Direct total]	[1,345,173]	[10,120,945]	[10,558,619]
Indirect	25,888,836	29,622,000	54,005,949
TOTAL	27,234,009	39.7m	64,564,568

Please note: apart from direct reach (people), numbers are rounded to the nearest 100. Definitions outlining AT2030’s full definitions of reach can be found in Annex 1.
Significant overachievement is due to substantial unexpected engagement with the Paris 2024 Paralympics from AT2030’s Para Sport Against Stigma, Sector Events & Engagement and Amplification of the Paralympics sub-programmes. Overall reach impact indicator targets for indirect reach in 25/26 will need review.

Impact Indicator		3
Title		Number of life stories reflecting AT life-changing impact
Target (2024/25)	34 (cumulative)
Achieved (2024/25)	37 (cumulative), which includes 7 for this year.

‘Impact Stories | AT2030 Programme’ detail the direct impact of AT2030 on the lives of people with disabilities. Seven Impact Stories were added this year (target for 2024/25 was four). These included:
1. Bala Murugan – The experience of a Deaf student pursuing a tertiary education and the impact of receiving a specialised phone through the AT2030’s ‘Mobile as AT’ project. The phone has live captions, transcription, and video calling features, breaking communication barriers and enabling him to learn effectively and stay connected with his family.
2. Man Kumari – The story of an 11-year-old person with limb difference who received a prosthetic limb using 3D technology, digital modelling, and fabricated using polypropylene filament. This enabled them to walk to school, fetch water, help their mother with chores, and most importantly, playing chungi; a beloved Nepali children’s game - with their friends.
3. Amplifying athletes’ voices through Radio drama - Gladys Chiwinja, a Malawian Para-athlete specialising in sitting volleyball and shot put, and Innocent Katsache, a scriptwriter at Story Workshop Educational Trust (SWET) discuss how sparking interest through radio drama contributed to challenging discrimination, highlighting the transformative power of storytelling in changing perceptions and promoting inclusivity.
Recommendation: As the programme grows in size and ambition and develops more learning evidence across the sector and geographies, AT2030 should assess and implement a broader range of impact indicators to more rigorously measure and communicate the impact of the programme at individual, community, national and international levels (to be implemented by 1 April 2026).
GDI Hub should extend the definition of ‘impact stories’ to include examples at both individual level and at sub-programme, or programme levels – to be implemented in March 2026.

OUTCOMES
AT2030 outcomes are divided into four categories: New Products, Ventures, Ideas, and Delivery Models.
Outcome Indicator	1
Title	New Products[3]
Target (2024/25)	Scale 15 new products (cumulative)
Achieved (2024/25)	15 (cumulative), scaled 2 new products this year
[3] This outcome captures progress scaling, new AT products (e.g. physical/software tools or devices) and AT-related product innovations. It includes existing AT products and AT-related product innovations used in new ways to enable increased access. Please note these may also be linked to ventures but are differentiated as the product/service itself (the ‘what’), rather than the operational/delivery service model (the ‘how’). The latter can be found at Outcome Indicator 2.

Two new products were produced in this reporting year, Wheel Ease Solutions – Azaadi, an electric clip-on kit that converts a manual wheelchair into an electric-powered vehicle in India - and TRUEAssist Technology (see Box 1).

Box 1: TRUEAssist Technology / Country: India / TRUEAssist Technology develops mobility-focused AT solutions for persons with disabilities. The company specialises in adaptive vehicle solutions, enabling greater accessibility in transportation. Their flagship innovation is a swivel seat mechanism for cars, allowing individuals with disabilities to enter and exit vehicles with ease. / Through the Attvaran programme, they were able to enhance their product design, conduct user testing and prototyping, and benefit from capacity development activities such as mentorship, business modelling, and pitch training. This support proved transformative, enabling Wheel Ease Solutions to validate their assistive product through extensive real-user engagement, directly leading to significant design and functional improvements. / TRUEAssist continues to explore a collaboration with Namma Yatri - a ride sharing company (like Uber) and has already leveraged some of their Attvaran funding to improve accessibility in a number of vehicles. They are now in conversation with vehicle manufacturers such as Suzuki to expand their reach. Attvaran also connected them to business strategists and auto retailers to better situate their marketing strategy and business development plans. / "When I started, people told me that mobility solutions for persons with disabilities wouldn’t work because they don’t even have access to public transport. Today, we’re proving that accessible vehicles aren’t just a possibility—they’re a necessity. With GDI Hub’s support, we are bringing this change to life." — Naina Padaki, Founder, TrueAssist Technology / Figure 2: TrueAssist Technology wheelchair user testing.

Outcome Indicator	2
Title	Ventures
Target (2024/25)	38 (cumulative total)
Achieved (2024/25)	38 (cumulative total), 2 new ventures supported to scale this year

‘Ventures’, describes the business organisation and surrounding ecosystem to support AT innovation[4]. Two new ventures were brought to scale through Attvaran, uDot – that creates interactive solutions for the blind and visually impaired to support social and economic inclusion and lifeandlimb.ai in India (see Box 2).
[4] Examples include: improved product development methods, development of robust evidence proving the validity of solutions, acquiring commercial, distribution and/or service links with relevant national and international partners, demonstration of funding or user base increases, or successful implementation of business plans.
This reporting year, AT2030 focussed on the Attvaran accelerator based in India. Attvaran learning is informing South-to-South knowledge transfer. This includes sharing tested models, ecosystem approaches and research - such as inclusive design, user engagement, and venture support - between similar development contexts. This is achieved through AT2030’s Data and Evidence Portal and collaborative events that bring together innovators, policy actors, and delivery partners from India and Africa, creating a dynamic knowledge ecosystem that informs AT innovation practice globally.

As a result of Attvaran support, both uDot and lifeandlimb.ai secured follow-on grant funding, which has helped them to expand their operations and take the solutions to market.
Box 2: lifeandlimb.ai / Country: India Imported prosthetic hands have been estimated to cost approximately $30,000 USD, making them inaccessible to most users in LMICs. LifeandLimb.AI is a pioneering biomechanical and AI-driven prosthetics company based at IIT Kanpur. Their core innovation—myoelectric prosthetic hand motors and batteries to power the movement of devices controlled by electrical signals generated by muscles—is designed to provide affordable, high-quality artificial limbs controlled by Electromyography Muscle Sensor (EMG) sensors. / Through the Attvaran programme, the company engaged in business modelling and evidence-building activities, deepening their understanding of user needs and validating their approach through collaboration with regional, national, and international partners. They have transitioned from being Minimum Viable Product (MVP) stage to early sales. This includes institutional adoption in a large Government rehabilitation centre under the Ministry of Social Justice (ALIMCO) and a non-governmental organisation, Kiwanis, leading to large-scale production to enable wider access to advanced prosthetic hands, orthoses, and soft exosuits that help people with limb loss or limited mobility move more naturally and comfortably. They have now delivered 200+ affordable prosthetic hands to persons with disability. / "Assistive technology is not just about function—it’s about restoring dignity and independence. With GDI Hub’s support, we’ve moved from prototype to impact, ensuring our prosthetic solutions reach those who need them the most." — Nishant Agarwal, Founder & CEO, Life & Limb.AI / Figure 3: Life & Limb.AI prosthetic hand 3D render.

While not all Attvaran ventures reached scale (defined as significant purchase orders/distribution agreements or substantial grant funding/investment), they each amassed learning and experience which enabled them to pivot their approach. Examples are below:

Next Skills 360 Ed Tech Private Limited bridges educational gaps by teaching 21st-century skills and developing accessible coding tools for the visually impaired. Initially developed as a hardware-based Braille solution, the pilot revealed that the first prototype was not appropriate for a wide range of students who had not been taught Braille at school - instead, they used mobile phones. This learning led Next Skills to pivot their approach to a fully digital solution to close the gap, which (after further testing), is expected to reach a broader range of users. While the venture did not reach it’s intended goals during the accelerator, it strengthened its global partnerships, refined its product approach and built a robust business growth plan.

Insighte is a mental health and therapy service provider for children with autism, ADHD, global developmental delays (GDD) and other neurodivergent conditions, offering personalised, evidence-based therapy solutions. With feedback from pilot users and their technology mentor, Insighte recognised that the use of artificial intelligence in their solution required more thorough testing coupled with academic research to avoid potential harms. Therefore, instead of launching their chatbot as planned after the pilot stage, they adjusted their goals to reflect on learning and adjust their product to address the challenges in product alignment, safety and strategy. While a chatbot is still in the pipeline, the solution will require some adaptations.

Outcome Indicator	3
Title	Idea Uptake
Target (2024/25)	56 (cumulative)
Achieved (2024/25)	65 (cumulative), 14 achieved this year

This outcome captures the uptake of AT2030 programme ideas, findings and methodologies when there is evidence that they have been adopted by governments or organisations.
14 entities are on track and have implemented AT2030’s ideas during this reporting period. (For the full list, see Annex 2).
Box 3: Dignity kits
In September 2024 AT2030 co-developed inclusive dignity kits. These address disaster or crisis affected women and girls' immediate hygiene needs and promote mobility and safety by providing them with age-appropriate, gender-sensitive, and culturally suitable garments and other essential items.
During this reporting period, this product was included in UNFPA procurement in the Pacific Islands, Sri Lanka, Bangladesh and Indonesia.
Figure 4: A Dignity Kit showing examples of items contained within.

Box 4: Google Relate / Countries: Ghana, Kenya and Nigeria The Google Relate app is an AI-enabled technology developed by Google to help people with non-standard speech. With the app freely available in Ghana, the AT2030 programme trained local speech and language therapists to use the app, creating the opportunity to test and research how the app is currently being used, how it could be used in future, and how it could be improved. / Google examined the findings of the earlier research, and GDI Hub produced an award winning paper . ‘Mobile as AT’ continues to emerge as a dynamic opportunity to change lives. / A number of follow up grants were made by Google to support the implementation of the app, including expansion in Ghana to support other local languages, building research and evidence, and to support the rollout of Google Relate in two other African countries, Kenya and Nigeria. The initial work in Ghana led to Google making the application open source in these three countries, which directly correlates as an idea implemented from AT2030’s work. Google is incorporating this learning into its wider global business model and is piloting this model in Singapore. / Figure 5: Google Relate article published in Financial Times journal.

Outcome Indicator	4
Title	New Service Delivery Models
Target (2024/25)	12 (cumulative)
Achieved (2024/25)	12 (cumulative), 1 achieved this year

This outcome captures the use of AT2030 frameworks and approaches to guide the design, development, deployment, operation and retirement of AT services.
One new innovative service delivery model was reported as on track to scale/scaling up in this reporting year. This year’s target was small due to the new Business Case Addendum and service delivery models taking time to establish, so a realistic goal of ‘1’ was set.
Box 5: Strengthening National Assistive Technology Service Systems in Liberia / Countries: Liberia / In November 2024, to strengthen government AT procurement and data systems, CHAI supported the Ministry of Health in Liberia to review the newly developed, first-ever national AT quantification tool. The tool includes disability prevalence by domain, AT demand (met and unmet) and products delivered. Thirty-two participants gathered to discuss and validate the quantification assumptions for the tool. The workshop was chaired by the Ministry’s National Quantification Technical Committee, with participants including MOH supply chain focal persons, programme managers, health facility clinicians and AT specialists. The user-friendly, Excel-based quantification tool focused on 5 priority products for this first rapid exercise, and has the potential to be expanded for forecasting of additional types of assistive products. / Figure 6: Select attendees from AT Quantification Tool Review Workshop in Monrovia, Liberia / Figure 7: Screen capture of Liberia’s national AT quantification tool

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The AT2030 programme continues to deliver good value for money and impact, directly benefiting over 500,000 people this year alone — surpassing its original target. Its innovative approach, robust evidence base (which it continues to build upon), and strong partnership approaches have positioned the UK as a global leader in AT research and innovation.

AT2030’s work transforms lives and catalyses wider systemic change, leveraging significant match funding and has shown evidence of driving AT policy, research, and market development in LMICs. AT2030 is a strong demonstration of the UK’s commitment to ‘Leave No One Behind’, disability inclusion, developing local partnerships and fostering sustainable development to do development differently.

Continued investment will provide opportunities to test if the programme’s proven models and lessons can be scaled and replicated across new contexts. The programme continues to amplify the UK’s global influence and deliver tangible benefits for some of the world’s most marginalised communities.

## C. DETAILED OUTPUT SCORING
While the output numbers may have changed since the previous Annual Review, in line with the updated logframe, the descriptors, unless otherwise stated, have not.

Output Title	INCLUDE - To grow advocacy, engagement, partnerships and networks with a focus on driving AT access and inclusion, and to develop, use and disseminate strategic tools and case studies.
Output number:		OP1	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N/A (new logframe)

Indicator(s)	Milestone(s) for this review	Progress
1.a Number of partnerships supported to increase AT capacity and access to AT	10	31 / Exceeded expectations
1.b Number of strategic tools developed to increase AT capacity and access to information	5	8 / Moderately exceeded expectations
1.c Number of case studies published	3	12 / Exceeded expectations
1.d Value of matched funding provided through partnerships	£1,950,000	£4,750,338 / Substantially exceeded expectations

OP1: Output description and supporting narrative.
Overall output 1 has exceeded expectations, with a continually growing number of partnerships and by far exceeding the matched funding target for the year. More case studies were published than planned, primarily because partners took the initiative to create more personal stories of change.

1.a Number of partnerships supported to increase AT capacity and access to AT
31 new partnerships were supported this year to increase AT capacity and access. These new partnerships have been instrumental in driving widespread engagement and implementation across the programme. These collaborations, including governments, research institutions, OPDs, NGOs, and private sector actors have enabled the delivery of impactful work on the ground, supported knowledge exchange, and strengthening capacity across regions to advance access to assistive technology. A full list of partners can be found in Annex 3.

Examples of partnerships:
- In Malawi, the Blantyre City Assembly partnered with Loughborough University London’s leads of AT2030’s Para Sport Against Stigma sub-programme to deliver the Tisewere Tonse (Let us All Play) awareness activities.  The activities were conceptualised using the Making Noise toolkit and aimed to promote inclusion and understanding of sports and issues affecting persons with disabilities in the lead up to Malawi’s Disability Awareness Month (November). The Blantyre City Assembly/Mayor was engaged in planning and was present to open the activities, giving the Tiswere Tonse – ‘Let Us All Play’ awareness event maximum support and visibility, further enhanced by the Journalists Association of Malawi who lobbied for more news coverage of the events which contributed to wider publicity. The collaboration resulted in a commitment for future editions of the Blantyre City Games to feature sports for persons with disabilities.
- The International Nepal Fellowship was engaged as a new partner via AT2030 Local Production Systems of AT workstream for the local development of prostheses for leprosy patients.
- The National Centre for the Promotion of Employment of Persons with Disabilities (NCPEDP), Samarthanam Trust, Swami Vivekananda Youth Mission, Enable India, the International Center for Research on Assistive Technology and Accessibility (i-CReAT), the Kerala Medical Technology Consortium, Path India, the India Business Disability Network, the Confederation of Indian Industries and Purple Jallosh were brought together to build out AT2030 Accelerator Attvaran ecosystem expertise in market access, finance, technical assistance and communications.

Partnerships by Country / Partnerships by Sector graph
Figure 8: Partnerships by country and by type.
1.b Number of strategic tools developed to increase AT capacity and access to information
Eight strategic tools were developed to increase AT capacity and access to information against a target of five. These include:

1. A Mentoring Playbook for Disability Innovation designed to support organisations to launch and manage mentoring programmes for early-career researchers and start-ups in the disability innovation sector.
2. Storytelling for disability advocacy workbook aimed at empowering communities to drive meaningful conversations, influence policies, and foster environments where misconceptions and negative perceptions of disability can be challenged.
3. Three additional WHO Training in Assistive Products (TAP) modules in Assistive products in Emergencies, Wheelchairs in Emergencies and Dressing Aids. TAP online modules are designed to prepare primary health and other personnel to fulfil an assistive technology role.
4. I’mPOSSIBLE toolkit localised in Malawi to foster inclusion and challenge perceptions of disability through the values of the Paralympic Movement.
Where possible, these will be tracked for use and influence, for example WHO are leading a global research study on impact and effectiveness of TAP and the I’mPOSSIBLE toolkit is collating impact evidence as a project outcome.

Box 6: Inclusive Design in Cities: A Global action report: A Global Action Report / Countries: Mongolia, India, Indonesia, Kenya, Sierra Leone, Colombia / This report equips cities with practical evidence-based actions to accelerate accessibility and inclusion in their physical infrastructure, buildings, services and operation. This report brings together the lessons learned and recommendations from six case studies from around the world. / Cities worldwide are experiencing continued growth and increasing resource challenges. In LMIC settings, this is particularly challenging, where in many cases huge infrastructural development is necessary. With resource constraints and increasing global challenges (rising inequality, climate changes, pandemics), it is even more critical that accessibility and inclusive design are integrated into the planning and design of cities to ensure persons with disabilities are not left behind. / Disability policy is generally set by national governments, while cities need locally adaptable and practical frameworks for inclusive action. This report sets out the global agenda of inclusive practices for cities to catalyse shared learning and collective efforts and help cities to create an inclusive city. / Figure 6: Global Action Report cover page.

1.c Number of case studies published
In this reporting year, 12 case studies were published which are listed below:
1. Case Study: Making Noise
2. Case Study: Growing a Para Sport Ecosystem in Malawi
3. Case Study: Malawi Para Games
4. Tacilia, Designing Interactive Technology for Blind Students
5. Dance and the Paralympics - a collaboration between UK and South African Deaf and disabled artists to coincide with the 2024 Paralympic Games
6. Storytelling for Assistive Technology Advocacy
7. Personalised Co-creation of Locally Produced Prosthetics in Nepal: Case Study 1 –Prosthetic Foot
8. Personalised Co-creation of Locally Produced Prosthetics in Nepal: Case Study 2 –Prosthetic Hand
9. Zimachitika Para sport Radio Drama – Leveraging Edutainment for Disability Inclusion (see Box 7)
10. Case Study: Paris 2024, Malawi, and the Power of Media: How Making Noise is Changing Disability Narratives
11. Beyond this land - attracting new audiences to Para sport
12. Accelerating access to assistive technology: report on multi-country workshop, Jakarta, Indonesia

Box 7: Zimachitikia Para Sport Radio Drama – Leveraging Edutainment for Disability Inclusion
Countries: Malawi
In Malawi, individuals with disabilities face systemic stigma and social exclusion, often resulting in barriers to education, employment, and community participation.
The Zimachitika Para sport Radio Drama Series was designed to tackle stigma by sharing the experiences of individuals with disabilities through fictional storytelling. By focusing on Para Sports, the drama sought to highlight the capabilities of people with disabilities, foster community discussions, and promote inclusive attitudes. As over 70% of the population rely on radio for trusted information, it’s extensive reach made it an effective tool for engaging diverse audiences, including those in rural areas.
Figure 9: Zimachitika Radio series recording, Blantyre, Malawi
To ensure authentic and impactful narratives, Para athletes participated in a dedicated workshop to share their lived experiences, which directly shaped the storylines.

This output exceeded the target through strong partner engagement, increased programming activity, and growing engagement from downstream partners to document and share evidence of impact across AT2030’s priority countries.

Figure 10: Radio Drama co-design storytelling workshop, Blantyre, Malawi.

1.d	Value of matched funding provided through partnerships
AT2030’s matched funding (in funding or in kind) exceeded expectations, raising more than £2.5m over the annual target toward the programme. Contributions included:

1. WHO: contributed match funding of £1,476,541 from the Government of Ireland, ATscale/UNOPS and in-kind contributions from WHO.
2. UCL: contributed match funding of £1,512,958 from overhead waivers, in-kind operational support to the GDI Hub Community Interest Company (C.I.C) and in-kind staff contributions.
3. Google: contributed £396,500 in match funding towards AT2030’s Automatic Speech Recognition workstream as a part of the CDLI.
4. CHAI: contributed £400,099 in match funding primarily through government contributions in Rwanda and Sierra Leone as well as through CHAI’s Build a World of Play program (BAWOP) funded by LEGO Foundation.
This increase in match funding is testament to the programme’s ongoing and growing impact and credibility in the AT and disability sectors, reflecting the value that global stakeholders place on its work and collaborative approach.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The logframe was redesigned ahead of this performance year in line with the new ToC.
Outputs 1.a, 1.c and 1.d moderately or substantially exceeded expectations. Targets will be reviewed for the 2025/26 performance year to ensure they remain ambitious. In particular, the target for output 1.c (Case Studies published) appears to be too low over a 12-month period, albeit the programme was entering a new phase of delivery at the beginning of the reporting period and with an updated ToC. All subsequent targets will be reviewed in the logframe.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation / from 23/24 Annual Review		Local partnerships: AT2030, supported by UCL and GDI Hub academics, will enhance local partners' capacity and reputations as disability inclusive researchers by sharing technical knowledge and co-authoring papers.
Progress during 2024/25		UCL provided technical knowledge to local partners through training sessions and co-authored papers with researchers in Brazil, Kenya, and India as part of the Mobile as AT project. / In Ghana, UCL collaborated on the Centre for Digital Language Inclusion’s work to develop Automatic Speech Recognition models for individuals with non-standard speech. / Additionally, UCL worked with researchers and implementation partners in Nepal under the programme’s local production systems of assistive technology and sustainable AT ecosystems workstream.
Output Title	INQUIRE - Critical Research Questions are answered and new innovative methodologies produced or trialled.
Output number:			OP2	Output Score:	A
Impact weighting (%):			25%	Weighting revised since last AR?	N/A (new logframe)

Indicator(s)	Milestone(s) 2024/25	Progress
2.a Number of peer reviewed / journal articles published	5	19 / Substantially exceeded expectations
2.b Number of influencing papers, answering important research questions published	15	15 / Met expectations
2.c Number of downloads/views/citations for articles/papers	30,000	28,604 / Almost met expectations

OP2: Output description and supporting narrative.
During this reporting period, the new outputs set out in the ToC have been met or exceeded with the number of peer-reviewed papers and influencing published. The number of downloads, views and citations narrowly missed the annual target. While this appears to be a large number, 30,000 was an ambitious target. 28,604 downloads/views/citations in one year still demonstrates very strong engagement with programme outputs.
2.1 Number of peer reviewed / journal articles published
19 journal articles were published (see Annex 4 for complete list). Due to the nature of publishing papers with unpredictable processing and publishing timelines, several articles submitted last year were published this year and so are included in this data. The number of publications highlights the programme’s ongoing contribution to evidence generation and thought leadership in the global AT and disability sectors.
2.2 Number of influencing papers, answering important research questions published
In the reporting year 2024/25, 15 influencing papers were published, meeting the target set. (See Annex 5 for complete list).
2.3 Number of downloads/views/citations for articles/papers
In the reporting year 2024/25, there were 28,604 downloads, views and citations from published outputs.
The output for the number of downloads and views of articles and papers narrowly missed by 1,396. This shortfall is likely due to a combination of factors, including the technical nature of some papers which are aimed at academic or limited technical audiences, and the timing of publications not aligning with key sector events (due to publishing lags) that typically drive higher engagement. Due to the factors noted above, this is difficult to predict. Three of this year’s most downloaded, viewed or cited papers are:
1. Artificial intelligence alone will not democratise education: on educational inequality, techno-solutionism and inclusive tools (UCL and GDI Hub), (volume 16, 2024), (12,793 views/downloads/citations). This publication focuses on posing questions about the future of AI in Education, intending to initiate the pressing conversation that could set the right foundations (e.g., inclusion and diversity) for a new generation of education that is permeated with AI technology.
2. A Systematic Review of Ability-diverse Collaboration through Ability-based Lens in HCI (UCL and GDI Hub), (volume 11, 2024), (4,043 views/downloads/citations). This review offers an analysis of 117 papers sourced from the ACM Digital Library spanning the last two decades and contributes (1) a unified taxonomy and the Ability-Diverse Collaboration Framework, (2) a reflective discussion and mapping of the current design space, and (3) future research opportunities and challenges.
3. Enhancing Communication Equity: Evaluation of an Automated Speech Recognition Application in Ghana (UCL and GDI Hub), (CHI conference paper), (2,896 views/downloads/citations). This study explores the use of Google Project Relate, a personalised speech recognition app, to support people in Ghana with communication difficulties (see Box 4, p.8 for details of this project).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Given the OP2a milestone for this review moderately exceeded expectations, the 25/26 cumulative milestone of 23 will need to be revised upwards.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation from 23/24 Annual Review	Dissemination: While the AT2030 website’s functionality and search function were improved in 2023/24, further development will take place in 2024/25 to improve access to existing research, data and evidence.
Progress during 24/25	Several improvements were made to the AT2030.org website to enhance usability and accessibility. The publications, blog and news sections were simplified, making information easier to locate. Search functionality was enhanced, allowing users to filter by output and topic. / The website’s structure was redesigned to align with the updated AT2030 programme framework, providing dedicated landing pages for new programme Clusters. / The website homepage achieved the highest level of accessibility certification under the Web Content Accessibility Guidelines (WCAG).

Output Title	INCUBATE - Establishing an AT innovation, venture acceleration or other programme, which either creates or contributes to an existing AT innovation ecosystem
Output number:		OP3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N/A (new logframe)

Indicator(s)	Milestone(s) for this review	Progress
3.a Number of innovative assistive technologies supported	6	13 / Substantially exceeded expectations
3.b Number of Innovation Ecosystem development interventions	2	3 / Exceeded

OP3: Output description and supporting narrative.
Output 3.a has been moderately exceeded, as the Attvaran accelerator supported more ATs than originally planned, mainly due to better-than-expected interest and engagement from partners supporting the accelerator. Output 3.b was assessed as met, although it achieved one more innovation ecosystem intervention than expected.
3.a Number of innovative assistive technologies supported
The Attvaran accelerator moderately exceeded expectations by supporting 13 innovative assistive technologies against a target of eight. This was due to it receiving a significantly higher level of interest and partnership support than expected. The inaugural cohort received notable support from the British High Commission in India as well as from the broader AT ecosystem, reflecting both the demand for inclusive innovation in the region and the growing recognition of the accelerator as a high-impact platform within the AT ecosystem.
The inaugural cohort of Attvaran supported 20 innovative AT companies in total (some at different stages of scale and success) across India with the goal of regional impact. Attvaran subsequently garnered support from 50 partners and mentors, secured over 200% in-kind matched funding and more than £80,000 grants for startups, facilitated exposure for start-ups at several high-profile events, and enriched the ecosystem by hosting 20+ expert guest talks and numerous roundtables and pitch days.

Box 8: SaralX
SaralX is a digital accessibility company dedicated to ensuring that websites, mobile applications, and digital documents are fully inclusive and accessible for all users, including those with disabilities. Their work aligns with global accessibility standards, and they are actively helping organisations comply with accessibility laws and policies.
Through the Attvaran programme, SaralX was able to complete hands-on product testing and strategic refinement of their accessibility solutions, boost industry visibility and engage in valuable knowledge exchange with other assistive tech founders. They supported the introduction of frameworks for scaling, investment readiness, and improved cash flow management.
Taking part in the programme allowed SaralX to shift from early-stage uncertainty to a high-demand business, securing contracts with the Government of India. They developed strategies to build long-term financial sustainability beyond one-off projects, grow their team and begin hiring for leadership roles to support scaling and compliance and to explore global markets.
"Before Attvaran, we were uncertain about the future of SaralX. Today, demand has skyrocketed, and we are scaling fast. GDI Hub’s support provided us with credibility, valuable mentorship, and a network that helped shape our growth trajectory."
— Akashdeep Bansal, Founder & CEO, SaralX
During the reporting period, 13 innovative assistive technologies were supported. These were:
1. Exobot Dynamics
2. Insighte
3. EnableMe Access
4. BeAble
5. SaralX
6. SignAble
7. Dhanvantri Biomedical
8. Panoculon Labs
9. Next Skills 360 EdTech Private Limited
10. Phonologix Health Solutions
11. Nirvesh Enterprises Private Ltd
12. Grailmaker Innovations Private Ltd
13. Sunbots Innovations LLP
For more details about these products, please go to Annex 6.
3.b Number of Innovation Ecosystem development interventions
Three innovation ecosystem development interventions were achieved. Box 9 offers details of one of these.
Box 9: Centre for Digital Language Inclusion (CDLI): Automatic Speech Recognition / Automatic Speech Recognition is transforming the communication ability of people with a-typical speech. The prevalence of mobile devices, alongside free-to-access apps, is making Automatic Speech Recognition accessible, convenient, and less stigmatising for people with slurred or difficult-to-understand speech. / This year GDI Hub launched the Centre for Digital Language Inclusion (CDLI) with partners the Royal Academy of Engineering, University of Ghana and Talking Tipps. The Centre will collect datasets of non-standard speech to build Automatic Speech Recognition models, enabling disabled people with communication barriers to take advantage of Automatic Speech Recognition software. The centre will also facilitate the development of AI-driven inclusive communication technologies and train others to use this innovative technology. / Building on Google’s work and the knowledge from the AT2030 programme, the CDLI uses AI to develop inclusive communication solutions for non-English-speaking populations in Africa, who have limited access to AT. CDLI is collecting non-standard speech data in native African languages for the first time, developing open-source tools, and training users and innovators. Supported by Google.org, it will expand data collection to more languages, enabling local innovators to build accessible apps and improve communication equality across Africa. / "Google is committed to improving accessibility in emerging markets like Africa, and we are excited to see this initiative make speech recognition more accessible in African languages for people with non-standard speech." / -Sara Basson, Google Emerging Markets Accessibility and Disability Inclusion Lead. / Figure 11: CDLI team and partners at UCL East launch event in January 2025, London, United Kingdom.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The target for 3.a (Number of innovative assistive technologies supported) will be revised for 2025/26.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Lessons:
- Attvaran accelerator: The Indian landscape has emerged as a clear opportunity for AT innovation and disability inclusion. It is now positioned to transform the national AT ecosystem and to contribute to global progress, amplifying the impact of FCDO’s initial investment through greater than expected momentum. This will foster mutual value through UK-India knowledge exchange and GDI Hub’s expertise.
- Follow-on funding: A record of follow-on funding earned by ventures is critical to make the investment case for an AT research and innovation programme.
Recommendations:
Attvaran accelerator: Although AT2030 no longer invests in India, it is recommended that the programme continues to seek opportunities to leverage valuable insights, data, evidence and partnerships to inform and strengthen the AT efforts in other regions, e.g. focussing on South-South AT knowledge transfer from India to sub-Saharan Africa, which for AT is a new pathway for scale and investment. The programme has built the foundations for cross-regional knowledge transfer, scalable models and approaches to inclusive AT innovation. It now has strategies for engaging government, private sector, and grassroots stakeholders and should seek to leverage these through AT2030 and through new funding and support partnerships. Progress will be reported in the 2025/26 AR.
AT2030 will continue to apply learning from previous accelerators such as Attvaran to shape how programs are designed and delivered in African contexts, particularly around locally anchored problem definition, early integration of co-creation, evidence and validation. Insights on where ideas/ventures typically stall, the importance of lived-experience-led design, and the need for strong ecosystem partnerships are directly informing programme structure and delivery in countries such as Ghana, Kenya and Uganda, particularly ensuring the strengthening of local innovation capacity. Progress will be reported in the 2025/26 AR.
Follow-on Funding: GDI Hub should refine AT2030’s approach to collecting follow-on funding data by moving from one-off annual outreach to a more integrated, year-round engagement process. This includes setting clearer expectations with ventures at the outset, venture support touchpoints, and streamlining collection through simplified tools and ongoing relationship management. The new approach should be put into practice in 2025/26. Follow-on funding will be reported as part of AT2030’s more robust impact assessment (recommendation on page 3).

Output Title	INVEST - Accessible & Assistive Technology Growth Fund established with investment crowded in
Output number:		OP4	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	N/A (new logframe)

Indicator(s)	Milestone(s) for this review	Progress
4.a Number of ventures supported to scale innovation	1	0

OP4: Output description and supporting narrative.
This output relates specifically to the Assistive Technology Growth Fund (ATGF). Due to longer than anticipated recruitment and contracting of the General Partner (GP) who will design and run the fund, and the longer than anticipated lead in time for ‘first close’ (referring to when the first tranche of funding is secured), the output did not meet its original target. The recently agreed target date for first close is now June 2026 and at this point, investments in ventures will begin.
4.a Number of ventures supported to scale innovation
As stated above, the ATGF has a delayed timeline. SEAF (previously known as Small Enterprise Assistance Funds) were recruited as the General Partner (GP).
In the reporting year, the pipeline workstream developed a database which included over 500 ventures across priority LMICs. Lists of top 50 and 20 priority ventures were made, supported by structured interviews to understand their market readiness and fit to the ATGF. Engagement with the pipeline was guided by the consulting agency Finance for Good and Inclusive Finance during the business case development stage at the start of the reporting year.
This is an ambitious pilot project and carries some risk. FCDO is working closely with GDI Hub and SEAF to monitor the situation and mitigate risks.
The process of establishing the ATGF has been largely linear and well-structured, from business case development to tendering for both an advisor and a GP. While progress has been steady, it has taken longer than initially anticipated; particularly in identifying and contracting a values-aligned GP and navigating the fundraising climate . Legal and contractual steps proceeded smoothly with strong counsel support from Hogan Lovells. Alongside this, the design and development of the Venture & Ecosystem Strengthening (VES) facility has matured rapidly, aiming to provide tailored, high-impact support to pipeline ventures.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The target for this output will be revised for 2025/26 in line with new project timelines.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is a new output for 2024/25.
Recommendations for 2025/26
Lessons:
- The importance of early GP engagement, aligning incentives, and investing in the GDI Hub–GP relationship to support co-owned fundraising, awareness and pipeline development work.
- The impact of international political shifts may affect the ability of the ATGF to fundraise. Regular reviews of the risk and mitigation strategy are therefore necessary.
Recommendations:
- GDI Hub should prioritise the testing of the VES minimum viable product with selected ventures and accelerate outreach to foundations and institutional investors, with the goal of launching the full VES offer and achieving diversified capital commitments by early 2026 (25/26 FY).
- A level of training will likely be necessary to build the expertise of the GP in disability inclusion and AT and to build out their associated networks. To be completed in 2025/26.
- Alternative plans for fundraising should be put in place and, with support from FCDO and the GDI Hub, the GP should take advantage of international events and plan some specific fundraising activities for potential investors.

Output Title	INTEGRATE - New country pilots, policies and initiatives (e.g. providing support) to embed AT into national/regional/global policy landscapes to stimulate demand, improve supply of AT for LMIC’s as well as in humanitarian contexts to create a more enabling environment.
Output number:		OP5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	N/A (New logframe)

Indicator(s)	Milestone(s) for this review	Progress
5.a Number of pilots, strategies or initiatives at the country, regional or global level	2	2

Output 5a met expectations during this reporting period.

OP5: Output description and supporting narrative.
Two pilots were implemented at a country level during this reporting period. These were: Strengthening Wheelchair Provision Capacity, Zimbabwe and Locking Liner Pilot, Nepal.

Box 10: Strengthening Wheelchair Provision Capacity in Zimbabwe (Pilot) / Country: Zimbabwe / In Zimbabwe, UNICEF collaborated with the government and local stakeholders to pilot wheelchair provision. The aim was to showcase the positive impact of enhanced accessibility and mobility on the lives of children with physical disabilities. The project included the provision of 300 wheelchairs tailored for 5–18-year old’s, emphasising the transformation in their independence, mobility, and engagement in different aspects of life. / To future-proof this service post pilot, comprehensive training and mentorship in seating and 24-hour positioning was given to Rehabilitation Officers and Social Workers within the disability sector. The goal being to empower them to establish and deliver essential seating services for children at their respective institutions and communities. Participants gained a thorough understanding and practical mastery of the core theoretical and practical techniques necessary to deliver quality basic wheelchair services. This included the knowledge required for conducting assessments, measurements, prescriptions, and fittings. / The pilot findings will be used to demonstrate efficacy of the product inclusion and scalability, evidencing the increase in the uptake of added products in LMIC countries, their viability of sustainable small-scale implementation in collaboration with government partners. It will also inform research questions, with expected papers on areas such as 'Market Shaping for AT'. / Figure 12: Rehabilitation Officers and Social Workers at the UNICEF Community-Based Outreach Seating Training.

‘Locking Liner Pilot Nepal’, in partnership with manufacturer Operation Namaste, the University of Kathmandu, and International Nepal Fellowship, evaluated a new version of locking liners. Three patients were fitted with the liner during the pilot study and are being monitored to assess its benefits and the ease of training healthcare providers. A further eight patients have been selected for testing in the next financial year following the pilot.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/A
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation from 23/24 Annual Review	Logframe: Targets should be reviewed on a rolling 6-monthly basis to ensure they are up to date and remain stretching.
Progress during 24/25	Logframe targets are now reviewed as part of the quarterly review process with FCDO programme team. This has enabled programme management teams to identify issues that may affect programme delivery (as far as possible) being identified as early as possible, and remedial measures taken.

## D: VALUE FOR MONEY

AT2030 continues to provide strong value for money across the ‘5 Es’: Economy, Efficiency, Effectiveness, Equity and cost Effectiveness. Examples are summarised below.
Table 3: Value for Money
Economy
Economy refers to the careful management of resources to ensure that inputs (such as funds, materials, and human resources) are procured at the lowest possible cost without compromising quality.
AT2030 places a strong emphasis on careful resource management and cost control throughout its operations. In this reporting year, the programme has successfully leveraged £4,750,338 in cash and in-kind contributions from partners, significantly reducing direct programme costs and maximising the value of UK taxpayer investment. This match funding approach has enabled the programme to deliver greater impact and reach by multiplying the resources available for assistive technology initiatives.
The use of digital tools, such as Airtable, has streamlined project management and knowledge sharing, reduced administrative overheads and enabled more efficient allocation of resources.
To ensure high-quality expertise at a lower cost, AT2030 utilises academic salary scales for professional inputs, rather than higher consultancy rates. For example, a senior researcher costs approximately £210 per day under AT2030’s grant structure, compared to a discounted consultancy rate of £462 for the same level of expertise. This approach maintains the quality of inputs while delivering significant savings.
Robust financial management underpins all programme activities, with regular audits and quarterly reviews ensuring transparency and accountability. These practices guarantee that all expenditures are necessary, justified, and aligned with value for money principles.
Efficiency
Efficiency refers to the relationship between the resources used (inputs) and the outputs or outcomes achieved, focusing on maximising outputs or outcomes from the resources invested.
The programme employs robust monitoring and evaluation frameworks, including bi-weekly meetings, quarterly reviews, and annual reports, ensuring that progress is tracked effectively, issues are identified early, and corrective actions are taken promptly.
Partnerships and collaboration are central to AT2030’s approach, minimising duplication and improving resource use.
GDI Hub’s active communications team disseminates research findings through partner networks, including GAATO, GATE Network, EASTIN, AAATE, and others.
Collaborations with WHO and UNICEF create demand for new products in global procurement catalogues, significantly lowering the cost of goods in LMICs. For example, in Rwanda, the price of hearing aids was reduced by 94%, from $2,000 to $118, resulting in a shipment of 1,200 hearing aids as part of a pilot programme that completed in 2024/25.
Effectiveness
Effectiveness refers to the extent to which a programme achieves its intended outcomes and objectives, focusing on actual impact and results.
High levels of engagement are demonstrated through nearly 209,000 downloads, views and citations of AT2030’s published materials since the programme’s inception.
The AT Insights Portal and AT Innovators Map provide access to data and evidence for government policymakers, INGOs, OPDs, and specialised agencies, enabling informed, evidence-based decisions.
The ‘Mobile as AT’ project is influencing mobile phone developers to improve accessibility and is informing other programmes, such as FCDO’s AI for Development (AI4D). Building on this learning, GDI-Hub launched CDLI (co-funded by Google.org) to harness the power of AI and the potential of communication solutions to change lives. The CDLI is developing inclusive solutions for people with communication difficulties and trains people how to use them. They are collecting datasets of non-standard speech to build Automatic Speech Recognition models, enabling disabled people with communication barriers to take advantage of Automatic Speech Recognition software.
The ‘Positioning OPDs as Equal Partners on AT’ initiative with IDA has strengthened the role of persons with disabilities and their representative organisations in advocacy for AT.
Equity
Equity refers to the fair distribution of resources and benefits among marginalised populations, aiming to reduce inequalities and ensure interventions reach those most in need.
AT2030 develops AT that is specifically designed to be accessible and affordable for persons with disabilities in LMICs, bridging the gap between high-resource and low-resource settings and reaching some of the most marginalised populations.
The programme uses a person-centred approach, involving persons with disabilities in the design, implementation, monitoring and evaluation phases.
Training and capacity-building activities for local organisations and stakeholders empower communities to support and advocate for the needs of persons with disabilities.
AT2030 has increased its focus on data disaggregation including gender. It has also launched a new workstream to assess the access to AT for women and girls versus men and boys.
The Para Sport Against Stigma (PSAS) project promotes inclusive participation, empowerment, and community engagement through sport, influencing policy and providing access to adaptive sports equipment.
Investment into AT2030 was a key element of the Research & Evidence Directorate’s 2024 Global Disability Summit commitments and supports the ‘Leave No One Behind’ initiative. The Sustainable Development Goals cannot be achieved without prioritising the needs of individuals with disabilities.
Cost-Effectiveness
Cost-effectiveness refers to the ability of a programme to achieve its desired outcomes at the lowest possible cost, evaluating whether resources are used efficiently to produce maximum benefit.
To date, AT2030 has raised over £19.7 million in funding or in-kind donations, aiming for 100% match funding through increased third-party funding from donors, governments, and private companies, as well as partnerships with NGOs, academic institutions, and the private sector.
The programme focuses on developing affordable, scalable and replicable AT solutions. For example, AT2030’s work in Nepal aimed at increasing access to high-quality AT by fitting people with lower limb difference with a transtibial prosthetic leg manufactured via a digital prosthetic workflow. The device, developed through scanning, computer-aided design, and 3D printing technologies, represents a scalable solution for addressing the global gap in assistive technology.
Cost-effective innovations, such as the Training in Priority Assistive Products (TAP) initiative by WHO, primary health and community-level personnel provides basic assistive products, addressing the global shortage of trained personnel.

The Assistive Technology Growth Fund (ATGF)
During the reporting year, AT2030 initiated the establishment of ATGF. The purpose of the ATGF is to demonstrate a market for risk capital investment in AT, which is a high-risk, high-reward strategy based on knowledge of a robust pipeline of scalable AT ventures with large addressable markets. The fund is still being raised so it is too early to report in this review period but, once established, ATGF will deliver insights into the VFM of this investment model for AT.
Assessment of VfM
Table 3 demonstrates that AT2030 continues to deliver strong results, and good value for money across all 5 ‘E’ indicators and should continue. AT2030 has met or exceeded 4 out of its 5 programme outputs for the 2024–2025 review period. The only output not met was related to the AT Growth Fund, which is delayed but expected to progress in the next cycle.
AT2030 met all four of its outcome targets for this reporting period: Scaling 15 new products (target: 15), supporting 38 ventures (target: 38), achieving uptake of 65 programme ideas by governments and organizations (target: 56), and implementing 12 new service delivery models (target: 12).
Programme outputs, outcomes and impact (Outputs, Outcomes and Impacts) met or exceeded expectations. The programme also has a 100% match funding target and has raised £4.75 million this year, taking the total to date to £24.45 million.
AT2030 is a key element of Research & Evidence Directorate’s 2022 Global Disability Summit commitments and supports FCDO's 2022 Disability Inclusion and Rights Strategy.
The ‘Leave No One Behind’ initiative is not possible without disability inclusion, and the Sustainable Development Goals cannot be achieved without prioritising the needs of individuals with disabilities.

E: RISK
The programme is currently going through a due diligence refresh process to assess GDI Hub’s standards of due diligence and fiduciary control, including reviews of governance structures, commitments to integrity and ethical conduct, name screening and bank account checks (to conclude in 2025).

Overview of risk management
The overall risk rating for AT2030 at the end of this reporting period is Moderate. The top 3 programme risks in the register in this period are as follows:

Risks and Description	Probability (H, M, L)	Impact / (H, M, L)	Mitigating Actions
(Financial & Fiduciary) / As the funding landscape changes, this may impact forecasted plans for AT2030 in the future.	High	Medium	GDI Hub to undertake scenario planning to prepare for different eventualities. FCDO and GDI Hub maintain open communication lines. FCDO will communicate in a transparent way.
(Policy & Programme Delivery) / The current funding landscape may impact on the progress of the AT Growth Fund (ATGF) and how quickly it attracts funds.	Medium	High	Ensure GDI Hub is monitoring that the General Partner is identifying and engaging key stakeholders early with a targeted plan and that they have implemented a strong marketing strategy to attract investors. Request regular updates on the ATGF project plan from GDI Hub, and make sure this includes alternative funding and engagement strategies if the current ones are not working. / FCDO will provide support for outreach to potential funders - making connections/introductions and facilitating events to introduce potential funders to SEAF, GDI Hub and the needs and ambitions of the ATGF.
(Safeguarding) / AT2030 innovations support vulnerable populations, which heightens risks of abuse, exploitation, or neglect of beneficiaries.	Medium	High	Ensure GDI Hub continue to review and enforce comprehensive safeguarding policies with downstream partners that outline clear procedures for preventing, identifying and responding to safeguarding concerns and reports. / Ensure that where there is direct work with vulnerable communities, in-country systems and background checks are carried out on staff undertaking this work. / This is included in contracts, KPIs and is regularly monitored, and that this is reported to FCDO in quarterly reporting.

FCDO’s programme team continually monitors risk and reviews and assigns mitigating actions for every risk on a quarterly basis. AT2030’s Programme Team meets at least once a month. Discussions between the FCDO and GDI Hub continue to be open and collaborative, whilst providing a good level of challenge.

F: PROGRAMME MANAGEMENT : DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Throughout the reporting cycle, GDI Hub communicated with FCDO and programme partners on a regular basis. GDI Hub produced monthly email updates to all partners (including FCDO), which included research highlights and media outputs. GDI Hub also engaged in biweekly catch-up calls with FCDO, hosted biannual AT2030 Advisory Board meetings and attended formal quarterly review meetings with FCDO.
The financial year end accounts of implementing partners are checked by GDI Hub and provided to FCDO annually. In 2024/25 GDI Hub was audited as part of its commitment to FCDO. The auditors confirmed there were no material errors relating to the grant accounting and no significant weaknesses relating to internal controls. Programme forecasts and expenditure were managed closely and have broadly been in line with budget. Quarterly and annual programme forecasts are provided to FCDO at the beginning of each quarter and clarify any changes or variance.
Year-end variance for 24/25 was £37,408.97 overspent (0.83% variance) against the ceiling budget for the year of £4.5million.
Coordination with FCDO Posts ensures that in-country programmes and partner connections are optimised.
A due diligence review exercise started in 2024/25 and will complete by the end of 2025.
With the implementation of a revised programme of work this year following the approval of the Business Case Addendum and ToC, a new finance template, logframe and quarterly reporting mechanism were co-designed with FCDO. These new templates make it easier to record and assess partner progress against targets which are now reviewed during quarterly review meetings to check progress and identify any mitigating actions.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Across the year, GDI Hub undertakes various activities with FCDO and downstream partners to ensure continuous monitoring of the progress and quality of AT2030. This included:
- Bi-weekly meetings of the Directors and FCDO which has a set agenda (highlights, challenges, opportunities, etc.),
- Bi-weekly operational meetings with members of the GDI Hub and FCDO Programme teams
- Monthly AT2030 delivery meetings with all CIC and UCL sub-programme and cluster leads
- Monthly GDI Hub programme management meetings with downstream partners
- Quarterly review meetings with GDI Hub and FCDO
- Bi-annual Advisory Board meetings
- Monthly Programme updates (newsletters)
- Annual Review
- Monitoring trips
- Annual Audit
- Revised Advisory Board membership
- Partner due diligence

Evidence
AT2030 conducts yearly audits to ensure that all impact-related data is accurately reflected in the programme’s logframe. The programme has a strong focus on producing and building on comprehensive and robust evidence (19 peer-reviewed papers and 15 influencing papers published this reporting year). The facilitation of evidence access is supported by AT2030’s strategic tools such as:
- Updated downstream ‘Partner Support Pack’ outlining GDI Hub’s structure, key performance indicators (KPIs) definitions, overall strategic direction and approach to data disaggregation.
- The gender concept note guides downstream partners on exploring how disabled women and gender minorities are disproportionately impacted in terms of access to and inclusion of AT, and what approaches are effective in addressing these disparities.
- Access to evidence is improved through AT2030’s Data Portal and is powered by artificial intelligence (AI). For completion in 2025/26, it will enable users - policy makers, programme leads, innovators, academics and more broadly those interested in AT - to interrogate thousands of verified academic documents, data sources and grey literature within seconds. This will be invaluable for evidence-based policy making, programme and financial decisions.
In the last reporting year, partner reporting began to incorporate data disaggregation of direct beneficiaries by gender (sex), research participation, AT beneficiaries, and types of disabilities. Partners are now more intentional about how they collect disaggregated data, and this is being tracked. Existing disaggregated gender data informed the gender workstream and plan for mainstreaming gender across the programme. However, the ongoing collection of disaggregated data has proven to be challenging (see ‘Learning’ below).
Multiple workshops were held to present the findings and co-develop a Theory of Change (ToC) the outcome of which outlines the steps to achieve Gender Equitable access to AT. This included a workshop on 12th November 2024 (Q3) attended by FCDO to support the development of the ToC and assess the programme’s gender focus.
Two systematic literature scoping reviews were also conducted:
- ‘Outcomes of AT use by sex and gender; a scoping review’
- ‘A Scoping Review of Gendered barriers and facilitators of access and use of assistive technology’
This work highlighted a significant disparity in the access and use of AT, with women reporting lower rates of access despite a higher prevalence of disability compared to men.
The AT2030 programme will continue to address gender inequalities in accessing AT through dissemination of the gender ToC both internally and to external partners through webinars and knowledge sharing. GDI Hub will work with sub-programme leads to identify opportunities for gender inclusion mainstreaming and processes to address gendered barriers to AT access to achieve gender equitable AT access for women and girls.
The BCA and new AT2030 ToC places increased emphasis on collecting country-level data, including financial spend, to enable more detailed profiling and alignment with FCDO priorities and planning.

Monitoring trips, training and events during this review period included:

- FCDO monitoring visit (see Box 11 below) included engagement with stakeholders and regular thematic deep dives. Areas covered were monitoring implementation progress of the ‘Disability Management Information System (DMIS)’ and CHAI’s ‘Strengthening enabling market environments for AT provision’ in Liberia, Rwanda and Sierra Leone.
- Launch event for the Attvaran Accelerator in partnership with IIT Delhi and IIT Madras. This featured keynote lectures promoting the mainstreaming of AT with panel discussions sharing insights on startup journeys, the role of NGOs in scaling innovations, and investment opportunities within this crucial sector.
- As part of the Local Productions Systems of AT (led by GDI) in Nepal, bespoke product development participant testing phase (after long wait for wound healing), workshops were held with local teams to define protocols.
Box 11: Monitoring in Rwanda / The AT2030 programme team travelled to Kigali, Rwanda with GDI Hub’s Head of Programmes, as part of the monitoring and evaluation of the Strengthening enabling market environments for AT provision in Liberia, Rwanda and Sierra Leone workstream led by the Clinton Health Access Initiative (CHAI). / This visit included a demonstration of the Disability Management Information System (DMIS) with the National Council of Disabilities, a meeting with Kimironko sector leadership and registered DMIS individuals (programme beneficiaries), as well as a programme review of the AT2030 workstream.	Figure 14: Group photo of FCDO, GDI Hub and CHAI representatives alongside sector leadership on DMIS implementation and registered DMIS individuals a the Kimironko Sector Office in Kigali, Rwanda.

Learning
Over the past year, AT2030 has strengthened its learning processes by implementing the new 'What Works' framework, a participatory learning system designed to systematically capture and analyse lessons across the programme. This framework builds on existing reporting systems and outputs from AT2030’s clusters, enabling programme participants, implementers, and partners to act as active evaluators.
Additionally, structured monthly check-ins, quarterly learning workshops, and strategic review sessions have embedded continuous learning and improvement within the programme cycle. At least one report of learnings is produced each quarter, ensuring that insights are regularly documented and shared.
For example, AT2030’s Para Sport Against Stigma programme found:
- What works: Bringing media and disability advocacy/service providers together through sport is providing a platform to tangibly engage with communities and sectors that typically have no interaction or little interest in disability inclusion.
- What does not work: Planning for media and community engagement activities with less than 50 days to the Games. This needs to start 2 years out in future and ahead of the Paralympics in Los Angeles 2028.
Additionally, AT2030’s work focused on strengthening enabling market environments for AT provision in Liberia, Rwanda and Sierra Leone found:
- Liberia: Local AT procurement and supply chain management capacity is limited, and country can benefit from opportunities to send focal persons abroad for learning trips/capacity-building.
- Rwanda: Wide stakeholder engagement is critical to successful implementation of DMIS by increasing the depth of knowledge on key barriers and opportunities.
The ‘What Works’ framework generates strategic intelligence around what works to get AT to people who need it, for whom it works, why it works, how it works and the contexts it works in. This then directly informing programme adjustments, resource allocation, and scaling decisions. By synthesising learning across all subprogrammes, the framework identifies patterns and strategic opportunities, establishing the AT2030 programme as an evidence base for understanding AT access. This approach also prioritises the involvement of people with disabilities and local partners as primary knowledge generators, ensuring that learning is grounded in lived experience and is immediately actionable.
With a stronger focus on collecting disaggregated data, the programme has found that this has proven to be complex and challenging due to the programme’s broad geographic spread, diverse stakeholder involvement, and varying capacities for data collection by partners and countries. Many regions where the programme operates face systemic barriers such as limited infrastructure, inconsistent data standards, and under-resourced local institutions, which hinder the reliable collection of detailed data, especially disaggregated by gender and disability. To improve data disaggregation, the GDI Hub programme management team will utilise a coordinated, capacity-building approach, to work alongside partners to improve data collection techniques, particularly in LMIC countries where resources are limited, and the cultural context is important to consider. GDI Hub will look to develop standardised data collection tools and guidelines that are co-designed with AT2030 partners, women and people with disabilities to ensure consistency and relevance across diverse contexts.
Other key lessons identified over the past year include the importance of participatory evaluation in generating accurate and relevant learning; the value of real-time feedback for programme adaptation; and the need to understand the broader impact of AT beyond individual users. The programme has also recognised the significance of building local evaluation capacity to sustain learning and adaptation, and the necessity of exploring the effects of AT provision on families and communities, not just individual beneficiaries.
This was demonstrated in the OPD and AT User Engagement sub-programme where research conducted in partnership with Kilimanjaro Blind Trust Africa (KBTA) and the Special Talent Exchange Programme (STEP). This supported OPDs through participatory engagement and evaluation to understand organisation’s challenges and barriers, followed by building local OPD capacity through trainings and workshops. This project used local network feedback to design solutions that increased OPD skills thus broadening the wider impact of AT for users, their families and communities.

Date of last narrative financial report	29/05/2026	Date of last audited annual statement	31/03/2025

Annexes

Annex 1 - Definitions of reach

Direct reach (people): Directly reached individuals refers to people who participate at individual level in the activities and/or outputs of AT2030. This includes individuals reached by the programme in its endeavour to find out ‘what works’ and is not the same as beneficiary counting, as we are interested in benefits as well as inclusion. This reach nevertheless typically refers to individuals.

Direct reach (systemic): Groups who benefit from the outputs and outcomes of the AT2030 programme relating to improved provision of AT through policy and system advances regarding access to AT (products/services), and community and organisation level change, as well as events, programmes, and capacity development. This includes systemic changes of a defined and specific magnitude in terms of the number and manner of people affected and included. This reach typically refers to groups. This captures core success factors for the appropriate provision of AT set out in the Scoping Report 2018 and notably includes changes in the provision of rights and recognitions, and the engagement of disabled people in the process.

Indirect Reach (people): Individuals who are not directly involved or impacted through the programme but could still derive benefit from it.​ These individuals can be reasonably identified as included within the community, regional and/or national-level catchment.

Annex 2 – Number of entities (countries or organisations) implementing/adopting AT2030 funded ideas

1. Google Relate (see box on page 8)
2. The African Union Region 5 Sports Council have actively taken up insights and recommendations from the Para Sport Against Stigma sub-programme into AU region 5 action plan (2024-2027) with a focus on disability inclusion and access to Assistive Technology.
3. The Attvaran Accelerator introduced the EMPOWER conference to AT Innovation as a conference theme, featured for the first time.
4. UNFPA Pacific Islands office has taken up the AT2030 co-developed inclusive dignity kits as part of their procurement process.
5. UNFPA Sri Lanka office has taken up the AT2030 co-developed inclusive dignity kits as part of their procurement process.
6. UNFPA Bangladesh office has taken up the AT2030 co-developed inclusive dignity kits as part of their procurement process.
7. UNFPA Indonesia office has taken up the AT2030 co-developed inclusive dignity kits as part of their procurement process.
8. Kiribati has completed household surveys to qualify need and unmet need for assistive technology using the AT2030 supported rATA survey
9. The Solomon Islands have completed household surveys to qualify need and unmet need for assistive technology using the AT2030 supported rATA survey.
10. The Dominican Republic has completed household surveys to qualify need and unmet need for assistive technology using the AT2030 supported rATA survey.
11. India has completed household surveys to qualify need and unmet need for assistive technology using the AT2030 supported rATA survey.
12. Sri Lanka has completed national mapping using the AT2030 developed ATA-C tool.
13. Tanzania has completed national mapping using the AT2030 developed ATA-C Tool.
14. Colombia has completed national mapping using the AT2030 developed ATA-C tool

Annex 3 - Partnerships:

UNICEF Liberia offices supported the programme by deploying AT2030 developed AT tools to local communities.
UN Interagency Task Force for Non-Communicable Diseases supported the programme on the development of the WHO AT investment case.
WHO Egypt Country Office supported national AT development through the implementation of AT2030 developed tools and resources such as the rATA and ATA-C.
WHO India Country Office supported national AT development through the implementation of AT2030 developed tools and resources such as the rATA and ATA-C.
WHO Jordan Country Office supported national AT development through the implementation of AT2030 developed tools and resources such as the rATA and ATA-C.
Senses Hub partnered with the Para Sport Against Stigma Programme to host and facilitate events and meetings for AT interaction and awareness across PSAS and Senses Hub.
The Kenya National Paralympic Committee facilitated communication and connections with athletes facilitating and participating in focus group discussions under the Para Sport Against Stigma programme.
British Ambassador’s residence supported the AT2030 programme’s showcase alongside the Paris Paralympics Beyond Sport panel and reception.
The GREAT campaign contributed to the programme by co-hosting the Paris reception.
Greenwhich and Docklands Festival partnered with the AT2030 programme and put on performances from disabled athletes both in the UK and South Africa showcasing AT use in sport and the Arts.
German Government financially supported the programme’s presence at the World Urban Forum in Cairo.
World Blind Union financially supported the programme’s presence at the World Urban Forum in Cairo.
WHO Sierra Leone Country Office supported the Training of Assistive Products inception and rollout.
MIT Sierra Leone collaborated with the AT2030 programme to expand their procurement management tool to include AT devices.
National Centre for the Promotion of Employment of Persons with Disabilities (NCPEDP) contributed technical, research and ecosystem support to the Attvaran accelerator.
Samarthanam Trust contributed technical, research and ecosystem support to the Attvaran accelerator.
Swami Vivekananda Youth Mission contributed technical, research and ecosystem support to the Attvaran accelerator.
Enable India contributed technical, research and ecosystem support to the Attvaran accelerator.
International Center for Research on Assistive Technology and Accessibility (i-CReAT) contributed technical, research and ecosystem support to the Attvaran accelerator.
Kerala Medical Technology Consortium (KMTC) contributed technical, research and ecosystem support to the Attvaran accelerator.
Path contributed technical, research and ecosystem support to the Attvaran accelerator.
India Business Disability Network, Confederation of Indian Industries contributed technical, research and ecosystem support to the Attvaran accelerator.
Purple Jallosh contributed technical, research and ecosystem support to the Attvaran accelerator.
Blantyre City Assembly partnered with the Para Sport Against Stigma programme and led the proceedings of ‘Tiswere Tonse - Let Us All Play’ awareness event at the highest Mayoral level.
The Journalists Association of Malawi lobbied for move news coverage of PSAS events which contributed to the elevation and dissemination of the programme across Malawi and subsequently increased impact via reach.
University of Ghana supported the Centre for Digital Language Inclusion data collection of Ghanaian languages and hosted the hackathon.
WHO Rwanda Country Office supported the Training of Assistive Products inception and rollout.
EYElliance Rwanda supported AT2030’s systems strengthening work, serving as the technical partner for assessing vision related products for Rwanda’s new Community Based Health Insurance (CBHI) Package including population needs, cost effectiveness and recommendations for product inclusion.
International Nepal Fellowship supported the patient testing and aftercare of locally produced prosthetic liners in Nepal.
United Nations Department of Economic & Social Affairs provided continuous ecosystem support to programmatic activity delivery and implementation.
International Telecommunication Union (ITU) co-delivered several technical workshops to inform the Assistive Product List price and evidence review.

Annex 4 - Peer Reviewed Journal Articles/Papers

Paper Title	Platform / Journal
A Systematic Review of Ability-diverse Collaboration through Ability-based Lens in HCI Studies	Proceedings of the CHI Conference on Human Factors in Computing Systems (CHI ’24) / https://at2030.org/ability-diverse-collaboration-through-ability-based-lens-in-hci/
Exploring Information Needs for Tracking to Support Using Wheelchairs in Everyday Life	Extended Abstracts of the CHI Conference on Human Factors in Computing Systems (CHI EA ’24) / https://at2030.org/exploring-information-needs-for-tracking-to-support-using-wheelchairs-in-everyday-life/
Enhancing Communication Equity: Evaluation of an Automated Speech Recognition Application in Ghana	Proceedings of the 2024 CHI Conference on Human Factors in Computing Systems (CHI ’24) / https://at2030.org/evaluation-of-an-automated-speech-recognition-application-in-ghana/
A Scoping Review of Digital Fabrication Techniques Applied to Prosthetics & Orthotics Part 1 – Prosthetics	Frontiers in Rehabilitation Sciences, 2024, / https://at2030.org/digital-fabrication-techniques/
Mapping Assistive Technology Start-ups	Design for Equality and Justice, 2024, / https://at2030.org/mapping-assistive-technology-startups/ https://link.springer.com/chapter/10.1007/978-3-031-61698-3_27
Multi-country rapid assistive technology assessment (‎rATA)‎ 2019-2021: findings from a consultative review	World Health Organization, 2024, / https://at2030.org/findings-from-a-consultative-review/
On the Relation between Assistive Technology System Elements and Access to Assistive Products Based on 20 Country Surveys	Healthcare 2023, / https://at2030.org/relation-between-assistive-technology-system-elements/
Challenges and Strategies for Accessibility Research in the Global South: A Panel Discussion	Association for Computing Machinery (ACM), 2024 / https://at2030.org/challenges-strategies-accessibility-research/
Artificial Intelligence Alone Will Not Democratise Education: On Educational Inequality, Techno-Solutionism and Inclusive Tools	Sustainability 2024, / https://at2030.org/ai-and-education/
Harmonising Assistive Technology Assessment Data: A Case Study in Nepal	Studies in Health Technology and Informatics, 2023, / https://at2030.org/at-assessment-nepal/
PRET Printer: Development and Evaluation of a Passive Refreshable Tactile Printer in proceedings of ACM Compass conference held July 8th to July 11th at IIIT Delhi, India.	Association for Computing Machinery (ACM), 2024, / https://at2030.org/pret-printer/
Urban Transformations in Sierra Leone (book)	UCL Press, 2024, / https://www.at2030.org/inclusive-cities
Scaffolding Digital Literacy Through Digital Skills Training for Disabled People in the Global South.	Association for Computing Machinery (ACM), 2024, / https://at2030.org/scaffolding-digital-literacy/
A Scoping Review of Digital Fabrication Techniques Applied to Prosthetics & Orthotics' Part 2 – orthotics	Prosthetics and Orthotics International, 2024, / https://at2030.org/digital-fabrication-techniques-part2/
Unlocking Sustainable and Resilient Assistive Technology Innovation and Delivery Ecosystems: Personalised Cocreation of Locally Produced Prosthetics'	Innovation Ecosystem Development, 2024, / https://at2030.org/locally-produced-prosthetics/
Demographic, socioeconomic, and social barriers to use of mobility assistive products: a multistate analysis of the English Longitudinal Study of Ageing	The Lancet Public Health, 2024, / https://at2030.org/demographic-socioeconomic-barriers/
From Information Seeking to Empowerment: Using Large Language Model Chatbot in Supporting Wheelchair Life in Low Resource Settings	Association for Computing Machinery (ACM), 2024, / https://at2030.org/language-model-chatbot/
Development of Priority Assistive Product Lists in Three African Countries	International Journal of Environmental Research and Public Health (IJERPH), 2024, / https://at2030.org/development-of-priority-assistive-product-lists/
A human rights-based approach to assistive technology provision in global policy.	Research Handbook on Disability Policy (Book chapter, 2023) / https://at2030.org/human-rights-at/

Annex 5 - Influencing Papers

Can commercial be political? https://at2030.org/can-commercial-be-political/
Making Noise: Media Monitoring Report https://at2030.org/media-monitoring-report/
Disability Innovation in Pakistan https://at2030.org/gdi-hub-in-pakistan/
OPD Capacity Building for a Disability Inclusive Future Kenya Project Report https://at2030.org/opd-kenya/
Shujaaz Youth Attitudes Towards Disability Sport https://at2030.org/youth-attitudes-towards-disability-sport/
Disability and Assistive Technology in Population-Based Data https://at2030.org/disability-and-assistive-technology-in-population-based-data/
Access to smartphones in Kenya: the research case for mobile as AT https://at2030.org/access-smartphones-kenya/
Can Automated Speech Recognition improve the lives of people with communication disabilities in Ghana? https://at2030.org/ai-ghana/
Enhancing mobile accessibility for persons with hearing and visual impairments: case for mobile as AT https://at2030.org/mobile-accessibility-for-persons-with-hearing-and-visual/
A Global-Local Innovation Approach for Appropriate Technology in LMIC: A case study in Nepal https://at2030.org/nepcon-conference-2024-may-10-atw030-gdi-hub-highlights/
A scoping review of quality guidelines for Assistive Technology provision https://at2030.org/a-scoping-review-of-quality-guidelines-for-assistive-technology-provision/
AI for Disability Inclusion in Africa https://at2030.org/ai-disability-inclusion-africa/
60 Decibels Performance Snapshot (ATIF) (Trestle Labs) https://at2030.org/performance-snapshot-trestlelabs/
Global Comparison Report https://www.at2030.org/inclusive-cities
Nepal Wheelchair Provision Workshop Report https://at2030.org/nepal-wheelchair-provision-workshop-report/

Annex 6 - Number of innovative assistive technologies supported

Exobot Dynamics: Exobot Dynamics received support through AT2030’s Attvaran accelerator, including access to online resources, expert mentoring, business modelling guidance, and opportunities to engage in sector events. This enabled the team to strengthen evidence gathering, build strategic partnerships, improve user relationships, and develop a clear, sustainable business growth plan. Attvaran facilitated Exobot Dynamics in product development of their prosthetic hand for upper limb amputees; an innovation designed to bridge the gap between loss and possibility. As a result of Attvaran the Exobot Hand technology was refined, with a better understanding of user needs that aligned with both market demand and social impact. As a result, Exbot Dynamics received a minimum commitment of an INR25,000 investment to expand their team and accelerate product development, with an additional minimal commitment for another investor of INR50,000.
“Attvaran has helped us understand the nuances of product development and positioning in the disability sector. We built the ability to understand the market needs and what customers are looking for, along with sustaining a profitable business. Earlier, we had mixed views on how our product is received by the user and how can we monetize our offerings while being socially relevant. The mentoring sessions and discussion with people brought together by Attvaran team, enabled us to solidify our plans by careful planning and milestone setting. We are grateful for the opportunity to be a part of Attvaran and expand our learnings.”

Insighte: who offer personalised therapy for children with autism and ADHD through a platform that supports home, school and online services received comprehensive support through Attvaran, including access to online resources, mentoring, lectures, and event participation, with focused assistance in business modelling, capacity development, and product design. The program helped them gather key evidence, strengthen collaborations with regional, national, and international partners, and enhance relationships with users and customers, setting the stage for successful business growth.

EnableMe Access: who advocate for accessibility and inclusion by providing training, assessments and solutions for various needs received valuable support through Attvaran, including access to online resources, mentoring, user testing guidance, and opportunities to pitch at demo days. Participation in the program helped them gather critical evidence, build collaborations with regional, national, and international partners, and develop a successful business growth plan. Attvaran also facilitated networking opportunities with other assistive technology startups and provided access to mentorship.

BeAble: whose ArmAble solution combines hardware and software to create interaction therapeutic games that engage patients in high-repetition exercises essentially for neuroplasticity benefited from Attvaran’s support, including access to online resources, mentoring, lectures, and opportunities to pitch at demo days, with focused guidance on business modelling and user testing. Through the program, they gathered important evidence, strengthened collaborations with regional, national, and international partners, and enhanced relationships with users and customers. As a result, they successfully streamlined their work processes and OKRs, enabling them to build a clear and effective business strategy.

SaralX: who provide technology and expert feedback to ensure digital assets are accessible and compliant received extensive support through Attvaran, including access to online resources, mentoring, lectures, and event participation, with a focus on business modelling, capacity development, product design, and prototyping. The program enabled them to gather critical evidence, strengthen collaborations with partners at multiple levels, and improve relationships with users and customers. Active mentorship played a key role in refining their product, strategy, and business insights, contributing to successful growth plans.
“Guidance from the mentor helped us in refining our product, strategy, and business insights.”

SignAble: whose application of on-demand Indian Sign Language (ISL) interpretations service using Video Remote Interpretation (VRI) and Video Relay Service (VRS) with a web-based application that allows employees to access ISL interpretation visa laptops or desktops without needing mobile devices benefited from Attvaran’s support, including access to online resources, mentoring, lectures, and event opportunities, with particular focus on business modelling and capacity development. Through the program, they gathered valuable evidence, strengthened collaborations with regional, national, and international partners, and improved relationships with users and customers, laying the groundwork for successful business growth.

Dhanvantri Biomedical: whose Sahayatha wheelchair team received targeted support including access to online resources, expert mentoring, participation in lectures, and opportunities to attend key events. The program was particularly valuable in guiding user testing and helping the team gather evidence to strengthen their design and engagement strategies. As a result, they improved relationships with users, developed a clear business growth plan, and are now on a stronger path toward achieving product-market fit—an outcome directly supported by Attvaran’s mentoring.

Panoculon Labs: who have created AI-powered smart glasses and navigation for better environmental perception without GPS received comprehensive support through Attvaran, including access to online resources, expert mentoring, business modelling guidance, and opportunities to participate in key events and demo days. The program was especially helpful in user testing and capacity development, enabling the team to gather critical evidence, strengthen customer relationships, and refine their business growth strategy. As a result, they gained exposure through tailored sessions for AT startups, deepened engagement within the assistive technology space, and secured INR500,000 in grant funding, which was used to advance prototyping efforts.

Next Skills 360 EdTech Private Limited: who bridge educational gaps by teaching 21st century skills to underserved students, including accessibly coding tools for the visually impaired, received targeted support through Attvaran, including access to online resources, expert mentoring, participation in lectures and events, and guidance on user testing. The team also had the opportunity to pitch at demo days. As a result, they strengthened collaboration with regional, national, and international partners, gathered key user insights, and developed a solid business growth plan. With inputs gained through the program, they successfully fine-tuned their product, which launched in January 2025 (Q4).

Phonologix Health Solutions: who address communication disorders with the Speech Ally application and platform by offering early intervention through gamified activities and teletherapy the team received comprehensive support including access to online resources, expert-led lectures, mentoring, and opportunities to pitch at demo days. Focused guidance on product design, business modelling, and capacity development helped them gather evidence, build strategic partnerships, and strengthen their business growth plan. The sessions were instrumental in validating and refining their business strategy, improving their pricing model, and gaining deeper insights into customer behaviour. As a result, they secured a INR500,000 grant, which has supported product enhancement and expanded access to underserved clients previously unable to afford their services.

Nirvesh Enterprises Private Ltd: who enhance stroke survivor care with Synapril, a multimodal wearable system for comprehensive physiological assessments, received valuable support through Attvaran, including access to online resources, expert mentoring, and participation in lectures and events, with a particular focus on business modelling and capacity development. As a result, the team strengthened collaborations with partners across regional, national, and international levels, deepened customer relationships, and refined their business growth strategy. This led to securing INR500,000 in equity funding, enabling significant progress in technology development, expanding access for end users, and positioning the company for entry into global markets.

Grailmaker Innovations Private Ltd: who help the visually impaired navigate spaces the Spacefelt application, offering personalised navigation through QR labels received tailored support through Attvaran, including access to online resources, expert mentoring, and participation in lectures, events, and demo days. The program focused on business modelling and product design, helping the team gather evidence, strengthen user relationships, and build strategic partnerships at various levels. One-on-one mentorship provided valuable insights that refined their business model and improved engagement with B2B clients, particularly through Diversity and Inclusion (D&I) networks in the corporate sector. The team secured INR500,000 in grant funding, which is being invested in expanding application features—such as multilingual access and sign language content—to enhance inclusivity and reach.

Sunbots Innovations LLP: who address the educational and employment gap for 9.5 million blind and visually impaired children with their SMARTON mobile application and camera-enabled device that connects to any glasses using camera vision and generative AT to make physical and digital content accessible benefited from Attvaran’s support, including access to online resources, expert mentoring, user testing guidance, and the opportunity to pitch at demo days. The program played a key role in refining their business model, gathering user insights, and strengthening collaborations with regional, national, and international partners. Through Attvaran, they showcased their innovation at events like Empower and the Bengaluru Tech Summit, connecting with NGOs and CSR stakeholders. Valuable insights from guest speakers enriched their understanding of business strategy and customer needs, contributing to stronger user relationships and a clear growth path.