Support to Social Protection Programme (SSPP2) Annual Review

Title: Support to Social Protection Programme (SSPP2)
Programme Value £ (full life): up to £65,000,000		Review date: 4 September 2025
Programme Code: 300825	AMP start date: 04/09/2020	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2020	2021	2022	2023	2024
Overall Output Score	A	A	A	B	B
Risk Rating	Moderate	Moderate	Moderate	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000651.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/61806215.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

The Support to Social Protection Programme (SSPP2) was approved in May 2019, with an initial budget of up to £65,000,000. The programme has the objective of improving Mozambique's social protection systems and building an expanded shock-responsive social protection system. The SSPP2 is currently delivered in three components:

1. Support to the Government of Mozambique’s (GoM) social protection programmes to address malnutrition, chronic poverty and vulnerability to shocks.
2. Improving social protection institutions to build credible, sustainable and flexible systems.
3. Developing policies and programmes needed for shock-responsive social protection.

Overview:

The overall score for this annual review is B covering the review period 1st April 2024 to 31st March 2025. Two of the four outputs fell below expectations, while the other two outputs met expectations.

In this annual review, the overall score and the scores for the four outputs remain unchanged from the previous year. However, a key development during the current review period is the change of government in January 2025, which has demonstrated a strong commitment to reforming the sector and accelerating the quality and pace of programme implementation. The persistently low scores reflect the previous administration’s lack of political will to advance social protection initiatives. This was further compounded by its decision to deprioritise direct support to beneficiaries—a stance that remained in effect until the change in leadership in January 2025.

In the short-term (i.e. the period covered by this Annual Review), changes to the availability of UK ODA finance for social protection in Mozambique have not had an impact on achievement of the four outputs, although these changes have had an impact on delivery of the MEL (Monitoring, Evaluation and Learning) component, including a study that ‘Impact Indicator 1’ relies on as a data source. This will have an impact on future years and the recommendations are tailored to the expectation of a reduced ODA budget at post.

Although the programme’s measurable performance as of April 1, 2025, remains broadly consistent with the previous year, several noteworthy achievements and positive developments have occurred during the Reporting Period. Many of these achievements relate to the change in government that took place at the start of January 2025 which has begun to address many of the blockages in the sector. These include:

- UNICEF substantially exceeding the number of beneficiaries they have reached with the child grant (see Output Indicator 1.1).
- Contracting of WFP to deliver anticipatory payments and plans to further use external contractors to delivery payments during 2025.
- Measurement of specific UK attribution for each output indicator.
Following the end of the Reporting Period on 31 March 2025, significant changes have emerged at the Ministry. These include a complete restructuring of the senior leadership team and a new acceptance to engaging external service providers to enhance delivery. These developments present strategic opportunities for the UK and other stakeholders to collaborate with the new Minister in strengthening delivery mechanisms.

For the reporting period the FCDO delivered its objectives through four mechanisms and adjusted funding between them due to performance issues:

1. A World Bank Multi donor trust fund (MDTF) co financed with the World Bank, and two other donors. The UK did not transfer funds during this reporting period but the MDTF has been spending pooled resources to which the FCDO has supported in the past, contributing 11% of the total funding.
2. A UN managed fund (the UN Joint Programme or UNJP) to support the Child Grant programme co-financed by the Netherlands, Sweden, Finland, Ireland and Canada where the UK contributes 26%. Over the period UK contributed £3,573,891 and reached 48,668 beneficiaries - output 1.1.
3. A programme delivered by a civil society organisation called MUVA that focused on women’s empowerment.  This component received a total amount of £1,249,02 from the UK over the review period.
4. Support to WFP to deliver anticipatory action to support beneficiaries to manage climatic shocks but also provide proof of concept for government finance. This component received £3,899,637 over the reporting period.
In addition to financing, the UK has played a key role in advocacy and direct policy support to GoM in progress towards achieving their national targets.

On bringing WFP into delivery: Due to the underperformance of World Bank component, FCDO decided to bring in WFP as a partner to the shock response component specifically for anticipatory action activation response. Detail findings of implementation are provided in indicator 3.3. with approximately 450,000 people reached with early warning messages and up to 28,668 households reached with cash transfers and commodity vouchers during the Window 1 activation.

On the UK attribution: Following one of the recommendations in last year’s annual review, an attempt has been made to estimate specific UK attribution for each of the outputs. The approach involves consideration of contributions by different partners to the UNJP (which the UK used to finance and still has resources left in it) and the MDTF, consideration of the UK contribution as a percentage of total contributions, and consideration of the number of beneficiaries reached (or other quantified targets included in the logframe). The resulting figures for UK attribution come heavily caveated. The attribution which can be calculated using such an approach is inevitably approximate, not least because of uncertainties around payment timings and changes in contributions by a number of partners.

In addition to the lack of prioritisation of social spending by the Mozambican government, there is a risk that the government is unable to finance the programme due to government’s shrinking fiscal space. While economic growth has shown some recovery, rising from 4.4% in 2022 to 5.4% in 2023, the projection for 2024 is lower, at 4.3%, and government expenditure has increased, largely driven by rising salary costs and debt finance. The fiscal space is expected to remain restricted for the coming years and without economic diversification, the benefits of the growth will unlikely benefit the most vulnerable populations thus not reducing the needs in the sector.
[note] From IMF article IV data

FCDO and other development partners will continue to engage in discussions with the government on how to improve GoM financing for the sector.

Reduced GoM spend has also impacted institutional capacity of INAS, the main implementer of GoM social protection programmes, leading to delays in implementation and budget execution of the current programme, exacerbated by the rapid expansion of these programmes in response to crises. To address this, both the World Bank and UNJP programme have integrated activities aiming at improving institutional capacity. A light institutional capacity assessment is ongoing to identify the most appropriate strategies.

The two critical bottlenecks mentioned above - the institutional capacity of INAS and the fiscal space needed to support social protection - will require significant attention in the coming year.

Progress of recommendations from previous Annual Review

Recommendations from the previous AR
	Recommendation	Progress	Comment
1	Update the programme log-frame to align with recently approved time extension up to 2027 and adjust targets to reflect UK’s contribution rather than just national ones.	Achieved	Log-frame updated
2	Ensure more regular discussions with the World Bank and INAS, to identify areas that need additional support to ensure targets in the World Bank project action plan are met. This should include specific areas for both UK diplomacy/policy engagement and for programming.	Achieved	At the end of the reporting period the government agreed to numerous meetings including at ministerial level. The UK joined the WB mission, and all the initial UK asks have been met. For example: The SPER project was restructured and an agreement signed with the Ministry of Finance. A unit was established to deliver the project in MTGAS and INAS.
3	Consider further support for additional technical staff for INAS that can improve WB implemented component delivery.	Achieved	After restructuring, most project funds will be implemented by providers to accelerate delivery (WFP, GiveDirectly, UNICEF).
4	Capitalise on increased GoM interest to expand digital payments to social protection beneficiaries, by directly supporting the delivery of digital payments to child grant beneficiaries.	Ongoing	First quarter of 2024, Vice Minister of Economy and Finance (MEF), conveyed a strong message to modernise, enhance efficiency, transparency, and accessibility in the delivery of social protection benefits.
5	Review the implementation of MUVA’s action plan through quarterly meetings with MUVA.	Achieved	Achieved

Major lessons and recommendations for the year ahead

The main lessons and recommendations from this review period are captured in the tables below. Due to ODA reductions, the programme should develop a clear transition plan to shift from its current structure toward a focus on technical engagement. Strategic collaboration with the new Minister through direct UK assistance to the Ministry will help establish a stronger bilateral relationship.

Recommendations for the year ahead
	Recommendation	Responsible	Target date
1	As the programme has now scored two consecutive 'B's the team will develop a formal improvement plan with partners within this first quarter.	FCDO	01/10/2025
2	Develop a transition plan for a responsible exit from the current programme and transition to technical engagement and focus of SP on anticipatory action and/or innovation and digital.	FCDO	01/01/2026
3	The UK should include shock response Social Protection as part of a new programme for climate related action and finance focused on leveraging climate finance for the social protection system. This should include plans to leverage external and domestic finance.	FCDO	01/01/2026
4	Restructure the programme with MUVA and FSD reducing its scope and ensuring greater political buy-in from the Ministry and key stakeholders.	FCDO	01/10/2025
5	For the coming year add more effective quantitative target to WFP component.	FCDO	01/10/2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

At the impact level, the SSPP2 programme aims to reduce extreme poverty and vulnerability to shocks in Mozambique, by building a “bigger, better and more shock responsive social protection system”. This will be achieved primarily through; Component 1, which funds cash transfers, technical assistance, and coordination. Component 2 that supports policy reform and coordination, while Component 3—the Emergency Response Fund—provides rapid humanitarian aid during crises. The approach is grounded in strong evidence that cash transfers reduce poverty and that shock-responsive systems offer more sustainable and better value for money protection than traditional humanitarian aid.

Mozambique’s economic performance deteriorated markedly in 2024. Annual real GDP growth declined to 2.2% in 2024 from 5.5% in 2023, driven by a contraction of 5.7% year-on-year in the fourth quarter of 2024 primarily attributable to post-election protests and climate-related shocks, including Cyclone Chido and the El Niño phenomenon.Poverty is estimated to affect about 68.2 percent of the total population in Mozambique which is basically at the same levels as last year. Inequality is widespread, particularly between urban and rural areas, where access to basic services is limited. The rural population is particularly vulnerable to environmental shocks and structural barriers, that hinder poverty reduction and inclusive growth.
[note] Economic Report 2025 – Mozambique: https://www.seco.admin.ch/dam/seco/de/dokumente/Aussenwirtschaft/Wirtschaftsbeziehungen/L%C3%A4nderinformationen/Mittlerer%20Osten%20und%20Afrika/rapport_economique_mozambique.pdf.download.pdf/Wirtschaftsbericht%20Mosambik%202025.pdf
[note] IMF Country Report No. 24/219
[note] Macro Poverty Outlook WB / April 2025: https://thedocs.worldbank.org/en/doc/bae48ff2fefc5a869546775b3f010735-0500062021/related/mpo-moz.pdf

To achieve the desired outcome, the programme is expected to expand the number of beneficiaries and increase transfer values, while investing in system strengthening to improve delivery mechanisms. Although technical and political challenges have slowed innovation, past UK support has demonstrated progress in expanding coverage and initiating reforms. The programme balances the trade-off between scale and adequacy of support, aiming for a technically and politically feasible expansion.

Increasing social protection coverage and spending can have significant impact on reducing poverty and inequality. Simulation results indicate that extending coverage of PSSB (from the Basic Social Subsidy Program in Portuguese) to all eligible beneficiaries and increasing the amount of cash transfers based on the INAS’s proposal can lead to a 2.4 percentage points (of population) decline in poverty and a 1.8 percent decline in income inequality (proxied by Gini index). Consumption levels are estimated to increase, particularly for the poor (with an 8 percent increase in the lowest income quintile)2.

During the Reporting period, there have been no changes to outcome and impact indicators from the original business case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead

As outlined in the narrative above, up to December 2025—during the previous government administration, the sector faced significant challenges due to limited government interest and a lack of accountability among ministry officials responsible for delivering social assistance programmes. This has resulted in very slow mobilisation of externally financed social protection delivery, reforms to the sector and domestically financed programmes, which were intended to form the core of the Government of Mozambique’s social protection strategy.

The approach taken by FCDO Mozambique to turn the project around while also maximising VFM in the run-up to the change in the Mozambican government at the end of 2024, has been to:

1. Reallocate funding from components showing limited progress to ensure more efficient use of resources, such as from the World Bank project.
2. Shift programme delivery to more effective partners, particularly those that the government can leverage to accelerate implementation and improve outcomes.
3. Pilot and evaluate alternative approaches that can serve as evidence-based models to inform and influence future government policy.
And once the new government had been inaugurated in January 2025, FCDO:

Ensured direct access to Ministers working on Social Protection to discuss progress in the sector and how the government might unlock it’s programmes – between January and March we had a number of early engagements with the Ministry and started a small programme of direct technical support to planning and prioritisation with the Ministry.

Worked with key external partners to ensure social protection was at the top of the new government’s agenda including.

  - Working with the IMF to ensure it integrated Social protection as part of its article IV discussions and the new programme,
  - As co-chair of the Social Protection Working Group, led coordination effort to agree core shared messages to the new government with all other stakeholders to the sector,
Over the next year to address the risks of either continued slow performance and slow delivery FCDO will;

- Build on the engagement with the ministry and co-develop an informal mutual accountability framework.
- Continue to press multilateral partners – particularly the World Bank and UN Joint Programmes—to uphold their delivery commitments and strategically deploy their political and financial leverage. This includes regular performance tracking, structured engagement, and escalation of underperformance through appropriate channels.
- Continue shifting resources to parts of the programme that can either shift the dial politically and or delivery more quickly – this is likely to include WFP but also a suite of direct technical assistance to the Ministry as part of mutual accountability.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The rationale and need for the programme to continue to remain strong as Mozambique remains one of the poorest countries in the world and there is little medium-term prospect of a significant exit from poverty.

While the rationale remains strong despite recent improvements, the VfM is still not proven. The overall justification of the programme depends on government commitment to reform and use of domestic resources at scale. Without the recent changes in government and the early signs of commitment to reform and accelerate progress it would be very hard to justify continued financing as this would mean Social Protection became almost entirely donor financed and unsustainable. However, once domestic and multilateral commitments restart at pace VfM and overall impact picks up swiftly due to the large amount of multilateral resources (over US$100m) and domestic resources planned for the sector (currently over 3% or GDP).

Thus on balance given recent government commitments and recent measures taken by the Ministry (such as a complete change in the senior members at the ministry to increase delivery) we judge that on balance the programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	A higher proportion of poor and vulnerable people receive more predictable social protection transfers
Output number:		1	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of children receiving child grant support	50,000 (20,000 -UNICEF; 30,000 -WB)	Moderately not met / UNJP: 48,668 / WB: 0
% of poor and vulnerable households receiving transfers (disaggregated by programme type)	28%	Not met / 1% of poor and vulnerable households / All programmes: 239,452 HH = 1% / PSSB - 149,741 (53,357 M; 96,384F) / PASD - 27,787 (11,194M; 16,593F) / PASP - 55,056 (24,077M; 30,979F) / PAUS - 6,868 (2,560M; 4,308F)
1.3. Government Contribution to Social Protection (Billion MZN)	6.8Billion Meticais (MZM)	Not Met / In principal budget allocation: MZN10.5B (0.7% of GDP) / Actual Expenditure: MZN979.5M (0.1% of GDP)
[note] INAS PESOE 2024
[note] UNICEF budget brief 2024

Briefly describe the output’s activities and provide supporting narrative for the score.

The output 1 is one of the two with the highest impact weighting of the SSPP2. It gives an indication of vulnerable people reached and government commitment to the social sector. This output scored an overall B, with two indicators not met and one moderately not met expectations. The target achievements were impacted by continued delays in the World Bank component and government support to it’s regular programmes. The Social Protection and Economic Resilience Project (SPER), funded by the World Bank, underwent restructuring in the first quarter of 2025, and all activities under the project will be implemented by a third-party provider to prevent further delays. Agreements have been signed with the World Food Programme (WFP), and ongoing negotiations are taking place between the World Bank and Give Directly and UNICEF for programme delivery. WFP is preparing to start the implementation, having already received the first tranche under the signed output agreement. These agreements, combined with government-led delivery, are expected to significantly accelerate progress ahead of the next annual review and reflect a renewed commitment to timely implementation on the part of the government.

  1. Number of children receiving child grant support: Moderately not met
UN joint programme – Strong Performance despite delays to start the digital payments. The initial target for the UNJP programme was 39,000 children, this target has been exceeded by 9,668 children The programme reached 48,668 beneficiaries by December 2024. Despite the efforts to pay these beneficiaries digitally, the transition to this modality is still ongoing and these payments were made semi-digitally through OPA (Offline payment application) that captures the beneficiary data to a server, confirming that individuals received the entitlement in person and in cash.

World Bank - delayed commencement of all activities - Activities funded by the World Bank for the child grant programme did not commence during the review period due to delays from the Government of Mozambique (GoM). As a part of programme restructuring, the overall target for World Bank for this component was revised and reduced to 69,757 as part with the aim to streamline implementation and focus on delivering subsidies to beneficiaries who are already registered in e-INAS by January 2025. However, due to the process delays no beneficiaries received payments during this review.
[note] Initial target was 110,000 beneficiaries

  1. % of poor and vulnerable households receiving transfers (disaggregated by programme type, gender, disability, rural/urban): Not met
The 2024 Economic and Social Plan (PESOE) aimed to transition social transfer payments from manual to digital methods, targeting 1,069,140 households living in poverty and vulnerability. This would represent a 3.0% increase compared to the number of households reached in 2023. INAS set specific goals for each program:

- 786,916 households under the Basic Social Subsidy Programme (PSSB)
- 90,099 households under the Direct Social Support Programme (PASD)
- 11,100 households under the Social Unit Assistance Programme (PAUS)
- 181,025 households under the Productive Social Action Programme (PASP)
Despite the ambitious targets set in the 2024 Economic and Social Plan in practice only 1% of poor and vulnerable households received social transfers, falling significantly short of the 28% target. A total of 239,452 households were reached across all programmes. Disaggregated data shows that the Basic Social Subsidy Programme (PSSB) supported 147,741 households, while the Direct Social Support Programme (PASD) reached 27,787 households (11,194 male; 16,593 female). The Productive Social Action Programme (PASP) covered 55,056 households (24,077 male; 30,979 female), and the Social Unit Assistance Programme (PAUS) reached 6,868 households (2,560 male; 4,308 female). These figures represent only 20.09% of enrolled beneficiaries, highlighting a substantial gap between planned and actual coverage.

  1. Government Contribution to Social Protection (Billion MZN): Not met
During the reporting period, the government had an actual expenditure of MZN979.5M (0.1% of GDP). Despite efforts to strengthen social protection, challenges persist due to limited fiscal space and political commitment to the sector. In 2023-24, disbursements for social protection had significant delays due to liquidity constraints, resulting in limited spending execution and posing operational hurdles for INAS preventing regular payments to beneficiaries.

These two indicators have been affected by the lack of political commitment to the sector during 2024. During 2024 the sector received almost no funds from government to pay beneficiaries.

Social protection spending in 2024 fell sharply to its lowest level in a decade, totalling just 979.5 million Meticais—four times less than in 2023 and representing only 0.1 percent of GDP and 0.2 percent of total government expenditure. This significant decline is primarily linked to reduced and irregular disbursements from the Ministry of Finance, driven by ongoing liquidity constraints, as well as persistent operational challenges within INAS.

Output Title	The national social protection system is strengthened to manage cash transfers more effectively and efficiently
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. % of beneficiaries receiving transfers on time, through an outsourced provider or digital means (disaggregated by gender, disability, rural/urban)	60% receiving on time; 30% receiving digital payments	Partially Met / UNJP: 2% of the total paid / Only 25% receiving on time (WB report) / 56% receiving digital (WB report)
2.2. INAS able to provide a) financial reporting on time; b) reduced administrative cost; c) fiduciary risk rating reduced	Meeting all three measures	Not met / All Audits Delayed / Admin costs did not reduce as OPA was the main payment modality in 2024 for both WB and UNJP / Fiduciary risk remains high

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has scored a B with both indicators not meeting expectations. The indicators for output 2 are proxy indicators to assess the results of the institutional strengthening component of the programme through the World Bank. Timeliness is a key factor, as evidence indicates that timely payments enable beneficiaries to plan more effectively and reduce reliance on negative coping mechanisms such as borrowing, reducing food intake, or withdrawing children from school. In addition, the shift towards digital payments is a strategic move to enhance programme efficiency. Digital modalities significantly reduce the time required to process and disburse payments, helping to minimise delays and administrative bottlenecks. They also lower operational costs for the government and mitigate fiduciary risks by improving transparency and traceability. Furthermore, digital payments contribute to broader development goals by promoting financial inclusion and literacy among beneficiaries, many of whom may be engaging with formal financial systems for the first time.

  1. % of beneficiaries receiving transfers on time and through digital means: Partially Met
As many beneficiaries did not receive payment in 2024 it means that very few can be said to have been reached on time. 25% represents the World Bank estimate of timeliness of those paid so in practice the score should be significantly lower.

47% of beneficiaries actually paid received payments against a target of 45%. The government’s low disbursement of funds from the Ministry of Finance to the sector affected INAS’s consistency in delivering payments to social protection beneficiaries.

The variation in the percentage of beneficiaries that received digital payments compared to the previous year (3.6% vs 34%) is explained by the fact that in 2022, beneficiaries enrolled in the shock responsive approach, were paid digitally. Cash transfers in 2024 were mostly delivered to regular beneficiaries who are not registered for digital payments. UNJP through UNICEF, paid 2% of the total paid beneficiaries from this AR period using digital payments (mobile money transfers). Digital payments are expected to grow significantly next year as most of the pre-conditions to continue with payments are almost met by the National Institute of Social Action(INAS) and the mobile money operators(MMO) such us, separation of accounts for different funding sources and creation of corporate accounts for each of the 31 INAS delegations.

  1. INAS able to provide a) financial reporting on time; b) reduced administrative cost; c) fiduciary risk rating reduced: Not Met

INAS has failed to deliver on time on all the elements for this indicator. INAS’s financial management is poor and performance reflects the low level of accountability for poor performance in the institutions in the sector and the need for greater institutional capacity. The audit report prepared by Tribunal Administrativo (Mozambique’s Administrative Tribunal) presented a qualified audit opinion mainly driven by the fragility of INAS’s financial administrative system, which represents only one of the institutional weaknesses. The UK, along with partners should consider whether providing funding for more staff to INAS would help strengthen their capacity.

To improve INAS’s performance (as implementer of the WB MDTF), a set of actions were agreed with the World Bank, including: 1. restructuring the project to reduce activities with low performance and underspend risk (reducing USD 4,7 million form the project); 2. reducing targets of the child grant; 3. revising institutional capacity component.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year. As a result of this review, we recommend clarifying the methodology for calculating results against the indicator percentage paid on time. The percentage should refer only to those paid not the total number of targeted beneficiaries and should be calculated as whether the beneficiaries received the expected funds within the quarter (not monthly). The rationale for doing this is that there are currently multiple possible interpretations of “% of beneficiaries receiving transfers on time”.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

See overall recommendations above in section A.

Output Title	The national social protection system is better prepared for shocks and faster and better targeted responses when needed
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Policies and processes needed for a shock responsive social protection system in place	Policies, protocols, operating procedures, triggers and emergency plans for the operation of shock responsive social protection are in place	Met / Government now has policies and systems in place to respond to shocks
3.2. Average time between shock responsive triggers and citizens receiving cash transfers reduces by 10% every year	not triggered	Substantially Exceeded / During 2024, INAS activated the PASD-PE program to respond to droughts under AA.
3.3. INAS working together with the National Institute of Disaster Management (INGD) and the Secretariat for Food and Nutrition Security (SETSAN) to predict and respond to emerging crises	INAS leading response to slow onset crisis	Met / INAS is leading the activation of cash transfers to drought affected people with support from INDG, INAM.

Briefly describe the output’s activities and provide supporting narrative for the score.

Given that the government began making shock responsive payments, as well as the fact INAS and INGD signed an agreement with WFP to work together, we assessed that this output has overall been met. In addition, the agreement by the government to sub-contract WFP for shock responsive payments and anticipatory action shows that they are committed to joint action in this sector and have an agreed way of working. Our assessment is thus that the indicator 3.1 Policies and processes needed for a shock responsive social protection system in place, has been met.

  1. Average time between shock responsive triggers and citizens receiving cash transfers reduces by 10% every year: Substantially Exceeded
FCDO has been supporting the government preparedness to respond to Anticipatory Action activations. In the past, there were instances where social protection systems took over a year to respond following climate-related shocks. This year INGD and INAS were able to arrange payments far more rapidly in response to droughts in the centre of the country.

  1. INAS working together with the National Institute of Disaster Management (INGD) and the Secretariat for Food and Nutrition Security (SETSAN) to predict and respond to emerging crises: Met
INAS and INGD have been working together to deliver cash assistance to respond to Anticipatory Action activations with WFP support funded by the UK. Approximately 28,668 households were reached with cash transfers and commodity vouchers during the period. Households received three months of MZN2,500 (£29) cash-transfers, totalling MZN7500 (£86) per household. Moreover approximately 450,000 people were reached with early warning messages between October and April as a result of INAS and INGD action. Early warning messages were disseminated through community radios to communities in the districts of Changara (Tete), Chemba and Caia (Sofala) and Chibuto, Mabalane, and Guija (Gaza).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to this output since the previous AR. The plan is to add a target to WFP component to account better for its service delivery on shock response social protection.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The results matrix was reviewed to incorporate indicators and milestones up to March 2027.

Recommendation for this year:

The UK should include shock response Social Protection as part of a new programme for climate related action and finance focused on leveraging climate finance for the social protection system. This should include plans to leverage external and domestic finance.

Output Title	Social protection programmes address gender gaps leading to improved agency and empowerment
Output number:		4	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. Number of women who reported improvements in their ability to achieve their economic goals.	Grant Agreement Signed	Met / Agreement signed with FSDMoc, having Muva as downstream partner.
4.2. Number of young and disadvantaged people reached through transformative social protection programmes (MUVA)	350	Substantially Exceeded / 589 participants were reached in Nampula, Beira and Maputo
4.3. Number of women reporting improved agency (self esteem) and decent job opportunities as a result of social protection programmes	Number of participants signing up: 350; (1) Number of young people (60% female) with increased technical competences: 80%; (2) Number of young people (60% female) with increased agency: 70%	Substantially Exceeded / Number of participants: 589 / (1) 60% of young people female with increased technical competences: 80% / (2) with increased agency: 70%
[note] MUVA report results

Briefly describe the output’s activities and provide supporting narrative for the score.

The MUVA UP: Promoting Gender-Sensitive Social Protection and Models of Transformative Public Works For Women & Youth program has closed and successfully exceeded its impact targets, supporting 1,549 disadvantaged youth—60% of whom were women—through structured work experience facilitated by MUVA models, surpassing the original target of 1,200.

At the outcome level, the programme made strong progress in consolidating MUVA as a national actor and laying the foundation for future scale-up. While full integration into national systems was not achieved during the grant period, the programme generated robust evidence and built a compelling case for future adoption. MUVA secured diversified funding, developed a strategic plan for 2025–2030, and gained recognition as a Mozambican non-profit in youth employment, social protection, and women’s economic empowerment. These achievements position MUVA to contribute meaningfully to FCDO’s strategic objectives in resilience and poverty reduction. The programme delivered strong results against its impact objectives, supported by a total revised Accountable Grant value of GBP 3,482,295.

  1. Number of women who reported improvements in their ability to achieve their economic goals. Met
Advancing Women’s Economic Empowerment in Social Protection Project (AWEESP) is under the FCDO project Support of Social Protection Programme - Female Economic Empowerment & Mozambique Demographic Transition - Waala Programme.
AWEESP aims to increase households access to economic opportunities by enhancing women's agency, expanding access to relevant financial services, and skills and capabilities. The project also aims at enabling a supportive environment for the integration of WEE in child grant by strengthening system actors' capabilities. After a long period of discussions with MTGAS, the agreement with FSDMoc, with MUVA signed up as downstream partner, was signed. A workplan for each of the institutions in the project has been agreed.

  1. Number of young and disadvantaged people reached through transformative social protection programmes (MUVA). Met
This Accountable Grant (AG) was implemented in two phases: (i) an Inception Phase (November 2021 – June 2022), followed by (ii) an Implementation Phase (July 2022 – March 2025). It had two main objectives: (i) To support disadvantaged youth—particularly young women—in meeting their basic needs and strengthening their resilience through work experience in both public and private sector settings; and (ii) To consolidate and strengthen MUVA, a Mozambican non-profit organization, as a national actor in inclusive economic empowerment. The project also aimed to generate evidence, foster adaptive learning, and inform policy dialogue to improve employment and social protection systems. For it’s late year of implementation, MUVA exceeded the initial target of 350, reaching 589 beneficiaries through transformative social protection programmes.

  1. Number of women reporting improved agency (self-esteem) and decent job opportunities as a result of social protection programmes: Met
The programme exceeded its target by reaching 589 participants (60% women) during 2024, many of whom reported improved self-esteem and agency as a result of their participation. MUVA’s model was successfully piloted in two public service sectors—Municipal Water Authorities and Municipal Transit Police—yielding operational benefits and institutional interest, though budget constraints limited long-term integration. In the private sector, over 70% of MUVA graduates secured employment or internships, surpassing the satisfaction benchmark and expanding access to decent job opportunities for women and youth, even amid economic and political instability.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to this output. Looking ahead, recommend restructure of the programme with MUVA and FSD reducing its scope and ensuring greater political buy-in from the Ministry and key stakeholders will be made.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.
Recommendation to review the implementation of MUVA’s action plan through quarterly meetings with MUVA. This programme has closed and all recommendations considered.

## D: VALUE FOR MONEY

Key cost drivers and performance

Between April 2024 and March 2025, FCDO disbursed a total of £9,014,038. The key cost drivers were direct cash transfers, which accounted for 52% of the total budget (£5,350,785), supporting Child Grant and drought Anticipatory Actions beneficiaries. Staffing costs represented 25% (£2,253,739), covering essential programme personnel and technical support, while operations and overheads made up the remaining 23% (£2,028,425), supporting logistics, systems, and coordination.

Economy
The data indicates that the Child Grant UN Joint Programme is demonstrating improving economic value for money. The increase in budget execution from $4 million (£2.95M) to $8 million (£5.9M) also suggests stronger financial absorption and operational capacity, which is a positive sign of programme maturity. In contrast, the WFP Anticipatory Actions project shows higher per-beneficiary costs at $50 (£37) in 2024. However, this is economically justifiable given the project's early stage, where start-up costs, such as system development, training of government staff, and beneficiary registration are typically front-loaded. These investments are foundational and expected to reduce future delivery costs as the programme scales and becomes more efficient.
Overall, while the WFP project currently has higher costs, both programmes show a trajectory toward cost-efficiency and scalability, with the Child Grant programme already delivering strong economic value for money. The strategic investment in systems and capacity building in the WFP project is likely to yield long-term savings and improved delivery outcomes.
The MUVA Assistentes Accountable Grant pilot demonstrated strong economic value for money through substantial cost reductions and sustained impact. The cost per participant fell from £2,726 during the initial pilot phase to £460 by the end of the programme in March 2025. This reduction reflects improved delivery efficiency, reduced experimental and design costs, and the benefits of scaling. Beneficiaries reported increased employability, improved returns to education, increased agency indicating that the programme maintained its effectiveness while becoming more financially sustainable. These results suggest that the model is well-positioned for scale-up, offering a high benefit-cost ratio and strong potential for long-term impact indicating that the programme maintained its effectiveness while becoming more financially sustainable.
Meanwhile, the FSDMoç Women’s Economic Empowerment programme is in its mobilisation phase, with process indicators currently being tracked. Although impact data is not yet available, the programme is designed to contribute meaningfully to gender equity and inclusion. Implemented jointly with the Demography programme, it aims to improve women’s access to economic opportunities, financial services, and decision-making power. The strategic focus on women’s empowerment aligns with broader development goals and positions the programme as a key contributor to inclusive growth. As delivery progresses, it is expected to demonstrate both cost-effectiveness and transformative impact for marginalised women.

Efficiency

The programme showed reasonable efficiency by delivering more impact at lower cost in some components. One of them includes the Child Grant UN Joint Programme which reduced its cost per child from $49 (£37.66) to $30 (£22.50) while doubling its reach, supported by a lean budget where 70% was allocated to direct cash transfers. MUVA Assistentes also reduced its cost per participant from £2,726 to £460, maintaining strong outcomes in employability and agency. Although WFP’s Anticipatory Actions had higher costs (£37 per beneficiary), these were driven by necessary start-up investments expected to decline over time. Overall, full budget execution (£9M) and a balanced cost distribution 52% to transfers, 25% to staffing, and 23% to operations reflect efficient resource use and strong delivery capacity.

Effectiveness

The Mozambique Social Protection Anticipatory Actions intervention is demonstrating growing effectiveness by enhancing multisector coordination and implementation. Building on policy and analytical groundwork laid by the WFP’s Enabling Humanitarian Environment initiative. the project is improving technical support to key government institutions INAS and INGD, through collaboration between social protection and humanitarian sectors. Early reporting suggests that these anticipatory actions are enabling the government to respond more efficiently, reduce losses, and strengthen community resilience, indicating promising potential for long-term impact.

Equity

The programme doesn’t have specific indicators for equity measurement. However, as per programme value for money guidance equity element is advised to be integrated through the programme lifecycle. In line with that principle, the programme is primarily centred on equity and social inclusion, with a purposeful emphasis on reaching the most disadvantaged and poorest groups. This includes children, households affected by drought, and women, particularly those facing systemic barriers to economic participation. By prioritising these populations, the programme seeks to address deep-rooted inequalities and ensure that support reaches those who need it most. The mobilisation of the FSD Moç Women’s Economic Empowerment initiative will play a pivotal role in enhancing gender equity by actively working to improve women’s access to financial services, such as savings, credit, and insurance. It also promotes broader economic opportunities for women, including entrepreneurship, employment, and financial literacy. By integrating this initiative, the programme not only strengthens its gender-responsive approach but also contributes to building more resilient and inclusive communities where women can thrive economically and socially.

Assessment of whether the programme continues to represent value for money

Despite relatively high implementation costs due to essential start-up investments of the WFP Anticipatory Actions project the overall programme shows clear efficiency gains, with programmes delivering more impact at lower cost. The Child Grant UN Joint Programme halved its cost per child while doubling its reach. The MUVA Assistentes pilot reduced cost per participant from while sustaining core outcomes, reflecting scalable and financially sustainable delivery. The portfolio’s trajectory points to increasing cost-efficiency, sustained impact, and long-term resilience for vulnerable populations.

In contexts where poverty is widespread and state capacity is limited, such programmes often serve as lifelines reducing hunger, improving health and education outcomes, and preventing the use of negative coping mechanisms. Mozambique Social Protection Anticipatory Actions intervention is improving multisector coordination and implementation will bring economic benefit, such as increased human capital, reduced inequality, and enhanced resilience to shocks, often outweigh the upfront costs. Moreover, when programmes are well-targeted and increasingly digitised, they become more efficient and transparent, reducing leakage and improving delivery. In fragile settings, the value of reaching those most in need, especially when no alternative safety nets exist, makes even high-cost interventions a worthwhile intervention.

E: RISK

Overview of risk management

The overall risk of the programme as Major.

The delivery challenges in the social protection sector remained although some improvement at the end of the assessed period with the new government structure after the 2024 presidential elections. The presidential elections risk materialised with impact in project implementation and fiscal context. The programme risk remained as major mainly because some of the key indicators like budget execution worsened with impact on programme sustainability in the assessed period.

The Government’s slow disbursement of funds to INAS delegations and consequent low levels of payment to beneficiaries of regular programmes continue to be the main challenge. This risk materialised in 2023 and worsened in 2024. There was a decrease in the budget execution from around £34 million in 2023 to £16 million in 2024 representing a reduction in 46%. This risk had impact in regular cash transfer programmes with a total of 20% payment rate at national level in 2024. However, the national election at the end of 2024 financial year led to changes in the sector with the merge of the Ministry of Gender, Children and Social Action with the Ministry of Labour to become the Ministry of Labour, Gender and Social Action (MTGAS). This change opened opportunities to engage with the new Ministry to mitigate this situation. The engagement was carried out by partners, mainly the World Bank and UNICEF, and BHC at high level. Early results of this engagement show some openness in approaching the issues. In one side, the Ministry has agreed with partners to make payments through parallel systems like WFP and discussions with Give Directly and UNICEF are taking place.. The Ministry will also receive support from BHC on planning and prioritization. This shows a willingness of MTGAS to resolve the situation which will be carefully assessed in the next annual review.

The risk of presidential post-election violence in 2024 in Mozambique materialised. Post-election violence resulted in insecurity and restrictions of physical access of around three months at national level. This resulted in the closure of all private and public institutions. This included road closure, affecting the implementation of social protection programme, including payment of beneficiaries in the regular programmes and shock responsive social protection in drought impacted areas. Although the post-election violence ended, the situation remains fragile. BHC and implementing partners continue to monitor potential violence focus through Government Authorities relationships, INSO and UNDSS.

For the activities implemented in Cabo Delgado, the conflict continues to pose a significant risk. This is outside of the control of our implementing partners but both UNICEF and the World Bank have put in place emergency planning to partially mitigate the risk. For example, by further implementation of digital payments.

Current level of fiduciary risk and direction of travel since last ASP	Worsening
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The overall performance of delivery of the Child Grant by the UN Joint Programme has been good despite some challenges outside the implementing partners control. This has been mentioned in detail in the risk section of the annual review. The report was submitted on time and a joint review was carried out with other donors. UN Joint Programme carried out regular technical working groups to update donors and discuss key topics of the sector. Two amendment letters were signed in 2024. The first amendment letter was to increase £2 million that were disbursed and spent by 31st March 2025. The second amendment letter was signed to change the Standard Administrative Arrangement date from 31st March 2025 to December 2026 when the UN Joint programme ends.

MUVA Accountable Grant closed in March 2024 with an institutional capacity and financial sustainability challenge. FCDO signed an amendment letter to increase funding for institutional capacity and financial sustainability that was executed until end of last financial year. An exit plan was agreed between MUVA and BHC to guide Accountable Grant closure and ensure a smooth process. FCDO carried out an asset spot check and asset disposal process that transferred the assets to the recently approved FSD/MUVA Accountable Grant. Final Narrative and Financial reports were submitted on time pending a last audit report.

FCDO signed a new Contribution Arrangement (CA) with WFP to implement Social Protection Anticipatory actions in drought impacted areas to be implemented until March 2025. All PrOF compliance requirement has been followed before the signature of the CA. Due to delays caused by post-election protests, a no cost-extension amendment was agreed and signed to change the end date to June 2025 to allow WFP to finalise project and report. WFP submitted project updates and preliminary financial reports and is expected to submit final reports end of August. A second phase of the WFP Anticipatory Actions was approved by FCDO.

The World Bank MDTF has been affected by MTGAS/INAS delays challenges in implementation with impact on budget execution. The MDTF submitted all reports as agreed and carried out two field missions to provide support to the government. No UK funds were disbursed the MDTF in the assessed period due to the implementation challenges. FCDO expects to disburse remaining funds in 2025 as the execution situation improves. A cross-office World Bank due diligence refresher was completed in December 2024.

A new Accountable Grant was signed with FSD Mozambique to implement the Women Economic Empowerment project in the last quarter of 2024. All compliance requirements were followed including a new due diligence completed in December 2024.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Over the past year, the programme has strengthened its learning and adaptive management through a range of monitoring and evaluation activities. These included regular performance monitoring, log frame reviews and updates based on the previous year’s recommendations, and escalation of risks—particularly during periods of political instability. Lessons and evidence from previous phases were revisited and integrated into ongoing planning and implementation processes.
During the reporting period, two field visits were conducted to Nampula Province—one as part of routine monitoring and the other linked to the Annual Review process. In addition, one asset spot check was carried out in collaboration with MUVA to assess the use and condition of programme resources. The delivery plan was reviewed and discussed regularly, with structured discussions taking place at least quarterly, ensuring continuous oversight and adaptive management throughout the year.
The FCDO’s internal Social Protection Cluster engaged in three key monitoring mechanisms: participation in World Bank missions, engagement in the UN Joint Programme Technical Working Group, and field visits. The World Bank conducted regular field missions, with the most recent taking place from 31 March to 18 April 2025. While the mission noted some progress, it concluded that overall project performance remained unsatisfactory. FCDO Social Protection Cluster also contributed to the Child Grant UN Joint Programme Technical Working Group, collaborating with other donors to monitor implementation progress and address sectoral challenges.
In addition, two joint field visits were conducted with UNICEF to Nampula Province—in May 2024 and July 2025—focusing on INAS delegations and direct engagement with beneficiaries. These visits provided valuable insights into delivery bottlenecks and community-level feedback, which informed programme adjustments.
Evidence and Learning:
Key lessons from the year include the need for more adaptive delivery mechanisms, as delays in partner performance prompted the strategic engagement of WFP to enhance responsiveness. For the broader FCDO and development community, the experience highlights the importance of flexible funding modalities and integrated approaches that link climate resilience with social protection. These findings have direct implications for the programme’s future direction, particularly in advancing anticipatory action and digital innovation.

Date of last narrative financial report	WB MDTF – 13/12/2024 / UNICEF – 25/04/2025 / WFP – 29/07/2025 / MUVA – 03/07/2025 / FSD – 12/08/2025	Date of last audited annual statement	WB MDTF – 13/12/2024 / UNICEF – 25/04/2025 / MUVA – 19/05/2025

List of abbreviations

AG	Accountable Grant
AR	Annual Review
AWEESP	Advancing Women’s Economic Empowerment in Social Protection Project
BHC	British High Commission
CA	Contribution Arrangement
COVID	Corona Virus
ENSSB	National Strategy for Basic Social Security
FCDO	Foreign Commonwealth and Development Office
FSD	Financial Sector Depenning
FSDMoç	Financial Sector Deepening Mozambique
GBP	Great Britain Pound
GDP	Gross Domestic Product
GoM	Government of Mozambique
ILO	International Labour Organization
IMF	International Monetary Fund
INAM	National Institute of Meteorology
INAS	National Institute of Social Action
INGD	National Institute of Disaster Management
INSO	International NGO Safety Organization
MDTF	Multi Donor Trust Fund
MEF	Ministry of Economy and Finance
MEL	Monitoring Evaluation and Learning
MoU	Memorandum of Understanding
MTGAS	Ministry of Labour, Gender and Social Action
MUVA	Associação para o Empoderamento da Rapariga - MUVA
MZN	Mozambique Metical
ODA	Overseas Development Assistance
OPA	Offline Payment Application
PASD	Direct Social Action Programme
PASD-PE	Direct Social Action Programme – Post Emergency
PASP	Productive Social Action Programme
PAUS	Social Unity Assistance Programme
PCR	Project Completion Review
PEA	Political Economic Analysis
PESOE	Economic and Social Plan
PSSB	Basic Social Subsidy Programme
SETSAN	Secretariat for Food and Nutrition Security
SP	Social Protection
SPER	Social Protection Economic Resilience Programme
SSPP2	Support to Social Protection Programme 2
UK	United Kingdom
UN	United Nations
UNDSS	United Nations Department of Safety and Security
UNICEF	United Nations Children Fund
UNJP	United Nations Joint Programme
VFM	Value For Money
WB	World Bank Group
WFP	World Food Programme