## Annual Review Template

Title: Better Lives for Somali Women and Children (Health and Nutrition)
Programme Value £ (full life): £ 120 million		Review date: 21 April 2025
Programme Code : [AMP ID#] 300857	AMP start date: 21 April 2022	AMP end date: 31 March 2028

Summary of Programme Performance
Year	2022/23	2023/24	2024/25
Overall Output Score	A	B	A+
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Better Lives for Somali Women and Children (Better Lives) programme is now in its third year of implementation. The programme has three distinct objectives as outlined in its original business case.

1. Extend access to an essential package of reproductive, maternal and child health services (EPHS).
2. Effectively promote healthy behaviours and demand for services, and
3. Strengthen the health system at all levels including government stewardship of coordination and efficient resource management and delivery.

Commencing in April 2022, the programme, originally designed to take a development approach, was pivoted to support humanitarian interventions during its first 18 months of implementation[1]. Better Lives experienced significant reduction in Official Development Assistance (ODA) in May 2022. The funding cuts saw the programme budget reduced from £20m annually to £14.9m in 2022/2023 and £11m in 2023/2024. During the 2024/2025 review period, it received funding to support capital expenditure (Capital Department Expenditure Limit – CDEL) focused on climate resilience taking the 2024/25 annual budget to £16.2m.
[1] Reasons for the initial humanitarian approach i) challenges in comprehensive engagement with Government in 2022 due to elections and significant political change, making decisions on reduction of geographical scope difficult; and ii) reduction in ODA that further complicated the discussions.

The transition to a multi-year development focus was realised from 1 October 2023. To ensure delivery of the above objectives and especially in view of reduced ODA, the programme has worked with the Somalia (including Somaliland) Government and used the entry of the World Bank and its Global Financing Facility (GFF) to create a more efficient coordinated approach with key partners including the Global Fund to fight AIDS, TB and Malaria (GFATM) and the Vaccine Alliance (Gavi), among others.

The programme’s development phase has focused on the following specific objectives: i) improve the delivery of high impact services that will advance health and nutrition outcomes for women and children in target regions; ii) develop regional and district health authority capacity to lead on the implementation and provide oversight as stewards of the health sector, and iii) ensure climate resilience, supply chain and evidence-based planning and monitoring inform programme implementation.

In addition to UNICEF service delivery, the business case envisioned that the programme would support a Technical Assistant component that would drive health systems strengthening (HSS), deployed through a private sector supplier; and an independent Monitoring, Evaluation and Learning (ME&L) component co-owned with the FCDO Humanitarian Assistance and Resilience Building (HARBS) programme. The technical assistance work was paused because of the reductions in ODA, whilst the ME&L work was awarded to Oxford Policy Management (OPM) in August 2023. Better Lives ME&L initiatives began robustly in January 2024 with key milestones across several deliverables realised during this review period.

On 25th February the UK Prime Minister announced a reduction of UK ODA from 0.5 to 0.3% of Gross National Income (GNI) by 2027. At the time of writing, the Spending Review allocation for the British Embassy Mogadishu has not been finalised. Based on planning assumptions, it is highly unlikely that the UK will maintain a significant bilateral health programme beyond 2025/2026. The British Embassy Mogadishu (BEM) team is, therefore, planning an early closure of the Better Lives programme. The impact of this to vulnerable populations amongst other contextual considerations is outlined in the summary sections below.

Summary supporting narrative for the overall score in this review

In this review period the Better Lives programme has scored an A+ overall. This is primarily due to progress made against annual targets for the programme outcome and output indicators. An assessment of the overall risk of this programme at this Annual Review indicates the level as Major. This has not changed since the last Annual Review. The risk rating places the programme within the overall BEM risk appetite – high.

UNICEF and downstream partners have had an impressive year of delivery and significantly showcased improved implementation of the core service delivery components. The partners have also taken on additional funding towards establishing climate resilient activities at both health facilities and the community levels – driving and enhancing excellent delivery overall.

UNICEF’s leveraging of alternative funding sources and wider health systems strengthening initiatives has improved efficiency in delivery by scaling up services and increasing reach to beneficiaries despite FCDO’s declining funds and a difficult operating context. The contextual issues have included the adverse effects of climate change that resulted in a rise of disease outbreaks, ongoing inter-clan conflict and national insecurity attributable to the ongoing Federal Government of Somalia’s (FGS) fight against al-shabaab.

The programme has reached 1.4 million individuals (women, girls, men and boys). This is a significant increase (by 266%) compared to the 553,637 individuals reached in the last Annual Review period (2023/24).

Table 1: Breakdown of achievement across the 1.4million reached:

Services	People Reached
OPD services-new	498,072
OPD services-revisits	73,131
Antenatal care (ANC) services	71,414
Delivery services (skilled delivery at birth)	39,615
Postnatal Care (PNC) services (mother and newborn)	37,801
Family Planning services	3,959
Immunisation services	353,271*
Nutrition Services (severe acute malnutrition with and without complications)	83,053
Nutrition Infant and Young Child Feeding services	310,533
Total reached	1,470,849

*Includes all children reached with all vaccine antigens between 0 and 59 months (children under five years).

Please see a summary of the outputs (scores and weighting) in Section C below.

Some of the figures in the table above do not directly correspond with the figures outlined in the output sections below. This is because the breakdown includes individuals reached across the whole spectrum of services per intervention whilst data in the output sections are specific to what is measured by each indicator[2].
[2] For example, 71,414 women reached with ANC services includes all pregnant women who accessed services in the 1st, 2nd, 3rd and 4th trimesters whilst the indicators in the output sections only speak specifically to either reach across ANC 1 (first trimester) or ANC 4 (fourth trimester) – parameters that best showcase coverage of ANC according to WHO global guidelines. Immunisation reached includes children who were both vaccinated through routine visits at the health facilities and through the Big-Catch up campaigns (detail provided in the relevant output sections).

The programme takes cognisance of the ongoing seismic shifts in health financing globally, as a result of USAID budget reductions and those announced by the UK Government and other donors. The Government of Somalia including Somaliland and partners are not ready to absorb the impact that this will have across the health and nutrition sector. UNICEF and other partners began drastically restructuring their programmes in the last quarter of the review period across their global, regional and country platforms – and still delivered optimally. BEM will have to incorporate these changes within its operating model in Somalia in the follow-on period, which will demand radical thinking on how to strategically shift the UK Health partnership in Somalia.

Summary of the programme context:

Climate shocks
Ranked 178 out of 185 countries on the ND-GAIN Index (2024)[3], Somalia is one of the most vulnerable countries in the world to the impacts of climate change. Climate change is affecting Somalia today – temperatures are already 1 degree higher than historic levels. Future changes in Somalia are highly likely to be beyond anything seen before in any country on earth – temperatures will increase, rainfall patterns will change. The frequency and intensity of drought and flood cycles will increase and there will be new risks from tropical cyclones. This will both create new disease burden risks, and challenge health service delivery. Extreme heat will become a major health risk and a drag on productivity and growth.
[3] The Notre Dame Global Adaptation Initiative aims to enhance climate adaptation efforts globally by helping both private and public sectors prioritise adaptation strategies, by identifying vulnerable areas and providing practical solutions to prevent climate related disasters.

Flooding and Drought
Somalia continued to grapple with various challenges in the review period that have affected service delivery. The seasonal Gu rains from April to June 2024 were heavy and resulted in flash floods across central and southern Somalia, affecting Better Lives programme supported regions in Gedo, Galgaduud, Mudug and Banadir. The heavy rains and flooding destroyed the road infrastructure that was already in a deteriorated state – preventing movement of both people and goods to major towns such as Dollow (Gedo region) and Hobyo (Mudug region). The situation also hindered transportation of pharmaceutical and medical supplies from UNICEF and partner warehouses located in the capitals (Mogadishu and Hargeisa) to the last mile health facilities. This critically affected delivery of services resulting, in some cases, to stock out of supplies and lower utilisation of health services by the beneficiaries.

Below average rainfalls between October and December 2024 led to a substantial reduction in crop production, particularly in south central Somalia which led to migration of populations from Better Lives supported areas including Galmudug, further impacting health facility utilisation.

Insecurity
Insecurity and conflict especially in Gedo and Galmudug regions resulted in further population displacements, and in some instances, suspension or complete closure of services.

In February, Trocaire temporarily suspended all its services, including health, in Luuq district. This decision followed serious security breaches, direct threats to the Trocaire staff and violations of fundamental humanitarian principles by armed militia operating in the region. A week prior to the suspension, and during an intense episode of inter-clan violence, armed militia had stormed into the Trocaire compound in Luuq and forcibly seized three of the partner vehicles. Earlier in October 2024, armed gunmen had gained access into Luuq district hospital, also supported by the Better Lives programme, and killed a patient on the hospital grounds. This incident and others have exposed both patients and staff to serious risk and have been cited as a grave breach of humanitarian principles. Whilst the activities were resumed after a month of closure, the service delivery results from Gedo have shown a decline in access to healthcare services including across outpatient department, immunisation and nutrition interventions. Trocaire management led and engaged in extensive negotiations with the State (Jubaland) government to ensure that staff and patients are protected from future incidents.

In Galmudug region, Mercy USA also fully closed one of its facilities in August 2024 due to interclan conflict in the region. This necessitated reassigning of staff to the nearest facilities. However, most of the staff including nurses and midwives had to be let go noting that they were not keen to move to other regions. UNICEF and Mercy USA have ensured that the supplies (including nutrition commodities) that were in the facility at the time were transported to the closest warehouse for safe storage.

The above conflict is taking place in the wider context of rising threat from the Al-shabaab. In early 2025, Al-shabaab intensified operations with monthly incidents reported to have increased by 50%[4], with notable operations in several states including Banadir region. The persistent violence has forced UNICEF and downstream partners to restrict movement and suspend outreach activities in some instances. There are reports of partners who have had to withdraw from rural areas entirely. Furthermore, the insecurity has increased displacement of populations which has amplified disease risk in Better Lives areas of operation including Banadir, Jubaland and Galmudug[5].
[4] International NGO Safety Organisation Somalia and Somaliland Security report, April 2025.
[5] Integrated Disease Surveillance Weekly Epidemiological Bulletin, March 2025.

Government Dynamics:
Somalia continues to face profound challenges in security, governance, and socioeconomic development. Despite ongoing efforts by Somali authorities and international partners, the country remains plagued by instability, weak government institutions, and the enduring threat of terrorism, particularly from Al-shabaab. Al-shabaab remains the primary threat to Somalia’s security, conducting frequent attacks on government facilities, military installations, and civilian targets. The group’s ability to infiltrate major cities, including Mogadishu, highlights the weakness of Somalia’s security apparatus.

Inter-clan rivalries over land, water resources, and political influence continue to spark violence, particularly in rural areas. Clan militias often operate outside government control, creating additional layers of instability. Weak conflict resolution mechanisms exacerbate these tensions, with local communities frequently resorting to violence rather than legal or government-mediated solutions. The Somali National Army (SNA) is under-resourced and heavily dependent on international forces, particularly the AUSSOM and its predecessor, ATMIS[6].
[6] African Union Support and Stabilisation Mission in Somalia (AUSSOM) – April 2022 to December 2025; African Union Transition Mission in Somalia – established in January 2025.

The FGS exercises control primarily in urban centres like Mogadishu. There are ongoing political tensions between the FGS and FMS especially of Puntland and Jubaland – that have been excluded from the National Consultative Council[7] - which risks further fracturing of the sub-national states as the country heads to contested elections.
[7] The NCC is a de facto high-level platform for executive leaders at FGS and FMS levels in Somalia who negotiate and agree on contentious political issues.

The review period has seen a significant shift in BEM and FGS relations, informed by an ambition to strengthen reforms and ways of working with donors and partners, and which have delayed programme implementation. Key multilateral partners including Gavi and Global Fund continued to play a major role in ensuring rapid and effective humanitarian, health and social protection responses are delivered to regions that remain in conflict. Together with FCDO and other donors, these partners continued to influence the delivery of the Essential Package of health Services (EPHS). The FGS, and to a lesser extent the Government of Somaliland, has consistently raised significant concerns over this dynamic with insistence that the health sector strategy for Somalia should be conceptualised and led by the health authorities.

The health authorities, whilst recognising the significant support provided to the sector by FCDO, Gavi and GFATM, continue to emphasise donor and partner alignment towards an integrated ‘one plan, one budget, one report’ strategic programming. However, the health authorities do not have the capacity to guide this reform, and a government-led health sector coordination mechanism to inform the process is lacking. This situation is further exacerbated by strenuous relationships between the Federal Government and Federal Member States (FMS) and related departments including the Ministries of Health (MoHs). This has contributed, for instance, to delayed disbursement of funds to the State level MoHs with resultant delayed service delivery.

Delivery of several Better Lives activities have been affected by the above situation. This includes the implementation and finalisation of the climate vulnerability and adaptation assessment, delayed realisation of the ME&L deliverables including third-party monitoring activities and the programmes’ baseline assessment, and the climate and health assessment. Protracted discussions with the FGS Minister for Health and Federal Ministry of Health (FMoH) counterparts led by the BEM Senior leadership have been required to unblock delays to the programme.

USAID Cuts
The USAID stop work orders and ODA reductions have had a devastating impact. So far, Somalia has experienced approximately a 40% decline in funding across its health and nutrition sector. According to an assessment conducted by the Somalia (including Somaliland) Health Cluster in April 2025, 189 health and nutrition facilities have been closed. This translates to a 30% reduction in coverage of health and nutrition services. As mentioned in the output sections below, there has been a concomitant increase in the number of beneficiaries accessing Better Lives facilities as a result, especially in Banadir region. For example, Action Against Hunger managing Better Lives health and nutrition funded activities in Banadir region has witnessed a doubling in the admission of severe acute malnutrition cases in its facilities as from January this year, owing to closure of 27 facilities within its operational vicinity, that were previously funded through USAID.

UNICEF reports that the current nutrition supplies (specifically therapeutic foods) are projected to last until September 2025. Approximately 466,000 children are currently at risk of Severe Acute Malnutrition (SAM), and they would be 12 times more exposed to dying if they miss the much-needed life-saving treatment. To meet the needs, follow-on supplies would need to be procured and in-country by September 2025 at the latest. $12million is required to procure these and deliver life-saving treatment.

Disease Outbreak
Underpinning the above is the fact that Somalia is currently handling four distinct acute phase disease outbreaks, that is, acute watery diarrhoea/ cholera, measles, whooping cough and diphtheria. In April 2025 alone, 391 health facilities reported a total of 3,898 suspected epidemic alerts[8]. Among those reported were suspected measles (257), diphtheria (21), severe acute respiratory infections (1072), meningitis (8), whooping cough (64), typhoid (547), influenza-like illness (1,677), neonatal tetanus (3), acute jaundice (15), and bloody diarrhoea/shigellosis (212).
[8] Integrated Disease Surveillance and Response Epidemiology Bulletin Somalia, Federal Government of Somalia Ministry of Health, Department of Health Emergencies | Epi Week 16 (14th Apr – 20th Apr 2025) | Publication Date: 27 Apr 2025

Summary of FCDO Partnership

The review period has provided a more stable environment to enhance delivery as regards financial budgets and seen a stronger support from FCDO to both UNICEF and downstream partners. Having learnt key lessons from the last review period, during which significant ODA cuts were experienced in the programme, FCDO has pushed for and achieved a stronger way of working between itself and UNICEF, and between UNICEF and wider partners including the Federal Ministry of Health (FMOH), Somalia, and the Ministry of Health Development (MoHD), Somaliland.

Despite the significantly improved FCDO ODA budget certainty over the period of implementation, the Better Lives budget remains well below the levels intended in the business case. Better Lives, as mentioned above, was originally designed to deliver £20m in interventions every year. However, the programme has been allocated much less annual funding over the years due to UK ODA budget limitations, receiving only £16.2m for 2024/ 2025. This shortfall has resulted in difficult decisions.

The recalibration of the remaining Better Lives budget to 95% focused on core service delivery (initially allocated at 80%) and 5% divided between demand creation and behaviour change and health systems strengthening has prompted the need for innovative approaches with the BEM delivery team acting more as a facilitator than as a bilateral donor. To bridge the gap, there has been significant collaboration with other key actors in Somalia including with the World Bank and its GFF, GFATM and Gavi, driven by BEM with UNICEF as an able co-facilitator. Leveraging of support from these partners has been further increased this year as their funding and implementation became more assured (following the design of the follow-on programmes in the last implementation period). FCDO has also strengthened its partnership with other donors including Sweden, Germany and the King Salman Aid and Relief Center (KSrelief) to support various interventions such as immunisation, management of severe acute malnutrition, and management of common childhood ailments.

The Better Lives team has worked synergistically with the HARBS programme to realise opportunities to drive rapid response to outbreaks. This has been through the CAAFIMAD programme (explained further below). The efforts have significantly contributed to realisation of development gains.

As the UK flagship country for the Healthy Women Children and Newborns (HWCN – formerly the Ending Preventable Deaths – EPD – programme), work begun earnestly in Somalia[9] including Somaliland to draw on Technical Assistance resources and ensure recruitment of a Programme funded role that would augment BEM advisory capacity, to support health systems strengthening. Additionally, work kicked off through the Women Integrated Sexual Health (WISH II) and Global Health Workforce Programme (GHWP), both Centrally Managed Programmes (CMPs).
[9] Somalia includes Somaliland as the latter is under the jurisdiction of the FGS. All such reference in follow-on text will have this implied.

Through specifically defined dual key mechanisms[10] built into the programmes, the two CMPs are directly contributing to Better Lives in Somalia. WISH II has begun implementing sexual and reproductive health services in Banadir, Galmudug and Southwest regions (the former being specific regions where Better Lives is also implemented) and within specific Better Lives supported districts and facilities[11]. The GHWP has gone through its design stage and will enhance staff capacity, including those supported and implementing Better Lives activities in Awdal and Togdheer regions of Somaliland. Working in this manner, the two programmes will enhance efficiency and optimisation of resources and further widen the reach of beneficiaries supported. However, the CMPs will also be affected by the UK ODA budget cuts, with the maximum effect expected in 2026/ 2027 and follow-on financial years. This will greatly limit the extent to which the programmes will contribute to support delivery against their original objectives.
[10] Dual Key mechanism is an approach intended to build on programme coherence and consistency in delivery. It provides the required authority for the programme (at UK level) to engage in Somalia (with the BEM team) with day-to-day management agreed by the two Senior Responsible Owners within a framework established and approved by the Somalia Portfolio Board.
[11] WISH II main implementing partner in Somalia is the International Rescue Committee (IRC).

With the transition of the Better Lives programme out of 4 regions and 17 districts across Somalia and Somaliland in September 2023, BEM worked closely with UNICEF and the health authorities of Somalia and Somaliland to finalise prioritisation of the health facilities to be supported during the development phase. The discussions, though protracted, were finalised in April 2024. This saw an additional number of facilities (102 up from the original 93) across primary healthcare units, health centers, district and regional hospitals supported during the review period. This was necessary to ensure and facilitate access for beneficiaries especially in more rural communities such as Galmudug. Government specific financing or financing to support the transition including to ensure ongoing support for regions exited, or to cover components not fully supported through FCDO funding, has not been forthcoming. The FGS national budget allocation to the social sector has been minimal owing to priority given to the security sector, in the fight against Al-shabaab.

The Somalia Government leadership has been central to the delivery of the development phase of the Better Lives programme. The FMOH and MoHD have led decisions on the selection of facilities and interventions implemented. To ensure that the envisioned approach of supporting quality health services (as outlined in the business case) is maintained, the programme re-introduced a modest element of demand creation and behaviour change and health systems strengthening at the sub-national level and a revamped wider package of services which has been further taken forward during this review period.

FCDO has been intentional in providing additional funding - £5.2 million - to support climate resilient activities in 87 out of the total 102 facilities, informed by the climate and health vulnerability and adaptation assessment finalised in June 2024. Health facilities will now have better waste disposal and sanitation systems including wash areas and latrines for staff and patients, and solar powered fridges for better storage of vaccines and pharmaceutical supplies.
The work supported on service delivery, demand creation and behaviour change, health systems strengthening and climate resilience has seen a stronger multisectoral approach in delivery which has resulted in programme efficiencies as outlined in the VfM section further below.

Underlying the Better Lives business case is the assumption that the bilateral programme will transition to the World Bank under the Federal Government of Somalia (FGS) leadership subject to several benchmarks being met. The original benchmarks outlined in the business case were analysed by a team from the FCDO Central Human Development Department. An assessment of progress against these benchmarks was conducted as part of this review. Summary of headline findings are below:

1. The World Bank’s health and nutrition programme (Damaal Caafimaad) in Somalia is yet to demonstrate reasonable implementation that would allow for a successful transition. The programme has spent 63% (US$62.23 million) out of the allocated US$104.25 million between June 2021 and end of March 2025. This is a significant shortfall, especially as the programme ends in May 2025. However, an extension has been granted to June 2026 to allow finalisation of the activities in collaboration with the FMOH.
2. The World Bank’s slow implementation and different modality of working – through contracted implementing partners instead of directly through Government systems – does not allow building on and developing existing government systems.
3. The Damaal Caafimaad programme had specific health systems strengthening (HSS) objectives including strengthening of government public financial management, fiscal sustainability and economic growth including across the private sector. However, the HSS component has not worked well with only minimal data management activities implemented - focused on capacity building of Ministry of Health (MoH) staff.
4. Whilst the World Bank HSS component was meant to also strengthen coordination at FGS and Federal Member State (FMS) Levels, health sector coordination is currently weak with infrequent meetings and humanitarian support dominating the development sector. The FGS has played an active role in perpetuating this with resultant minimal to no transfer of resources to the FMS. The FGS has developed the National Transformation Plan as a follow- on to the Health Sector Strategic Plan II to mitigate these issues.

The above gaps do not offer confidence in the leadership and delivery of the Federal Government’s World Bank’s programme and creates risks that an FCDO contribution to the next generation of this programme is good value for money. The World Bank approach will also require delicate negotiated agreements for support to flow to Somaliland – a UK health objective. However, the assessment provided alternative options through which FCDO would consider a transition from a bilateral programme. The Global Financing Facility – Joint Financing Framework (GFF-JFF) is a trust fund that would allow for donors to pool funding whilst accounting for the risks. GFF-JFF would provide accountability and transparency of funds and allow for tracking of results by FCDO to inform impact on programming, among other parameters. This pooled fund option has been successfully adopted in Nigeria and further discussions are ongoing to establish a similar modality between FCDO and World Bank/ GFF in the Democratic Republic of Congo and Mali. BEM is currently exploring this modality, together with the World Bank and discussions have progressed. Communicating the results and option to the FGS (and Government of Somaliland) to manage expectations and establish a framework of mutual accountability will be key.

From early 2024, the Federal Ministry of Health has collaborated with the Ministry of Labour and Social Affairs (MoLSA) to realise a World Bank funded Social Safety Nets programme. Whilst FCDO leadership for this is provided through the HARBS programme, the Better Lives facilities in Banadir are being used by the programme to support vulnerable women and children to improve access to basic healthcare services by way of conditional cash transfers distributed as incentives. Another example of Better Lives leveraging in support and testing new approaches that could be replicated, in this case for demand creation. There have been some challenges in ensuring optimal engagement of the Ministry of Health and its collaboration with MoLSA and the approach which will be scaled up to other regions, will require ongoing monitoring to define any potential conflict-sensitivity and mitigate any associated risks in a timely manner.

Summary of Partner (UNICEF) delivery performance

The review period has seen UNICEF, as the Better Lives programme’s prime partner, pick up and showcase excellent results in the delivery of the programme. Since its inception in 2022, UNICEF has optimally supported engagement with Government, especially during difficult negotiations, including those that necessitated decisions on transitioning out of regions in Somalia and Somaliland. Between January and April 2024, UNICEF further led the discussions with FMOH and MoHD towards both finalisation of the selection of the facilities in which to implement services and defining a cost-effective and high impact package of healthcare services aligned to the EPHS that would best serve the needs of the vulnerable populations in supported geographies.

Importantly, UNICEF has lived up to the reasons of why FCDO selected it to lead Better Lives programme implementation. This includes its ability to leverage the competitive advantage of different partners to realise positive delivery outcomes, its ability to procure pharmaceutical and nutrition supplies whilst ensuring vast economies of scale and its significant inherent capacity to frontload funds to realise fast and timely programme implementation. UNICEF’s role as principle recipient of various key Global Health Initiatives (GHIs) being implemented in Somalia including Somaliland (Gavi, GFATM) and the World Bank and its role too as a key partner for other donor funding including Germany (KfW), Sweden and the Bill and Melinda Gates Foundation has allowed it to create synergies with the Better Lives programme that have helped realise high utilisation rates in key interventions within Better Lives facilities, even in the context of the challenges highlighted above.

Additionally, partners have provided reports that UNICEF has improved its monitoring and support of downstream partner activities at field level. This feedback has also been corroborated by Third Party Monitoring (TPM) exercises conducted. During the review period, UNICEF restructured its Zonal Field offices teams ensuring that these were now ‘manned’ by staff with longer-term experience and who knew the local/ contextual issues. Trocaire specifically reported improved supply chain management from UNICEF with regards to a marginal move from the push to pull system of procurement and distribution of medical and nutrition commodities to the facilities. This has seen some health facilities experience less stock out and able to improve their overall quality of care.

Despite the above, several challenges remain that BEM will need to work on with UNICEF in the next period. These include the need for UNICEF to be proactive in driving discussions with the State level ministries of health and local administration to safeguard programming; the need for UNICEF to support partners and MoH staff at facility level in improving knowledge and skills towards better pharmaceutical and supply chain management; and better management of budgets. On the latter, partners have complained that UNICEF takes time in actualising the specific partner documents at the start of each programming cycle which at times results in delays in implementation. Similarly, UNICEF struggled to provide the required granularity and regularity of budgeting, forecasting and expenditure reporting required for the new CDEL allocation. This required significant support and investment from FCDO, to ensure compliance with FCDO requirements.

With the upcoming potential scaling down of Better Lives activities because of wider FCDO reductions in ODA, UNICEF will have to work closely with partners to support a responsible and smooth transition of activities, including engaging FGS as early as possible to realise alternative options for access to services and thus ensure that vulnerable populations do not suffer in the process. This will be incredibly challenging with UNICEF, as it happens concurrently with wider institutional budget reductions and major restructuring in Somalia.

Future of a UK funded health programme in Somalia, in a 0.3% world

The recent announcement by the UK Prime Minister of reduction in ODA to 0.3% of GNI will have a major impact on health programming in Somalia. This financial year is the “transition year” to ensure timely exiting from areas no longer considered a priority. As with all bilateral Posts around the world BEM has been asked to model 30%, 50% and 70% ODA funding reductions from 26/27. Under all these scenarios, maintaining a large service delivery bilateral health programme is not affordable and why an early exit with closure at the end of the financial year is considered highly likely.

Direct impacts of reduced UK health funding. The 102 facilities supported by the Better Lives programme cover a total catchment population of 2,600,000 individuals among them women, girls, men and boys. Women and children who make up the bulk of the vulnerable population targeted by the programme represent 70% of this population. Whilst the programme reached 1.4 million individuals during the review period, the wider population retain the capacity to access services in supported facilities, a situation that will be amplified by the closure of USAID funded interventions. No other bilateral donor is expected to fill this service delivery gap left by the early closure of Better Lives, and it is unlikely that the Governments of Somalia or Somaliland will be able to self-finance service delivery through their own domestic resource mobilisations – a situation also witnessed when the UK Government exited regions following the 2022 ODA cuts. The World Bank successor health programme is expected (including Somaliland) to begin in Somalia towards the end of 2026 which will mean a gap in service provision if there is a decision to work in current Better Lives areas. At the time of writing, the World Bank had not confirmed the IDA21 allocation to Somalia, and it remained unclear on where health featured in the hierarchy of cross-Government investment priorities. By signalling early the end of UK Better Lives funding to downstream partners and local communities, this might allow for local financing solutions for modest services, but this is expected to be ad hoc.

Somalia’s health financing landscape is characterised by a heavy reliance on external aid and out-of-pocket payments (88% of total health funding), with limited government investment. In 2020, before the on-budget World Bank programme, the Federal Government of Somalia allocated approximately US$9.4million to the health sector, representing about 0.18% of the country’s Gross Domestic Product (GDP) and 1.9% of total government expenditure[12]. This financial shortfall has led to significant dependence on donors and development partners. In January 2025, the budget allocation to the health sector has marginally increased to 6.9%. This low allocation reflects the FGS’ inability to raise adequate funding for essential health services.
[12] World Bank Somalia economic Update, June 2022, edition No. 7.

The state of the major institutions is weak, and the civil service is underdeveloped and under resourced. This means that there is a high turnover of staff, particularly within those who are skilled. Allocations on health expenditure by the FGS remain very low. Most of the expenditure is on recurrent staff costs exacerbated by the problem of ghost workers. There is no performance management framework, roles and responsibilities remain unclear, and salaries are often topped up or paid for by individual donors in an uncoordinated manner. Decentralisation of aid between the FGS and FMS is still nascent and without strong leadership at both national and sub-national levels bottom-up planning with or without community engagement is far from a reality for all. Capacity is lacking across all ministries which impacts on the financial management systems needed for the health sector to ensure efficient and effective expenditure. For example, any fees raised by facilities are not necessarily re-invested into facility improvements. This lack of financial resource planning impacts prioritisation of activities within the EPHS. A strong government-led coordination mechanism to work on the above necessary reforms is lacking.
Indirect impacts of the reduction in UK health funding. Historically, the US and UK Governments have been the largest sovereign donors to Gavi’s and GFATM’s core programmes. The current shift in the global funding landscape will significantly change this dynamic. Whilst FCDO is yet to outline its support to these Global Health Institutions (GHIs) for their next funding cycles (2026/2027), the USAID funding cuts have reduced the Gavi and GFATM global budgets by 30% and 33% respectively. Locally, this has necessitated difficult decisions for programming in both Somalia and Somaliland. Both GHIs have begun communicating with the FMoH and MoHD the impact that this will have to programming related to immunisation, malaria, HIV/AIDs and Tuberculosis. By end of June 2025, GFATM expects a 10% reduction in its overall funding landscape to Somalia with a further anticipated reduction in overall budgets in the next 2 years. The major impact will be felt across the programmes’ health systems strengthening support including across all six WHO building blocks[13]. Significantly, Gavi and GFATM will have to cease support to the health management information system (data platforms in Somalia and Somaliland) and pharmaceutical and supply chain.
[13] The WHO building blocks are a framework established by the World Health Organization to strengthen health systems, consisting of six essential components: service delivery, health workforce, data information systems, medical products, financing, and governance.

The World Health Organisation (WHO) which has been a significant player in the Somalia health sector will imminently phase considerable funding cuts by December 2025. The US Government has already communicated of its intent to stop all funding to the organisation. As such, this will significantly affect disease surveillance and response, primary health care support and support to government coordination and leadership (as some of the mandate of WHO) in Somalia.

As mentioned in previous sections, GAVI, GFATM, the World Bank and other donors have consistently used the Better Lives programme as an anchor for driving integration and ensuring reach across vulnerable populations. Indeed, the Better Lives business case was designed with this in mind, and the supported facilities and populations have benefited from the pharmaceutical products and medical supplies, vaccine antigens and demand creation activities that these partners provide through their programming. Cessation of the Better Lives programme will, therefore, have a wider negative effect to the target population, beyond the main services directly implemented.

Revised strategy for UK health partnership. Despite the reduction in UK bilateral health funding the BEM is still expecting to remain technically engaged in the health sector in Somalia (including Somaliland). This will be guided by a wider paradigm shift in FCDO away from direct health service provision, which is unsustainable and risks substitution, to a health systems strengthening, technical advice and guidance partnership approach. Steers from the FCDO Global Health Department outline a modality of working and emphasise on the continued ODA support to programmes that meet:
1. The highest need including new/ growing global health threats such as climate change, sexual and reproductive health and rights and anti-microbial resistance.
2. Maximum value for money (VfM) for the UK taxpayer and focus on outcomes that are not being delivered through FCDO multilateral and GHI investments, particularly work done by Gavi, GFATM, WHO and UN agencies.
3. Health systems strengthening/ transformation support rather than direct service delivery. This is with the intent of supporting Governments in Low- and Middle-Income Countries (LMICs) such as Somalia to deliver their own health outcomes. There would need to be consideration towards embedding resilient health systems alongside humanitarian action. Within this, there is emphasis of protecting SRHR and expanding universal health coverage.
4. Catalytic demands with the intent that programmes receiving UK ODA funding should look to support wider UK diplomacy/ advocacy campaigns on global health and leverage wider investments by other actors both domestically and internationally; and
5. UK relations with country governments based on partnerships (rather than paternalism).
Somalia is, therefore, well placed to continued UK Government support on health programming initiatives that support system strengthening whilst working closely with the FGS and Somaliland authorities, GHIs and World Bank. Areas of focus for the UK over the next 12 months will be supporting the design of the next phase of World Bank health programming, with a likely modest UK contribution, research and policy thinking on the enhanced role of the private sector in health service provision; and supporting health governance and accountability mechanisms whilst working closely with the BEM Governance team to improve FGS and FMS leadership, planning and citizen engagement.
BEM has already messaged to Better Lives partners that it is highly unlikely there will be funding for bilateral health service delivery beyond this financial year (20255/26). Final decisions will need to be weighed within the Equalities Impact assessment for BEM (noting the targeting of Better Lives is women and children). UK reductions and a wider ODA reset will require a fundamental rethink in Somalia and Somaliland on health service delivery models, particularly what is affordable for the state.

BEM is in the process of defining what the possible financial and delivery model for the next UK Government engagement in health would be whilst considering the Somalia and Somaliland context. FCDO retains the responsibility of supporting partners to ensure a smooth exit and thinking through potential reputational risks to the organisation.

Major lessons and recommendations for the year ahead

LESSON LEARNED - Healthcare Delivery in insecure and conflict affected areas
The insecurity and inter-clan conflicts resulting in disruption of health service delivery including timely distribution of pharmaceutical and medical supplies necessitates a new approach to working with local administrations. Strengthening partnerships with local health authorities can improve coordination and security for healthcare delivery. Costly alternatives, such as air transport also contribute to VfM (with regards to effectiveness and efficiency) as they ensure timely delivery of supplies and subsequently contribute to delivery of quality care. Contingency planning with partners and the Ministry of Health is vital to maintaining healthcare access during conflicts. Involving community leaders in safety and security assessments can help mitigate emerging threats. Leveraging existing and strong humanitarian delivery mechanisms like the CAAFIMAAD Plus consortium[14] – that also operates through some Better Lives implementing partners (Trocaire and Action Against Hunger) and in similar regions is key in ensuring continuity and rapid response to shocks that would otherwise erode gains realised through the longer-term programme. UNICEF’s role in bridging the gap between partners and government (FGS and Federal Member State – FMS) will be critical in ensuring timely mitigation of any risks to service delivery.
[14] A FCDO Somali funded Programme providing Integrated Emergency life-saving Health, Nutrition, WASH and Protection support for vulnerable populations in South Central Somalia and

LESSON LEARNED – Partnerships and Resource Mobilisation
The reduction of Better Lives support in the demand creation and behaviour change and health system strengthening components requires ongoing leveraging of resources from other UNICEF-managed programs, including GFATM, World Bank, GAVI, the Bill and Melinda Gates Foundation, among others. These partnerships have provided a platform that BEM is now using to broach wider discussions including on sustainable pooled funding mechanisms that the next generation of a UK funded health programme in Somalia could pivot to. This is even more critical to the sector, as it seeks to maximise the impact and effectiveness of wider donor funds, which are almost all reducing. These partnerships continue to showcase partners’ alignment with the partnership principles agreed with the FGS and signed to in November 2023.

RECOMMENDATION – Communication and programme transitions:
Timely comprehensive discussions with both partners and the FGS and Somaliland will be necessary and important in the wake of scaling down the programme noting the highly likely decision to exit from bilateral programming. This will allow for a smooth transition and responsible exit from direct service delivery ensuring that the most vulnerable populations currently supported do not experience worse health situations. Early communication and ongoing collaboration with and support to the FGS and Government of Somaliland will prompt thinking through a sustainable approach for the health authorities’ continued support to the sector, including identification of other donors that could fill the space. Risks associated with the exit of UK funding will need to be carefully calibrated and mitigation measures comprehensively outlined and instituted. The risk appetite for the programme will, therefore, be increased to ensure appropriate mitigation actions are included in support of continued delivery in the short-term. (Action: BEM in collaboration with UNICEF).

RECOMMENDATION - Timely response to emergencies:
The Somalia emergency and conflict-prone context demands a dedicated contingent and flexible budget to ensure timely response. Otherwise, there would be erosion of gains realised through previously implemented or ongoing programming. Rapid and comprehensive response to emergencies also contributes to resilience of targeted communities and health systems. A mechanism that allows comprehensive response to emergencies within the Better Lives areas should continue to be sought through the HARBS programme. This will also ensure continued surveillance and timely response to diseases of outbreak potential especially without the Better Lives bilateral programme that has been the delivery model for response in the supported regions. (Action: BEM’s realisation and actualisation of opportunities existent within the HARBS programme).

RECOMMENDATION - Supply chain management in humanitarian contexts
The global increase in emergencies has placed extreme pressure on the supply chain, leading to delays in the delivery of essential commodities, health, and nutrition supplies. UNICEF, with its largest humanitarian supply hub, maintains a significant procurement capacity but is also dependent on the availability of efficient transport modalities across the Pacific to deliver goods. Approximately 40% of supplies procured at the beginning of the program are either in the final preparation stage or travelling by sea to Somalia. It is critical to initiate procurement processes as early as possible and secure sufficient funds to maintain this throughout the program timeline. UNICEF should continue to leverage its comparative advantage in frontloading funds at the beginning of each programme cycle in support of early commodity procurement. (Action: BEM with direct collaboration of UNICEF and downstream partners).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Better Lives business case Theory of Change (ToC) for the development phase of the programme was significantly refreshed by HHELMS in February to March 2024, in collaboration with UNICEF, downstream partners and the Government. The revised ToC has also provided an integrated framework for developing the baseline (and subsequent midline and endline data collection), establishing TPM arrangements and for programme evaluation – deliverables which are now all ongoing. Whilst the existing Better Lives business case ToC provided a coherent justification for the programme, its further refinement and updating targeted the following issues:

1. Reorientation of the programme away from the comprehensive systems strengthening, stewardship and coordination, and demand creation towards more focus on service delivery.
2. Full articulation of the causal pathways, especially to bring about behaviour change, including the roles of different actors (e.g., assumptions related to the motivation and behaviour of target groups and factors affecting their ability and willingness to use services).
3. Specifying as assumptions the conditions under which causal pathways will function as intended, and hence some of the key risks to successful implementation.
Additionally, the ToC review sought to address clarity between outputs and outcome as defined in the existing programme log frame. The review also included a more explicit analysis of the roles of different actors in ensuring optimal Better Lives implementation.

In line with the above changes, the Better Lives logical framework has also been revised, specifically on indicators to be used, and this has informed coherent programme delivery from 1 April 2024.

The Better Lives Programme Theory of Change (ToC) holds that increased coverage and utilisation of key essential services will be enhanced by effective demand creation, strengthened infrastructure and community resilience supported by strong health systems and improved Government stewardship. In the 2023/2024 Better Lives review period, the eight assumptions depicted in the programme’s business case underwent changes to reflect programme adaptation to contextual issues and to take into account the ODA reductions and consequent decrease of the demand creation and behaviour change, and health systems strengthening components as outlined in sections above.

The above ToC statement holds true, given the results of this Annual Review. Ongoing service delivery is dependent on a community that is aware of the available health care delivered and that is effectively supported to positively seek and access these services. FCDO and partners including health authorities need to interact comprehensively, align and support key factors to realise this. The factors include:

1. Engagement with Government, including their willingness to be involved, at strategic/policy level to curate programme structure, delivery and sustainability in the context of ongoing insecurity, uncertainty of allocation of the national budget to the health sector and a dearth of strong health systems.
2. Strong engagement by the health authorities on ongoing interventions and ensuring better commitment to delivery of both services and system strengthening initiatives.
3. Capacitated regional and district management teams and health facility and community staff.
4. Ensuring and taking forward collaboration with the MoH on programmatic aspects including coordination, governance of the programme and overall programme implementation.
5. Planning, convening, and implementing joint supportive supervision visits between FMOH, partners and UNICEF with outcome reports shared and actions followed through.
6. Support of alignment of programme priorities (at programmatic and policy level) with other key actors including World Bank, Gavi, GFATM.
7. Robust monitoring and supervision of health facility staff performance and augmenting this with tailored training.
8. Support to ongoing related interventions to the Better Lives programme including ensuring better commitment by the MoHs.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The overarching Better Lives programme impact indicator is ‘improved health and nutrition status for vulnerable Somalis’. This is further defined by the specific three impact indicators below:
- Maternal Mortality Ratio (MMR);
- Under five Mortality Rate; and
- Severe Acute Malnutrition Rate.
UNICEF has had the intention of supporting a nationwide (Somalia including Somaliland) Multiple Indicator Cluster Survey (MICS) to complement the Somali Health and Demographic Survey (SHDS) conducted in 2020 and provide more recent data across health and nutrition indicators and disease burden. However, this has not been realised owing to resource constraints. The World Bank’s plan to conduct national household surveys supplemented by rapid reviews, in collaboration with the FMOH and MoHD, has also not materialised. Moreover, the last census in Somalia was conducted in 1976. As such, assessment of impact indicators for the Better Lives programme has proved difficult.

To offset the above challenge, BEM has factored in an assessment of impact level indicators through the commissioned programme evaluation that is currently underway and projected to end in January 2027. Noting the early closure of UNICEF, the evaluation timelines will be reviewed and brought forward. In addition, and whilst focusing on UNICEF programme support, the Better Lives programme evaluation will seek to cover wider interventions that directly contribute to and influence implementation. This will include understanding the extent to which
system strengthening activities (technical assistance within the Ministry of Health in Somalia and Somaliland) under the Healthy Women Children and Newborns work that directly feeds into Better Lives, impacts the programme. Complimentary support to Better Lives, provided through other programmes including the World Bank’s female health worker programme, GFATM (community health and health management information systems among others) and Gavi (support to vaccines and cold chain systems), will also be reviewed.

Better Lives’ six outcome indicators have been used to assess the programme’s contribution to broader health needs. These specifically provide analyses for the period October 2023 to February 2024 (development phase of the programme). Progress is as follows:

Indicator(s)	Milestone(s) for this review: Planned (April 2024 – March 2025)	Milestones (Progress) Achieved (April 2024 – Mar 2025)	Score
Outcome Level: Improved access to quality essential health and nutrition services
Outcome Indicator 1: Modern Contraception Use
% of women in catchment areas supported by Better Lives using modern contraception.	1.7%	3%	A+
Outcome indicator 2: Antenatal Care (ANC) Coverage
Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in catchment areas of Better Lives supported facilities/ ANC-4th visit coverage	33%	39%	A
Indicator 3: Skilled Delivery at birth
Skilled attendance at birth - % of deliveries in Better Lives supported areas attended by skilled health personnel/ Skilled birth attendant delivery rate	50%	87%	A++
Outcome Indicator 4: Immunisation coverage
Proportion of children in catchment areas of Better Lives supported facilities vaccinated with the third dose of pentavalent vaccine/Pentavalent 3rd dose coverage (0 - 11 m)	71%	126%	A++
Outcome Indicator 5: Severe Acute Malnutrition
Severe acute malnutrition – proportion of discharged children who recovered from SAM treatment in OTP/SC	95%	96%	A
Outcome Indicator 6: Utilisation and access
Proportion of population in the catchment areas of Better Lives supported facilities using OPD services[15]/ outpatient utilisation rate	0.26	0.46	A+
[15] The number of outpatient visits from the catchment areas of Better Lives supported facilities as a proportion of the estimated total population in the catchment population served by the Better Lives supported facilities

All six outcome indicators surpassed the milestone targets for the reporting period. The high achievement is majorly attributed to established service availability across all target health facilities, as compared to the last review period when facilities specifically in Galmudug, Togdheer and Awdal regions had a delayed start of operationalisation over a five-month period (October 2023 to February 2024) pending prioritisation discussions with the respective health authorities.

Joint monitoring and supervision by UNICEF, partners and the MoHs has further contributed to the achievement by ensuring a coordinated approach to identifying and directly addressing gaps in a timely manner with MoH staff in the facilities. Gaps addressed included ensuring that eligible children below five years were targeted for immunisation through the Gavi funded Big Catch-Up Campaigns (BCU) to increase immunisation coverage, provision of stronger health and nutrition integrated service delivery across multiple service points (antenatal care, immunisation, etc.), and consistent supply of family planning commodities through UNFPA.

UNICEF continued to leverage support through wider programmes to strengthen demand creation and community mobilisation with subsequent increased service utilisation in Better Lives areas. Specifically, this included social and behaviour change activities supported by the German funded Joint Resilience programme (in Galmudug), and Gavi, GFATM and World Bank funded community/ female health workers.

Of note, the aggregated performance masks significant regional variations, with Somaliland performing better than regions in Somalia, and Galmudug having the lowest achievement (across all indicators. Moving forward, the BL program will need to realise innovative approaches and stronger leverage with other donor supported programmes to improve community engagement and social mobilization for behaviour change in poorly performing regions, especially in view of declining funding. Specific achievements per indicator are detailed further below.

Outcome indicator 1: 3% of women in Better Lives supported areas use modern contraception. Overall, contraceptive use remains very low in Somalia due to cultural and religious reasons. Noting these constraints, a low target was set using baseline data from the national data platform – the District Health Information System (DHIS II). The programme utilised the Reproductive Health Supplies Centrally Managed Programme (CMP) to ensure consistent provision of family planning commodities to the respective health facilities. UNFPA, through the Global Agreement with FCDO holds the contract for this CMP for commodity supplies in implementing countries. Ongoing strong collaboration between UNICEF and UNFPA, therefore, has served to increase the supplies at end-user facilities. Key to improve uptake of family planning will be a ‘values clarification and attitudes transformation’ training targeting front-line healthcare workers in the next implementation phase. This will encourage participants to explore their assumptions about sexual reproductive health and rights, including contraceptive use, and examine their role in assuring women’s safe access to these services.

The USAID funding cuts have adversely affected UNFPA, which has since begun closure of its previously funded facilities and interventions in Somalia. The WISH II programme will serve as an alternative especially as regards provision of trainings to the Better Lives staff in the interim and in supplementing provision of family planning commodities. Discussions with the International Rescue Committee have begun.

Outcome indicators 2 and 3: During the review period, UNICEF worked with partners to strengthen forecasting of medical supplies for maternal and newborn child-care and directly supported transportation of supplies to the facilities from alternative funding sources, which significantly contributed to their consistent availability and achievement of these indicators. An adjustment to the population denominator across these indicators to allow for use of health facility catchment population figures instead of district level catchment population further ensured accuracy in indicator calculation. Further, specific training on management of pregnant women, counselling on antenatal care (ANC) and care for the newborn increased staff knowledge and awareness. These factors further enhanced beneficiary confidence and utilisation of antenatal care services and skilled delivery at birth.

Outcome indicator 4: The immunisation coverage of children vaccinated with Pentavalent 3[16] significantly surpassed the target due to integration of immunisation and nutrition services at the point of first contact with the clients/ patients. In total, 95,793 children aged 0-11 months were vaccinated. Nutrition services including screening of children under the age of five years and management of severe acute malnutrition (SAM) with or without complications at the stabilisation centres or outpatient therapeutic centres, respectively, act as a pull factor for beneficiaries to access services. Partners consistently leveraged this to ensure better uptake of services. Moreover, three rounds of the Big Catch-Up Campaigns[17] that included Better Lives supported facilities and populations were conducted reaching 634,970 children under the age of five years in total. Gavi support in the campaigns was on community mobilisation, logistics and provision of vaccines. BEM support included staffing (and payment of their incentives) and medical supplies (including syringes and personal protective equipment).
[16] A vaccine targeted at reducing the incidence of diphtheria, pertussis/whooping cough, tetanus pneumonia and meningitis diseases. Given at 14 weeks, pentavalent 3 vaccine is used as a measure for full immunisation in children below the age of 1 year.
[17] The ‘Big Catch-up’ is a targeted global effort to boost vaccination among children following declines driven by the COVID-19 pandemic. It is aligned to the immunisation agenda 2030 and is driven by Gavi with support from key partners including WHO, UNICEF and the Bill & Melinda Gates foundation among others.

Outcome indicator 5: Between April 2024 and March 2025, 97% of children admitted for management of severe acute malnutrition were discharged as recovered, exceeding the 95% target. Several factors contributed to this achievement including targeted training of health and nutrition workers, their close supportive supervision by both UNICEF zonal teams (located at field level) and downstream partners, and integrated provision of services as noted in the point above on immunization. Additionally, UNICEF health and nutrition sectors strengthened their integration – an aspect that has greatly improved this year. Consequently, there was improved data analysis on the number of patients requiring nutrition services in specific Better Lives facilities and enhanced provision of nutrition supplies to support comprehensive quality management. UNICEF also leveraged community outreach services through Sweden and the World Bank’s Female Health Workers (FHWs) Programme in targeted areas which enhanced utilisation of services.

Outcome indicator 6: Despite disruption of services due to ongoing inter-clan conflict in Galmudug and Gedo, especially between December 2024 and February 2025, and the temporary closure of Awdal Hospital in Somaliland due to a rainstorm in late 2024, the health facility utilisation rate surpassed the target of 0.26. Again, engagement of the World Bank’s Programme FHWs and social mobilisers through the Gavi immunization Programme helped increase awareness amongst and mobilized communities to utilize health services.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Access to basic social services continues to be severely constrained by the effects of a poorly regulated health system ravaged by over 3 decades of war, ongoing shocks including disease outbreaks, limited government capacity and very low financing for health care. Whilst donor funding remains the key financing modality to the Somalia health sector, the decline in funding from the international community requires realisation of a different modality for implementation that does not include donor-led financing.

The Better Lives programme is the only large multi-year health and nutrition development programme that has been rolled out substantially and that continues to demonstrate positive results across a wide range of interventions. Better Lives facilities and associated services have played a life-saving role in response to regular climate shocks and increasing impacts of worsening insecurity. The programme has also led a strong approach to health systems strengthening. It has improved capacities of the district and regional health management teams in all its regions; driven the revision and expansion of the community health strategy in direct collaboration with UNICEF; and ensured skills and knowledge capacity building to its health workforce. Additionally, Better Lives has strengthened data quality and use through participation in health indicator review and actions with the Ministries of Health.

Other key programmes including the Damaal Caafimaad World Bank programme have struggled with implementation, including not having begun in Southwest State and has only implemented 63% of its funding, having begun in June 2021. The USAID cuts provide considerable complexities to an already financially constrained environment. GFATM and Gavi next funding cycles remain uncertain as a result. In any case, the contribution of the latter two to the EPHS has been limited as these are mainly vertical programmes [18].
[18] Gavi’s focus is on immunisation and provision of related antigens, whilst GFATM focuses on treatment and management of malaria, tuberculosis, and HIV/AIDS. Both have significant health system strengthening support which the Better Lives programme has leveraged.

A recent report[19] indicates that whilst the maternal mortality rate in Somalia has declined from 692/ 100,000 live births (Somalia Health and Demographic Survey, 2020) to 563/100,000 live births in 2023 progress is slow and insufficient. Collective effort from Somalia Government, donors, and multilateral agencies will be required to further support a move to better healthcare.
[19] Trends in maternal mortality estimates 2000 to 2023 Estimates by WHO, UNICEF, UNFPA, World Bank Group and UNDESA/Population Division

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Health facilities deliver quality reproductive maternal healthcare and nutrition services, including family planning, to women of childbearing age
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 – March 2025)	Milestones for this review: Achieved (April 2024 – March 2025)	Progress	Score
Output Indicator 1.1:
Number of Better Lives supported health facilities providing contraceptive services	44	61	139%	A++
Output Indicator 1.2:
Number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy[20]	31,233	17,557	56%	C
Output Indicator 1.3:
Number of deliveries assisted by skilled birth attendants at Better Lives supported health facilities[21].	29,094	39,615	136%	A++
Output Indicator 1.4:
Number of women who received post-natal care (PNC) within 48 hours of childbirth.	14,136	25,603	181%	A++
Output Indicator 1.5:
Number of facility-based staff and community health care workers that are trained in Maternal and Newborn Care in the targeted Better Lives health facilities.	100	96	96%	A
[20] Outcome indicator 2 measures 4th ANC visit - which is recommended by WHO at that level as it captures coverage and provides an understanding of women who are completing the recommended 4 ANC visits at a minimum. The ANC 1 indicator is a measure of the specific programme’s/ partners’ strengths in identifying and ‘recruiting’ pregnant mothers into the system to begin receiving services. This will further lead (if done well and supported by strong community health systems) to increased skilled deliveries at birth and better postnatal care outcomes.
[21] Output indicator 1.3 measures the number of deliveries whilst at outcome level, the percentage (coverage) is measured. The indicators have been recommended by the health authorities, partners and HHELMS team following extensive discussions. They reflect indicator language within the DHIS II.

Briefly describe the output’s activities and provide supporting narrative for the score.

This year saw the number of healthcare facilities increase to 102, from 93. The increase in facilities was agreed with the health authorities specifically in Galmudug to ensure optimal access to services for vulnerable women and children in the scarcely populated region. The 102 health facilities include 10 district hospitals, 69 health centres, 19 primary health units and 4 outreach sites and are fully operational. 94% (82 out of 87) of the targeted facilities have delivered interventions aligned to the four essential health services packages, that is, maternal and neonatal health, immunisations (for both children under five years and those specific to pregnant and lactating women), child health including management of childhood illnesses, and nutrition. However, nutrition integration remained a challenge in some health facilities in Togdheer and Galmudug regions due to limited human resource capacity. One health centre in Galmudug region does not have the full complement of cold chain equipment for storage of vaccines; whilst another facility in the same region was closed due to insecurity. Four district hospitals in Awdal and Togdheer regions are only providing Comprehensive Emergency Obstetric and Newborn Care (CEmONC)[22] services. Further detail on how UNICEF and partners have worked to ensure ongoing delivery despite the challenges is provided in the sections below.
[22] CEmONC services are the interventions provided to pregnant women and newborns experiencing fatal complications, including severe bleeding, infection, prolonged or obstructed labour, eclampsia, and asphyxia in the newborn. CEmONC interventions include safe blood transfusion, providing oxytocin and antibiotics, performing caesarean sections, manual removal of the placenta, assisted vaginal delivery, abortion (only when pregnancy is life-threatening) and resuscitation of the newborn.

A climate and health vulnerability and adaptation (V&A) assessment was conducted across all Better Lives facilities and completed in June 2024. As a result, the programme expanded its essential health services delivery package to include water sanitation, and hygiene (WASH) services. These have been integrated within the wider maternal newborn and child health and nutrition package.

Output Indicator 1.1: As mentioned in the outcome indicator 1 section above, there was a higher reach as regards women accessing modern contraceptives during the review period, despite the cultural constraints. 61 out of the targeted 44 health facilities provided contraceptive commodities. Improving this indicator will require strengthened social mobilisation and community behaviour change. So far, UNICEF and the downstream partners have leveraged existing community structures including the World Bank’s female health worker (FHW) programme, the UNICEF nutrition supported community health workers (CHWs), and social mobilisers funded through the Gavi programme to create demand for family planning services. However, the coverage of these community-led activities remains limited. Traction and optimal uptake of these services would be better realised from direct support through the Better Lives programme – which would ensure provision of a comprehensive package delivered through specific programme funded staff.

The number of antenatal care (ANC) clients seen for the first visit before 12 weeks of pregnancy (Output Indicator 1.2) increased during the review period, although the target has not been reached. This is due to minimal understanding of the total catchment population which led to setting of a higher target. The baseline assessment will seek to address this. A total of 17,557 pregnant women attended ANC in their first trimester, compared to 13,546 in the previous period (April 2023 to March 2024). The progress is attributed to the availability of improved ANC services at the supported facilities including within the primary healthcare units (PHUs) and the increased functional health facilities providing the services. Specifically, PHUs have served to increase access to services for women who would have otherwise struggled to get necessary care. The CHWs that support each PHU and assigned a certain catchment population affiliated to the same provide services at household level and refer clients to nearby health centres and district/ regional hospitals, thereby increasing access. Use of ultrasounds in the first trimester has also encouraged visits for ANC. These have been provided from multiple sources including the Better Lives programme (through the CDEL funding), and community engagement that has facilitated funding from the diaspora. Additionally, increased health education targeting ANC clients in facilities and communities has further raised the importance of early ANC especially noting the culture of hiding pregnancies amongst pregnant women in Somalia until the last trimester.

Output Indicator 1.3: The period saw the number of deliveries assisted by skilled birth attendants within the Better Lives supported healthcare facilities increase and surpass the target (136% achievement). Increased utilisation of these services by pregnant women contributed to this, especially given the scaling down of similar activities run by UNFPA and Save the Children in facilities previously funded through USAID. Referral services, especially between health centres and district hospitals, were strengthened through the Better Lives programme to further enhance timely access, with a further consequence that more women outside of Better Lives catchment population accessed the supported facilities.

Output Indicator 1.4: The number of women who received post-natal care (PNC) within 48 hours of childbirth (25,603) surpassed the set target of 14,136. By leveraging community health workers’ activities supported through other donor funded programmes, UNICEF and partners were able to ensure a wider reach by strengthening house-to-house visits. The PNC clients include deliveries conducted at home and that arrive at the facilities within 48hrs to ensure that the newborn babies receive vaccines[23], hence the high achievement of this indicator. However, note is taken that this achievement failed to ensure that all women who delivered with the help of skilled birth attendance at the Better Lives supported health facilities received PNC services. Culturally, the Somali community does not stay for more than a few hours within the facility following a normal delivery that is also without ensuing complications to both the mother and child. This does not allow for a full assessment of both and provision of the required after-care including ensuring comprehensive breastfeeding of the child, which are interventions included in the PNC package. The Somali Health and Demographic Survey (SHDS)[24] indicates that an overwhelming 89% of the mothers do not receive post-natal care check up in the first two days after childbirth. UNICEF and partners have incorporated training of frontline and community healthcare workers in the next implementation period to support increased community awareness of the need of PNC services.
[23] Specifically, the bacille Calmette-Guérin (BCG) vaccine given at birth in regions/ countries with high incidence of Tuberculosis.
[24] Somali Health and Demographic Survey, 2020_Executive Summary. Federal Government of Somalia.

Output Indicator 1.5: Number of facility-based staff and CHWs that are trained in maternal and newborn care in the targeted Better Lives health facilities. A training needs assessment, supported by downstream partners and the State and Federal Ministries of Health, identified several critical training needs for staff in the Better Lives facilities. These included training on integrated management of childhood illnesses (IMCI), Kangaroo Mother Care (KMC)[25], Early Essential Newborn Care (EENC), Basic Emergency Obstetric and Newborn Care (BEmONC[26]), infection prevention and control, and healthcare waste management. To address these needs, a phased training approach was initiated whilst considering the availability of trainers (including from alternative funding sources, e.g. the GFATM) and availability of approved national guidelines. On the latter, UNICEF is working with both the FMOH and MoHD in Somalia and Somaliland, respectively, to review and revise existing guidelines and training materials to ensure they are fit for purpose.
[25] Kangaroo Mother Care (KMC) is a method of caring for preterm or low-birth-weight infants that involves continuous skin-to-skin contact with the mother or a substitute caregiver. This practice is recommended to start immediately after birth and should be maintained for 8-24 hours per day to promote bonding and breastfeeding. It has been shown to be a safe and effective alternative to conventional neonatal care, particularly in under-resourced settings, and can significantly reduce morbidity and mortality rates in low-birth-weight infants.
[26] Basic emergency obstetric and newborn care (BEmONC) is a primary health care level initiative promoted in low- and middle-income countries to reduce maternal and newborn mortality. Provided at the health centre or facility level, it includes the following signal functions: Administration of parenteral antibiotics and anticonvulsants, removal of retained products of conception, assisted vaginal delivery, manual removal of the placenta and resuscitation of the newborn.

In the reporting period, the programme successfully trained 96 healthcare workers (44 female and 52 male) in IMCI across Galmudug and Banadir. This has ensured that each supported facility has at least two trained healthcare workers – essential for enhancing the quality of services. Similar trainings are planned for Gedo, Togdheer and Awdal regions. Additionally, UNICEF collaborated with the FMOH and MoHD to conduct a training of trainers (ToT) for KMC in Mogadishu (Somalia) and Hargeisa (Somaliland). The trainings have benefitted healthcare professionals in health centres and district/ regional hospitals, professional associations and Banadir and Hargeisa Universities, towards creating a pool of professionals that can expand care across the country. Costs for these trainings have been from both Better Lives and leveraged from alternative sources including grants from Saudi donors and the Joint Resilience Programme (German).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Revisions to the estimation of the catchment population was a significant change across all indicators reported in the current logical framework. Previously, district populations were used as denominators resulting in inaccurate calculation of the program performance. The change was necessary as the Better Lives health facilities cover between 10 and 39% of all health facilities within the target districts, hence health facility specific catchment population has now been used. Work done by BEM and UNICEF with support from OPM, to revise the Better Lives programme logical framework during the review period has strengthened the indicators’ targets to ensure achievement of realistic milestones despite ongoing challenges with the population denominator. The impact weighting was revised upwards to reflect the contribution this output indicator makes towards the achievement of the project outcome. The baseline assessment that is currently being finalised will provide a more coherent approach to calculation of the indicators for the next review period, including for the programme’s evaluation and completion report.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from previous Annual Review

Recommendation	Progress
In consideration of the Somalia context where there is steep competition of resources, it is important to have a joint FCDO-partner communication plan that ensures inclusion of the prime implementing partner (in this case UNICEF) in discussions with the Government from the onset. This should be stipulated and folded into an overarching formal Governance Structure agreed upon by the FMOH and MoHD (separately), UNICEF and FCDO. This should be further jointly considered by FCDO and UNICEF in discussions in the next phases of the Better Lives programme – to be taken forward by the Programme Responsible Owner.	Successful. Following the signing of the (November 2023) MoU on Health Partnership between the UK Government and Federal Government of Somalia[27], work on establishing a comprehensive Governance Structure for the programme was discussed. There is consideration of inefficiencies that would be created by having multiple Governance structures for the various health programmes supported through several donors in Somalia. The FMOH has recommended an approach to incorporate this through the Joint Annual Review and wider national Health Sector Coordination Mechanism.
Ensure regular meetings with downstream partners are instituted and conducted to better gauge the operational challenges considering contextual changes and emerging shocks. These meetings will be organised jointly across partners implementing services in Somalia and Somaliland and will also create opportunities to learn lessons and adapt programming appropriately – to be taken forward by the Better Lives Senior Programme Manager.	Successful and to be continued. During the review period, three meetings with downstream partners were conducted. The schedule set in the previous review period – with regularity of meetings aimed for every two months – will be used as it has proved fruitful. This will be especially important to ensure ongoing discussions with partners and incorporate feedback into the scale-down of interventions in the next review period.
Leveraging support through other funding streams will be critical in strengthening Better Lives and ensuring its impact to vulnerable populations, in the face of declining funding. Critically, the FCDO team should continue to seek alignment with the World Bank, GFATM and Gavi programmes whilst considering changes in these programme’s specific upcoming cycles to strengthen this approach. Specifically, this should include alignment with the World Bank’s Female Health Worker programme; Gavi’s immunisation strategy, and GFATM’s health systems strengthening proposed support whilst ensuring geographical overlaps – this will be taken forward by the Programme’s Responsible Owner.	To be continued. A nuanced approach to engagement with these specific programmes will need to be considered to inform the final year of the Better Lives programme, including transitioning of delivery to other donors. Ongoing conversations with the Somalia focal points of the World Bank, GFATM and Gavi programmes will aid to determine which Better Lives interventions can be specifically taken up by these programmes to support basic needs for the most vulnerable. This will further determine the health systems strengthening opportunities the next generation of UK funding will support in Somalia including Somaliland. health programme in Somalia including Somaliland.
Data quality and use: with support from the programme specific monitoring, learning and evaluation supplier, work with partners to ensure timely data analysis and presentation towards improved programme implementation. Taken forward by the Programme Responsible Owner	Successful and to be continued. Having supported the consolidation and review of the Better Lives programme specific datasets in Somalia including Somaliland (across a number of stakeholders including Gavi, GFATM and WHO), data analysis continued during the review period aligned to the DHIS II. Support to direct partner implementation and related data analysis begun in April 2024 with specific focus on the indicators reported against the programme’s logical framework. As mentioned above, this analysis will be ongoing whilst incorporating findings from TPM, baseline assessment, conflict sensitivity, GEDSI review and programme evaluation studies.
Quality improvement: FCDO to support UNICEF’s initiative for improved uptake of ANC services towards better pregnancy and delivery outcomes (‘first pregnancy strategy’) and continued collaboration with UNFPA on family planning and related supplies – Taken forward by the Programme Responsible Owner	Successful and to be continued. Positive uptake of ANC and family planning services will be strengthened in the next implementation cycle. However, scale down of activities will be built into programme delivery to ensure that lessons learnt from the Better Lives programme are picked up by potential donors that can continue to provide the services.
[27] The MoU on Joint Health Partnership between the UK Government and the FGS set the framework for working, collaboration and communication between UNICEF, the FMOH and FCDO.

Lessons Learnt

1. Leveraging wider funding. Budget reductions with the current programme funding allocation lower than what was proposed in the business case continues to significantly affect the programme’s capacity to fully implement key components including demand creation and behaviour change. This has necessitated drawing on wider funding streams in the health sector (e.g. World Bank, Gavi, Sweden and GFTAM). Despite further proposed funding cuts and an imminent full-scale reduction of the service delivery component for the programme, continued working with these partners will be important to ensure that the most vulnerable women and children receive the care they need.
2. Community health workers. A stronger approach to community health worker support (largely supported by the World Bank’s investments) is crucial to help sustain uptake of healthcare services including immunisation. UNICEF’s programming provides the advantage of leveraging resources across key donors, partners and multilaterals.
3. FGS Leadership. Government’s consistent support for provision of quality health and nutrition services is required to sustain the gains made to the sector through donor funding. It is critical that both the FMOH and MoHD contribute to thinking on what the next phase of support to the Somalia (including Somaliland) health sector will look like, bearing in mind that provision of basic services should be the precinct of the Somalia Government.

Recommendations:

1. Transition of the Better Lives programme. The Better Lives programme has one more year to implement services as outlined in its original business case. This final year will need to ensure a streamlined scale down of interventions in support of a responsible exit from the Somalia (including Somaliland) health sector by 31 March 2026. BEM will have to put in place measures that support this smooth transition whilst working closely with the Government of Somalia including Somaliland – by August 2025, taken forward by the Senior Responsible Owner working with the Programme Responsible Owner.
2. Monitoring, evaluation and learning deliverables. Scale down of activities and transition of the Better Lives programme will need to factor in findings from the various ME&L deliverables that have been incorporated into the programme. Specifically, findings from the baseline assessment and programme evaluation will critically contribute to the programme completion report and will be disseminated to donors, UN agencies, partners, the World Bank, Gavi and GFATM working in partnership with the programme to further inform and guide outlook of the health sector in Somalia including Somaliland. Importantly, BEM will ensure engagement of the FMOH and MOHD to steer positive use of these findings.
3. Ensure that disaggregation of data (by gender and age) is included in the updated programme log frame for the next implementation cycle to aid in monitoring and assessing inclusion of vulnerable and marginalised groups into programme services. Whilst this recommendation was noted for the previous review period, progress has been limited by the need for the FMOH and MoHD to support an indicator review specifically targeting the DHIS II indicators. At facility level, disaggregation of data by gender is factored into the data collection registers. However, this is not replicated within the national DHIS II platform. BEM has and will continue to advocate for this with the respective health authorities of Somalia and Somaliland – taken forward by the Programme Responsible Owner.
Output Title	Health facilities deliver quality essential package of services to children under 5
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 – March 2025)	Milestone (s) for this review: Achieved (April 2024 – March 2025)	Progress	Score
Output Indicator 2.1
Dropout rate Pentavalent 1st dose to Pentavalent 3rd dose	8.2%	8.5%	104%	A+
Output Indicator 2.2
Number of children disaggregated by gender, aged 6-59, months with severe acute malnutrition who receive treatment.	72,689	83,053	114%	A+
Output Indicator 2.3
Number of children (0-59 months) with diarrhoea treated with oral rehydration solution (ORS) and Zinc sulphate, disaggregated by age.	39,549	35,688	90%	B
Output Indicator 2.4
Number of children 0-59 months with Pneumonia treated with Amoxicillin	31,541	28,084	89%	B

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has also performed well and showcases a mix of having surpassed the targets and meeting or almost meeting these across indicators. There has been generally higher utilisation of health services within the Better Lives facilities especially for children under the age of five years accessing immunisation and nutrition interventions. The programme was able to absorb some of the gaps occasioned by the closure of USAID facilities. 27 health facilities have been closed in total between January and early March 2025 in Banadir region, with Action Against Hunger (ACF) reporting increased admissions for cases requiring management for severe acute malnutrition (SAM) as early as January 2025. The partner further indicates that the number of children admitted in the stabilisation centres[28] doubled that seen in a similar period in 2024.
[28] Stabilisation Centers are specific units within hospitals designated to admit and provide management for patients with severe acute malnutrition and related complications (e.g., communicable diseases). Care is received in an isolated set-up as these patients have low immunity. Management includes treatment of diseases and provision of specific nutrient-rich therapeutic foods.

As mentioned in the programme overview section above (context), Gedo region was adversely affected by ongoing conflict in Luuq and Dollow districts. The impact of the conflict was serious enough to warrant suspension of Better Lives health and nutrition activities, including community outreach, supported through Trocaire, between February and March 2025. This further resulted in an increased influx of Internally Displaced Persons (IDPs) from Gedo to Mogadishu. The Somalia Camp Coordination and Camp Management (CCCM) Cluster reported that 19,000 IDPs migrated to Mogadishu from January 1, 2025, as a result of the ongoing inter-clan conflict.

To manage the increased cases and ensure better provision of services in response to the mounting needs, Action Against Hunger, collaborated with the FGS Banadir Regional Administration (BRA) and the World Bank team to leverage their support by way of increasing the FHWs allocated to the region. This has strengthened community outreach interventions under Better Lives. Moreover, the initiative has facilitated improved referral linkages in Deynille and Hodan districts (supported through Better Lives) targeting the increased cases of deliveries (pregnant women), SAM and immunisation.

The inter-clan conflict and closure of previously USAID funded facilities in Galmudug has, likewise, resulted in an increase of patients accessing services in Better Lives facilities. Both Mercy USA (implementing in Galmudug) and ACF have received requests from community members/ leaders to support the ensuing gaps especially as regards to nutrition.

Output Indicator 2.1: Dropout rate of Pentavalent 1st dose to Pentavalent 3rd dose. The milestone for this indicator remained within the target of less than 10% as recommended by WHO. Increased number of children accessing Better Lives facilities for routine immunisation due to closure of USAID funded programming contributed to this. Additionally, the Gavi funded BCU that specifically targeted Better Lives supported regions also served to ensure more children reached for full immunisation coverage.

Output Indicator 2.2: Through the Better Lives programme direct support, UNICEF was able to enhance early screening and detection of acute malnutrition which resulted in the increased management of children aged between 6-59 months with severe acute malnutrition, hence surpassing the target (114%). Specifically, UNICEF increased support to running costs including incentives (salaries) to nurses and CHWs towards provision of integrated health and nutrition services at the healthcare facilities. At the beginning of the review period, UNICEF and BEM agreed to repurpose funds previously allocated to procure nutrition supplies to instead cover these activities. The Somalia UNICEF nutrition sector supports nation-wide pooled procurement and prepositioning of nutrition supplies. UNICEF had earlier procured enough nutrition supplies to cover all facilities including those for Better Lives at the beginning of the review period enabling their timely provision and negating the need for further funding towards their procurement.

Increased uptake of nutrition interventions was further realised as a result of the partnership between BEM and the King Salman Humanitarian Aid and Relief Center (KSrelief) to support a multisectoral response to severe acute malnutrition in Somalia and Somaliland. This partnership was launched on December 1, 2023, and followed the successful culmination of discussions that came on the back of the response to the drought in 2022. Implementation of activities associated with this project were extended to April 2025, to accommodate a slower start to the KSrelief specific activities. Activities supported included procurement of nutrition therapeutic foods for distribution to stabilisation centers and outpatient therapeutic programmes (OTPs)[29]; provision of messaging towards promoting increased access to integrated health, nutrition, and WASH interventions; and provision of a minimum WASH package of interventions (including distribution of hygiene kits to caregivers of children with SAM). Implemented in the Better Lives areas, the project was intended to reach an additional 53,047 children (24,034 boys and 29,040 girls) aged 6-59 months with management of severe SAM. Below are the specific achievements of the programme between April 2024 and March 2025:
[29] Outpatient therapeutic programme (OTP) is a strategy for treating acute malnutrition in the community, which involves the community involvement, providing children with good appetites and management of uncomplicated severe acute malnutrition among children of 6–59 months old by providing them ready-to-use therapeutic food at home along with standard medical care.

- 52,420 cartons of ready to use therapeutic food (RUTF) procured and distributed to 93 supported healthcare facilities that specifically provide nutrition interventions.
- 219 boxes of water purification tablets, 6,250 boxes of disinfectant, 4,800 boxes of bar soap and 24,000 twenty-litre jerricans procured and distributed to communities in the Better Lives catchment areas to support water storage.
- Training of 47 front-line healthcare workers from Awdal, Togdheer, Gedo and Banadir regions on infection prevention and control.
- 1,205,448 children screened for malnutrition, and
- 384,750 caregivers counselled on maternal infant and young child nutrition (MIYCN (achieving 126% of the target).
Output indicators 2.3 and 2.4: the number of children treated for diarrhoea and pneumonia, respectively, during the review period surpassed the set targets. Performance of these indicators is dependent on the consistent availability of pharmaceutical and medical supplies (zinc sulphate and oral rehydration solution for management of diarrhoea, and amoxicillin antibiotic for management of pneumonia). No stock outs of these key drugs were reported during the period. IMCI training conducted, and that targeted frontline healthcare workers and CHWs providing house-to-house care ensured that staff were able to appropriately identify, refer (in the case of the CHWs) and treat common childhood illnesses.

The increase of children accessing services for management of diarrhoea and pneumonia is also because of an increase in the burden of these diseases and others including measles and malaria in Better Lives regions. As of 17 April 2025, there are four active outbreaks in the country – Acute watery diarrhoea/ cholera, influenza, Whooping cough and measles. The Health Cluster has significantly strengthened its Integrated Disease Surveillance and Response (IDSR) across regions in Somalia and Somaliland, which has heightened reporting of cases in Better Lives areas. This has seen an increase in the number of healthcare facilities submitting their weekly surveillance reports into the DHIS II. Overall, 391 (93%) out of 419 health facilities have reported timely. This further allows for a more comprehensive analysis of the communicable diseases that are affecting specific facilities including those supported through Better Lives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Together with output indicator 1, this output comprises the core of service delivery, specifically targeting children below the age of five years. The indicators specific to this output remained the same as those reported in the 2023/2024 Annual Review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous Annual Review, and recommendations for the year ahead have been factored into and are similar to those of output 1 above.

Lessons Learned:

1. Collaboration between UNICEF, FCDO and KSrelief has strengthened specific strategic and programmatic actions for addressing malnutrition. This includes the multi-sectoral approach to programming where, for example, strengthened WASH messaging at the facility level for the most vulnerable families with SAM children has proved crucial in addressing the root causes of malnutrition.
2. In support of timely procurement and distribution of supplies to address needs, it is important to factor in adequate resources for logistics management. This should include a comprehensive allocation of operational costs through the downstream partners’ budgets to facilitate re-distribution of supplies between facilities/ and where they are most needed.
3. To ensure optimal and sustainable impact on management of malnutrition, joint interventions must be programmed at scale. This should also factor in a degree of autonomy that allows partners to manage funds, timelines for interventions and reporting – bringing together various donor requirements to ensure a streamlined approach to delivery.

Output Title	Health facilities deliver quality curative services
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 to March 2025)	Milestone(s) for this review: Achieved (April 2024 to March 2025)	Progress	Score
Output Indicator 3.1:
Number of people using OPD services at Better Lives supported health facilities (disaggregated by age and gender)	518,277	498,072	96%	A
Output Indicator 3.2:
Proportion of health facilities with at least 80% availability of selected tracer medicines and medical supplies	80%	74%	93%	A

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Indicator 3.1: As of end of February 2025, the number of people accessing outpatient department (OPD) services at the Better Lives supported health facilities increased from 262,887 reported in the previous quarter (October to December 2023) to 498,072 and recording a cumulative increase of 93%. This increased access to OPD services is consistent with the health facility utilisation rate reported under outcome indicator 6. As mentioned in various sections above, operationalisation of all Better Lives health facilities in the review period and resultant availability of OPD related services; active leveraging of immunisation, demand creation and behaviour change activities through established partnerships; and increased influx of patients to the Better Lives facilities as a result of the closure of previous USAID supported facilities has directly contributed to the increased utilisation.

Outpatient department services is the only indicator that is disaggregated by both age and gender within the DHIS II. Women and girls represent 58 per cent of the new OPD consultations and are the primary beneficiaries of the program. Girls and women aged five years or older accounted for the highest number of new OPD consultations, totalling 186,846 in the reporting period. This was followed by girls aged five years and lower (109,777). 41 per cent of the new OPD visits were children under five years.

The implementation period coincided with the start of the of the World Bank funded and Federal Ministry of Health and Ministry of Labour and Social Affairs (MoLSA) – led Baxnaano programme. In collaboration with the two ministries, the programme has facilitated access to and utilisation of Better Lives services specifically in Banadir region. Services provided include raising awareness of the availability of health and nutrition services and promoting behaviour change among caretakers to strengthen uptake of maternal, newborn and child health services. This has also promoted uptake of the Better Lives OPD services.

Regional variations, however, exist with regards to uptake of services owing to various reasons. The inter-clan conflict in Gedo region has disrupted service delivery, particularly in Luuq district as mentioned above. The withdrawal of World Food Programme (WFP) food distribution has also negatively impacted health seeking behaviour in Togdheer where declines in facility (OPD) visits has been noted.

Output Indicator 3.2: By the end of March 2025, 74% of the targeted 80% of Better Lives facilities had reported comprehensive availability of tracer[30] medicines. UNICEF developed Standard Operating Procedures (SOPs) for supply chain management in collaboration with downstream partners during the review period. The SOPs have addressed the need for timely forecasting and quantification of supplies and use of facility consumption data to calculate the pharmaceutical, medical, and nutrition supplies needs for each health facility. This has facilitated use of the pull rather than the push mechanism for procurement of commodities thereby ensuring their consistent supply.
[30] Tracer drugs are specific drugs/medicines required to manage the common ailments for a specific context, targeting the most vulnerable populations. They represent and are part of the essential medicines recommended by national policy of a particular country and satisfy the priority healthcare needs of the population. Managing tracer drugs through logistics management information systems is a strategy to enhance their smooth flow for continuous provision of quality health service.

Noting that the aim is to ensure that none of the targeted facilities have shortage of critical supplies, UNICEF has outlined the challenges associated with this and has begun working with partners to address. These challenges include delayed requests from facility staff and partners to supply new stocks, long logistics lead times associated with procurement from UNICEF’s supply division in Copenhagen, and inaccuracy of the forecasting which does not also take into consideration the lead times. Whilst the SOPs will serve to standardise processes for the timely distribution of health and nutrition supplies, with a focus on addressing the systemic supply management issues, UNICEF has planned for training of partners and pharmacy staff at the facilities in the next phase of implementation which will further improve pharmaceutical supply chain management by enhancing staff knowledge and skills.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Work is ongoing to ensure better understanding of the catchment population served by each of the Better Lives facilities. As mentioned, the baseline assessment currently underway will help to define this and further allow for accurate calculation of health facility utilisation rate. With the Ministry of Health, the BEM team is also working to address the issue of data disaggregation by gender and age at the DHIS II level.

Output Indicator 3.2 on proportion of health facilities with at least 80% availability of selected tracer medicines and medical supplies was introduced in this review period and following completion of the revision of the Better Lives programme Theory of Change in March 2024. This addition was necessary to ensure tracking of the availability of essential medicines, the lack of which would result in diminished access by beneficiaries and overall decline in quality of care.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Output Indicator 3 has been included in the Better Lives programme log frame for the first time during this review period. Lessons learnt and recommendations will be tracked for the upcoming review period and reported at the end of the development phase in 2026.

Output Title	Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices
Output number:		4	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 to March 2025)	Milestone(s) for this review: Achieved (April to March 2025)	Progress	Score
Output Indicator 4.1
Number of primary caregivers of children aged 0-23 months who received IYCF counselling	306,974	310,533	101%	A
Output Indicator 4.2
Proportion of women interviewed in ANC who know at least three danger signs of newborn complications	4,825	5,416	112%	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Indicator 4.1: This output was defined to focus on demand creation and behaviour change, targeting care givers of children and women directly receiving reproductive health services in the Better Lives facilities. The indicator is aimed at improving child feeding practices as aligned to global WHO IYCF guidelines and especially in the context of diminished funding that minimises reach to beneficiaries with (house-to-house) demand creation and behaviour change activities. The primary care givers of children aged 0-23 months were targeted at both facility (during ANC, PNC, and management of various ailments in the outpatient department) and community level, with majority of those reached being at the facilities. Nutrition services serve as major pull factors to clients which has contributed to the achievement of this indicator. Owing to this, more women (as the main care givers) were reached than anticipated. All 310,533 caretakers reached were also provided with information on early stimulation of the child especially as regards breastfeeding practices with the aim of ensuring that the knowledge shared can contribute to child health and development.

Lack of accurate population (denominator) data also affects accuracy in determining targets against indicators. The upcoming baseline survey will seek to correct this by assessing the catchment population for supported facilities.

Output Indicator 4.2 data on the proportion of women interviewed in ANC who know at least three danger signs of newborn complications exceeded the target set. Despite the decline in funding and resultant cut to the demand creation and behaviour change component, leveraging of the outreach services offered through Sweden, Gavi, GFATM and World Bank funded programmes has strengthened uptake of services whilst improving knowledge outcomes amongst the targeted population.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was finalised as part of the start of the development phase of the Better Lives programme; no changes are planned as a result of the review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons Learnt:
1. Partner engagement on data collection. The need to adequately sensitise partners on data collection and reporting of various indicators, including those newly adopted for programme implementation should not be underestimated. Ensuring that all partners are on board and are aware of data collection and reporting requirements is critical to provide ownership of programme delivery.
2. Community health workers. A stronger approach to community health worker support (largely supported by the World Bank’s investments) is crucial to help sustain uptake of healthcare services including immunisation. UNICEF’s programming provides the advantage of leveraging resources across key donors, partners and multilaterals.
Recommendations:
Work with UNICEF to strengthen the timely adoption of updated log frame indicators by partners and improve partner data collection systems. Accountability of this will be ensured through the quarterly review meetings and meetings with downstream partners conducted every two months. This approach has been set and agreed with BEM - from April 2024, to be taken forward by the Programme Officer with support from the Programme Responsible Owner.

Output Title	Enhanced reporting and supervision of service delivery
Output number:		5	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 – March 2025)	Milestone(s) for this review: Achieved (April 2024 – March 2025)	Progress	Score
Output Indicator 51.
Proportion of facilities submitting timely and complete HMIS reports in the DHIS II (RMNCH Form completeness)	95%	96%	96%	A
Output Indicator 5.2
Number of joint supportive supervision visits conducted in the supported facilities, between the MoH, UNICEF and implementing partners.	4	6	>100%	A++
Output Indicator 5.3
% of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits	75%	75%	100%	A

Briefly describe the output’s activities and provide supporting narrative for the score.

Both UNICEF and downstream partners performed well towards achievement of this output, fully achieving the milestone targets for the reporting period. The DHIS II reporting performance was also surpassed with regards to timeliness and completeness of data reporting across all targeted facilities.

Output Indicator 5.1: 96% of Better Lives health facilities submitted the Reproductive, Maternal, Newborn, and Child Health (RMNCH) summary forms for each facility. The program supports 15 District Health Management Information System (HMIS) Officers across all 15 districts where the programme is implemented. The Federal Government and State level HMIS teams, funded by GFATM, collaborate with the district teams to ensure timely and complete submissions. The strong performance in DHIS2 reporting is also linked to field monitoring visits by partners (Action Against Hunger, Save the Children, Mercy USA and Trocaire) and the zonal UNICEF teams that include focal points managing the Gavi and GFATM nutrition and data quality teams. Review meetings with implementing partners have also contributed to improved performance. However, gaps remain that require improvements with support from district HMIS teams and implementing partners. For example, some Better Lives health facilities did not submit any reporting related to contraceptive use into the DHIS II.

Output Indicator 5.2: During the review period, 6 supportive supervision visits were conducted in the supported facilities, by the MoH, UNICEF and downstream implementing partners. These included 2 visits in Togdheer and Awdal and 4 visits in Galmudug, Jubaland and Banadir regions.

Several key observations and action points were identified. At Save the Children warehouse in Boroma district (Awdal region), stock cards[31] were unavailable, and the storage rooms did not meet the required standards for medical supplies. Further visits to specific health centres (3) in Awdal region revealed discrepancies between the supplies received and the dispatch waybill issued by Save the Children. Concerns were raised about the logistics process for delivery of supplies, and the lack of logos on printed documentation tools that accompany the supplies. Service utilization issues included an inadequate number of midwives within facilities (health centres and hospitals), gaps in World Food Programme (WFP) feeding support owing to closure of facilities supported through USAID funding, lack of newborn resuscitation units, inadequate referral pathways for patients to access services at the hospitals, and gaps in outpatient therapeutic programme (OTP) services. Additionally, staff reported gaps in training, particularly in supply management and other basic areas.
[31] Stock cards are inventory management tools used in warehouses and pharmacies for tracking stock (pharmaceutical, medical and nutrition supplies) movement and keeping the optimal levels of supplies.

Within the Mercy USA supported facilities in the Togdheer region, all supervised health centres displayed catchment area population estimates, but the data lacked disaggregation by critical demographics (age and gender of beneficiaries served), which would hinder effective resource allocation. Recommendations included rectifying the disaggregated data and developing implementing dashboards for better programme visibility. Human resource challenges were noted, particularly in Odweine district, where there were no assigned Health Education personnel and CHWs. Recommendations included mapping CHWs supported by other partners with a view to leverage this resource to contribute to Better Lives supported activities.

Further issues identified included distribution of unnecessary medical supplies within some facilities in Togdheer regions and the absence of commodities for hygiene management. Recommendations included maintaining robust stock management systems and ensuring proper storage of medical supplies. In total, 40 action points were identified, with all immediate ones resolved and 11 partially addressed, including capacity building of staff, establishment of an electronic Logistics Management Information System (e-LMIS), and establishment of newborn corners.

Output Indicator 5.3: all Better Lives targeted facilities (100%) that were monitored were noted to have implemented recommendations from previous Joint Supportive Supervision (JSS) visits. UNICEF has strengthened the program monitoring as part of its plan to address aid diversion in Somalia. A report is provided every month as an update to donors on potential incidents of aid diversion, covering issues related to both medical and nutrition supplies. BEM, in turn, ensures ongoing discussions with UNICEF to ascertain if facilities noted as posing high risk for aid diversion are properly monitored, with further measures applied through BEM-led TPM exercises. To date, no Better Lives procured and distributed supplies have been implicated in aid diversion either in Somalia or Somaliland.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output this year. One indicator related to climate change and health that had been included within output 5 in the previous review period has now been moved to output 6 to facilitate more comprehensive reporting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
BEM led monitoring: Work with partners and the ME&L supplier to incorporate better monitoring and addressing of social exclusion issues in service delivery work in the next review period – ongoing, to be taken forward by the Programme Responsible Owner.	Successful. This has been achieved through the third-party monitoring activities. Further detail on cross cutting issues including on Gender Equality Disability and Social Inclusion is provided after the output section below. Progress on this recommendation remains a priority for the next review period.

Lessons Learnt:

1. Communications. Communication and collaboration between partners and the Ministries of Health enhances Programme delivery and leverages the comparative advantage of each partner in support of improved delivery.
2. Data quality: Ongoing issues with quality of data in the national DHIS II inhibit the use of data for effectively tracking progress and improving performance. Continued engagement with partners supporting the DHIS II system, including GFATM, is important and provides opportunities to help strengthen the system.
3. Demand creation. Community outreach and other demand creation activities are fundamental to increasing health facility utilization and it is important to balance this with supply side activities – and will continually be a key element for monitoring during joint supportive supervision visits.

Output Title	Support to improving climate resilience of health services delivered
Output number:		6	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review: Planned (April 2024 – March 2025)	Milestone(s) for this review: Achieved (April 2024 – March 2025)	Progress	Score
Output Indicator 6.1
Number of health care facilities assessed and provided with climate resilient energy support	43	43	100%	A

Briefly describe the output’s activities and provide supporting narrative for the score.

With support from the UK FCDO Ending Preventable Deaths Global Centre for Expertise, a Climate Vulnerability and Adaptation (V&A) assessment of national health policy, sub-national capability, and health facility level gaps for strengthening climate resilience was undertaken during the review period. This assessment helped determine the baseline on the status of climate resilient health systems in the health facilities to inform the level of intervention required. This activity used the World Health Organisation (WHO) Framework for measuring climate resilient health systems. 93 health facilities were assessed across Somalia and Somaliland. The assessment garnered information on:

- Mapping national policy frameworks on climate and health and how this is being implemented.
- How best to work with the Government to build the capacity of regional and district MoH staff to strengthen their ownership on sustainable approaches to climate resilience.
- Skills building, education, and training of frontline health workers.
- Mapping linkages to existing facility, district and regional level disease surveillance and early warning tools for better forecasting of shocks.
- Assessment of potential small-scale capital investments at facility-level to ensure resilient water sources and mitigate risks occasioned by medical waste management and strengthening cold chain systems for storage of medical supplies and pharmaceuticals (including vaccines), and support to renewable energy.
The assessment revealed that the Better Lives facilities were facing significant challenges in infection, prevention and control (IPC) with resultant high infection rates for beneficiaries as well as staff accessing the facilities, lack of waste management and water provision facilities. These issues were because of inadequate training of staff, and limited resources – a situation that had not allowed rehabilitation of the infrastructure within the facilities even during implementation of the Somalia Health and Nutrition (SHINE) programme. SHINE had been the UK Government flagship health and nutrition programme and was the predecessor to Better Lives. The above issues were also noted at the OPM-led TPM exercise conducted between December 2023 and April 2024.

In 2023, Somalia became a member of the Alliance for Transformative Action on Climate and Health (ATACH). This has given the FMOH the opportunity to take forward commitments to building climate-resilient and low carbon sustainable health systems with this further cemented during the COP28 conference. Following this, Somalia has developed a National Determined Contributions (NDC) implementation plan with the objective of mainly addressing Somali’s vulnerability to climate, and risks to achieving long-term development goals. However, the FMOH acknowledges that the process towards realization of the commitments made will require extensive advocacy especially for financial resources which are a significant constraint. Activities funded through FCDO have also addressed some leadership and governance issues to enable the health authorities in Somalia and Somaliland to attain the knowledge necessary to oversee and support climate and health activities of their partners.

During the review period, FCDO committed £5.2million in support of climate resilience activities across 43 (out of the 93) specific targeted facilities. By 31 March 2025, UNICEF had issued contracts to realise the full commitment of these funds and had begun implementation of related activities. The main activities taken forward, among others, include:

1. Setting up of handwashing facilities at points of care and toilets/latrines: this includes provision of soap; and designing, development and distribution of information education and communication (IEC) materials at these points.
2. Ensuring that health facilities have access to safe and sufficient drinking water through installation of elevated water tanks at the health facilities; procurement and installation of solar powered motorized pumps; installation of rainwater harvesting systems; and deep borehole drilling in areas affected by water scarcity with the intent that the boreholes serve both the facilities and catchment populations served.
3. Construction of flood-proofed sanitary latrines at the health facilities, with improved access for persons with disabilities. The latrines would also have provisions for menstrual hygiene management, and showers/ bathing facilities for pregnant women and women that have delivered.
4. Construction of healthcare waste management at all targeted health centers and hospitals: including construction of incinerators, and placenta pits.
5. Procurement of essential maternal and newborn equipment (including delivery beds, and incubators) and placement of these within hospitals and health centers to improve patient care.
6. All the above activities have been complemented by training healthcare workers to ensure they have the requisite knowledge and skills to mitigate environmental risks that may arise from their own operations. Learning modules imparted included: management of health care waste, safety in management of chemicals, infection prevention and control, among others.
7. Leadership and Governance: support the review of governance structures, specific responsibilities, and accountability mechanisms for climate change and health within the MoH at Federal and Regional levels.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

As indicated in the section above, this indicator was moved from the output related to demand creation and behaviour change activities as it was realised during the revision of the Better Lives log frame that it would be necessary to have a bespoke indicator that reflected the enormity of the CDEL/ climate change work taken up by the Better Lives programme. This would also reflect and speak to the specific outcome indicator that was also defined specifically to capture these interventions. However, the Key Performance Indicator related to this indicator, and as defined in the International Climate Finance (ICF) methodology note has not changed from the previous period. The climate and health vulnerability and adaptation assessment produced during this review period as well as the related workplan will be key documents for informing Better Lives activities and milestones for this output over the next review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous annual review
Recommendation	Progress
During the inception phase of the substantive Better Lives programme, develop an action plan outlining key parameters for robust identification, implementation, and analysis of effective use of proposed CDEL activities – to be taken forward by FCDO Programme Responsible Owner, the FCDO Somalia ICF/ CDEL programme leads in collaboration with UNICEF and downstream partners.	Completed. In collaboration with the BEM Climate Adviser, a climate and health vulnerability assessment has been commissioned to help UNICEF identify the interventions to support on climate resilience from 1 April 2024. Progress on this recommendation remains a priority for the next review period.

Lessons Learnt:

Implementation of climate resilient activities requires a consistent and informed approach to achieve impact. Partners’ (including UNICEF) understanding of the required interventions under the overall ICF and associated CDEL funding, the methodology and related indicators will need constant monitoring and review and further strengthening in the next review phase.

Involvement of the Government staff/health authorities from the onset is important to ensure sustainability of the interventions. There has been willingness from local authorities to learn about ICF driven activities. However, this has been more consistent and driven within the MoHD as compared to the FMOH. There is need to ensure further engagement of the FMOH and Federal Member states for successful implementation of related interventions.

Strategic and Programmatic wider achievement.

Gender Equality Disability and Social Inclusion (GEDSI): during the review period, HHELMS supported a desk review study of the programme with the objective of providing contextually relevant and timely insights into GEDSI evidence to inform and support the programme to build an inclusive and sustainable healthcare system that can address systemic barriers to inclusion, champions equality of access and works to empower communities to demand quality services. The detailed findings of the GEDSI desk review will be provided as an annex to this report and will inform a lesson learning approach with the health authorities. Healthy Women Children and Newborns (formerly ending preventable deaths – EPD) agenda: In 2021, the UK Government launched an approach paper setting out how FCDO will take an integrated approach to work on ending preventable deaths. This commitment would engender support across four main pillars in a phased approach in Somalia including Somaliland – which is a flagship country.
Several streams of work aligned to the agenda have begun, specifically in Somaliland, including development of a Somaliland Health Sector Coordination Framework, mapping of donors in the health and nutrition sector, capacity building on MEL and health management information systems (HMIS), and policy work on legislative reforms on consent related to caesarean sections.

The technical assistance work undertaken between July 2024 and March 2025 has laid a solid foundation for reducing preventable deaths among women, children, and newborns in Somaliland. Through strengthening governance, enhancing technical capacity, and integrating nutrition and climate resilience into health systems, the health sector has become more responsive and better equipped to address the root causes of maternal and child mortality. The UK has positioned itself as a trusted partner in this area. There is an opportunity to extend and expand this work, as the UK moves to a different partnership role in the health sector.
Conflict Sensitivity Analysis: the main outcome of the analysis was that the Better Lives programme can serve as a bridge to create harmony among stakeholders. As the programme demonstrates clear benefits, such as improved health and nutrition for all, it cultivates goodwill and reduces tensions. It offers a shared goal that transcends individual clan interests and fosters collaboration. Based on the data collected and analysed, several recommendations have been identified to enhance the design and implementation of the Better Lives programme. These aim to ensure that the programme does not inadvertently worsen tensions or conflicts, particularly in resource-scarce or politically sensitive areas. Additionally, the programme should be conflict- and culturally sensitive, gender-responsive, and climate-conscious, with a strong emphasis on accessibility, availability, affordability, and acceptability to better serve communities in need. The main findings from the report are provided as Annex 1 to this report.

The findings from the Conflict Sensitivity Analysis will be communicated to the FMOH as part of the efforts to ensure that they contribute to thinking on a responsible exit of the programme. Further discussions with the World Bank, GFATM, GAVI and wider donors will also be undertaken to support a smooth transition to the World Bank led approach. Communication with partners, including UNICEF, has been undertaken to further facilitate.
## D: VALUE FOR MONEY (1 page)

Between November 2024 and February 2025, the HHELMS team conducted the first value for money (VfM) assessment of the Better Lives programme. The assessment followed the outlined framework as documented within the programme’s business care, whilst taking into consideration contextual changes, and as agreed with BEM. The assessment covered the development phase of the Better Lives programme for the period 1 October 2023 to 15 March 2025. However, the findings detailed below are specific to this Annual Review and coincide with the April 2024 to March 2025 respective dates.

Key cost drivers and performance

The key costs for the Better Lives Programme are pharmaceutical and medical supplies, nutrition commodities, staff incentives, and security costs. The main factors affecting these costs include the, fluctuating global market prices, and political and conflict dynamics within Somalia and Somaliland. These cost drivers have not changed from the last review period.

VfM performance compared to the original VfM proposition in the business case

The table below provides a summary of the overall VfM assessment of the Better Lives Programme. Details against each of the 5E’s is provided further below.

Due to data limitations, some adjustments to the assessment against the 5E’s were made. For example, the economy section did not compare staff, consultant and recurrent costs as the data was not available in disaggregated categories. Instead, a trend analysis of key economic components over time was done. The assessment adopted a rubric system to highlight the rating for each metric[32].
[32] Please note for the overall rubrics and judgement, red indicates poor, yellow indicates adequate, light green indicates good and dark green indicates excellent performance. Table 1 gives a summary of the overall VfM for the Better Lives programme.
Overall judgement on programme VfM
### Table 2: Summary of the Better Lives programme VfM
“E”	Judgement	Summary
Economy	Adequate	As a leading global partner, UNICEF is able to demonstrate economies of scale that are used on the Better Lives programme. The programme has experienced challenges with supply chain management; and while it has taken steps to improve this, it is too soon to assess its improvements.
Efficiency	Good	Better Lives approach to coordination with partners and government, relationship building, and adaptation of the programme has ensured an established continuous improvement strategy that stands to strengthen the programme through its implementation. The programme is maximising the opportunities available to it by building partnerships and synergies with other programmes providing both service delivery and health system strengthening interventions. / The programme has met some standards across both adequate, good, and excellent levels but as it has not met all the standards, the rating has been judged as ‘good’ overall.
Effectiveness	Good	Better Lives aims to enhance programme effectiveness (and hence quality) through improved utilisation of service, strengthened health system capacity, pharmaceutical and medical supplies availability and supply chain system efficiency, healthcare worker training, and quality and timely data collection. The indicators which are tracked via the log frame result in the programme being judged as 'good.' Strengthening of timely reporting of data against the DHIS II (national data platform) is required on some indicators and including on data disaggregation. It is for this reason that the rating is good and not excellent.
Equity	Adequate	UNICEF Somalia focuses on the most vulnerable through a need-based approach. Better Lives identifies regions with higher concentrations of vulnerable groups. Data gaps complicate measuring reach towards the more vulnerable groups. Some standards are met, but overall, this metric is judged as 'adequate.'

Economy
#### The data available to assess the economy of the Better Lives Programme was limited. Whilst there was sufficient data on activities in the biannual reports provided by UNICEF and partners, this did not meet the standards to inform a full analysis. To enable an analysis with the data available, the assessment used the sub-criterion: Procurement practices and supply chain management assessment to identify opportunities to realise economies of scale and operationalise cost savings, for the basis of the judgement on economy. In line with the available evidence, the programme was noted to have processes in place to manage the supply chain and was determined as able to identify savings through UNICEF’s global procurement. However, there are improvements that need to be made to the supply chain management to improve efficiencies and reduce risks of stockouts and delays. It is acknowledged that the programme has already taken steps to address current challenges (i.e. through its bottleneck analysis with downstream partners and development of the SOPs). However, more time is required to assess whether these measures have improved supply chain management and procurement practices of the programme.
#### Key cost components for the development phase of the Better Lives programme:
The last quarter of 2023 had the lowest spend for the development phase of the Better Lives programme. This period also focused on mobilisation activities and as such key costs related to staff and other personnel time and contractual services. The programme had not yet started procurement of supplies and commodities, and the analysis found nil expenditure on these cost drivers between October-December 2023. In 2024, key cost components have changed as the programme’s focus has shifted to procurement of supplies and setting up contracts for downstream partners.
From January to March 2024, the percentage of expenditure on transfers and grants to counterparts (downstream partners) increased to 74%, while it was about 39% between April-September 2024 and 59% from October to December 2024. Supplies and commodities formed the highest share of expenditure between April - September 2024 at 39% and increased further to 48% in January - March 2025. Costs relating to staff and other personnel were the largest share of expenditure for October-December 2023 but reduced to 12-14% in the subsequent quarters. General operating and other direct costs have also remained the same. The distribution of expenditure in 2024/2025 is broadly representative of how the budget should be utilised on a large service delivery programme, particularly with the key cost drivers being grants and supply costs.
Some key challenges with procurement and supply chain management have been noted as below:
- UNICEF’s global procurement process through its supply chain division in Copenhagen have resulted in longer lead times and imposed higher delivery costs. A global increase in emergencies has put pressure on supply chains, leading to delays in the delivery of essential commodities, as well as health and nutrition supplies and this is envisioned to worsen in the context of decreasing international aid overall. While UNICEF maintains a significant level of procurement capacity, its system is dependent on the availability of containers and boats crossing the Pacific to deliver goods. At the start of the programme UNICEF was able to overcome this challenge by providing funding support earlier (frontloading funding through alternative sources), to ensure that approximately 40% of the supplies at the start of the programme were either already procured, in the final preparation stage, or on the way by sea to Somalia. Reduced funding sources to support this would put future deliveries at risk, resulting in significant stock outs of supplies with negative impact on quality of care.
- Ongoing security challenges specifically in Jubaland has caused difficulty in travelling by road between districts. As a result, partners are relying on airlifting for critical supplies, which also puts facilities at risk of delays or stockouts and further adding to the costs.
- Downstream partners lack experience in supply chain management, particularly quantification processes or forecasting, which impacts the quality of data used in procurement requests with regards to accuracy of forecasting and quantification of supplies required.
- There exist gaps in communication between health centres, meaning if one of the facilities is overstocked with a particular pharmaceutical or medical supply, there is no established system to communicate and transfer these to another facility that is in desperate need.
To address supply chain issues, UNICEF has since contracted a supply chain specialist to support the streamlining of the processes used by the programme. They also held a two-day workshop in November 2024, attended by their downstream partners to conduct a bottleneck analysis of the current procedures. Following the workshop, UNICEF produced a standard operating procedure (SOP) which aims to resolve the procedural issues but also transition the programme from a push system to a pull system. The SOPs have since been rolled out to partners. However, it is too early to assess the impact of the changes.
Despite the above, there have been savings realised due to good procurement practices through UNICEF:
UNICEF’s Supply Division Hub consolidates all global requirements and has established economies of scale in its global operations, allowing UNICEF to procure essential medicines and equipment at competitive prices. An example of this is that UNICEF saves $2.85 per 1,000 250mg Amoxicillin tablets, which is a 17% saving against the international median price.
UNICEF also conducted an analysis of annual cost in one of their health and nutrition facilities (BEmONC centre) and found a total reduction of $13,662 in annual costs after integration, compared with overall costs of $55,752 before integration. This equates to a 25% reduction. Costs considered include HR costs and utilities and cleaning products.
In addition to savings made through UNICEF’s global procurement practices, by design, the programme leverages funds from its organisational capabilities. For example, the programme uses the Last Mile Monitoring System – developed by UNICEF – to monitor stock movements. This information is visible via a dashboard and allows UNICEF and other partners to monitor stock movements in real time, and access up-to-date information on the location, condition, and status of the supplies. The system was developed as part of another programme (German funded) but is also used on the Better Lives programme at no additional cost.
Efficiency
The Better Lives Programme ensures resource allocation aligns with health system needs in Somalia. Through a national policy review and ongoing stakeholder consultations—including with GAVI, the World Bank, and the Somali Government—the programme identifies gaps and complements existing initiatives. Coordination with donors and UNICEF's experience in Somalia enables synergy with other programmes. Additionally, Better Lives conducted a climate vulnerability assessment to enhance resilience in healthcare facilities. As a result, services now integrate Water, Sanitation, and Hygiene (WASH), expanding access to clean energy and climate-adaptive healthcare.

However, the programme faces challenges due to earlier separation of health and nutrition services, affecting delivery efficiency. Facility selection delays have also led to resource constraints, limiting service quality.

Better Lives has established mechanisms to improve service quality. Quarterly review meetings involve government and donors and employ a modality of tracking progress and addressing key challenges. TPM assessments verify implementation, with upcoming evaluations expected to assess new efficiency measures. Climate adaptation efforts include a GBP 8 million investment for climate-resilient healthcare facilities, expanding renewable energy solutions. Patient satisfaction surveys show high approval rates in some regions but highlight concerns regarding wait times and medicine shortages – specifically of specialised cases such as non-communicable chronic illnesses.

The Better Lives Programme maintains strong relationships with the Somali and Somaliland health ministries, ensuring government engagement in programme activities. However, extensive government involvement— with processes similar to the World Bank engagement—has led to delays in TPM assessments and climate vulnerability analysis. UNICEF and FCDO acknowledge the need to set boundaries to prevent ongoing disruptions. Beyond governmental ties, the programme actively participates in coordination mechanisms such as the Somali Health Partner Group and Key Financiers Group, fostering collaboration with major donors and advocating for Better Lives' impact. Partnerships with World Bank, Global Fund, and UNFPA help mitigate resource shortages, with ongoing efforts to secure additional funding for health and nutrition services.

Better Lives prioritizes continuous learning and adaptation, led by HHELMS through quarterly review meetings and annual learning cycles. Action trackers document lessons and inform programme improvements. An annual learning event brings together key stakeholders, supporting coordinated health sector development. Challenges remain in securing timely support from partners, highlighting the need for structured planning. The programme’s ability to leverage funds during the 2020 FCDO budget cuts illustrates its adaptability. UNICEF has also refined procurement processes based on past learnings, transitioning (marginally) from a push system to a pull system with further efforts planned for. Additionally, continual contextual analysis has driven Better Lives to integrate nutrition, WASH, and climate initiatives. Capacity-building efforts for frontline health workers and leveraging community health workers from UNICEF’s nutrition programme further enhance its adaptability and efficiency.

Equity
Sub-criterion 1: Addressing Health Access Challenges for Disadvantaged Groups

UNICEF uses a vulnerability-based approach, adapting programme targets to prioritize the most at-risk populations, especially in remote regions like Awdal and Galmudug. However, limited access to rural areas due to security challenges constrains equity efforts.

Sub-criterion 2: Clear Strategy to Reach Disadvantaged Groups

A TPM assessment found accessibility for vulnerable groups to be lowest in Banadir, where none of the observed facilities provided easy access. By contrast, over 60% of facilities elsewhere had no reported accessibility issues. The Baxnaano Project facilitates cash transfers for vulnerable households, linking them to health and nutrition services and this programme has provided good opportunities to supplement uptake in Better Lives facilities in Banadir region. National strategies, including Somalia’s Universal Health Coverage and Nutrition policies, prioritize disadvantaged groups, though a lack of disaggregated data at national DHIS II level limits precise tracking of programme reach.

Following the June 2024 climate vulnerability assessment, Better Lives expanded essential health services to include WASH and climate-related initiatives. UNICEF now integrates nutrition and WASH services into healthcare, ensuring a more holistic approach. Though indicators in the log frame require updates, the programme remains on track. The emphasis on climate-resilient healthcare aims to improve service accessibility and responsiveness for marginalized populations.

Effectiveness
Better lives approach to increased utilisation, improved health system capacity, improved availability of essential medicines and supplies, training of healthcare workers, improved data collection, and improved supply chain efficiency aims to strengthen effectiveness. The programme is tracking these key indicators through the log frame.
The programme has met most standards across adequate, good, and excellent levels but as it has not met all the standards. Overall, the effectiveness metric has been judged as ‘good’.

Sub Criterion 1: Increased utilisation of health services

Better Lives has successfully met all six indicators related to improving access to essential health and nutrition services (Sub-criterion 1: Increased Utilization of Health Services). UNICEF’s strategies, including large-scale immunization campaigns and outreach efforts, have helped achieve targets, with integration of Outpatient Therapeutic Programmes contributing to coverage. Despite initial barriers, family planning commodities are now accessible, though demand-generation remains key. However, the scale-down of the World Food Programme (WFP) has led to decreased food distribution, reducing health service utilization. FCDO log frames allow milestone adjustments, but revisions must account for extenuating circumstances, such as delays in programme rollout. Baseline district-level data is critical for tracking real programme impact.

Sub-criterion 2: Improvements in Health System Capacity and Efficiency

UNICEF’s supply chain innovations, including oral rehydration solutions and zinc co-packs, enhance treatment efficiency. Milestones for reporting completeness and joint supervision visits were exceeded (above 95%). Despite progress, stockouts persist, with only 70% of facilities reporting availability of tracer medicines against the 80% milestone. The WHO and FMOH led Harmonized Health Facility Assessment ensures comprehensive health infrastructure evaluations. UNICEF has begun transitioning from a push to a pull supply system, and refining HMIS data collection. Mapping community health workers and leveraging GAVI and UNFPA partnerships are priorities for demand generation and supply consistency.

Climate vulnerability indicators have been updated in the logframe and were further assessed in November 2024. UNICEF aims to integrate disaggregated data by gender and vulnerable groups into the DHIS II, with the aim of improving measurement of targeted interventions. Quality indicators will be monitored from the next review period, ensuring an equitable approach to healthcare (Sub-criterion 3: Addressing Target Vulnerabilities).

Assessment of whether the Programme continues to represent value for money

Based on the above analysis of outcome and output attainment, the theory of change, VfM and evidence analysis, there is sufficient evidence to support the continuation of the Better Lives programme.

A priority for 2025/2026 will be to work with the HHELMS team to strengthen UNICEF, downstream partners and Better Lives programme VfM frameworks with regards to strengthening analysis using data that was not available to inform the above VfM analysis in this review period. Particularly exploring cost-efficiency and cost-effectiveness will be critical in supporting the Government’s own assessment of how best to use its own limited, but modestly growing health resources to greatest impact.

E: RISK

Overview of risk management

The overall Better Lives programme risk assessment remains at major. The programme has remained within its risk appetite during the review period and within the wider BEM’s overall high-risk appetite.

Over the past year, the main trends in risk exposure for the program have been driven by natural disasters, disease outbreaks, and security challenges. Regions supported by the program have faced significant risks, such as severe storms in Awdal region in Somaliland, disease outbreaks like measles and cholera in Gedo, and security disruptions due to troop withdrawals in Mudug and inter-clan clashes further orchestrated by militia insurgents in Gedo. UNICEF's response has focused on maintaining service provision through temporary relocations, targeted measles campaigns, and enhanced security measures including with implementing partners. Continuous monitoring and collaboration with local health authorities were key components of the response to ensure the health and safety of the affected population.

As related to conflict and ongoing insecurity, the programme will need to ensure that it does not inadvertently worsen tensions or conflicts, particularly in resource-scarce or politically sensitive areas. In the remaining period, the programme will be steered towards being conflict- and culturally sensitive, gender-responsive, and climate-conscious, with a strong emphasis on accessibility, availability, affordability, and acceptability to better serve communities in need.

The political fragmentation and overly centralised Federal approach have been key issues that the programme partners have had to contend with. The programme’s direction to exit bilateral programming and work through a pooled fund mechanism will be a key measure towards strengthening FGS-FMS relationships in move that supports improved state building.

Another major trend in risk exposure has been the ongoing challenge of aid diversion in Somalia/Somaliland, where limited resources and high competition for humanitarian aid can lead to manipulation of access and misuse. To address this, UNICEF has intensified its monitoring activities through monthly and quarterly review meetings with implementing partners, as well as monthly supervision and monitoring visits to Better Lives-supported health facilities. UNICEF also maintained rigorous monitoring of partners' compliance with the Harmonized Approach to Cash Transfers (HACT) processes. This included training UNICEF and implementing partner staff on HACT procedures, conducting micro-assessments, periodic audits, and spot checks based on UNICEF’s risk-based audit methodology. Additionally, UNICEF has conducted wide-scale training sessions on the Last Mile Supply Monitoring (LMSM) solution for supply management and undertaken Logistics Capacity Assessments (LCA) for some partners.

In consultation with partners, UNICEF developed a Standard Operating Procedure (SOP) for supply distribution and requisitions to simplify and standardize the in-country distribution of health and nutrition supplies. A Consumption/Requisition form was introduced as part of the Logistics Management Information System (LMIS) to monitor consumption and match it to Health Management Information System (HMIS) reports. Furthermore, UNICEF is in the process of rolling out an electronic Logistics Management Information System (eLMIS) to increase end-to-end data visibility across the supply chain which will be augmented by staff capacity building on pharmaceutical and supply chain management.

Additionally, the Prevention of Sexual Exploitation and Abuse (PSEA) is a corporate responsibility for UNICEF. The organization is committed to several measures to strengthen the internal safeguarding system and mitigate risks. This includes rigorous vetting of staff during the selection process, regular training for all personnel on PSEA, and ensuring managers at all levels support and develop systems that maintain a safe and enabling environment. Implementing partners are assessed using the UN Common Assessment PSEA tool and are equipped with adequate knowledge about procedures and reporting channels. PSEA is mainstreamed into programs and operations, including integrating PSEA risk assessment into planning, monitoring, and assurance activities. UNICEF implements the UN Protocol on the Provision of Assistance to Victims of Sexual Exploitation and Abuse (SEA) and has established mechanisms for the prompt investigation of all SEA allegations received.

A key emerging risk is the executive orders by the US government to suspend aid with terminations of a number of humanitarian grants supporting lifesaving health and nutrition programmes. This coupled with signals from other donors on reduction of aid has put further strains on an already constrained fiscal space in Somalia. It is expected that this will significantly impact operational capacity of implementing partners and UNICEF’s capacity to complement the Better Lives programme with existing resources from other donors which has been a key factor contributing to success of the programme.

A major risk to be aware of is the upcoming reduction of funding in view of the 0.3% new ODA environment. This will contribute to failure to respond to shocks and crises and forward planning to safeguard against the increasing reputational risk to FCDO will be required. Given this, the Better Lives programme SRO and PRO will continuously monitor if the residual risk of ‘major’ will need to be reviewed and thereby increase the current risk appetite from ‘Cautious’. If this is the case, decisions will be made to escalate this to London whilst working closely with the FGS (and Somaliland) to manage a responsible exit of the Better Lives programme.

BEM employs controls and assurances as outlined in the Programme Operating Framework. This includes delivery chain risk maps, due diligence assessments, and partner and programme level risk registers. The overall Better Lives programme risk register is updated by the BEM Better Lives programme team quarterly, and the lead Programme Manager, PRO and SRO review all risk categories, safeguarding, fraud, loss, and aid diversion cases quarterly.

A follow up action from the last review was conducting a due diligence assessment which was conducted during this review period. UNICEF is taking forward improvements noted that UNICEF is taking forward from their own internal audit processes, and which FCDO will follow up on progress updates. To enhance the partner performance, FCDO-UNICEF jointly developed KPIs reported against every six-months, including on agreed actions from UNICEF’s internal audit report. FCDO will also proactively support UNICEF in the next review period to strengthen delivery, monitoring and evaluation initiatives; and improve working across partners to leverage resources.

Additionally, BEM instituted monthly and quarterly conversations with UNICEF and partners on risk, which has encouraged prompt escalation of any emerging or major risk and strengthened timely mitigation actions. Further, BEM holds regular (monthly and ad hoc) conversations with the FMoH and MoHD during which any risks to programme delivery are highlighted.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The implementation modality proposed for the programme in the Better Lives business case was the use of a single fund manager – UNICEF with downstream implementation by international NGO partners.

Performance of partnership (s)

UNICEF has provided six-monthly progress reports with aggregated information from downstream partners on performance and delivery. This has been complimented by BEM commissioned TPM, quarterly review meetings of the programme attended by the FCDO, MoH, UNICEF and downstream partners, and joint FCDO-MoH-UNICEF monitoring field visits to Somaliland. UNICEF’s performance has been reasonable given the constraints on UK funding and complexity of context. This has been seen through UNICEF’s proactive and optimal engagement with the FMOH and MoHD particularly in leading discussions to determine health facilities to be operationalised and in mitigating delays that have threatened to curtail delivery.

UNICEF also demonstrated effective performance in delivery and programme management, including downstream partners management given the constraints on UK funding and complexity of context. This saw UNICEF’s resilience and flexibility to programme on CDEL funded climate and health initiatives. Following a Climate and Health Vulnerability Assessment recommendations, UNICEF had rigorous planning and prioritisation exercise that enabled them to generate a work plan within tight timelines commit the activities within the financial year, whilst engaging with the MoH and partners to deliver the desired outcomes. UNICEF programme delivery team remained responsive throughout the reporting period and worked closely with the BEM Programme and Finance team to align the spending categorise i.e. CDEL and RDEL. BEM Programme and Finance team flagged challenges on quality of forecasting and expenditure and procurement reporting updates. To enhance delivery in the upcoming period, BEM and UNICEF teams agreed track delivery plans of all CDEL activities committed by April 2025 and ensure these are fully completed by September 2025.

BEM and UNICEF have had regular meetings with both Somalia and Somaliland Ministries of health. The complex relationship between FGS and Somaliland means that meetings continue to be held separately for FMoH and MoHD. This has brought complexity and additional management requirements to the programme. Whilst the separate planning for and conducting of meetings has meant additional effort from the BEM staff, the situation has not adversely affected programme delivery including on decisions made as regards programme locations and interventions. BEM has continuously worked with key partners including GFATM, Gavi and World Bank to ensure alignment in delivery approach – a process that has also been encouraged by the health authorities.

The partnership with KSrelief, though had begun with delays as regards agreeing common working arrangements and further, mutual signing of the agreements, this has now been finalised, and the programme is in its closure phase. BEM is reviewing the need for a follow-on programme in light of the reviewed budgets.

Asset monitoring and control

The downstream partners each manage an FCDO specific asset register for all equipment procured for use within the health facilities, the field offices and for programme operations. Asset register updates are incorporated into the UNICEF 6-monthly progress reports. The End of Project report for the Emergency programme was submitted in May 2024 and provided an updated asset register with a record of asset disposal in locations where Better Lives exited. All other assets have been retained in facilities currently operational whilst others – from facilities that were closed – were transported to nearby Better Lives facilities to ensure support to ongoing activities. Additional assets are under procurement (mainly as relates to hospital and health centre medical equipment) funded through the CDEL climate funds which will be included in the asset register updates.

The TPM exercise that is underway has a provision to conduct an asset spot check. Findings from this will be incorporated in this report once received.

Quality of financial management

The Better Lives programmes 2024/25 budget allocation was £14million split as £11million resource (RDEL) and £3million capital (CDEL) including international climate finance (ICF). As highlighted in the last review period, during the year under review, the programme implementation included a full climate and health vulnerability and adaptation assessment which allowed BEM to allocate additional funds to take forward the recommendations from the assessment. UNICEF remained agile and provided sufficient flexibility in allocating resources to deliver on CDEL ICF which had come in during the last half of the reporting period, and were able to increase spend by 15%. This brought the full year revised programme budget to £16,182,273 as shown in table 1 below.

Table 3: Outline of the Better Lives programme budget breakdown for 2024/2025

The agreed financial reporting modality with UNICEF is through a six-monthly financial report alongside the bi-annual narrative report. To improve the quality of communication, responsiveness, and ensure more openness on delivery challenges and timely escalation of risks, the team has monthly meetings with UNICEF to discuss key technical and compliance issues as indicated earlier. This has allowed the BEM Programme team to build and maintain strong working relationships with UNICEF. The BEM and UNICEF team have also had adhoc conversation, especially to understand the delivery of the CDEL budget, and which also included finance, and risk leads from FCDO.

UNICEF has remained on track on expenditure and reporting. Detailed analysis of UNICEF (and downstream partners’) statements of expenditure was assessed for VfM by the MEL partner to provide guidance on programme achievement of VfM metrics moving forward.

BEM has instituted monthly meetings with UNICEF to ensure comprehensive discussion of the financial expenditure given the decision to close the programme. UNICEF will work on a financial review across all funded programming components (including CDEL) and regularly update this to reflect any under/ overspends. This will allow timely discussions of any underspends to ensure full budget delivery by March 2026.

Date of last narrative financial report	7 March 2025 (TBC)	Date of last audited annual statement	April 2023 (TBC)

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Overview:

Underpinning the above, BEM has significantly taken forward several monitoring evaluation and learning activities through the Humanitarian & Health Evaluation Learning and Monitoring in Somalia (HHELMS) team/ OPM. These include two third party monitoring (TPM) activities with results realised in March 2024 and April 2025; a programme baseline assessment, evaluation (ongoing until programme closure), a Gender Equality Disability and Social Inclusion (GEDSI) analysis, a conflict sensitivity analysis and a value for money (VfM) analysis. The conflict sensitivity analysis work deserves specific mention.

The analysis was conducted to ensure that the Better Lives programme was working within and through an approach that does not inadvertently exacerbate existing tensions. The analysis has provided deeper understanding of the conflict dynamics in targeted locations (Gedo and Galmudug) whilst mapping key actors, triggers and structural factors influencing instability. Further, the analysis has assessed how political, economic and security developments – such as upcoming state and federal elections and fluctuating donor support – could impact programme delivery and effectiveness. This and other ME&L deliverables showcase the strength of FCDO as an ongoing key player in the health sector to influence overall sector strategy.

Partner-led monitoring activities:

In Somalia (Galmudug, Jubaland, and Banadir Regional Administration): At least one joint field visit was conducted in each state to health facilities during the review period – mainly conducted by UNICEF and partners jointly with the FMOH and FMS. Action points were developed to address gaps and weaknesses. General observations included that there was relatively good service provision including availability of adequate supplies, 24/7 service provision, and staffing that could support services. Staff used Health Management Information System (HMIS) and Logistics Management Information System (LMIS) registers to capture consumption data. Main issues identified included the use of non-electric autoclaves, limited nutrition services, and low utilization of services in some instances. For example, in Q1 joint monitoring, some Action Against Hunger (ACF) and Mercy USA facilities did not provide nutrition and Expanded Program on Immunization (EPI) services. The reasons for these gaps were jointly identified, and action points were agreed upon. Integration of services was initiated at ACF and Trocaire facilities, and Mercy USA agreed to start and finalise program document amendments to include nutrition services.

UNICEF and implementing partners conducted several field visits with the MOHD, BEM and implementing partners (Mercy USA and Save the Children) – on site in Somaliland.

In (Awdal and Togdheer): Collaborative quarterly supportive supervision was conducted by Mercy USA, Save the Children International (SCI), and the Ministry of Health Development (MOHD). Additionally, SCI and Mercy USA, in conjunction with the MOHD district health management team, carried out monthly supportive supervision visits across Better Lives-supported facilities.

Following each quarterly joint supervision visit, a review meeting was held, attended by representatives from MOHD, UNICEF, FCDO, and implementing partners (IPs). Over the years, numerous recommendations have been made to various levels and institutions, focusing on financial management, supply management, warehousing, and service delivery at the facility level.

In response to these recommendations, guidelines and Standard Operating Procedures (SOPs) for supply management were developed. Training sessions on financial and logistics management were conducted for IPs, leading to improvements in warehousing. In keeping with some recommendations, Save the Children has relocated to a new warehouse (in Awdal region) that meets the required standards for warehousing.

Review Meetings:

Monthly Meetings with implementing partners: UNICEF field offices conduct monthly meetings with implementing partners in their regions. The UNICEF Mogadishu field office, covering the south-central region, managed to conduct monthly meetings with ACF, Mercy USA, and Trocaire prior to the first Quarterly Review Meeting (QRM). Key issues focused on the integration of nutrition services into existing services. A significant portion of the discussion was dedicated to addressing existing supply gaps and outlining effective strategies for resolving them. The importance of strengthening coordination at the sub-national level to leverage existing female health workers in the community, who can link community members to Better Lives supported facilities, was also highlighted. This was possible with an expanded UNICEF footprint with newly established offices/hubs as part of the decentralization process. For Better Lives regions, UNICEF has health and nutrition staff based in Dollow, Galkayo, and Dhusamareb. Other UNICEF hubs outside Better Lives regions include Baidoa, Kismayu, and Beledweyne.

Quarterly Review Meetings (QRMs): Regular Better Lives quarterly review meetings were held mostly in person in Mogadishu and Somaliland. During the review period, three QRMs were conducted in Mogadishu and three in Somaliland with partners and Government counterparts. These meetings have been complemented by specific implementing partner meetings led by UNICEF with the aim of addressing bottlenecks and actions realised during the QRMs.

Recommendations to changes in the MEL system:

Noting the upcoming programme closure, BEM Is currently reviewing the MEL deliverables to take forward in the next review period. A balance will need to be realised to ensure that activities supported take cognisance of the need to scale down the programme. Decisions will be made in close collaboration with UNICEF and the health authorities.