## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Indicator formulation
Group | Indicator Name | Description | Numerator | Denominator | Indicator Calculations | Data Source | Agreed upon
Impact: Improved health and nutrition status for vulnerable Somalis
Maternal & Neonatal Mortality | Maternal mortality ratio | Proportion of women who died of pregnancy related events per 100,000 live births in facility | Maternal death in facility | Live Birth in facility | Number of maternal deaths in health facilities/Number of live births in health facilities​×100 | DHIS2/HMIS
Child Mortality | Under five mortality rate | Proportion of children (0-59 months) who died per 1,000 population 0-59 months | Child death in facility | Population 0-59 months | Number of deaths of children (0-59 months) in the facility/Number of child admissions (0-59 months) in the facility | DHIS2/HMIS
Nutrition - SAM | Severe Acute Malnutrition Rate | Proportion of discharged children who recovered from SAM treatment in OTP/SC | Total # of children aged 6 59 months with SAM admitted into treatment who are discharged as recovered | Total # of children aged 6 59 months discharged | Total # of children aged 6 59 months with SAM admitted into treatment who are discharged as recovered/Total # of children aged 6 59 months dischargedx100 | ONA/DHIS2
Outcome A: Improved access to, and use of, quality essential health and nutrition services
Maternal Health - FP | % of women in catchment areas supported by Better Lives using modern contraception. | Proportion of women aged 15-49 years using modern contraception (new ) in better live catchment area | Number of women aged 15-49 years using modern contraception method in Better live catchment area. | Estimated Population 15-49 years female (WCBA) in Better live catchment area. | Number of women aged 15-49 years using modern contraception method in Better live catchment area./Estimated Population 15-49 years female (WCBA) in Better live catchment area.)×100 | DHIS2/HMIS | Agreed
Maternal Health - ANC | Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in catchment areas of Better Lives supported facilities/Antenatal Client 4th visit coverage | Proportion of antenatal clients seen for 4th visit of estimated pregnant population in catchment areas of Better Lives supported facilities/The indicator measures the percentage of women aged 15 to 49 with a live birth who received antenatal care at least four times during pregnancy | Antenatal Client 4th visit | Estimated Population of Pregnant women in catchment areas of Better Lives supported facilities | Antenatal Client 4th visit/Estimated Population of Pregnant women in catchment areas of Better Lives supported facilities | DHIS2/HMIS | Agreed
Maternal Health - Delivery | Skilled attendance at birth - % of deliveries in Better Lives supported areas attended by skilled health personnel./Skilled birth attendant delivery rate | Proportion of deliveries carried out by skilled birth attendants in facilities in Better Lives supported areas | Actual Deliveries by skilled birth attendant at health facility in Better Lives supported areas | Number of expected Deliveries in facility (sum) in Better Lives supported areas | Actual Deliveries by skilled birth attendant at health facility in Better Lives supported areas/ Number of expected Deliveries (Sum) in Better Lives supported areas)×100 | DHIS2/HMIS | Agreed
Immunisation - coverage: | proportion of children in catchment areas of Better Lives supported facilities vaccinated with the third dose of pentavalent vaccine/Pentavalent 3rd dose coverage (0 - 11 m) | Proportion of infants (0-11 m) who received Pentavalent vaccine 3rd dose in catchment areas of Better Lives supported facilities | Pentavalent 3rd doses (0-11 m) in catchment areas of Better Lives supported facilities | Estimated Population of 0-11 months children in catchment areas of Better Lives supported facilities | Pentavalent 3rd doses (0-11 m) in catchment areas of Better Lives supported facilities/Estimated Population of 0-11 months children in catchment areas of Better Lives supported facilities×100% | DHIS2/HMIS | Agreed
Nutrition - SAM | Severe acute malnutrition – proportion of discharged children who recovered from SAM treatment in OTP/SC | Proportion of discharged children who recovered from SAM treatment in OTP/SC | Total # of children aged 6 59 months with SAM admitted into treatment who are discharged as recovered | Total # of children aged 6 59 months discharged | Total # of children aged 6 59 months with SAM admitted into treatment who are discharged as recovered/Total # of children aged 6 59 months dischargedx100 |  | Agreed
Hospital / HC - Outpatient | Utilisation and access – proportion of population in the catchment areas of Better Lives supported facilities using OPD services/Outpatient Utilisation rate - all | Rate at which the population uses Outpatient services in the catchment areas of Better Lives supported facilities | The number of all Outpatient visits - in the catchment areas of Better Lives supported facilities | Estimated Population in the catchment areas of Better Lives supported facilities | The number of Outpatient visits - in the catchment areas of Better Lives supported facilities/Estimated Population in the catchment areas of Better Lives supported facilities*100 | DHIS2/HMIS | Agreed
Outcome B: Improve climate resilience of health system
| Number of people with improved climate resilience [ICF4]/Number of facilities with improved climate resilience | Number of people in Better Live catchment areas supported with climate resilience activities | N/A | N/A | This will be based on the number of facilities provided with support like Solar energey, water, sanitation and hygiene | Program reports/Supervison visits reports or assessment reports | Agreed
Output 1: Health facilities deliver quality reproductive maternal healthcare and nutrition services, including family planning, to women of childbearing age
Maternal Health - FP | Number of Better Lives supported health facilities providing contraceptive services |  | Number of Better Lives supported health facilities providing contraceptive services | N/A | N/A | DHIS2/HMIS | Agreed
Maternal Health - ANC | Number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy/"Antenatal Client 1st visit - before 12 weeks" | Antenatal care visits seen in the first trimester | N/A | N/A | N/A | DHIS2/HMIS | Agreed
Maternal Health - Delivery | Number of deliveries assisted by skilled birth attendants at Better Lives supported health facilities/Delivery by Skilled birth attendant | Number of deliveries carried out by skilled birth attendants in facility in the catchment areas of Better Lives | N/A | N/A | N/A | DHIS2/HMIS | Agreed
Maternal Health - Postpartum | Number of women who received post-natal care (PNC) within 48 hours of childbirth. | Number of postnatal mothers who received a checkup within 48 hours of delivery | Postnatal 1st Visit new mother (0-48 hrs) | N/A | N/A | DHIS2/HMIS | Agreed
HRH | Number of facility-based staff and community health care workers that are trained in Maternal and Newborn Care in the targeted Better Lives health facilities. | community health workers trained in the Better Lives areas and supporting facilities | N/A | N/A | N/A | Program reports/Supervison visits reports or assessment reports | Agreed
Output 2: Health facilities deliver quality essential package of services to children under 5
Immunisation - DOR | Dropout rate between infants receiving the 1st dose (penta 1) of pentavalent vaccine and the 3rd dose (penta 3)/Dropout rate Pentavalant 1st dose to Pentavalent 3rd dose | Proportion of infants who received Pentavalent 1st dose but not Pentavalent 3rd dose | Pentavalent 1st doses (0 - 11 m) minus Pentavalent 3rd doses (0 - 11 m) | Penta 1st doses (0 - 11 m) | Pentavalent 1st doses (0 - 11 m) minus Pentavalent 3rd doses (0 - 11 m)/Penta 1st doses (0 - 11 m)*100 | DHIS2/HMIS | Agreed
Nutrition - SAM | Number of children disaggregated by gender, aged 6-59, months with severe acute malnutrition who receive treatment. |  | # of male and female children ( 6-59 months) with severe acute malnutrition who receive treatment |  |  | ONA/DHIS2 | Agreed
Child Health - IMCI | Number of children (0-59 months) with diarrhoea treated with oral rehydration solution (ORS) and Zinc sulphate, disaggregated by age and gender/Number of Diarrhoea treatment of (0-59 Children) with ORS + Zinc |  | Child with diarrhoea (0-59 months) treated with ORS + Zinc in the catchment areas of Better Lives supported facilities |  |  | DHIS2/HMIS | Agreed
| Number of children 0-59 months with Pneumonia treated with Amoxicillin |  | Number of children (0-59 m) with pneumonia treated with Amoxicillin |  |  | DHIS2/HMIS | Agreed
Output 3: Health facilities deliver quality curative services
Hospital / HC - Outpatient | Number of people using OPD services at Better Lives supported health facilities (disaggregated by age and gender) | The number of Outpatient visits - in the catchment areas of Better Lives supported facilities | N/A | N/A | N/A | DHIS2/HMIS | Agreed
Essential Medicines (for all items listed under Essential Medicines) | Proportion of facilities that report essential tracer medicine stockouts/Proportion of health facilities with at least 80% availability of selected tracer medicines and medical supplies | All eligible facilities that are stocking pharmaceutical supplies and can measure tracer items. | Number of health facilities with at least 80% availability of selected tracer medicines and medical supplies in the catchment areas of Better Lives supported facilities | Number of facilities in the catchment areas of Better Lives supported areas | Number of health facilities with at least 80% availability of selected tracer medicines and medical supplies in the catchment areas of Better Lives supported facilities/Number of facilities in the catchment areas of Better Lives supported areas*100 | DHIS2/HMIS but from mid-2025 we might use the E-LMIS | Agreed
HRH | Proportion of targeted health facilities with appropriate staffing complement and staff available | Not to be collected | N/A | N/A | N/A | Program reports/Supervison visits reports or assessment reports | Agreed
Output 4: Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices
Nutrition - Vit A / Micronutrient | Number of primary caregivers of children aged 0-23 months who received IYCF counselling |  | Number of primary caregivers of children aged 0-23 months who received IYCF counselling | N/A | N/A | ONA/DHIS2 | Agreed
Maternal Health - ANC | Proportion of women interviewed in ANC who know at least three danger signs of newborn complications | This indicator will measure the number of women who understand complications that would lead them to access healthcare. | Number of pregnant women in the Better Lives catchment population | Women of child bearring age | Number of pregnant women accessing ANC services in BL facilities divided by the number of women of child bearing age in the same catchment populations. | This will be included in the TPM on quaterly basis and focused on the region planned for the period | Agreed
Output 5: Enhanced reporting and supervision of service delivery
Monitoring and Reporting | Proportion of facilities submitting timely and complete HMIS reports in the DHIS II |  | Actual reports submitted on timely and complete on the DHIS2 by facilities in the catchment areas of Better Lives supported facilities | Expected reports on DHIS2 by facilities in the catchment areas of Better Lives supported facilities | Actual reports submitted on timely and complete on the DHIS2 by facilities in the catchment areas of Better Lives supported facilities/Expected reports on DHIS2 by facilities in the catchment areas of Better Lives supported facilities *100 | DHIS2/HMIS | Agreed
HSS/M&E | Number of joint supportive supervision visits conducted in the supported facilities, between the MoH, UNICEF and implementing partners. |  |  |  |  | Program reports/Supervison visits reports or assessment reports | Agreed
| % of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits |  | Number of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits | Number of Better Lives supported facilities visited for integrated supportive supervision visits | Number of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits/Number of Better Lives supported facilities visited for integrated supportive supervision visits *100 | Program reports/Supervison visits reports or assessment reports | Agreed
| Output 6: Support to improving climate resilience of health services delivered |  |  |  | N/A | UNICEF and partner reports | Agreed
6.1 | Number of health care facilities assessed and provided with climate resilient energy support | The specific numbner of facilities assessed and provided with climate resilient services. Current targeted are 87 | N/A | N/A
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Discuss in the next quarterly review with the partners and government
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be reported bi-annually or annually as is dependent on TPM exercises

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
Impact Indicators
1 | Impact Indicator 1: Maternal mortality ratio | No change
2 | Impact Indicator 2: Under five mortality rate | No change
3 | Impact Indicator 3: Severe Acute Malnutrition Rate | No change
Outcome Indicators
| OUTCOME A: Improved access to, and use of, quality essential health and nutrition services | This is at a lower causal level than current formulation of Output 1. Propose a clearer structure where Outputs relate to delivery of services, and outcome to access and use. This is at a lower causal level than current formulation of Output 1. Propose a clearer structure where Outputs relate to delivery of services, and outcome to access and use. There is currently no outcome (or outcome indicators) related to improving health sector stewardship and systems. This reflects the reduced ambition of the programme in this area but an additional outcome is required to reflect climate resilience objectives. Noting the above and to incorporate partners' comments, the overall indicator was changed from: Improved access to quality essential health and nutrition services to Improved access to, and use of, quality essential health and nutrition services All of the outcome indicators are defined as proportions, rather than absolute numbers. This is meaningful at this level if the denominator is the population served by a facility but this depends on being able to make accurate estimates of population served by a health facility and the possible effects of population displacement. | Caroline Mwangi | 2024-08-14
4 | Outcome A.1 % of women in catchment areas supported by Better Lives using modern contraception. | Changed from: Family Planning - % of health facilities that provide contraceptive services in Better Lives supported areas, in collaboration with UNFPA. Considerations made for change: This is a measure of service availability so does not belong at this level. Need also to know how many people are supplied with contraceptive services, and what number/proportion of the population are using them. | Caroline Mwangi | 2024-08-14
5 | Outcome Indicator A.2: Antenatal Care (ANC) coverage – Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in catchment areas of Better Lives supported facilities | Remains the same: Antenatal Care (ANC) coverage – Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in Better Lives supported health facilities. If use proportionate measure, need to clarify that denominator is estimated number of pregnant women in the target population. Appropriate to include proportionate measures of ANC4 as outcome measure and ANC1 numbers as output measure because ANC4 also requires behavioural change Other considerations: Possible to report as data is available in DHIS2. Although its important to agree on the population to use for the denominator | Caroline Mwangi | 2024-08-14
6 | Outcome Indicator A.3: Skilled attendance at birth - % of deliveries in Better Lives supported areas attended by skilled health personnel. | Changed from: Skilled attendance at birth - % of deliveries attended by skilled health personnel in Better Lives healthcare facilities. Denominator should be estimated number of births in the target population. Output 1.3 measures attended deliveries at facilities. | Caroline Mwangi | 2024-08-14
7 | Outcome Indicator A.4: Immunisation coverage: proportion of children in catchment areas of Better Lives supported facilities vaccinated with the third dose of pentavalent vaccine | Changed from: Immunisation coverage – Proportion of children vaccinated with the third dose of pentavalent vaccine If use proportionate measure, need to clarify that denominator is number of children in the target population. The target population to allow for determination of the denominator needs to be defined. | Caroline Mwangi | 2024-08-14
8 | Outcome Indicator A.5: Severe acute malnutrition – proportion of discharged children who recovered from SAM treatment in OTP/SC | No change. This is a measure of the effectiveness of treatment for SAM (included in DHIS II). A low number treated (Output 2.2) but with high effectiveness would score well Note that efforts need to continue in communities to identify and treat children with SAM whilst recognising that those managed are only a small proportion of the population. | Caroline Mwangi | 2024-08-14
9 | Outcome Indicator A.6: Utilisation and access – proportion of population in the catchment areas of Better Lives supported facilities using OPD services | Changed from: Utilisation and access – Health facility utilisation rate. To support measurement, there is need to define proportion of the population and the type of service we are measuring. It is best if we use OPD service which will be a good indicator. e.g. Number of people/Proportion of population with adequate access to primary health care services (OPD services) provided in better live supported facilities | Caroline Mwangi | 2024-08-14
10 | OUTCOME B: Improve climate resilience of health system | Outcome indicator to reflect climate change resilience objective. Improved resilience (outcome) should lead to improved health and nutrition status (impact), so no additional impact indicator required. Indicator updated as: Number of people served by health facilities with improved access to clean energy(ICF2) | Caroline Mwangi | 2024-08-14
| Output 1: Health facilities deliver quality reproductive maternal healthcare and nutrition services, including family planning, to women of childbearing age | Changed from: Women of childbearing age access and utilize quality RMNCAH and nutrition services including family planning - which was at a higher level in the causal pathway than the Outcome. Redefined to relate to services delivered | Caroline Mwangi | 2024-08-14
| Output Indicator 1.1: Number of Better Lives supported health facilities providing contraceptive services | Changed from: Number of health facilities providing contraceptive services in Better Lives supported areas, in collaboration with UNFPA. | Caroline Mwangi | 2024-08-14
| Output Indicator 1.2: Number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy | Changed from: Proportion/number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy Outputs to be defined in terms of numbers, outcomes as proportion of target population | Caroline Mwangi | 2024-08-14
| Output Indicator 1.3: Number of deliveries assisted by skilled birth attendants at Better Lives supported health facilities. | No change | Caroline Mwangi | 2024-08-14
| Output Indicator 1.4: Number of women who received post-natal care (PNC) within 48 hours of childbirth. | No change | Caroline Mwangi | 2024-08-14
| Output Indicator 1.5: Number of facility-based staff and community health care workers that are trained in Maternal and Newborn Care in the targeted Better Lives health facilities. | Moved from 3.1 | Caroline Mwangi | 2024-08-14
| Output 2: Health facilities deliver quality essential package of services to children under 5 | Changed from: Children under five have access to an essential package of health services to reduce morbidity and mortality from malnutrition and main childhood illnesses like Malaria, pneumonia, diarrhoea, and measles Contents of essential package still to be confirmed. Prior consideration is number/proportion of health facilities that have staff, skills and supplies to deliver the essential package [Measurement is provided by related indicators listed below: all should be disaggregated by age and gender] | Caroline Mwangi | 2024-08-14
| Output Indicator 2.1: Dropout rate between infants receiving the 1st dose (penta 1) of pentavalent vaccine and the 3rd dose (penta 3) | No change | Caroline Mwangi | 2024-08-14
| Output Indicator 2.2: Number of children disaggregated by gender, aged 6-59, months with severe acute malnutrition who receive treatment. | No change | Caroline Mwangi | 2024-08-14
2024-08-14
| Output Indicator 2.3: Number of children (0-59 months) with diarrhoea treated with oral rehydration solution (ORS) and Zinc sulphate, disaggregated by age and gender. | No change If incidence of diarrhoea falls but treatment proportion unchanged, this will show fall but still appropriate as output measure | Caroline Mwangi | 2024-08-14
| Output Indicator 2.4: Number of children 0-59 months with Pneumonia treated with Amoxicillin | Changed from: Proportion of children 0-59 months with malaria treated with Amoxicillin; Proportion of children 0-59 months with Pneumonia treated with Amoxicillin Proposed outputs should be numbers treated. Proportions of children in population with diseases would be outcome measure | Caroline Mwangi | 2024-08-14
| Output 3: People are accessing quality curative health services. | No change “Access” should be higher in the causal pathway Indicators partially cover resources required to deliver (quality) services and do not relate to access Should include an indicator of the numbers of people accessing services, and of community/client satisfaction with services available/delivered (including in relation to use of competing/complementary private services) Output 3 should measure capacity of facilities to deliver services | Caroline Mwangi | 2024-08-14
| Output indicator 3.1: Number of people using OPD services at Better Lives supported health facilities (disaggregated by age and gender) | Indicator added to reflect an indicator of aggregate services delivered | Caroline Mwangi | 2024-08-14
| Output Indicator 3.2: Proportion of facilities that report essential tracer medicine stockouts | Changed from: Forecasting accuracy: Proportion of health facilities timely reporting stock status in the LMIS The change was as a result of High forecasting accuracy could be combined with severe stock shortages (if supply system disrupted). Indicator should be moved to Output 5 (quality of reporting), and replaced with an appropriate indicator of stock availability. Therefore, final indicator agreed on is Proportion of facilities that report essential tracer medicine stockouts Denominator: Number of health facilities visited, or reported in LMIS: Diagnostic Tracer Items to be determined: e.g. Amoxicillin | Caroline Mwangi | 2024-08-14
| Output indicator 3.3: Proportion of targeted health facilities with appropriate staffing complement and staff available | This is a new indicator added to ensure reporting against staffin. However, following various discussions with UNICEF, health authorities and partners, the indicator was found not to be feasible to collect data and in any case, funding decline would not allow for recruitment of additional staff. It was recommended that partners work with the available staff per facility and ensure that these contribute to as much cost-effciiency as possible (e.g., the health nurses also provide family planning services and nutrition for a more integrated approach) | Caroline Mwangi | 2024-08-14
| Output 4: Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices | Changed from: Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices. | Caroline Mwangi | 2024-08-14
| Output Indicator 4.1: Number of primary caregivers of children aged 0-23 months who received IYCF counselling | No change | Caroline Mwangi | 2024-08-14
| Output Indicator 4.2: Proportion of women interviewed in ANC who know at least three danger signs of newborn complications | Changed from: Number of women interviewed in ANC who know at least 3 danger signs of newborn complications as Proportion of women interviewed who know danger signs would be better indication of knowledge Collection of data for this indicator will require close collaboration with TPM Data collection (that includes client satisfation surveys) and Baseline Assessment data collaction elements. Downstream partners to also consider options to support more regular data collection. | Caroline Mwangi | 2024-08-14
| Output 5: Enhanced reporting and supervision of service delivery | Changed from: The MOH and partners have enhanced capacity to deliver, monitor and report on services towards strengthening the quality of health systems. The indicators relate mainly to the capacity of facilities, the phrasing of the Output relates to capacity of MOH and partners. The latter is mainly outside the scope of Better Lives so propose narrowing this to focus on the main issues that the programme is addressing. The proposed indicators do not address some wider system and stewardship issues (e.g. referral, HR systems etc.) whose importance was stressed in the workshop – but these should be considered as assumptions since not addressed by the programme. | Caroline Mwangi | 2024-08-14
| Output Indicator 5.1: Proportion of facilities submitting timely and complete HMIS reports in the DHIS II | Changed from: Proportion of facilities supported to improve reporting that submit timely and complete HMIS reports against the DHIS II as the standard of measurement - because this is a measure of effectiveness of support, but a better measure of facility reporting capacity is the proportion of facilities submitting timely and complete HMIS reports. Numbers provided with support would be appropriate process indicator | Caroline Mwangi | 2024-08-14
| Output Indicator 5.2: Number of joint supportive supervision visits conducted in the supported facilities, between the MoH, UNICEF and implementing partners. | No change | Caroline Mwangi | 2024-08-14
| Output Indicator 5.3: % of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits | No change. However, the indicator will require a clear operational definition of “actioned feedback” throughout the implementatio process. | Caroline Mwangi | 2024-08-14
| Output 6: Support to improving climate resilience of health services delivered | New indicators included | Caroline Mwangi | 2024-08-14
| Output indicator 6.1: Number of people supported to better adapt to the effects of climate change [ICF1] | Agreed that this indicator would instead be reported at outcome level | Caroline Mwangi | 2024-08-14
| Output Indicator 6.2: Number of facilities in programme areas that are assessed for climate resilient support | New indicator included | Caroline Mwangi | 2024-08-14

## Logframe UNICEF-FCDO- Final
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
BETTER LIVES FOR SOMALI WOMEN AND CHILDREN LOGICAL FRAMEWORK - APRIL 2024 - MARCH 2025
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | [7 empty] | Assumptions
Improved health and nutrition status for vulnerable Somalis | Maternal mortality ratio | Planned | 621 | [7 empty] | These impact indicators will be measured through a bespoke Better Lives programme evaluation. Additional input will be provided through baseline assessment that will support understanding of the Better Lives catchment population figures. Data will be traingulated through the SHDS and MICS conducted by FGS and Somaliland.
Achieved
Source:
Better Lives programme evaluation conducted by OPM as the MEL adviser
| Impact Indicator 2 |  | Baseline
| Under five mortality rate | Planned | 106
Achieved
Source:
Better Lives programme evaluation conducted by OPM as the MEL adviser
| Impact Indicator 3 |  | Baseline
| Severe Acute Malnutrition Rate | Planned | 2.6
Achieved
Source:
Better Lives programme evaluation conducted by OPM as the MEL adviser
OUTCOME | Outcome Indicator 1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
OUTCOME A: Improved access to, and use of, quality essential health and nutrition services | % of women in catchment areas supported by Better Lives using modern contraception. | Planned | 1.5% | 2% | 1.6% | 1.7% | 1.7% | 1.8% | 1.9% | 2% | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 2.216% |  | 2.971%
Source:
DHIS2/HMIS
| Outcome Indicator 2 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in catchment areas of Better Lives supported facilities/ ANC-4th visit coverage | Planned | 29% | 42% | 30% | 33% | 33% | 36% | 39% | 42%
|  | Achieved |  |  | 20.03% |  | 38.99%
Source:
DHIS2/HMIS
| Outcome Indicator 3 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Skilled attendance at birth - % of deliveries in Better Lives supported areas attended by skilled health personnel./Skilled birth attendant delivery rate | Planned | 47% | 54.5% | 48.5% | 50% | 50% | 52% | 53% | 55%
|  | Achieved |  |  | 44.6% |  | 86.61%
Source:
DHIS2/HMIS
| Outcome Indicator 4 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| proportion of children in catchment areas of Better Lives supported facilities vaccinated with the third dose of pentavalent vaccine/Pentavalent 3rd dose coverage (0 - 11 m) | Planned | 61.37% | 86% | 66% | 71% | 71% | 76% | 81% | 86%
|  | Achieved |  |  | 62.22% |  | 125.5%
Source:
DHIS2/HMIS
| Outcome Indicator 5 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Severe acute malnutrition – proportion of discharged children who recovered from SAM treatment in OTP/SC | Planned | 90% | 95% | 92% | 95% | 95% | 95% | 95% | 95%
|  | Achieved |  |  | 96.4% | 96% | 96%
Source:
ONA/DHIS2
| Outcome Indicator 6 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Proportion of population in the catchment areas of Better Lives supported facilities using OPD services. | Planned | 0.21648 | 0.32 | 0.24 | 0.26 | 0.26 | 0.28 | 0.3 | 0.32
|  | Achieved |  |  | 0.38 |  | 0.45518
Source:
DHIS2/HMIS
OUTCOME | Outcome Indicator 1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
OUTCOME B: Improve climate resilience of health system | Number of people served by health facilities with improved access to clean energy(ICF2) | Planned | 0 | 1144575 | 228915 | 457830 |  | 686745 | 915660 | 1144575 | Number of consultations in the BL health facilities with improved access clean energy such as Solar powered fridges, Biogas etc. Consultation visits include OPD, ANC, PNC, SBA. Proportion of facilities with clean energy.
|  | Achieved |  |  | 272966 |  | TBD
Source:
Program reports/Supervison visits reports or assessment reports
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
Health facilities deliver quality reproductive maternal healthcare and nutrition services, including family planning, to women of childbearing age | Number of Better Lives supported health facilities providing contraceptive services | Planned | 24 | 74 | 34 | 44 | 44 | 54 | 64 | 74 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 25 | 36 | 61
Source:
DHIS2/HMIS
| Output Indicator 1.2 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy | Planned | 14938 | 76930 | 15386 | 31233 | 31233 | 46158 | 61544 | 76930 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 9308 | 8249 | 17557
Source:
DHIS2/HMIS
| Output Indicator 1.3 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Number of deliveries assisted by skilled birth attendants at Better Lives supported health facilities. | Planned | 28240 | 30423 | 28664 | 29094 | 29094 | 29530 | 29973 | 30423 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 19826 | 19789 | 39615
Source:
DHIS2/HMIS
| Output Indicator 1.4 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Number of women who received post-natal care (PNC) within 48 hours of childbirth. | Planned | 13721 | 14781 | 13927 | 14136 | 14136 | 14348 | 14563 | 14781 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 13035 | 12568 | 25603
Source:
DHIS2/HMIS
| Output Indicator 1.5 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Number of facility-based staff and community health care workers that are trained in Maternal and Newborn Care in the targeted Better Lives health facilities. | Planned | 55 | 500 | 100 | 100 | 100 | 100 | 100 | 100 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 46 | 50 | 96
Source:
Program reports/ Training reports/Supervison visits reports or assessment reports; UNICEF and partner project document reports; analysis during the quarterly review meetings; TPM verification exercises
IMPACT WEIGHTING (40%)
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
Health facilities deliver quality essential package of services to children under 5 | Dropout rate Pentavalant 1st dose to Pentavalent 3rd dose | Planned | 8.7% | 7.8% | 8.5% | 8.2% | 8.2% | 8% | 7.8% | 7.8% | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 9.9% | 8.1% | 8.469%
Source:
DHIS2/HMIS
| Output Indicator 2.3 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Number of children disaggregated by gender, aged 6-59, months with severe acute malnutrition who receive treatment. | Planned | 82896 | 257689 | 36344.5 | 36344.5 | 72689 | 37437 | 37437 | 37437
|  | Achieved |  |  | 45497 | 37556 | 83053
Source:
ONA/DHIS2
| Output Indicator 2.4 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Number of children (0-59 months) with diarrhoea treated with oral rehydration solution (ORS) and Zinc sulphate, disaggregated by age. (Gender will be incoperated after discussion with the government) | Planned | 19195 | 21193 | 19579 | 19970 | 39549 | 20370 | 20777 | 21193
|  | Achieved |  |  | 20776 | 14912 | 35688
Source:
DHIS2/HMIS
| Output Indicator 2.5 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Number of children 0-59 months with Pneumonia treated with Amoxicillin | Planned | 15308 | 64273 | 15615 | 15926 | 31541 | 16245 | 16570 | 16901
|  | Achieved |  |  | 15972 | 12112 | 28084
Source:
DHIS2/HMIS
IMPACT WEIGHTING (20%)
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
Health facilities deliver quality curative services | Number of people using OPD services at Better Lives supported health facilities (disaggregated by age and gender) | Planned | 247777 | 287241 | 255410 | 262867 | 518277 | 270753 | 278875 | 287241 | Work to extend coverage of essential services will bring them to vulnerable Somalis who would otherwise not receive them. Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity. Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change. Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments. Stimulating increased domestic commitment to financing and evidence-based policy at all levels will contribute to sustainability. Working more closely with Government, including possibly financing through Government systems, will contribute to sustainability and stability.
|  | Achieved |  |  | 272966 | 225106 | 498072
Source:
DHIS2/HMIS
| Output Indicator 3.2 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Proportion of health facilities with at least 80% availability of selected tracer medicines and medical supplies | Planned | 0% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
|  | Achieved |  |  | 70% | 70% | 74%
Source:
DHIS2/HMIS, may use eLMIS once rolled out
IMPACT WEIGHTING (10%)
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices | Number of primary caregivers of children aged 0-23 months who received IYCF counselling | Planned | 212003 | 157948 | 153487 | 153487 | 306974 | 157947.5 | 157947.5 | 157947.5 | Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity.
|  | Achieved |  |  | 183379 | 127154 | 310533
Source:
ONA/DHIS2
| Output Indicator 4.2 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Proportion of women interviewed in ANC who know at least three danger signs of newborn complications | Planned |  | N/A | 4825 | 4825 | 5416 |  |  |  | Improving quality of care and tackling other barriers to uptake will increase utilisation of services and positive impact. Increased utilisation of quality care will reduce preventable death and morbidity.
|  | Achieved |  |  |  |  | 112%
Source: FCDO run Third party monitoring exercise (Dec 2024 to March 2025)
This will be done through quick assessment, it can also be report on the supervision visits if we include in our questionaire
IMPACT WEIGHTING (5%)
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
Enhanced reporting and supervision of service delivery | Proportion of facilities submitting timely and complete HMIS reports in the DHIS II (RMNCH Form completeness) | Planned | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | Building core health system elements including government stewardship will strengthen value for money of delivery over the long-term. Strengthening district and community systems (not just national level) will increase resilience of investments.
|  | Achieved |  |  | 96% | 96% | 96%
Source:
DHIS2/HMIS
| Output Indicator 5.2 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| Number of joint supportive supervision visits conducted in the supported facilities, between the MoH, UNICEF and implementing partners. | Planned | 2 | 10 | 2 | 2 | 4 | 2 | 2 | 2
|  | Achieved |  | 1 | 1 | 2 | 6
Source:
Program reports/Supervison visits reports or assessment reports
IMPACT WEIGHTING (15%) | Output Indicator 5.3 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026)
| % of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits | Planned | 0 | 90% | 70% | 75% | 75% | 80% | 85% | 90%
|  | Achieved |  |  | 70% | 75% | 75%
Source:
Program reports/Supervison visits reports or assessment reports
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
Support to improving climate resilience of health services delivered | Output Indicator 6.1 |  | Baseline | Target (National )- EOP 2026 | Milestone-1 (Apr - Sept 2024) | Milestone-2 (Oct 2024 - March 2025) | Review Period (Milestone 1 and Milestone 2) (April 2024 - March 2025) | Milestone-3 (Apr - Sept 2025) | Milestone-4 (Oct 2025 - March 2026) | Milestone-5 (Apr - Sept 2026) | Assumptions
| Number of health care facilities assessed and provided with climate resilient energy support | Planned | 0 | 87 | 31 | 43 | 43 | 73 | 80 | 87 | Health systems that focus on reducing overall vulnerability and developing specific system capacities are more resilient to climate change.
|  | Achieved |  |  | 31 | 43 | 43
Source:
DHIS2/HMIS; UNICEF and partner specific reports
IMPACT WEIGHTING (10%)
INPUTS (£) | FCDO (£) |  | Govt (£)
INPUTS (HR) | FCDO (FTEs)
Most updated LF as from 01 November 2024
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: April 2022 - March 2023
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Impact not mandated for UNICEF
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: World Bank Group
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UN Estimate
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partner to provide the catchment population for facilities during the revision
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This indicator will be reported at district level using the district catchment population and the district new OPD visits
Note on B69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: yearly increase of 3% across the milestones and look at trends
Note on B74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as ANC-1
Note on B79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as ANC-1
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fadumo to provide total number of staff
Note on B144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires a survey or a rapid assessment, no data available

## Logframe Partners (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
BETTER LIVES FOR SOMALI WOMEN AND CHILDREN LOGICAL FRAMEWORK - APRIL 2024 - MARCH 2025
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | [7 empty] | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Improved health and nutrition status for vulnerable Somalis | Maternal mortality ratio/Institutional Maternal mortality ration | Planned | 690
Achieved
Source:
| Impact Indicator 2 |  | Baseline | [7 empty] | Milestone 1 | Milestone 2 | Target (date)
| Under five mortality rate/Institutional Child Mortality Rate in Facility | Planned | 117
Achieved
Source:
| Impact Indicator 3 |  | Baseline | [7 empty] | Milestone 1 | Milestone 2 | Target (date)
| Severe Acute Malnutrition Rate/ – proportion of discharged children who recovered from SAM treatment in OTP/SC | Planned | 15.4
Achieved
Source:
OUTCOME | Outcome Indicator 1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
OUTCOME A: Improved access to, and use of, quality essential health and nutrition services | % of women in catchment areas supported by Better Lives using modern contraception. | Planned
Achieved
Source:
DHIS2/HMIS
| Outcome Indicator 2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date)
| Proportion of antenatal clients seen for the 4th visit by skilled personnel, of estimated pregnant population in catchment areas of Better Lives supported facilities/ ANC-4th visit coverage | Planned
Achieved
Source:
DHIS2/HMIS
| Outcome Indicator 3 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date)
| Skilled attendance at birth - % of deliveries in Better Lives supported areas attended by skilled health personnel./Skilled birth attendant delivery rate | Planned
Achieved
Source:
DHIS2/HMIS
| Outcome Indicator 4 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date)
| proportion of children in catchment areas of Better Lives supported facilities vaccinated with the third dose of pentavalent vaccine/Pentavalent 3rd dose coverage (0 - 11 m) | Planned
Achieved
Source:
DHIS2/HMIS
| Outcome Indicator 5 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date)
| Severe acute malnutrition – proportion of discharged children who recovered from SAM treatment in OTP/SC | Planned
Achieved
Source:
ONA/DHIS2
| Outcome Indicator 6 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date)
| Proportion of population in the catchment areas of Better Lives supported facilities using OPD services. | Planned
Achieved
Source:
DHIS2/HMIS
OUTCOME | Outcome Indicator 1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
OUTCOME B: Improve climate resilience of health system | Number of people served by health facilities with improved access to clean energy(ICF2) | Planned
Achieved
Source:
Program reports/Supervison visits reports or assessment reports
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Mudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Health facilities deliver quality reproductive maternal healthcare and nutrition services, including family planning, to women of childbearing age | Number of Better Lives supported health facilities providing contraceptive services | Planned
Achieved
Source:
DHIS2/HMIS
| Output Indicator 1.2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (mudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of antenatal clients seen for the 1st visit before 12 weeks of pregnancy | Planned
Achieved
Source:
DHIS2/HMIS
| Output Indicator 1.3 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Mudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of deliveries assisted by skilled birth attendants at Better Lives supported health facilities. | Planned
Achieved
Source:
DHIS2/HMIS
| Output Indicator 1.4 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Mudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of women who received post-natal care (PNC) within 48 hours of childbirth. | Planned
Achieved
Source:
DHIS2/HMIS
| Output Indicator 1.5 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of facility-based staff and community health care workers that are trained in Maternal and Newborn Care in the targeted Better Lives health facilities. | Planned
Achieved
Source:
Program reports/ Training reports/Supervison visits reports or assessment reports
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Mudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Health facilities deliver quality essential package of services to children under 5 | Dropout rate Pentavalant 1st dose to Pentavalent 3rd dose | Planned | 8.7% | 8.5% | 8.7% | 5% | 4.5% | 5% | 7.8% | 8.1%
Achieved
Source:
DHIS2/HMIS
| Output Indicator 2.3 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of children disaggregated by gender, aged 6-59, months with severe acute malnutrition who receive treatment. | Planned | 82.896
Achieved
Source:
ONA/DHIS2
| Output Indicator 2.4 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of children (0-59 months) with diarrhoea treated with oral rehydration solution (ORS) and Zinc sulphate, disaggregated by age. (Gender will be incoperated after discussion with the government) | Planned
Achieved
Source:
DHIS2/HMIS
| Output Indicator 2.5 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of children 0-59 months with Pneumonia treated with Amoxicillin | Planned
Achieved
Source:
DHIS2/HMIS
IMPACT WEIGHTING (%)
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Health facilities deliver quality curative services | Number of people using OPD services at Better Lives supported health facilities (disaggregated by age and gender) | Planned | 272562 | 299818 | 43894 | 127930 | 57081 | 59634 | 53325 | 93518
Achieved
Source:
DHIS2/HMIS
| Output Indicator 3.2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Proportion of health facilities with at least 80% availability of selected tracer medicines and medical supplies | Planned | 0% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
Achieved
Source:
DHIS2/HMIS, may use eLMIS once rolled out
| Output Indicator 3.3 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Proportion of targeted health facilities with appropriate staffing complement and staff available | Planned
Achieved
Source:
Program reports/Supervison visits reports or assessment reports
IMPACT WEIGHTING (%)
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Parents, caregivers, children, and pregnant women receive support intended to enhance healthcare practices | Number of primary caregivers of children aged 0-23 months who received IYCF counselling | Planned | 209.757
Achieved
Source:
ONA/DHIS2
| Output Indicator 4.2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Proportion of women interviewed in ANC who know at least three danger signs of newborn complications | Planned | 0
Achieved
Source:
This will be done through quick assessment, it can also be report on the supervision visits if we include in our questionaire
IMPACT WEIGHTING (%)
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Enhanced reporting and supervision of service delivery | Proportion of facilities submitting timely and complete HMIS reports in the DHIS II (RMNCH Form completeness) | Planned | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
Achieved
Source:
DHIS2/HMIS
| Output Indicator 5.2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of joint supportive supervision visits conducted in the supported facilities, between the MoH, UNICEF and implementing partners. | Planned | 0
Achieved
Source:
Program reports/Supervison visits reports or assessment reports
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| % of Better Lives supported facilities that have implemented recommendations from the previous integrated supportive supervision visits | Planned | 0
Achieved
Source:
Program reports/Supervison visits reports or assessment reports
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Support to improving climate resilience of health services delivered | Percentage of energy requirements of all supported health care facilities that are met by electricity generated from renewable (solar) energy source | Planned | 0
Achieved
Source:
DHIS2/HMIS
| Output Indicator 6.2 |  | Baseline | Target (National ) | Target (BRA ) | Target (Gedo ) | Target (Galgadud ) | Target (Galmudug ) | Target (Awdal ) | Target (Togdher ) | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number of health care facilities assessed and provided with climate resilient energy support | Planned | 0
Achieved
Source:
DHIS2/HMIS
IMPACT WEIGHTING (%)
INPUTS (£) | FCDO (£) |  | Govt (£) | [7 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: April 2022 - March 2023

## Catchment Population
GPS coordinates
S/N | Region | District | Name of the facility | Longitude | Latitude | PESS District population at Facility catchment | PESS District population at BL Facility catchment | Under-1 catchment Population (3.8%) | Under-5 catchment population (18%) | Estimated catchment Pregnant women (4.5%) | Expected Live births in the catchment (4%) | WCBA catchment population (22%)
1 | Awdal | Borama | Central HC | 43.182 | 9.9363 | 35186 | 15833 | 601 | 2849 | 712 | 633 | 3483
2 | Awdal | Borama | Shifo HC | 43.1846 | 9.9311 | 22650 | 10192 | 387 | 1834 | 458 | 407 | 2242
3 | Awdal | Borama | Sheed Dheer HC | 43.1793 | 9.929 | 21471 | 9661 | 367 | 1738 | 434 | 386 | 2125
4 | Awdal | Borama | Qoorgaab HC | 43.1952 | 9.9338 | 38764 | 17443 | 662 | 3139 | 784 | 697 | 3837
5 | Awdal | Borama | SH Ali Jawhar HC | 43.1925 | 9.9473 | 35251 | 15862 | 602 | 2855 | 713 | 634 | 3489
6 | Awdal | Borama | Sh. Osman HC | 43.1707 | 9.9485 | 19858 | 8936 | 339 | 1608 | 402 | 357 | 1965
7 | Awdal | Borama | Borama Hospital | 43.1803 | 9.9367 | 379199 | 170639 | 6484 | 30715 | 7678 | 6825 | 37540
8 | Awdal | Borama | Idhanka HC | 43.3032 | 9.6948 | 29913 | 13460 | 511 | 2422 | 605 | 538 | 2961
9 | Awdal | Borama | Quljeed HC | 43.0109 | 10.0895 | 24738 | 11132 | 423 | 2003 | 500 | 445 | 2449
10 | Awdal | Borama | Boon HC | 43.0878 | 10.1948 | 30407 | 13683 | 519 | 2462 | 615 | 547 | 3010
11 | Awdal | Zeila | Hariirad HC | 42.8432 | 10.3272 | 14723 | 6625 | 251 | 1192 | 298 | 265 | 1457
12 | Awdal | Zeila | Abdikadir HC | 42.8917 | 10.5096 | 5599 | 2519 | 95 | 453 | 113 | 100 | 554
13 | Awdal | Zeila | Jidhi HC | 43.0681 | 10.6209 | 4973 | 2237 | 85 | 402 | 100 | 89 | 492
14 | Awdal | Zeila | Fiqi Adan HC | 43.1939 | 10.3744 | 6281 | 2826 | 107 | 508 | 127 | 113 | 621
15 | Awdal | Zeila | Zeila Hospital | 43.4762 | 11.3548 | 43532 | 19589 | 744 | 3526 | 881 | 783 | 4309
16 | Awdal | Zeila | Lowyo'ado HC | 43.2579 | 11.4592 | 5933 | 2669 | 101 | 480 | 120 | 106 | 587
17 | Togdheer | Buroa | Aden Saleban Health Center | 45.5774 | 9.5224 | 26595 | 11967 | 454 | 2154 | 538 | 478 | 2632
18 | Togdheer | Buroa | Bali-Dhig Health Center | 45.9142 | 8.3686 | 14319 | 6443 | 244 | 1159 | 289 | 257 | 1417
19 | Togdheer | Buroa | Burao Central Health Center | 45.5376 | 9.5238 | 23676 | 10654 | 404 | 1917 | 479 | 426 | 2343
20 | Togdheer | Buroa | Burao General Hospital | 45.5372 | 9.5344 | 412543 | 185644 | 7054 | 33415 | 8353 | 7425 | 40841
21 | Togdheer | Buroa | Caqil Yare Health Center | 45.5363 | 9.5618 | 8142 | 3663 | 139 | 659 | 164 | 146 | 805
22 | Togdheer | Buroa | Dhagah-Dher Health Center | 45.7684 | 8.4163 | 6871 | 3091 | 117 | 556 | 139 | 123 | 680
23 | Togdheer | Buroa | Dhoqoshay Health Center | 45.718 | 8.5136 | 11641 | 5238 | 199 | 942 | 235 | 209 | 1152
24 | Togdheer | Buroa | Dr. Alag Health Center | 45.5243 | 9.526 | 25799 | 11609 | 441 | 2089 | 522 | 464 | 2553
25 | Togdheer | Buroa | Dr. Yusuf Health Center | 45.5444 | 9.5115 | 23101 | 10395 | 395 | 1871 | 467 | 415 | 2286
26 | Togdheer | Buroa | Druqsi Health Center | 45.4616 | 8.5171 | 16240 | 7308 | 277 | 1315 | 328 | 292 | 1607
27 | Togdheer | Buroa | Gebo gebo Health Center | 45.8908 | 9.7993 | 9206 | 4142 | 157 | 745 | 186 | 165 | 911
28 | Togdheer | Buroa | Haradagubatoxiil Health Center | 45.4651 | 8.7816 | 11258 | 5066 | 192 | 911 | 227 | 202 | 1114
29 | Togdheer | Buroa | Kosar Health Center | 45.5211 | 9.5799 | 8621 | 3879 | 147 | 698 | 174 | 155 | 853
30 | Togdheer | Buroa | Nasiye Health Center | 45.6354 | 8.7518 | 7467 | 3360 | 127 | 604 | 151 | 134 | 739
31 | Togdheer | Buroa | Qoryale Health Center | 45.968 | 9.0654 | 17065 | 7679 | 291 | 1382 | 345 | 307 | 1689
32 | Togdheer | Buroa | Riyo xidho health Center | 45.968 | 9.0654 | 6850 | 3082 | 117 | 554 | 138 | 123 | 678
33 | Togdheer | Buroa | Shansha-Ade Health Center | 45.5991 | 8.474 | 10209 | 4594 | 174 | 826 | 206 | 183 | 1010
34 | Togdheer | Buroa | War-Ibran Health Center | 45.8924 | 8.8006 | 11895 | 5352 | 203 | 963 | 240 | 214 | 1177
35 | Togdheer | Buroa | Yirowe Health Center | 45.8924 | 8.8006 | 21477 | 9664 | 367 | 1739 | 434 | 386 | 2126
36 | Togdheer | Odweine | Abdi Farah HC | 44.9867 | 9.188 | 5683 | 2557 | 97 | 460 | 115 | 102 | 562
37 | Togdheer | Odweine | Haji Salah Health Center | 45.2415 | 8.59 | 8676 | 3904 | 148 | 702 | 175 | 156 | 858
38 | Togdheer | Odweine | Jameecaad Health Centre | 45.2849 | 9.2385 | 5732 | 2579 | 98 | 464 | 116 | 103 | 567
39 | Togdheer | Odweine | Odwayne Health Center | 45.0636 | 9.407 | 9352 | 4208 | 159 | 757 | 189 | 168 | 925
40 | Togdheer | Odweine | Odwayne Hospital | 45.0645 | 9.4083 | 65841 | 29628 | 1125 | 5333 | 1333 | 1185 | 6518
41 | Gedo | Beled Hawa | Belet Hawa District Hospital | 41.8766 | 3.9562 | 57627 | 25932 | 985 | 4667 | 1166 | 1037 | 5705
42 | Gedo | Beled Hawa | Beled Hawa HC | 41.8755 | 3.9302 | 25757 | 11590 | 440 | 2086 | 521 | 463 | 2549
43 | Gedo | Beled Hawa | Belet Hawa Outreach | 41.8755 | 3.9302 | 21104 | 9496 | 360 | 1709 | 427 | 379 | 2089
44 | Gedo | Beled Hawa | Belet Amin PHU | 41.8939 | 3.9562 | 8391 | 3775 | 143 | 679 | 169 | 151 | 830
45 | Gedo | Dollow | Dollow District Hospital | 42.079 | 4.1642 | 25828 | 11622 | 441 | 2091 | 522 | 464 | 2556
46 | Gedo | Dollow | Gedweyne HC | 42.3064 | 4.0233 | 18909 | 8509 | 323 | 1531 | 382 | 340 | 1871
47 | Gedo | Dollow | Dollow Outreach | 42.079 | 4.1642 | 8678 | 3905 | 148 | 702 | 175 | 156 | 859
48 | Gedo | Garbaharey | Garbaharrey District Hospital | 42.2153 | 3.3313 | 69794 | 31407 | 1193 | 5653 | 1413 | 1256 | 6909
49 | Gedo | Garbaharey | Garbaharrey HC | 42.2154 | 3.331 | 19544 | 8794 | 334 | 1582 | 395 | 351 | 1934
50 | Gedo | Garbaharey | Garbaharrey Outreach Team | 42.2153 | 3.3313 | 22278 | 10025 | 380 | 1804 | 451 | 401 | 2205
51 | Gedo | Luuq | Luuq District Hospital | 42.5446 | 3.8003 | 29659 | 13346 | 507 | 2402 | 600 | 533 | 2936
52 | Gedo | Luuq | Akara HC | 42.9229 | 4.3164 | 70647 | 31791 | 1208 | 5722 | 1430 | 1271 | 6994
53 | Gedo | Luuq | Usbo HC | 42.6664 | 4.0466 | 10941 | 4923 | 187 | 886 | 221 | 196 | 1083
54 | Gedo | Luuq | Luuq Outreach | 42.9229 | 4.3164 | 11667 | 5250 | 199 | 945 | 236 | 210 | 1155
55 | Gedo | Luuq | Abow PHU | 42.5303 | 3.8806 | 3502 | 1575 | 59 | 283 | 70 | 63 | 346
56 | Benadir | SHINGANI | Shangani Referral HC | 45.3461 | 2.0353 | 30887 | 13899 | 528 | 2501 | 625 | 555 | 3057
57 | Benadir | DEYNILE | Deynille District Hosp | 45.2875 | 2.1286 | 52877 | 23794 | 904 | 4282 | 1070 | 951 | 5234
58 | Benadir | DEYNILE | Isse Abdi HC | 45.3307 | 2.0836 | 9937 | 4471 | 169 | 804 | 201 | 178 | 983
59 | Benadir | DEYNILE | Kulmiye HC | 45.2513 | 2.0787 | 8594 | 3867 | 146 | 696 | 174 | 154 | 850
60 | Benadir | DEYNILE | Forilow HC | 45.2513 | 2.0788 | 6731 | 3028 | 115 | 545 | 136 | 121 | 666
61 | Benadir | HODON | Hodan HC | 45.3151 | 2.0491 | 17821 | 8019 | 304 | 1443 | 360 | 320 | 1764
62 | Benadir | HODON | October HC | 45.318 | 2.0364 | 14276 | 6424 | 244 | 1156 | 289 | 256 | 1413
63 | Galgadud | Dhusamareb + Guriel | Dayah Hospital | 46.3758 | 5.5452 | 82931 | 37318 | 1418 | 6717 | 1679 | 1492 | 8209
64 | Galgadud | Dhusamareb + Guriel | Isterlin Hospital | 45.8701 | 5.3042 | 74483 | 33517 | 1273 | 6033 | 1508 | 1340 | 7373
65 | Galgadud | Dhusamareb + Guriel | Bohol HC | 46.3691 | 5.9213 | 11379 | 5120 | 194 | 921 | 230 | 204 | 1126
66 | Galgadud | Dhusamareb + Guriel | Marergur HC | 46.5123 | 5.751 | 9713 | 4370 | 166 | 786 | 196 | 174 | 961
67 | Galgadud | Dhusamareb + Guriel | Gadoon HC | 46.676 | 5.6925 | 13965 | 6284 | 238 | 1131 | 282 | 251 | 1382
68 | Galgadud | Dhusamareb + Guriel | Eldhere HC | 46.5286 | 5.4723 | 8348 | 3756 | 142 | 676 | 169 | 150 | 826
69 | Galgadud | Dhusamareb + Guriel | Faragoye HC | 46.5285 | 5.472 | 4208 | 1893 | 71 | 340 | 85 | 75 | 416
70 | Mudug | Hobyo | Hobyo District Hospital | 48.525 | 5.3504 | 55611 | 25024 | 950 | 4504 | 1126 | 1000 | 5505
71 | Mudug | Hobyo | Wisil HC, | 48.1287 | 5.4259 | 52701 | 23715 | 901 | 4268 | 1067 | 948 | 5217
72 | Mudug | Hobyo | Elgula HC | 47.8514 | 6.0137 | 11203 | 5041 | 191 | 907 | 226 | 201 | 1109
73 | Mudug | Hobyo | Eldibir HC | 48.3497 | 5.8872 | 14150 | 6367 | 241 | 1146 | 286 | 254 | 1400
74 | Mudug | Hobyo | Gawan HC | 48.2981 | 5.3107 | 8499 | 3824 | 145 | 688 | 172 | 152 | 841
75 | Mudug | Hobyo | Bud-BuD HC | 48.6855 | 6.1741 | 17066 | 7679 | 291 | 1382 | 345 | 307 | 1689
76 | Mudug | Hobyo | Hero-dhagahley HC | 48.2408 | 5.5783 | 7387 | 3324 | 126 | 598 | 149 | 132 | 731
77 | Mudug | Hobyo | Bajela HC | 47.7051 | 5.7894 | 7749 | 3487 | 132 | 627 | 156 | 139 | 767
78 | Mudug | Hobyo | qaranrow HC | 47.4888 | 5.7905 | 5194 | 2337 | 88 | 420 | 105 | 93 | 514
79 | Mudug | Hobyo | Barak Ciise |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Galgadud | Abudwak | Abudwak District Hsopital | 46.2262 | 6.2396 | 72029 | 32413 | 1231 | 5834 | 1458 | 1296 | 7130
81 | Galgadud | Abudwak | Dhabat HC | 46.4601 | 6.4344 | 7269 | 3271 | 124 | 588 | 147 | 130 | 719
82 | Galgadud | Abudwak | Wabari HC | 46.2142 | 6.259 | 3440 | 1548 | 58 | 278 | 69 | 61 | 340
83 | Galgadud | Abudwak | Bangele HC | 46.3125 | 6.0841 | 9524 | 4285 | 162 | 771 | 192 | 171 | 942
84 | Galgadud | Balanbale | Balanable General Hospital | 45.7565 | 5.7633 | 21000 | 9450 | 359 | 1701 | 425 | 378 | 2079
85 | Galgadud | Balanbale | Elasha HC | 45.8504 | 6.0744 | 7015 | 3156 | 119 | 568 | 142 | 126 | 694
86 | Galgadud | Balanbale | Turbi HC | 45.6917 | 5.9265 | 3108 | 1398 | 53 | 251 | 62 | 55 | 307
87 | Galgadud | Balanbale | Barwaqo HC | 45.6061 | 5.7973 | 3336 | 1501 | 57 | 270 | 67 | 60 | 330
[6 empty] | 2543494 | 1144532 | 43451 | 205975 | 51459 | 45738 | 251759