Contribution Arrangement Amendment Letter

Project Name: Improving access to quality basic health and nutrition services for vulnerable populations including those affected by drought and emergencies.

FCDO Project Number: 300857-402, this has changed from 300857-104 in the original Contribution Arrangement.

HERA Purchase Order Number PUR1065234

UNICEF Grant Number: SC230521

I refer to the Contribution Arrangement between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and UNICEF signed on 29 September 2023 and subsequently amended on 30 October 2023 (Amendment No. 001/2023) and on 25 November 2024 (Amendment No. 002/2024).

1. Following recent correspondence, FCDO proposes to decrease the amount made available to UNICEF by £4,092,392 (Four Million, Ninety Two Thousand, Three Hundred Ninety Two, pounds sterling).
2. I propose that the figures £43,039,881.00 (Forty Three Million, Thirty Nine Thousand, Eight Hundred Eighty One pounds sterling) in paragraph 3. of Amendment No. 002/2024 to be deleted and replaced with £38,947,489.00 (Thirty Eight Million, Nine Hundred Forty Seven Thousand, Four Hundred Eighty Nine, pounds sterling)
3. I further propose amendment of below section 1(b) of the original Contribution Arrangement dated 29th September 2023.
1(b) Start/End Dates:	Project Dates – 1 October 2023 – 31 December 2026 as per below schedule.

Implementation Dates 1 October 2023 – 30 September 2026

Project Close-out period (no activities): 1 October 2026 - 31st December 2026

To be deleted and replaced with:

1(b) Start/End Dates:	Project Dates – 1 October 2023 – 30 June 2026 as per below schedule.

Implementation Dates 1 October 2023 – 31 March 2026

Project Close-out period: 1 April 2026 - 30 June 2026

In accordance with the reporting requirements set out in Section 2, paragraph 12.2 of the UNICEF–FCDO Framework Arrangement signed on 3 February 2015, UNICEF shall submit a final report summarizing programme performance and results, together with provisional financial information, no later than three months following the completion or termination of this Arrangement (30 September 2026).

I propose that the activities under this arrangement also include procurement of nutrition supplies and vaccines in line with the concept note attached in Annex 1.

1. This letter of amendment will place on record our common understanding of the above change(s) and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 003/2026.
2. Please sign both copies of this letter, return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of UNICEF
Name:
Position:
Address/Contact Details:
Date:

Annex 1:

Concept Note from UNICEF Somalia to the
Foreign, Commonwealth and Development Office (FCDO)

Overview

Priority Area: Health and Nutrition

Sub-Priority Area: Strengthening the health and nutrition program in Somalia by reaching un-vaccinated and malnourished children.

Project Duration: 2025/2026

Geographic Coverage: National including Jubaland, Southwest, Banadir, Hirshabelle, Galmudug, Northeast, Puntland and Somaliland States of Somalia

Focus Population: 180,000 children under 15 months and 25000 SAM children under five years.

Background

UNOCHA estimates that over 3.5 million people are internally displaced with many children and women facing multiple risks, including malnutrition, and contracting vaccine-preventable diseases such as measles. The recurrence of vaccine-preventable underlines the immunity gaps that Somali children face due to a fragile health system, low routine vaccination coverage, gaps in the provision of primary health services and insecurity that hinders access to children and communities living under insurgent-controlled areas. As per WUENIC, Somalia has approximately 1.5 million zero-dose children and the country has so far reached approached 63% of them by implementing 3 rounds of the Big Catch-Up initiative. Though the under-5 mortality has been on a downward trend, it remains disproportionately high, and Somalia has one of the highest under-five mortality rates in the world— at 104 per 1,000 live-births per the 2023 UN Inter-agency Group for Child Mortality Estimates IGME). Vaccine-preventable diseases remain among the main causes of the under-5 mortality with malnutrition as the underlying cause.

Main objective:

To contribute to the reduction of morbidity and mortality of children in Somalia that is due malnutrition and vaccine-preventable diseases.

Specific objective:

To ensure timely availability of essential nutrition supplies, especially the RUTF for management of severe wasting and avoid disruptions in service delivery in early 2026.

To ensure availability of traditional vaccines to immunise at least 95% of children from 0-11 months with measles vaccination and other life-saving vaccines as per the national immunisation schedule.