## Annual Review Template

Title: Somalia Security and Justice Programme II
Programme Value £ (full life): £28.5m approved over 5 years and up to £54m over 8 years subject to further approvals		Review date:
Programme Code: 300860	AMP start date: 08/10/2021	AMP end date: 31/03/2029

Summary of Programme Performance
Year	2022	2023		2024	2025
Overall Output Score	A	A		B	A
Risk Rating	Severe	Severe		Severe	Severe
DevTracker Link to Business Case:			https://iati.fcdo.gov.uk/iati_documents/D0005061.odt
DevTracker Link to results framework:			https://iati.fcdo.gov.uk/iati_documents/D0005057.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
The Security and Justice Programme II (SSJP) is part of the UK’s wider effort in Somalia to

1. Reduce current and future threats to U.K. interests
2. Enable Somalis to lead safer, healthier, and less vulnerable lives
3. Support prosperity
4. Reduce risks to stability across East Africa
The SSJPII seeks to advance the rule of law and ensure safety and security for all citizens through inclusive security and justice initiatives that reinforce the social contract and support an inclusive and enduring political settlement.

It was envisaged that this would be achieved under SSJP II by (i) improving political, legal and financial frameworks, (ii) moving institutional cultures towards listening to the public and collaboration so that people’s expectations are better met by their duty bearers, and (iii) shifting social norms so that the processes of engagement and response reinforce inclusive approaches to the rule of law.

For the review period (July 2024 to June 2025), the primary component of SSJP II was the Nabadaynta Soomaaliya programme (aka ‘Nabadaynta’ in this annual review), managed by the International Organization for Migration (IOM). The previous annual review included analysis of the Rapid Stabilisation Support (RSS) programme, which will be assessed alongside the ISF stabilisation annual review. The Nabadaynta programme is jointly funded by the UK and the European Union, while the Netherlands, one of the original donors, withdrew from the programme in September 2024 due to internal ODA reductions. Additionally, during this period, SSJPII financed the Joint Police Programme II (JPP), whose results will be evaluated in the next review.

At the time of writing this annual review, FCDO Somalia confirmed its decision to close the Nabadaynta programme at the end of the current financial year. This aligns with the four-year break point outlined in the original SSJPII Business Case, which runs until 2029. The decision reflects significant reductions in FCDO Somalia’s ODA allocation for 2026/27 onwards, following the UK’s shift to allocating 0.3% of GNI to ODA.”

FCDO Somalia plans to design a new programme that builds on the existing UK-funded, IOM-led stabilisation and early recovery initiative (currently financed by ISF) and integrates elements of the community-centred security approaches delivered through Nabadaynta. Consequently, this review provides recommendations for both Nabadaynta and the forthcoming programme, which is expected to launch in April 2026.”

Nabadaynta has undergone significant changes from its original delivery structure. The most notable shifts include the replacement of UNOPS by IOM as fund manager in mid-2023 and the removal of half the implementing partners (IP1 – ASAL/Saferworld) in late 2024. While these changes were detailed in the 2023/24 Annual Review, their scale and impact have left programme delivery and progress toward the outcomes in the original Business Case and Terms of Reference off-track, due to factors beyond the control of IOM or the remaining implementing partners

In September 2024, IOM submitted a revised programme strategy to reflect these changes and updated the monitoring framework accordingly, which donors subsequently approved. While this adaptation has complicated the assessment of broader strategic shifts against the original framework, FCDO Somalia determine that it is the most appropriate and fair way to track progress during this reporting year. Overall, the programme received an ‘A’ score for the 2024/25 annual review, due to a strong performance and delivery against the adapted criteria agreed by donors. However, the annual review team is concerned that changes to the original monitoring structure have limited the ability to fully assess progress toward the business case outcomes. This limitation must be documented in the final Programme Completion Report, due in 2026.

Summary supporting narrative for the overall score in this review
The 2024 annual review highlighted slow progress, it said “IOM must swiftly address the challenges flagged to unlock the potential and focus on delivery.” In response, IOM was tasked with developing a revised programme approach and a simplified results framework to better reflect the realities of the operating environment and to enable more agile and context-responsive delivery. IOM responded well to this request submitting a revised strategic approach and streamlined monitoring framework to donors at the end of 2024.

Over the review period, the programme showed significant improvement in delivery. IOM’s renewed strategy, endorsed by donors at the end of 2024, created a more coherent and effective delivery chain. Activities were tailored to local contexts and expanded into two new districts Dollow and Xudur with a strong focus on community engagement and inclusive approaches to security and justice. Key achievements include the successful implementation of inclusive security sector governance and accountability initiatives, such as ‘town halls’ in Baidoa and Kismayo, which increased government participation and strengthened public confidence. These efforts particularly benefited marginalised groups through initiatives like media partnerships and radio programming.

Monitoring, Evaluation, and Learning (MEL) systems have improved, with more sophisticated, triangulated, and nuanced reporting at both output and outcome levels. Most revised milestones have been met or exceeded, reflecting a year of positive delivery and demonstrating the programme’s ability to adapt and perform under challenging circumstances. While the simplification of the results framework has made milestone achievement more attainable, indicators selected are more activity-based than outcome-focused. It has helped ensure the programme remained viable and measurable in a highly complex and volatile context. The use of perception surveys, while resource-intensive and potentially subject to bias, has added additional insight into community-level impact.

It is important to acknowledge that the programme continues to operate in an extremely challenging environment. The focus areas, Baidoa, Xudur, Kismayo, and Dollow, have experienced significant political instability, security threats (including from Al-Shabaab), and inter-clan tensions. These dynamics, coupled with resource constraints and the limited capacity of formal institutions, have inevitably affected the pace and scale of delivery. However, the programme has shown resilience and adaptability, and the current trajectory suggests a stronger foundation for future impact.

Given the improvements in delivery, the achievement of revised milestones, and the programme’s ability to navigate a complex and shifting context, the programme is assessed as meeting expectation ‘A’ for this review period. While recognising the need for continued focus on strategic clarity, sustainability, and outcome-level impact as the programme transitions into its final phase and informs the design of a successor initiative.

Reviewers’ concerns and considerations
Despite the improved performance and milestone delivery, the review team identified several areas of concern that warrant attention:

Simplification of the results framework: The revised framework includes indicators that are largely activity-based (e.g. number of interventions or production of case studies), which may not fully capture the depth of outcome-level change. This raises questions about the robustness of the evidence base for assessing long-term impact. Moving forward, a clarification of the links between programme outputs and outcomes, will allow both the results Mapping and the Case Studies to describe progress towards the intended outcomes. Additional indicators should be added to ensure evidence that supports outcome level change is captured.

Sustainability and outcome-level progress: After three years of implementation, the programme’s contribution to sustainable improvements in addressing locally identified security and justice issues remains limited, due to the strategic delivery issues mentioned above. There is low confidence in the programme’s ability to achieve the outcomes as drafted in the original business case (2020-2029) within the remaining phase1 timeframe. This needs to be considered if the programme is extended beyond March 2026.

- Contextual volatility and overly optimistic goals: Contextual volatility and overly optimistic assumptions have significantly affected delivery. The business case anticipated that Somalia would avoid a sharp decline into protracted political and communal violence, a projection that has proven unrealistic. The operating environment, particularly in Baidoa, Xudur, and Dollow, remains highly volatile, marked by ongoing conflict, political instability, and institutional fragility. These factors continue to constrain the programme’s ability to deliver at scale and pace. Each SSJPII/Nabadaynta operating area is deeply affected by violence and displacement, driven by Al-Shabaab and entrenched clan and sub-clan tensions that shape Somalia’s fragile political landscape. During the review period, for example, AS mounted an armed assault on Baidoa (repelled largely by Ethiopian National Defence Forces), while the FGS and Jubaland FMS leadership engaged in direct confrontation, including an armed stand-off in Dollow in late July, as both sides competed for control of key districts
- Assumptions of external stakeholders: Some assumptions in the Business Case about stakeholder capacity proved unrealistic. Federal Member States faced severe resource constraints and political economy challenges, which limited the functionality of formal institutions, including the FMS ministries supported by Nabadaynta. Capacity gaps and internal politics often hampered delivery. The business case also assumed that complementary programmes would start in 2023 to reinforce Nabadaynta’s activities and outcomes. The Joint Police Programme (UNDP), a key component in the theory of change, was delayed and only launched in 2025.
- Delayed reset and implementation lag: Although the programme is now on a stronger footing, the reformulation of the project and rebuilding a complex but cohesive delivery team only took place during the review period. This delayed reset has meant that the programme is still catching up on the ambitions set out in the original business case. Together, the contextual factors mean that programme progress in the context is constantly challenging. The depth and breadth of the hurdles mean that any positive changes will take considerable expertise, patience and time (on the demand-side, the supply-side and the dynamics between them), as the original business case recognised.

Strategic clarity and future direction: The review highlighted the need for greater clarity on the overarching strategy for security and justice programming in Somalia. These strategic considerations, including the implications of reduced ODA and the decision not to extend Nabadaynta beyond March 2026, will need to be addressed in more detail in the forthcoming Project Completion Review (PCR).
These concerns do not negate the progress made this year but underscore the importance of maintaining momentum, ensuring strategic alignment, and embedding sustainability and outcome-orientation in the final phase of implementation and in the design of any successor programme.

Major lessons from the reporting period and recommendations
Effectiveness in Somalia’s complex, politically sensitive environment requires time, trust-building, and adaptive management. This year’s progress shows that with a coherent delivery chain and strong local engagement; meaningful results are achievable even in volatile contexts. Partners managed local sensitivities well, maintaining transparency and building buy-in despite challenges. Expansion into new districts and inclusive engagement underscore the value of sustained commitment.
However, the revised results framework underrepresents how community priorities are addressed. Making this more explicit would strengthen outcome-level reporting and future programming. There is also scope to deepen learning on supply-side responses, accountability, and public communications, and share these insights across the BEM portfolio, including the Somalia Stability Fund and IOM’s stabilisation work.
Key lessons:
Delivering effective security and justice programmes requires a continuous understanding of the local political economy dynamics During the inception phase, up to a year was spent understanding local political economy dynamics, and identify locally appropriate approaches, which helped build trust among partners. However, the programme has struggled to maintain continuous monitoring of rapidly changing conflict dynamics and adapt activities accordingly. Significant shifts in the operating environment occurred during the reporting period, yet it remains unclear how IOM managed increased security risks or their impact on delivery. While partners appear to handle focus groups and town hall meetings well, risks persist if sensitive issues are raised too visibly. Partners also reported challenges in building buy-in and navigating security threats. Recognising that risks cannot be fully eliminated, these should be closely monitored, as their materialisation could have far-reaching implications.”

The revised results framework gives insufficient visibility to whether actions are being taken to deliver responses or issues raised. The RF limited its scope to interventions, hence focused monitoring on tracking interest, appetite and government buy-in. As mentioned above, just building the interest and confidence to engage takes time, and while this has been achieved and issues that require actioning surfaced, the results framework reporting is not capturing how many demand-side priorities are responded to hence missing the opportunity to capture those results.

- The learning on when, why and how change do or don’t happen could be drawn out more and, ideally, would be combined with lessons emerging from other initiatives. These include the Somalia Stability Fund (SSF) and IOM’s work on durable solutions and stabilisation, amongst others. The Nabadaynta MEL partner also could be requested to more systematically share their insights across a wider set of interventions shaping public safety.
- Due to legacy issues which resulted in delayed activities it is too early to assess if the localised engagement processes are having a sustainable impact on broader security governance issues. With the programme not progressing to phase two, replication to other FMS and adoption into an FGS framework looks even less feasible. However, the lessons learnt on community engagement and trust building should be considered and included in any successor programme.
Recommendations
In the near term for Nabadaynta (next 6 months)
Make budget and planning as certain as possible for the remaining project period. A rapid decision by FCDO on the final resource envelope for 25/26 will facilitate the VfM of that extra spend, particularly in the context of the end of EU contributions in 2026 and upcoming decision-making from BEM across its security and justice, stability, stabilisation and, perhaps, durable solutions investments. Planning decisions and allocations will need to be discussed and agreed through the delivery chain. BEM should try to hear all those voices and not rely wholly on IOM decisions.

Focus remaining resources on how key security and stability concerns and risks are, or can be, addressed in preparation for the future FCDO Somalia portfolio: At this juncture, it seems unlikely that more in-depth and relatively costly studies (e.g. on trust) are the best use of limited resources. Remaining funds would be best targeted at the goals, geographies, institutions and relationships most likely to be the focus of the future BEM portfolio. This might include handling the pressures of mass and long-term displacement into key towns, or efforts to inform and shape large-scale World Bank initiatives, etc.

Adjust the result framework slightly to capture what works to incentivise positive change in the programme and linking to other initiatives. In particular, the results framework could give more visibility to the achievement of FMS responsiveness in such a resource-constrained context, beyond more engagement and listening. Even more evidence of the quality and nature of feedback on steps taken and not taken (and why) would be useful. The results framework can, and should, also help to motivate more efforts to link up to other highly relevant programmes to maximum internal and external coherence (see also below on portfolio synergy).

It is recommended that the explicit and intentional linkages designed into the project between the listening groups, thematic dramas, talk shows and other communications outreach – are given more visibility in the learning processes that will need to inform the evolutions of the portfolio.

For the longer term:
Nabadaynta will close at the end of March 2026. Therefore, the following recommendations below should be considered for any future programme design.

Give more attention and visibility to the media mentoring and strategic communications: FCDO should explore more deeply how media strengthening and communications are amplifying impact and can do so further. Are there wider benefits that can be developed to foster an active, accurate, inclusive and resilient profession of journalism (notwithstanding the constant dangers faced by those involved)? What dynamics are the spread and changes in social media use having? How can these be leveraged more effectively and safely?

Sustain direct engagement between FCDO and the MEL partner on approaches and learning, particularly where that expertise cuts across other parts of the portfolio. The use of a dedicated MEL partner in Nabadaynta is a good idea and there are considerable nuance and sophistication in the monitoring approach. FCDO would benefit from direct engagement with the partner. For future investments, FCDO might benefit from MEL that is independent from the lead implementation partner, even if that requires more programme management time within FCDO. FCDO should also consider whether perceptions surveys are optimal VfM given the inherent sensitivity of discussing local security and justice dynamics and relationships between communities and duty bearers. Perceptions also tend to be highly variable depending on single and/or most recent events. There are reliability problems when using a survey to assess people’s trust and engagement over time.

1. Build synergy across FCDO partners. There seem to be opportunities for more mutually reinforcing work (e.g. on surveys like the Conciliation Barometer[1] and on dispute resolution approaches) between IOM-implemented work on stabilisation, durable solutions and security and justice and the implementers of the SSF. Context understanding and risk management across programmes could be more systematically integrated to assist FCDO. BEM partners like IOM could join the SSF coordination meetings with the FMS (initiated, for example, in Jubaland in November 2024, not yet convened since but planned to be quarterly).
  [1] The Heshiin Beeg- Conciliation Barometer is a pilot study conducted in two FMS states (Puntland and SWS), informed by the National Reconciliation Framework (NRF). The study aims to understand and measure peace, cohesion, and conciliation. Piloted in three districts each in Puntland South-west, it is intended to fill evidence gaps and identify drivers and barriers to peace. The sample size is 1600 engaging 800 respondents in each state. In SWS, the districts sampled have been Baidoa, Barawe and Afgoe.
2. People-centered security in more stable areas: early results suggest deeper engagement at the local level with a broader range of actors - federal, district, and non-state actors can play a critical role in building community resilience and preventing further deterioration of security. With a shift in internal security strategy, future programming should consider applying the Nabadaynta community security methodology to build trust, assess social norms, and develop localised solutions for improving safety and justice in high-risk areas, including urban centres.
3. Design the portfolio, results and timeframes on the basis of the context complexity and volatility. In Somalia, “political and economic conduct [remain] under-determined by formal institutions cooperation and allegiance are instead exchanged via transactional politics, which includes both targeted violence and material incentives”[2] as well as the instrumentalization of identity groups.” These context realities need to be the starting point for the design of the portfolio, its components and their interlinkages. For example, can the compounded risk assessment under SSF help to guide UK resource prioritisation by geographies and workstreams, to manage expectations upfront?
  [2] Somalia’s Politics: The Usual Business? A Synthesis Paper of the Conflict Research Programme, 2021

Focus on strategies and approaches that maximise influence of SSJP learning on FCDO’s emerging joined up portfolio approach and the World Bank’s new local development support, notably in terms of governance and social norms. Substantial experience has been gained in Nabadaynta on how much time and attention is needed to navigate the complex identity-based and/or personal relationships in Somali society, business and across its spectrum of different authorities (federal-FMS-region-district etc.). Given the experience gained through the SSF, stabilisation and durable solutions programming, it will be invaluable for FCDO to build on and share that experience. The greatest impact is likely to come from focusing on urban and peri-urban areas, where authorities can more effectively launch initiatives to build public confidence and strengthen their legitimacy.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The range of investments planned in the SSJP Business Case were envisaged to help:
- Promote citizen engagement with government on security and justice concerns, notably through the participation of more confident marginalized people.
- Motivate greater government interest in and responsiveness to those concerns.
and in so doing:
  - Improve the rule of law and security governance.
  - Improve the social contract between the public and duty-bearers by changing the culture behind interaction between the public and those in power; and thus:
  - Foster inclusive political settlements for peace and stability
The intention was to invest in “more politically informed programming that delivers real-world benefits.” The SSJPII was to invest in developing the capabilities of the Somali Police Force and the State Police Forces of the Federal Member States to provide civilian-led community security, enabling other force capacities to address A-S. It was also to establish the policy and legal frameworks for the development of State Darawish forces[3] which have the potential to ‘hold’ newly recovered areas, as well as acceptable alternatives to AS administered and enforced justice.
[3] Formed from clan-based militia that fought in Somalia’s civil war and then rose to resist Al-Shabaab, Darawish are generally recruited from the dominant clan-based forces in each region. They are recognised in the Somali National Security Architecture as part of the Police. The NPM assigns the following responsibilities to the Darawish of the Federal Member States: to fight terrorism and to tackle armed insurgencies in their respective territories, either independently or in concert with federal forces.
The business case also envisaged a component in which these positive results would be driven forward by (i) improving political, legal and financial approaches, (ii) moving institutional cultures towards listening to the public and collaboration so that people’s expectations are better met by their duty bearers , and (iii) shifting social norms so that the processes of engagement and response reinforce inclusive approaches to the rule of law. However, support to supply-side provision of public safety was delayed, partly due to the political economy and dysfunctions of Somalia’s security sector and partly due to resource constraints within the IC supporting rule of law and policing programmes. For the period covered by this review, Nabadaynta was mainly the active component. However, the programme contributed to Joint Policing Programme during Q4 (the results will be assessed in the next review).
Phase 1 of Nabadaynta concludes this financial year. As outlined in the business case, the intention during this phase was to test approaches that would strengthen positive social norms to uphold and reinforce more fair, inclusive and effective delivery of security and justice in select locations – and to then scale and expand in the second phase (beyond March 2026). Due to the FCDO ODA reductions and a reduced allocation for Somalia, continuation beyond phase 1 is not feasible. However, the team aims to preserve and build on the programme’s most impactful elements, particularly those related to community engagement and social norms.
The Nabadaynta programme was designed as a joint donor initiative aimed at improving local processes to improve security and justice within a small number of selected districts by delivering the necessary shifts in governance-related norms and behaviours. It seeks to help catalyse a new kind of state and social contract, building up from diverse local dynamics, tailoring efforts to those and shifting traditional cultural practices that can be more harmful or prejudicial to certain groups. Its stated outcome is “Communities and duty bearers (in target locations) leverage improved levels of engagement, trust, capacity, and agency to address locally identified security and justice issues” towards the impact that “Somalis benefit from improved security and access to justice through inclusive approaches that enjoy elite support and public confidence.”

The idea linking the activities to the outputs to outcome and impact contributions is that a virtuous cycle would develop through Nabadaynta whereby support to diverse groups of people collectively to acquire and share knowledge will enable them to have a better interface with government duty-bearers in their security and justice issues. This would lead to a responsiveness from duty-bearers that is more conducive to confidence in government and social harmony and thus to local peace and sustainable stability.

What is most important in this is the process by which local ‘solutions’ are reached. By building perceptions of fairness in (a) the choice of justice provider (in a hybrid system of elders, Islamic ‘court’ or a civil law government authority) and (b) the operation of government-led justice, the idea is to counter the attraction of the speed and harsh decisiveness of A-S militants that may be more appealing to some in the short term.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The new delivery chain (following the removal of IP1 from the programme) has been mobilised more effectively and coherently in the review period after the internal tensions of the past. There is verifiable evidence that the activities funded through the project are building engagement and trust between participating community members. There is also evidence that duty-bearers are more interested in showing responsiveness by listening to the concerns raised, including to the voices of the more marginalised (such as displaced people) and commit to actioning the issues raised or provide information to promote common understanding. Duty bearers are also requesting more interaction sessions, which is a positive sign. Embedded advisors in key FMS ministries are in place and facilitating minister and/or director general engagement.

Delivery accelerated in January 2025. This was enabled also by the combination of long-standing international and Somali expertise in IP2 and in the media/strategic communications partners. Sub-partnerships were deepened with third-tier partners with long experience operating in South-West State (GREDO) and in Jubaland (WASDA in Kismayo), while a third local partner (ADA) was added in the new focus district of Dollow.

Although delivery of activities has accelerated and milestones have largely been met, there is nonetheless very limited evidence that output progress will, and can, sustainably convert to outcome and impact contribution. While there have been significant changes in the budget for delivery of the programme, the reductions in budget are not the cause of the limited outcome-level progress. This is more because of the patience and length of time required to change social norms, influence the political economy and transform the supply-side resources and other capabilities that together determine progress at that results level.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Given the ongoing contribution of Nabadaynta to the Somalia and FMS-specific experience required for achieving VfM, the programme should continue until its now-envisaged end date of March 2026. In that time, it is essential that BEM draws on the Nabadaynta experience and relationships to help evolve its portfolio. It is equally worthwhile to ensure that the learning of Nabadaynta partners, notably IoM and the MEL partner are brought together to help shape the refreshed approach. They can bring invaluable insights into the contextual realities at the strategic and operational levels.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Nabadaynta funds a third-party MEL partner to run a sophisticated results monitoring system. Between April and June 2025, the partner applied a mixed-methods approach[4] to assess progress made across four target districts: Kismayo, Baidoa, Xudur and Dollow. This reporting for UK FY24-25 (April 24 to March 2025) does not quite align with the period covered by this AR but it is logical, given the robust and detailed assessment efforts, to use the findings in the progress descriptions for each of the four output indicators. Particular effort was made in the MEL process to triangulate output indicators 1.2, 1.3, 2.2 and 3.3.
[4] This approach combined telephone surveys with beneficiaries, in-person surveys with control respondents (who lived in the same communities but had not participated in Nabadaynta activities) and qualitative interviews with beneficiaries, control group and both implementing partner (IP) and sub-IPs.

It should be noted that, while on output indicators, partners have delivered beyond the expectations set in the results framework, the reviewers find that either the indicators and/or the 2025 milestones have been set too easily within reach for a programme in its fourth year. It is recommended that any future work to define results on attitude and behaviour change use measures of capacity, opportunity and motivation change to understand attribution at output level and contribution at outcome level.

Output Title	Engagement and trust between communities and duty bearers (government officials, police and judiciary) is improved
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
# and description of interventions delivered to improve engagement and trust between communities and duty bearers	16 (cumulative) [or 22 per Altai report]	34 (cumulative)
% of beneficiaries (communities and duty bearers) reporting improved levels of engagement with other groups (disaggregated by gender, age group, location, and social status)	35% (average across beneficiaries and target groups)	Beneficiary: 72%. Control:35%. / Participants from marginalised groups including IDPs and minority clans reported increased confidence in interacting with duty bearers, noting that these platforms gave them a safe space for them to raise issues and be heard. Evidence shows that these activities provided opportunities for interaction, especially for groups who previously lacked access to duty bearers
% of beneficiaries (communities and duty bearers) reporting increased levels of trust with other groups (disaggregated by gender, age group, location, and social status)	25% (average across beneficiaries and target groups)	Beneficiary: 81%. Control: 29.9%. / Trust was notably higher among women, youth, and IDPs, suggesting the programme's / effectiveness in creating inclusive and safe spaces for engagement

Briefly describe the output’s activities and provide supporting narrative for the score.
This output is about bringing together stakeholders from community groups and formal institutions of security and justice, in a safe and inclusive way. The aim was for the stakeholders to interact and identify localised security and justice priorities.

These are referred to in the project documentation as Listening, Discussion and Action Groups (LDAGs) and Area Based Problem sessions (ABPs) which would be connected into ‘Townhalls’ (moved under IOM’s direct implementation since Q3) involving key FMS, district and other duty-bearer officials. IOM and Equal Access, as well as the district-focused third tier partners, have experienced local staff based in Kismayo and Jubaland facilitating the relationships and dialogue.

Community Engagement: There is good evidence of increased participation from marginalised groups in project activities and of growing demand for inclusive processes and reporting of violence. It is still too early in the implementation to accurately assess impacts directly on the security and justice concerns and on sustainability. This aligns with the MEL output reporting indicating that, “while engagement between citizens and duty bearers has improved as a result of Nabadaynta activities, there is concern amongst communities and duty bearers about the sustainability of the changes they had observed.

Community outreach: Strategic communications (e.g. dramas, talk shows) have generated significant public interest in the target districts (Baidoa and Kismayo). A survey in April 2025 funded by a separate FCDO project asked about the reach of the radio discussion programmes produced by two Nabadaynta partner stations – Radio Kismayo and Radio Baidoa (not all four due to survey length) and received positive feedback about the content, particularly for the discussion programme.

Trust-building: Although indicator 1.1. ‘Achievement of activities’ (assesses the # of interventions), however additional qualitative monitoring done by the MEL partner finds that there was “improved trust among beneficiaries” and this was largely driven by foundational factors such as greater awareness raising, which enhanced understanding of security and justice issues, the roles of relevant actors, and referral processes. Initiatives like the LDAGs, Townhalls, and ABPs provided safe spaces for dialogue and collaboration, bridging initial communication gaps between communities and duty bearers.” MEL reporting has highlighted that, according to mentors and the radio journalists, radio broadcasts created new, inclusive platforms for communities to engage on sensitive issues. There is also evidence that the radio shows can have positive impact on levels of trust.[5] It is not apparent, however, whether levels of trust fluctuate and why, while the Town Hall Planning Committee takes stock of issues raised and actions taken, capturing this information and linking it to the expected outcome and impacts has been lacking hence denying the opportunity the showcase this trust building pathway.
[5] When asked to evaluate their level of trust between 1 (no trust at all) and 5 (full trust) before listening to the radio discussion shows, respondents ranked government, police, and judiciary at 3.0, 3.2, and 2.9 respectively; after listening to the shows, these average rankings rose to 4.3, 4.2, and 4.1, respectively. (Output Monitoring report: FY24-25)

Government Relations: Constructive relationships have been built with FMS ministries in Jubaland and SWS, changing their expectations of their role and dampening an instinctive appetite to exert control (e.g. on the choice of local NGO partner or who can validly attend the townhalls). In Kismayo, for example, the FMS government came round to the idea of involving IDPs and hearing their issues. It is not clear, however, how dependent this is on the funded adviser embedded in each of the three ministries, whether and how the older and newer appointees will help deliver sustainable change and whether positive effects would continue in the event of a change of the political coalition of clan members currently leading the FMS.

Government interest and appreciation: Key counterparts in the ministries of the relevant Federal Member States Town Hall Events have become increasingly involved. Even if the appetite for infrastructure and other hardware support is undiminished, Nabadaynta processes are recognised by FMS ministries as valuable platforms for dialogue and as having enabled improvements in public trust.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Last year the Output 1 was defined as “Inclusive context: Continuous contextual understanding of dynamics of security and justice in specific locations in Somalia (including from gendered, social and political economy perspectives)”. It was weighted 14% and scored an A in the 2024 AR. In the revision of the results system led by IOM and agreed with the joint donors, the output has been revised as per the table above – focussing on engagement and trust.

Progress on recommendations from the previous annual review (if completed), lessons learned this year and recommendations for the year ahead.
The 2024 annual review found that the project met the Output 1 requirement for research and analysis, and for the number of findings, but that it did not meet the requirement for the findings to be joint (i.e. demonstrating blending and a collaborative approach between implementing partners). It recommended that the project needs to review this requirement and “adapt to a more simplified approach to sense making from the wide-ranging research and analyses produced to inform adaptation”.

There has been progress since last year’s review. IOM has taken significant steps, alongside IP2, to drive more joined up implementation through the delivery chain. There is a sense of a unified set of partners operating with a collective Nabadaynta identity, though it is difficult in this annual review to properly and fairly assess the complementarity, and thus relative value and necessity, of IOM (as a direct delivery organisation and not simply a fund manager like UNOPS) with Equal Access in the second tier. However, they have managed to focus all efforts on programme implementation across all implementing partners.
It is recommended that the explicit and intentional linkages designed into the project - between the listening groups, thematic dramas, talk shows and other communications outreach – are given more visibility in the learning processes that will need to inform the evolutions of the portfolio. It is also recommended to refocus indicator 1 away from counting input interventions but rather record aspects that are indicative of greater engagement and trust. This might include tracking who comes to group events to understand whether key community figures are participating together, the quality of collaboration and joint action. An additional indicator on the number of events at which local officials have given feedback on steps taken or not taken on concerns previously raised by the ‘host’ community members and by IDPs could also be informative.

Output Title	The capacity of duty bearers (police, judiciary, government officials) and select community members (in target locations) to address security and justice issues is strengthened
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
# and description of interventions delivered to strengthen the capacity of beneficiaries to address improved security and justice services	8 (cumulative)	21
% of beneficiaries reporting increased capacity to address security and justice issues (disaggregated by gender, age group, location, and social status)	35% (average across beneficiaries)	63.3% / The qualitative reporting is that the beneficiaries of activities have been actively applying skills and knowledge acquired through the programme activities. These include Independent Townhall Planning Committees (ITHPC), the Action Group members coordinating with formal justice actors and the Justice Promoters.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2 focuses on strengthening the capacity of duty bearers and selected community members to address security and justice issues. By enhancing the knowledge, skills, and confidence of key stakeholders, their capabilities would be built to convene and facilitate dialogue and to take action on context-specific challenges. Six activities contribute to this effort: 1) Support to the Independent Townhall Planning Committees (ITHPC), 2) Support to Action Groups, 3) Training delivered to newly appointed judges and prosecutors, 4) Training for Justice Promoters, 5) Embedded Advisors to the Ministries of justice and internal security, 6) the Security and Justice Coordination Cluster, and 7) Radio Journalist Mentoring.

The annual review assesses this output to have met expectations as milestones have been exceeded. However, much of the reporting focuses on inputs like training and doesn’t include evidence of where duty bearer capability has been improved enough for them to take practical action independently. Positive buy-in from the duty-bearers is important, but it is too early to say with confidence that the capabilities are being built to sustain the steps and responsiveness for long term mitigation or removal of the problem, and how dependent this is on embedded advisers. There is limited evidence on sustainability, considering the existing capability challenges within ministries, the team will need to consider the sustainability aspect of the capacity building approach beyond delivering the interventions.

- Duty bearers’ capacity-building through embedded advisers: Following a tricky period of managing contracts taken on from ex-IP1[6], including recruiting afresh for some of the roles, Nabadaynta/IoM recently completed the contracting of embedded advisors in South-west State (SWS) Ministry of Internal Security (retained from IP1) and Ministry of Justice and Constitutional Affairs respectively. In addition, a third embed, a Community Liaison Advisor, sits across both Ministries, totalling three embeds in SWS. In Jubaland, Nabadaynta has three contracted embedded advisors; one in the Ministry of Internal Security, one in the Ministry of Justice and Constitutional Affairs and one in the Jubaland Judiciary (retained).
  [6] To ensure continuity of support to the FMS focus ministries, all the embedded advisors previously on Asal contracts were automatically transferred to an IOM administered contract (with salary remaining the same). Following an IoM review of performance and comparative salaries, it was decided in early 2025 to replace some of the embeds and lower the salaries. The contracting process took place in the first half of 2025. The final recruitment process, that of the Embedded Advisor in the Jubaland Ministry of Justice and Constitutional Affairs, was completed in June 2025.
- Reported capacity gains: The MEL partner found that “respondents including Action Group members, Justice Promoters (JPs), and Judicial Training Institute (JTIs) trainees, cited improved skills and knowledge on various topics, including conducting awareness raising skills on security and justice issues and pathways, navigating conflict resolution and community engagement and facilitation skills.” This indicates increased confidence by the beneficiaries in engaging with both community members, formal and informal duty bearers.
- Awareness Building: There is evidence of improved understanding of citizen rights and government responsibilities particularly by the participants in the project activities but also by some degree of diffusion to other people in the implementation localities. Monitoring surveys show improvements in the control group of respondents but even more so in the ‘treatment’ groups. As per the MEL output reporting: “Participants also noted improved capacity and credibility of duty bearers, particularly the police, due to their enhanced knowledge and engagement through the programme.”
- Media development: The media capacity development is a key part of the delivery chain to drive the theory of change, notably on diffusion of impact beyond the groups and places directly facilitated by the project. Significant efforts to strengthen journalist capacity through training, mentoring, improved editorial guidelines and systems-strengthening help to craft the impactful GESI-sensitive radio programming - dramas linked to subsequent talk shows that are reaching a wider population than ABP groups, justice promoters and Townhall participants. They also are designed to build journalist practices, confidence, risk management and resilience.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Last year Output 2 was defined as “Output 2: Common concerns: Support for convening people/groups with divergent interests and/or identities to coalesce around common concerns”. It was weighted 35% and scored a B in the 2024 AR. The output has since been revised as per the table above focussing on capacity, with new indicators that combine the counting and (from the MEL monitoring report) the description of interventions, as well as perception surveys.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The 2024 annual review found that, in Output 2, the project vastly exceeded the number of area-based problems (ABPs) it was designed to identify, reaching 17 when the target was three. However, it did not reach the requirement for joint working and building consensus around the issues identified.

For the remaining period of the programme in 2025/26, it is recommended that the media capacity development work could be captured better in the results framework, perhaps through an additional and separate indicator or two. There are two important angles to measuring the investment’s impact and to ensuring there is learning from it. The first relates to the inclusivity and resilience of media practices. The second relates to the diffusion potential, including how many people are listening to the dramas and talk shows and where.

BEM, with IOM and its partners, could also reflect on whether MEL VfM would be improved with or without the perception surveys. It could be argued that perceptions are too uneven and affected by reporting biases hence their reliability is not guaranteed. That said, it might be counter-productive to pull back altogether from survey work if there is a robust baseline on which an endline comparison needs to be based. It is, however, recommended that the indicator tracks whether certain techniques are being used by the officials and selected community leaders (risk maps, scorecards etc.) and the frequency.

Output Title	Communities and duty bearers take (joint and individual) action to address local security and justice issues
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
# and description of interventions delivered to encourage beneficiaries to take joint and individual action on security and justice issues	12 (cumulative)	20.
# and description of actions taken by Action Groups and Radio Station Mentees and through Town Halls on security and justice issues	15 (cumulative)	28
% of LDAG beneficiaries reporting taking action on security and justice issues (disaggregated by gender, age group, location, and social status)	70%	89.6% / 94.1% of women and 94.7% of duty bearers reported that had taken action, with the most common action noted as the participation in community forums, conducting awareness raising, resolving disputes, and advocacy for IDP and other marginalised groups on security and justice issues.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 focuses on promoting agency, through learning and a greater sense of shared responsibility, to motivate “communities and duty bearers to take meaningful action on identified security and justice issues. The aim is to support sustained improvements in security and justice.” Four core Nabadaynta activities contribute to motivating beneficiaries and stakeholders to take action on security and justice issues: 1) Action Groups; 2) Townhalls; 3) Listening, Discussion, and Action Groups (LDAGs); and 4) Radio Journalist Mentorship. Action can include “knowledge sharing and discussion, advocacy, raising awareness about justice pathways, and addressing the needs of marginalised groups.”

A few examples of actions taken: (i) through the justice promoters communities awareness sessions, 19 cases were brought forward and were facilitated to pursue justice through their preferred justice pathway i.e. customary xeer /elders, ADR[7] centers, religious court and formal justice system including some opted not pursue their case after they were educated on the various paths they can pursue. (ii) During a Kismayo townhall, concerns about rising mobile phone thefts, the Deputy Minister of Internal Security acknowledged the issues. Police patrols and spot checks soon increased in markets known for selling stolen goods.
(iii) In Xudur, residents raised concerns about military camps near homes. As a result, three of four camps were relocated, addressing fears due to their vulnerability to attacks.
[7] ADR- Alternative Dispute Resolution mechanism

As shown in the table above, the MEL partner reports that more than the set number of interventions and actions have been delivered over the past FY. As for LDAGs, they are described as having emerged as safe spaces that built and provided tools to engage meaningfully on previously sensitive issues. Beneficiaries interviewed by the MEL partner are estimated to have reached over 670 community members with key messages learned through the LDAGs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Last year Output 3 was defined as “Somali-led strategies: Support for Somali-led development and implementation of strategies for achieving changes in safety and/or fairness on common concerns”. It was weighted 7% and scored a B in the 2024 AR. For 2025, the wording has been changed and the weighting increased to 30%. The output has since been revised as per the table above – focussing on action taken.

Progress on recommendations from the previous annual review (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
In 2024, the AR found that Output 3 exceeded the quantity of Somali-led strategies required, but with a lack of compelling evidence that lasting change has resulted from these initiatives.

As for recommendation for output 1 and output 2, it is recommended to include in results framework what actions are taken in terms of concrete steps to address security and justice issues raised by the participatory groups (LDAGs, ABPs, Townhalls), beyond further project-funded awareness/knowledge, engagement and training events.

As for the sections above, it is recommended to remove the “# and description” of interventions to encourage action as this seems to be an indicator of progress made. The second indicator could perhaps be split to distinguish between (a) actions involving more discussion, listening and planning and (b) actions taken by duty-bearers and other leaders to address the problem(s) raised. It could also be useful to disaggregate in the qualitative reporting between ‘low-hanging fruits’ relative to issues that matter most to community feelings of safety and security, differentiating between ‘host’ populations and IDPs.

Output Title	Evidence of i) programme's strategic adaptation driven by research and learning and sharing these lessons with other programmes and/or partners; ii) extent to which the programme delivers GESI-informed programming
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	Yes- upwards

Indicator(s)	Milestone(s) for this review	Progress
Case study demonstrating strategic adaptation based on research and learning, and how the programme has shared these lessons with other programmes and/or partners	1	1 (as per MEL reporting) but AR concludes: / Moderately not met: 5 tactical adaptations made to enhance delivery and results. None meets the ‘strategic adaptation’ threshold.
Case study demonstrating that the programme delivers GESI-informed programming	1	1 (as per MEL reporting) but AR concludes: / Exceeded Expectation; with six examples of GESI informed activities that are currently promoting equal participation in the various platforms of problem-solving dialogue.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]
This Output focuses on utilisation of learning to inform adaptation management, an approach central to Nabadaynta, and important to help the programme respond to complexities of supporting the delivery of security and justice services in a fragile and conflict-ridden context like Somalia. The adaptation approach is two-fold; tactical; which is about adjusting ‘certain ways of doing things to improve delivery, and strategic adaptation which refers to a deeper refection of ‘what is working or not’ in the design and delivery of activities, towards achieving the programme goals in a constantly shifting context.

Indicator 4.1: Moderately Not Met: The indicator is about demonstrating how learning has informed strategic adaptation, including dissemination within Nabadaynta partnership and broader ecosystem of security and justice. The type of adaptations reported, (e.g. increasing production of learning briefs and time dedicated to learning, changing engagement approaches to enable collaborative problem solving and incentives for government actors to strengthen their collaboration), would be the usual type of activities expected of a programme like Nabadaynta and therefore are judged to be in the realm of tactical adaptations to optimise delivery of activities. None of the examples align to the explanation of strategic adaptive management approach which would entail a deeper examination of current approaches, to find out whether they are still aligned to the programme goals, possibly informed by evidence of what is working or not working. While there has been a lot of effort dedicated to continuous learning, this review has not found evidence deeper reflections of these key approaches to inform a strategic shift in order to keep aligned to the goal.

Indicator 4.2. The project exceeded the Milestone set for this indicator, with six examples of how Nabadaynta programming is delivering GESI informed activities targeting formal and informal security and justice actors. The project is delivering strongly on efforts to challenge power imbalances and the structural, systemic issues, which include harmful norms, underpinning gender injustice and social exclusion. Bringing diverse communities and security and justice actors in one place to collectively identify problems and discuss solutions in a context where power imbalances have for long been very discriminatory is a clear demonstration of GESI- informed programming. That being so, the range of gender justice and social inclusion achievements, range within being responsive, with promising transformative power. There is evidence of a solid foundation for inclusive, community-driven approaches to security and justice, which however remain in the confines of the programme activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
In line with the recommendations of the 2024 annual review, and in response to the operational adjustments needed after the exit of IP 1, Nabadaynta programme revised the MERL approach to conform with revised activities to ensure better alignment with the capabilities of the remaining partnerships and still keep the programme relevant to the goal of inclusive approach to security and justice solutions. For Output 4, revision to the Results Framework led to reduced indicators, but increased weighting to reflect the importance of learning as well as a realistic appraisal of the GESI ambition on what Nabadaynta programme can achieve in a context fraught with inequality and gender injustices, especially in the design and delivery of formal and informal security and justice services.

Last year, output 4 was worded slightly differently as “Learning & adaptation: Evidence of i) programme’s strategic decision-making driven by learning; and ii) use of learning to influence strategic decision-making of other actors (Somali and international)”. The GESI-related objective was made more explicit for this review period.

No further changes are recommended.

Progress on recommendations from the previous annual review (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The 2024 annual review found that Output 4 met its requirements for learning and adaptation using evidence generated by project activities, but that the lack of observational change means the project has slightly underachieved on these outputs. The recommendation relevant to this Output was actioned. It had recommended the need for the MERL partner to review the MERL framework, ensuring it is easy to understand for all partners, and has a realistic level of ambition for measuring progress on incorporating GESI in activities. A substantive RF review was finalised and approved.
## D: VALUE FOR MONEY (1 page)
Assessment of whether the programme continues to represent value for money

During the review period, the programme significantly improved its ability to build public trust and confidence in authorities and to promote joint action on security and justice issues. Nabadaynta’s implementation remains a highly worthwhile investment for BEM. There are, however, two primary challenges in assessing Value for Money for the programme. The first is the overarching strategic context for UK Official Development Assistance (ODA) globally and in Somalia. With less ODA resources are available, this puts significant pressure on the budget and makes it more difficult to sustain significant support in political settlement objectives. This was mitigated by working closely with IOM to ensure they prioritised activities in the workplan informed by resources available. Second, SSJPII was designed to shift how the public engage with duty-bearers and change how authority is exercised so that there is greater responsiveness to public needs, hence creating a virtuous cycle of trust and confidence to counter the AS threat. This takes many years and requires administrations’ investment in service delivery (which remain extremely scarce). It also can easily be derailed by immediate security dynamics involving AS but also FMS and FGS forces, as well as powerful neighbours.

The envisaged resources, technical assistance and improvement in security and justice agencies have not materialised to the scale required. The assumption of minimum stability has also not played out in practice. In key areas, including Nabadaynta focus areas, delivery has been buffeted by rivalries and conflicts of competing political (and clan) forces, increasing the cost drivers and risks in programme delivery chains further. Better Value for Money may now lie in integrating programming, finding efficiencies across stability (stabilisation, security and justice and durable solutions) investments in a joined-up portfolio-based approach.

Equity: Nabadaynta maintained a deliberate focus on equity by designing activities to include women, youth, internally displaced persons (IDPs), minority clan members, and persons living with disabilities (PLWDs). Action Groups, justice promoters, radio dramas, LDAGs, and townhalls were structured to ensure participation from these groups. Stakeholder engagement followed a middle-out approach, engaging both community representatives and duty bearers to support inclusive dialogue and joint action on security and justice issues. Disaggregated beneficiary data was collected across interventions.

Effectiveness: The programme met expectation at strategic level through the building of trust and positive accountability spaces, including improved collaboration between state leadership and the citizens. During the period, there was enhanced responsiveness to SGBV cases, four district-level case studies documented these changes with supporting qualitative and quantitative data. To ensure that the programme can develop and implement targeted interventions, and adapt where necessary, approximately 10% of the annual budget ($987,000) was allocated to monitoring, evaluation, research, learning (MERL), and adaptation activities, supporting evidence-based decision-making and improving programme responsiveness.

Efficiency: Adaptive management remained a core feature of programme delivery. Twelve adaptations were made in response to evidence and feedback, including adjustments to Townhall formats, training curricula for justice promoters, and radio drama themes. Risk management reviews are undertaken regularly with partners, allowing for the timely mitigation of security, political, and operational risks.

Economy: Economy was promoted through the localisation of staffing, with national staff occupying an increased proportion of MEL, operational, and technical advisory roles. IOM continued to apply cost control measures to procurement processes, ensuring fair competition and adherence to IOM financial regulations.

E: RISK [½ to 1 page]

Overview of risk management
### Risk Overview
The programme’s risk rating remains severe, with monthly reviews and updated mitigation actions by the team and implementing partners. Due to the thematic focus and volatile environment, especially rising security incidents in Baidoa and Dollow, upcoming elections, and the AU peacekeeping transition, Nabadaynta’s risk level is unlikely to improve. To mitigate, the field team (led by area coordinators) proactively engages with the communities and government stakeholders to assess active risks and shift activities that pose threat to participants. On this basis, IOM reviews the workplan accordingly curtailing movement and limiting the townhalls to a time when the situation is not volatile
### Strategic Risks
- Clan Conflict: Lack of political settlement fuels clan-based exclusion, increasing tensions and marginalisation.
- Elections: Upcoming elections heighten risks of conflict and displacement, with clan dynamics influencing leadership.
- FGS-FMS Tensions: Particularly in Jubaland, political friction threatens security and stability in the Gedo region hence impacting on safety, justice access and stability.
- Al-Shabaab Insurgency: the increased incidents around Baidoa raises concerns on resilience over sustained attacks and long-term stability. In addition, AS control in remote areas restricts justice access and enforces discriminatory practices, especially against women and minorities.
### Programme Delivery Risks
- AU Mission Transition: ATMIS withdrawal and Somalia security limited capacity have led to increased insecurity and al-Shabaab exploiting this weakness to gains ground.
- Safety Concerns: with increased security incidents, townhall events and media engagement pose risks to participants and journalists due to potential targeting.
- Community Fatigue: Persistent violence and limited resources risk eroding public trust and engagement. Clear communication on programme limitations is essential.
### Financial Risks
No major financial risks reported. The Netherlands’ exit was mitigated through staffing and budget adjustments, reducing the budget from $35M to $26M while maintaining delivery efficiency.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Programme Management and delivery: IOM has upheld consistency in providing quarterly delivery narratives, risk register and updates. Reporting has been submitted on time and of good quality with supplementary documentary requests provided in a timely manner. This includes an annual progress report describing progress towards outcomes and detailed performance against output indicators as contained in the theory of change and results framework including the associated resource forecast, funds receipt and utilization of the resources used to deliver.

The programme has established a robust asset monitoring and tracking tool for the project which is shared with FCDO on a quarterly basis. The fund management team (IOM) proactively discusses risks as part of its monthly programme management meeting with implementation partners and MERL service provider and shares an updated risk tracker with FCDO.

The main issue that dominated the team's programme and performance management efforts during this reporting period was the adaptation of the programme delivery arrangements to support more effective delivery against the revised programme ambition, design and the theory of change. As mentioned in the 2024 annual review, Nabadaynta’s commitment to deliver integrated or blended solutions to the concrete challenges faced by target communities proved challenging in practice. It frequently required lengthy negotiations, slowed the pace of delivery, and ultimately called into question the VfM of continuing under the Programme’s original delivery arrangements.

Following the full withdrawal of IP1/Asal in August 2024, the programme delivery arrangements were simplified with IOM directly implementing activities for which it has expertise. The One Programme Approach[8] was adapted to reflect the new realities of the programme, enabling swifter co-creation and collaboration between IOM, Equal Access International (and partners) and Altai.
[8] The One Programme Approach aims to agree shared values and ways of working that incentivise and enable collaboration amongst the programme IPs and prevent siloed working. This approach includes developing the governance arrangements and establishing the systems, and capabilities required to deliver a single, coherent and adaptive programme.

Revised governance arrangements and systems have enabled the delivery of a single, coherent and adaptive programme under IOM leadership. In addition to modifications to programme delivery, Nabadaynta also simplified the MERL system in line with annual review 2024 recommendations and feedback from the EU. In November 2024, the Programme produced a revised and simplified Theory of Change and revised Results Framework. Revisions were made to the monitoring system so that it is fit for purpose and in line with the broader changes to programme delivery outlined above. The simplified MERL system is now fully integrated into the programme governance arrangements and systems to enable the delivery of a single, coherent, and adaptive programme. With the adaptations to the programme fully completed by Q3 2024, the programme has been able to fully focus on delivery for the remainder of Y2.

Financial performance: This review specifically focused on component 401 which is the flagship programme of SSJPII. Despite FCDO’s financial pressure and shifting priorities, financial commitment towards this component has remained unchanged since signing the MOU with IOM in 2023; with UK financial commitment for Nabadaynta standing at £14.2m over a three-year period.

There is no major financial risk to be reported. The programme team maintained a high-level of oversight, carefully reviewing partner budgets to ensure transparency, accuracy and accountability in financial forecasting and expenditures.

The impact on the programme of the withdrawal of the Netherlands as a donor as of 15th November 2024 was mitigated by streamlining the programme’s staff and office support structure, by having IOM play a more direct role in implementation of certain components, as well as by revising the partners’ scope of works and budgets resulting in greater efficiencies. Programme delivery has continued with a budget revision from £25,959,618 (all three co-donors i.e. UK, EU and Netherlands) to £19,187,094 (UK and EU funding) following a through scenario analysis against work and resource planning.

Period	Y1 expense and forecast for Yr2 & Yr3 –est. in GBP	Donors’ funds disbursement schedule estimate in GBP
		FCDO	EU	Netherlands	Total
Year 1 (01 July 2023 to 31 March 2024)	£4,968,415	£2,500,000	£1,552,501	£1,187,394	£5,239,895
Year 2 (01 April 2024 to 31 March 2025)	£7,680,735	£5,574,537	£2,349,050	£0.00	£7,449,050
Year 3 (01 April 2025 to 31 March 2026)	£7,933,332	£6,600,000	£1,293,537	£0.00	£7,893,537
TOTAL	£20,582,482	£14,774,537	£5,195,087	£1,187,394.28	£20,582,482

As of June 2025, the actual expenditure stood at 75% of the total funds disbursed within the reporting period. Payments to downstream partners are linked to milestones and at the time of drafting this review, all commitments had been honored. This milestone-linked payment method is effective in not only incentivizing IPs but also providing an added layer of quality assurance.

Overall forecasts have fallen within the 5% allowable variance over each quarters. This demonstrates a key lesson for FCDO to design multi-donor funded programmes to leverage on financial flow. Forecasting variances have been brought about by the flexible and adaptive nature of this programme whereby implementation activities have been postponed in some instances as a responsive approach to risk management while others have been merged to ensure maximum efficiency[9].
[9] FLEXIBLE approach is the ability to increase or decrease spend and pace of implementation. 2) RESPONSIVE approach is the ability to amend activities, goals or strategic intent in response to client needs or major unexpected events. 3) ADAPTIVE approach is the ability to adapt activities, strategies etc based on real-time learning, changes in operating context during implementation. See the Lifecycle Section of the PrOF and click on "Flexing or Adapting Delivery" for a more detailed explanation.

Commercial Performance: IOM Fund Management team meets bi-weekly with the EU representative and FCDO programme team to discuss emerging risks, status of the programme and implementation priorities which allows for continuous adaptation in response. The two teams meet every quarter to review progress against deliverables. There are other ad hoc meetings depending on the programme needs, which the team have fully engaged in during the year. The IOM team have maintained a responsive, open, transparent, and solutions focussed approach to technical delivery, management and administration. IOM has been proactive in flagging risks and raising potential issues to BEM, and have worked closely with programme team to mitigate, address, and adapt deliverables as need be changing timelines and circumstances for all stakeholders.

Stakeholder Management: SSJPII has a solid track record in the security and justice Sphere and continues to rally the international community and Somali government stakeholders. This is key in remaining focused despite diminishing budget allocations owing to global economic shifts. Through intentional collaboration, the programme team have established a strong working relationship with our partners, built on trust, understanding and mutual benefit. The IPs continue to be engaged and responsive to BEM ensuring the programme is agile, adaptable and responsive. However, as described above partners have shared concerns around the continuing uncertainty and realism around UK ODA financing

During this period, the fund manager organised two quarterly review workshops convening all downstream IPs for a three-day workshop to agree priorities and explore collaborative ways of working. The partners reviewed lessons learnt and recommendations which fed into the next phase of programming. This included agreeing workplans, milestones and budgets to ensure alignment and delivery of project outcomes and outputs.

Cross-programme collaboration: During this reporting period, Nabadaynta began collaborating with other IOM implemented programmes to ensure greater coherence. The programme is cooperating with the FCDO/ISF-funded programmes – stabilisation, Danwadaag and RESTORE programmes, including Collaborative Safety and Security Framework (CSSF), adapting the CSSF methodology and rolling it out in selected areas. In addition, Nabadaynta collaborated with UNTMIS and UNDP in joint mission and stakeholder engagement in Kismayo and worked with JJCP to compare requests on training for Kismayo judges and prosecutors. Other areas of collaboration are under discussion, including on linking the Justice Promoters with other similar initiatives to strengthen referrals i.e. Gashaan programme.

Date of last narrative financial report	June 2025	Date of last audited annual statement	29/05/2025 / Financial Reports | Governing Bodies

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
Nabadaynta has developed and integrated an elaborate MEL system, which evolved during the review period as summarised in the section above. The contracting of a third-party provider has enabled the collection of multiple data sets, including perception survey data, which backs up and details the results framework indicators. In addition, the delivery partners systematically report progress on their work plans and the ‘comms strategy’ and media mentoring partners have measured the impact of their outreach support.

It is recommended that, in planning the next phase of support, BEM reflects carefully on cost vs. benefit of MEL investments. Broad perception surveys are notoriously susceptible both to reporting bias and/or the volatility caused by the most recent events. They may well not be the most reliable guide to progress on public confidence, particularly in sensitive aspect of security and justice or even to measure participation and responsiveness.

For the remaining period of NS, it would also be worth focussing ever scarcer resources on delivery rather than ad hoc studies of generic concepts like ‘trust’, which are interesting but perhaps too far beyond the reach of external actors like the UK. The calculation of VfM would seem better based on what duty-bearers and the broadest spectrum of community stakeholders would consider most important over the short to medium term (albeit without losing sight of long-term goals).

Evidence
In terms of the evidence-base underpinning the results framework, the available reporting on NS is robust. The weakness lies in the potential for reporting bias and the volatility of perceptions noted above. With little to no change to the quality of delivery, survey data can, for example, suddenly deteriorate in the face of new or resurgent dangers.

It is also recommended for BEM to contract any third-party M & E service provider separately from the lead delivery partner. Although the reviewers found no reason to judge that the M&E reporting in the programme was skewed in any way (and noted that the MEL partner was brought across to IOM from UNOPS), perceptions of the robustness of reporting and analysis are inherently enhanced by independence from partners implementing Theories of Action within the Theory of Change. The additional partner management is generally worth it.

Learning
The learning ecosystem within Nabadaynta has matured from intention to application. Last year’s report highlighted the planned development of tools that would become the Learning Log and Rapid Learning Briefs.

This year, these mechanisms have been operational and have contributed directly to programme adaptation. Learning has become embedded in routine programme cycles, with quarterly Strategic Reflection Sessions, partner check-ins, and cross-consortium sharing. These learning moments are increasingly informed by evidence, rather than anecdote, and have supported shifts in activity design – for instance, improving the inclusion of women and IDPs in townhall facilitation, adapting radio content to reflect locally relevant conflict narratives etc. The programme’s annual Learning and Adaptation Case Study (under Output 4) marks a major step forward in documenting how evidence-informed decisions are being made.

Unlike last year – where adaptation was more implied than tracked – the programme can now demonstrate clear instances where learning has led to adjustments in strategy or implementation (e.g. revising the GESI strategy, shifting outreach methods, or refining training content).

Finally, learning is increasingly partner-led and context-sensitive, reflecting the programme’s commitment to distributed ownership. Reflection and adaptation processes are no longer confined to the MERL partner or consortium leads, but are being shaped by field teams, local implementers, and beneficiaries, creating a more dynamic and grounded learning system