## Annual Review Template

Title: UK investment in the Global Fund to Fight AIDS, Tuberculosis and Malaria 2023-2025
Programme Value £ (full life): £1,000,000,000 (£1BN)		Review date: May 2025
Programme Code: 300869	AMP start date: 27/11/2023	AMP end date: 31/07/2027

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Mod	Mod

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004251.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004252.xlsm

A. SUMMARY AND OVERVIEW

Description of programme

Ending the epidemics of AIDS, tuberculosis (TB) and malaria and strengthening the wider health system are crucial to tackling poverty and enabling individuals and economies to thrive. Most of the UK’s support to tackle these three diseases is channelled through our investment in the Global Fund to Fight AIDS, TB, and malaria (the Global Fund).

The Global Fund is the largest multilateral grant funder of health systems with significant investments in supply chains, health management information systems, health workforce and laboratory systems. In addition to directly investing in health systems, programmes to fight the three diseases also benefit health systems indirectly by reducing the burden of HIV, TB, and malaria on health facilities and health expenditure. Investment in the Global Fund contributes to the UK Government’s international development mission, to create a world free from poverty on a liveable planet, by reducing infections and mortality from the three diseases and building strong and sustainable health systems to drive Universal Health Coverage and better prepare and respond to pandemics. This includes tackling new and growing challenges such as climate and health and the rollback of human rights through specific programming and/or catalytic investments. The work of the Global Fund is also crucial in the progress towards achieving the Sustainable Development Goal (SDG) 3 target of ending AIDS, TB and malaria by 2030.

This programme supports the Global Fund’s 7th replenishment period (2023-2025) and has two main elements:

Support the Global Fund’s core work across the three diseases and wider health system and contribute to the goal of universal health coverage (UHC);

Strengthen the supporting architecture to enhance the impact of our core investment through a separate technical assistance component, the Global Fund Accelerator Programme, managed by FCDO.

The published UK-Global Fund performance agreement sets out the UK’s priorities over the programme period. The agreement is underpinned by annual targets with progress assessed through the Annual Review process.  The UK was one of the founding members of the Global Fund in 2002 and remains the third largest investor to date. The UK is an active participant at the Global Fund Board and has representation on both the Strategy Committee (SC) and the Audit and Finance Committee (AFC). The UK also has representation on the Joint Committee Working Group (established in 2024) between the Global Fund, Gavi and the GFF.

Summary supporting narrative for the overall score in this review

Output	Weighting	Score
Output 1 Maximised impact on the three diseases through improved coverage of HIV, TB and malaria prevention and treatment interventions	40%	A
Output 2 Building fair and resilient systems for health	15%	B
Output 3 Tackling global challenges	15%	A
Output 4 Organisational Effectiveness	25%	A
Output 5 / Global Fund Accelerator	5%	B

This review covers the second year of the 7th replenishment cycle (2023-25) with a cut-off of May 2025. The Global Fund has performed well overall, meeting the majority of indicator targets. Whilst overall delivery is broadly on track, the underlying output scoring highlights a more mixed picture. As described in this annual review, the Global Fund have demonstrated strong progress at country level in meeting delivery targets, but there is still a need for accelerated progress on institutional reform areas, including gender and sustainability; this has been reflected within the recommendations given by FCDO.

For all HIV, TB and Malaria specific indicators, the Global Fund uses the portfolio performance target of 90%. This sets an ambition for the indicator to achieve 90% performance against the aggregate grant targets. The rationale for using performance targets rather than aggregate targets is that performance targets provide a consistent and stable benchmark for evaluation over a fixed period, whereas aggregate targets can only be set once grant agreements are finalized and may change over time. Whilst progress against performance targets have been used for the purposes of this review, actual results against individual grant targets are summarised in Annex A. For some sub-indicators, data was either unavailable or reporting was to set baselines only; these have been excluded in the assessment of indicator performance and overall output scores.

In 2023, the Global Fund accounted for 28% of all international financing for HIV, 76% for TB and 62% for malaria. The Global Fund works in more than 100 countries delivering results at scale. Some key headlines in the past year include:
- A reported 65 million lives and a 63% reduction in the combined death rate from AIDS, TB and malaria since 2002
- By end 2023, countries supported by the Global Fund saw a combined 11% reduction in mortality rate and a 4% reduction in incidence rate for the three diseases compared to 2021.
- The Global Fund have completed the first targeted Health Facility Assessments (tHFAs) in 2024. This is a key milestone in RSSH measurement. The results from this round of tHFAs will serve as the baseline scores for assessing improvement in integrated people-centered quality service provision via four KPIs.
- The Global Fund have carried out targeted work to strengthen health management information systems (HMIS) and monitoring and evaluation (M&E) systems within countries with support from the Global Fund partnership
- The Global Fund and Private Sector partners announced a new Climate and Health Fund to tackle the health impacts of climate change
- The Global Fund NextGen market shaping initiatives achieved the first Pooled-Procurement Mechanism (PPM) delivery of African-manufactured anti-retrovirals (ARVs), and Board approval of both a quality assurance policy for Vector Control Products and an updated Procurement Policy
- The Board approved of a set of policy changes aimed at increasing the sustainability of Global Fund grants; this included increased funding to both Malaria and TB in a higher replenishment scenario.
- The Board Approved the suite of catalytic investments to be taken forward into Grant Cycle 8, with the UK successfully leading an initiative to secure additional funding for the UK’s priority areas of RSSH and Gender & Human Rights
This year also saw the launch of the 8th replenishment Investment Case; the 8th replenishment cycle will cover the latter half of the 2023-28 strategy period.

Major lessons and recommendations for the year ahead

Specific recommendations for both the Global Fund and the FCDO are highlighted throughout this review and summarised below. These will be taken forward through the different forms of engagement that FCDO has with the Global Fund, including UK representation on the Board and committees, strategic dialogues, interactions between the FCDO programme team / advisers and Global Fund Secretariat, and FCDO’s engagement with, and funding for, other stakeholders such as the World Health Organization (WHO) and Gavi (the Vaccine Alliance).

Output	Recommendations to Global Fund	Recommendations to FCDO
Output 1 Maximised impact on the three diseases through improved coverage of HIV, TB and malaria prevention and treatment interventions	The Global Fund should provide greater clarity on plans to address climate change and drug/insecticide resistance in malaria and sustain progress, particularly in a constrained funding environment
Output 2 Building fair and resilient systems for health	The Global Fund should prioritise sustainability planning across all existing and future grants, supporting countries in developing plans to mobilise domestic resource and transition towards self-financing for health systems, ensuring these are integrated with wider HSS efforts in country. This commitment should be evidenced through Secretariat-led efforts to define transition pathways for every portfolio under GC8, alongside routine reporting on KPIs R1a/b and transition progress. / The Global Fund should accelerate integration of services, ensuring integration goes deeper to organisational and institutional levels. Whilst key baselines for measuring integration have been established, evidence of implementation remains limited. FCDO expects integration to be actively supported and embedded across all levels of the Secretariat as a core policy objective, with clear accountability mechanisms and reporting structures to the Board and/or Strategy Committee.	FCDO to establish an approach to coordinated monitoring and engagement of sustainability and transition across the Global Fund, the World Bank, and other partners to ensure alignment and accountability.
Output 3 Tackling global challenges	The Global Fund to ensure clear applicant guidance for the integration of human rights and gender considerations into grant proposals is available and updated in line with the current context; FCDO’s GFA advisors to provide technical support to this as needed.	FCDO to review the Global Fund’s Evaluation on Human Rights Barriers once made available
Output 4 Organisational Effectiveness	The Global Fund should continue to actively pursue and strengthen collaboration with other GHIs, including Gavi, the World Bank and the GFF. This effort should be visibly championed by senior leadership, with a clear roadmap for sustaining momentum beyond the conclusion of the Joint Committee Working Group (JCWG) in late 2025.
Output 5 / Global Fund Accelerator (GFA)		FCDO and TA providers to strengthen oversight and financial management in TA workstreams, using insights from advisers in-country to inform accurate forecasting and reporting on budget utilisation. / FCDO to establish and utilise quarterly meetings with GFA Secondees

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (TOC) for this programme is that: The Global Fund works effectively with partners, including national governments, to translate support (financial/other) into effective grants to deliver the 2023-2028 strategy and 2023-2025 investment case, overseen by strong governance and utilising learning based on best practice. Improved leadership, governance and organisational effectiveness of the Global Fund, together with strengthened national ownership of the response to AIDS, TB and malaria translates into improved delivery and coverage of services within strengthened health systems; and this translates into sufficient results to get back on track to achieve SDG 3 targets. The steps in this TOC remain valid and all outcome and impact indicators remain unchanged.

This review captures the first full set of reporting against the new strategy period (2023-28) and covers the first year of the implementation of grant cycle 7 (GC7) grants. Whilst it is still early in terms of reporting on implementation and outcomes, the KPI results show that grants have recovered well following a stalling of progress in some areas during the Covid-19 pandemic and are showing a positive shift towards alignment with initiatives of the 2023-28 Strategy. Despite this impressive recovery, we remain increasingly off-track to achieve the SDG 3 targets to ensure healthy lives and promote well-being for all at all ages. Malaria is the most off the trajectory to reach the SDG 3.3 target for 2030 and is also the most at risk of stalling or reversal of progress.

2024 was a difficult year for global health, with growing external threats including drug and insecticide resistance, climate change and the roll-back of the human rights agenda. FCDO recognises that the environment in which the Global Fund operates is becoming increasingly challenging. These challenges are exacerbated in an increasingly constrained funding environment, and it is crucial that the Global Fund continue to take a rigorous approach to ensuring value for money in all of its grants, seeking efficiencies and targeting interventions to those who need them most. Over the first half of 2025, the Global Fund have had to react quickly in an environment of great uncertainty, and we acknowledge the efforts made in working with countries to assess risks and protect essential programming, whilst also planning for a range of future funding scenarios. Whilst the immediate focus is rightly on stabilising the system and minimising lives lost, the Global Fund should also be looking at a longer-term view of supporting countries in their transition to self-financing.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome indicator(s)	Progress
KPI H2: Portfolio performance for % of people living with HIV who are on anti-retroviral therapy (ART)	Met / Target: Grant portfolio performance at or above 90%. / Latest Result: 98%
KPI T2: Portfolio performance for TB Treatment Success Rate (all forms). / This measures % of patients with all forms of TB, bacteriologically confirmed plus clinically diagnosed, successfully treated (cured plus treatment completed) among all TB patients notified during a specified period.	Met / Target: Grant portfolio performance at or above 90%. / Latest Result: 96%
KPI M3: Portfolio performance for proportion of confirmed malaria cases that received first-line antimalarial treatment at public sector health facilities	Met / Target: Grant portfolio performance at or above 90%. / Latest Result: 99%
KPI S1: % of countries with improvement in scores for provision of integrated, people centered high quality service delivery from latest baseline	Target: 100% countries improved scores compared to latest baseline (2023, 2025) by mid Strategy (2025) and end of Strategy (2028) / Latest Result: Baseline set – average score of 74 across 16 cohort countries
KPI P3: Percentage of countries with improved or sustained high performance in human resources for implementation of IHR	On Track / Target: 90% of countries show significant improvement, or have maintained high performance by end of Strategy (2028) / Latest Result: 42%

Impact indicator(s)	Progress
KPI I1: Projected reduction in combined mortality rate across the three diseases from 2021 baseline to end 2028	On-track to achieve ‘intermediate’ target level / Target: Combined mortality rate reduction of [35% - 54% - 70%] across the three diseases from 2021 to end 2028. / Latest Result: 11% reduction in combined mortality rate from 2021 to 2023
KPI I2: Projected reduction in combined incidence rate across the three diseases from 2021 baseline to end 2028	On-track to achieve ‘intermediate’ target level / Target: Combined incidence rate reduction of [30% - 42% - 60%] across the three diseases from 2021 to end 2028. / Latest Result: 4% reduction in combined incidence rate from 2021 to 2023
Universal Health Coverage (UHC) Service Coverage Index2, Average for High Impact Countries (excluding China)	Target: Increase in the average UHC service coverage index in high impact countries (excluding China) of 6% between 2021 and 2023. / Latest Result: 2021 Result = 51.77%. More recent data not yet available.

Outcome indicators for this programme were chosen to reflect key aspects of treatment and care for HIV, TB, and malaria, and progress on health systems strengthening and health security. Where data is available, all outcome indicators have met their target or have been assessed as on-track where targets are not annual. The Global Fund continues to achieve a high level of impact against the three diseases, with KPIs H2, T2 and M3 all exceeding their targets.

With regards to HIV, H2 has exceeded its performance target, with 79% anti-retroviral therapy (ART) coverage achieved in 95 countries against a grant target of 81% leading to a portfolio performance of 98%. As described under output 1, KPI performance across HIV is generally strong, but the Global Fund note that these results mask inequities in the delivery of and access to services for Key Populations, children and adolescents, and men across prevention and care. To tackle this, the Global Fund is supporting efforts to reach those left behind through focused testing approaches, acceleration of the roll-out of prevention tools, increased investments in testing for pregnant and breastfeeding women to support elimination of vertical transmission, and the scale up of ART, supporting differentiated and targeted service delivery models. With the increasing rollback of human rights globally combined with significant reductions in global funding for HIV programming, Global Fund initiatives to tackle gender and human rights related barriers to health have become even more critical in ensuring ongoing progress against the disease.

For TB, whilst KPI T2 has met its performance target, achieving an overall treatment success rate of 88% in 72 countries against a grant target of 91%, one TB specific indicator described later in this review has significantly fallen short (output 1.2). Progress on TB is largely positive, and 2023 saw the highest number of people ever notified with TB recorded, marking a full recovery of TB programs from the setbacks caused by COVID-19. Early diagnosis, tackling barriers to service access and the successful treatment of ‘missing’ persons with TB (including drug-resistant TB, ‘DR-TB’) continue to be key priorities for the Global Fund, with challenges arising primarily through lack of funding, particularly for TB prevention activities. Given the funding gaps observed across TB grants in Grant Cycle 7 (GC7), the Secretariat is working to optimize and increase efficiencies and integration in TB programs and develop country-led and evidence-based recommendations. This will be supported by funding for TB Reach waves 10 and 11 through the GFA which is supporting testing and evaluating new approaches to rollout of TB preventative treatment (wave 10) and integration of TB services (wave 10 and 11).

As with TB, most malaria indicators have met their targets, with only one falling short (output 3.2). KPI M3 has exceeded its performance target, with 97% treatment rate reported across 53 countries against a grant target of 98%. According to the 2024 Global Fund results report[1], malaria programmes have fully recovered from the impact of COVID-19 and are successfully expanding access to prevention and treatment tools for malaria, including long-lasting insecticidal nets (LLINs), seasonal malaria chemoprevention, preventive treatment for pregnant women, indoor residual spraying, and antimalarial medicines. However, out of the three diseases, malaria remains the most at risk, with growing threats including drug and insecticide resistance, climate change and conflict threatening the stalling or reversal of progress. To maximise impact moving forward, there is a need for the use of a mix of treatment options based on sub national tailoring informed by quality data (including climate data where possible) in the planning stage, and scale up specifically of innovative new technologies such as dual-active ingredient bednets and malaria vaccines. The funding for Roll Back Malaria through GFA offers an opportunity to bring efficiencies through stronger collaboration between malaria actors that impact malaria interventions, especially through the Big Push[2] which provides an overarching framework to accelerate malaria elimination.
[1] theglobalfund.org/media/14794/core_2024-results_report_en.pdf
[2] About us | RBM Partnership to End Malaria | The Big Push

KPI S1 tracks improvements made in-country for the provision of integrated and people centred services. The 2024 result for this indicator is the first set of data available and so will act as a baseline to assess progress over future years. Further assessment of the Global Fund’s progress and ambitions on integration can be found under output 2.1. KPI P3 measures improvements in human resources for implementation of the World Health Organisation’s (WHO) International Health Regulations (IHR), and has been reported as ‘on-track’ to achieve the 2028 Strategy target. Data for this indicator is taken from the WHO State Parties Self-Assessment Annual Reporting (SPAR), which scores countries based on their capacity to prevent, detect, and respond to public health risks. Going forward, the Global Fund will continue supporting national field epidemiology training programs to improve surveillance, rapid response, outbreak investigation, and testing. They will also focus on animal and environmental surveillance and contact tracing for early warning, and training for health workers to ensure primary care is prepared for emerging diseases.

Impact indicators used in this review assess the Global Fund’s contribution to reducing death and incidence rates across the three diseases, and to the wider global health objective of achieving Universal Health Coverage (UHC). From 2021 to 2023, the combined mortality rate across HIV, TB and malaria (KPI I1) has reduced by 11%, and the combined incidence rate (KPI I2) by 4%. For both indicators, the reduction was driven primarily by HIV, with malaria showing the smallest decline in both deaths and cases; this reflects the fragility of the current gains made on malaria as described above. Based on modelled projections using current data, both KPI I1 and I2 are on-track to their Board approved ‘intermediate’ targets by 2028. The Global Fund note that these projections are subject to a number of uncertainties, particularly given unpredictability around factors such as levels of domestic and international funding available in the future. It should also be noted that both of these indicators reflect a collaborative effort of all partners in the fight against the three diseases, and not just that of the Global Fund.

Finally, the UHC indicator has not been reported in this review. This metric is dependent on the 2023 WHO UHC date which has not yet been published; we expect this will be available for assessment in next year’s review.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The Global Fund is the main international mechanism supporting the fight against HIV and AIDS, TB and malaria and the largest international grant funder of health systems.  Our investment in the Global Fund’s seventh replenishment continues to deliver high impact both in terms of lives saved, and progress made in the drive towards strong and sustainable health systems. The Global Fund also plays a critical role in delivering on the UK’s wider global health objectives such as our commitments to working multilaterally and in partnership, including with the Global South; tackling poverty; protecting and empowering women and girls; and bolstering international health security.

A key achievement of this year has been securing Board alignment and unanimous approval of a set of sustainability changes, including revisions to the Sustainability, Transition and Co-financing (STC) Policy, the allocation methodology and the catalytic investment priorities for grant cycle 8 (GC8). The proposals were the most far-reaching policy reforms since 2016 and will be an important step forward in supporting countries in their journey towards self-financing. Leveraging domestic financing remains a key area for improvement with underperformance seen in relevant indicators, particularly given increasing risks to future funding. We must now see evidence of how these changes will be operationalised as we approach GC8, as well as a focus on driving efficiencies and effective integration and collaboration across the Global Health architecture. We will continue to use our full range of levers to monitor progress over the final year of this programme and ensure areas of underperformance are addressed.

Overall, the programme continues to represent good value for money and is aligned with the FCDO’s position within international development and global health. The UK’s £1 billion contribution to the 7th replenishment is forecast to save approximately 1.276 million lives, avert 28.25 million new infections or cases across the three diseases, and create $32.77 billion in economic returns through health gain from 2023-25.

## C. DETAILED OUTPUT SCORING

Output Title	Maximised impact on the three diseases through improved coverage of HIV, TB and malaria prevention and treatment interventions.
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
HIV / KPI H1: portfolio performance for % of people living with HIV who know their HIV status. / KPI H3: portfolio performance for % of people living with HIV and on ART who are virologically suppressed	KPIs H1: Grant portfolio performance at or above 90%. / KPI H3: Grant portfolio performance at or above 90%.	Met / KPI H1: 95% Objective Met. / KPI H3:102% Objective Met.
TB / KPI T1: Portfolio performance for # of patients with all forms of TB notified (i.e., bacteriologically confirmed + clinically diagnosed); *includes only those with new and relapse TB / KPI T4: Portfolio performance for % of patients with rifampicin-resistant (RR) and/or muti-drug resistant TB (MDR-T) successfully treated / KPI T5: Portfolio performance for # of people in contact with TB patients who began preventive therapy (TPT)	KPI T1: Grant portfolio performance at or above 90%. / KPI T4: Grant portfolio performance at or above 90%. / KPI T5: Grant portfolio performance at or above 90%.	Partially Met / KPI T1: 101% / Objective Met. / KPI T4: 106% / Objective Met. / KPI T5: 55% / Objective Not Met.
Malaria / KPI M1: Portfolio performance for # long-lasting insecticidal nets (LLINs) distributed through mass campaign and continuous distribution / KPI M2: Portfolio performance for proportion of suspected malaria cases that receive a parasitological test at public sector health facilities / KPI M5: Portfolio performance for % of children who received the full number of courses of seasonal malaria chemoprevention (SMC) per transmission season in the targeted areas	KPI M1: Grant portfolio performance at or above 90%. / KPI M2: Grant portfolio performance at or above 90%. / KPI M5: Grant portfolio performance at or above 90%.	Met / KPI M1: 96% / Objective Met. / KPI M2: 101% / Objective Met. / KPI M5: 97% / Objective Met.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output tracks the coverage and impact of prevention and treatment interventions for each of the three diseases. Scoring against the indicators above does not consider results from the full breadth of the Global Fund’s KPIs related to the three diseases; this assessment is therefore limited to KPIs captured within the Logframe. These KPIs have been chosen as the most important to FCDO in terms of measuring programme success, but we acknowledge that the indicators selected for this review alone do not necessarily provide for a full reflection of the current position of the Fund in the fight against HIV, TB and malaria at the end of GC7 Year 2.

Under indicator 1.1, the Global Fund have performed very well across all HIV KPIs, including H1 and H3 which have both exceeded their performance targets. However, we note the limitations in the use of this data alone; for example, the Global Fund note that KPI H3 only measures the suppression rates of those who have successfully received a test, and its high-performance masks lower suppression seen amongst children. Whilst GC7 grants aim to improve access to HIV testing, coverage gaps remain due to challenges including funding gaps, weak demand (often resulting from stigma and social barriers), supply chain challenges and issues with sample transportation. The Global Fund is taking steps to address these barriers through its country grants and catalytic investments, but such a multi-faceted problem is complex and time consuming to address. The role of civil society in improving access is particularly prevalent across the HIV space, and the Global Fund is a powerful advocate for community-led approaches, most notably through the work of its Community Rights and Gender Unit. FCDO were also pleased this year to see the Global Fund step up in understanding how it could support the rollout of Lenacapvir, demonstrating its commitment to supporting equitable access and the use of innovative technologies.

Indicator 1.2 covers TB and has been assessed as ‘partially met’ due to KPI T5 (people in contact with TB patients who began preventive therapy) failing to meet its target. Performance for KPIs T1 and T4 were strong, but Global Fund note this is skewed somewhat by positive results in the largest portfolios such as India and Indonesia. Underperformance of T5 can be attributed to issues including insufficient funding for prevention and testing, as well as a reluctance of health care providers and patients alike to take TB preventative treatment. Additionally, the 2025 Office of the Inspector General ([3]OIG) annual report notes that, whilst TB notification and treatment success rates have improved significantly, difficulties remain in finding and reaching drug resistant cases. The Global Fund is taking steps to address these challenges, including through the expansion of access to multiplex molecular diagnostic tools, increased TB advocacy work, incorporating prevention and treatment activities into community engagement and targeted training of health care workers. The development of a TB vaccine looks promising and will need collaboration with partners for its introduction. The Secretariat is involved in various working groups and initiatives to ensure country readiness and access for the new TB vaccine as part of prevention efforts, and we look forward to seeing this work progress.
[3] The Office of the Inspector General is the independent audit function of the Global Fund.

Malaria programming has been highlighted through previous annual reviews as being an area of concern, given the particular vulnerability to external factors such as climate change, and the rate at which cases/deaths rebound when control measures are removed or insufficient. Additionally, domestic financing for Malaria is low comparative to the other diseases, creating greater reliance on increasingly uncertain external funding. The Global Fund is the main mechanism for tackling Malaria globally and FCDO recognise its invaluable efforts in this space; KPIs M1, M2 and M5 captured under output 1.3 have all performed well, exceeding their performance targets. There are however areas of underperformance highlighted across the portfolio, with delays in vector control interventions and limited availability and/or use of bednets identified as common themes through several OIG audits in 2024 (see also section B). The OIG annual report does note however that, whilst they continue to experience challenges, Malaria programs are also generating significant positive impact, averting millions of cases and deaths. This is a reflection of the Global Fund’s efforts to provide quality malaria prevention, treatment and care programs; current initiatives include their work to accelerate the implementation of sub-nationally tailored strategies for Malaria, support innovation to address biological threats, and expand access through market shaping to lower prices and widen the supplier base. In addition to this, CHAI’s market shaping work (through the GFA) supported malaria programme reviews in Mozambique and Uganda; these included updating geospatial maps of disease burden and carrying out retrospective analysis of impact, coverage and quality. These insights will ultimately help malaria programmes improve effectiveness and efficiency by optimising national intervention targeting and mix and will subsequently influence what ends up being included in Global Fund funding requests. This work should be replicated in another 6 countries before the end of GC7. Moving forward, the FCDO would like to see more clarity on how the Global Fund plans to address the rising threats of climate change and drug/insecticide resistance on Malaria, as well as plans for how best to support ongoing progress in a reduced funding environment.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The previous annual review used KPIs from the 2017-22 strategy period as proxies where data for the above KPIs was not yet available. This is therefore the first year that the annual review is based on 2023-28 KPIs as was originally planned at the stage of programme design. No other changes have been made to this output; targets for the third year of the programme will now be set.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from Previous Annual Review	2024 Progress
The Global Fund should prioritise recovery, protection, and strengthening of malaria programmes to address emerging issues such as insecticide and anti-malarial drug resistance.	The Board approved a revised allocation methodology in November 2024 which increases funding to Malaria in a high replenishment scenario. / With the exception of M4, all malaria KPIs on track. The Global Fund continues to make investments to ensure provision of quality malaria prevention, and treatment and care programs in countries. However, the risk to Malaria is very high and growing; this is acknowledged by the Secretariat, but it is not clear how this will be addressed. / Modelling completed through the Malaria Atlas Project (MAP) in 2024 predicts that even in a flat replenishment scenario, Malaria cases are expected to rise by a further 112 million, with up to 280,700 additional deaths. In addition, a 23% to malaria in Grant Cycle 8 ($4.17bn to $3.2bn) is expected to result in an additional 146 million Malaria cases, and up to 381,000 additional deaths between 2027 and 2029.
In line with Lusaka Agenda principles, the Global Fund should also prioritise collaboration with Gavi and GFF under the new collaborative workstreams to strengthen impact of collective investments including making optimal, prioritised use of new tools, in particular malaria vaccines, and improving joined-up RSSH investments to strengthen PHC. Important to see tangible action at country-level through the first-wave countries.	The JCWG has met regularly through the latter part of 2024 into 2025. There have been some challenges in terms of group engagement and progress has been slow; feedback from group meetings on the effectiveness of the JCWG is mixed. / A Deepdive on Malaria was conducted in February 2025 and highlighted a lack of shared vision across the GHIs; this has led to engagement across the Global Fund and Gavi boards. This work reflects the potential of the group to drive alignment across the institutions but now must continue to progress in 2025 to deliver impact.

2025 Recommendations

The Global Fund should provide greater clarity on plans to address climate change and drug/insecticide resistance in malaria and sustain progress, particularly in a constrained funding environment

Output Title	Building fair and resilient systems for health.
Output number:		2	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Increased investments in integrated people-centred quality services / (KPIs S2, S4, S7, S8) / KPI S2: % of countries with improvement in scores for provision of integrated supportive supervision at health facilities / KPI S4: % of countries with systems in place for community health service delivery / KPI S7: % of countries that have documented evidence of using required disaggregated data to inform planning or programmatic decision making for priority populations in HIV, TB and malaria / KPI S8: KPI S8: % of health facilities with tracer health products available on the day of visit for HIV, TB & malaria respectively	KPI S2: 100% countries improved scores compared to latest baseline / (2023, 2025) by mid Strategy (2025) and by end of Strategy (2028) / KPI S4: 38% of countries (40 countries) meet at least 3 of the 4 criteria by end of Strategy (2028). Interim target of 26% for 2024. / KPI S7: 80% countries meet the threshold for use of disaggregated data by end of / Strategy (2028) / KPI S8: Achieve on-shelf availability (OSA) of at least 90% by 2025 and maintain annual 90% result till end Strategy (2028) for HIV, TB, malaria respectively	On Track / KPI S2: Progress from the baseline will be reported for the first time Q2 2026 / KPI S4: 28% / Objective on track. / KPI S7: 84% (data available for High-Impact (HI) countries only) / Objective on track. / KPI S8: / HIV/Aids – 89%, TB - 81%, Malaria - 85% / Objective on track.
2.2 Enhanced preparedness for and preventing future pandemics (KPIs P1, P2) / KPI P1: % of countries with improved or sustained high performance in laboratory testing capacity modalities / KPI P2: % of countries with improved or sustained high performance in early warning surveillance function	KPI P1: 90% of countries show significant improvement, or have maintained high performance by end of Strategy (2028) / KPI P2: 90% of countries show significant improvement, or have maintained high performance by end of Strategy (2028)	On Track / KPI P1: 48% / Objective on track. / KPI P2: 68% / Objective on track.
2.3 Increases in sustainable financing; Global Fund leverage of domestic financing for the three diseases (KPI R1b) / KPI R1b: % of milestones achieved for implementation of mitigating actions by countries at risk of not meeting co-financing commitments	KPI R1b: 80% mitigating actions implemented by countries at risk of not meeting co-financing commitments, assessed annually	Not Met / KPI R1b: 29% / Objective not met.
2.4 Increased investments addressing human rights (KPIs E1, E2a) / KPI E1: % of countries with increases in scale of programs to reduce Human Rights related barriers for a) HIV; b) TB; c) Malaria respectively / KPI E2a: % of countries with at least half of the custom equity indicators performing at minimum acceptable level	KPI E1: 50% of countries in cohort show increase in scale of programming from baseline for a comprehensive response to human rights barriers to HIV, TB, malaria services respectively, for 2023-2025 Allocation Period. KPI E2a: 70% countries have at least half of the custom equity indicators with a performance of 90% or more, assessed annually	Partially Met / KPI E1: HIV 41%, TB 50%, Malaria 100% Objective partially met / KPI E2a: Will be reported for the first time Q4 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses the Global Fund’s impact on key areas of health systems strengthening (HSS), referred to by the Global Fund as Resilient and Sustainable Systems for Health (RSSH); health systems strengthening and integration are key priorities for the FCDO. According to the most recent data, where KPIs have longer term targets aligned with the end of the current strategy period, the Global Fund reports that it is ‘on-track’ to meet them across all relevant indicators. However, none of the KPIs captured in this Logframe, which are assessed against annual targets, have met them for 2024.

As highlighted in a 2024 OIG audit of the effectiveness of the Global Fund model to deliver the 2023-28 strategy, there has been an increase in the quantity of RSSH investments in GC7 compared to GC6, mainly due to the re-purposing of Covid-19 Response Mechanism (C19RM) investments to support RSSH-PPR (pandemic preparedness and response) interventions. As of January 2025, approximately $ 5.9 billion of RSSH investment was estimated to be available for the GC7 period, which included $1.5 billion of direct RSSH investments and approximately $2.4 billion of contributory RSSH investments. The Global Fund also reported increased efforts towards systems strengthening initiatives (rather than systems support) through engagement on systems maturity building and sustainability, and the scaling up of infrastructure and equipment leveraging C19RM. Examples of this work include investments of $432m into Health Information Systems (HIS), $508M into Human Resources for Health (HRH), and $479M into Laboratory Systems, as well as targeted initiatives to strengthen community systems and support community-led monitoring (CLM), such as ‘CLM+’ and ‘Community Pulse’. However, 2024 OIG audits also repeatedly highlight challenges in implementing investments in health systems strengthening, noting grants are well designed but timely execution is an issue. The report also notes that many countries still lack national strategies for HSS and are hampered by the lack of quality data for planning and sub-national tailoring; insufficient availability and use of data is a weakness that is highlighted several times in this and the previous annual review. This is a chronic issue that FCDO have seen across many countries, with bottlenecks in the use of data occurring even where sufficient data is available. In addition, many countries are using multiple different information systems; the Global Fund should work with other investors to ensure systems are joined up and look to create an integrated HIS that works for sub-national tailoring.

In January 2025, the Board approved a limited time extension to C19RM. This extension will provide an opportunity for the C19RM Investment Committee, guided by the Secretariat, to identify opportunities where additional time can optimize delivery, address challenges, and scale up RSSH/PPR activities. This additional flexibility will be particularly useful given the growing resource constraints that the Global Fund and countries face. An update to the Board in May 2025 described how the Global Fund have scaled up RSSH investments at unprecedented rate through GC7 allocations, following the establishment of an Implementation Acceleration Initiative at the end of 2023. Since then, a cross-divisional Secretariat Integration Working Group has been set-up to discuss ways to further support countries’ efforts to enhance and accelerate integration through differentiated approach with aim to improve programmatic outcomes, efficiency, and sustainability. As a result of these efforts, 17 high priority countries have now developed RSSH workplans, and monitoring and issue resolution cycles have been implemented in all priority cohort countries. Another key RSSH milestone in 2024 was the completion of the first targeted Health Facility Assessments (tHFAs). tHFAs were conducted in 16 countries to assess the provision of integrated, people-centered services at health facilities, and the support that health workers receive to provide quality care. The results from these assessments will serve as the baseline scores for assessing improvement in integrated people-centered quality service provision via RSSH KPIs including S2. Whilst we await the data for these KPIs, the FCDO would like to see the Global Fund further build momentum on the integration of services moving into GC8, both at programme and institutional level (policy, strategy, data and capacity).
The key area of underperformance under this output is indicator 2.3 ‘Increases in sustainable financing’. Whilst GC7 co-financing currently shows an increase on GC6 baselines, the 2024 OIG report on the effectiveness of the Global Fund model to deliver the 2023-28 Strategy still rates catalysing domestic resources as requiring ‘significant improvement’. KPI R1b fell significantly short of its target, with 29% of mitigating actions implemented by countries at risk of not meeting co-financing commitments compared to a target of 80%. This underperformance is driven by challenges including delays in the adoption of new processes by countries, the complexity of existing mitigating actions, and mismatches between risk and KPI reporting timelines. The Secretariat is supporting countries in addressing these issues, including through close review and acceleration of the implementation of mitigating actions, actively monitoring progress through grant processes, and increasing engagement and communication with countries on the implementation of mitigating action. KPI R1a is not captured in this Logframe but tracks the realisation of domestic financing commitments. This too remains off-track which is attributed largely to macro-economic challenges and extenuating circumstances in-country, missing data, and changes in the expenditure verification processes. FCDO do recognise however that there is a significant lag period on the reporting of KPI R1a as it tracks implementation of GC6 commitments, and so is not necessarily representative of the current situation. Looking forward, the Secretariat is placing a greater focus on improving systems and processes for regular monitoring of co-financing progress and looking at ways to better hold country stakeholders accountable to their reporting requirements. It will also be vital for the Global Fund and other partners to remain engaged in the development of national health financing strategies and other country level planning processes to support improvements in health financing through the remainder of GC7 and into GC8, particularly in countries most vulnerable to changes in external financing.
Indicator 2.4 has been assessed as ‘partially met’; this does not take into account the lack of data for KPI E2a. KPI E1 measures improvements in the response to human rights barriers in HIV, TB, malaria services respectively. HIV was the only area that failed to meet the 50% target, but FCDO do acknowledge the higher baseline for HIV meaning slower progress comparative to the other diseases can be expected. For TB, the biggest improvement was seen around ensuring people-centered and rights-based TB services are being provided at health facilities, but 30% of countries are still reported to rely on one-off, pilot programs without ongoing subnational implementation. For malaria, all programme areas saw an increase in scores in 2024 compared to the baseline, with the greatest increase noted around monitoring and reforming laws, regulations and policies. Overcoming human rights related barriers is critical in ensuring equitable access to prevention, testing and treatment services across the Global Fund portfolio, and this work is becoming more challenging in the current context with anti-rights and anti-gender movements gaining traction. As outlined in the Breaking Down Barriers Initiative report[4] in 2024, the work of the Global Fund to support and sustain community-led interventions, strengthen national ownership, integrate programming, and implement cross-cutting approaches based on strong partnerships will all be essential in continuing to scale-up human rights programs and ensure long-term, equitable access to health services.
[4] crg_2024-progress-reduce-human-rights-related-barriers-hiv-tb-malaria_summary_en.pdf

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The previous annual review used KPIs from the 2017-22 strategy period as data for the above KPIs was not yet available. In addition, indicator 2.2. previously had a qualitative target to assess National Reference Laboratories as no suitable proxy for KPIs P1 and P2 were available. This is therefore the first year that the annual review is based fully on 2023-28 KPIs as was originally planned at the stage of programme design. No other changes have been made to this output; targets for the third year of the programme will now be set.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation from Previous Annual Review	2024 Progress
The Global Fund should review results of the planned RSSH investment in GC7. In countries where RRSH progress is slow or weak, GF should provide additional support.	As of January 2025, approximately $ 5.9 billion of RSSH investment was estimated to be available for the GC7 period. Some priority areas of RSSH investment include supporting health sector governance for integrated people-centered services ($118 million), Human Resources for Health (HRH) and Community Health Worker (CHW) ($508 million), and laboratory systems ($479 million). / Moving forward, prioritization and sustainability should be key goals, with each focus area having measurable sustainability indicators by the end of GC8. Integration efforts and partnerships with other organisations must deepen at organisational and institutional levels to enhance system strengthening.
The Global Fund should prioritise supporting countries to implement their planned RSSH investments in GC7 to lay the groundwork for stronger RSSH in GC8. This should clearly demonstrate a pathway to integration of services into primary health care systems, demonstrating a wider health systems strengthening approach that includes, human resources, health financing, information/surveillance systems.	Strong performance of GC6 grants is demonstrated by In-Country Absorption (ICA) including RSSH modules that are catching up on past implementation delays. GC7 grants are at an early stage of implementation and investments in RSSH related activities require time to materialize. / The Secretariat are in the process of preparing guidance ahead of GC8 grant applications; we expect to see the commitment to RSSH and integration incorporated into this across all possible funding scenarios.
The Global Fund should ensure that stratified data is properly used to undertake sub-national and community-centred programming, especially in sub-national regions with a high burden of disease.	We have observed a strong focus on improving quality and use of data in-country. This includes investments directly into RSSH in the way of supporting countries to build robust and integrated data management and reporting systems. There are also efforts underway to improve oversight and monitoring of RSSH investments and enhance accountability of country-stakeholders with regards to reporting. / KPI S7 which tracks the percentage of countries that have documented evidence of using disaggregated data for planning or decision-making is showing incremental progress in disaggregated data use among the High Impact country portfolio.
The Global Fund should work to implement the recommendations on co-financing in the Strategic Review (2017-22), and next steps as proposed to the Board following a co-financing update in November 2023.	The Secretariat has demonstrated progress across the recommendations; specific progress against sustainability and co-financing are discussed in this review. / In November 2024, the Board approved a package of sustainability reforms including a revised Sustainability, Transition and Co-financing policy. These policies will be reviewed again in 2026. / FCDO would now look to see further evidence of how these policy changes will be operationalised; we await further updates from the Secretariat on this and on guidance produced ahead of GC8.

2025 Recommendations:

The Global Fund should prioritise sustainability planning across all existing and future grants, supporting countries in developing plans to mobilise domestic resource and transition towards self-financing for health systems, ensuring these are integrated with wider HSS efforts in country. This commitment should be evidenced through Secretariat-led efforts to define transition pathways for every portfolio under GC8, alongside routine reporting on relevant KPIs and transition progress.
FCDO to establish an approach to coordinated monitoring and engagement of sustainability and transition across the Global Fund, the World Bank, and other partners to ensure alignment and accountability.

The Global Fund should accelerate integration of services, ensuring integration goes deeper to organisational and institutional levels. Whilst key baselines for measuring integration have been established, evidence of implementation remains limited. FCDO expects integration to be actively supported and embedded across all levels of the Secretariat as a core policy objective, with clear accountability mechanisms and reporting structures to the Board and/or Strategy Committee.

Output Title	Tackling Global Challenges
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Enhanced support to local production of high-quality health commodities (KPI S9) / KPI S9: % of priority products with the desired number of suppliers that meet Quality Assurance requirements	KPI S9: 90% of priority products have desired number of suppliers that meet quality assurance requirements. / AND / Brief qualitative status update on progress on the regional manufacturing efforts.	Met / KPI S9: 94% Objective Met. / Positive Status Update Received
3.2. Maximised support to woman and girls / (KPIs H5, H6, M4, S3, E3b) / KPI H5: Portfolio performance for % of high-risk adolescent girls and young women reached with HIV prevention programs / KPI H6: Portfolio performance for % of pregnant women living with HIV who received antiretroviral medicine to reduce the risk of vertical transmission of HIV / KPI M4: Portfolio performance for proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment for malaria ( IPTp3) / KPI S3: % of countries with improvement in scores for provision of HTM integrated services to pregnant women from latest baseline / KPI E3b: % of countries with at least half of the gender indicators performing at minimum acceptable level	KPI H5: Grant portfolio performance at or above 90%. / KPI H6: Grant portfolio performance at or above 90%. / KPI M4: Grant portfolio performance at or above 90%. / KPI S3: 100% countries improved scores compared to latest baseline (2023, 2025) by mid Strategy (2025) and by end of Strategy (2028) / KPI E3b: 70% countries have at least half of the gender indicators with a performance of 90% or more.	Partially Met / KPI H5: 103% / Objective Met. / KPI H6: 92% / Objective Met. / KPI M4: 80% / Objective Not Met. / KPI S3: Will be reported for the first time Q4 2025. / KPI E3b: Progress from the baseline will be reported for the first time Q2 2026
3.3 Enhanced focus on meeting the needs of the marginalised and hard-to-reach population (KPIs H4, E2b) / KPI H4: Portfolio performance for coverage of prevention programs among specific Key Populations / KPI E2b: % of countries with at least half of the custom equity indicators showing a faster progression compared to the standard indicator	KPI H4: Grant portfolio performance at or above 90%. / KPI E2b: 70% countries have at least half of the custom equity indicators showing faster progression compared to standard indicator	Partially Met / KPI H4: 87% / Objective Partially Met / KPI E2b: Progress against the baseline will be reported for the first time Q4 2026.
3.4. Continued effective humanitarian response	Ensure continuity of prevention, treatment and other essential services for the three diseases in emergency situations, through: / Reprogramming of existing grant funds - undertaken as a first option. / If reprogramming cannot cover prioritized needs, additional funding through the Emergency Fund Strategic Initiative may be provided (subject to available funding).	Met / As of November 2024, the Global Fund had released US $14.2 million in emergency funding to support countries facing emergencies to mitigate the risk of disruption to HIV, TB, and malaria services.
3.5. Enhanced response to climate change	1. Develop a clear strategy and plan to integrate climate into GF operations through GC8 and beyond, taking on board lessons learnt from GC7, C19RM and the Climate & Health CI 2. Undergo capacity building work with CCMs/PRs to: - Ensure climate and health are integrated into grant applications - Support the use of climate and health data at country level to inform planning - Develop climate action plans, focusing on highly vulnerable countries as a priority 3. Work with partners to shape the international climate-health finance agenda and drive forward improvements in the quality and quantity of climate-health financing to protect HTM gains 4. Develop and agree a methodology for classification of GF resources/actions against ICF	Met / See update below.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses the Global Fund’s contribution towards global challenges which align with the UK Government’s international development priorities, including championing rights and equality, empowering women and girls, and building systems that are resilient to climate impacts and other shocks. The Global Fund have performed generally well across this output, with some areas for improvement highlighted below.

KPI S9 (indicator 3.1) results for 2024 are positive, with 34 out of 36 priority products having the desired number of suppliers meeting QA requirements. Of the 36 priority products in the 2024 KPI cohort, 14 are for HIV, 11 for TB and 11 for malaria. Across the three diseases, Malaria is somewhat lagging, with 2 malaria high volume products continuing to have an insufficient number of suppliers this year. Supply continuity constraints are also observed for Chlorfenapyr Dual AI nets, which were added to the list of priority products in 2024. However, the Global Fund now has five WHO-prequalified suppliers for Chlorfenapyr Dual AI mosquito nets, compared to only two in mid-2024, and expect to begin procuring Dual AI nets from Africa-based suppliers within the next 12–18 months. This is a very positive development and FCDO support the increased priority being placed on the supply of Dual AI bednets, particularly from African manufacturers; these are highly effective at interrupting transmission which is one of the primary objectives of malaria interventions.

The Global Fund are supporting capacity building for African manufacturing under the NextGen Market Shaping strategic initiative, working with partners such as MedAccess and Unitaid, both of which are also funded by the FCDO. For example, the UK’s set-aside from our Global Fund contribution, the Global Fund Accelerator (GFA) programme, specifically funds a market shaping grant with MedAccess, improving value for money for the Global Fund, increasing access to commodities, and generating cost savings across the broader procurement ecosystem. Current areas of work under the Global Fund’s NextGen initiative include the provision of Technical Assistance to support regional manufacturers and regulators, funding for a pilot scheme for local manufacturers of HIV ARVs, and the production of guidance including a technical brief on regulatory systems strengthening and a regulatory systems strategy for the organisation. Some key highlights from the Global Fund’s market shaping work in 2024 include:
- HIV self-tests: 200,000 HIV rapid self-tests manufactured by a supplier based in Cape Town, South Africa.
- ITNs: More than 16.8M insecticide-treated nets were procured from an Africa-based supplier (n.b. majority were non-dual AI nets and FCDO is keen to understand if these same suppliers are building capacity to switch to Dual AI for future procurements)
- ARVs: First delivery of Tenofovir/Lamivudine/Dolutegravir (TLD) manufactured in Africa shipped in 2024.
- 37% of total Artemether Lumefantrine demand to treat malaria was supplied from Africa-based suppliers. This represents a 13% increase since 2021.
- New supplier qualified by WHO’s Pre-Qualification Programme for sulfoxide-pyrimethamine (SP) tablets for preventing malaria in pregnant women.
- 61% of general medicines procurement (in volume) for Africa was fulfilled by African manufacturers

Moving forward, FCDO would like to see the Global Fund continue to scale up the manufacturing and distribution of new technologies, particularly Dual-AI bednets. Furthermore, we are keen to understand if the Global Fund have longer term goals that they are aiming for in terms of the quantities that they would ideally be procuring from Africa in the future, i.e. what does success look like in this space?
We also encourage the Global Fund to take a longer-term approach to considering the VfM of regional manufacturing efforts, recognising that commodity prices may be higher in the short term, but these efforts will lead to longer-term gains in terms of greater sustainability by building local economies and driving self-sufficiency.

Indicators 3.2 and 3.3 under this output are interrelated, and assess the Global Fund’s ability to reach key, vulnerable, and marginalised communities, addressing gender and human rights related barriers to drive health equity. As well as advocating for this through our engagement with the Global Fund (i.e. using Board and Committee seats, our annual strategic dialogue etc.), FCDO are supporting initiatives through the Global Fund accelerator to strengthen community rights and gender in health programmes, with a technical assistance programme delivered in partnership with BackUp focused on programming through a community, rights and gender lens. Where data is available, KPI performance across these two indicators is generally strong, reflecting the commendable progress made in integrating gender equality and human rights into Global Fund grant-making. Technical Review Panel (TRP) assessments report that nearly half of GC7 funding in Windows 1-5 of GC7 focused on gender equality, and an increase in the quality of Funding Requests from Breaking Down Barriers[5] (BDB) countries was observed in terms of quality of focus on relevant priorities. Despite these efforts, areas for improvement remain. Both OIG and KPI reporting reveals underperformance in areas of service delivery, such as for M4 (80%) where several countries face stock-outs and late antenatal care attendance, and hinderances in programme design as a result of data gaps and a lack of community engagement within Country Coordinating Mechanisms (CCMs). These issues have led to a theme seen through multiple OIG audits of difficulties in executing interventions effectively targeting vulnerable populations. The Global Fund is working to improve performance by enhancing collaboration between malaria and maternal health programmes to boost antenatal care coverage and reduce stock-outs, including introducing community-level IPTp delivery in hard-to-reach areas.
[5] ‘Breaking Down Barriers’ is a strategic initiative which delivers technical assistance to tackle human rights-related and gender-related barriers to HIV, TB and malaria services.

As highlighted by previous annual reviews, there is a need to increase coverage of prevention services (H2, 87%), but the Global Fund are making good progress. The Secretariat continues to coordinate across the partnership to accelerate HIV prevention product introduction and to address barriers to access, and in 2023, the Prevention Outcome Monitoring Toolkit (POMT) was launched to improve the monitoring of HIV prevention outcomes to focus implementation and prioritization. FCDO acknowledge the challenges faced by the Global Fund and by countries, with anti-rights movements and shrinking civic space threatening access to services for key populations. Given the increasingly challenging operating context and wider resource constraints, there is a growing need for the integration of gender equality and human rights considerations into all grant applications and monitoring frameworks, and for any prioritisation discussions to be well informed by the needs of implementing country governments, balanced with what those who work most closely with the vulnerable (e.g. civil society groups) have identified as areas of need.

Indicator 3.4 assesses the Global Fund’s ability to respond to health needs in countries affected by humanitarian crisis, referred to within the Global Fund portfolio as challenging operating environments (COEs). COEs account for approximately one-third of the global disease burden for HIV, TB and malaria and over 30% of the Global Fund’s funding allocation for grant cycle 7 In his update to the Board in November 2024, the Executive Director (ED) of the Global Fund reported that $14.2 million had been released through the Emergency Fund (EF) strategic initiative in 2024, with an extra $30 million added to the EF budget, and an additional $45 million to target critical emerging needs, approved by the Audit and Finance Committee (AFC) in October 2024. The Global Fund continue to demonstrate their ability to support countries to rapidly respond to crisis. For example, in response to the Mpox outbreak, over $19 million from C19RM was provided to the Democratic Republic of the Congo (DRC), Rwanda, Ghana, Côte d'Ivoire, Uganda, Liberia and Burundi through a combination of reprogramming and Portfolio Optimization. In terms of what this funding is able to achieve, in DRC as an example, it was used to enhance disease surveillance and laboratory systems, support community-based awareness raising and education programs, reinforce infection prevention and control measures to protect frontline health workers.
With regards to output 3.5, in 2024, the Global Fund completed an assessment of the global climate adaptation finance gap (i.e. international financing available for climate, or ICF), and a review of international finance tracking and reporting frameworks and guidance. This has been used to inform the approach to track and report on climate-related investments for GC8, and a draft methodology for classifying Global Fund resources in alignment with the ICF framework has been produced and shared. The Fund also conducted a comprehensive review of country and programmatic needs related to climate impacts on HIV, TB, malaria, and health systems, identifying priority interventions in collaboration with technical teams. To build awareness and guide climate-health planning in countries, a new interactive learning package was developed for Country Coordinating Mechanisms (CCMs), with initial rollout planned for mid-2025. In January 2025, the Global Fund announced a $50 million Climate and Health strategic catalytic fund in partnership with the Gates Foundation and Sanofi to bridge the climate-health finance and capacity gaps. This should be particularly impactful for high burden malaria countries who are most vulnerable to climate volatility, and FCDO look forward to receiving updates on the operationalisation of this fund. The Global Fund also continues to engage globally through platforms like COP28 and partners with organizations such as WHO, the World Bank, and the Green Climate Fund to align health and climate goals. The Secretariat provided a comprehensive update on climate-health activities to the Strategy Committee and the Board in November 2024, and are due to provide a similar update with more information on specific programs and progress in late 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The description of indicator 3.4 was changed from 'Enhanced response to humanitarian crisis' to 'Continued effective humanitarian response'. The rationale for this change was that this was an area that the Global Fund do well, and our expectation therefore is that this is maintained rather than enhanced year on year.

In addition, the previous annual review used some KPIs from the 2017-22 strategy period as proxies where data for the above KPIs was not yet available; these have now been replaced by the 2023-28 KPIs as originally planned. No other changes have been made to this output; targets for the third year of the programme will now be set.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation from Previous Annual Review	2024 Progress
The Global Fund should take forward the recommendations on gender equality and human rights in the Strategic Review (‘SR’, 2017-22), as noted in the Secretariat response.	The Secretariat 'partially accepted' the SR recommendations – recommendations were not accepted where the ‘action plan' overlapped with work already being carried out. In preparation for GC8, the Board approved a Catalytic Investment to Address Human Rights and Gender Barriers, which will help countries scale up evidence-based gender equality and human rights initiatives to improve HTM outcomes. Additionally, gender considerations will be integrated into Catalytic Investments to Build Community Networks & Engagement and improve HIV, TB, and malaria outcomes through integration with reproductive, sexual health, maternal and newborn services.
The Global Fund should develop and implement a robust monitoring approach for gender equality interventions as a matter of priority, ahead of planned gender and equity evaluations.	Data for some of the dedicated gender, equity and human rights KPIs is now available. Regular reporting on performance against these to the Board continues as part of the broader Strategic Reporting. FCDO would welcome more specific reporting on the catalytic investments on gender equality as well as thematic reporting on the impact of gender and equity investments. / An ELO (Evaluation and Learning Office) Evaluation on Human Rights barriers due to start in July 2025, with the final report expected in May 2026.

2025 Recommendations

- The Global Fund should ensure clear applicant guidance for the integration of human rights and gender considerations into grant proposals is available and updated in line with the current context; FCDO’s GFA advisors to provide technical support to this as needed.
- FCDO to review the Global Fund’s Evaluation on Human Rights Barriers once made available

Output Title	Organisational effectiveness
Output number:		4	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. Collaborative leadership across the international system; evidence of Global Fund engaging with GAVI and GFF at HQ and country level to enhance coordination and alignment, including participation in coordination structures and transparent sharing of workplans and budgets.	Strong demonstration of commitment, including action at the country level, to working with Gavi, the GFF, and others in line with the agreed deliverables of the four workstreams, and in relation to aspects of the Lusaka Agenda that align with the GF’s strategy.	Partially met / See update below
4.2. Enhanced management for value for money and impact	A commitment by the Global Fund to improve the VFM technical brief for GC8 during 2025 Global Fund to share a progress update on the VfM roadmap with the FCDO by May 17, 2025. Global Fund on track to deliver in line with the milestones/deliverables defined within the VfM roadmap (pending specifics due early 2025)	Met / VfM Roadmap endorsed by the MEC in 2024. / Progress update received May 2025; workstreams include updating VfM guidance ahead of GC8.
4.3. Enhanced focus on delivering impact in challenging operating environments through Global Fund grant management	Build knowledge by sharing with CCMs, PRs and CTs best practices and experiences in delivering services in COEs. / Support in-country engagement with CTs, PRs and CCMs and relevant partners in a sub-set of COE portfolios to identify key implementation challenges and co-create adaptive approaches The Secretariat to take forward the agreed actions from 2024 Review of the Additional Safeguards Policy (ASP)[6]	Met / The Global Fund has effectively supported Country Teams (CTs), Principal Recipients (PRs) and CCMs managing grants in COEs, strengthening in-country engagement with relevant partners in 2024. / The Secretariat has made progress across all commitments relating to ASP reform.
4.4 Strong risk management (KPIs R2, F3) / KPI R2: % of countries meeting criteria of timeliness and quality for audit deliverables / KPI F3: Portion of grant budgets that have been reported by country programs as spent on services delivered / Fraud and Fiduciary risk within the Board approved Risk Appetite, reported through regular (semi-annual) reporting	KPI R2: 80% countries meet criteria for timeliness and quality of audit deliverables, assessed annually / KPI F3: For each Allocation Period, in-country absorption by end Y1: 75%, Y2: 80%, Y3: 85% / Fraud and Fiduciary risk reported within the Board approved Risk Appetite	Met / KPI R2: 80% / Objective met. / KPI F3: 85% / Objective met. / Fraud & Fiduciary Risk: Moderate / Within risk appetite as of December 2024,
4.5. Prevention of sexual exploitation, harassment and abuse of power	1.Ensure all allegations of SEAH brought to the attention of the Global Fund are appropriately managed with a victim/survivor-centred approach. 2.Develop guidelines and toolkits to support in-country partners to deliver a victim/survivor-centred response to all SEAH allegations. 3.Develop online modules, training, and guidance to support PR PSEAH capacity building activities across the GF’s nine capacity standards 4.Ensure beneficiaries of Global Fund support programmes are informed of their rights to access them in a safe and inclusive environment free from the threat of SEAH, and know the options available for making a report. (Year 1: On track to pilot an awareness raising initiative in two countries (Phase I); Year 2: On track to scale pilot (Phase II); Year 3: On track to further scale pilot (Phase III)	On Track / 1.On track and progressing well – currently finalizing terms of reference for the multi-disciplinary approach to sexual exploitation, abuse and harassment cases adhered to by OIG and Ethics throughout Y2 of GC7 / 2.On track and progressing well – published the PSEAH Briefing Note for Country Coordinating Mechanisms (CCMs) Victim/Survivor Support Services Protocol, Self-Assessment for SEAH Reporting Mechanisms, and Checklist for Addressing Incidents and Allegations of SEAH / 3.On track and progressing well – online resource library structured across 9 PSEAH capacity standards was populated with a variety of resources in 2024 and will continue to grow in 2025 to include bespoke guidance for GF implementers and CCMs / 4.On track and progressing well – Three countries piloted the beneficiary-facing awareness campaigns in Y1, and 3 additional countries were added in Y2
4.6. Country-Coordinating Mechanism (CCM) Evolution	% of Global Fund High Impact (HI)/Core CCMs reaching Oversight Maturity Level 2 (NB. Levels = 0-3). / Year 2 (2024) Target: 37%	Met / 2024 Result: 36% / Objective Met.
[6] Agreed Secretariat actions: - Undertake a review of all countries currently under the ASP by Q4 2024. - Work with country stakeholders to develop an ASP exit plan which is fully aligned with their ASP exit criteria - Establish a monitoring strategy which provides a clear framework of the frequency and scope of monitoring a country’s progress in meeting its ASP exit criteria - Work with Country Coordinating Mechanism (CCM) and PRs to identify mechanisms to provide the necessary technical and coordination expertise to support country-led capacity building efforts, working with additional partners where appropriate and tailored to the unique country context

Briefly describe the output’s activities and provide supporting narrative for the score.

This output assesses how grants are designed and delivered to maximise value for money and impact, particularly for the most vulnerable, and to manage risk, including the risk of sexual exploitation, abuse and harassment (SEAH). Additional areas of evaluation added to this output for GC7 include the delivery of the CCM Evolution strategic initiative, and progress towards Global Health Institutions alignment per the recommendations of the Lusaka Agenda.

The last annual review described the formation of the joint committee working group (JCWG) following the agreement of the 4 joint workstreams in late 2023. Since then, the JCWG has made some gains, most notably within the Malaria workstream, but progress has been slow in other areas, leading to the assessment as ‘partially met’. Feedback from JCWG meetings highlights a lack of clarity within the HSS workstream, particularly around collaboration objectives and a roadmap to implementation, and a more general observation that it has been difficult for the JCWG to see evidence of and track progress. FCDO acknowledge that progress within these workstreams requires collaborative efforts from all partner organisations and recognise the leadership of the Global Fund in establishing and advancing the work of this committee. We are encouraged to see Global Fund leadership demonstrating a personal commitment to collaboration, with the ED engaging actively with the leads of other organizations to understand current challenges and opportunities and motivate and guide joint working. We also positively note additional areas of collaboration that the Global Fund are exploring with others, including across funding applications, audits, and at country level, for example with the joint missions to Ethiopia and Mozambique which took place in 2024. Given the importance of collaboration to the long-term work of the Global Health Institutions (GHIs), this area must continue to be a priority. FCDO would therefore like to see an increase in senior-level visible commitment to drive this agenda forward, and for the Global Fund and others to set an ambition for combined GHI applications, funding policies, procedures and replenishment cycles in the future.
The key deliverable in terms of improved value for money in Global Fund grants in 2024 was the endorsement of a Value for Money (VfM) roadmap by the Management Executive Committee. This roadmap comprises of multiple workstreams led by stakeholders from Departments across the Secretariat and coordinated by the Health Finance team; it is not designed to reflect all Global Fund efforts on Value for Money, but to prioritize areas where the Secretariat could make additional, tangible improvements in VfM work-streams and further embed VfM efforts into Global Fund operations ahead of GC8. Final implementation of the roadmap is due March 2026, with the next interim update to Global Fund management due in summer 2025. This interim update will take into account the evolving external context, including ongoing efforts to strengthen prioritisation and efficiency within existing grants, given pressures on external financing. Global Fund note that workstreams under the roadmap are likely to evolve during implementation, but current ambitions include creating harmonised payment scales for health workers, enhancing program management cost analysis, and improving VfM guidance ahead of GC8.

With regards to output 4.3, the Global Fund has effectively supported the management of grants in COEs in 2024. Led by the Implementation and Challenging Operating Environments (ICOE) team, in coordination with country teams, regular situational updates have been used to identify and facilitate targeted support, and identify and support relevant partners, for example in Haiti following the escalation of conflict in early 2024. At the global level, the Global Fund hosted its 5th COE workshop, “Differentiate to Accelerate,” in June 2024, bringing together over 110 global participants to share knowledge and build capacity. The event focused on addressing challenges in emergency response and service delivery in complex settings, with participants developing actionable strategies for national and sub-national implementation. Significant progress has been made in the ASP exit criteria review, with revised criteria approved for 28 of 29 countries; the final review is pending completion of an OIG audit in May 2025. The Secretariat is advancing its management response to the OIG ASP advisory by supporting Country Teams (CTs) with tailored communication, developing ASP exit roadmaps, and collaborating with partners on targeted technical assistance. Additionally, best practice materials such as toolkits and templates are being developed, and internal monitoring mechanisms are being enhanced to track country progress and ensure effective oversight. A weakness of the ASP noted by a DAI report commissioned through the GFA was the lack of clarity over the standard guidelines/milestones that a country must comply with; the Secretariat’s efforts in 2024 should be a very positive step in overcoming this.
The Global Fund continues to demonstrate robust risk management, with ‘fraud & fiduciary Risk’ remaining within the risk appetite and both KPIs R2 and F3 meeting their targets for 2024; both of these KPIs are important to monitor how effectively risks within grants are identified and mitigated, and how much of the allocated funds are actually being used to deliver the required services. For the former, 12 out of 15 (80%) countries where Supreme Audit Institutions (SAIs) perform audits on grants met the criteria for timely, quality and compliant audits, demonstrating a significant improvement compared to the 2023 result (47%). The Global Fund acknowledge a need to further improve across the three metrics, particularly ‘timeliness’, and are working with countries to understand the root cause of any delays, and support improvement in performance through an SAI engagement note and targeted training. By the end of 2023, in-country absorption (ICA, KPI F3) for GC6 reached 85%, with over 80% absorption across most grant components. Absorption was slightly lower for the HIV prevention module (80%), driven by one underperforming component (condom and lubricant programming), and for the RSSH stand-alone grants (63%). RSSH absorption has shown a trend across previous grant cycles of lagging behind to then catch-up in the last year of implementation. This is due to the greater time taken to design and implement RSSH initiatives, as well as challenges in accurate budgeting given the longer time horizon.

Prevention of sexual exploitation, harassment and abuse of power (PSEAH) is a programme area that the Global Fund have been rapidly maturing in over the last few years, moving now towards more of a steady state in terms of progress. 2024 saw a lot of activity to continue capacity building and training across the partnership to ensure all stakeholders knew how to identify, manage and respond to incidences of PSEAH. Although initial plans for in-country workshops in 2025 had to shift due to changing circumstances, the ambition remains strong, with a pivot towards scalable, on-demand online training made to allow capacity building work to continue. Additionally in 2025, a pilot initiative through CCMs is being run to test local ownership of awareness campaigns in countries, tailored to community needs. Good progress has been made against all four aspects of the target set for this indicator, and FCDO are assured of the Global Fund’s commitment to safeguarding against PSEAH. This was also reflected in FCDO’s Central Assurance Assessment (CAA) which was conducted in 2024 and highlighted a strong leadership commitment to safeguarding, clear oversight, and active engagement in PSEAH across the organisation.

Finally, output 4.6 tracks progress in CCM maturity building, in line with the objectives of the CCM Evolution strategic initiative which ended at the end of 2023. The 2024 result shows a 14% increase on 2024. Whilst this has fallen just below target, FCDO recognise that funding for CCM Oversight Officers is increasingly constrained given broader fiscal challenges and encourage the Global Fund to make use of our GFA advisors to support further engagement with CCMs in GFA countries. There is strong evidence of the Global Fund continuing to prioritise capacity building across CCMs in a range of areas, including with initiatives mentioned throughout this review, and so this indicator has been assessed as ‘met’. It is critical that momentum increases towards evolving the CCMs with changes in the wider health architecture, ensuring focus on the future including on RSSH, integration and equity.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The previous annual review used KPIs from the 2017-22 strategy period as proxies where data for the above KPIs was not yet available. This is therefore the first year that the annual review is based fully on 2023-28 KPIs as was originally planned at the stage of programme design. FCDO changed the year 2 target for indicator 4.2 to incorporate the new VfM roadmap developed in 2024. Additionally, the Global Fund changed the year 2 target for their CCM evolution initiative (indicator 4.6) from 48% to 40%; this was deemed a more realistic target given resource constraints which are expected to continue in 2025. No other changes have been made to this output; targets for the third year of the programme will now be set.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from Previous Annual Review	2024 Progress
The Global Fund should continue to work with GAVI and GFF to progress the 4 workstreams delivering tangible action in a set of first waves countries (also see recommendation under output 1).	There have been challenges in building momentum with the JCWG (see output 1) and deliverables for the group are yet to be agreed. / There has been evidence of other areas of collaboration across the GHIS such as collaboration with Gavi on evaluation efforts (noted in the IEP annual review), funding request reviews (noted in the TRP performance report to the Strategy Committee) and ambitions for aligned audits (noted anecdotally by the OIG).
The Global Fund should continue with the planned implementation of the VfM roadmap; FCDO to review progress and outcomes reported to the Audit and Finance Committee.	See output 4.2
The Global Fund Secretariat and Independent Evaluation Panel should determine scope and timing of the partnership evaluation, (as previously recommended in the Annual Review year 3 of the GC6 programme).	No partnership evaluation yet planned that we are aware of.
The Global Fund should prioritise capacity building and assessment of Principle Recipients around PSEAH.	Capacity building efforts are progressing well (see output 4.5). / FCDO’s CAA completed in 2024 (and due for sign off in 2025) highlighted a lack of capacity building at sub-recipient and sub-sub-recipient level (where most SEAH is reported) and so recommended that additional support/guidance is produced for Principal Recipients that will support the strength of downstream partner capacity assessments, and the effectiveness of risk mitigations and beneficiary engagement.
The Global Fund should continue with planned implementation of the CCM evolution; FCDO to review progress and outcomes reported to the Strategy Committee.	See output 4.5

2025 Recommendations

The Global Fund should continue to actively pursue and strengthen collaboration with other GHIs, including Gavi, the World Bank and the GFF. This effort should be visibly championed by senior leadership, with a clear roadmap for sustaining momentum beyond the conclusion of the Joint Committee Working Group (WG) in late 2025.
Output Title	Global Fund Accelerator
Output number:		5	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1 – Technical Assistance (TA) partners (Back UP and CHAI) act as a catalyst in selected countries to strengthen health systems and promote provision of integrated preventative and curative health services	N/A for BACKUP Health / 0 number of countries for CHAI	Not on Track / CHAI has completed their inception period and started to commission TA in various countries including on integrated primary health care, joint planning and budgeting and support to health financing dialogues. / BACKUP’s only milestones are its baseline and final target due to the project’s short life cycle and so cannot be assessed for FY24/25. / Despite, slow progress both GFA TA partners still maintain confidence in achieving their output and outcome milestones by the end of GFA 7’s life cycle with some promising work already demonstrated within the later stages of this financial year. / In the second year of the GFA we expect to see improved focus and delivery on integration, Global Cycle 7 (GC7) reprioritisation as well as GC8 preparation with improved collaboration with GFA advisers.
2 – Improved quality, design and integration reflected in Global Fund investments in targeted countries (through GFA Health Adviser work)	GFA advisers ensure strategic portfolio of TA with buy in from critical stakeholders and governments with CHAI and BU workplan evidence	Met – On Track / In the second year of the GFA, we expect to complete support for GC7 reprioritisation and begin focusing on GC8 funding request through engagement with Country Coordinating Mechanisms (CCM) and other key stakeholders.
3 – Improved strategic approach to GF investments in priority areas (including equity and HRH and integration) through secondee influence	Global Fund, Gavi, GFF Joint Committee Working Group established and collaborative workstreams identified	Met – On Track / Within the first year of the GFA, Secondees have contributed in establishing Global Fund/Gavi/GFF Joint Committee Working Group alongside identifying collaborative workstreams. / This places Secondees in a good position to be able to use these collaborative workstreams to demonstrate real-world change in ways of working in at least 5 countries by the next GFA Annual Review.
4 – Market shaping investments support increased affordable access to treatment, testing and prevention tools for HIV, TB and malaria and contribute to Global Fund value for money (Med Access and CHAI)	MedAccess: / - $4.1M Cumulative Global savings achieved across LMIC procurers through VGs and partnerships / - $1.4M Cumulative savings to GFATM funded procurement programmes through VGs and partnerships / CHAI: / (HIV) Rapid response to donor transitions, focused on procurement, data sharing, and market coordination, while also laying the groundwork to support broader market sustainability and stability / (TB) ~30% negotiated price cut in BPaL/M regimen from ~$430 to $310 per patient course / (Malaria) 0 malaria cases averted in four focal countries by working with national malaria programs to optimize the allocation of Global Fund funding for malaria, leveraging CHAI’s complementary funding from the Gates Foundation	Partially Met – On Track / CHAI developed a set of outcome indicators, one for each disease: / For TB, there is a focus on reduction of costs across both diagnostics and treatments, whilst also scaling up on case finding and prevention post-exposure. The results far surpassed the outcome target of a ~30% price reduction from $430 to $310 per patient course, achieving deals with Lupin that resulted in the full BPaLM regimen dropping below $300 for the first time to just $284 per course—a 34% reduction from the original $430 target / In the malaria space, they are working to maximise the number of cases averted in four focal countries, optimising Global Fund allocations. Whilst no cases were recorded as averted in Year 1, this is as planned with the groundwork the focus as well as planning for scale-up in Years 2 and 3. / Finally, in HIV, CHAI is supporting the HIV commodity market(s) to sustain optimal function, ensuring resilience amid the funding reductions and leveraging innovations to accelerate impact. In year 1, CHAI’s HIV market analysis identified and evaluated actual and potential impacts on supply chains, among other key areas, and, in close collaboration with MOHs, identified the products most at risk of supply disruption. CHAI also worked with major global procurers to develop mitigation strategies, such as advancing orders, and engaged closely with suppliers to provide clear information in a moment of significant confusion and conflicting market signals. This early response laid the foundation for broader efforts, which have since transitioned to other programs, including the Unitaid-funded THRIVE project, and continue to deliver leading analysis on the real-world impacts of funding disruptions. / MedAccess, in this financial year are yet to contribute much towards the market shaping investment outcome. This is due to no deals having yet been secured within this FY. However, MedAccess is well placed to have deals confirmed by the first half of FY25/26 as most of this FY was spent advancing multiple deals towards the latter stages of completion. Additionally, unlike other GFA outcomes, the VFM investment generated by MedAccess’ Market Shaping work only increases as the GFA goes on, as well as post GFA 7 – with post-grant impacts expected to be measured till at least 2032.
5 – Innovative, approaches to delivery of TB prevention, detection and care deliver increased rates of diagnosis and treatment, particularly for marginalised populations	0 (projects only in very initial stage of implementation)	Met – On Track / Currently, no results on additional lives saved can be published as the TB Reach project pivotal to this outcome indicator is only in its initial stage of implementation. / In the second year of the GFA, we expect 17,175 additional lives to be saved.
6 – Improved Global Coordination and Reinvigoration - Roll Back Malaria coordinates global and regional efforts to address high-priority policy issues, with evidence and data used to inform strategic, policy, and decision-making under the Big Push framework.	RBM launches the Big Push coordination framework, formalises SterCo and MIMLG, and activates structured coordination on high-priority policy themes including AMDR	Met – On Track / RBM had made significant progress in strengthening policy coordination under the Big Push framework. Two key mechanisms were formalised: / • The Steering Committee (SterCo) was institutionalised to provide strategic oversight across Big Push pillars and ensure partner alignment on priority areas. / • The Malaria Incident Management and Leadership Group (MIMLG) was launched as a rapid coordination structure for real-time response, policy alignment, and strategic decision-making in emergency or high-risk contexts. / One of the most significant advances under this coordination structure was the development of a more systematic response to antimalarial drug resistance (AMDR): / • In March 2025, RBM and WHO co-convened the Global AMDR Consultation, engaging over 50 representatives from national programmes, regional bodies, research institutions, and technical partners. / • The consultation reached consensus on four sub-regional groupings and formally designated focal points for five sub-regions (West, Central, East, Southern Africa, and the Horn). / • A dual governance model was proposed—combining technical task forces with regional-level policy engagement mechanisms—to enhance responsiveness, coordination, and cross-border information flow. / This meets the milestone for FY24/25 which was ‘launch the Big Push coordination framework, formalise SterCo and MIMLG, and activate structured coordination on high-priority policy themes including AMDR’
7 – Policy research and convening enhance GHI and partner commitments to the Lusaka Agenda	2 policy research reports or convenings produced that enhance GHI and partner commitments to the Lusaka Agenda	Partially Met – On Track / Assessing progress for policy research has been somewhat challenging as whilst one piece of work has been conducted out of the two required, the Policy Fund project was mainly repurposed in this FY in order to improve the Value for Money and progress of other outcomes. As such, it would be most suitable to describe this outcome as ‘partially on track’.

Briefly describe the output’s activities and provide supporting narrative for the score.

5% of the UK’s commitment to the Global Fund funds a set-aside programme managed by FCDO called the Global Fund Accelerator (GFA) programme. The programme is split into 9 different project areas that includes 9 FCDO health advisers in-country with supporting technical assistance programmes, as well as 3 secondments in Geneva, and strategic funding to market shaping and disease focused organisations that can increase the impact of our GF contributions.

The purpose of the GFA is to support the Global Fund’s work in tackling the immediate impact of the three most deadly infectious diseases – HIV/AIDS, tuberculosis and malaria – and put the international community on the right track to end the three diseases as epidemics by 2030. The indicators under output 5 are taken from the ‘outcome’ indicators of the GFA Logframe; performance of the GFA programme against these indicator targets is mixed but overall presents an encouraging picture for the first full year of implementation of GFA7. Whilst some targets have not been met, work undertaken in the past year has laid significant foundations to build upon in the following years of the programme, with progress made towards maximizing the UK’s core investment in the Global Fund.

Summary supporting narrative for the overall score in this review

GFA 7 has earned an overall rating of B, highlighting that it did not meet expectations for some programme elements. Numerous factors have been attributed to this scoring which are outlined below and explored in depth throughout the separate GFA annual review:

Start-up Delays affecting output – Several projects, most notably those which are new to the GFA as part of GFA7, experienced delays in establishing the required capacity for start-up. This was due to three key reasons: 1) unfamiliarity in working with FCDO/GFA, 2) delivering in areas outside of their traditional scope of work through their work with FCDO, and 3) difficult political contexts in specific countries. Of these three examples, three projects were clearly affected as a result of this: Roll Back Malaria, Clinton Health Access Initiative (Specifically in their Technical Assistance workstream), and BACKUP Health. More detail on how these programmes were affected is included within the GFA annual review.

Additionally, the inception period for some projects took longer than expected, especially in projects where increased TA provision and FCDO capacity was required; for example, more time than first anticipated was required to agree and establish robust reporting and monitoring mechanism. However, once working relationships were established and reporting concerns addressed, improvements were seen towards the end of Year 1 and continue to be seen in an upwards trajectory in the early stages of Year 2

Under-utilisation of budgets – This was a key factor in the GFA receiving a ‘B’ rating. Projects across the programme were initially overprogrammed, leading to an overestimation of both spending in the GFA’s first financial year and scope for partners to deliver; the delays described above further increased the underspend. To mitigate this occurring again, FCDO have worked with GFA partners to carry out stringent re-forecasting, and all unspent funds have since been either redistributed successfully or carried over into the programme’s final financial year.

Unprecedented changes in operating context – FY24/25 was a very challenging year, with USG cuts to foreign development assistance and stop-work orders forcing many international health programmes to re-prioritise or close. This has directly impacted several of our GFA partners, such as Roll Back Malaria, who underwent significant budget restrictions which triggered urgent adjustments in programme timelines and delivery.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

At the time of writing last year’s annual review, many of the GFA projects were still in the very early stages and indicators/targets were still to be agreed. This year is therefore the first year that progress against pre-defined targets has been assessed. Targets for the next year of the programme will now be set.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from Previous Annual Review	Progress
FCDO should prioritise the permanent recruitment of the full complement of programme-funded advisers.	Completed – in place: nine in-country GFA Advisers have been set up at post.
FCDO should map strategic priorities and deliverable for all Secondees and GFA advisers and establish in-country TA aligned with these priorities.	Completed – in place: strategic priorities and deliverable have been established in-country for GFA Advisers across the nine GFA countries and for Secondees at post.
FCDO should identify strategic policy research questions for support via the policy workstream.	Partially completed – One policy project has been commissioned so far this year from the policy workstream budget. Further work to be scoped as necessary and as budget allows.
FCDO should embed new Programme Management tools and processes across all projects to ensure consistency in reporting, monitoring and information sharing.	Completed – in place: Quarterly meetings have been standardised across all partner projects with additionally ad hoc steering meetings to ensure quality of reporting, and delivery of outcome and outputs.

Major lessons and recommendations for the year ahead
The overarching major lessons and recommendations for the year ahead are listed below:
Improvement of programme and financial management by partners – As mentioned in the prior section, underspends significantly impacted the GFA score, primarily due to forecast overestimations and slow delivery due to complex political economies and rapid changes in the contexts (multiple crises, political upheaval, changes in partnerships and resourcing in countries). To ensure that GFA 7 utilises its full allocation, partners will need to ensure accurate forecasts and improve delivery as well as to be adaptive and responsive to contexts utilising funding well in agreement with GFA advisers and value for money principles.
Improve collaboration and communication with GFA Advisers – One lesson learned is that the GFA Advisers could be better utilised and informed by partners to set strategic direction and tackle bottlenecks using the various levers available to them including diplomatic engagement, technical expertise, board positions, coordination platforms and HQ levers. Going forward, both CHAI and BACKUP can enhance their impact in line with host country and UK priorities by collaborating more closely with the GFA adviser in country. A strengthened and deepened partnership needs to go beyond programme and financial management to drive change. Successful TA is seen as a critical lever by GFA advisers towards sustainable systems strengthening.
Flexibility – The flexible and adaptive funding enables the TA to meet demand and respond to opportunities that increase impact. In this FY, budget lines from and unallocated spends from other projects were heavily altered, utilised and drawn upon in order to be redistributed so that the programme could pivot underspend to respond to GFA priorities in a rapidly evolving context. This also led to additional funding being distributed to the TB Reach programme thus providing further support in the delivery of Global Fund and GFA’s TB outcomes. It is therefore recommended that the GFA be regularly assessed and further streamlined so that it can continue to be used as a flexible tool to enhance the delivery of other projects (particularly those which are likely to represent good value
2025 recommendations:
FCDO and TA providers to strengthen oversight and financial management in TA workstreams, using insights from advisers in-country to inform accurate forecasting and reporting on budget utilisation.

FCDO to establish and utilise quarterly meetings with GFA Secondees

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The second year of this programme has demonstrated good VfM, aligning with the proposition in the business case. Building on the plans developed in the first year of grant cycle 7, the Global Fund has made advances through the creation and agreement of a VfM roadmap designed to better operationalise economy, efficiency and equity during GC8. As noted by an OIG audit on the effectiveness of programmes to deliver the 2023-28 Strategy conducted in 2024, further embedding of the VfM framework is now needed to deliver on the Global Fund’s ambitious mandate; this roadmap should set the pathway for how this will be achieved. Milestones for the VfM roadmap and progress to date were shared with FCDO in preparation for this review and will continue to be monitored over the next year. In addition, the GFA programme continues to offer good value for money, with investments chosen specifically to complement and increase the value of our core investment.

As highlighted in the previous annual review, key opportunities to strengthen VfM further include with efficiencies made through the integration agenda and on sustainability, for example ensuring RSSH investments contribute to long-term systems strengthening; through market shaping capacity building activities both by the Global Fund (e.g. regional manufacturing, pooled procurements etc.) and across the GFA workstreams; and through ensuring that Global Fund programmes are situated in broader sustainability planning to support the progressive transition to self-financing. Given the increasingly challenging and uncertain global funding landscape, finding efficiencies and opportunities for integration both within the Global Fund and across the Global Health architecture will be vital to maximise impacts and ensure VfM across all current and future investments. The Global Fund are currently working through options for a range of future funding scenarios; FCDO will await the outcomes of this work and scrutinise any decisions made with regards to prioritisation through our seat on the Board and committees.

Economy

The Global Fund makes very good use of economies of scale, working with partners and negotiating directly with manufacturers to secure commodities at lower cost and at scale in many countries. This work has accelerated access to a range of critical testing, prevention and treatment tools, including antiretroviral medicines (ARVs) for people with HIV and bednets for Malaria prevention. Examples of the impact of these efforts include the cost of a 1-year supply of antiretroviral therapy, which has been reduced from more than US$10,000 in 2000 to as low as US$45 per year today, and the cost of insecticide-treated mosquito nets, which have decreased by 33% since 2014.

In addition to the Global Fund’s direct investments, its investments in the fight against HIV, TB and malaria have freed up resources and capacities, making health and community systems better able to respond to other diseases. To the end of 2023, investments from the Global Fund partnership in HIV, TB and malaria programs are estimated to have freed up 2.9 billion hospitalization days and averted 5.5 billion outpatient visits, generating US$103 billion in cost savings and enabling health facilities to tackle other health priorities.

When measured at budget rate (i.e. the exchange rate on the date the budget was set) the total operating expenditure (OPEX) for 2024 was USD 340.6 million. This was USD 1.6 million below the approved OPEX budget and represents 99.5% budget utilization, illustrating the Secretariat’s efforts to maintain budget discipline whilst delivering on key priorities. Total operating costs for the Global Fund are comparatively low compared to other Global Health Institutions and they remain a relatively lean organization with disciplined cost control measures in place. In 2024, the Global Fund reported that OPEX accounted for 6% of total expenditure, a decrease of 2% compared to 2023 driven by a 35% increase in grant expenditure compared to 2023.; benchmarking analysis included in the 7th replenishment investment case (2022) reported that the OPEX of four comparable organisations ranged from 7% to 37%.

The 2025 OPEX budget approved by Board in November; in the preparation of this budget the Secretariat demonstrated a number of cost saving initiatives including a revised travel plan, increased efficiencies, and reduced professional costs. The proposal also highlighted the immediate priority for 2025 of stabilisation and preparation for 8th replenishment, with a longer-term view to drive forward a new wave of sustainability measures.

Efficiency

The Global Fund follows a transparent Allocation Methodology, distributing funds based on need through consideration of a country’s economic capacity and disease burden. To maximize utilization of funds, money is reprogrammed as needed to increase impact and, where appropriate, re-allocated across countries through “portfolio optimisation”. Global Fund reports strong performance in allocation utilisation (AU) across GC7 grants to date, with an AU of 97% and USD 3.2 billion disbursed after the first year of implementation as of 31st December 2024. C19RM specifically reports an AU of 99%, with actual disbursements of USD 3.4 billion as of 31 December 2024 and forecasted disbursement of USD 763 million until 31 December 2025.

In terms of in-country absorption (ICA), the Global Fund report strong performance of HTM grants in GC6, with an 89% ICA, exceeding the 85% target by +4%. Most modules in GC6 reached high absorption including direct RSSH at 81% ICA; this was slow to begin with but absorption picked up towards the end of the cycle. Based on the most recent expenditure reports until December 2024, in-country absorption for C19RM grants is currently at 65%. Ongoing efforts to support C19RM implementation acceleration and execution of funds include the Resilient and Sustainable Systems for Health (RSSH) Acceleration Implementation Initiative, technical assistance through Centrally Managed Limited Investments (CMLIs), Secretariat Monitoring & Oversight as well as quarterly reporting through C19RM Monitoring & Evaluation (M&E) Framework.

As raised in the previous annual review, further efficiency gains could be made by the Global Fund through progressing the integration agenda and ensuring that all programmes contribute to supporting and strengthening the health system, moving away from siloed disease support. FCDO would also like to see greater collaborative working across the Global Health architecture, with an ambition to move towards aligned replenishments and/or grant cycles and longer grant cycles (4-5 years) to reduce transaction/admin costs.

Equity
Equity considerations form a key part of the Global Fund’s mandate, as the three diseases disproportionately affect marginalized or impoverished people/communities globally. The allocation methodology is designed to deliver funding to countries based on need. It was revised as part of a suite of sustainability policy changes approved by the Board in November, to further prioritize funding to low-income countries (LICs) and lower lower-middle income countries (L-LMICs) and support upper lower-middle income countries (U-LMIC) and upper-middle income (UMICs) in their transition to domestic financing.

The 2023-28 strategy period contains KPIs focused around equity, which have been used in this review to assess both efforts to reduce human rights barriers to health (see output 2.4) and maximise support to women and girls (see output 3.2). In GC7, progress has been achieved in defining and prioritizing equity indicators, as well as expanding data disaggregation dimensions. This has allowed for valuable insights into disparities at both national and subnational levels, which are now being used to guide equity-oriented programming and investments.

In 2025, the Global Fund will conduct an evaluation of Integration of Gender Approaches in HIV, Tuberculosis and Malaria Programs; this review should provide valuable insights into how effectively gender and equality are considered and incorporated into Global Fund programming.

Effectiveness (and Cost-Effectiveness)
The Global Fund continues to have a significant impact on the fight against the three diseases, demonstrating progress towards the delivery of the intended health outcomes across the portfolios. Whilst some data is missing and some KPI performance targets have not been fully met, the Global Fund are demonstrating positive progress overall under increasingly challenging circumstances.

Reviews and evaluations produced both by teams within the Global Fund, FCDO and other external partners have highlighted areas for improvement, and the Global Fund Secretariat has been largely accepting of recommendations and shown commitment towards addressing these. Examples of this can be found throughout this review, with progress made on year 1 recommendations, and on the findings of an OIG advisory on the Additional Safeguards Policy. Where recommendations have not been accepted, the Secretariat has communicated clearly the rationale for this decision. The Global Fund’s operating model is inherently vulnerable to risk due to the high-level of country ownership; mechanisms are in place to mitigate these risks by improving the effectiveness of their investments, such as through close working with WHO/Gavi in the development of technical guidance, and through the work of the Office of the Inspector General (OIG) and skilled Technical Review Panel (TRP) to provide necessary assurance and identify weak points.

In terms of cost-effectiveness, many of the Global Fund investments are included in Disease Control Priorities 3’s (DCP3) ‘Highest-Priority Package’ (HPP) of very cost-effective interventions to be incorporated into UHC packages. In addition, a 2024 lancet commission on Global Health included HIV, TB and Malaria as 3 of the 15 priority conditions to focus on to reduce mortality and morbidity, noting that in countries with a high probability of premature death, tackling infectious disease and maternal conditions are the two highest priority strands of intervention. Programming to fight HIV, TB, and malaria are also highlighted as mega or great buys in the FCDO’s ‘best buys’ work, due to the impact of the three diseases on poverty and economic growth, and their disproportionate effect on key and vulnerable populations.

Sustainability
The Global Fund includes sustainability within its consideration of VfM. Sustainability in this context relies on progress on multiple fronts, including epidemic control, resilient health systems and financial sustainability. Financial sustainability can be enhanced by increased or improved country co-financing, support to transition readiness and planning, and more efficient use of resources.

KPIs R1a (Realization of domestic co-financing commitments) and R1b (Mitigation actions for countries at risk of not meeting co-financing commitments) have both failed to meet their targets for this reporting period (noting the lag on reporting of R1a as referenced above). Reasons for underperformance of the former include macro-economic challenges and extenuating circumstances in-country, missing data, high historic minimum co-financing requirements and updates in the compliance methodology used to verify realisations (see output 2.3 for an assessment of the latter). To minimize risk to of the achievement of GC7 commitments, the Secretariat is focused on building more robust data systems and processes for regular monitoring of co-financing commitments, putting in place mechanisms to strengthen accountability of country stakeholders.

The ‘Sustainability and Efficiency’ sub-risk within the Health Financing risk category and monitored through the Global Fund’s Integrated Risk Management (IRM) tool, is currently rated as Very High for High Impact and Core portfolio countries. The Secretariat is working with countries to identify and address the root causes for this and put in place appropriate mitigation actions, aligned with the ambition to place a greater focus on VfM in Global Fund operations.

As outlined in section B above, in 2024 the Secretariat prepared a suite of proposed policy reforms designed to shift funding away from upper middle-income countries and support those who were able to transition away from Global Fund support towards self-financing. These policy amendments were approved by the in Board in November 2024; changes include a revised Eligibility Policy which makes it clear that transition from the Global Fund is permanent, and a revised STC policy which includes a requirement for all countries to undertake sustainability planning and for the first time requires low-income countries to make programmatic co-financing commitments. At the time of writing, the Secretariat is preparing Sustainability, Transition and Co-financing guidance for countries (as well as other disease-specific and cross-cutting guidance) ahead of GC8 funding applications, and we await further detail on how these policies will be implemented effectively in time for the next cycle. A collaborative approach across all health partners including the World Bank will be critical to effectively support all countries in progressively moving to self-financing. All of these policies will be reviewed again as part of the process of developing the next Global Fund Strategy; this work is expected to start in 2026.

Value-Add of the GFA Programme

The individual projects of the GFA programme have been carefully selected for their ability to complement and maximize the UK’s core investment in the Global Fund, with VfM considerations built into their choice and design. Examples of how the GFA enhances the impact of our core contribution are listed below.

The various projects within the GFA programme have demonstrated different levels of VfM in accordance with the VfM framework; these have been reviewed extensively as part of the GFA annual review with an overall conclusion that the GFA programme in FY24/25 delivered moderate VfM.

Project	Example of greater impact and VfM in addition to a core contribution to the Global Fund
BACKUP Health	TA delivered through BACKUP is central to enable to the GFA Health Advisers to support community system strengthening in three focal countries: Mozambique, Uganda, and Zimbabwe. / This is in line with country and UK priorities, improving the impact of Global Fund grants.
GFA Health Advisers & Secondees	Given the Global Fund does not have in-country staff, the GFA Health Advisers have supported the Global Fund’s Health Systems programming and have been able to advance key UK priorities such as Health System Strengthening and equity. They contribute directly to improving Global Fund grant performance. / The Human Resources for Health (HRH) and equity secondments are important to support the progress towards strengthening health equity and gender considerations across Global Fund programmes and reporting. The Gavi secondment focuses on the wider collaborative work across the GHIs.
Clinton Health Access Initiative (CHAI)	The CHAI Market Shaping (MS) project is working towards increasing access to HIV, TB and malaria health commodities for those living in underserved communities. This leverages the Global Fund’s leadership and contributes to cost savings for global procurers as well as those in Low- and Middle-Income Countries (LMIC). / Furthermore, CHAI works to drive integrated approaches to service delivery with a particular focus on commodities critical to the Global Fund. / As part of the separate Technical Assistance project, CHAI is working in a collaborative partnership between GFA Health Advisers, / and partner countries, to maximize the value of Global Fund investments and advance shared strategic priorities.
MedAccess	Like CHAI’s market shaping workstream, MedAccess’ work has previously increased access and affordability to HIV, TB and malaria health commodities for those living in underserved communities. This leverages the Global Fund’s leadership and contributes to cost savings for procurers in LMICs. While this hasn’t yet happened under this Facility given the lack of deals in FY 24/25, MedAccess have a strong pipeline of deals which will start delivering impact from FY25/26 onwards.
TB Reach	The TB Reach grant provides opportunities to improve integration of TB service delivery within health systems has the potential to accelerate the finding of missing people with TB while addressing other health conditions or diseases that may contribute to TB morbidity and underscores its value for money as a part of the Global Fund Accelerator programme.
RBM	The RBM Partnership grant supports the Partnership to serve as the central convening and coordinating platform in the malaria space aligning global efforts, avoiding duplication and amplifying results. The Partnership’s ability to mobilise funding through advocacy, support countries in securing and effectively using resources and drive accountability through data and partnerships makes it cost effective, offering impact and value for money.
GFA Flexible Policy Fund	The GFA Flexible Policy Fund contributes value for money by supporting continual improvement of the Global Fund through generation and dissemination of evidence. For example, in this FY a report on Channelling Global Fund Development Assistance for Health (DAH) through country systems was published by Oxford Policy Management (OPM) using the GFA 7 flexible policy fund.

Assessment of whether the programme continues to represent value for money

Overall, this programme continues to represent good value for money for the FCDO and is in line with the expectations at programme design. The size and reach of the Global Fund mean it is able to effectively support the delivery of interventions on a huge scale across a large number of countries; this breadth and diversity of support, and subsequent impact on recipients, could not be achieved bilaterally whilst delivering the same levels of economy and efficiency. On the grant-side of spend there is a robust VfM framework in place that covers economy, efficiency, effectiveness, equity and sustainability. Value for money must continue to be a focus for all activities, both grant funded and delivered through catalytic investments. Sustainability has been highlighted as the area with the most scope for improvement, and the importance of this continues to grow given challenges in the global funding landscape.

Value for money will continue to be a core metric for the FCDO when taking decisions on future funding to the Global Fund, most notably this year (2025) as we consider our pledge to the 8th replenishment (2026-28). VfM will also be a key consideration informing FCDO’s strategic priorities for the Global Fund, both in the current and future grant cycles.

E: RISK

Overview of risk management

The main risks for this programme relate to the external context and to delivery, where FCDO has a high-risk appetite.

The single greatest risk to delivery at present is external funding. The US is the single largest donor to the Global Fund, providing around one third of total funding. Pauses and cuts to US foreign aid in 2024 and into 2025 have generated significant uncertainty around future disbursements to the 7th replenishment and the likelihood of a pledge to the 8th. The Global Fund will need to plan for a range of possible future funding scenarios and be prepared to make efficiency gains and difficult trade-offs in future funding decisions, with the support of the Board. The current focus is rightly on assessing and mitigating the immediate impacts of US funding cuts to countries, identifying ways to reallocate funding to support areas that are most vulnerable. Moving towards the 8th replenishment, the Global Fund, with the support of the UK and South Africa as co-hosts, will need to look for opportunities to both galvanise ongoing support from existing donors, widen the donor base, and explore potential options for non-monetary contributions such as access offers from the private sector.

With regards to disease specific programming, Malaria remains the area of highest concern for the FCDO, and the risk of stalling or reversal of progress is increasing. This is largely driven by external factors outside of the control of the Global Fund (climate change, conflict, drug and insecticide resistance etc.) and is recognised by the Global Fund leadership as an area to prioritise. The Joint Committee Working Group (JCWG) formed in 2024 between the Global Fund, Gavi (the vaccine alliance) and the Global Financing Facility (GFF) has undertaken a deep dive on Malaria, to agree current challenges and identify opportunities for alignment. This work is yet to progress further but provides an opportunity for collaborative efforts to maximise the impact of available resource on both protecting the gains made to date and driving further progress. The Global Fund’s work on market shaping and capacity building for regional manufacturing will also be a vital tool in continuing to scale up access to innovative new technologies such as dual active ingredient bednets. Whilst more than 16.8M insecticide-treated nets were procured by Global Fund from an Africa-based supplier in 2024, the majority of these were non-dual active. Looking ahead, it is essential to ensure that these initiatives form part of a broader strategy that addresses the growing risks of drug and insecticide resistance and integrates climate resilience into malaria programming. This will help to ensure that investments deliver maximum impact and long-term value for money. The FCDO will continue to raise Malaria as a priority area for improvement through our seat on the Board/committees, and through the annual strategic dialogue with the Global Fund.

The rollback on sexual and reproductive health and rights (SRHR) remains a significant threat, especially with the loss of key US contributions to HIV programming, including through the United States President's Emergency Plan For AIDS Relief (PEPFAR). Concerns are growing about how this rollback will affect donor contributions to major Global Health Institutions including the Global Fund, where SRHR is crucial or strongly linked to core delivery. For the Global Fund, this rollback poses the greatest risk to HIV program beneficiaries, particularly young women, girls, and LGBTQI+ populations who are disproportionately impacted by new HIV infections. This jeopardizes progress toward reducing new HIV infections and ending AIDS. The UK will continue to use its Board position to advocate strongly for SRHR rights and support the Global Fund in defending and advancing its work in this area.

The Global Fund has robust mechanisms in place for managing risk, with a three-lines of defence model consisting of country teams, the risk department and functional oversight teams and the Office of the Inspector General (OIG). The OIG is independent of the Secretariat and critically assesses the organisation’s risk management, governance, and internal controls and investigates alleged incidents in Global Fund programmes (including incidents of SEAH, fraud, and corruption). Risks are differentiated across the three thematic risk areas (operational, grant-facing and business process), recorded and monitored through the Integrated Risk Management (IRM) tool, and reported on regularly to the Audit and Finance Committee (AFC) and the Board. A Central Assurance Assessment (CAA) was completed by the FCDO in 2024 and assessed the overall risk for the Global Fund as ‘Moderate’. There we no major areas for concern, but areas for improvement were identified across all 4 pillars, including outdated policies, gaps in risk appetite and a middling fraud risk maturity.

Within the FCDO, risks are captured and monitored through a programme risk register, reviewed regularly and updated managed accordingly. Key risks highlighted in FCDO’s risk register include loss of future funding, failure to mitigate the stalling or reversal of progress on Malaria, and a failure of the Secretariat to make adjustments in delivery of the new Strategy, resulting in weak implementation. Existing risks have not changed substantially in recent years, but new risks were added in 2024 specifically to address decisions on US funding, risks to the 8th replenishment and the risk that the JCWG fails to achieve its intended outcomes in terms of collaboration across the Global Health Institutions. There are currently two risks outside of the FCDO risk appetite for policy & programme delivery (withdrawal of USAID and a failure of the 8th replenishment to raise sufficient funds); these are being monitored by the programme team and will be escalated as necessary.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Global Fund is a high performing organisation and thus performs well in delivery, commercial and financial aspects.

Delivery against the Global Fund’s own monitoring and evaluation framework is monitored through a suite of KPIs, many of which are captured in the outputs in this review and reported to the Board on a biannual basis. In addition, the Global Fund delivers independent evaluation and learning through two structures: the Evaluation and Learning Office (ELO) who carry out thematic evaluations on topics chosen and agreed in collaboration with the Board, and the Independent Evaluation Panel (IEP), an independent advisory and oversight panel who review the quality of independent evaluation activities.FCDO’s programming to support to the Global Fund is set out in a Memorandum of Understanding and Performance Agreement, through which performance is managed, and a Logframe (based largely on Global Fund KPIs) is agreed to monitor progress on a yearly basis. The Performance Agreement is also valuable for shaping the discussion points for the annual Strategic Dialogue which takes place between the Global Fund and FCDO, ensuring the conversation is targeted towards progress in line with the UK’s development priorities. This framework of monitoring and evaluation allows FCDO to effectively assess Global Fund’s performance in line with its own core mission, and with the UK Government priorities, and to identify areas at risk or in need of strengthening.

The Global Fund has robust processes in place to ensure funds are delivered through effective and impactful grants. Funding requests are developed by in-country stakeholders through regional and country coordinating mechanisms with support from technical partners. Quality assurance for funding requests is carried out by an independent technical review panel and a grant approval committee which brings in a wide range of stakeholders, including FCDO, prior to Board approval. Oversight of implementation is undertaken by the Secretariat, country and regional coordinating mechanism oversight committees, local fund agents contracted to support fiduciary risk management, and, where necessary, by fiscal agents. All of these mechanisms give adequate assurance to FCDO that our funding is being disbursed to grants which provide both value for money and actively contribute to the delivery of the Global Fund’s mission and the key objectives of the 2023-28 strategy.

The Global Fund is an effective partner, engaging with the FCDO both through the programme team and the expert health advisers, including those based in-country as part of the Global Fund Accelerator programme. Additional engagement with FCDO’s newly formed temporary ‘Replenishment Team’ also commenced this year; this will include attendance at a UK-South Africa-Global Fund steering group to plan for the 8th replenishment event in late 2025 and agree an aligned lobbying strategy to galvanise ongoing support from other donors. The corporate governance structure of the Global Fund was last independently reviewed in March 2024, and its performance was assessed to be ‘on an upward trajectory’ and that, overall, it was ‘effective in undertaking its core functions’ and ‘[contributed] to the Global Fund’s continued success’. The policy framework of the Global Fund is impressive, with a substantial policy architecture in place.

The Global Fund has strict quality assurance criteria to obtain high quality pharmaceuticals, diagnostics products and medical devices, as well as stringent policies on Procurement and Management of Health Products; the most recent version of the Global Fund’s procurement policy was approved by the Board in April 2024. The Global Fund also plays a significant role in global markets for health products used in the fight against the three diseases, using its resulting market power to shape markets through the Pooled Procurement Mechanism (PPM) ‘Wambo’, which in 2024 managed $1.78 billion in orders. The Global Fund Accelerator programme (GFA) also has components supporting market-shaping for three disease commodities through agreements with MedAccess focused on volume guarantees and CHAI that works on a broader set of initiatives, that includes supporting generic product development in the HIV space, increasing the use of TB screening using digital technology and improving malaria data quality that enables better supply planning.

Overall, the financial performance of the Global Fund continues to be good, and financial management remains a key strength. Financial performance reports are presented to the Board twice per year, and an annual audited financial statement is published following board approval. No significant concerns have been reported in any of these reports in 2024/25, and the 2024 annual report has been approved for publication by an external auditor with no major discrepancies noted. In addition to its programme financial performance, the Global Fund has a good attention to operational efficiency, reporting to the Board on measures such as time to grant signature and speed of disbursement, and corrective action taken as needed. Operating Expenses (OPEX) for the year 2024 reached US$ 341m with optimal budget utilization of 99.5%. The Global Fund’s Strategic Initiatives (catalytic investments to support programs and activities that complement country allocations) financial performance is improving, with 87% fund utilization at December 2023.  At the end of December 2024, GC7 Strategic Initiative’s (SI) fund utilization reached 13% of the Grant Approvals Committee (GAC) total approved funding (which includes additional private sector funding received in late 2024 and planned for use in 2025-2026); this demonstrates a good start compared to previous cycles. For the first year of implementation, SIs utilized 71% (US$ 18M) of the planned GAC-approved budgets, signalling strong implementation progress.

Transparency of the Global Fund’s activities is generally high, and a range of routes are available to monitor programme performance. For example, the Secretariat reports results annually with bi-annual reporting against the KPI framework to the Board. Two areas of weakness regarding transparency were identified through the CAA; these were around a lack of transparency over the Secretariat’s progress on agreed management actions, and on a lack of transparency over sub-principal recipient activities. The UK was a member of the Board, the Strategy and Ethics and Governance Committees over the last year and has also had the opportunity to observe Audit and Finance Committee meetings. These seats provide a key opportunity to monitor and drive progress against the Global Fund’s goals and UK priorities, as well as to contribute to decision making at the Secretariat level. FCDO will continue to actively engage with our Board and Committee roles, recognising these as a vital tool to deliver on the UK Government’s international development priorities through our investment in the Global Fund.

The evidence for the Annual Review is taken from regular reporting from the Global Fund Secretariat and independent scrutiny bodies (OIG, ELO, IEP, TRP). Supplementary information was provided from the Secretariat as needed, and additional feedback on the Global Fund’s engagement, collaboration, operations and performance at country level was obtained from FCDO’s country offices and health advisors both within and outside of the GFA remit.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

FCDO’s core Global Fund programme team attended the 52nd Board Meeting in Malawi in November 2024, during which time we undertook brief visits to a range of facilities in receipt of Global Fund funding. These visits were group trips organised by the Global Fund and there was limited opportunity to ask questions; we will therefore continue to look for opportunities to conduct longer and more tailored site visits over the coming year. FCDO have a team of in-country advisors, some of which are funded through the GFA. These advisors continue to provide field level feedback and valuable insight into the effectiveness of Global Fund processes and programming at country level, as well as the key challenges faced.

Monitoring of Global Fund activities over the past year has largely been through reporting received through the Board/Committees, and attendance at Board/Committee meetings. Additional evidence for this review has been gained through regular engagement with Global Fund colleagues, including the annual strategic dialogue between FCDO and the Global Fund, centred around progress against the performance agreement.

FCDO visited the Global Fund headquarters in Geneva in September 2024 for a series of meetings relating to the 2024 Central Assurance Assessment; the report has been shared with the Global Fund and is being finalised at the time of writing.

Evidence
Results are now available for the majority of KPIs under the 2023-28 Strategy monitoring and evaluation framework; the most recent data and accompanying narrative is available on the Global Fund’s online reporting platform ‘Oskar’. Reporting on the remaining KPIs is expected by the end of Q4 2025. Additional evidence for this report has been taken from reporting to the Board/committees, written updates from the Global Fund and FCDO’s Central Assurance Assessment. The previous annual review used some KPIs from the 2017-22 strategy period as proxies where data was not yet available; this is no longer required but otherwise there has been no changes in the type of evidence used for this review.

Learning
The Global Fund and its implementing/technical partners (including FCDO through its GFA funded technical assistance) produce reports, dashboards and other materials to analyse data from the monitoring and evaluation framework and other sources, and assess the effectiveness of Global Fund programs, identifying areas for improvement. The Global Fund describes itself as an organisation that is ‘committed to continuous learning’ and the Secretariat demonstrates this through their responses to findings and recommendations from reviews and audit reports, such as those produced by the OIG. Most OIG recommendations are accepted and an agreed management action (AMA) put in place. In instances where the recommendation(s) has not been accepted, the Secretariat has communicated clearly the rationale for this decision; in most instances this is because other measures or interventions are already in place to ensure areas of underperformance or concern are addressed. In addition, the new evaluation model delivered through the ELO includes a requirement for the Secretariat to formally respond to evaluation reports with progress against agreed actions tracked, as set out in the current Standard Operating Procedures (SOPs). Evaluations are carried out in line with the Board-agreed evaluation calendar, and the end-to-end process is designed to ensure key learnings are identified and carried forward by Global Fund management.

In 2024, FCDO commissioned a review of the effectiveness of the Global Fund’s use of country systems by DAI through the policy component of the Global Fund Accelerator. The purpose of this review was to capture learning across the 6 GFA countries on the process of Funding Request development, and the role of the GFA within this. The report was very helpful in supporting FCDO’s thinking about how Global Fund processes could or should change to drive greater impact, and this has informed our position in the Strategy Committee e.g. calling for guidance and TA for integration to be made available to countries well in advance of GC8. The review has also been useful in thinking about how the GFA should evolve in support of this e.g. underlining the need for strategic prioritisation and a stronger focus on VfM. The final DAI report has been shared with the Global Fund.

Date of last narrative financial report	March 2025	Date of last audited annual statement	March 2025

Annex A – Portfolio Performance vs. Aggregate Grant Performance

Indicator(s)	Portfolio Performance	Grant Performance
Outcome 1	KPI H2: 98%	Latest Result: 79% coverage in 96 countries against an aggregate target of 81%
Outcome 2	KPI T2: 96%.	Latest Result: Overall treatment success rate of 88% in 72 countries against an aggregate grant target of 91%
Outcome 3	KPI M3: 99%	Latest Result: 97% treatment rate in 54 countries against to an aggregate grant target of 98%
HIV	KPIs H1: 95%. / KPI H3: 102%.	KPI H1: 86% achieved across 66 countries against an aggregate grant target of 90% / KPI H3: 94% achieved across 80 countries against an aggregate grant target of 92%
TB	KPI T1: 101%. / KPI T4: 106%. / KPI T5: 55%.	KPI T1: 6.90m against an aggregate grant target of 6.82m notifications across 85 countries / KPI T4: 73% achieved across 47 countries against an aggregate grant target of 69% / KPI T5: 1.97m contacts on TPT across 49 countries while the aggregate grant target was 3.56m
Malaria	KPI M1: 96% / KPI M2: 101% / KPI M5: 97%	KPI M1: 227m bed nets distributed in 57 countries against an aggregate grant target of 238m / KPI M2: 97% testing rate in 58 countries against an aggregate grant target of 96% / KPI M5: 95% across 12 countries against an aggregate grant target of 98%
3.2. Maximised support to woman and girls / (KPIs H5, H6, M4, S3, E3b)	KPI H5: 103% / KPI H6: 92% / KPI M4: 80%	KPI H5: 25.4% achieved across 12 countries against an aggregate grant target of 24.5% / KPI H6: 87% achieved across 46 countries against an aggregate grant target of 94% / KPI M4: Overall IPTp3 coverage was at 53% across 29 countries compared to a 67% aggregate grant target
3.3 Enhanced focus on meeting the needs of the marginalised and hard-to-reach population (KPIs H4, E2b)	KPI H4: 87%	KPI H4: 46% achieved across 98 countries against an aggregate grant target of 54%