## 2024 Annual Review

Title: UK Investment in Gavi, the Vaccine Alliance (2021-2025)
Programme Value £ (full life): £1.06 billion[1]		Review date: October 2025 (covering 2024)
Programme Code: 300871	AMP start date: 1 April 2021	AMP end date: 31 March 2026
[1] FCDO also contribute to Gavi through commitments to the International Finance Facility for Immunisation (IFFIm). Gavi will receive approximately £590m in proceeds from these commitments 2021-25, bringing the total contribution to £1.65bn (2021-25).

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000801.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0001172.xlsx

A. SUMMARY AND OVERVIEW

Gavi, the Vaccine Alliance, is a global health partnership that brings together national governments, vaccine manufacturers, non-governmental organisations, multilaterals, the Gates Foundation and the private sector. Its purpose is to increase access to immunisation in lower income countries and introduce new and underused vaccines in these settings. Gavi has no direct in-country presence, with its operations overseen by the Gavi Secretariat based in Geneva and Washington DC. Its mission is delivered in partnership with in-country partners, principally implementing country governments and key Alliance partners (the World Health Organization (WHO), UNICEF and the World Bank). Since 2000, the Gavi Alliance has contributed to the routine immunisation of over 1.2 billion children and helped to prevent more than 20.6 million future deaths from illnesses such as hepatitis, pneumonia, measles, meningitis, rubella, and yellow fever. Gavi has delivered over 2.1 billion vaccinations through preventative campaigns since 2000, and in 2024 Gavi delivered over 49 million vaccine doses for outbreak response. In purchasing vaccines for over 50% of the world’s children, Gavi has a unique ability to shape the vaccine market expanding access to vaccines at lower cost for lower income countries.

Gavi’s operating model is designed to support countries to scale up their financing of routine immunisation programmes over time, until a country is fully self-financing, in accordance with an eligibility, co-financing and transition policy. Once countries achieve a defined gross national income (GNI) per capita threshold, they begin a process of transition away from Gavi support until they become fully self-financing. Gavi also provides targeted and time-limited support to transitioned countries to help them sustain high levels of immunisation coverage.

The UK is one of six original donors to Gavi and has been a leading donor since Gavi’s inception in 2000, investing in core and innovative financing instruments to progress Gavi’s mission. The UK is an active participant at the Gavi Board, sharing a constituency with Canada and Qatar. The UK/Canada/Qatar constituency also sits on the Audit and Finance Committee (AFC), the Policy and Programme Committee (PPC), and the Market Sensitive Decisions Committee (MSDC). The UK supports and advises on technical working groups including the Alliance Partnerships and Performance Team (APPT).

This Annual Review covers Gavi’s fourth year (2024) of its fifth strategic period, 2021-2025, of the core mission known as “Gavi 5.1”. In 2020 and 2021, routine immunisation was significantly impacted by the COVID-19 pandemic and countries experienced backsliding after two decades of progress. Introduction of vaccines approved in the Vaccine Investment Strategy (VIS) 2018 was also paused. Given the effects of the pandemic, in December 2022, the Gavi Board approved an evolution of the 5.0 programme strategy to Gavi 5.1, which renewed focus on routine immunisation and reaching zero-dose children, new vaccine introductions, and a strengthened Alliance role in outbreak and pandemic preparedness and response, alongside continued COVID-19 vaccinations in countries supported by the COVAX Advance Market Commitment (COVAX AMC). The UK was a donor to the COVAX AMC and its performance was assessed in a separate FCDO annual review. Following the closure of the COVAX Facility in 2023, reporting on COVID-19 immunisation for 2024 has been incorporated into this core Annual Review.

2024 was a year of progress and change for Gavi, recovering immunisation coverage post-COVID19. Gavi’s new CEO, Dr Sania Nishtar joined in March 2024, putting in place a 180-day plan which focussed on strengthening the capabilities and culture of the secretariat, and strengthening delivery. In 2024 Gavi advanced reforms of its operations to prepare for delivery under Gavi 6.0 (the planned 2026-2030 programme), in the context of broader reforms to the global health architecture. Initially under the CEO’s 180-day plan and now known as the Gavi Leap, an ambitious programme of internal reform was initiated by Gavi to examine and, where necessary, reform all aspects of the Secretariat’s structure, policies and ways of working to ensure it adapts to a rapidly evolving global health landscape. The key changes implemented during the first wave include four key areas:
- Institutional structures for decision-making in the secretariat: Four senior leadership sub-groups were created, and various forums and committees disbanded. This restructuring enhanced alignment across leadership channels, clarified escalation pathways, and enables more holistic, cross-cutting reviews of key initiatives and decisions.
- Reform of end-to-end grant management process: The grant management initiative, EVOLVE, was restructured to focus on delivery, with project team members embedded within Secretariat teams to accelerate progress.
- Revamp of policy and decision-making frameworks: Updated and streamlined the Secretariat’s decision-making processes, approval pathways and policy management to ensure they appropriately balance empowerment with accountability and oversight. Extensive policy hygiene exercise was undertaken, putting in place a central repository.
- Revitalising Gavi's culture and capacities of the Gavi secretariat to improve efficiency: The Delivery Cascade was institutionalised, providing a set of processes, workplans, workflows, review meeting cadences and tools, including Business Intelligence and Artificial Intelligence-powered dashboards, designed for efficient delivery processes and effective implementation.

Programmatic acceleration

Gavi made progress in its mission to accelerate access to immunisation, with momentum building in areas that had previously stalled. The revitalised HPV programme saw expansion, with more girls vaccinated in 2024 than in the previous decade combined – a powerful signal of renewed commitment and delivery. Malaria vaccine introductions in 17 countries reflected strong technical and political will to deploy the latest tool in the fight against a long-standing killer. Countries made progress in reversing pandemic-era setbacks, with routine immunisation coverage accelerating and under-5 mortality falling by 12% compared to 2019 – surpassing the 2025 target two years ahead of schedule. Market-shaping efforts helped expand access and affordability, with notable gains in reduced pricing, supply security, and innovation. For example, the weighted average price (WAP) of Malaria vaccine decreased by over 40% from 2023 to 2024 and the WAP of Typhoid Conjugate Vaccine (TCV) decreased by more than 30% during the same time period. Gavi also strengthened its institutional partnerships, deepening collaboration with the Global Fund and Global Financing Facility (GFF) through four joint workstreams under the Lusaka Agenda, while engaging with MDBs and partners through initiatives like African Vaccine Manufacturing Accelerator (AVMA) to support long-term regional manufacturing capacity.

The UK Matching Fund played a critical role in leveraging private sector engagement in high-impact countries. In 2024, it was activated for three new partnerships[2]: with the aim of strengthening immunisation and maternal and child health services across key regions, directly addressing infrastructure gaps, data quality challenges, and limited healthcare access for vulnerable populations.
[2] The Power of Nutrition and the Aga Khan Development Network in Pakistan; with ELMA and the Gates Foundation in Ethiopia; and with Zipline, The UPS Foundation, and IFPW in Nigeria.

Against this backdrop of progress, challenges remain – particularly in low-income and fragile settings where recovery has been uneven and health systems continue to face pressure from conflict, displacement, and demographic growth. Increasing populations require countries to reach more children to achieve gains. Progress on reducing the number of zero-dose children still falls short of pre-pandemic levels and will require accelerated efforts to meet the 2025 target. Despite these constraints, Gavi continues to deploy resources with efficiency and impact – evidenced by $19.8 billion in economic benefits being generated in Gavi-supported countries in 2024. The Alliance is currently positioned to advance progress towards its 2025 strategy, with ongoing efforts across strategic indicators and targeted support for areas requiring additional focus.

In 2024, Gavi continued to implement organisational reforms and delivery improvements, driven by the “Gavi Leap” initiative and a renewed focus on operational efficiency. The Secretariat has been working to ‘right size’ for 6.0 where it will need to reduce operating costs by at least 30%. Recognising the effect this restructuring has on staff wellbeing and culture, Gavi ran an internal campaign promoting their employee assistance programme, established a position for a staff councillor (who joined in May 2025), and put in place flexible working guidance. They are planning a further wellbeing survey in early 2026 which will help establish a baseline for staff engagement in 6.0. Though the Operating Expenses budget increased from 2023, this came in under budget in 2024. Targets were also exceeded on staff attrition rates and time to hire. Though resources disbursed were marginally below expected this is explained by Gavi’s focus in 2024 on ensuring countries are using existing cash balances ahead of further HSS disbursements.

Gavi’s delivery effectiveness was demonstrated by the completion of all scheduled audits, robust risk management practices, and a reduction in the average time from programme approval to disbursement to 7.9 months. The proportion of funds channelled through government systems increased to 55%. Additionally, although the use of country systems increased, strengthening of assurance and financial management at subnational levels is needed. These challenges underscore the need for continued, capacity building, and adaptive management as Gavi moves into its next year. Gavi has maintained its commitment to PSEAH, with good progress implementing the PSEAH audit recommendations, and all partner agreements now including PSEAH clauses. We encourage Gavi to sustain this focus for 2025.

Summary supporting narrative for the overall score in this review

This is the fourth annual review of Gavi’s fifth strategic period. The overall score for the 2024 review period is [X]. This is derived from the following output scores:

Output	Score	Definition	Description
1	A+	Output Moderately exceeded expectations	Introduce and scale-up vaccines
2	A	Output met Expectation	Strengthen health systems to increase equity in immunisation
3	A	Output met Expectation	Improve sustainability of immunisation programmes
4	A	Output met Expectation	Ensure healthy markets for vaccines and related products
5	A+	Outputs moderately exceeded expectation	Organisational effectiveness
6	A	Output met Expectation	Delivery effectiveness
7	A	Output met Expectation	African Vaccine Manufacturing Accelerator (AVMA)

Between 2021 and 2024, Gavi vaccinated over 279 million children through routine immunisation, reaching more children than in any previous year. Gavi also unlocked over $73.6 billion in economic benefits and averted more than 5.56 million future deaths: all well ahead of target. The number of zero-dose children in Gavi-supported countries decreased by 500,000 in 2024, reflecting substantial country efforts in reaching the most vulnerable children. However, this progress was still not sufficient to adequately reduce the number of zero-dose children to target levels[3], which remains higher than pre-pandemic levels and Gavi is off-track to meet its target by next year.
[3] ‘Zero-dose’ children are those who have not received even a single dose of vaccine. For operational purposes, Gavi defines zero-dose children as infants who have not received the first dose of diphtheria, tetanus, and pertussis-containing vaccine (DTP1) by the end of their first year of life.

Some key headlines in the past year include:
- Routine immunisation coverage levels showed modest improvement following pandemic-related declines in 2021-2022 and stagnation in 2023. Coverage for the third dose of DTP3 in the 57 Gavi-supported countries increased to 82% in 2024, up from 81% in 2023 and 78% in 2021. This means DTP3 coverage in Gavi-supported countries is nearly back to pre-pandemic levels (i.e. 83% in 2019). Coverage for the first dose of measles-containing vaccine (MCV1) saw a bigger increase, improving two percentage points from 78% in 2023 to 80% in 2024.
- Following Board approval in December 2023, the Alliance approved support for the Big Catch-Up to 35 countries, with a target of reaching 25 million missed children[4]. The first shipments to countries occurred within four months of the Board decision and an estimated 5.5 million missed children had been caught up by the end of 2024[5].
  [4] In Gavi's operational definition, "missed children" refers to zero-dose children and under-immunised children.
  [5] At the end of Q2 2025, a total of 10.4 million children had been reached in 28 of the 36 countries who provided reports on time.
- Breadth of protection (BoP), defined as the average coverage of Gavi-supported vaccines, increased from 55% in 2023 to 63% in 2024, already exceeding Gavi’s overall 5.1 target. In aggregate all Gavi-supported vaccines had higher coverage in 2024 than in 2023.
- Following the Board’s approval of a revitalised human papillomavirus (HPV) programme, Gavi-supported countries accelerated introductions and rollout of HPV vaccines to increase coverage by 9pp from 16% in 2023 to 25% in 2024. As of 2024, 59.8m girls have been fully immunised with HPV vaccine with Gavi support, on track for the HPV vaccine programme revitalisation target of 86 million by end 2025. More girls were vaccinated with Gavi support in 2024 than in the previous decade combined
- 2024 marked the start of countries introducing malaria vaccines into their routine immunisation programmes with the support of Gavi’s malaria vaccine programme. During 2024, 14 countries introduced the two malaria vaccines, bringing the total number of countries implementing the vaccines to 17 and targeting approximately 5 million children. This is one of the fastest rollouts of new vaccines to countries in Gavi’s history.
- In 2024, countries contributed US$ 255 million in co-financing. This brought total co-financing contributions to US$ 1.96 billion since 2008. Co-financing mobilised by countries in 2024 represents a 19% increase from 2023 and a 57% increase from 2022.
- Outbreaks of vaccine-preventable diseases such as measles, cholera, meningitis and yellow fever continued on an upward trend driven by conflict and population displacement, gaps in routine immunisation coverage, lack of access to safe water and sanitation infrastructure, and rapid urbanisation. Disease outbreaks continue to put many lives at risk and strain health workforces and systems. Countries requested record international support for outbreak control, with 50 vaccine requests approved by the International Coordinating Group (ICG) and Measles and Rubella Partnership Outbreak Response Fund in 2024, reaching over 55 million persons at risk in active outbreak areas.
- The Joint Committee Working Group (JCWG) was formed under the Lusaka Agenda in September 2024 to oversee collaboration between Gavi, the Global Fund, and GFF across three workstreams: Malaria, Resilient and Sustainable Systems for Health (RSSH)/Health System Strengthening (HSS), and Country Engagement. The JCWG is scheduled to be replaced by the Gavi-Global Fund Taskforce Teams, which will continue its functions.
- AVMA was formally launched on 20 June 2024 and secured up to US$ 1.2 billion in pledges from 13 governments and organisations. The 21 June 2024 high level Roundtable on Strengthening Local Production in Africa, co-hosted with the World Bank Group and Africa CDC, brought together multilateral development banks, development finance institutions, suppliers, and partners to identify complementary investments and enabling environments necessary for AVMA's long-term success. Africa CDC and Gavi co-convened the 2nd Vaccines and Other Health Products Manufacturing Forum held in Cairo in February 2025, which brought together 280 participants including manufacturers, regulators, financiers, and representatives from 12 African Union Member States. The Forum validated AVMA's catalytic role in the sector while highlighting persistent challenges, particularly around early-stage financing gaps, regulatory pathways, and demand certainty that require continued attention to ensure sustainable African vaccine manufacturing.

Many countries saw large improvements in DTP3 coverage in 2024, with 13 countries seeing an increase of +5pp or more, including Chad, Somalia, Ethiopia, Liberia, South Sudan, Cameroon, Guinea, PNG, Haiti, Mauritania, Syria, Mali, and Niger. These improvements were moderated by large decreases in other countries, many of which faced significant conflict-related disruption including steep declines in Sudan, Myanmar, Yemen, and Mozambique. Average coverage in fragile and conflict (F&C) countries (61% DTP3 coverage) continues to lag significantly behind high impact (84%) and core countries (85%). However, 8 out of 12 F&C countries[6] had increased coverage from 2023 to 2024; at segment level, this impressive progress was offset by Yemen (-4pp) and Sudan (-12pp) which both saw substantial declines from 2023 to 2024 due to conflict. The majority (40 of 57) of Gavi-supported countries increased or maintained routine coverage in 2024, and about half have achieved DTP3 coverage at or above 2019 levels. Despite overall coverage being 1pp lower than in 2019, with population growth Gavi57 countries reached more children with routine vaccines in 2024 than in any previous year. In 2024, Gavi57 countries saw a 3% increase in the number of births compared to 2019, with most of this increase coming from African countries.
[6] The eight F&C countries that increased DTP3 coverage in 2024 were Mali (+7 percentage points), Syria (+7pp), Papua New Guinea (+7pp), Haiti (+6pp), CAR (+2pp), Chad (+1pp), Niger (+1pp), and Somalia (+1pp).

Africa has now recovered immunisation coverage to pre-pandemic levels. The WHO AFRO region saw declines in DTP3 from 76% in 2019 to 72% in 2022, but has now fully recovered in 2024 – with DTP3 coverage back up to 76%. At the same time, lower-middle income countries have recovered immunisation coverage to pre-pandemic levels, while low-income countries continue to be impacted – underscoring the importance of building resilient health systems.

As a group, the 26 low-income countries have struggled to recover from declines during the pandemic, with coverage still at 70% in 2024 relative to 75% in 2019, whereas lower-middle income countries supported by Gavi have exceeded 2019 coverage by 1pp, reaching 87% in 2024. The stagnation in low-income countries is driven by steep conflict-related declines in Yemen and Sudan, despite many low-income countries seeing improvement including DR Congo, Ethiopia, Mali, Syria, and Chad.

Lessons from LMICs highlight the value of partnerships, integration, and local adaptation in strengthening immunisation systems. Indonesia’s private-sector collaboration improved demand, logistics, and delivery in remote areas. Honduras integrated immunisation with health and emergency programmes, boosting resilience. Viet Nam’s life-course approach expanded coverage to older children, enhancing equity. Bolivia’s community-led planning with indigenous leaders reduced cultural barriers and hesitancy. Digital data systems in Honduras and Indonesia improved accountability and targeting of zero-dose children. These experiences offer transferable, locally tailored, partnership-driven strategies for LICs to improve sustainability, efficiency, and equity.[7]
[7] Final_MIC_Learning_Report
Timely measurement of performance through WHO/UNICEF estimates of national immunization coverage (WUENIC) remains a priority focus area and saw significant improvement in 2024. Last year, Gavi reported that nearly 30% of zero-dose children in Gavi-supported countries live in eight countries where WUENIC held coverage constant since the last household survey due to data quality challenges.

Coverage estimates have been updated in seven of these countries, including historical revisions to coverage. For example, estimates in Nigeria have been updated based on a new survey after being held flat for several years. Nigeria saw DTP3 coverage decline from 66% in 2019 to 61% in 2021, before recovering to an all-time high of 67% in 2023 and remaining there in 2024. After an extensive data review exercise led by UNICEF, coverage in Somalia has been updated for the first time after being held flat since 2012, showing an improvement from 57% in 2019 to 70% in 2024.

Gavi remains on track for most of its 2025 targets. Advances were made in particular around breadth of protection, MCV2 and HPVC coverage, vaccine introductions – including malaria, the number of countries implementing Big Catch-Up support and co-financing. New vaccine introductions had fallen behind in 2023, but countries succeeded in accelerating introductions in 2024, achieving the 2025 target ahead of time. In particular, malaria vaccine introductions were ahead of target. In Ghana, early results have been promising, with a 45% reduction in malaria cases among children under five attributed to the vaccine rollout. As part of a broader set of control measures, the vaccine adds a powerful new layer of protection—its impact is amplified when combined with existing tools like bed nets and treatment protocols[8].
[8] https://gna.org.gh/2025/05/ghana-records-45-per-cent-reduction-in-malaria-among-children-under-five-2/

Recommendations for the year ahead

Output	Recommendations 2024
Output 1: Introduce and scale-up vaccines	Recommendation 1: Gavi to work with other health actors to continue strengthening the second year of life contact point – including by leveraging malaria vaccine 4th dose touchpoint - to help countries reduce drop-out between doses & reduce Under Immunised Children.
Output 1: Introduce and scale-up vaccines	Recommendation 2: Indicator 1.5 does not currently provide meaningful results due to a lack of data and Indicator 1.6 is particularly complex to calculate. Gavi to consider how reporting can be improved for 2025. In developing the results framework for 6.0, Gavi should ensure that all indicators are able to be measured to provide meaningful results.
Output 1: Introduce and scale-up vaccines	Recommendation 3: Gavi to work with GPEI to provide a joint workplan accompanied by a shared measurement framework and implement annual reporting to PPC and Gavi Board thereafter. The joint workplan and measurement framework will have clear accountability lines and agree to a more systematic and comprehensive approach to integration.
Output 2: Strengthen health systems to increase equity in immunisation	Recommendation 4: Gavi - through the JCWG and CEO Task Force - to progress the joint workstreams on malaria, HSS, country implementation and back-office functions reporting regularly on progress through the Gavi and Global Fund governance committees and Boards.
Output 3: Improve sustainability of immunisation programmes	Recommendation 5: Gavi to work with Global Fund to ensure coherence of current co-financing, eligibility and transition policies and guidance on applicability in a manner that is practical for countries. Gavi to work with Global Fund to better align policies when any future changes are made.
Output 3: Improve sustainability of immunisation programmes	Recommendation 6: FCDO to use its funding and board positions to encourage World Bank and WHO to coordinate their Public Financial Management, Domestic Resource Mobilisation and technical engagement efforts together with Gavi and other GHIs to support countries with access to lending to develop sustainable health financing plans in the pathway to transition from Gavi/GHI support.
Output 3: Improve sustainability of immunisation programmes	Recommendation 7: Gavi to work with MDBs, particularly World Bank as a core partner, to develop a strategic approach to joint-financing of vaccine programmes particularly in PT and AT countries to better support the pathway to sustainable financing.
Output 5: Organisational effectiveness (internal)	Recommendation 8: Gavi Secretariat to ensure that robust systems are in place at all levels to learn lessons in real time from 6.0 policy and programmatic changes, and to course correct as needed.
Output 5: Organisational effectiveness (internal)	Recommendation 9: Gavi to implement an evaluation of their private sector partnerships, including match funding and INFUSE projects. Evaluations should consider how successfully lessons from their 4.0 private sector engagement approach were addressed, looking at the value for money and sustainability of projects. Lessons should support their upcoming Partners in Innovation programme.
Output 5: Organisational effectiveness (internal)	Recommendation 10: Gavi Secretariat should implement regular people surveys at maximum 18-month intervals to assess staff wellbeing and regular Alliance health surveys. Results should be reported back through Committees to the Board.
Output 5: Organisational effectiveness (internal)	Recommendation 11: Gavi to drive efficiencies in the Secretariat Operating Budget throughout 2025 and 2026 at the level endorsed by the AFC and Board, in order to ensure a smooth transition into the 6.0 period.
Output 6: Programmatic delivery effectiveness	Recommendation 12: Gavi to continue to prioritise PSEAH work as an essential part of doing business, fully implementing the annual workplan, with a particular focus on operationalising PSEAH activities and monitoring, continuing implementing partner due diligence and capacity building, and collaboration with other Geneva based organisations to strengthen approaches on PSEAH in health settings at country level. Gavi to fully implement the recommendations and provide updates from the PSEAH Audit.
Output 6: Programmatic delivery effectiveness	Recommendation 13: Gavi to sharpen the focus on cash balances in country. Gavi should design, and implement, policies to periodically reassess the need for cash support with a view to reallocating cash support to countries and/or areas of greatest need.
Output 7: AVMA	Recommendation 14: Gavi to use the AVMA Investors Forum to leverage support from bilateral donors behind ecosystem priorities, notably regulatory strengthening. In parallel, Gavi should use the Gavi–Africa CDC African Vaccine Manufacturing Forum to convene manufacturers, AU Member States and regulators to secure progress on demand commitments from African countries and regulatory milestones.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Gavi’s original theory of change for 5.0/5.1 is that increased equitable and sustainable use of vaccines will reduce mortality and morbidity from vaccine-preventable diseases, thereby reducing poverty and contributing to increased economic prosperity. Strong immunisation programmes lead to healthier, more resilient populations, building human capital and increasing the returns to other investments such as education, which boosts productivity and fosters economic growth. The levers for achieving this are introducing and scaling up vaccines; strengthening health systems to increase equity in immunisation coverage; improving the sustainability of immunisation programmes; and ensuring healthy markets for vaccines and related products. Gavi’s four primary inputs are resource mobilisation, market shaping, the introduction of country co-financed vaccines, and health system strengthening.

The theory of change is reliant on assumptions that all countries continue to prioritise and maintain immunisation levels, and transitioned countries can maintain effective levels of routine immunisation. Since Gavi programmes began in 2000, routine vaccination coverage has increased from 57% to 82%, with a 47% reduction in the number of zero-dose children. Gavi’s vaccine portfolio has also grown significantly over time – in 2024, Gavi supported vaccines against 20 infectious diseases, compared to six in Gavi 1.0. This progress suffered during the COVID-19 pandemic, which created significant economic, health and immunisation disruptions in 2020 and 2021 and had a direct impact on Gavi’s work. While many countries are still feeling the implications of the pandemic, 28 of the 57 countries supported by Gavi succeeded in recovering coverage to above pre-pandemic levels by 2024. This suggests that the original theory of change largely remains valid, but with dependencies continuing to be impacted by economic constraints. The assumptions underpinning the timelines for achieving 2025 results were anchored on the assumptions of an earlier return to 2019 levels and, given the continued impact of the COVID-19 pandemic on routine immunisation systems, some 2025 targets are at risk despite strong annual performance.

During 2023, the COVAX Facility was formally closed. It was agreed to reallocate £120m of UK funding across three areas of Gavi: The Big Catch-up (£31m), AVMA (£49m) and Gavi’s core programming (£40m). As such, as part of the 2023 annual review process, it was agreed to add three additional indicators to the logframe to monitor progress across these three areas, which will be reported on for the first time in this annual review and in the 2025 annual review.[9]
[9] Output indicators 1.4a, 2.7, 7.1, 7.2 and 7.3.

New Output indicators starting 2024 and 2025
Output Indicator	2024 milestone	2025 milestone &Target
1.4.a Of which are introductions of Gavi-supported malaria vaccines into routine immunisation	15	5 (20 total)
2.7 Number of countries implementing Big Catch-Up support	15	20 (35 total)
7.1 AVMA formally launched (Measured for only 2024)	Yes	N/A
7.2 AVMA eligible manufacturers who formally engaged with Gavi on the AVMA	1	1 (2 total)
7.3 AVMA Governance processes completed	1	1 (1 total)

Outcome Reporting

Impact indicator	Milestone	Progress
Under 5 mortality rate in Gavi eligible countries	8% decrease on baseline	12% decrease on baseline[10]
Outcome indicator(s)	Milestone	Progress
Additional future deaths averted (cumulative number in new strategy period)	5.5 million	>5.56 million
Reduction in number of zero-dose children	9.2 million (0% increase relative to baseline)	10.2 million (11% increase relative to baseline)
Unique children immunised (cumulative number in new strategy period)	248 million	>279 million
Economic benefits unlocked (cumulative amount in new strategy period)	US $70 billion	>US $73.6 billion
[10] UN IGME reports data on a longer timeline compared to other metrics meaning data for 2023 became available in January 2025.

Gavi has already met the 2025 target for the impact indicator of under-five mortality rate in Gavi-supported countries, with a 12% decrease. For comparison, high income countries saw only a 5% decrease. Gavi has also exceeded three of the four outcome indicators, with 1.7 million future deaths averted, more than 72 million unique children vaccinated and having unlocked more than $21.6 billion in economic benefits. This means that Gavi is on track to meet its overall commitment of averting 7-8 million future deaths by 2025.

Alongside steady increases in routine vaccine coverage, the number of zero-dose children in 57 Gavi-supported countries decreased by 500,000 to 10.2 million in 2024. This was largely driven by coverage improvements in large countries including India, Ethiopia, and DR Congo, where sub-national and tailored strategies made inroads. However, this figure is still 1 million children higher than the 2024 milestone and there has still not been a return to pre-pandemic levels. The COVID-19 pandemic, rising birth cohorts, and fragility continue to play a role in slowing down progress. Fragile settings represent a substantial and growing share of Gavi’s portfolio, with 28% of zero-dose children in Gavi-eligible countries residing in fragile-classified countries in 2024, up from 23% in 2019. Progress on the Big Catch-Up campaign, implementing learnings from the Zero Dose evaluation, as well as recently approved Board strategies in fragile and humanitarian settings, such as immunising children up to the age of 5, are likely to help see further progress for this indicator. However, Gavi is highly unlikely to meet the 2025 target of 6.9 million children, which would require a 32% reduction over the next year.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Output 1: Introduce and scale-up vaccines
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Breadth of protection: average across all Gavi-supported vaccines	+14pp (58%)	Exceeded +19pp (63%)
1.2 Reach of routine immunisations: DTP3, MCV2, PCV3 and HPV2 coverage	DTP3: +0pp (83%) / MCV2: +11pp (68%) / PCV3: +19pp (75%) / HPVC: +13pp (17%)	Met on average DTP3: -1pp (82%) –Not met / MCV2: +13pp (70%) – Exceeded / PCV3: +19pp (75%) – Met / HPVC: +22pp (25%) –Exceeded
1.3 Rate of scale-up of new vaccines	PCV3: 90% / Rotac: 90% / MCV2: 90% / YF: 90%	Exceeded on average PCV3: 92% – Exceeded / Rotac: 95% –Exceeded / MCV2: 77% – Not met / YF: 98% –Exceeded
1.4 Introductions of Gavi-supported vaccines into routine immunisation	20 (62 total in 5.1 through end of 2024)	Exceeded 28 (70 total in 5.1 through end of 2024)
1.4a Of which are introductions of Gavi-supported malaria vaccines into routine immunisation	15 (15 total in 5.1 through end of 2024)	Exceeded 17 (17 total in 5.1 through end of 2024)
1.5 Preventative campaign reach (measles)	50% of previously unvaccinated children under 5 who receive an MCV dose through a campaign	Limited Data: 77%[11]
1.6 Timely outbreak detection and response	+3pp (28%)	Not met / -14pp (4%)
[11] Based on data from six countries, limited data available.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.1: Exceeded. Breadth of protection (BoP), which averages coverage across ten Gavi-supported vaccines, has steadily increased since 2019. Between 2023 and 2024, BoP in Gavi57 countries rose from 56% to 63%, exceeding the annual milestone of 58% in 2024 and already exceeding the 2025 target of 60%. The 8 percentage point (pp) increase in BoP was driven by increases in coverage of the second dose of inactivated polio vaccine (IPV2), last dose in the schedule for human papillomavirus vaccine (HPVC), second dose of measles-containing vaccine (MCV2), pneumococcal conjugate vaccine (PCV3), rubella containing vaccine (RCV1), yellow fever vaccine (YFV), and last dose in the schedule for rotavirus vaccine (RotaC). All Gavi-supported vaccines had higher coverage in 2024 than in 2023.

Output 1.2: Met on average. MCV2 coverage has risen from 57% in 2019 to 66% in 2023 and 70% in 2024, exceeding the 2024 milestone and already meeting the 2025 target for Gavi 5.0/5.1. This is due to improvements in large population countries such as DR Congo, Uganda, India, and Ethiopia. With a baseline of just 3% in 2019, HPVC coverage among implementing countries has also steadily risen to 25% in 2024, an increase of 9pp from last year (16%), surpassing the 2024 milestone and already exceeding the 2025 target for Gavi 5.0/5.1. The improvement reflects the Alliance HPV revitalisation efforts and was largely driven by switches to one-dose schedules, following a change in SAGE recommendations, and introductions with one dose in large countries such as Nigeria and Bangladesh. PCV3 coverage in Gavi57 countries has significantly increased from 56% in 2019 to 71% in 2023 and 75% in 2024, meeting the 2024 milestone. This was largely due to completion of PCV scale-up in India. While the 2024 milestone of 83% was narrowly missed, DTP3 coverage in Gavi57 countries improved from 81% in 2023 to 82% in 2024, nearly returning to pre-pandemic levels after a 5pp drop between 2019 (83%) and 2021 (78%). This was driven by significant improvement in many countries, including India, DR Congo, Ethiopia, Mali, and Syria. The improvement was moderated by substantive declines in Sudan, Yemen, Uzbekistan, and Madagascar in 2024. Recovery remains uneven across countries in 2024: 28 countries (49%) had DTP3 coverage at or above 2019 levels, while 29 countries (51%) remained below. Coverage in fragile and conflict countries (61%) continues to be significantly lower than high-impact (84%) and core countries (85%).

Output 1.3: Exceeded on average. This indicator is defined as the coverage of four new routine vaccines (PCV3, Rotac, MCV2 and YFV) relative to their benchmark vaccine (DTP3 or MCV1) within the reference time frame for new introductions (2 years for PCV3 and Rotac and 3 years for MCV2 and YFV). It indicates whether a new introduction increases coverage quickly to match coverage of existing vaccines in the national schedule, and its target is 90% for all four vaccines. Coverage of PCV3, Rotac, and YFV relative to the benchmark vaccines in 2024 is 92%, 95%, and 97%, respectively, all exceeding the target threshold. Coverage of MCV2 relative to the benchmark vaccine of MCV1 decreased by 2pp from last year to 77% in 2024, falling short of the 90% threshold. The drop in MCV2 coverage was driven by declines in countries such as Papua New Guinea, lack of timely scale-up in Ethiopia, Nigeria, and Mozambique, and downwards revisions in coverage in Senegal and Ethiopia. Ethiopia and Nigeria both experienced stockouts of MCV2 in 2024. It should also be noted that this indicator assumes it takes three years post-introduction for a new MCV2 routine vaccine to achieve coverage relative to that of the existing MCV1 routine vaccine following a similar immunisation schedule, and as such more recent introductions are excluded.

Output 1.4: Exceeded. In 2024, significant progress was made towards strategic indicator 1.4, with 28 routine introductions. This was largely driven by new introductions of the malaria vaccine, HPV revitalisation efforts, and postponed launches from 2023. Overall, 70 routine introductions have been completed between 2021 and end 2024, against the cumulative target of 82 by end 2025. Looking ahead to 2025, the overall number of routine introductions has exceeded the Gavi 5.0/5.1 target. In 2025, 37 additional routine introductions are planned. This is a result of the exceptionally high number of country applications for Gavi support approved over the last year, driven by the applications for the recent or revitalised programmes such as malaria, hepatitis B birth dose, HPV, and catalytic support to new introductions in Middle Income Countries (MICs).

Output 1.4a: Exceeded. 2024 saw the rapid introduction and rollout of malaria vaccines across 17 countries; one of the fastest vaccine roll-outs. New introductions in 2024 began with Cameroon in January 2024 and Burkina Faso in February 2024. Although initial supply limitations meant that subnational targeting of high-risk populations was necessary in early introduction countries, the WHO recommendation and pre-qualification of a second malaria vaccine (R21) in December 2023 facilitated the introduction of the vaccine in 17 countries in 2024. During the country-level planning processes, national malaria control and immunisation programmes collaborated in the identification of high-risk populations in moderate and high transmission areas and identified how the vaccine would be incorporated into the national mix of malaria interventions. Each country planning for and introducing the malaria vaccine was provided with technical assistance through Gavi’s extended partners peer-learning and lesson sharing, which was facilitated through weekly teleconferences and webinars and through four face-to-face peer learning workshops with Gavi support and participation. During 2024 approximately 5 million children were targeted with the malaria vaccine and Gavi and UNICEF delivered more than 12 million doses.

Output 1.5: Limited data.: 23 Measles/Measles-Rubella campaigns were conducted in 2024. Out of these, 17 countries conducted a post-campaign coverage survey (PCCS) with two pending report submissions. Only six of these surveys have collected and reported information on the measles zero dose indicator through the PCCS, with an average of 77% of measles zero dose children reached during the campaigns. Although this shows an improvement in the completion rate for the PCCS,. the challenge of measuring and reporting on this measles campaign reach indicator is well established and has been reviewed for the 6.0 strategy. Further details on this are noted under Recommendation 3 later in the report.

Output 1.6: Not met In 2024, the number of countries experiencing large or disruptive outbreaks increased sharply. As such, countries requested record international support for outbreak control, with 50 vaccine requests approved by the International Coordinating Group (ICG) on Vaccine Provision and the Measles and Rubella Partnership Outbreak Response Fund in 2024, reaching over 55 million persons at risk in active outbreak areas (cholera: 33 requests; meningitis: 6; measles: 6; yellow fever: 5; Ebola virus disease: 0)[12]. While the median time from outbreak detection to response improved in all disease areas in 2024, challenges to detect and respond to outbreaks within the indicator timelines persist, and only 2 (4%) out of the 47 outbreak response vaccination activities with complete data available met the disease specific timeliness criteria. To make these findings more actionable in 6.0, Gavi will monitor additional sub-indicators including time from outbreak detection to application to ICG or the relevant mechanism, time from application to approval, and time from approval to initiation of outbreak response, as this will aid in determining where delays are occurring (i.e. outbreak detection and request submission at country level, request processing at global level or country implementation) and what support may be needed to improve timeliness.
[12] Of these, 19 of 50 outbreak response requests were in Fragile & Conflict segment countries – primarily South Sudan (Cholera: 5; Yellow Fever: 1; Measles: 1), Sudan (Cholera: 6); Niger (Meningitis: 2; Cholera: 2), Somalia (Cholera: 1), and Yemen (Cholera: 1). Outbreaks easily spread in these settings with lower levels of routine immunization coverage, limited access to safe water and sanitation, timely and appropriate case management, and movement of displaced persons. Vaccination remains a primary line of defence and means to protect populations, though campaigns are challenging and take time to implement given the difficult logistical and security context, including often limited access to at-risk populations, cold storage for vaccines, and health system structures to support campaign implementation.

Large and disruptive outbreaks, many of which cross borders, continue to put lives at risk and put pressure on health workforces and systems. The record number of requests place strain on global stockpiles (cholera, meningitis) and the Gavi Secretariat and Alliance partners worked to ensure global supplies of outbreak response vaccines increased to meet this demand, and that the vaccines and funding for implementation were available and rapidly supplied to countries.

Even with this increasing outbreak trend, the time to detect, request and receive international vaccine support, and respond to these outbreaks has improved year-on-year. For example, while not meeting the target of 27 days, the time from outbreak detection to start of cholera vaccination campaign halved from a median of 131 days in 2022 to 66 in 2024. Importantly, the cholera outbreak declaration is often at a national level, whereas the response is at district level, therefore response in a district may be more timely than the indicator captures. This is because doses can be reallocated in-country once they arrive to reach the highest burden area where they will have most impact i.e., where the outbreak has recently arrived and is still expanding, rather than the originally affected areas that triggered the national outbreak declaration that may already be in decline. Furthermore, without a clear definition of an outbreak threshold for cholera – as it depends on countries’ endemicity and quality of surveillance – determining the starting point for calculating timeliness remains a challenge. Aiming to enhance outbreak detection and vaccination targeting, Gavi supplied 1.8 million cholera rapid diagnostic tests to 16 countries in 2014 and supported studies to improve their use, reduced costs through pooled procurement, and prepared to expand support to 21 countries in 2025.

Pentavalent meningococcal conjugate vaccine (MenACWYX or MenFive) was used for the first time in 2024 for outbreak response, following the vaccine’s prequalification and updated SAGE recommendations. Over 5 million children and adolescents in Niger and Nigeria were reached during active epidemics, preventing future death and disability. Even with the first use of this vaccine, which required substantial effort in healthcare worker training, communication, and adverse events following immunisation (AEFI) management, the median time to launch the reactive vaccination campaign from a district crossing the epidemic threshold decreased 10% from 2023 to 2024 (median: 72 to 65 days). Preliminary data for 2025 shows that this trend continues to improve (median: 58 days)

Following IA2030 Partnership Council recommendations, ICG and Gavi have improved approval processes and countries are beginning to use doses already in-country more rapidly, i.e., those unused from past campaigns, repurposed from a previously approved response that is no longer necessary, or prepositioned stock from global stockpiles in highest risk countries. This is enabling a faster response and stopping outbreaks before they spread, such as Zambia’s approach to cholera outbreak containment in 2024, with outbreak detection to oral cholera vaccine (OCV) campaign launch just 12 calendar days. It should be noted that accountability for meeting this indicator is shared between governments – whose role is most critical in timely detection, confirmation, request, and implementation, Alliance partners – whose role is critical in outbreak preparedness and response support, and the ICG mechanism – which is a consortium of partners whose role is critical in rapidly reviewing and approving requests and facilitating the transfer of operational funds. The Gavi Secretariat provides funding for vaccines, operational funds, and outbreak response technical assistance but implementation is led by governments, and alliance partners; UNICEF and WHO primarily.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations 2023	Progress in 2024
Recommendation 1: Gavi to support HPV programmes to be sustained by increasing focus on institutionalising HPV programmes into national programmes using an integrated approach.	Gavi is increasing its focus on institutionalising HPV vaccine delivery into national immunisation programmes through two main approaches: / Generating evidence on integrated best practices and implementation feasibility: / Gavi is funding a multi-country HPV learning agenda through its strategic focus area (SFA) funds until 2025, with 10 projects focussed on: adolescent service integration (7), cross-portfolio knowledge translation (1), HPV measurement (1), and cervical cancer screening integration (1). This agenda includes dedicated support from Global Affairs Canada. The adolescent service integration projects, implemented across 11 countries, are testing service delivery models that combine HPV vaccination with other adolescent health services, developed through participatory approaches to meet the needs of adolescents, caregivers, and health workers. A cross-portfolio knowledge translation project is aligning lessons and dissemination strategies across the portfolio, culminating in an in-person workshop to synthesise insights and contribute to global evidence on sustainable HPV programming. Leveraging Unitaid investment in cervical cancer screening, one project is learning from integration of HPV vaccination for girls and screening for women in Nigeria and Cote d’Ivoire. / Providing technical support and targeted funding: / Additional health systems strengthening funding has been provided to 16 countries for interventions to strengthen their HPV vaccination programmes, and dedicated targeted country assistance (TCA) is provided to 42 countries to support Ministries of Health to ensure HPV vaccination is sustainably embedded within national health strategies and service delivery systems.
Recommendation 2: Gavi to work with other health partners to strengthen the second year of life contact point – including by leveraging malaria vaccine introductions - to help countries reduce drop-out between doses & reduce Under Immunised Children.	Gavi is strengthening the second year of life (2YL) platform by using key vaccine contacts to improve immunisation coverage and integration with broader health services. / MCV2: Gavi, in collaboration with the Measles and Rubella partnership (M&RP), are leveraging the second dose of measles-containing vaccine (MCV2) as a strategic entry point to strengthen the 2YL vaccination platform. To support this effort, Gavi is helping countries transition from 10-dose to 5-dose MCV vial presentations, aiming to improve both first and second dose coverage, reduce missed opportunities for vaccination, and lower drop-out rates - ultimately reaching more under-immunised children. / Malaria: As selected countries enter into the second year of malaria vaccine implementation, Gavi and Alliance partners are also supporting the delivery of the fourth malaria vaccine dose as an additional opportunity to reinforce 2YL services. This includes providing technical assistance and guidance to countries on community-focused demand generation, as well as integrating other public health interventions (including Global Fund-supported seasonal malaria chemoprevention) to check immunisation status and refer children for follow up vaccination, and the use of the vaccination touchpoint as an opportunity for malaria messaging and distribution of insecticide treated bed nets. Joint immunisation and malaria communications and service delivery activities are being planned across the two programmes and are included in the package of increased coordination and operational support across Gavi and Global Fund. / Learning agenda: In parallel, Gavi is supporting a learning agenda to generate evidence for both vaccine strategies. For MCV2, studies are underway in two countries (Zambia and Ethiopia) through 2025 to measure the impact of the 5-dose presentation switch on coverage, assess cost-effectiveness, evaluate health care worker behaviour and practices, and overall programmatic impact of the MCV presentation switch. For the malaria vaccine, four multi-country studies across seven countries with malaria vaccine are examining how its implementation can improve uptake of other routine immunisations and primary health care services and evaluating strategies to tailor the vaccine schedules for areas of highly seasonal malaria transmission. / Health systems strengthening: Subject to available funding, the 6.0 Health Systems Strategy will include an increased focus on reaching and fully immunising children through the second year of life as a priority for countries to consider, including through tailored service delivery and demand strategies to reduce drop-out after the last vaccination contact in the first year of life. The second year of life will also serve as a critical opportunity for catch-up vaccination, building from the experience and learnings of the Big Catch Up. Furthermore, the HSIS allocation formula now includes consideration for MCV2 coverage to recognise the importance of this contact point and inform resource allocation. However, this approach may be at risk of funding constraints in a context where the HSS envelope has been cut by more than 45%.
Recommendation 3: Indicator 1.5 does not currently provide meaningful results due to a lack of data and Indicator 1.6 is particularly complex to calculate. Gavi to consider how reporting can be improved for 2024 and 2025. In developing the results framework for 6.0, Gavi should ensure that all indicators are able to be measured to provide meaningful results.	Indicator 1.5: Preventative campaign reach (measles) - unvaccinated under 5s who receive an MCV dose through campaigns / Gavi continues to update the previous year’s figures as new post-campaign coverage survey (PCCS) reports are received. However, in order to improve the indicator, Gavi has engaged with the Measles and Rubella Programme (M&RP) partners to explore how this indicator could be more effectively measured, such as alternative/more targeted post-campaign coverage survey approaches – and how countries can better use this data to inform mop-up/RI strategies. Through the Measles and Rubella Partnership, Gavi has proposed a new KPI: 100% of countries do a PCCS within 3 months of campaign, with reporting that includes data relevant to indicator 1.5. Additionally, Gavi is interested in expanding the focus beyond zero dose to also include those who are 'under-immunised' (e.g. have received one dose) which better reflects the programmatic goal of reducing dropout and improving full immunisation coverage. / For Gavi 6.0: The Secretariat agrees with the importance of ensuring all indicators are measurable and can provide meaningful results in 6.0. Multiple discussions on this indicator were held in the Alliance Technical Working Group for developing the 6.0 measurement framework. Indicator 1.5 is not being included in the mission and strategy performance indicators for 6.0 because this has been less meaningful in 5.0 due to lack of data and limited data quality. Campaigns are expected to be a focus of the Gavi 6.0 Execution Framework and the Board will have visibility on process-oriented metrics related to campaign implementation. / Indicator 1.6: Timely outbreak detection and response / Gavi is engaging with both the ICG and Measles and Rubella Programme (M&RP) partners on how to make the interpretation of this indicator more actionable and how to ensure that the support provided to countries can be better monitored, not only in terms of timeliness but also how to leverage learnings from outbreak response to strengthen routine immunisation, notably through root cause analyses. In particular, closer monitoring of improvements in the duration of the time spent on each step of the pathway is underway across disease programs, including monitoring median and 25th/75th percentiles of these time steps. The ICG is also reviewing the target timelines for each disease program to ensure they remain fit for purpose, and WHO disease control teams are reviewing definitions and modalities of tracking of outbreak thresholds and declarations. / For Gavi 6.0: Indicator 1.6 is included among the strategy and performance indicators for 6.0. A decision on this was a result of conducting a thorough review of the indicator with Alliance colleagues. Multiple discussions on this indicator were held in the Alliance Technical Working Group as well as with FCDO colleagues where it became clear that IA2030 is continuing to use this indicator and that retaining this indicator would be necessary to remain aligned with IA2030. More granular tracking of timeliness is planned in addition. Meanwhile, some issues with data availability remain for the timeliness indicator, in particular in cases such as cholera outbreaks in endemic settings. This is due to the difficulty of clearly defining the start of the outbreak, since epidemic thresholds are not established for cholera, and initial responses often emphasise access to clinical care and other control measures (e.g. access to safe water). Furthermore, outbreak declaration is often at national level whereas response is conducted at district level. Data on this indicator is available for other outbreaks and we will work with WHO and the ICG Secretariat to define and track cholera outbreak response more consistently to be able to more meaningfully use this indicator.
Recommendation 4: Gavi to work with other actors, most notably Global Fund, to support country-led, comprehensive approaches to malaria that includes joint planning and coordinated service delivery and works towards a goal of harmonised applications, reporting, and financing. Collaboration should reduce transaction costs for countries, optimise malaria interventions and ensure limited resources are utilised in support of country priorities in the most effective manner, supporting a step-change in results at a moment when development gains in malaria are under threat.	Gavi has made progress on this recommendation, engaging closely with the Global Fund, the Global Financing Facility (GFF), and others to adapt respective approaches to supporting countries in a more coordinated, streamlined way. Gavi has requested guidance regarding potential solutions from the Joint Committee Working Group, a consultative body with representatives from the governance bodies of Gavi, Global Fund, and the GFF, and most recently, brought forward a discussion on deepening collaboration to the Gavi Board (during the April 2025 retreat) and Gavi PPC, with a specific focus on enhanced collaboration with Global Fund on malaria. Gavi continues to operationalise the guidance received to date on country-focused initiatives to strengthen the coordination of planning, application, and delivery of coordinated and/or integrated malaria-focused services – with a particular focus on the “Wave 1” countries identified through this joint initiative (Chad, Ethiopia, Guinea, Malawi, and Mozambique). All five countries have included malaria in their priority actions and the country teams from Gavi and Global Fund have increased their coordination around support for coordinated planning and service delivery. For Mozambique and Guinea, the focus is on including all malaria interventions in plans to integrate PHC services during 2025. Ethiopia and Chad are carrying out detailed planning on how to combine interventions such as bednet distribution, vaccine rollout, and seasonal malarial chemoprophylaxis in Q3 2025. Malawi is prioritising a cost benefit analysis of malaria interventions. All five countries have taken preliminary steps to coordinate between EPI and NMC programmes and are considering additional steps, including common monitoring. These activities represent initial progress towards Gavi and Global Fund’s joint commitment to integrate their support behind national malaria and immunisation plans in at least 80% of countries implementing malaria vaccines by 2027. Additional shifts will be assessed and taken forward by a forthcoming joint Gavi-Global Fund Taskforce convened by the respective organisations’ CEO and ED.

Output Title	Output 2: Strengthen health systems to increase equity in immunisation
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Geographic equity (DTP3 coverage in the 20% of districts with the lowest coverage)	+4pp from 2019 baseline (71%)	Not met: -1pp (66%)
2.2 DTP drop-out in Gavi57	+0pp from 2019 baseline (6%)	Met: +0pp (6%)
2.3 Coverage of first dose of DTP vaccine (DTP1)	+0pp from 2019 baseline (88%)	Not met: -1pp (87%)
2.4 MCV1 coverage in Gavi57	+0pp from 2019 baseline (81%)	Not met: -1pp (80%)
2.5 Composite Effective Vaccine Management score	+1.4pp from 2021 baseline (73.8%)	Exceeded: 74.1%
2.6 % of HSS and Equity Accelerator Fund (EAF) grant applications including interventions to address gender-related barriers to immunisation	60%	Exceeded: 100%
2.7 Number of countries implementing Big Catch-Up support	15	Exceeded: 26

Briefly describe the output’s activities and provide supporting narrative for the score.

Coverage of DTP1 and MCV1 continue to improve at portfolio level yet remain below pre-pandemic levels. Despite coverage being lower than 2019, with population growth (3% higher than 2019) Gavi57 countries reached more children in 2024 than in any other year. There is also variability across Gavi’s segments, with fragile and conflict-afflicted[13] countries continuing to have significantly lower coverage on average (DTP1: 70%; MCV1 60%) than high impact[14] (DTP1: 89%; MCV1 83%) and core[15] countries (DTP1: 90%; MCV1 83%).
[13] Afghanistan, CAR, Chad, Haiti, Mali, Niger, Papua New Guinea, Somalia, South Sudan, Sudan, Syrian Arab Republic and Yemen.
[14] India, Nigeria, Ethiopia, DRC and Pakistan.
[15] Burundi, Benin, Burkina Faso, Bangladesh, Côte d'Ivoire, Cameroon, Congo, Comoros, Djibouti, Eritrea, Ghana, Guinea, Gambia, Guinea-Bissau, Kenya, Kyrgyzstan, Cambodia, Lao PDR, Liberia, Lesotho, Madagascar, Myanmar, Mozambique, Mauritania, Malawi, Nepal, DPR Korea, Rwanda, Senegal, Solomon Islands, Sierra Leone, Sao Tome and Principe, Togo, Tajikistan, Timor-Leste, Tanzania, Uganda, Zambia, Zimbabwe.

By 2024, nearly all countries have launched new health systems programming to strengthen and expand the reach of health systems to fully immunise zero-dose children, and through the Big Catch-Up, 35 countries were approved for additional vaccine and cash support to immunise children not reached during the pandemic. Acceleration of this programming in 2025 will be critical to progressing towards the zero-dose goal (requiring a 32% reduction to reach the Gavi 5.0 target), however, this will be challenging amid broader Official Development Assistance (ODA) reductions which are impacting the delivery of primary health care services and key platforms (e.g. digital health information systems) across many Gavi countries. Beginning in 2026, Gavi will roll out the new, Gavi Board-approved 6.0 Health Systems Strategy alongside key grant management reforms, aiming to strengthen sustainability and equity while offering countries greater flexibility. At the same time, Gavi’s own health systems funding will decrease by roughly 45% compared to 5.0 levels, making it essential for countries to optimise the resources available.

Output 2.1: Not met. DTP3 coverage in the 20% of districts with the lowest coverage was 66% in 2024, a decline from 69% in 2023. Reporting on this indicator is not consistent across all Gavi-supported countries and can change from year to year. In 2023, for example, some countries with large declines (e.g. Sudan, Senegal) and low coverage (e.g. DPRK) did not report against this indicator, driving the unweighted average up. In 2024, some countries with low coverage (e.g. Somalia, South Sudan) did report and other historically well performing countries (e.g. India, Malawi) did not, driving the average down. Additionally, sub-national data is often observed to have data quality issues. Due to these factors, it is difficult to interpret the results from year to year. This indicator now sits 1pp below pre-pandemic levels – the same as national-level DTP3 coverage (82%), underscoring the need for attention to address subnational disparities in reach and access to immunisation. Among the 38 countries that have reported consistently across all years (a more meaningful indicator given countries coming in and out of the data set tend to skew the data) coverage has remained constant at 70%, although still slightly below the 71% target and no increase from last year.

Output 2.2: Met. Drop-out between the 1st and 3rd dose of DTP vaccine remained at 6% in 2024, consistent with the 1 percentage point (pp) increase in both DTP1 and DTP3 coverage across Gavi57 countries. Dropout has historically been much higher in Fragile and Conflict countries (13%) compared to Gavi57 countries as a whole, highlighting the need for concerted efforts in these countries to maintain demand for and access to immunisation beyond the first contact. Through enhanced catch-up policies and programming supported by the Big Catch-Up, countries also have an opportunity to reach children up to age 5.

Output 2.3: Not met. Coverage of the first dose of DTP vaccine (DTP1) increased by 1pp to 87% in 2024, compared to 2023, but still lags 1pp behind the 2019 baseline. In 2024, there were 10.2 million children not immunised with DTP1 (i.e., zero-dose children) compared to 10.7m zero-dose children in 2023 (a 5% decrease). This is 10% higher than 2019 levels (900k more zero-dose children) and will require a 32% reduction to meet Gavi’s 2025 target. The reduction in the number of zero-dose children in 2024 was driven primarily by increases in coverage in high-impact countries, especially Ethiopia (+4pp), DR Congo (+2pp), and India[16] (+3pp). Looking at long-term trends, Gavi-supported countries were reducing the number of zero-dose children at a rate necessary to meet the 2025 target during Gavi 4.0 (2015-2019). However, the COVID-19 pandemic disrupted this decline and recent ODA cuts pose new challenges for country health systems. 28% of zero-dose children in Gavi-supported countries live in countries in the Fragile & Conflict segment, up from 18% in 2020 although these countries account for only 12% of the Gavi57 surviving infant cohort. Four fragile and conflict countries (Mozambique, Myanmar, Sudan and Yemen) experienced especially significant coverage declines in 2024.
[16] As of 2022, India is among 19 countries that have transitioned from Gavi support and now self-finance their immunisation programmes. Due to the size of its birth cohort, India continues to receive timebound, targeted support from Gavi.

Output 2.4: Not met. While coverage for the first dose of measles-containing vaccine (MCV1) increased from 78% in 2023 to 80% in 2024, it still falls below the 81% coverage at the baseline (2019) and the level of coverage required to prevent outbreaks (95%). In 2024, 24 Gavi57 countries increased MCV1 coverage including India (+4pp), Ethiopia (+4pp), Mali (+4pp), Guinea (+5pp), and 27 countries experienced a decline including Papua New Guinea (-8pp), Sudan (-5pp), Benin (-8pp), Kenya (-3pp). Gavi57 countries represent 15.5 million (75%) of the 20.6 million children globally missing the first dose of measles vaccines. Given the high transmissibility of the virus and risk for serious outbreaks, continued investment to close immunity gaps through routine immunisation of at least two doses of measles vaccine and supplementary campaigns remains critical.
Output 2.5: Exceeded. The Composite Effective Vaccine Management (EVM) score reflects the collective efforts of countries, the Gavi Secretariat and Alliance partners to strengthen immunisation supply chains and ensure equity and efficiency objectives are achieved. In 2024, the composite EVM score across all Gavi-supported countries that completed an EVM assessment was 74.1%. Eight EVM assessments were conducted during the year in Burkina Faso, Chad, Guinea Bissau, Haiti, Lesotho, Malawi, Mali, and South Sudan. All these countries recorded improvements compared to their previous assessments, underscoring progress in supply chain performance. This positive trend signals continued recovery from COVID-19 related disruptions, which had previously delayed country applications and implementation. As highlighted in the 2023 Annual Review, the introduction of EVM 2.0 introduced more rigorous scoring criteria, which moderated results despite underlying improvements. The increase in both the number of assessments and their scores in 2024 demonstrates renewed momentum as countries re-engage with routine immunisation strengthening efforts. Malawi notably became the first Gavi-supported country to complete a second EVM 2.0 assessment, achieving an 11% improvement since its initial assessment in 2021.

Output 2.6: Exceeded. In 2024, 12 countries applied for HSS and/or EAF grants. All countries (100%) included interventions to address gender-related barriers to immunisation in their applications. Common gender responsive approaches included: conducting integrated outreach vaccination services specifically designed to meet the health needs of mothers and adolescent girls (Nepal, Guinea, Nigeria); organising flexible vaccination sessions/weekend sessions/extending vaccination schedules to be more convenient for female caregivers (DR Congo, Liberia, Zimbabwe, Guinea); engaging women-led CSOs and women groups to address gender-related barriers to immunisation through capacity building and inclusive engagement (Nepal, DR Congo); engaging male immunisation champions to promote positive attitudes towards vaccination (Zimbabwe, Nigeria, Gambia); organising vaccination sessions at congregation points such as markets frequented by mothers and caregivers, crossroads, ports, and women’s gatherings (DR Congo); strengthening a gender-responsive health workforce through inclusive training, leadership development, and capacity building to improve equitable immunisation service delivery (Nepal, DR Congo, Benin, Rwanda, Liberia, Nigeria). In many cases gender technical assistance is embedded in EPI services at the sub-national level. This has led to many positive results, often beyond immunisation services, with examples of having influenced malaria programming and gender being fully incorporated into EPI plans. Gavi is now developing a community of practice, listing out all examples of gender-based indicators, mapping all relevant documents and building an AI chatbot to support gender inclusion.

Output 2.7: Exceeded. By end 2024, 26 of 35 approved Gavi-supported countries were implementing Big Catch-Up immunisation activities to vaccinate children who were missed during the COVID-19 pandemic, restore routine immunisation coverage to at least pre-pandemic levels and strengthen routine immunisation systems – having administered by end 2024 more than 20 million catch-up doses of pentavalent vaccine, measles-containing vaccine (MCV) and inactivated polio vaccine (IPV), reaching an estimated more than 6.4 million children. By end March 2025, those figures had climbed to 32 countries implementing, at least 27.5 million doses administered and over 7.1 million children reached. This was supported by the deployment of approximately 170 Technical Assistance positions across 20 countries as well as regional offices to support readiness and preparatory activities. Notwithstanding this progress, the cross-Alliance Big Catch-Up Task Team has been working with countries to accelerate implementation given that some countries have experienced delays in implementation and the programme formally ends in December 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation 2023	Progress in 2024
Recommendation 5: Gavi to ensure processes are in place to learn lessons from the range of strategies being undertaken through Big Catch Up and Equity Accelerator Funding on how innovative approaches and integrated planning and programming can be most effective and impactful.	Gavi is monitoring, evaluating, and learning from the experiences of zero-dose and Big Catch Up in a number of ways to strengthen ongoing programming and inform the design of 6.0 approaches. Learnings will be incorporated into Gavi 6.0 Programme Funding Guidelines to support countries in designing appropriate and evidence-based interventions. / Related to zero-dose (ZD) this includes: / The ZD Learning Hub advanced the programmatic evidence base across the IRMMA framework in Bangladesh, Mali, Nigeria, and Uganda, and at the global level. In Bangladesh and Nigeria, implementation research and costing demonstrated the effectiveness of tailored ZD interventions, while strengthened subnational monitoring data supported collaborative solution-finding. Mali conducted a household survey in three districts to explore ZD determinants and establish a baseline for two supply-side interventions. Uganda evaluated its house-to-house registration campaign to improve microplanning and is documenting barriers and facilitators to EAF-funded activities. All countries recorded instances of evidence use for decision-making. Globally, accomplishments included a knowledge translation toolkit, a webinar series, and semi-annual updates, which informed both country-level decisions and Gavi 6.0 strategies (https:///zdlh.gavi.org). / The Phase 2 Evaluation of Gavi’s contribution to reaching ZD children and missed communities provided robust and credible evidence to enable programmatic improvements during Gavi 5.0/5.1 and to inform the development of Gavi 6.0. Gavi commissioned Ipsos to undertake an independent evaluation of Gavi’s contribution to reaching ZD children and missed communities between September 2022 and October 2025, including how Gavi’s funding and non-funding instruments, and its Secretariat architecture, facilitated critical interventions and global health outcomes in the countries it supports. / Multi-country convenings organised to share lessons from ZD, gender, demand and equity programming in 5.1 and foster peer-to-peer dialogue. In September 2024, Gavi also organised a ZD learning week to share emerging evidence on reaching ZD children. / The ZD Implementation Monitoring Mechanism is being rolled out to track and assess how well workplan interventions (including funding) are being implemented to identify and reach ZD and under-immunised children. It utilises a defined set of metrics to enhance visibility into what is working and what is not across priority investment areas and the ZD agenda. This enhanced visibility supports evidence-based decision-making, helps country teams and the Alliance identify specific gaps in delivery or coordination to enable timely course correction so that children who have not received any routine vaccines are effectively reached and vaccinated. / Related to the Big Catch Up, this includes: / Quarterly progress reporting from the 35 countries and aggregating the results into a global dashboard, enabling stakeholders to track progress regularly and address challenges swiftly. The quarterly monitoring forms capture information from implementing countries on readiness, performance against targets, service delivery strategies used, successes, challenges and adjustments made. Countries are also encouraged to conduct intra-action reviews, rapid convenience assessments and behavioural and social drivers of vaccination assessments to understand what drives uptake of vaccines in older children and the effectiveness of the catch-up approach. / Gavi has commissioned nine country case studies to generate evidence and learning from the Big Catch-Up and facilitate in-depth understanding of countries’ catch-up planning, implementation, monitoring and results to bring out best practices, challenges and lessons learned. The case studies, which will be available in December 2025, will also analyse the barriers preventing individuals from receiving vaccinations on time or through catch-up efforts and explore how catch-up vaccination efforts can be established, strengthened and institutionalised within immunisation services and primary health care for sustainable coverage. Experiences of providing catch-up vaccination in fragile and conflict-affected areas will also be documented. / An independent evaluation of the Big Catch-Up is planned to identify and document effective strategies and delivery approaches to reach ZD and under-immunised children and whether the design of the Big Catch-Up approach achieved the intended outcomes. The final report is expected in mid-2026. / In addition, Gavi funded Big Catch-Up-specific technical assistance positions in the UNICEF and WHO Regional Working Groups who convene regular meetings with country colleagues to share their unique approaches, progress and challenges in the preparation and implementation of the Big Catch-Up. Gavi-supported Big Catch-Up TA at the country level are also documenting their learnings in collaboration with the Regional Working Groups. A TechNet community platform for the Big Catch-Up has been created to share resources and lessons learned. / Gavi is in the process of mainstreaming these Big Catch-Up learnings into Gavi 6.0, subject to available funding, developing an approach to institutionalise and routinise catch-up vaccination at the country-level to leverage the intensified efforts and learnings under the Big Catch-Up. The Gavi Secretariat, as part of the new Health System Strategy, has been incorporating best practices and innovative approaches to reach older children up to age five into Gavi’s Programme Funding Guidelines to guide investments towards impactful interventions.
Recommendation 6: Gavi Secretariat to work with Alliance Partners to ensure that all are ready to deliver the key shifts proposed in the Health Systems Strategy for the 6.0 period. This will include ensuring processes are in place for stronger use of country systems, working with countries to set national HSS priorities, aligning behind national HSS plans/strategies, and ensuring HSS funds are used to sustainably strengthen Primary Health Care (PHC).	The key operational shifts required to implement the Health Systems Strategy have been agreed with Alliance partners and are detailed in the document recently approved by the Gavi Board. This includes work to develop the Programme Funding Guidelines for Gavi 6.0, which will serve as the guide to countries as they develop their new applications for holistic cash support and will outline the ‘flagship interventions’ and key considerations for PHC integration. The Secretariat is also developing a robust change management and socialisation plan for Gavi 6.0, which will include the key elements of the Health Systems Strategy, to ensure that the Secretariat, partners and countries understand the major shifts and are prepared to implement them from 2026. / As part of the 6.0 grant management reform and to strengthen country ownership and alignment of Gavi support to national plans and priorities, two countries, Mozambique and Guinea-Bissau have successfully piloted the use of their National Immunisation Strategies to apply for holistic Gavi support for the 2026-2030 period. The learnings from this pilot will inform the scale-up of this approach in Gavi 6.0. There remains a risk that NIS are not fully aligned to broader health sector plans, and Gavi is engaging actively with WHO and UNICEF (who oversee the NIS tools and guidance and provide TA at country level) to strengthen these linkages. / Regarding the use of country systems, in Gavi 5.0 Gavi exceeded one of two Board KPIs to channel at least 55% of funding through country systems and has met the second to increase to 66% the number of countries using country systems. This was enabled with dedicated funding to strengthen Financial Management and Risk Assurance (FMRA). While Gavi is likely to retain a high ambition to channel funding through country systems in 6.0, the new target which will include risk and assurance for an estimated 50 countries, expanded use of mobile money solutions, and capacity building, will need to be informed by the level of available funding. / Gavi has shown progress in strengthening country planning systems, with 100% approval rate for HSS/EAF applications during 2024. This is particularly notable given EAF applications had a higher approval bar.
Recommendation 7: Gavi to progress the Lusaka Agenda workstreams with the Global Fund and GFF on malaria, HSS (including HSS metrics) and country implementation, showing tangible progress in a set of first wave countries. This progress should be set out clearly in implementation plans that are tracked by the Joint Committee Working Group (JCWG), with Gavi governance mechanisms effectively used to address bottlenecks.	Gavi has been fully involved in the JCWG process which has engaged in a series of deep dives into the three programmatic workstreams: malaria, health systems strengthening, and country engagement to carry the collaboration forward. Each one has identified progress to date, examples of effective collaboration, and both short- and long-term options for future action for JCWG views. These have included activities that can be operationalised by the secretariats or countries themselves with GHI support, and those related to GHI operating models that in many cases would need the involvement of governance bodies. Malaria and HSS short-term actions are underway. / All five wave 1 countries have identified their 3-4 priority areas for action, the majority of which are HSS-related, with several countries mentioning supply chain strengthening, Human Resources for Health (HRH) and Portfolio Financial Management (PFM). Work is now underway to address these and Gavi remains engaged in WHO’s work on HSS metrics which is now at the stage of being piloted in selected countries. / The new Health Systems Strategy more clearly positions Gavi’s health systems investments as designed to strengthen PHC and integrate with other PHC programmes. It also highlights strengthening alignment with other institutions in support of national priorities and plans as one of five key shifts. This will build on areas where collaboration is already more advanced, including joint efforts through the Africa Frontline First initiative to align investments in the community health workforce, and partnership on healthcare waste management. / Two proposals have been shared with the Global Fund to facilitate increased collaboration; a joint statement of intent to take forward collaboration together with GFF, and a joint letter to country teams identifying HSS areas where increased collaboration is expected.

Output Title	Output 3: Improve sustainability of immunisation programmes
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of Gavi57 countries meeting their co-financing obligations	100%	Met: 100%
3.2 Number of former-Gavi countries that maintain or increase DTP3 coverage relative to transition year	No decline (9 countries)	Exceeded: No decline (10 countries)
3.3 Countries on track for successful transition	55%	Not met: 36%

Briefly describe the output’s activities and provide supporting narrative for the score

Output 3.1: Met. Gavi-supported countries continued to meet their co-financing obligations, despite competing priorities, macro-economic challenges, and expanded vaccine portfolios. In 2024, countries contributed a record US$ 255 million in co-financing, bringing total co-financing contributions to US$ 1.96 billion since 2008. Co-financing mobilised by countries in 2024 represents a 19% increase from 2023 and a 57% increase from 2022. With growing vaccine portfolios, and the rising share of vaccine costs in preparatory and accelerated transition countries, co-financing is on a marked upward trajectory. Despite the growing co-financing obligations, countries have demonstrated their commitment to financing immunisation by making their contributions on a timelier basis compared to previous years. Excluding six countries that have benefited from a co-financing waiver due to humanitarian crises[17], all countries have fully met their cofinancing obligations for 2024. Domestic resources provide the majority of country co-financing, reaching 84% in 2024. The remaining 16% of co-financing paid in 2024 leveraged World Bank concessional lending, which is an increase over the average share of co-financing paid through World Bank loans of 11% the previous six years (2019-2024). The role of World Bank (WB) concessional lending has been particularly significant for countries in Accelerated Transition (AT) in 2024 who received 94% of all these loans. Grant funding in 2024 remains minimal, at less than 1% of total co-financing.
[17] Sudan, Somalia, South Sudan, Afghanistan, Syria and Yemen

Output 3.2: Exceeded. Taking the most recent two-year period, this indicator captures former-Gavi countries in which DTP3 coverage has remained constant or increased in at least one year compared to coverage in 2019. Of the 17 former Gavi-eligible countries included in this indicator[18] that are eligible to receive support under the Middle-Income Countries (MICs) Approach to prevent and mitigate immunisation coverage backsliding, 10 maintained or increased their DTP3 coverage in 2024 or 2023 when compared with 2019. Among the countries that were not able to sustain their DTP3 coverage, Azerbaijan (-23pp), Bolivia (-16pp), and Honduras (-13pp) are notable for having large decreases in their 2024 coverage relative to 2019. Gavi is supporting Bolivia, Honduras, Angola, Indonesia, and Viet Nam to prevent backsliding. For example in Bolivia Gavi provided targeted technical assistance to mobilise local government funding for operational support and transfer good practice from stringer regions to weaker ones. In Honduras co-investment with the World Bank’s RESHAPE programme is supporting cold chain and data management improvements. Angola has improved due to a focus on avoiding stock-outs of vaccines using UNICEF’s Vaccine Independence Initiative (VII) scheme. Countries share best practice through Gavi’s peer learning platform supported by Gavi’s MICs approach.
[18] Former-Gavi countries defined by the Board as part of the MICs Approach in December 2020, including Angola, Armenia, Azerbaijan, Bolivia, Bhutan, Cuba, Georgia, Guyana, Honduras, Indonesia, Kiribati, Sri Lanka, Republic of Moldova, Mongolia, Timor-Leste, Ukraine, and Viet Nam

Output 3.3: Not met. This indicator covers countries in the accelerated transition phase and signals whether they are on track for a “successful transition” by measuring: (1) whether they met their most recent co-financing obligation and (2) their ability to reach and maintain high immunisation coverage. In 2024, all accelerated transition countries met their co-financing obligations, with four out of these eleven countries (36%) able to maintain their DTP1 and DTP3 coverage at or above the thresholds set for this indicator (90% for DTP1, and 85% for DTP3). Among the seven countries that did not meet the immunisation coverage requirements set for this indicator, two saw improvements in DTP1 and DTP3 coverage in 2024 (Djibouti, Papua New Guinea), three saw no change between DTP1 and DTP3 coverage (Congo, Rep., Nigeria, São Tomé), one had no change in DTP1 coverage but saw a decline in DTP3 coverage (Lao PDR), and one country’s coverage declined (Côte d’Ivoire). It should be noted that the countries included in this indicator change over time due to changes in country eligibility for Gavi support. For 2024, Congo Rep., transitioned from the preparatory to the accelerated transition phase, thereby increasing the total number of accelerated transition countries in 2024 by one additional country[19]. Whilst not specific just to AT countries; Gavi has provided joint financing alongside the World Bank in 12 countries so far across 4.0 and 5.1 with a volume of around $3.2bn in total. Success remains highly dependent on Bank Task Team Leaders and SCMs in country - selection of the projects so far has been opportunistic. The new MDB multiplier initiative announced in 2025 for Gavi 6.0 aims to provide a strengthened strategic framework for this engagement.
[19] Countries in Gavi’s accelerated transition phase in 2024 include: Bangladesh, Congo (Rep.), Côte d’Ivoire, Djibouti, Ghana, Kenya, Lao PDR, Nigeria, Papua New Guinea, São Tomé, Solomon Islands

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations 2023	Progress in 2024
Recommendation 8: Gavi to work with other GHIs – in particular Global Fund - to ensure co-financing and transition policies are coherent and practical for countries. Essential that Development Banks (especially World Bank) are part of this process to ensure that grant and concessional loan financing – as well as technical engagement in Public Financial Management and Domestic Resource Mobilisation efforts- supports the pathway to transition from Gavi/GHI support, and that countries transitioning from Gavi/GHI support have access to lending to sustain their transition.	There is close and regular engagement with the Global Fund’s Health Finance Department to ensure coherence between our co-financing and transition approaches and share lessons learned from engagement and implementation at country level. The preparation of options for country joint financing for CCEOP investments in 6.0 provides a recent example, as options were informed by experience shared by the Global Fund in mobilising domestic resources for health systems strengthening activities, while Gavi shared its experience in co-financing commodities (vaccines). / Over the last 5 years (2019-2024), concessional lending from the World Bank accounted for 11% of co-financing paid by countries, and 16% in 2024. Most of the concessional loan financing from the World Bank supports the pathway to transition: in 2024, 75% of countries benefiting from WB loans for co-financing payments were in accelerated transition, and countries in accelerated transition represented 94% of the total concessional lending (USD 42.6 million) provided by the World Bank for procurement of Gavi-supported vaccines. / In addition, in 2024 Gavi continued expanding collaboration with MDBs to include the Asian Development Bank and the Asian Infrastructure Investment Bank. Together, we are working to expand the financing available to Gavi-supported countries for immunisation in support of their transition. As part of this collaboration, we are exploring the use of innovative financing instruments to strengthen and sustain immunisation investments.
Recommendation 9: Gavi and Alliance Partners to work with national governments, where relevant to support sub-national governments in developing robust sustainability/transition plans that include credible accountability mechanisms to monitor progress.	Gavi and Alliance Partners are actively engaging countries in transition to work on transition roadmaps that aim to provide a clear pathway for successful transition, laying out both domestic financing requirements and key activities to increase or sustain coverage, building on clear metrics. In July 2024, nine countries – Benin, Congo, Côte d’Ivoire, Djibouti, Ghana, Mauritania, Nigeria, Sao Tome and Principe and Senegal – signed the Abidjan Declaration where countries commit to a future where the costs of immunisation will be borne entirely out of their own budgets, while also agreeing on regularly monitoring progress. In October 2024, countries followed up on their commitments and met again at technical level to review progress and agree on specific actions to strengthen transition preparedness. Co-financing for countries in accelerated transition increased by 29% in 2024, from $101 million in 2023 to $131 million in 2024, and 100% of countries approaching transition out of Gavi support met their co-financing obligations. Engagement at sub-national level on sustainability is not restricted to countries in transition and mostly focuses on improving programmatic performance and domestic financing of operational activities. In DR Congo, which is in the initial self-financing phase, building on the experience of the Gates Foundation, MoUs are being prepared with three provinces with the objective to mobilise additional domestic resources and establish specific milestones, with clear monitoring mechanisms including both political and technical leadership at provincial level.

Output Title	Output 4: Ensure healthy markets for vaccines and related products
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Yes, revised downwards by 5pp to accommodate new AVMA output

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of markets exhibiting acceptable supply dynamics	10	Met: 10
4.2 Number of innovative products within the pipeline with commercial-scale manufacturers	Progressive trend towards 2025 target of 8	Exceeded: 12
4.3 Number of vaccine and immunisation-related products with improved characteristics	Progressive trend towards 2025 target of 9	Met: 6 / Compared to 3 in 2023

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4.1: Met: In 2024, the number of vaccine markets assessed as exhibiting Acceptable levels of health (as measured using the Healthy Markets Framework – HMF) was maintained at ten. The vaccine markets with unacceptable levels of health were rotavirus, malaria, human papillomavirus (HPV), and oral cholera (OCV). Despite market health challenges, targeted interventions helped mitigate supply disruptions: rotavirus supply outlook improved through supplier capacity scale-up and transition to a more programmatically favourable presentation; malaria vaccine access improved with early prequalification of R21/Matrix-M and expanded RTS,S production; HPV supply shortfalls were offset by higher than expected supply availability and by the WHO endorsement of single dose use for a HPV2 vaccine; and oral cholera supply rose 35%, yet unmet demand persisted due to outbreak surges. Ebola was an additional Gavi-supported vaccine market with an acceptable level of market health in 2024 but was not formally included in output indicator 4.1.
Output 4.2: Exceeded: Metrics for MicroArray Patches (MAP) and controlled temperature chain (CTC) have exceeded targets for Gavi 5.0/5.1. With an additional vaccine MAP trial for pandemic influenza, the total of vaccine MAP candidates in clinical development and relevant for low- and middle-income countries (LMICs) increased to nine. A multivalent meningococcal conjugate vaccine (MMCV) received WHO prequalification for CTC use, for storage outside of the cold chain for up to 15 days, bringing the total of CTC-certified vaccines to three. Significant progress was made for measles rubella MAPs (MR-MAPs), the most advanced MAP for LMICs. Following positive Phase 1/2 study results, demonstrating proof-of-concept safety and efficacy in infants, a Phase 3 clinical trial is now under preparation, opening a pathway to initial licensure by the end of the Gavi 6.0 period. Another Phase 2 trial for the same MAP platform is planned to investigate a shorter skin-wear time. Several “next-generation” vaccines potentially suitable for already Gavi-supported programmes are expected to be prequalified during 6.0, offering higher valencies, alternative delivery technologies or novel antigen combinations.

Output 4.3: Met: 2024 progress against indicator 4.3 is tracking at six products with improved characteristics procured, against a 2024 cumulative target of seven. The three newly procured products in 2024 were a Cold Chain Equipment Optimisation Platform (CCEOP) refrigerator with upgraded integrated remote temperature monitoring systems, a rotavirus vaccine presentation in blow-fill seal (BFS) offering a programmatic improvement from the current plastic tube presentation[20], and a CTC-certified MMCV. While a new hexavalent product received WHO prequalification in 2024, country switch applications did not materialise as expected, so initial procurement is expected in 2025. The indicator is expected to reach the 5.0/5.1 target of nine, with the recently prequalified class of actively powered vaccine carriers and 2nd generation freeze-preventive vaccine carriers.
[20] While the rotavirus vaccine BFS presentation was first introduced in three Gavi countries in 2019, its production was halted shortly after. The renewed availability of this presentation was made possible following a strategic decision by the manufacturer to scale up its production.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations 2023	Progress in 2024
Recommendation 10: Gavi to utilise fora such as the Developing Country Vaccine Manufacturers Network annual general meeting, UNICEF annual Vaccine Industry Consultation and AVMA’s Manufacturing Forum to engage with regional manufacturing initiatives across the ecosystem, to reduce duplication, share learning and increase collaboration.	The 2nd Vaccine and other Health products Manufacturing Forum (Cairo February 2025), held in partnership with Africa CDC, with an additional pre-event day focusing on manufacturer and donor engagement – hosted by Gavi – demonstrated Gavi’s contribution to effective ecosystem engagement. The forum was characterised as dynamic, well-attended, and substantively rich, positioning AVMA as a catalytic mechanism within the broader ecosystem of manufacturing and regulatory support initiatives. Manufacturer engagement was substantial, with tailored sessions on regulatory, financing and other priorities, helping improve alignment across stakeholders. Encouraging signs emerged around regional coordination efforts, particularly through the growing involvement of Regional Economic Communities, North African partners, and new Regional Centres of Regulatory Excellence. / In addition to planned participation in platforms such as the DCVMN Annual General Meeting, UNICEF’s Vaccine Industry Consultation, and AVMA’s Manufacturing Forum, during 2024 Gavi has also participated in strategic discussions at the Global Health Market Shaping Conference in Barcelona and the WHO Local Production Forum in Abu Dhabi, strengthening alignment between regional manufacturing initiatives and global market health sustainability, while promoting collaboration and shared learning across the ecosystem. / The UNICEF VIC is scheduled for September, when a substantial Gavi delegation will hold the customary deep dives with the entire vaccine supplier base, both current and future suppliers. In addition, a joint Gavi-UNICEF side session is planned to update manufacturers on the operationalisation of AVMA, including the AVMA eligibility application process and UNICEF’s role in managing milestone incentives and tender procedures related to accelerator payments. / The DCVMN Annual General Meeting for 2025 is scheduled in October, when Gavi will be participating in a panel discussion on Building a Resilient Vaccine Ecosystem in Africa: Demand Generation, Unified Procurement and Sustainable Pricing.

Output Title	Output 5: Organisational effectiveness (internal)
Output number:		5	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Operating expense ratio: Operating expenses (total Secretariat costs, evaluations & assessments as a percentage of total expenditures / Overhead ratio: Overheads (Management, general & fundraising and IFFIm & Gavi campaign) as a percentage of total expenditures	<7.5% / <3%	Exceeded: / 6.84% / 2.81%
5.2 Resources disbursed as planned according to Board-approved forecasts	24.9% (annual)	Not met: 23.9%
5.3 Gavi's centralised evaluations on track as per approved work plan	On track (4 evaluations planned)	Met. Progress on track.
5.4 Staff attrition	<19%	Exceeded: 5.5%
5.5 Average time to hire	<4.5 months (approx. 99 working days)	Exceeded: 93 days

Briefly describe the output’s activities and provide supporting narrative for the score.

Gavi moderately exceeded expectations across outputs related to organisational effectiveness in 2024, surpassing targets in three areas. The organisation is currently implementing significant structural changes, which are expected to continue through 2025. While progress on key indicators has been positive, challenges emerged with the EVOLVE grant management reform programme. Performance issues with the initial vendor led to an external review, after which the EVOLVE programme was sunset and grant management reform efforts integrated into Gavi Leap.

Output 5.1: Exceeded. Operating expenses as a percentage of total expenditures was 6.84% (calculated on a statutory basis according to Generally Accepted Accounting Principles (GAAP)), exceeding the target of less than 7.5%. Operating expenses were $207m, $14m (7%) higher than the prior year (with Gavi Core and the COVAX Facility combined) but under budget. 2024 saw an increase due to an increase in Secretariat support needed to ensure delivery of 5.1 objectives as we approach the end of the strategic period, as well as greater investment in transformation and change initiatives. Total expenditures (the denominator, calculated on a statutory accrual basis with Gavi Core and COVAX combined) were $3,025m with the high level of programmatic disbursements resulting in the Opex ratio exceeding the target. Overheads as a percentage of total expenditures were 2.81% (again calculated on a statutory accrual basis). Overheads were $85m, $7m higher than the prior year, mainly driven by transformation and change initiatives in 2024 such as FaB (Forecast and Budget), Vendor Management and DAX (“Data Exchange” automation and integration between Gavi and UNICEF systems).

Output 5.2: Not met. Resources disbursed in 2024 were $3,122m. After excluding $582m of repurposed COVAX AMC interest and contributions, $2,539m representing 23.9% of core resources planned to be disbursed according to Board approved forecasts with strong vaccine disbursements representing 97% of the forecast supporting routine programmes and Gavi 5.1 must wins (HPV & Malaria). 2024 saw greater focus and review of in-country cash balances ahead of HSS disbursements to ensure efficient use of resources. In the event that sufficient cash balances were already sitting in-country to cover spending requirements, disbursements were deferred and, as a result, cash programme disbursements were lower than anticipated. Whilst this indicator is assessed as objectively “not met” Gavi are right to hold back disbursement of new funds until existing cash balances sitting in country have been effectively utilised.

Output 5.3: Met. Progress on 4 planned evaluations in 2024 was on track.
Evaluation of Gavi’s contribution to reaching zero-dose children and missed communities Phase 1: Published in June 2024. The evaluation contributed to strategic and programmatic decision-making for Gavi 5.0/5.1 and development of Gavi 6.0.
Evaluation of Gavi’s contribution to reaching zero-dose children and missed communities Phase 2: Progress on track with implementation underway in 2024. The purpose of this evaluation is to generate strategic lessons learned on the implementation of the ZD agenda to inform course correction, development and operationalisation of the Gavi 6.0 strategy, including on: Operationalising Gavi 5.0/5.1 grants for preventing ZD children; the role of partners in the implementation of the ZD agenda; to provide lessons on how the Gavi 5.0/5.1 Strategy zero-dose agenda has promoted an integrated approach to investing in primary health care (PHC); to inform the operationalisation of ZIP in Gavi 6.0 and to better understand the role of Advocacy in delivering the Zero Dose agenda.
Mid-term Evaluation of Gavi 5.0 (MTE): Published in June 2024. This supported course correction in Gavi 5.1. and informed the development of Gavi 6.0 (2026-2030).

The COVAX Phase 2/endline study: Progress on track with publication planned in Q3 2025. This is the first joint evaluation commissioned by the Gavi Alliance founding partners and CEPI. Learnings from this work are intended to help inform Gavi 6.0 operationalisation, including PPPR / GHS, and generate insights for strengthening Alliance partnership – particularly in the context of the recent adoption of the WHO Pandemic Agreement by the World Health Assembly and ongoing work of the interim Medical Countermeasures Network.
Across 2024 Gavi have also been considering MOPAN recommendations on evaluations, which included developing a holistic approach to evaluation, expanding dissemination of learning, addressing cross-cutting issues, and better linking centralised and decentralised evaluations. A deeper dive on this assessment has been paused while the joint Gavi-Global Fund task team is established, which will look at how they can collaborate on monitoring and evaluations as part of its remit.
Output 5.4: Exceeded. Gavi has exceeded its voluntary attrition target of below 19%, achieving a result of 5.5% in 2024. This marks a return to Gavi’s typical stability following the temporary spike in 2023 linked to the COVAX close-out. Gavi have instigated a number of culture and wellbeing initiatives in 2024 and will be running a follow up people survey in 2026 (the second after their 2023 survey) to measure the effect of these, and the restructuring on staff engagement.

Output 5.5: Exceeded. While organisational review phases connected to Gavi’s recruitment activity had an impact on the overall time to hire (in comparison to 2023), Gavi succeeded in maintaining an average time to hire of 93 working days, outperforming the target of <4.5 months (~99 days). This steady pace of outperforming targets reflects the stabilisation of the recruitment team and early gains from process enhancements which were launched in 2023.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations 2023	Progress to date
Recommendation 11: Gavi to drive efficiencies in the Secretariat Operating Budget throughout 2024 and 2025 at the level endorsed by the AFC and Board, in order to ensure a smooth transition into the 6.0 period.	Under the guidance of the AFC, Gavi is currently conducting an Organisational Review aimed at driving efficiencies in the 6.0 Secretariat Operating Budget to ensure Operating Expenditure and Secretariat resources are in line with the Board approved strategy. In 2025, Gavi will continue to implement the outcome of the Organisational Review to ensure it is fit for purpose in Gavi 6.0.

Output Title	Output 6: Programmatic delivery effectiveness
Output number:		6	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
6.1 Audits on track against AFC-approved plans (both internal and programme) at 80% overall target delivery.	80% target delivery of approved plan: / Internal: 7 / Programme: 15	Exceeded: 109% delivery of approved plan: / Internal: 9 / Programme: 15
6.2 % top risks in the Board-approved Risk & Assurance Report that are within risk appetite	80%	Met: 80%
6.3 % of implementing partner agreement templates that include PSEAH clauses	100%	Met: 100% / All partner service agreements and grants agreement have included PSEAH
6.4 Average time between approval and disbursement of programme support	9 months	Exceeded: 7.9 months
6.5 Proportion of funds going through government systems	Progressive trend towards cumulative 55% by 2025	Met: 55%

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6.1: Exceeded. Gavi’s programme and internal audit teams have completed all audits in the AFC-approved 2024 workplan, including a greater number of Secretariat audits than originally foreseen as discussed with the AFC during the year. This indicator is regularly updated and reported to the AFC. Recognising that audits frequently straddle year-ends it represents completed audits from the 2024 annual workplan at the time of reporting. The audit plan is a living plan and is adjusted in liaison with the AFC throughout the year in response to changing contexts and emerging risks. In October 2024, Gavi’s Audit and Investigations (A&I) functions underwent an External Quality Assessment; such an independent external assessment is a requirement of the Institute of Internal Auditors and needs to be carried out at least every five years.  The external assessors, the French Institute of Internal Auditors, presented their report to the Gavi Audit and Finance Committee in February 2025, concluding that the audit functions already conform to the new Global Internal Audit Standards which came into force in 2025. As of the last AFC report in October 2025, overdue open actions for secretariat (internal) audits were at 8% at 28 February 2025, meeting the target of 10% or less, an improvement from 15% as of 30 September 2024. This improvement has continued; A&I is currently preparing an update for the next AFC meeting, where overdue actions stand at 5% as at 31 August 2025. However, overdue open country audit recommendations rose from 37% as at 30 September 2024 to 43% as at 31 March 2025, in that period remaining above the target of 30% or less. This has recently improved; A&I is currently preparing an update for the next AFC meeting, where overdue country audit recommendations stand at 24% as at 30 September 2025, within the target. The reimbursement rate rose to 99% from 96% in 2024, reflecting Gavi's zero tolerance for fund misuse. However, staffing levels across audit areas including secretariat and country audits has decreased for 2025 due to the reduction in secretariat to adjust to this change Gavi will maintain the focus on completing the audit work plan just over a longer timeframe. To manage costs and maintain audit coverage, Gavi has increasingly used consultants, supervised by Geneva-based teams.

Output 6.2: Met. The 2024 Annual Risk and Assurance Report details 10 top risks, i.e. risks that could potentially have an impact on the ability of the Alliance to achieve its mission and deliver on its strategic goals. The report also highlights 10 other relevant risks to be monitored. It shows that Gavi’s overall risk profile has slightly improved with four top risks decreasing (Country management capacity, Sustainable transition and backsliding risk, Misuse and suboptimal absorption of funds and Impact of health systems strengthening investments) and only one risk increasing (Decrease in donor funding / 6.0 Replenishment ). Compared to 2023, Gavi’s risk landscape has evolved with the removal of four 2023 top risks and the entry of four new risks. The key drivers of the changes to Gavi’s risk profile are linked to progress in mitigating actions, current socio-economic environment, development in global health and developments within Gavi. Significant progress has been made to mitigate 2024 top risks, notably through the CEO’s 180-day plan that ensures actionable risk mitigations through priorities setting and strengthening of accountability.

Output 6.3: Met. In 2024, Gavi completed implementation of PSEAH clauses in all four of the partner agreements templates included in the original indicator (Services Agreements, grant agreements with UNICEF, grant agreements with WHO and expanded partners agreement templates). In addition to the updates to agreement template categories in the original indicator, Gavi has also integrated PSEAH clauses in all new implementing partner agreement templates for 2024 covering additional UN agencies (PAHO and UNOPS) and CSOs that are contracted through the outsourced fund manager. Efforts are now underway to update all legal templates with implementing partners in countries as part of 6.0 operationalisation, in order to ensure PSEAH is included in the common framework for all Gavi implementing partner agreement templates. The Board approved a new PSEAH policy and it became effective in December 24, supported by an internal intranet ‘one-stop-shop’ page on PSEAH, ongoing training and a broader speak-up campaign and ethics hotline. The Policy is aligned to CAPSEAH and requires that each year ERCO delivers against a PSEAH workplan which helps prioritise and track delivery. There is a PSEAH Leaders Group which acts as an organisation-wide sounding board, where leaders can discuss concepts, implementation issues and present wider work (e.g. they reviewed the key messages from the Wilton Park event on PSEAH Resourcing). Collaboration with The Global Fund, WHO and wider UN (particularly in country) remains a priority. The team are monitoring the impact of ODA cuts on delivery partners and will continue to monitor whether this affects ability to manage PSEAH risks. Efforts are currently underway to standardise and simplify contract language to facilitate improved system integration. Monitoring mechanisms include the tracking of case referrals and partner queries, which have appropriately increased as the process matures. Training and capacity-building initiatives at the country level are expanding, and alignment with UN partners continues to strengthen through collaborative forums such as the Alliance Risk and Advisory Group.

Output 6.4: Exceeded. As the Gavi 5.0/5.1 Strategic Period (2021-2025) approaches its conclusion, Gavi has achieved an average duration of 7.9 months between programme approval and first disbursements in 2024. This represents a 2-month reduction, which is a 20% improvement from the baseline of 9.9 months recorded in 2021. Progress over the strategic period includes an average of 8.9 months in 2022, a significant improvement to 7.3 months in 2023, followed by a slight increase to 7.9 months in 2024. Importantly, this performance exceeds the milestone target of 9 months. The slight increase in 2024 can be attributed to a surge in first disbursements by September 2024, which raised the average time to 7.7 months. This coincided with a shift from quarterly to monthly routine monitoring, enabling more frequent reporting and systematic flagging of applications at risk of exceeding the nine-month target. This enhanced cadence reinforced accountability and facilitated timely remedial actions. Another key factor was the 43% increase in the number of first disbursements, rising from 146 (as of 2023 FCDO reporting) to 209 (as of 2024 FCDO reporting). Qualitative factors also influenced timelines, including country-level decisions to postpone launches or campaigns due to budgetary adjustments or delayed vaccine shipments, or the presence of existing in-country cash balances that led teams to defer disbursements. Despite the challenges, cross-country collaboration with the Gavi Secretariat has maintained momentum. Country teams use past lessons for ongoing improvement. With coordinated efforts and Director-level meetings, Gavi provides timely support to help countries advance immunisation and strengthen health systems.

Output 6.5: Met. At the end of Q4 2024, 55% percent of the US$ 1.3 billion disbursed cumulatively since the beginning of the strategic period has been disbursed directly to governments. With 39 countries using country systems representing 67% of the 58[21] under the strategic period, and one more country (Bangladesh) preparing to transition in 2025, it is expected that the target will be exceeded by the end of 2025. As this indicator is monitored through Gavi's governance mechanisms it will be reported to the board. Below is the breakdown of all 58 countries and their categorisation.
[21] Syria is considered one country but represented as two in this count.
Gavi has notably improved its use of country systems, especially nationally. Focus is now shifting to strengthening systems and assurance at the subnational level. Assurance Providers (APs) are active in 48 countries, though some do not require them, prompting a revision of the Terms of Reference.

Key drivers supporting countries to meet the target:

- Technical Assistance provided through the Financial Management Risk Assurance (FMRA) envelope to continue to support the majority of the 39 Gavi-supported countries (including 13 which recently progressed) using country systems. This includes focusing on broader strategic initiatives such as strengthening the Supreme Audit Institutions and Accountancy Profession for Health. These investments helped to strengthen Public Financial Management (PFM) in Gavi-supported countries, by validating and reinforcing the national assurance agencies’ capabilities with regards to accountability and transparency over how donor funds (including Gavi’s) are used by the Government. These efforts also contribute to ensuring that Gavi is aligned with regards valuing national oversight activities, consistent with the Lusaka Agenda across GHIs.
- 48 assurance providers (APs) were contracted by Gavi to mitigate fiduciary risks and prevent backsliding in line with Gavi’s objective of enhancing “Strategic Engagement with Assurance Providers”. The APs have a broader scope of work than in the past, providing direct support to Gavi countries with end-to-end financial management. Assurance providers are not present in every country. The decision to deploy APs is strategic and risk-based, meaning they are prioritised for countries where fiduciary risk is higher or where systems require additional support to ensure proper use of funds.
- Continued investments in capacity building (systems, people and processes) across select countries are expected to increase more direct disbursements through country systems in 2025 and ensure that all 7 elements of the PFM model are included in this indicator. These elements are: inclusion of Gavi support as part of government budgets; funding through a treasury account at three levels (Treasury, Treasury/Ministry of Health, Treasury/MoH at subnational levels); funds held on account managed by a government ministry outside Treasury, funding accounted for within the government’s main accounting systems, Gavi funds covered by government audit procedures, government employees leading financial management of Gavi funds and procurement managed by government.
- Reduction in the aging of cash balances is expected to continue, thus demonstrating improved implementation and subsequent increase in direct disbursement. In 2024, coordinated efforts by both the Secretariat and countries to catch up on delayed activities led to a significant reduction in older cash balances. It is noteworthy that Cash Balance Age decreased in 2024, driven by the cash absorption capacity initiative. As COVID-19 grants sunset and are repurposed, these aging cash balances will continue to decrease​. Steady progress – in line with the CEO 180-day plan to lower the average age of cash balances to under 9 months – is being achieved by:
  - Improved forecasts taking into account countries’ ability to absorb.
  - Execution at pace of action plans for countries where challenges are anticipated.
  - Staggered disbursements based on performance.
  - Focus on grant closure.
  - Regular reporting enabling better management of grants.
  - UNICEF/WHO providing quarterly reports with capacity building efforts at country level to do their own reporting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations 2023	Progress in 2024
Recommendation 12: Gavi to fully implement the Protection from Sexual Exploitation, Abuse and Harassment (PSEAH) Audit recommendations and PSEAH framework specifically on due diligence and capacity building with implementing partners at country level - using a risk-based approach to allow for optimal use of resources and prioritisation (e.g. by prioritising the highest risk contexts). Gavi to provide updates for any issues or delays in implementation to the Governance Committee.	Gavi continues to operationalise its Protection from Sexual Exploitation, Abuse and Harassment (PSEAH) Policy by developing and formalising due diligence and capacity building measures across supplier and implementing partner engagement, particularly for civil society organisations (CSOs), using a risk-based approach to optimise resource allocation and prioritisation. / The Supplier Due Diligence Standard Operating Procedure (SOP) and related tools have been finalised and approved by management. / A revised High-Risk Supplier Questionnaire has been developed and finalised for use, for high-risk suppliers, including CSOs. It includes targeted PSEAH safeguards, requiring CSOs to confirm the existence of safeguarding policies and mandatory staff training (Sections C1 and C1a), background checks (D1), and whistleblowing policies that explicitly include PSEAH issues (Section F). / Risk-based triggers guide the application of enhanced requirements—for example, subcontracting due diligence, safeguarding training, and mapped delivery chains are prioritised for CSOs in high-risk contexts. / The new questionnaire structure introduces clear “YES–NO–N/A” formats for faster assessment and scoring, enabling more consistent application of due diligence across country programs and supplier types. / The finalised due diligence tools have been uploaded to the iRisk risk management module, where all partner assessments will be conducted and logged. Gavi is committed to providing timely updates to the Governance Committee in the event of any delays or challenges in full implementation and will continue working with country teams to ensure high-risk contexts are prioritised for PSEAH capacity-building support. / Lastly, Gavi will provide an update on the recommendations for PSEAH audit actions.
Recommendation 13: Gavi to collaborate with other Geneva based organisations to strengthen approaches on PSEAH (e.g. World Health Organisation on engagement with health ministries and United Nations High Commissioner for Refugees (UNHCR) who have developed strong victim-centred support processes).	Gavi continues to expand collaboration with Geneva-based partners to enhance PSEAH strategies. Recent engagements include: / Discussions with WHO on PSEAH principles and their focal points framework in countries. / High-level dialogue with UNICEF at GHC on risk & compliance activities. / Partnership with the Global Fund to leverage training experience and explore joint awareness initiatives. / The Alliance Risk and Advisory Group quarterly meetings with representation from UNICEF, WHO, the World Bank where multiple risks are discussed and shared. / Given the reduction in funding throughout the GHIs Gavi’s central PSEAH expertise remains intact, however partner capacity is at risk, and activities may need to be reprioritised. / The Alliance Risk and Advisory Group, is monitoring absorption capacity and considers PSEAH a top risk for the group.
Recommendation 14: Gavi to sharpen the focus on cash balances in country. Utilisation should not be the only focus. Gavi should design, and implement, policies to periodically reassess the need for cash support with a view to reallocating cash support to countries and/or areas of greatest need.	Gavi is working to sharpen the disbursement policy at the Secretariat with a view to reducing the level of idle and aged cash in-country. This includes adjusting each country’s initial funding allocation to what can reasonably be absorbed. Gavi is also working on policies to (a) promptly recover funds once grants are ended, (b) review mid-cycle each country’s disbursement needs, and (c) determines how any savings may be re-allocated to areas of greatest need across the portfolio. / To address the possibility of currency depreciation as a result of grant currency conversion to local currency as well as the risk of local banks being nationalised or becoming insolvent, engagement with key stakeholders both at the Secretariat and at the country level will be initiated to explore the feasibility of policy on cash management which may include interest-bearing accounts as a grant requirement or validation of local bank rating. Gavi is working to strengthen existing policies on cash disbursements to include requirements for quarterly cash balance, monitoring of grant cash absorption and grant cash forecast. Together with the Treasury team and key country stakeholders, a cash management guide is under development to provide guidance to countries on management of grant currency conversion, banking risk and short-term cash investments.

Output Title	Output 7: AVMA
Output number:		7	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
7.1 AVMA formally launched	Yes	Met: AVMA was formally launched at the June 2024 event in Paris
7.2 AVMA eligible manufacturers who formally engaged with Gavi on AVMA	1	Met: 1
7.3 AVMA Governance processes completed	1	Met: AVMA’s governance was fully established in 2024

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 7.1: Met: The African Vaccine Manufacturing Accelerator (AVMA) was formally launched on 20 June 2024 at a high-level event co-convened by the African Union, the Government of France, and Gavi at the Élysée Palace in Paris. The launch followed nearly two years of collaborative design with Africa Centres for Disease Control & Prevention (Africa CDC) and other stakeholders and secured US $1.2 billion in pledges from 13 governments and organisations. At launch, AVMA’s Expressions of Interest process was opened to manufacturers, its dedicated website was activated, and implementation arrangements with UNICEF were advanced to integrate AVMA’s milestone and accelerator payments into existing tender and contracting processes. The launch positioned AVMA as a central pillar of Gavi’s Regional Manufacturing Strategy, aimed at both building a sustainable African manufacturing base and improving pandemic and outbreak vaccine supply resilience.

Output 7.2: Met: In 2024, one AVMA-eligible manufacturer formally engaged with Gavi through the Expressions of Interest process, initiating structured discussions on WHO prequalification readiness, manufacturing control criteria, and operational requirements to access milestone and accelerator payments. This early engagement served as a practical test case for AVMA’s operational pathways and informed refinements to manufacturer guidance and the application process. Gavi also maintained regular strategic engagement with Africa CDC in the lead-up to the June 2024 launch, and subsequently in joint planning for the February 2025 AVMA Manufacturing Forum, ensuring alignment between AVMA’s operational roll-out and the African Union’s broader local production agenda. Targeted outreach to African manufacturers and financing partners included several update calls with African vaccine manufacturers via the African Vaccine Manufacturing Initiative (AVMI), which provided detailed information on AVMA’s operationalisation, application timelines, and integration with UNICEF tendering processes. Gavi also played a leading role in multiple high-profile convenings to position AVMA within the broader manufacturing and investment ecosystem:

- Strategic Roundtable on Strengthening Local Production in Africa and launch of AVMA (21 June 2024, co-hosted with the World Bank Group and Africa CDC): This ministerial-level dialogue brought together MDBs, DFIs, suppliers, and partners to identify complementary investments, enabling environments, and regulatory harmonisation needed to ensure AVMA’s long-term success. Recommendations included expanding sustainable financing options, widening market access for African producers, investing in agile manufacturing capacity, and strengthening workforce skills and demand aggregation mechanisms.
- 2nd Edition of the Global Event on Harnessing Private Sector Engagement for Sustainable Vaccine and Pharmaceutical Manufacturing in Africa (25–26 June 2024, Nairobi): Gavi provided detailed briefings to industry and DFIs on AVMA’s design, eligibility criteria, and funding pathways, highlighting opportunities for private sector and investor participation in commercially viable African vaccine manufacturing.

These combined engagements supported AVMA’s market signalling objectives, built early interest among potential applicants, and reinforced alignment with Africa’s broader local production, financing, and regulatory strengthening agenda.

Output 7.3: Met: AVMA’s governance structures were fully established in 2024. The inaugural AVMA Investors Forum was held on 18 September 2024 with participation from all major donor partners. The Forum finalised its Terms of Reference, agreed procedural elements such as Chair nomination and tenure, and initiated structured discussions on treasury management options, use of interest income, and priority vaccine designation processes. In parallel, the African Vaccine Manufacturing Forum was confirmed as an annual co-convened platform with Africa CDC, forming the broader stakeholder advisory mechanism for AVMA. Together, these governance arrangements now provide the framework for oversight, strategic input, and stakeholder engagement throughout AVMA’s ten-year lifespan, including the triennial course-correction reviews (first scheduled for 2027). As part of Gavi’s overall approach to risk management, the PPC and Board considered AVMA risk reporting in 2024, reviewing identified risks, mitigations, and governance controls to ensure that AVMA’s design and early implementation remain consistent with Alliance-wide risk tolerance and fiduciary standards.

## D: VALUE FOR MONEY

Gavi continues to deliver value for money in challenging circumstances.

Gavi’s total expenditure for 2024 (on a disbursement basis, including Board approved programmes funded by COVAX AMC repurposed funds) was US$ 3,121 million, of which operating expenditures were US$ 202 million (6.5%) and programme expenditure was US$ 2,919 million. From an economy perspective, this demonstrates that its Secretariat continues to deliver programmes with low overheads.

Gavi’s cost drivers include expenditure on new and underused vaccines (57%); health systems strengthening grants (16%); partners engagement framework (10%); other programmes costs (8%), and operating costs (on a management reporting basis) (6%).
Economy

Gavi achieves economy through its approach to market shaping, which prioritises improved market sustainability and long-term market competition. By pooling demand for vaccines from low- and middle-income countries, Gavi is able to negotiate lower prices than individual countries would otherwise have access to. Gavi's predictable funding and pooling of demand has created an incentive for the pharmaceutical industry to set up a tiered pricing policy, whereby low-income countries are charged less than higher income countries for the same product. Additionally, Gavi promotes the diversification of its vaccine supplier base, which grew from just 5 in 2001 to 20 in 2024. More than half of these manufacturers are based in low- and middle-income countries.

Stronger competitive dynamics in markets have led to a further decrease of 6% in weighted average price (WAP) per dose of Gavi’s top three vaccines by value from 2021 to 2024 after a significant decrease of nearly 60% from 2010 to 2020, translating into improved VfM. For example, the WAP for full course of vaccination with rotavirus has reduced by 79% since 2010. Greater cost savings can be achieved if Gavi-implementing countries choose to adopt a greater number of products from some of the newer market entrants with the lowest prices. Gavi has launched a workstream on healthy demand to better understand how countries optimise product choices and prioritise antigen programmes, and how these processes impact long-term market health, supplier sustainability, and resulting financial implications for countries and donors.
Efficiency

Efficiency in delivering its outputs is demonstrated by Gavi meeting or exceeding most logframe milestones, as outlined earlier in this review. Since 2000, Gavi support has contributed to more than 1.2 billion children being vaccinated through routine programmes, and more than 2.1 billion vaccinations being delivered through preventive vaccination campaigns. This has ensured that coverage of DTP3 in Gavi-supported countries reached 82%, compared to the global average of 85%. A key driver of Gavi’s efficiency is its catalytic funding model, which leverages domestic resources for immunisation. In 2024, Gavi-eligible countries mobilised US$ 255 million for co-financing towards Gavi-supported vaccines, bringing total co-financing contributions since 2008 to US$ 1.96 billion. This is set to accelerate in 6.0, with an estimated US$ 4 billion in co-financing expected from countries over the 5-year period.
Effectiveness

By supporting countries to introduce, maintain, and recover delivery of cost-effective core and novel vaccines, Gavi enables wider economic and social benefits. For example, a study covering the 73 Gavi-supported countries shows that, for every US$ 1 spent on immunisation in the 2021–2030 period, US$ 21 are saved in health care costs, lost wages and lost productivity due to illness and death[22]. In 2024 alone, this translates to US$ 19.8 billion in economic benefits being generated in Gavi-supported countries. In terms of the impact of Gavi’s support on the disease burden, the under-five mortality rate in the 57 lower-income countries supported by Gavi fell from 54.1 to 51.3 deaths per 1,000 live births between 2022 and 2023[23] – a 12% reduction from the 2019 baseline (58.6 deaths per 1,000 live births). Gavi has therefore exceeded its mission target of a 10% reduction by 2025.
[22] Sim S.Y., Watts E., Constenla D., Brenzel L., Patenaude B.N. Return On Investment From Immunization Against 10 Pathogens In 94 Low- And Middle-Income Countries, 2011–30. Health Affairs, 2020
[23] Estimates for 2024 will be available in early 2026

Equity

Gavi employs tailored approaches to each of the countries it works with, recognising that increasing vaccination uptake will require different interventions in different contexts. Gavi’s 5.1 strategy has focused in particular on reaching zero-dose children by strengthening primary healthcare systems, building community demand, addressing gender-related barriers and using innovation – with support from the UK Matching Fund – to ensure that immunisation services reach the most marginalised. With vaccination coverage overall keeping up with population growth, the number of zero-dose children fell by 500,000 in 2024.

E: RISK

Overview of risk management

Gavi aim to make risk management integral to its culture, strategic planning, decision making and resource allocation. A coordinated and structured approach allows the Alliance to proactively manage risk. Gavi’s Risk Management approach is designed to generate a holistic view of top risks for the Alliance in the context of the strategic goals and corporate priorities. It serves to better understand risk exposure by providing increased transparency on the evolution of risks (year to year) and the related effectiveness of mitigating actions. The annual Risk assessment and assurance report are intended to help the Gavi Board and senior management focus on top risks, align strategy with risk exposure and oversee the effectiveness of risk mitigation.  Risks are grouped into four dimensions: programmatic, financial, organisational and engagement with partners. Risks are rated on a five-point scale – very high, high, medium, low and very low – based on their likelihood and potential impact. A well-defined top risk selection process provides a full overview of the Gavi Alliance risks to monitor, and of emerging risks related to Gavi 6.0 strategy.

Gavi has structured its risk management and assurance functions around a best practice "three lines of defence" model. A dedicated risk team in the Ethics, Risk and Compliance Office coordinates, facilitates and monitors the implementation of effective risk management practices across the Alliance as defined in Gavi’s updated Risk Policy (2024) and its related SOPs. The Senior Leadership Team (SLT) is overall responsible for managing Gavi Secretariat Risks and systematically reviews the top risks allocated to risk owners in the organisation. Risk is a standing item on the agenda of the SLT, Gavi Board meetings, and the AFC oversees the effectiveness of risk management systems and processes. Gavi’s risk management and assurance model has matured substantially since the inception of Gavi’s new Ethics, Risk and Compliance office in 2023.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Gavi has continued to perform well across delivery, commercial and financial aspects. An updated MOPAN review of Gavi was completed in late 2024 alongside FCDO’s Central Assurance Assessment (CAA), both found that overall Gavi’s organisational effectiveness and results performance remains high, and Gavi remains fit for purpose and delivers value for money. FCDO was engaged in the consultation process. MOPAN shed light on the complexities of Gavi’s funding mechanisms and evaluation functions. As part of ongoing efforts to evolve its model, Gavi is implementing the Gavi Leap, an internal reform programme to establish new ways of working over the course of 6.0, by placing countries at the centre and simplifying operational procedures and funding.

Commercial: Gavi’s market shaping priorities have focused on improved market sustainability and long-term market competition. Further cost savings can be achieved if Gavi implementing countries choose to adopt a greater number of products from some of the newer market entrants with the lowest prices. Gavi has launched a workstream on healthy demand to better understand how countries optimise product choices and prioritise antigen programmes, and how these processes impact long-term market health, supplier sustainability, and resulting financial implications for countries and donors.

Co-financing: Another critical area of delivery is Gavi’s co-financing and transition policy. Countries contribute a proportion of vaccine costs and this increases as countries’ economies grow. In 2024, co-financing for Gavi-supported vaccines totalled US$ 255 million, bringing total co-financing contributions since 2008 to US$ 1.96 billion, of which US$ 1 billion has come from high-impact countries. Overall, as well as a 33% increase in co-financing obligations compared to the previous year, country contributions were received and in a timelier manner than before the pandemic. Gavi’s ELTRACO model is widely regarded as a success story, with 19 countries having transitioned out of Gavi support to date. In response to the evolving context marked by a challenging macro-economic outlook, increasing risks of unsuccessful transition in a subset of countries, and continuing inequities in access to immunisation in lower middle-income countries, in 2023 Gavi initiated a review of its ELTRACO model, exploring opportunities to improve its approach to building programmatic and financial sustainability of immunisation programmes in Gavi 6.0. This reviewed policy was approved by the Gavi Board in July 2024.

Financial Management: Gavi’s financial reporting procedures are in line with internationally recognised best practices, with its financial statements fully complying to the United States generally accepted accounting principles (US GAAP). Annual external audits of Gavi’s financial statements have consistently returned an unqualified opinion.

Gavi continues to strengthen its internal financial management reporting with improved performance-based reporting produced monthly, reviewed by the Senior Management Team including actions required to mitigate any performance gaps or emerging issues, and presented to the AFC on a quarterly basis. This management reporting presents the financial performance for both the year to date and strategic period to date resources, programme disbursements and operating expenditure against the latest financial forecast with explanatory commentary including programmatic drivers and country segment insight. It also provides detail on Programme Funding Policy compliance, reserve requirements and Secretariat commitments vs Board approvals, on a half-yearly basis.

In addition to the above the Office of the Chief Financial Officer, with the support of the AFC, has commenced a reporting initiative, to align reporting across actual and forecast performance periods, increase transparency and provide insightful analysis, through automated data sets and efficient self-service reporting formats. These initiatives are being implemented through 2025 (to internal and governance stakeholders).

G: MONITORING, EVIDENCE AND LEARNING

Monitoring: The effectiveness of Gavi programmes is regularly monitored via the Gavi 5.1 Measurement Framework. Most indicators in the log frame are based on the 5.1 Mission and Strategy indicators approved by the Gavi Board, which are reported to the Board biannually. For Gavi 5.1, several of these same indicators are cascaded down into the country-level monitoring of Gavi’s grants, thus ensuring coherence from country to portfolio level. Performance monitoring of country progress occurs through the APPT and Gavi programmatic teams regularly review operational and strategic progress. FCDO monitors Gavi’s performance through active participation in Gavi’s formal governance structures. This includes membership of the Gavi Board and participation in several committees including the PPC, AFC, Market Sensitive Decisions Committee and the APPT.

Gavi’s Annual Evaluation Report for 2024 gives a full list full of evaluation activities: https://www.gavi.org/sites/default/files/programmes-impact/our-impact/Gavi-Annual-Evaluation-Report-2024.pdf.

Evidence from Gavi’s strategic evaluations was used in key areas of its work in 2024:

In February 2024, a meeting with Gavi’s SLT discussed evidence from the Evaluation of Gavi’s contribution to reaching zero-dose children and missed communities Year 1 annual report and the Mid-term evaluation of Gavi’s 2021–2025 strategy (MTE) to inform the design of Gavi 6.0. Key findings included: i) Weak capacity, especially at sub- national levels, limits grant absorption for ZD programming and necessitates focused TA, which currently does not reach subnational levels sufficiently; ii) Existing monitoring and accountability mechanisms are insufficient to track partner performance and ensure transparency on ZD outcomes; iii) Coordination mechanisms exist but with varying effectiveness and iv) Implementation gaps and government capacity challenges impact their quality, particularly at the national and sub- national levels.

Following the Technical Briefing to the Gavi Board and Programme and Policy Committee (PPC) in April 2024, multiple requests from Board and PPC members were received to access the final report of the Mid-term evaluation of Gavi’s 2021–2025 strategy, given its importance in informing design and operationalisation of Gavi 6.0 and the HSIS Policy.

Emerging insights from recent evaluations (including COVAX Phase 2 and Zero Dose evaluation) were used to inform the partnership deep-dive discussions at APPT meeting in Addis Ababa in October 2024.

In December 2024, the Gavi Board approved the consolidation of seven funding levers into one consolidated cash grant, aligned with recommendations from recent centralised evaluations (Zero Dose evaluation, Strat. Ops. and MTE).

Key lessons emerging from the joint evaluation of the COVAX Facility and COVAX AMC (Gavi Secretariat) and COVAX pillar delivery efforts include: i) Strengthened partnerships: the joint evaluation process deepened understanding of each agency’s mandates, capacities and priorities, creating a foundation for future collaboration. Enhanced coordination across programmatic and evaluation teams demonstrated how joint efforts can bridge gaps and align diverse perspectives; ii) Collaboration exemplar: this joint evaluation highlighted the effectiveness of early engagement, clear governance structures and transparent communication for smooth coordination and buy-in among multiple stakeholders and iii) Flexibility and tailored approaches: the joint evaluation underscored the need for flexibility in resource allocation, including evaluation planning and the importance of tailored approaches at the country level. Strategic use of partner expertise was also emphasised.

Date of last narrative financial report	19 June 2025	Date of last audited annual statement	19 June 2025