## Annual Review Shock Response Programme 2025

Title: Shock Response Programme
Programme Value £ (full life): £19.5 million		Review date: September 2025
Programme Code: 300886	AMP start date: 29 October 2021	AMP end date: 31 December 2030

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003437.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003718.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Shock Response Programme (SRP) aims to build resilience of vulnerable populations against future crises by ensuring governments and communities can better respond to conflict, climate, and food security shocks. The objective of the programme is to strengthen the reach and responsiveness of country systems to provide support to households that are poor, and vulnerable to (or affected by) shocks; and to accelerate progress made on financing and the use of climate information and data in driving an early response to identified shocks. The programme is financing two core components:

- £16.5 million contribution to the Sahel Adaptive Social Protection Programme (SASPP), delivered through a World Bank multi-donor trust fund from 23 November 2021 to 31 December 2030. Building on the first phase of the trust fund (2014-2020), which was supported by the UK, the second and third phases focus on building and strengthening government-led adaptive social protection systems.  Of note, while SASPP covers the six countries of Mali, Mauritania, Burkina Faso, Chad, Niger, and Senegal, the Foreign, Commonwealth & Development Office (FCDO) notionally only funds activities in the first five Sahel countries and therefore for the purposes of this annual review it will not include Senegal. It should be recognised that there are numerous synergies in the programmes across the region and therefore activities in Senegal also benefit the other countries, for example in terms of lessons learnt. The third phase of the SASPP is due to start during the next reporting period in 2025-26.
- Up to £3 million for the Centre of Disaster Protection (CDP) to implement a new project in the Sahel from July 2021 to October 2025. This project provides independent technical and advisory assistance to support key stakeholders, including governments and the World Bank, to strengthen disaster risk financing in crisis, with a particular focus on climate shocks, and to improve the use of climate data in early warning systems. The estimated total spend on this component will be £1,345,000 by the date of closure, that will make the remaining £1,655,000 available to implement a revised approach to the programme.

The SRP also leverages centrally managed programmes, including the Social Protection Technical Advice, Assistance and Resources Facility (STAAR) and the Better Assistance in Crises (BASIC), to build understanding and capacity around gender and climate and to use climate information to inform the social protection response in the region.

In 2024-25, the SRP also financed an additional component:

£25,000 to support work with the Mali national NGO Women in Law and Development in Africa (WILDAF). This component promoted women’s empowerment and participation, in peace and security by strengthening women’s capacities in mediation, advocacy, social protection, and security governance, and supporting Women's Rights Organisations to participate in and respond to the Women, Peace, and Security Agenda. This component offered a small pilot to test how civil society could include social protection in their work with government and start to understand how women’s rights groups understand social protection.

In 2025-26 a new component on Technical Assistance will be mobilised:

Up for £500,000 to support Technical Assistance (TA) for Social Policy. This is a new component currently under development, it will focus more on the enabling environment for social policy. The terms of reference have been drafted and currently the Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO) are working with commercial to set-up the component.

A no-cost business case extension was approved in July 2025, extending the SRP end date from March 2028 to December 2030 to align with the timeline of Phase 3 of the World Bank SASPP multi-donor trust fund.

Summary supporting narrative for the overall score in this review

Overall, the programme scored an A. The programme overall delivered good results despite delivering in challenging contexts. Whilst there were mixed results between the five countries, the SRP achieved its outputs, including through the SASPP phase 2 programme 2021-2025 supporting the delivery of providing 183,827 households (cumulative) with climate shock response cash transfers, and supporting the registration of 3,270,165 households (cumulative). The SRP, primarily delivered through the World Bank’s SASPP, has continued to utilise support from FCDO centrally managed programmes, as well as the Centre for Disaster Protection (CDP) to strengthen programme delivery. Advisory products will be incorporated into the design of the third phase of the SASPP which will start in the next reporting period 2025-26.

In November 2024 the World Bank with the UN World Food Programme (WFP) took officials including ministers from Mali and Burkina Faso to a visit in Pakistan to look at their social protection system, ministers from Niger were also invited but chose to join online only. This has led to an improved understanding of social protection at senior levels in these governments.

The SASPP has resumed in Mali as a component of the regional Sub-Saharan Africa Women's Empowerment and the Demographic Dividend Plus (SWEDD+) programme, focusing on women’s economic empowerment. Furthermore, the government of Mali held a conference in February and has declared a commitment towards setting up a national social cash transfer programme. There were no active projects in Burkina Faso and Niger during the reporting period. However, the World Bank were able to continue to support these countries through technical assistance and new projects are planned for Burkina Faso and Niger that we expect to get to the board for approval in 2026. The World Bank continued to deliver in challenging contexts with fragile security, food insecurity, and face climate-related shocks. There have been notable steps towards government ownership in Chad and Mauritania. In Chad the government requested support for a national-scale adaptive social protection (ASP) project, which started in November 2024. In Mauritania, the government requested support for the next phase of its ASP system development and has continued to provide its own sustained financing to ASP and has requested to move towards a Programme-for-Results (PforR)[1] financing using national systems. A new project is under preparation with this modality, for approval during the coming fiscal year.
[1] Programme-for-Results (PforR) is a World Bank financing instrument, which includes using a country’s own institutions and processes, and linking disbursement of funds directly to the achievement of specific program results.

Burkina Faso	Despite there being no active project in 2024-25 and a pause on cash transfers since December 2023, the World Bank agreed a new social safety net operation with the government. The project is expected to come to the World Bank board in 2026. The focus will likely be on the economic empowerment of poor households and continued system-building, particularly around the deployment of the social registry. / The security situation has deteriorated as has remained fragile, with a continued mistrust of western countries and organisations. In December 2023 the government paused all cash transfers financed by the World Bank and all other development and humanitarian actors. The government’s decision to suspend the use of the Cadre Harmonisé as a joint methodology to assess food insecurity has rendered the estimation of food insecurity in the country more difficult.
Chad	The new Chad Adaptive and Productive Safety Nets Project started in November 2024, following the government’s request for a national-scale ASP project. The project aims to strengthen the national social protection system and scale up ASP through a unified national platform. The World Bank also contributed to the National Social Protection Strategy (2024-2028).
Mali	Following the closure of the Emergency Social Safety Net (Jigisemejiri) project (2014 – 2023) the World Bank continued to support ASP systems through the Mali Drylands Development Project and the Promote Access to Finance Entrepreneurship and Employment Project. In April 2025, a new phase of ASP financing was approved as part of an additional financing to the SWEDD+ Project. The government held a national social protection conference in February 2025 and has made ministerial commitments to set-up a national social cash transfer programme by the end of 2025. SASPP is providing support to this process, under the leadership of the high-level committee established for this purpose.
Mauritania	Government ownership and financing of the shock response programmes have continued to increase. The government requested World Bank support for the next phase of its ASP system development through a (PforR operation, which is the first of its kind in the region to support ASP.
Niger	SASPP activities were paused following the government’s request to close the Niger Adaptive Safety Net Project 2 in June 2025. The World Bank continued to provide technical and capacity-building support. A new initiative focused on youth employment will be launched from next year 2025-26.

Country updates on implementation of national adaptive social protection systems:

In Burkina Faso, the Social Safety Net project, which started in 2014, closed at the end of the last reporting period in June 2024. At its closing, the project had supported a total of 1.29 million individuals with monetary transfers (both regular and shock-responsive) and economic inclusion measures and supported the establishment of the national social registry and the registration of 344,400 households (277,220 of which through SASPP financing which is about 21 % of all poor households). During this reporting period in 2024-2025, there was no active project in Burkina Faso, however, the World Bank SASPP continued to support through technical assistance. A new social safety net operation is planned in Burkina Faso by the World Bank for next financial year 2025-26 and is expected to focus on the economic empowerment of poor households and continued system-building, particularly around the deployment of the social registry. The team will also continue to support the operationalisation of the national safety net programme (the Programme d’appui à l’Autonomisation des Ménages Pauvres et Vulnérables – PAMPV) a key pillar of the ASP system going forward.

During the reporting period, the security situation remained fragile. The Armed Conflict Location and Event Data (ACLED) initiative identified 7,522 fatalities caused by security incidents in 2024, compared to 8,494 in 2023. An estimation of food insecurity is more difficult since the government suspended the use of the Cadre Harmonisé[2]. However, the Integrated food Security Phase Classification (IPC)[3] acute malnutrition analysis estimates that between August 2024 and July 2025, 425,000 children aged between six and 59 months could suffer from acute malnutrition.
[2] The Cadre Harmonisé (CH) is a harmonised, regional framework used for the analysis and identification of areas at risk and populations affected by food and nutrition insecurity in the Sahel and West Africa.
[3] The Integrated Food Security Phase Classification IPC is a standardised scale that integrates food security, nutrition and livelihood information into a statement about the nature and severity of a crisis and implications for strategic response.

In Chad, following the government’s request for a national-scale ASP project, a new operation, the Chad Adaptive and Productive Safety Nets Project was approved at the end of the last reporting period, and started during this reporting period in November 2024. The project aims to strengthen the national social protection system and scale up ASP through a unified national platform. It supports both system development and service delivery, structured around five core ASP instruments: the Unified Social Registry (USR), a digital payment module, the national food security information and early warning system, a refugee management module, and a government-led national safety net programme. Productive inclusion activities, and a shock-response mechanism, which can address floods, lean seasons, and forced displacement, are included in the project design. During the reporting period, the World Bank also contributed to the National Social Protection Strategy (2024-2028).

Despite political support, Chad continued to face significant challenges due to regional instability, particularly the conflict in Sudan. As of March 2025, Chad was hosting over 1.35 million refugees. Chad also has an estimated 500,000 internally displaced people from previous crises. Chad continues to face one of the highest levels of food insecurity globally. Climate-related shocks, such as recurrent droughts and erratic rainfall, have severely impacted agricultural production. The latest Cadre Harmonisé assessment estimates that 2.5 million people are in IPC Phase 3 or above (crisis or worse). Malnutrition rates have also deteriorated, rising from 28% in 2022 to 36.7% in 2024.

Following the closure of the Emergency Social Safety Net (Jigisemejiri) project (2014 – 2023) the World Bank continued support in Mali through the Mali Drylands Development Project and the Promote Access to Finance Entrepreneurship and Employment Project. Both of these projects contribute to building ASP systems by financing the Unified Social Registry Registre Social Unique – RSU). In April 2025, a new phase of ASP financing was approved as part of an additional financing to SWEDD+ project. The project aims to increase girls’ and women’s access to learning and their utilisation of health services; support productive inclusion activities targeting poor and vulnerable girls and women, and provide employment opportunities through an integrated package of productive inclusion measures. It is designed to address key constraints preventing women and girls from poor households from engaging in productive, climate-resilient livelihoods. In addition to the deployment of these economic activities, the project will provide critical resources to strengthen national ASP systems.

The unstable security has slowed progress. As of January 2025, Mali hosts 378,363 internally displaced persons. During the 2025 lean season (June – August) it is estimated that 1.47 million people (more than 6% of the population) are expected to face crisis conditions or worse (IPC Phase 3 and above). An additional over 4 million people (more than 17% of the population) are expected to be under stress conditions (IPC Phase 2).

Mauritania continued to make significant progress in ASP activities during the reporting period, which are anchored in the Social Safety Net System Project II. The government requested World Bank support for the next phase of its ASP system development through a PforR[4] operation, which is the first of its kind in the region to support ASP. The operation is planned for the end of 2025.

Mauritania continued to face additional pressure on resources due to the growing influx of refugees, primarily from Mali. As of February 2025, the UNHCR estimates that Mauritania is hosting approximately 167,791 Malian refugees and asylum seekers. In response, the government, working in collaboration with UNHCR and other partners and with support from SASPP, has formally integrated refugees into the national social registry, facilitating their access to social protection programmes and economic inclusion activities. Mauritania also continued to face significant food security risks. The March 2025 Cadre Harmonisé estimated that approximately 590,000 people will face acute food and nutrition insecurity during the 2025 lean season. This is a slight improvement from 656,000 in 2024, but still indicative of persistent fragility.

Following the military coup in Niger in 2023, ASP activities were paused for ten months while the World Bank assessed the political and economic situation. In May 2024 the World Bank agreed to resume working through the Niger government, however the government requested the early closure of the Niger Adaptive Safety Net Project 2 in June 2025 to launch a new initiative focused on youth productive inclusion and employment from next year 2025-26. Support from the World Bank was maintained through the disbursement pause with technical assistance and capacity-building, including in the development and strengthening of adaptive delivery systems and adaptive interventions. The ASP agenda was also further advanced through two complementary World Bank projects – the West Africa Unique Identification for Regional Integration and Inclusion Project and the Youth Employment and Productive Inclusion Project.

Insecurity and fragility remained a challenge in Niger during the reporting period. It is estimated that 2.2 million people (8.1% of the population) may face severe food insecurity between June and August 2025. There are also around 700,000 internally displaced people in Niger.

Major lessons and recommendations for the year ahead

Programme components
Following recommendations in last year’s annual review regarding adapting to the context, an information note was developed for the programme that set out a revised approach. This included two new components, the first on technical assistance and the second on civil society. Following the announcement of a reduction of Overseas Development Assistance (ODA) spending from 0.5% of gross national income (GNI) to 0.3%, there was a revised approach to the FCDO’s ODA spend. These changes caused some delays in planned new approaches for this financial year. The FCDO are now exploring a technical assistance (TA) component and will assess options for the civil society component.
Recommendation 1: It is recommended that the TA component of the SRP is mobilised in 2025-26 and options are assessed for a civil society component.
Logframe
There will be a need for a new logframe as the CDP component will close in September 2025, the SASPP has a revised results framework for phase 3, and the new TA component will be mobilised.
Recommendation 2: A new logframe should be revised by March 2026 six months ahead of the annual review, to show the revised approach of the programme. This should include the consideration of more delivery focused output indicators as well as including more robust evidence of the contribution of the SRP towards institutional capacity.
Lessons learned
The complex conflict and humanitarian emergencies in the Sahel are increasing poverty. Over the next year 2025-26, the FCDO should further define four key areas to inform the programme’s strategic approach. These areas are set out in the recommendations below:
Recommendation 3: Document models and lessons learnt on including refugees and host communities in social protection programmes in Mauritania and Chad.
Recommendation 4: Develop key points and recommendations on social cohesion and social protection in the Sahel, learning from the Justice and Stability in the Sahel (JASS) and other programmes.
Recommendation 5: Develop key points and recommendations on social exclusion risks and mitigations in the Sahel.
Recommendation 6: Identify opportunities for further linkages with the humanitarian, development and peace nexus that are relevant for social protection in the Sahel.
Update on overarching recommendations from the annual review 2023-24
Recommendations 2023-24	Update 2024-25
Programme
1. The logframe is designed to track many knowledge products, for the next annual review this could be revised to improve the tracking of the delivery aspects of the programme.	This recommendation will be incorporated into the logframe update for 2025-26 when the SRP logframe will be updated to align with the third phase of the SASPP.
2. The complexity of working in fragile and conflict-affected situations (FCAS) countries has been challenging for partners. Due to changes in government and government policies, working in three of the five countries has been particularly limited in 2024. The importance of staying present during these changes is critical and can enable better future relationships and positive progress towards resuming activities.	The World Bank with WFP organised a joint visit for the three countries to Pakistan, Mali and Burkina Faso officials joined in person and Niger online. This has led to a new programme in Mali and planned new pipeline social protection programmes in Niger and Burkina Faso. The multi-donor trust fund was key for the World Bank to finance staff to stay present at the country level, provided continued technical assistance, and understand the new political economy of these contexts, this resulted in countries resuming or planning to resume social protection programmes.
3. The Twin Track Approach (WFP and UNICEF) currently financed by Germany was designed to enable the delivery of cash assistance and complementary services. As far as possible, cash transfers are delivered through government programmes and delivery systems. Where government capacities are saturated or government has no access, delivery is aligned to government responses, but using service providers. This has been piloted in Mauritania, Mali and Niger – delivered to over 3.5 million people across the region. The approach has proven important to reach areas that the government is not able to access and continue the delivery of social safety nets during times of crisis. It is recommended to consider a field visit to understand how the programme works in practice. There is potential that the UK could leverage this programme for more flexible development and humanitarian programmes in the Sahel.	A World Bank led field visit for co-donors is planned for November 2025 in Chad, which will include seeing the activities on the twin track approach.
4. The context of the Sahel has changed substantially in the last four years since the programme was designed. The instability of the region has been heightened and the coups across the region are challenging the relevance of the CDP component of the programme. In three countries there is a limited footprint of any social protection programming. It is therefore unclear if diagnostic analysis and disaster plans will be taken forward by the governments in these contexts. It is recommended to develop an information note to consider how the programme’s strategic approach has needed to adapt to the new contexts.	This was completed by the SRP SRO / Social Development Adviser in consultation with Sahel Development Counsellors during the reporting period. This considers how the programme could improve and evidence its conflict sensitivity and effectiveness of working in fragile and conflict-affected situations (FCAS) contexts. It was recommended that political economy analysis and technical assistance are combined to provide analysis and flexible support to the programme. It will be considered how to take this forward in 2025-26.
The World Bank Sahel Adaptive Social Protection Programme (SASPP)
5. The World Bank SASPP programme has had to adapt its operations and ambitions to work effectively in FCAS countries. An adaptation of the delivery model has been required with an increase in staff in-country supporting the programme and negotiating ways of working. Consider how this can be best captured, and lessons learnt for other World Bank programmes in FCV contexts. As well as what the World Bank can learn from other FCAS countries and organisations.	SASPP compiled best practices on how to deploy social safety nets in FCV contexts, based on case studies from the region and beyond (see A guide to Implementing Social Safety Nets in Fragile, Conflict and Violent Contexts published in May 2025). The operational lessons learned are being incorporated in the ongoing design of new operations in Niger and Burkina Faso and reflected in the design of interventions recently approved in Chad and Mali. This was also considered in the design of phase 3 of the SASPP. To adapt the SASPP itself, Phase 3 proposes a flexible approach, which allows to sustain technical assistance and a strong presence in country, while providing teams with greater flexibility in the implementation of recipient-executed grants. The learning agenda has also evolved, with shorter/narrower tasks and the annual revision of priorities for knowledge management.
6. There is a high complexity of designing a World Bank multi-donor trust fund (MDTF) results framework for a regional programme. Once that is agreed upon it is very difficult for additional results to be added to the results framework. The design period of a new or revised MDTF programme is the most appropriate time to request results to be added to the framework. There are three embedded consultants on climate, resilient livelihoods and gender (financed by the STAAR programme) that plan to influence the results framework of the third phase of the MDTF.	The FCDO programme team were able to feed into the design and provide feedback on the results framework for phase 3. The revised results framework better captures new result areas, including those related to gender, coordination, and climate. STAAR consultants contributed to this effort.
7. The third phase of the SASPP programme is currently under design. The UK has invested in targeted technical assistance (TA) on disaster risk financing (DRF), climate, resilient livelihoods, gender and data disaggregation. The measure of the effectiveness of this TA will be how it is integrated into the phase 3 SASPP programme document. The FCDO should consider how this can be captured in the AR for 2025. A revised logframe may be required to align with SASPP phase 3.	Building on the first two phases, SASPP’s third phase (2025-2030) will continue strengthening ASP systems and expanding ASP programs. In addition, based on an in-depth diagnostic of progress in the region and key constraints to the development of national ASP systems, SASPP’s third phase will also place additional emphasis on ASP systems’ sustainability, their flexibility in fragile contexts, and their contribution to climate change adaptation and resilience.
The Centre for Disaster Protection (CDP)
8. There has been substantial investment in TA to improve the DRF of the SASPP programme through CDP and to embed this approach in the phase 3 of the SASPP programme. It is not clear that this TA is leading to outcomes and impact at a country level. It is recommended that this TA component is reviewed as the SASPP phase 3 design is finalised to understand the impact on the SASPP phase 3 programme. The contract is until June 2025 and the current workplan is until January 2025. The advisory board for the programme will be held in October, the SASPP 3 programme document completed in early 2025. By the end of March 2025, it should be decided whether the contract should come to an end, or if a no cost extension should be agreed. The logframe would need to be updated to reflect this decision.	A strategic decision has been agreed to end the component with CDP in September 2025. The agreed workplan will be completed and a review on lessons learnt. The programme team will develop a revised approach to technical assistance to support the programmes objectives.
Centrally managed programme (CMP) financed technical assistance (TA)
9. There is research and TA financed by CMPs in the region, including the STAAR study on social protection in FCV countries and the in-person workshop in Dakar. As well as the three consultants seconded into the World Bank SASPP programme. There is research on social networks and climate resilient livelihoods in Niger by the BASIC team. It is recommended that the TA components and complimentary research and evidence building are reviewed to ensure that they contribute to an integrated approach in the region.	The TA financed by STARR on social protection in FCV contexts is now being piloted by WFP and UNICEF in the region. The three consultants seconded into the World Bank SASPP team have been taken on as World Bank financed consultants and are on track to meet their objectives on climate livelihoods, integrating International Climate Fund (ICF) targets into the results framework and improved integration of gender. The basic team research has ended and has helped influence the SASPP team in how they are working in the Sahel and can complement local systems of social assistance.
Communications and advocacy
10. DFID/FCDO was a critical first donor in first version of the SASPP MDTF testing the proposal of social protection in the Sahel region. During the second phase of SASPP the UK has been pivotal in advocating for improved integration of climate, gender and DRF, and three other donors have now joined the MDTF. The UK will be the first investor into the third phase of the SASPP MDTF, other donors have committed they will follow. This demonstrates durable influence from the UK and buy-in from other donors.	The UK has now been the first to sign the new SASPP phase 3 MDTF agreement and in the process of making the first payment. The new SASPP 3 results framework has included stronger results on climate, disaster risk financing and gender and is more aligned to the UKs approach on climate and ICF. This is continued evidence of the value of the UKs technical inputs and leadership on adaptive social protection in the Sahel.
11. The FCDO is an active member of the Sahel Alliance coordination group on social protection that was set-up to improve joint understanding, coordination, and approaches. This alliance could be an opportunity to improve the impact of the UKs leadership on social protection. Furthermore, the IMF has played an integral role in improving national financing in Mauritania, along with a committed government. The FCDO (central teams) has been a committed advocate of the importance of adding the measurement of social spend to IMF programmes. It is recommended that lessons learnt from effective working in Mauritania and from working with the IMF are identified.	The Sahel Alliance coordination group on social protection has now closed and been integrated into the regional social protection meetings. This will improve how lessons learnt in the Sahel are shared with other organisations and governments working in West Africa. The SRO worked with the International Finance Institutions Department (IFID) to develop a guide on IMF and social sector spend, with a focus on social protection learning lessons from the region. The SRO and Sahel Economist are learning lessons from the Sahel region and working with the central social protection, fragility and IFID teams to support a community of practice session with the IMF on social protection in FCV.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Shock Response Programme (SRP) theory of change and logframe was revised in 2023 to better align with the World Bank’s theory of change and results framework, to integrate the Centre for Disaster Protection (CDP) component, as well as ensuring that climate adaption and resilience outcomes were adequately mainstreamed and monitored throughout the programme. The theory of change remains the same for the 2024-25 annual review.

Logframe indicators and targets were updated during the reporting period and approved by the Development Director. This was not a material change to the programme, as the theory of change, impact, outcome, and output statements remained the same. The changes are noted in the ‘Output’ section and summarised below:

- Reflecting the closure of the CDP component of the programme in 2025.  This project provided independent technical and advisory assistance to support key stakeholders, including governments and the World Bank, to strengthen disaster risk financing in crisis. As the component will close in 2025-26, three output indicators (1.4, 2.3 and 3.2) were revised to reflect a reduced ambition.
- Reflecting changes in the programme strategy which puts more of an emphasis on the importance of strengthening the capacity of institutions and partnerships. This included revising output indicator 4.2 to better reflect the range of partners that the World Bank engages with, and revising output indicator 4.3 to include the support that the FCDO centrally managed programmes are providing to strengthen the SRP. Finally, the weightings were adjusted for output 3 and output 4 so that they both have equal weightings of 20% to reflect the importance that both have to achieving the outcome.
- Amending the target in Burkina Faso due to contextual constraints. As the World Bank have not been able to sustain an active programme in Burkina Faso this year, the target / milestone for output indicator 2.1 was revised to consider the significant progress made over the lifetime of the programme to date.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Despite delivering in a challenging context, and a focus exclusively on technical and policy-level engagements as well as regional knowledge management. There have been no active projects in Burkina Faso and Niger over the reporting period, though policy dialogue and advisory capacity has continued and new projects are expected in both countries in early 2026. In Mali the continued policy dialogue led to a new project starting as part of a wider demographic programme. Whilst in Mauritania and Chad, substantial progress has been made. Despite the context challenges the programme continues to be on track to contribute to the expected outcomes and impact.

- Impact: Vulnerable people have increased resilience to shocks to protect their livelihoods and cover basic needs. This is measured by the percentage of poor (living below poverty line) that are included on national social registries and can be reached by shock response systems. The milestone that there was an improvement in the average percentage compared to the previous year (65%) was achieved, with a result of 70%. In addition, a major effort was made, which resulted in 99% of these households having up-to-date information in the national social registries.
- Outcome: National government social protection systems are strengthened and are better able to manage risks (including climate change risks) and provide timely support. This is measured by:
1. Programmes – the percentage of payments made on time: did not improve compared to last year due to a suspension of activities in Burkina Faso and Niger, where payments have been timely in the past (this outcome indicator is not measured in Mali). Around 25 % of payments were on time in Mauritania, as per the operational guidelines, during the reporting period. However, these resulted from delays in mobilising the funds at the Ministry of Finance, rather than issues with the payment system and once the order is given to make the payments, they are timely. In Chad, 94% of all payments on time, however this is a decrease from last year (100%). The share of digital payments has increased steadily each year, from 23 percent in 2022 to 64% in 2025.
2. Data and information – the evidence of improvements introduced to data and systems supporting the delivery of adaptive social protection (early warning systems and social registries): the average share of households in the registry with up-to-date information (as per the operational guidelines) increased from 93% in 2024 to 99% of the 3.2 million households currently registered in 2025. This was above the 77% target. To note the data is only from Burkina Faso, Mauritania, Niger.
3. Finance – the evidence of improvements introduced to financing mechanisms to enable a timely response to disasters: as with previous years, to date only Mauritania has adopted a disaster risk financing mechanism / instrument which is below the target of three countries by 2025. While progress remains limited, the degree of readiness of financing to ensure timely disaster response measured in the stress test has improved significantly during the period, with an average score in line with the program’s initial target.
4. Institutions & Partnerships – the evidence of governments committing own financing to shock response through Adaptive Social Protection (ASP) mechanisms: as with last year, Burkina Faso and Mauritania have committed to their own financing, with Mauritania also providing sustained financing over multiple years. Whilst this is slightly less progress than the target of at least two countries both committing and having sustained financing over multiple years, this still demonstrates significant progress in light of contextual constraints that the programme has been operating in.

Progress between 2021/22 and 2025, despite a complex context, is presented in the figure below:

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on SRP’s achievements in 2024-25 and the context of the wider portfolio, the programme should continue. The SRP continued to deliver results during a challenging implementation period, building on its successes from previous years and the first phase of the World Bank’s Sahel Adaptive Social Protection Programme (SASPP). At the end of the reporting period, ASP projects were agreed to be taken forward with the governments of the two countries where government-implemented programming had been paused (technical assistance and policy dialogue continued throughout the period) after sustained engagement from World Bank teams (Niger and Burkina Faso), while new engagement were recently approved in Mali, Burkina Faso and Mauritania have committed their own financing to shock response through ASP mechanisms, with Mauritania also continuing to provide sustained financing. A national-scale ASP project has also been approved in 2024 in Chad, while a new operation is planned for end 2025 in Mauritania. Lessons learnt to date have been incorporated into the third phase of the SASPP, recently approved with SASPP’s core donors.

As part of the SASPP, the World Bank has provided strong evidence of the benefits of ASP systems including increasing food security, incomes, and school enrolment (see section ‘G. Monitoring, Evidence and Learning’).

The programme remains aligned to the Sahel strategy, contributing to 2 of the 3 priority objectives, and to the UK’s Strategy for International Development, particularly contributing to a) providing women and girls with the freedom they need to succeed, b) stepping up our life-saving humanitarian work, c) and taking forward our work on climate change, nature, and global health.

## C. DETAILED OUTPUT SCORING

Output Title	Vulnerable households benefit from shock response cash transfers and productive inclusion activities
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1: # of beneficiary households receiving climate shock response cash transfers funded by SASPP / [cumulative for Phase II, # households, # individuals, # women]	150,000 (Ind: 906,000; F: 453,000)	183,827 (Ind: 1,161,082; F 587,271). In addition, 138,692 households have received COVID-response cash transfers through the SASPP. / Substantially exceeded expectation
1.2: # of direct beneficiaries receiving training and grants (productive inclusion support) funded by SASPP to strengthen resilience to climate shocks / [Cumulative from Phase II, includes baseline results as support is delivered over multiple years. Individual and female recipients]	91,689 (52,220 f) / (Burkina Faso 11,000; Mali 30,000; Niger 46,697; Chad 2,000; Mauritania 1,992)	56,254 (Burkina Faso 21,265 (21,265 f); Mali 11,000 (0 f); (Niger 16,697 (15,027 f) (Chad 2,000 (1,900 f); Mauritania (5,292 (4,928 f)) / Substantially did not meet expectation
1.3: % of complaints received by the Grievance Response Mechanism (GRM) that are resolved in a timely manner.	Improvement in average % compared to previous year / 81% (Burkina Faso 80%; Chad 90%; Mauritania 75%; Niger 80%)	88% (Burkina Faso: N/A; Chad 98%; Mauritania 78%; Niger N/A) / Burkina Faso and Niger are N/A due to disbursement suspension. / Moderately exceeded expectation
1.4: # of targeted activities undertaken to improve the gender-responsiveness and inclusiveness of the ASP systems.	1. Country-level reforms to payment systems include solutions that are adapted to the situation of women / 2. Operational recommendations for ASP for displaced populations take gender constraints into consideration, and propose recommendations to strengthen the gender-responsiveness of programs and systems	1. The team prepared guidance on how to foster gender-responsiveness in payment systems, which will be presented at the Regional Technical workshop planned end 2025 in the region. / 2. The World Bank prepared a policy note presenting priority recommendations, as well as a technical paper with guidance on how to apply a gender lens on ASP. Learning will be applied in Phase III of the SASPP, which includes the consideration of five pathways identified to enhance gender-responsiveness of ASP and maximise its impact on gender outcomes. / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

1.1 In Burkina Faso, due to the absence of a World Bank financed operation, the targets and achievements of the cumulative number of beneficiary households receiving climate shock response cash transfers funded by SASPP for 2024-25 remained the same as the previous year, namely 104,052 households (around 624,312 individuals), in addition to the 50,228 households supported in the context of COVID-responses in 2022. SASPP continued providing technical support to the Executive Secretariat of the National Food Security Council (Secrétariat Executif du Conseil National de Sécurité Alimentaire) to operationalise the lean season response manual (which has been an output from 2023-24) throughout the different stages of the national food security response planning cycle.

In Chad, the cumulative number of households supported through SASPP funding remained at 23,294 (an estimated 139,764 individuals), which is a result from 2023. There were 60,000 Sudanese refugee households supported in 2024-25, financed through the World Bank’s International Development Association (IDA)[5]. SASPP contributed to the IDA financed Refugees and Host Communities Support Project (PARCA), which delivers ASP to refugees and host communities. SASPP also contributed to the Chad Adaptive and Productive Safety Nets Project as a response to the government’s request for a national-scale ASP project, which started its implementation from November 2024.
[5] The World Bank’s International Development Association (IDA) helps the world’s poorest countries by providing grants and low- to zero-interest loans for programs that boost economic growth, help reduce poverty, and improve poor people’s lives.

In Mauritania, a cumulative 47,281 households were reached, which is an estimated 314,826 individuals, of which 164,143 are estimated as female beneficiaries. This is an increase of 23% from 2023-24’s results of 37,675 households (263,190 individuals; 138,325 female). Notably, the Mauritanian government made significant progress during the reporting period in financing and implementing regular and shock-responsive social protection programmes, and this included the government-funded programmes, the Elmaouna and Tekavoul Shock, which was also supported by the IMF.

In Mali, since the ASP operation closed in 2024, the SASPP was able to support social protection components in other World Bank projects including the Mali Drylands Development Project (PDAZAM) and the Promote Access to Finance, Entrepreneurship and Employment in Mali (PAFEEM) project. In Niger, the results remained the same as the previous year, due to a halt in disbursements prior to the closure of the Adaptive Safety Net Project 2 in June 2025, a total of 10,200 households (around 82,180 individuals) were supported by SASPP in response to climate shocks, in addition to the 30,000 households supported (for a period of 2 years) in response to the COVID crisis in 2022-2023. The World Bank were able to support the preparation of a pilot for introducing digital payments in urban areas during the reporting period.

1.2 The number of direct beneficiaries receiving training and grants (productive inclusion support) funded by SASPP to strengthen resilience to climate shocks substantially did not meet expectation in the three countries included in this indicator, due to the suspension of SASPP activities in Niger and the ending of the programme in Burkina Faso. The cumulative results were a total of 56,254 beneficiaries reached (61% of its objective of 91,689). However, in Mali, the new IDA operation, SWEDD+, which is supported by a SASPP grant, includes a component focused on providing productive economic inclusion activities which will reach an estimated 45,000 women.

Despite this target not being met due to operational constraints beyond the control of the programme, new operations have been agreed with governments in Burkina Faso and Niger going forwards in the next reporting period, and both governments have requested a productive focus.

Economic inclusion interventions are multifaceted packages, which include community-based savings groups, coaching, psychosocial interventions (addressing aspirations and life skills), micro-entrepreneurship training, market access facilitation, and grants. They are a core part of ASP and provide an important pathway to increase productivity, reduce food insecurity and contribute to resilience. The 2023-24 annual review noted that there was not specific evidence on how the livelihoods packages were preparing women for climate shocks specifically, and how the different modules and coaching support households to build climate resilience. In response, the FCDO funded a consultant to support the World Bank on improving this for the design of the upcoming Phase 3 of the programme. During the reporting period, the consultant also supported with work on integrating climate adaptation into economic inclusion interventions. An output of this work included a study in Mauritania and Senegal on climate adaptation opportunities for safety net beneficiaries to inform the revision of productive inclusion activities. As part of this effort, a qualitative study was also launched in collaboration to explore gender-specific and structural constraints to adopting climate adaptation practices, with the goal of informing programme design to enhance women’s climate resilience through economic inclusion.

1.3 There was an improvement to the previous year in the percentage of complaints received by the Grievance Response Mechanism (GRM) that are resolved in a timely manner, with 88% in 2024-25 on average compared to 81% in 2023-24. This percentage does not take into account Burkina Faso where the programme ended and Niger where results were not applicable due to a suspension of activities. However, there was some progress in Niger in enhancing the GRM, including the introduction of a toll-free hotline to complement the existing village-based complaints committees. In Chad the result was 98% compared to 85% the previous year and Mauritania was 78% compared to 75% the previous year. The results for this indicator are not available for Mali and so are not collected.

1.4 There was some progress with regards to the number of targeted activities undertaken to improve the gender-responsiveness and inclusiveness of the ASP systems during the reporting period.

The World Bank prepared a policy note presenting priority recommendations, as well as a technical paper with guidance on how to apply a gender lens on ASP. The technical paper covered the gendered context, the barriers women and girls face in accessing assets and resources, as well as key aspects of ASP policy, design, and delivery that require a lens on gender. It also covered efforts to protect women and girls from sexual exploitation, abuse and sexual harassment, the role of GRMs, staff codes of conduct and routine monitoring and learning. The analysis identified existing good practices that support gender-responsive programming.

For the next reporting period, the World Bank has identified five pathways to enhance gender-responsiveness of ASP and maximise its impact on gender outcomes. These include: (1) to increase capacity strengthening support for implementing partners in the delivery of ASP that is gender-responsive in the Sahel; (2) to improve the gender-focus of monitoring and evaluation systems; (3) to provide guidance on gender-responsive payment systems; (4) the expansion of evidence-based advocacy on ASP’s contribution to women’s empowerment; and (5) to improve ASP’s ability to respond to gender in design and delivery.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As recommended in the 2023-24 annual review, output indicator 1.4 was updated to track revised targets for 2024-25. As a decision was made to close the Centre of Disaster Protection (CDP) component of the programme in 2025-26, the output indicator was revised to lower the ambition for the CDP component for its final year in removing the reference to CDP support in improving the gender-responsiveness and inclusiveness of the ASP systems.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from previous annual review

Output 1 recommendations 2023-24	Update 2024-25
1. There are significant challenges to working in fragile and conflict-affected situations (FCAS) countries in the Sahel. These are challenging for all partners operating in the region. The World Bank’s model for delivery of social protection programming has required significant adaptation to work effectively. It would be good to capture how they are learning and adapting to deliver ASP in the region.	SASPP compiled best practices on how to deploy social safety nets in Fragile, Conflict and Violence (FCV) contexts, based on case studies from the region and beyond (See A guide to Implementing Social Safety Nets in Fragile, Conflict and Violent Contexts published in May 2025).
2. The livelihoods package of interventions does not detail how the programme is strengthening resilience to climate shocks. It seems to be an assumption rather than part of the design. A FCDO financed consultant in supporting SASPP on improving this for the design of SASPP 3. Once the SASPP 3 programme is designed update this output in the FCDO logframe for 2025.	This has been discussed with the World Bank and will be included in the results framework for phase 3 of the SASPP.
3. The milestones in output 1.4 should be redesigned to move away from compliance safeguarding targets for CDP and into more strategic outputs that connect to the programme outcomes.	This was updated in the logframe during 2024-25.

Lessons learned this year and recommendations for the year ahead

The World Bank SASPP team compiled best practices on how to deploy social safety nets in FCV contexts, based on case studies from the region and beyond (See A guide to Implementing Social Safety Nets in Fragile, Conflict and Violent Contexts published in May 2025). The operational lessons learned are being incorporated in the ongoing design of new operations in Niger and Burkina Faso and reflected in the design of interventions recently approved in Chad and Mali. This was also considered in the design of phase 3 of the SASPP. To adapt the SASPP itself, Phase 3 proposes a flexible approach, which allows to sustain technical assistance and a strong presence in country, while providing teams with greater flexibility in the implementation of recipient-executed grants. The learning agenda has also evolved, with shorter/narrower tasks and the annual revision of priorities for knowledge management.

The SASPP team has effectively used the flexibility of the MDTF to finance additional staff that can be based in the different countries, understand the political economy of social protection and adapt to changes in governance structures. These staff are also working more closely with the actors in the humanitarian sector and with actors that are delivering through cash transfers to improve coordination between the humanitarian, development and peace nexus and mitigate misinformation about cash transfers. The SASPP team plan to develop a document over the next year to demonstrate the additional value of a MDTF on social protection in FCV contexts. This will also showcase the continued value of donor investments in MDTF’s in FCV contexts.

Output Title	Expansion of social registries and improved early warning systems for adaptive social protection
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1: # of households in the social registry as a result of SASPP intervention / [Cumulative from Phase II, does not include Phase I results]	2,821,220 households registered onto social registries in the region / (Burkina Faso: 277,220; Chad 444,000; Mauritania 200,000; Mali 1,100,000; Niger 800,000)	3,202,985 households registered onto social registries in the region. / (Burkina Faso: 277,220; Chad 684,543; Mauritania 346,802; Mali 1,194,371; Niger 700,049) / Substantially exceeded expectation
2.2: # of technical and advisory documents produced by SASPP on adaptive social registries and poverty & vulnerability / [Cumulative for Phase II]	19 (registries: 11; vulnerability: 8)	60 (registries: 21; vulnerability: 39) / Substantially exceeded expectation
2.3: # of demand-responsive engagements or products for national government, World Bank and/or other stakeholders on linkages between early warning systems & social protection systems produced by CDP. / * Engagements and products can include, but are not limited to: analytical or advisory notes and reports; research publications; capacity building & training; workshops & presentations.	At least 2 demand-responsive engagements or products delivered.	CDP worked with the World Bank SASPP teams to deliver two disaster risk financing (DRF) diagnostics for Mali and for Chad. The DRF for Mali is published and the DRF for Chad is completed and is awaiting publication in French and in English. / There is also a flood impact study for Chad which is in development. / Met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

2.1 the target for the number of households in the social registry was revised from previous year, which previously only included results for Burkina Faso, to take into account the broader picture of data on the overall progress on social registries in the region. Overall, the World Bank has made significant progress in supporting the registration of households in the social registry across the region. The cumulative total is 3,270,165 exceeding the target of 2,821,220 households by 16 percent on average. Expectations were exceeded in Chad, Mauritania and Mali.

Despite the closing of Burkina Faso and Niger’s social safety net projects and the absence of a national social safety net programme in Mali, the SASPP has continued to provide technical assistance to national social registries in all countries. This included support on the development of the social registry in Niger, providing strategic options for coverage in Mali, and facilitation of updating the targeting protocol with a focus on hard-to-reach and insecure areas in Burkina Faso. Support from SASPP for social registries ranges from support to the development of the registries (management information systems, training, software and hardware, methodology, storage, etc.) to the financing of actual data collection. In some countries, data collection is also financed by governments and by other partners (e.g. WFP and other partners added around 65,000 households in Burkina Faso in 2025).

2.2 The number of technical advisory documents produced by SASPP on social adaptive registries and poverty and vulnerability was substantially exceeded with a cumulative total of 60 documents (21 on adaptive social registries and 39 on poverty and vulnerability) compared to the target of 19 documents. SASPP supported both broad regional analytical work and country-specific work. This included papers on dynamic social registries, non-agricultural income sources across the Sahel, social cohesion, climate change impacts.

2.3: the number of demand-responsive engagements or products for national government, World Bank and/or other stakeholders on linkages between early warning systems & social protection systems produced by CDP was met. CDP completed a disaster risk financing (DRF) diagnostic for Mali and a DRF diagnostic for Chad in collaboration with the World Bank SASPP country teams. For Mali, the diagnostic identified practical entry points to strengthen the integration of disaster risk financing into Mali’s adaptive social protection system. CDP held targeted consultations in February 2025 with government counterparts and partners to ensure the recommendations are actionable and aligned with national priorities. These discussions served as a platform to validate the diagnostic findings, encourage uptake, and inform ongoing dialogue between the World Bank, national authorities, and other stakeholders working on climate and shock-responsive social protection. In Chad, the diagnostic identified how DRF can most effectively support scalable, shock-response systems in Chad. CDP convened a multi-stakeholder consultation in April 2025 with government representatives and development partners including the United Nations Development Programme (UNDP), the German Society for International Cooperation (GIZ), the US Agency for International Development (USAID), the African Development Bank, and the International Organisation for Migration (IOM). This consultation provided an opportunity to reflect on the diagnostic’s recommendations, strengthen alignment across actors, and explore practical steps for integrating financing into the existing safety net system.

In addition, CDP in the process of completing a Chad Flood Impact Study which aims to develop a comprehensive flood risk profile to support flood response mechanisms under the World Bank’s Adaptive and Productive Safety Nets Project (APSNP) in Chad. Fondation pour les Études et Recherches sur le Développement International (FERDI) has assessed historical flood hazards and impacts through both qualitative and quantitative analysis, drawing on diverse data sources such as household surveys and remote sensing datasets. Completion of the work is expected by the end of September 2025 (originally expected in June 2025) due to delays in receiving key datasets and the addition of further primary analysis to strengthen the findings. The deliverables, including a detailed report, policy brief, and presentation, will inform emergency cash transfer mechanisms, support future disaster preparedness planning, and outline recommendations for follow-on research.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As mentioned above, output indicator 2.1 was revised to include social registry results for all countries supported in the SRP. Output indicator 2.3 was also revised to reduce the ambition of the CDP component to remove the reference to ‘at least two other engagements or product in development’ in addition to the ‘two demand-responsive engagements or products delivered’, as the CDP component will end in early financial year 2025/26 and so no new engagements were planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from previous annual review

Output 2 recommendations 2023-24	Update 2024-25
1. There are significant challenges to delivery in fragile and conflict-affected situations (FCAS) countries, in particular, for this output in Burkina Faso. Consideration should be given to how the logframe can be improved so that it captures the challenges of working in FCV countries and enables adaptive ways of working.	This was considered as part of a review of the programme’s strategic approach going forwards by the SRP SRO / Social Development Adviser in consultation with FCDO Sahel Development Counsellors.
2. CDP’s current contract ends in June 2025. They have provided a list of outputs and a workplan with planned work until the end of January 2025. During the reporting period, CDP’s key lead for the Sahel left the team and although CDP are in the process of recruiting a new person, this has left a significant knowledge gap.	The CDP component has been agreed to be closed, the current workplan is due to end at the end of November. The finalised learning documents and consultant reports are expected in October. The contract is held by the DRF team in FCDO, who will continue to support CDP work once the outputs for the SRP programme are completed. A new technical assistance component will be mobilised in 2025-26, which will focus more on the enabling environment for social policy. As part of the CDP programme closure, briefings will be held with the FCDO Sahel team and Development Counsellors based in the British Embassies in the Sahel. This will include a handover of CDP’s key documents developed for their support to the World Bank and how they could be used by Development Counsellors for future engagement in the region, as well as lessons learnt.
3. It is recommended that the FCDO programme team review the impact of the CDP partnership and wider technical assistance (TA) components completed through other partners such as the STAAR helpdesk and revise the programme’s strategy on TA based on lessons learnt.	CDP completed a learning component on the programme. The STARR helpdesk consultant positions will also be evaluated. This learning will be fed into the strategy for the programme going forwards in 2025-26.

Lessons learned this year and recommendations for the year ahead

The output indicators for this output may not have been ambitious enough given the huge over achievement in the indicators. Only 2.1 is delivery focused and 2.2 and 2.3 are knowledge product focused. Recommendation 2 of this annual review is to develop a new logframe. More delivery focused output indicators will be considered as part of this update.

The CDP component has not been able to effectively drive demand for DRF products from governments due to firstly, not having technical advisors / leads in the region that speak French and are able to drive demand and secondly, the many changes in governance in recent years which has made it very difficult for all partners to adjust their way of working and ensure they continue to speak to the new government priorities.
Output Title	Improved financing strategies and mechanisms for adaptive social protection
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – decreased from 25% to 20%

Indicator(s)	Milestone(s) for this review	Progress
3.1: # of analytical and advisory reports on risk financing / [Cumulative Phase II]	6	14 / Substantially exceeded expectations
3.2: # of demand-responsive engagements or products for national government, World Bank and/or other stakeholders on financing adaptive social protection produced by CDP.* / *engagements and products can include, but are not limited to: analytical or advisory notes and reports; research publications; capacity building & training; workshops & presentations.	At least 2 demand-responsive engagements or products delivered	CDP delivered 6 country case studies, and 1 regional synthesis paper. / Moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

3.1 the number of analytical and advisory reports on risk financing was substantially exceeded with 15 products in total compared to a target of 6 (cumulative). This included a collaboration between the World Bank SASPP team and the CDP on disaster risk finance (DRF) diagnostics in Chad and in Mali. In Chad, the study focuses on the compounding effects of multiple hazards on vulnerable populations and provides recommendations, including on expansion of safety net coverage and improving shock response effectiveness. In Mali, the study recommends expanding safety nets in high-vulnerability regions, strengthening the ASP system, integrating shock-responsive triggers, and promoting greater use of prearranged financing instruments such as contingency funds and sovereign insurance mechanisms. CDP also supported the World Bank SASPP team on case studies of disaster contingency funds for Chad and Mali, as well as a regional report synthesising best practices for ASP-related contingency funds.

The World Bank SASPP team also worked in partnership with the Consultative Group to Assist the Poor (CGAP) on a note on climate finance, specifically to demonstrate how social protection systems can serve as effective delivery channels for climate funds, enabling rapid, accountable, and targeted support to populations most vulnerable to climate change, enhancing their climate resilience and adaption.

3.2 the number of demand-responsive engagements or products for national government, World Bank and/or other stakeholders on financing adaptive social protection produced by CDP was moderately exceeded. The CDP commissioned the Overseas Development Institute (ODI) to conduct a regional study exploring how disaster risk financing can support scalable adaptive social protection in fragile and shock-prone settings. This included firstly two in-depth country case studies focused on Senegal and Mauritania to examine the institutional, financing, and delivery arrangements that shape the scalability of ASP in response to shocks in consultation with government officials, World Bank country teams, and development partners. Secondly, a regional synthesis paper was completed, which distilled lessons across countries and offered practical recommendations for donors, implementers, and governments aiming to align risk financing with social protection systems.

In addition, CDP completed country case studies on public financial management and ASP in Chad and in Mali. For Chad, two institutional case studies were finalised and submitted to the World Bank. The first examined ONASA (Office National de Sécurité Alimentaire), Chad’s public grain reserve institution, exploring its legal and financial frameworks and role in supporting food security responses. The second focused on FNSS (Fonds National de Solidarité et de Soutien aux Personnes Vulnérables), assessing its capacity to serve as a national ASP financing mechanism. Together, these studies offer concrete recommendations to better align national contingency financing tools with scalable social protection objectives.

For Mali, CDO completed a case study on the Fonds de Sécurité Alimentaire (FSA), a reserve fund within the national budget supporting emergency food purchases and logistics; and the Fonds Commun des Partenaires (FCP), a pooled donor mechanism supporting resilience-building and social protection scale-up in times of crisis. Both case studies provided granular insights into national capacities and limitations and have been submitted to the World Bank to inform future ASP/DRF strategy in Mali.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output indicator 3.2 was also revised to reduce the ambition of the CDP component to remove the reference to ‘at least two other engagements or product in development’ in addition to the ‘two demand-responsive engagements or products delivered’, as the CDP component will end in early financial year 2025/26 and so no new engagements were planned.

The weighting was reduced from 25% to 20% to reflect that both output 3 (on improving financing strategies and mechanisms) and output 4 (on increasing institutional capacity) are equally important to achieving the outcome of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Output 3 recommendations 2023-24	Update 2024-25
1. Many outputs in the logframe focus on knowledge products and it is therefore worth reviewing the logframe and identifying evidence that shows how the knowledge products are being utilised to improve programmatic outputs.	The SASPP proposes each year to identify selected knowledge products, explain how they were prepared and/or shared within countries, and identify processes to which they contributed (see Section D for examples). In addition, SASPP’s third phase proposes to organize its regional knowledge generation program around more specific questions, with products prepared over shorter duration (when possible), and to collectively select additional questions every year (based on the choices of SASPP team members), informed by their policy, design, and system needs. This more reactive design will help ensure knowledge management products are fully aligned with evolving needs in a challenging context.
2. Output indicators 3.1 and 3.2 are similar, and is it therefore recommended that these are reviewed, and separate output indicators are identified for future years. The output indicators are narrow and focused on products generated rather than transformations that CDP might be able to influence.	These indicators were not updated over the reporting period, but they will be reviewed and updated in 2025-26 as part of a logframe update to align with phase 3 of the SASPP.
3. The context of the Sahel has changed substantially in the last four years since the programme was designed. The instability of the region has been heightened and the coups across the region are challenging the relevance on this component of the programme. In three countries there is a limited footprint of any social protection programming. It is therefore unclear if these plans will be taken forward by the governments in these contexts.	The World Bank have effectively adapted their approach and used the flexibility in the MDTF to add additional staff in country to understand the new governments priorities and adapt the discussion on adaptive social protection to be politically relevant. This has led to the resumption of the new programme in Mali. New programmes are currently under design and negotiation in Burkina Faso and Niger, expected to go to the board in early 2026.
4. An information note should be completed which considers how the programme could improve and evidence, its conflict sensitivity and effectiveness of working in FCAS contexts. A revised approach could be relevant, which may require different partners to be identified.	A review of how the programme’s strategic approach needs to adapt to the new contexts was completed by the SRP SRO / Social Development Adviser in consultation with Sahel Development Counsellors during the reporting period. This considers how the programme could improve and evidence its conflict sensitivity and effectiveness of working in fragile and conflict-affected situations (FCAS) contexts. It was recommended that political economy analysis and technical assistance are combined to provide analysis and flexible support to the programme. It will be considered how to take this forwards in 2025-26.

Lessons learned this year and recommendations for the year ahead

The output target indicators have been knowledge product focused which has been very achievable for partners. The output indicators will be revised in the new logframe to include targets that to focus on other measurements regarding financing of adaptive social protection (Recommendation 2). This will also take into the recommendation from last year's annual review and incorporate the new SASPP phase 3 results framework. The SASPP team have agreed in future reports to explain more about how particular products are used and have an impact on systems, to link better between the output and outcome objectives of the programme. The CDP component will close in October 2025 and therefore that output indicator will be revised.

Output Title	Increased institutional capacity to deliver adaptive social protection and greater coordination between government and non-government actors.
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – increased from 15% to 20%

Indicator(s)	Milestone(s) for this review	Progress
4.1: # of technical and advisory documents produced by SASPP on institutional arrangements / [cumulative for Phase II]	15	25 / Substantially exceeded expectations
4.2: # of countries where the World Bank has an ongoing Memorandum of Understanding (MoU) or formalised agreement with WFP, UNICEF, UNHCR and/or IMF	5	1 MOU in Mauritania with WFP / No MOUs in Burkina Faso, Chad and Mali. There is however strong collaboration with WFP and UNICEF in Burkina Faso (e.g. in the context of sectoral working groups and the social registry task force); a joint ASP task force with WFP and UNICEF in Chad since 2023; and a tri-partite action plan in place with WFP and UNICEF in Mali. In Niger, the three institutions collaborated on the COVID-19 response, productive inclusion, drought response, revision of the social protection policy, and development of the social registry / Met expectations
4.3: # advisory products on improving the effectiveness of social safety nets (through the Social Protection Technical Assistance, Advice, and Resources Facility (STARR) or other FCDO funds)	4 products	6 products / Moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

4.1 The cumulative number of technical and advisory documents produced by SASPP on institutional arrangements was substantially exceeded with 25 documents produced in total compared to a target of 15. This was for both regional and country-specific documents and included a regional technical paper on standards for ASP, contributions to the draft decree of the RSU in Chad, contributions to the operational manual for floods in Mauritania, and mapping of key stakeholders and predominant synergies between the early warning system for food security and adaptive social protection in Mali.

4.2 The number of countries where the World Bank has an ongoing MoU or formalised agreement with WFP, UNICEF, UNHCR and/or IMF was met. This indicator was revised from only including formalised agreements (e.g. MoUs) to better reflect range of partners that the World Bank is engaging with on advancing ASP. Whilst the World Bank only has one formalised MoU with WFP in Mauritania (which is particularly effective in supporting the government national shock response framework), there is a strong collaboration with WFP and UNICEF at a regional and country level. In both Burkina Faso and Chad collaboration is demonstrated through a social registry task force (Burkina Faso) and an ASP taskforce (Chad). This allows for a clear road map, coordination of dialogue and missions, and joint trainings. In Burkina Faso, the social registry task force that the World Bank led strengthened partner coordination which resulted in the European Union working with WFP and an NGO (that had previously supported deployment in the first two regions in Burkina Faso) to support the RSU’s expansion in five additional regions. The World Bank also works with WFP and UNICEF as part of a tripartite action plan in Mali as well as working through sectoral working groups.

The World Bank SASPP team also fostered other key partnerships during the reporting period to ensure alignment and complementary in advancing ASP initiatives across the Sahel. This included collaboration with humanitarian actors, including the European Civil Protection and Humanitarian Aid Operations (ECHO) on operational coordination; participation in regular technical and policy dialogues on food security led by the Permanent Interstate Committee for Drought Control in the Sahel (Comité permanent Inter-États de Lutte contre la Sécheresse dans le Sahel) to integrate ASP instruments into national strategies; engaging with key regional policy actors, including the IMF and the Economic Community of West African States (ECOWAS) to promote the inclusion of ASP principles in country and regional level policy dialogues. As a result of this, the social protection framework and accompanying operational plan adopted by the Economic Community of West African States (ECOWAS) in November 2023 are underpinned by strong ASP foundations.

In November 2024, the SASPP team also worked with WFP to organise a study tour for ministers from Mali, Burkina Faso, and Niger, to learn from Pakistan’s experience with a national safety net program and social registries, which provided an opportunity for increased commitment to this agenda. A key achievement during the reporting period has also been that, with IMF support, the Governments of Burkina Faso and Chad have committed financing to their national safety net programme, while in Mauritania, funding has been secured for the shock-responsive safety net response.

4.3 the number of advisory products on improving the effectiveness of social safety nets (through the Social Protection Technical Assistance, Advice, and Resources Facility (STAAR) or other FCDO funds) was a new indicator added for 2024-25 to include the support provided through FCDO central funds to the programme. This was moderately exceeded compared to the target of 4 products. The Maintaining and strengthening social assistance systems in conflict settings: Sahel case study (Niger and Burkina Faso), has document lessons learnt and future ways of working, and is being utilised by WFP and UNICEF to improve ways of working in the Sahel. This target also included two core outputs on gender (a technical paper and a policy note), two core outputs on climate adaptation of productive inclusion interventions based on pilots in Senegal and Mauritania, and a core output on the impacts of ASP on resilience to climate change in the Sahel.

Beyond these six outputs, the three consultants that were centrally financed have informed SASPP’s work program, as reflected in ongoing operations (e.g. design of productive inclusion interventions, review of operational manuals from a gender perspective, guidance for gender-sensitive payment systems) as well as high level dialogue on climate financing. Climate and Gender are now more clearly articulated in the new results framework for phase 3. The finalised versions of some of the products are under review by the World Bank and will be published in the coming year. Due to changes in the FCDO to implement an ODA reduction from 0.5% to 0.3% of GNI between the financial years 2024-25 to 2025-26, the contracts for the consultants were discontinued in April 2025 before the work was finalised. Fortunately, the SASPP team was able to contract the consultants directly and a gap in the work was avoided.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A new output indicator 4.3 was added to include work that the FCDO is funding centrally to strengthen capacity through the STAAR.

The weighting was increased from 15% to 20% to reflect that both output 3 (on improving financing strategies and mechanisms) and output 4 (on increasing institutional capacity) are equally important to achieving the outcome of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from previous annual review

Output 4 recommendations 2023-24	Update 2024-25
1. There have been increasing improvements in coordination and approaches at a regional level between the World Bank, UNICEF and WFP. In part facilitated by Germany and their substantial investment in the SASPP programme and a joint UN programme. The FCDO could consider its role in regional bodies and identify gaps and opportunities.	This was considered as part of the review of the programme’s strategy going forwards. In November 2025 a joint field visit for adaptive social protection in Chad, looking at the work of WFP, UNICEF and the World Bank is planned and will help identify opportunities. Regional bodies have changed in recent years with the exit of the Alliance of Sahel states (AES) from ECOWAS. FCDO will continue to monitor the situation as the regional and international structure changes and identify gaps and opportunities for regional or global influence.
2. Increased coordination and advocacy were demonstrated between social protection actors and the IMF in Mauritania, this resulted in improved commitment to financing social protection. Recommendation for learning how this was negotiated and where appropriate and strategic advocate for similar working relationships.	The World Bank brief the IMF directly regarding social protection, and in the recently approved IMF programme in Chad, social protection and the social registry was included significantly. The SRO has worked with the economist and the social protection policy team and plans to present to the IMF community of practise on social protection to influence their way of working in the Sahel and in FCAS more broadly.
3. The suspension of cash-based transfers in Burkina Faso has obligated substantial improvements and joint ways of working between the World Bank, UN and other humanitarian actors. It would be important to learn lessons that might prevent this risk materialising in other contexts.	The SRO for SRP and the Humanitarian Advisor met with CALP (Choice and Dignity for people in Crisis), who have led a study on the suspension of cash in the region. They are now leading some trainings to prevent this from happening in other contexts and misinformation on cash. FCDO is working with them on a webinar and to support their work with other donors to raise awareness of the challenge and how to prevent the risk from materialising in other contexts.

Lessons learned this year and recommendations for the year ahead

1. Partnerships in the Sahel are critical for consistency when working with governments to avoid confusion and misinformation. The consistency between WFP, UNICEF and the World Bank is supporting the adaptive social protection agenda and by working together on joint briefings, visits for partners and for governments ministers has been effective. The start of the programme in Mali and their new ambition for a national social assistance programme is promising signs. The expected new projects planned for Burkina Faso and Niger expected to be approved in 2026, will demonstrate the effectiveness of this approach and an ability to adapt and work with these governments and their new priorities.
2. The World Bank has adapted its approach in Burkina Faso, due to the cash transfer ban the programme currently being designed will focus on productive inclusion. Those who take part will then receive cash for work as part of the programme, this is acceptable to the government. The programme design and implementation will be carefully monitored to ensure inclusion of women and vulnerable groups, such as people with disabilities. As well as how it is designed and implemented in the conflict sensitive way, given the complexities of the environment. It is not yet clear how shock responsive support will be included in the design, once the project appraisal document is prepared these areas will become clearer.
3. The three consultants seconded in the World Bank SASPP team were effective at influencing the design of the new phase 3 SASPP results framework and other key priorities on gender and climate. This has proved to be an effective way of working with the SASPP team and the leadership of the SASPP team has been supportive of these priorities.
4. The SRO has started to work with NGO networks and organisations such as CALP to dispel misinformation on cash in the region. Furthermore, the SRO is connecting the SASPP team to key opportunities in the region, such as the AES conference on humanitarian assistance. This resulted in improved coordination and linkages between the humanitarian and social protection sectors. The SRO will look at how to increase the opportunities to improve linkages across the sectors in the future.
5. The output indicators should be updated to include more robust evidence of the contribution towards institutional capacity. For example these could include trainings, secondments and delivery units in government. This will be looked at as part of the overall logframe update (Recommendation 2).

## D: VALUE FOR MONEY

Key cost drivers and performance

Key cost drivers for the SASPP component are programme delivery costs, including contributions to projects supporting ASP. Key cost drivers for the CDP component are staff costs (fees), including consultants.

VfM performance compared to the original VfM proposition in the business case

In the original business case, the preferred value for money (VfM) option was to fund the World Bank multi-donor trust fund combined with delivering through FCDO centrally managed programmes (specifically climate and weather, including disaster management expertise). The SRP has continued to follow this approach, whilst adapting the FCDO central support to include the Centre for Disaster Protection (CDP) and The Social Protection Technical Assistance, Advice and Resources (STAAR) facility consultants through the centrally managed Better Assistance in Crises (BASIC) programme. FCDO centrally managed programmes have been utilised to strengthen the evidence of the impacts of the programme.

The business case proposes some indicators to consider but also suggests engaging with partners in the mobilisation / delivery phase to agree the best indicators to be used in practice, based on the context and need. VfM frameworks with indicators were developed by the World Bank and CDP and were updated for this reporting period.

No targets have been provided in the World Bank’s VfM framework, however baselines have been provided to allow for comparisons. CDP provide a self-assessment with ratings against each criterion.

Economy

World Bank: The World Bank measures trust fund management costs as a percentage of total programme costs. Compared to the baseline of 0.4%, in financial year 2024-25, a total of USD 558,659 was spent on SASPP management, reporting, fiduciary aspects, as well as knowledge management and communications, representing 0.25% of total programme costs. The World Bank also measures supervision costs for recipient-executed grants as a percentage of total grants. Cumulatively, USD 2,274,180 has been spent to supervise recipient-executed grants, for a total grant amount of USD 175.7m (of which USD 87,064,639 has been disbursed). Supervision costs represent 1.29% of total grant amounts or 2.61% of total grants disbursed. Because the indicator measures cumulative costs of supervision, this percentage increases over time, during the life of the recipient-executed grants (baseline was 1.91%). These supervision costs remain very low, thanks to the joint supervision of SASPP financed grants and IDA financed projects.

CDP: Economy was assessed through two indicators during the reporting period. Firstly, the average fee of short-term technical assistants / consultants compared to benchmarked costs in the budget and the agreed fee rate caps. During the reporting period, on average, fee rates were 12% below the agreed fee rate caps of expert bands, improving on last year’s average. Secondly, the one-off cost savings secured on contracts and expenses, by assessing the total value of cost savings through negotiations, supplier selection and partnerships. In 2024-25, negotiations led to consultant rates below the agreed cap. While there were no major procurements during the reporting period, partnership agreements were established with the Overseas Development Institute (ODI) and FERDI (Fondation pour les Études et Recherches sur le Développement International).

Efficiency

World Bank: To assess efficiency, the World Bank measures (1) the financial costs of transfers (as a share of total transfers); and (2) the percentage of cash transfers done on time.

In financial year 2024-25, the financial cost of transfers remained consistent with the baseline, which is between 0.5% and 5% In Mali, the rate was between 2 and 3% of the transfer value for all transfers. In Mauritania, the fees were 0.5% for electronic payments (in Nouakchott) and between 2.5 and 3.85% for manual payments (the rest of the country). In Chad, the fees ranged between 3 and 5%, depending on the operator and regions (4.5% and 5% for electronic payments and 3% for manual payments (however, this increased up to 7.97% if additional costs such as logistics are included). No payments were made in Burkina Faso and Niger during the reporting period.

Compared to the baseline of 86%, the percentage of cash transfers completed on time was significantly lower in 2024-25 at 59% (average for Chad and Mauritania). This represents a decrease from previous years. There were no payments made in Burkina Faso and Niger during the reporting period, and these countries previously had high rates of timely payments (99% in Burkina Faso and 96% in Niger). There was also a significant decrease in the share of timely payments in Mauritania (25%). This was due to a delay in the mobilisation of funds at the central level to give the payment order, and not to the payment systems themselves (i.e. once the payment order is given, payments are timely.

In Mauritania, the World Bank are working towards providing technical assistance to the government to adopt a more effective system. The timeliness of payments is also a Disbursement-Linked Indicator in the proposed new project in Mauritania (a milestone which will trigger the disbursement of a tranche of the new project). The World Bank are also organising a regional workshop with counterparts in all countries in March 2026, to provide a platform for capacity building and South-South exchange on the various options for payment systems (including in FCV contexts).

CDP: Efficiency was measured through the management of overheads (the percentage of overheads of the total project spend). Core team fees (overheads) amounted to £35,198, covering project management, governance, financial management, security, and IT. This equates to 11% of the overall spend within the reporting period. This is an improvement from 2023-24, where the overheads were 29% which was assessed as being significantly high.

Effectiveness

World Bank: Effectiveness is measured by three indicators. Firstly, the cost per beneficiary of productive inclusion interventions. During the reporting period, there were no changes in the cost of interventions implemented in Niger, Burkina Faso, Mauritania, and Chad compared to the baseline costs of $263-584 in Niger, $262 in Burkina Faso, $252-285 in Chad, and $573 in Mauritania. Data is not available for Mali.

Secondly, the change in household level consumption as a result of productive inclusion measures. During the reporting period, there was a significant impact on consumption reported 18 months after the end of the projects in Niger (+$0.25 per day per beneficiary), Chad (+$0.21 per day per beneficiary), and Mauritania (+$0.31 per day per beneficiary). There was also increased diversification and impact on women’s non-agricultural incomes (+$268 in Niger per year per beneficiary, +$170 in Mauritania per year per beneficiary and +$123 in Chad per year per beneficiary). It was also found that there was an increase in participation to savings groups 18 months after the end of the projects in Burkina Faso (90%), Niger (86%), Mauritania (48%), and Chad (38%). There also a strong increase in savings over the last 3 months of the reporting period (+$20 per beneficiaryin Niger, +$27 per beneficiary in Mauritania, and +$60 per beneficiary in Burkina Faso).

Finally, effectiveness is measured by World Bank technical and advisory outputs resulting in changes in the government approach / policies on ASP. Examples of this during the reporting period include, (1) in Mali, impact evaluations of the productive inclusion interventions conducted in other countries within the region played a crucial role in incorporating productive inclusion interventions into the new Sub-Saharan Africa Women’s Empowerment and Demographic Dividend Plus (SWEDD+) project; (2) in Mauritania, SASPP analysis informed the development of options for entry into – and exit from – the Tekavoul program; which were adopted by the government; and (3) in Burkina Faso, expenditure analysis shaped the IMF advocacy for safety nets.

CDP: Due to the indirect nature of the work that CDP carry out there is currently insufficient evidence to show that CDP inputs to the programme explicitly contribute to increases in resilience to shocks of vulnerable people in the Sahel region. CDP measure effectiveness through the quality of delivery, which was only assessed during the reporting period through feedback on quality of deliverables from the members of government in Chad and Mali during consultation on the findings of disaster risk financing (DRF) diagnostics, which was overall positive.

Equity

World Bank: Equity is considered through the proportion (annual and cumulative) of women benefitting from climate shock response cash transfers, and receiving productive inclusion activities, funded by the SASPP. Women represent 50% of individuals who benefit from programs (their share in beneficiary households). For the recipients of benefits (the person who receives the cash on behalf of the households), annual data show that 90% of the recipients were women during 2024-25 compared to 134% last year in 2023-24. The high share in 2023-24 was partly due to the fact that in Burkina Faso, an average of 1.5 women were recipients in each household, accounting for households with multiple women. The decrease in 2024-25 is due to there being no SASPP-financed transfers in Burkina Faso during the reporting period.

CDP: CDP aimed to measure equity through evidence that project advisory and support emphasises or sheds light on inequities experienced by poor and/or vulnerable people. However, there was insufficient evidence to provide an assessment on this indicator during the reporting period, due to their being limited requests from governments on support specifically on gender and social inclusion.

Progress on recommendations from previous annual review

Value for money recommendations 2023-24	Update 2024-25
1. The SASPP World Bank programme has demonstrated strong VfM despite limited operations in three countries. For the World Bank, working in the Sahel region in fragile and conflict-affected situation (FCAS) countries, it is critical to stay engaged whilst there are changes in government and to continue to build capacity in the national government and political will for social protection systems. For the next annual review, the UK should consider with the World Bank how to measure the VfM of working in FCAS contexts without a functional IDA programme.	The SASPP team have adapted their way of working in FCAS and adjusted their strategic approach to the new governments of the central Sahel. The approach has led to a new IDA project in Mali, and new IDA projects in Burkina Faso and Niger are currently in the design phase. The SASPP team is going to develop a lessons learnt document on how to use the flexibility in MDTF to enable IDA projects in FCAS contexts. SRO will discuss with the economist how to measure/record the VFM of working in FCAS contexts when IDA projects are paused and/or ended due to governance changes.
2. CDP continues to have high administrative costs due to the nature of its work and set-up of the organisation. This should be monitored for next year to ensure it continues to be good VfM.	This was monitored over the reporting period. Overheads were 11% of the overall spend within the reporting period. This is an improvement from 2023-24, where the overheads were 29%.
3. It is recommended that for phase 3 of the SASPP programme data disaggregation by gender, age and disability is included in the design of the results framework. In 2025 the SASPP team plan to systematically identify additional entry points to further boost gender outcomes, with support from FCDO’s Social Protection Technical Assistance, Advice, and Resource (STAAR) initiative.	This has been incorporated into phase 3 of SASPP programme data collection. In addition, key actions to promote greater gender outcomes have been identified (presented in dedicated Technical Paper and Policy Note) and country- or program-specific recommendations have been prepared to improve the design of programs (e.g. Tekavoul in Mauritania) or system (e.g. payment systems, to be shared during the technical in-country workshop planned for November 2025).

Assessment of whether the programme continues to represent value for money

Based on SRP’s achievements in 2024-25 and the context of the wider portfolio, the programme should continue. The SRP continued to deliver results during a challenging implementation period, building on its successes from previous years and the first phase of the World Bank’s Sahel Adaptive Social Protection Programme (SASPP). As part of the SASPP, the World Bank has provided strong evidence of the benefits of ASP systems including increasing food security, incomes, and school enrolment (see section ‘G. Monitoring, Evidence and Learning’) demonstrating good value for money.

E: RISK

Overview of risk management

The overall risk rating for the SRP remained ‘moderate’. SRP continues to operate in a fragile and insecure region, compounded by climate change and decreasing humanitarian resources.

The SRP risk register is reviewed and updated at least quarterly by the FCDO programme team. Risks outside of the FCDO’s appetite level are escalated to department / directorate level to consider appropriate mitigation strategies. Risk levels have not gone beyond appetite this year and no risks were escalated to department / directorate level during the reporting period. The risk appetite for Safeguarding was increased from Cautious to Receptive following a recommendation from an internal FCDO audit that a Receptive appetite would better reflect the operating context of the Sahel. The region is one of the poorest and most fragile in the world, with high rates of gender inequality and social exclusion, meaning that sexual exploitation, abuse and harassment (SEAH) is a high risk. The risk appetite for the SRP is summarised below:

Risk appetite category	Shock Response Programme
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Safeguarding	Receptive
Financial & Fiduciary	Cautious
Reputational	Cautious
Public Service & Operations	Cautious
People	Cautious

A due diligence assessment (DDA) refresh of the World Bank for the SASPP was completed during the last reporting period 2023-24. There has been progress on the actions and recommendations from the DDA over this reporting period. This includes:

- Governance and engagement: an action was to ensure that governance structures and communication for the SASPP are sufficient. It was assessed that the governance has allowed for sufficient and regular communication with co-donors on progress through co-donor meetings that take place at least monthly. This also provides an opportunity for co-donors to share information and provide strategic oversight.
- Downstream partners and risk management: the updated DDA in 2024 assessed the WB as having robust and adequate financial management systems and processes. For the phase 2 the SASPP team did not complete a delivery chain risk map as is not a requirement according to our central level agreements between FCDO and the World Bank. The SASPP team are planning to develop a simple risk assessment for the SASPP phase 3, which will reflect the complex nature of the activities – including both TA/Bank-executed activities and activities in the 6 countries in the context of broader IDA engagements.
- Contingency planning: an action was to discuss with the World Bank contingency planning / alternative delivery mechanisms in a case where the World Bank needs to suspend funding due to changes of government. FCDO has discussed with WB and is satisfied with the actions put in place in such scenarios, including the World Bank's Operational Policy 7.30.
- Climate outputs / outcomes: an action was for the FCDO to work with the World Bank on agreeing a logframe that improved the tracking of outcomes of the climate aspects of social protection. This will be incorporated into Phase 3 of the programme, and during the reporting period FCDO funded consultants through the STAAR facility helpdesk has worked with the World Bank on this.
- Safeguarding: As the World Bank is not mandated to report incidents of sexual exploitation, abuse and harassment (SEAH) to the FCDO, it was clarified that the FCDO instead reviews the policies and procedures that the WB has in place to adequately address cases. This includes their grievance response mechanism, which an FCDO funded consultant through the STAAR facility helpdesk has supported the World Bank with over the reporting period. The DDA also recommended a follow-up on the proposal by the World Bank to use ClearCheck to conduct employment checks on potential employees past misconduct. The World Bank is one of the entities amongst other United Nation entities, that use ClearCheck to share information on individuals who have established allegations related to SEAH. In addition, the WB has procedures in place to screen people, particularly in operations that include service delivery to children and vulnerable groups. As part of project preparation, obligations to identify, mitigate and respond to SEAH are embedded in Environmental and Social Commitment Plans. In high and substantial SEAH risk projects, Borrowers are also required by ESCPs to develop dedicated SEAH action plans. All project, countries are required to put in place (if not existing) codes of conduct that prohibit SEAH for all project actors.

The SRP has risks under the following categories:

Strategy & Context

SRP operates in a very challenging and fluid environment, which experiences multiple emergencies (humanitarian, security, fiscal).

The risk that conflict in the region leads to an increase in food insecurity and therefore disrupts programme delivery remained moderate during the reporting period. This is already an issue due to economic crises and climate shocks (e.g. droughts). Conflict in the region would exacerbate existing migration waves, which would further disrupt programme delivery at the local level, overwhelm an already stretched humanitarian system, and would reduce national governments' ability to coordinate and prioritise social protection. Mitigations included working with the CDP to include climate triggers and disaster risk financing best practices into the design of adaptive social protection systems, and continuing to work with delivery partners to prioritise climate shock response.

The risk that the deteriorating political and security situation in one or more countries leads to worsening international relations, and stakeholders' lobbying to suspend delivery partner activities, remained moderate during the reporting period. Mitigations included context analysis, and engaging with delivery partners on contingency delivery mechanisms if funding cannot go through government units. During the reporting period, the World Bank continued to maintain engagement in countries where projects where delayed / paused (Mali, Burkina Faso, and Niger) through technical assistance and explored options for support (for example, through other World Bank projects).

Policy & Programme Delivery

SRP operates in a very challenging environment, and one of the ways that this is mitigated is through our choice of delivery partners, which continued to be the World Bank and CDP during the reporting period. The World Bank is an experienced agency established in the Sahel region with a considerable track record in delivering national systems strengthening work to deliver social protection over a long-term period. The CDP complemented the WB's work by providing required expertise on climate aspects of SRP.

The risk that there is low appetite and engagement from recipient national governments and / or ineffective engagement from delivery partners to prioritise social protection at scale (in comparison to tackling insecurity), result in ineffectiveness of the programme increased from moderate to major during the reporting period. This was due to changes in governance in the central Sahel and continued risk of instability in governance structures and policies. For detail:
- In Burkina Faso the changes in governments resulted in a change in policy, that has now banned all cash transfers in December 2023. This coincided with the end of the social protection programme, which was not renewed immediately, however the government has now in the process of designing a new IDA project on social protection and a project is expected to go to the board in early July 2026.
- In Niger in response to the military coup in July 2023, article Operational Policies and Bank Procedures 7.30[6] came into affect and all activities on IDA programmes were paused, this pause on programmes was lifted in May 2025 but the government of Niger did not resume to IDA supported social protection programme at that time. By June 2026 the IDA supported project in Niger was agreed to close and the government is now working with the SASPP team to design a new IDA supported project expected to go to the board in 2026.
  [6] The World Bank Operational Policies and Bank Procedures 7.30 is the operational manual for dealings with De Facto Governments
- In Mali the programme came to an end in 2023 and was not renewed at the time. However following a ministerial visit to Pakistan and continued policy dialogue with the SASPP team, the government supported an adaptive social protection component on an IDA financed demographic project. The SASPP team is also supporting the government of Mali to design a new national adaptive social protection programme.
Mitigations included delivery partners placing greater emphasis on policy dialogues with new government officials and engagement with government line ministries to facilitate politically relevant stakeholder engagement, initiating national consultations and development of country-level workplans, and rolling out disaster risk finance diagnostic and trigger work in Sahel countries. Also, continued technical engagement with governments throughout the period (including a minister-level trip to Pakistan for officials of the three countries) has laid the foundation for new operational engagements (new project approved in April 2025 in Mali, and under preparation in Niger and Burkina Faso). This points to the importance of SASPP’s contribution to WB presence in country and continued technical engagement.

The risk that climate is not adequately addressed through a lack of prioritisation, capacity or coordination with regional climate expertise resulting in a weak application of climate outcomes into country programmes and ineffective delivery improved from moderate to minor during the reporting period. Mitigations included support for the SASPP on climate from STAAR consultants. For Phase 3 of the SASPP, the World Bank will be putting more emphasis on climate outcomes, and this risk will be reduced and will not be necessary to monitor in the next annual review.

Safeguarding

SRP operates in environments where there are risks of safeguarding cases, particularly due to working in conflict affected contexts.

The risk that a weak implementation of safeguarding measures by downstream partners / government contractors allows for sexual exploitation, abuse and harassment (SEAH), which violates safeguarding principles and endangers vulnerable persons, worsened from moderate to major during the reporting period. Mitigations included ensuring that delivery partners (including downstream) have adequate policies and organisational practices, which can be assessed through the DDA, as well as having regular discussions about safeguarding.

The risk that grievance mechanisms do not allow for appropriate responses to reporting at community level leading to under-reporting of possible SEAH and abuse of power / corruption and resulting in failure of accountability to affected persons remained moderate during the reporting period. Mitigations included continuing to advocate for the World Bank to hold national governments accountable to ensure feedback/reporting systems are functional and effective and to encourage partner national governments to raise awareness among beneficiaries on SEAH. The regional Gender-Based Violence (GBV) and Safeguarding lead presented their strategy for the SASPP in October 2024 and confirmed that GBV specialists are included in all Project Implementation Unit teams.

Financial and Fiduciary

Financial and fiduciary risks recognise our programme relies on remote management with limited forms of verification in place given our staffing model and travel restrictions including the challenging context. FCDO works with established partners with strong financial and monitoring systems in place such as the World Bank.

The risk that the capacity of governments to appropriately use Recipient-executed Trust Funds (RETF) remains low, resulting in mismanagement of funds, corruption, aid diversion, and theft, improved from major to moderate during the reporting period. Mitigations included strong monitoring systems, oversight processes, and risk management systems by the World Bank to manage fraud and corruption risks, and FCDO monitoring of multi-donor trust fund compliance mechanisms through annual reviews, meetings and field visits.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

World Bank

The Sahel Adaptive Social Protection Programme (SASPP) component of the SRP is delivered through an administrative agreement with the World Bank. The SASPP is a multi-donor trust fund (MDTF) funded by contributions from the German Federal Ministry for Economic Cooperation and Development (BMZ), the French Development Agency (AFD), the Danish Royal Ministry of Foreign Affairs, and the UK (FCDO).

The SASPP management team and donors come together annually for a partnership council meeting to discuss the programme’s technical work at regional and country levels and to endorse the strategic directions. SASPP donors and the management team additionally meet monthly for a technical advisory group. The country focused activities are led and managed by the World Bank’s technical teams in the context of the Banks’ Social Protection and Jobs broader engagement in each country. A strong presence in each country provides the foundations for deep and regular engagement with government counterparts and development partners.

In July 2024, the UK and co-donors agreed that the World Bank could move the SASPP under an umbrella trust fund – the Sahel and West African Coastal Countries (SAWAC) as part of its governance structure. The SAWAC seeks to address key drivers of fragility, conflict, and violence (FCV) and strengthen sources of resilience in the Sahel and West African coastal countries. The SASPP Phase III MDTF is an Associated Trust Fund under the SAWAC, which means it retains its own reporting structure and fiduciary independence of the programme while strengthening the synergies.

In financial year 2024-25, the total UK contribution for the SASPP component was £6,000,000. The UK has contributed a total of £11,000,000 since the start of Phase II of the programme under the SRP from 2021.

Centre for Disaster Protection

The Centre for Disaster Protection (Sahel) component is delivered by the Centre for Disaster Protection (CDP) through a contract managed centrally by the FCDO. CDP’s work on SRP forms a part of this FCDO centrally managed contract but is invoiced separately to the Sahel programme team. The programme team meet monthly with the CDP Sahel management team – the Associate Director (Strategic Partnerships & Communications) and the Head of Operations to discuss progress. A decision was made in 2023-24 to close this component of the SRP in 2025-26. The CDP will be completing its final deliverables.

In financial year 2024-25, the expenditure for the CDP (Sahel) component was £408,498.12. The total expenditure to date since the project started in 2022 is £1,286,966.19.

Progress on recommendations from previous annual review

Programme management recommendations 2023-24	Update 2024-25
1. CDP should hold an advisory group consultation with key CDP staff and FCDO Sahel advisers to revise its approach and provide a costed plan for the length of the programme, (which currently is until June 2025). This should be finalised by October 2024 for the rest of the financial year. The SRP Programme Responsible Owner will consult procurement colleagues on future contracts and budgets and with the centrally managed CDP programme SRO and PRO.	This was received and approved. All deliverables will be completed by September 2025.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

This annual review was conducted by the SRP team (SRO and PRO), with inputs from the wider department, posts and other SASPP donors. Monthly donor meetings are held with the World Bank as well as the annual partnership council meeting. A donor field visit to Chad is planned for November 2025. The FCDO programme team have monthly meetings with CDP, review quarterly progress updates and invoices, and monthly forecasts. The FCDO programme team also meet monthly with the FCDO CDP contract managers. Both CDP and the World Bank provide annual reports.

There are travel restrictions for UK nationals in many countries where the SRP operates. Currently the FCDO advises against all travel to many parts of the Sahel, with some advice allowing all but essential travel to particular areas. The instability of the region limits the capacity of FCDO and partners to be able to conduct monitoring field visits and gather feedback from beneficiaries on the impact of the programme and recommendations for improvements. However, in 2024, there was a field visit to Mauritania which included a visit 45 kms from the capital city of Nouakchott to meet beneficiaries of the programme. There was also a visit to Chad in 2023 where the programme team were able to meet beneficiaries of the programme.

Evidence

Evidence and learning is embedded in the SRP. The SASPP component generates products to deepen knowledge of the impacts of social protection (for example, on the spill-overs of safety nets in the local economy and the long-term impacts of productive inclusion measures), to provide operational guidance (for example on implementing social safety nets in contexts of Fragility, Conflict and Violence (FCV), as well as the creation of advocacy materials to foster government buy-in and long-term sustainability. The SASPP also benefited from technical partnerships with the Consultative Group to Assist the Poor (CGAP) as well as the FCDO-funded CDP component. CDP worked with the World Bank on the SASPP to support detailed diagnostics (for example, on disaster risk financing landscapes).

Key headline results of the SASPP include:

- In Burkina Faso, 12 to 15 months after the safety net programme ended, participating children had a school enrolment rate 14.3% higher than non-participants
- In Mali, social safety nets increased by 56% the chances that a teenage girl enrolled in school was able to make it into the next grade
- In Mauritania, social safety nets reduced by 25% the proportion of households that could not preserve their health and education expenditure following a shock
- In Chad, the probability of a household often going a day without food has been reduced by 38% due to social safety nets
- In Niger, 18 months after the programme ended, women in a productive inclusion programme saw their incomes increase by 59%-110% and the share coming from non-agriculture activities by 62%-107%
- In Niger, when a drought occurred, beneficiary households maintained their consumption levels, in contrast to non-beneficiaries who had to reduce it by 24%

Learning

The SRP has continued to promote peer learning and knowledge sharing, for example, the SASPP team organised a regional technical workshop on national safety net programmes for government counterparts (another regional workshop is planned for November 2025, focused on payment systems). The SASPP also maintains a website in French and English, where publications are uploaded weekly (over 60 publications during the past fiscal year – www.worldbank.org/saspp). The CDP component also in the process of completing an operational learning and international learning report, which will be shared and discussed with FCDO central team and programme team.

An in-depth evaluation of Phase 2 of SASPP was undertaken to inform the formulation of its Phase 3 along three axes: (1) a partner review which identified programs and approaches which could strengthen and complement ASP in the Sahel and which gathered lessons on the implementation of SASPP’s second phase, (2) the inclusion of case studies on SASPP, on Burkina Faso and on Mauritania in the World Bank-wide evaluation of adaptive social protection carried out by the Independent Evaluation Group (IEG), and (3) an internal SASPP retreat setting SASPP’s ambition and identifying key constraints to the objective of establishing sustainable systems. The analysis pointed to a series of comparative advantages for SASPP – which the team decided to further harness during Phase 3: (1) SASPP’s long standing policy and technical engagement in the six countries, as well as the World Bank’s links with finance ministries and global and national climate actors, (2) SASPP’s technical expertise across all aspects of the agenda, coupled with in-country presence, (3) the ongoing partnerships SASPP has developed with key development and humanitarian partners in the region, including UNICEF, WFP and UNHCR, and (4) SASPP’s ability to complement and build on IDA resources for the expansion of coverage for both regular and temporary programs. In light of these findings, while maintaining a strong focus on strengthening ASP systems and expanding ASP programs, the third phase (2025-2030) will place additional emphasis on (i) ensuring ASP systems’ national ownership and sustainability, (ii) strengthening ASP’s contribution to climate change adaptation and resilience, and (iii) increasing ASP systems and programs’ flexibility in fragile and conflict contexts. The business model – which combines recipient-executed grants with in-country technical assistance and a strong regional knowledge and learning agenda – was maintained and endorsed by all donors for the third phase.

International Climate Finance[7] monitoring
[7] International Climate Finance is a UK government commitment to support developing countries to respond to the challenges and opportunities of climate change: International Climate Finance - GOV.UK

The programme is 60% International Climate Finance (ICF) and reports on the ICF Key Performance Indicator (KPI) 1: Number of people supported by ICF programmes to cope with the effects of climate change.

Date of last narrative financial report	World Bank: 8th September 2025 / CDP: 8th August 2025	Date of last audited annual statement	World Bank: 8th September 2025 (1st July 2024 – 30th June 2025) / CDP: 30th October 2024 (1st January 2023 – 31st December 2023)