## Annual Review Template

Title: Programme d’Appui pour la Consolidation de la Stabilité en RDC (PACS)
Programme Value £ (full life): £16m		Review date:
Programme Code: 300899	AMP start date: / 25/01/2023	AMP end date: / 31/03/2027

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A	A
Overall programme risk rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0002705.odt / DevTracker Programme GB-GOV-1-300899 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003954.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Programme d’Appui pour la Consolidation de la Stabilité en RDC (PACS) is a 4-year £16m programme to reduce violence in the Democratic Republic of Congo (DRC) and support the Government (GoDRC) to deliver national strategies for conflict resolution and prevention. The programme has the following overarching objectives:

Support Government of DRC (GoDRC) efforts to address the persistence of armed groups through mediation and disarmament, demobilisation, and reintegration (DDR), by delivering multi-sectoral stabilisation programming which addresses drivers of conflict at the community level in priority areas and by providing technical and programme support to mediation and the design of DDR initiatives; and

Support GoDRC efforts to deliver its national strategy for conflict resolution and prevention and to prepare for MONUSCO[1] drawdown. Offer technical assistance to GoDRC and international actors to improve the quality and impact of GoDRC and international community investments in conflict resolution.
[1] The United Nations Organization Stabilization Mission in the Democratic Republic of the Congo.

The main programme components and partners for this programme are:

  1. International Alert (IA), which is co-funded with Global Affairs Canada (GAC), the Dutch Embassy and the German Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ), which provides a Conflict Sensitivity Hub (CSH) for training and sharing of conflict and gender sensitivity expertise with humanitarian and development partners operating in eastern DRC (eDRC);

  1. Responsive Stabilisation Through Transition (RESET), a consortium of non-governmental organisations (NGOs) and one UN partner led by Mercy Corps, which delivers governance-centred area-based stabilisation to strengthen local peace and security in eDRC;

  1. United Nations Development Programme (UNDP), who works with our GoDRC partners to support their efforts to resolve the institutional challenges that drive conflict in eDRC and stabilisation interventions in areas under M23 control in eDRC;

  1. Targeted strategic technical assistance and analysis, which this review period included the collection, preservation and verification of conflict data and satellite imagery analysis by the Centre for Information Resilience (CIR) and inception of a project mapping of artisanal mining sites, armed actor presence and illicit mineral supply chains in eDRC by the International Peace Information Service (IPIS).

The programme intended to implement activities in three provinces in the east of DRC, alongside complementary influencing work in Kinshasa: North Kivu, South Kivu and Ituri. During the review period (January – December 2025), UN sanctioned non-state armed group (NSAG) M23[2] captured the provincial capitals of North and South Kivu (Goma and Bukavu) and expanded their territorial control. The meant that large areas of target provinces were no longer under government control during this review period. This necessitated a period of strategic and operational readjustment by all programme partners as well as a review of the theory of change and logframe by the programme team. While this readjustment delayed delivery of workplans, most targets were ultimately met during the review period, demonstrating the flexibility and adaptability of project partners.
[2] March 23 Movement (Mouvement du 23 Mars), a Congolese Tutsi-led rebel paramilitary group.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The PACS programme has scored an overall A in this annual review.

There was mixed delivery across outputs. The stabilisation output and strengthening DRC conflict management and stabilisation strategies output met expectation, while delivery on increasing conflict sensitive programming by Humanitarian, Development and Peace (HDP) actors was moderately below expectations. As the area-based stabilisation output has a 70% impact rating, this mixed performance balanced out as overall score of an A with the programme outputs being assessed as broadly meeting expectations.

While the first two years of the programme were focused on programme design, procurement and inception phases, this review period saw output activities substantively delivered. This is reflected in the increase in ambition in milestone targets in the results framework, as recommended in the previous review, with targets set to deliver reintegration of ex-combatants, socio-economic reintegration of displaced persons, capacity building of state and non-state organisations involved in conflict mitigation and resolution, and support to agricultural cooperatives to improve livelihoods. These targets were all met or exceeded.

During the review period, the escalation of conflict in the east, the break down and reformulation of peace processes and the significant geopolitical and financing shifts in DRC created significant operational challenges for implementing partners. The fact that these targets were met indicates high levels of flexibility and adaptability of implementing partners and interventions, as envisioned by the PACS programme business case. All projects made adjustments to activities and operating areas at the beginning of the review period, as well as conducting assessments to ensure sanctions compliance. This delayed workplans and delivery and required ongoing in-year adjustments. For example, basic training to police officers was cancelled due to delays in the provision of eligible candidates, with budget re-allocated to increased livelihoods support for those at risk of social and economic exclusion. Adjustments were consistently underpinned by ongoing conflict analysis and monitoring and evaluation, including community perceptions, in order to ensure conflict sensitivity of all interventions. A number of conflict sensitivity risks were identified and mitigated through this process, underscoring the need to prioritise this capacity in all adaptive programming modalities in highly changeable and conflict-affected areas.

The Conflict Sensitivity Hub (CSH) moderately underdelivered on its output targets this review period. Delivery of activities was delayed by the need to adjust project operations and the kind of support provided to HDP actors following the escalation of conflict in eDRC. The CSH’s ability to deliver to shorter timelines was impacted by the need to simultaneously fast-track work the CSH’s sustainability strategy, after the UK decided to cease funding to the CSH a year early. With these additional pressures, the team was not able to deliver all activities on schedule, however targets are due to be met by the end of the financial year.

Major lessons and recommendations for the year ahead

Key lessons:
The changes in the political and operating context call into question the sustainability of PACS interventions as originally envisaged. The programme has pivoted to place a stronger focus on short-medium term local stabilisation, which both FCDO, UN and other donor analysis has emphasised is a gap and a key need in the current conflict context in eDRC. These interventions are focused on conflict management: reducing civilian harm by increasing community resilience to conflict through strengthening social cohesion, livelihoods and government-responsiveness where present in target areas. National-level engagement on institutional and root drivers of conflict has continued but its translation to the local level in order to achieve impact within the most conflict-affected areas is likely to remain limited as long as peace processes continue with limited progress. Ongoing de-facto armed group control in the east and the stalled peace processes have undermined ongoing efforts to strengthen government performance and accountability in the provinces and address some of the underlying drivers of conflict through effective DDR and governance reform.

In the last remaining year of the programme, PACS should continue to focus on preventing civilian harm and further deterioration in conflict-affected areas, including through close coordination with other HDP actors. The programme should continue to be adaptive and flexible in identifying opportunities to support more inclusive, sustainable peace processes, as these processes are likely to be where new GoDRC conflict management strategies are rooted. This may require rapid operationalisation in order to take advantage of time-sensitive political opportunities, and PACS should maintain this budget flexibility and increase its programme management capacity in order to facilitate this. The PACS programme should continue to support key governance reform processes engaged in primarily through the UNDP project (namely, land governance reform, local security governance, and livestock management) and use the final year of the programme to assess the impact of this support and future viability, in line with the new FCDO development approach based on partnership.

Recommendations:
1. Increase programme management capacity of PACS, in order to enable greater adaptation and flexibility proportionate to the volatility and risk profile of the conflict and programme interventions.
2. Adjust workplans and outcomes for FY 26-27 in order to ensure a close-out plan which maximises sustainability of PACS interventions and generate lessons learnt to inform future conflict and resilience programming.
3. Assess whether the UK should continue providing funding which supports the activities of the PDDRCS[3] strategy and produce a recommendation for future programming and/or policy engagement.
  [3] The PDDRCS is the Government of DRC’s own DDR and community-based stabilisation programme.
4. Align the next annual review with the reporting and financial year, so that results of indicators with annual reporting can be fully considered.
5. Consider revising the weighting of outputs to reflect any changes in the structure, balance and focus of the programme.
6. As part of project closure and transition to a new, potentially paid-for model, IA should consider how they can more robustly collect, analyse and communicate outcome level results of their activities.
7. The 2:1 ratio for ex-combatant reintegration should be maintained as a minimum. Where the ratio of community members to ex-combatants may be increased, (e.g. 3:1), monitoring and evaluation of this should be prioritised in order to assess whether incremental increases in the community-to-ex‑combatant ratio result in sustained marginal improvements in community acceptance, or whether the effect diminishes after an optimal ratio is reached. This would represent an important contribution to the evidence base for DDR in DRC.
8. The programme should continue to consider how tailoring and adaptation of roles can be made inclusive of women and persons with disabilities as part of all livelihoods work, beyond HIMO.
9. Consider updating Outcome 3 and Output 3 indicators to reflect the specific work being done on land law reform, security sector governance and conflict-sensitive livestock management, currently being delivered by the UNDP project.
Progress against programme-level recommendations from the previous annual review:

2025 AR recommendation	Actions/ progress
Acknowledging the complicated context described above, a theory of change workshop should be run during the first half of next year in order to ensure outcome and impact level statements remain realistic and achievable. This should include consideration of the emerging results and lessons learned from the P-DDRCS pilot projects under the UN SCF funded IOM project and the early outputs from RESET and UNDP.	Achieved/delivered. The programme team held a workshop focused on reviewing the assumptions underpinning the programme theory of change. Findings from the external evaluation of the IOM reintegration project funded by the UN SCF were considered, as well as participation in the PDDRC governance mechanisms, the new Donor Group on Security and Stabilisation, and lessons from RESET and UNDP delivery. The results of this are reflected in the ‘Theory of Change’ section of this annual review.
Ensure budgets for Goma / eDRC-based programming have baselined salary budget lines against the market rate of competing organisations. This should be applied for programming across the embassy.	Not achieved/delivered. This issue was identified during the inception period of the RESET consortium and has since been resolved. The programme team reviews partners’ budgets, including salary costs, on a quarterly basis and will conduct budget analyses against relevant market rates for any future projects with new implementing partners in order to prevent similar issues from arising.
Prioritise appointing a third-party monitor for the programme in Q1 FY 25/26.	Not achieved/delivered. Appointment of a third-party monitor for the programme was not prioritised due to significant contextual changes. However, we did set more stretching milestones for the programme and ensure solid synergies with other stabilisation and nexus actors, which was part of this recommendation in last years’ annual review.
Continue to raise the risks to our ODA budget resulting from limited in-person monitoring visits through programme boards and country boards.	Achieved/delivered: in-person visits have become even more challenging during this annual review period due to the escalation of the conflict in the east. We have continued to review this risk in our quarterly PACS risk register review meetings, and escalate to Programme and Country Boards, where risk appetite and mitigations are discussed on a regular basis.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The PACS Theory of Change states that:

If communities are supported to resolve their internal conflict dynamics in a more transparent, constructive and peaceful manner, their mechanisms for inclusive democratic dialogue and resolution are strengthened, and they are able to benefit from visible ‘peace dividends’ from adopting non-violent means of resolving disputes - then they will be more resilient to negative external political influences which seek to fracture the community along traditional fault lines, which will reduce instances and impact of violence - because the causes of conflict are reduced; because the mechanisms to manage conflict are enhanced; and because the sources of support for peace are increased.

If Congolese and international actors - national and sub-national - focused on supporting stabilisation, conflict resolution and prevention – have access to targeted and specialist expertise and analysis; and if this support is aligned to and elevates larger investment and delivery of coherent national and international strategies - then the quality of interventions and the capacity of national actors to deliver will increase, enabling more sustainable impact from international support – because niche assistance that cannot be provided by other actors (otherwise inaccessible because it is either too specialist or because of long lead-in times) is made available.

If UN agencies, NGOs, policymakers, and donors have the skills and resources to deploy programmes, policies, and strategies that are conflict sensitive and support the development of a humanitarian-peacebuilding-development nexus; and if their efforts are better coordinated and better informed about local contexts - then assistance interventions in DRC are more likely to avoid exacerbating existing tensions, to feed into stabilisation efforts, promote more peaceful management of existing conflicts, and prevent further conflicts - because assistance interventions are more sensitive to conflict drivers in local areas, better adapted to mitigate conflict drivers, and better able to support the development of peace infrastructure.

As the programme delivery got underway, adjustments were made to outcome language in order to better capture the full range of activities being delivered. These changes were as follows:

- Outcome 1: Conflict-affected communities are more socially cohesive, state authority is improved and local conflict is prevented and resolved.
- Outcome 2: DRC’s national strategies for stabilisation are supported and strengthened (financially, technically and programmatically) à DRC's national strategies for conflict management and stabilisation are supported and strengthened.
- Outcome 3: Aid delivery and effectiveness in DRC is increased through more conflict and gender sensitive HDP programming [no change].
These adjustments capture programme work on local conflict resolution and reflect a broadening of programme and policy engagement beyond the PDDRCS to encompass peace processes and other strategies taking shape (for example, strategies for the return of state authority in the east).

As recommended in the previous annual review, a Theory of Change workshop was held during the review period in order to ensure that outcome and impact level statements remained realistic and achievable. A number of the assumptions made for the programme theory of change at the time of its design no longer hold or only partially hold as a result of contextual changes. We judge that this changes the weighting of results we can expect at the outcome and impact level of the theory of change but does not constitute a material change to the programme design. In summary, contextual changes, primarily loss of government control over key areas of planned intervention, have impacted the theory of change in that they have limited the ability of the programme to address long-term structural drivers of conflict such as lack of effective governance and government security and justice provision in M23 controlled areas. However, the UNDP programme has continued to work with the government to develop legislative and regulatory frameworks at the national level, and both UNDP and RESET projects continue to address proximate drivers of conflict at the local level. The programme therefore continues to deliver against all programme outcomes, meaning this is not a material change to the programme.

Programme-level theory of change assumptions have been updated as follows:

- Funding for PACS FY 26/27 remains available.
- The PDDRCS continues to function at a minimum level which enables combatants to be disarmed and demobilised for project reintegration activities.
- The GoDRC retains a commitment to DDR and a political solution to the conflict in the east through peace processes.
- Minimum threshold of security maintained in project areas of implementation and/or programme is able to adapt while still delivering results.
- The GoDRC remains able and willing to engage with project activities dependent on GoDRC action (for example, local service provision on justice and security).
- M23 allows peacebuilding activities, such as reintegration of returnees, to take place within areas under its control.
- The GoDRC allows activities necessary for meeting basic needs in line with sanctions to continue in M23 controlled areas.
- The nature and extent of insecurity do not limit communities’ confidence and capability to engage in conflict management and peacebuilding.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This is the first year of the programme in which delivery of output activities began in earnest. As such, there has been limited demonstration of outcome level results and a clearer picture will be provided at the end of Q4 when reporting on annual outcome milestone targets will be shared by partners. However, there is early evidence that the output to outcome pathways, particularly for outcome 1, are valid. For example, the indicator on level of social cohesion is annual but ongoing perception monitoring in target zones indicates that social cohesion has increased. In Beni, from a baseline of 72% of respondents reporting a high level of social cohesion, this has overall increased to 91.8%, with strong relations within religious groups (95%), sharing economic activities (93%), same ethnicity (88%) and interethnic (85.6%) relations. In Irumu, levels of social cohesion have increased to 94.4% (+19 pts), with strong relations across religion (95.3%), same/other ethnicity (90.6%/87.8%), economic activities (94%) and community leaders (96.6%). As increase in social cohesion is a central component of the theory of change, this is promising for outcome level results for the programme.

Interim reporting on levels of trust in government is more mixed. From an overall baseline of 43% of community members reporting a high level of trust in government, October-December perception data shows strengthening state security legitimacy but persistent customary justice preference and freedom of expression constraints. Customary justice dominates as first recourse (77% preference vs 51% state justice) and is valued for its accessibility (82% good-very good access). Formal justice faces persistent barriers: high costs (49%), distance (48%) and corruption (47%). On community participation in local governance, meeting attendance rose to 68% (+10 pts) and decision-making satisfaction at 60% (good-very good, +3 pts). Local authority performance was rated effective by 60% (+10 pts). On freedom of expression, criticism of authorities most restricted (32% feel free), while minorities (48%), political opinions (46%), and security issues (49%) show moderate freedoms. Social media/public expression remains low at 37%. Output level work on improving local governance through democratic dialogues and support to justice and security provision is therefore showing moderate conversion into outcome level results.

Outcome 2 on strengthened DRC national strategies for conflict management and stabilisation are meeting targets for adoption of new legal, regulatory texts and provincial strategies, demonstrated by the passing of the new Land Law, the national strategy for the prevention of community and customary conflict, and progress on the new Livestock Law, all with support from the UNDP project. Diplomatic access and influence have also shown concrete results in terms of encouraging use of evidence in decision-making on use of multi-donor stabilisation funding. This shows that technical assistance and support is converting into concrete changes to DRC’s national policies and strategies which are central to addressing root drivers of conflict, such as those related to land use and governance. The next targets for this outcome should measure the effectiveness of the implementation of these policies at the national and provincial level. While strong results may be possible in Ituri, this will not be possible in North Kivu and South Kivu as long as M23 continues to control the provincial capitals and significant territory. The programme should consider whether these reforms can be introduced as part of return of state authority strategies developed by the GoDRC and as part of peace processes.

Outcome 3 is delivered through CSH activities. The CSH will report on the number of organisations that have improved the delivery of their support through the integration of conflict sensitivity at the end of the project (now set for June 2026). Quarterly reporting has provided some anecdotal evidence to support outcome pathways as a result of trainings and technical assistance, such as feedback from participants on the relevance and quality of trainings and that they were well understood with high levels of engagement. These are indications that the likelihood of take-up is good. Dissemination of the recommendations of the MONUSCO withdrawal research and the subsequent reflection of these recommendations in the renewed mandate also suggests that the CSH research may have directly influenced MONUSCO tasking by member states. However, overall outcome level reporting from the CSH has been weak. As IA considers future options for the CSH, including a paid-for model, they should consider how they can more robustly collect, analyse and communicate outcome level results of their activities.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme should continue. Peace and stability remain a priority for the UK in DRC. The deteriorating conflict context means that contributions to strengthen DRC conflict strategies and improve conflict prevention, management and response at the local level have increased in importance during the review period. The programme has demonstrated that it has the capability to adapt to significant contextual changes, while still delivering against its theory of change. The final year of the programme represents an important opportunity to gather evidence on outcome pathways to inform future UK interventions in DRC, as well as meet outcome targets to improve social cohesion and state-citizen relations in vulnerable target areas.

## C. DETAILED OUTPUT SCORING

Output Title	Stabilisation and DDR activities in line with the PDDRCS are implemented in target communities.
Output number:		1	Output Score:	A
Impact weighting (%):		70	Weighting revised since last AR?	Yes, increased by 10%

Indicator(s)	Milestone(s) for this review	Progress
1.1 # of ex-combatants targeted with reintegration activities through programme interventions, disaggregated by location, gender, age, status, ethnicity, and persons with disabilities.	300	Achieved - 306 ex-combatants participated in High-Intensity Labour Works (HIMO), contributing to the construction of 54km of feeder road rehabilitation across 8 sites in Beni, North Kivu.
1.2 # of returnees socio-economically reintegrated into communities (disaggregated by sex and age group)	1000	Achieved - 40 community structures supported with reintegration, representing approximately 1000 beneficiaries across North and South Kivu.
1.3 # state and non-state institutions supported in conflict mitigation and resolution capacities through programme interventions, disaggregated by project	109 / UNDP: 30 / RESET: 79	Achieved - 103 (95% of milestone) / UNDP: 24 / RESET: 79
1.4 # of stability dividend actions from plans co-produced and co-invested by the State and the community through democratic dialogue undertaken by authorities	80	On track - 40 (50% of milestone) / Evidence is drawn from the partner logframe which has an annual milestone according to the financial year ending March 2026. The remaining activity to support delivery is scheduled for Q4 and so this milestone target is on track.
1.5 # of at-risk populations (especially women and youth) reached by support to agricultural cooperatives (disaggregated by location, gender, age, status, persons with disabilities)	420	Achieved – 435

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme achieved or exceeded target reintegration milestones for all categories of targeted beneficiaries: ex-combatants, returnees (internally displaced persons returning to their place of origin) and women and youth at risk of social and economic exclusion. Targets for capacity building of state and non-state authorities involved in conflict management and response were also met. 40/80 local actions were taken on priorities identified in stability action plans, jointly developed by authorities and communities through project-supported democratic dialogues. 80 actions is a FY 25-26 target with significant delivery planned for Q4, outside the scope of this annual review. This target is also therefore on track.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major changes were made during the review period. However, a number of adjustments to this output were made to reflect contextual changes and finalisation of milestone targets following the end of the inception period last year.

Due to the capture of Goma and Bukavu at the beginning of 2025, RESET and UNDP projects needed to update operational and delivery plans at the beginning of the review period. Project logframes also needed to be updated to reflect the new delivery locations and ensure contextually relevant milestone results for project indicators. However, this did not require major changes to project logframe indicators, as outputs (types of activities delivered and outcome pathways) remained consistent with what was planned during inception periods.

As recommended in the last annual review (recommendation 3), programme logframe milestones for this annual review period and outer years of the programme were already intended to be finalised and agreed at the beginning of this year following project inception periods last year. This was done in the first half of this annual review period, reflecting changes and adaptations as a result of the change in context. As part of this, the weighting of this output was increased to 70%, to reflect that the increase in armed conflict required a stronger emphasis on stabilisation interventions prioritising community resilience proportionally to addressing long-term structural drivers of conflict (primarily reflected in Output 2). Output indicator 1.2 was updated to capture increased effort to reintegrate internally displaced persons as part of the wider migration crisis in the east resulting from the conflict. Two additional output indicators were also added (1.3 and 1.4) to ensure the programme level logframe captured non-reintegration stabilisation activities such as building local conflict resolution capacity, enhanced delivery of targeted basic services (security, justice and natural resource governance), and access to sustainable livelihoods for vulnerable, conflict-affected populations were sufficiently captured.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2025 AR recommendation	Actions/ progress
Acknowledging the complicated context described above, a theory of change workshop should be run during the first half of next year in order to ensure outcome and impact level statements remain realistic and achievable. This should include consideration of the emerging results and lessons learned from the P-DDRCS pilot projects under the UN SCF funded IOM project and the early outputs from RESET and UNDP.	Achieved/delivered. The programme team held a workshop focused on reviewing the assumptions underpinning the programme theory of change. Findings from the external evaluation of the IOM reintegration project funded by the UN SCF informed this, as well as participation in the PDDRC governance mechanisms, the new Donor Group on Security and Stabilisation, and lessons from RESET and UNDP delivery. The results of this workshop are reflected in the ‘Theory of Change’ section of this annual review.
Ensure budgets for Goma/ eDRC-based programming have baselined salary budget lines against the market rate of competing organisations. This should be applied for programming across the embassy.	Not achieved/delivered. This issue was identified at an early stage of implementation within the RESET consortium and has since been resolved. The programme team reviews partners’ budgets, including salary costs, on a quarterly basis and will conduct budget analyses against market rates for future projects in order to prevent similar issues from arising.
Revise the results framework in Q1 FY 25/26 to reflect the operationalisation of the stabilisation component.	Achieved/delivered. See above section on output changes during this annual review period.
RESET should be closely coordinating with other stabilisation entities and coordination structures in Goma should be speaking regularly.	Achieved/delivered. RESET successfully set up a steering committee for the project, with consortium members, FCDO and GoDRC (PDDRCS National Coordinator) to ensure regular communication with ministerial-level GoDRC representative for stabilisation and PDDRCS. RESET has taken on a leading role on partner coordination, leading a monthly coordination meeting for peacebuilding, transition and stabilisation actors in DRC, with regular participation from around 25 NGOs and UN agencies. RESET has also progressively improved coordination with other PACS partners. This will culminate in a National Forum on Peace and Stability in eastern DRC in March 2026 jointly organised and co-hosted by RESET and UNDP, the other key stabilisation implementation partner for the PACS programme.

Learnings:
- Several authority-led actions and justice/economic workstreams required rephasing into late Q4 due to municipal/judicial calendars and security constraints. Seasonal economic interventions are particularly at risk if delivery falls behind schedule.
- The conversion rate from dialogue to state-action can sometimes be slower than anticipated. Good progress on institutional capacity cannot always be relied upon to consistently convert to documented authority-led actions at the planned pace. Regardless, early project evidence suggests that dialogue à authority commitments à delivery results are more durable than standalone project interventions or grants. There is early evidence that interventions anchored in local authorities and existing structures, such as (local security committee (CLSP) roadmaps and acts of commitment from authorities) improved local engagement, reduced contestation, and improved relations between local state actors and key demographics with whom relations were previously fraught (i.e. youth).
- While ex-combatant reintegration targets were met, these were significantly delayed during the reporting period due to delays in receiving accurate lists of eligible combatants from the PDDRCS. Original lists were divergent or contained duplicates and so had to be re-verified by IOM and local authorities. Time therefore needs to be built-in to allow for the need to reverify lists and potential delays in biometric registration by PDDRCS.
- Some ex-combatant settlement location preferences unexpectedly fell outside of initial project delivery geographies. This had financial, operational and conflict sensitivity considerations for the project, which needed to adapt delivery plans to ensure that additional community members were sensitised to ex-combatant return and included in economic livelihood opportunities.
- There is early evidence that mixed cohorts in high-intensity labour works (HIMO) with a 2:1 ratio of at-risk civilians to ex-combatants reduced stigma, diffused “benefit resentment” and bolstered community buy-in. This was also strengthened by project collaboration with host communities on ex-combatant verification and development of selection criteria for beneficiaries.
- Adaptation of roles as well as quotas were used to allow women and persons with disabilities to participate in HIMO from which they are ordinarily excluded. For example, some HIMO beneficiaries provided childcare or support services to construction workers. This was successful and demonstrates that task diversity and practical accessibility should be used to improve inclusion, in addition to quota targets.
- Basic training was originally planned for 120 new police recruits in Irumu (Ituri) at part of the project outcome 4 (government-led stability) workstream. This activity was cancelled because the programme team was not content that the GoDRC would provide lists of eligible trainees with sufficient time to deliver training, spend and subsequent community policy support activities within the programme lifetime. This demonstrated the likelihood of unexpected delays and therefore the need to have sufficient programme budget and timeline flexibility to deliver these kinds of activities.
In-year adaptations in response to these learnings:
- A detailed tracker was created to map the dialogue commitment à authority action à evidence link, which was used to create a clear evidence base, provide accountability and unblock issues with local authorities.
- Agricultural support preparatory actions, such as land-use security, fencing, cooperative capacity building and business planning, were frontloaded to ensure scale-up of agricultural planting support remained possible within the financial year and growing season.
- Budget and operational flexibility were built-in to account for potential additional settlement locations for ex-combatants, which required additional transport, family tracing and local community sensitisation in advance of reintegration.
- The RESET programme team presented a number of options to the programme team for reallocation of budget intended for police basic training. Based on conflict evidence and analysis, this budget was reallocated to increase support to sustainable livelihoods for at-risk community members.
Recommendations this year:
- 2:1 ratio for ex-combatant reintegration should be maintained as a minimum. Where the ratio of community members to ex-combatants may be increased, (e.g. 3:1), monitoring and evaluation of this should be prioritised in order to assess whether incremental increases in the community-to-ex‑combatant ratio result in sustained marginal improvements in community acceptance, or whether the effect diminishes after an optimal ratio is reached. This would represent an important contribution to the evidence base for DDR in DRC.
- The programme should continue to consider how tailoring and adaptation of roles can be made inclusive of women and persons with disabilities as part of livelihoods work, beyond HIMO.

Output Title	GoDRC and other key stakeholders have access to expertise and capacity building and are better coordinated on peacebuilding efforts and peace processes
Output number:		2	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 # of instances of UK lobbying or technical input to PDDRCS, GoDRC peacebuilding efforts and peace processes	3 instances	Achieved – 4 instances / UK lobbying for allocation of remaining SCF funds to the rapid response mechanism, based on evidence that rapid stabilisation interventions are a gap in the current conflict context. / UK lobbying to encourage coordination between the PBF, WB and AfDB on support to the government to improve its peace governance architecture. / UK lobbying on SCF support for FDLR returns resulted in addition of human rights risk monitoring as part of risk management strategy. / Detailed technical feedback provided on proposed new PBF portfolio level results framework, intended to better measure cumulative effect of PBF projects on conflict and fragility, as well as the Fund’s responsiveness, agility and catalysing effect.
2.2 # of instances of UK supporting use of evidence and analysis to inform PDDRCS and peace processes	3 instances	Achieved – including: / UK engagement on limit of one year extension and responsible closure of the SCF, based on evidence generated by the external evaluation. / CIR incident verification and mapping of areas of territorial control have informed UK diplomatic engagement.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme has achieved its targets for the reporting period, with UK using evidence and analysis to inform engagement. While targets were achieved at output level, it was challenging to translate these into outcome level results due to lack of certainty and coherence of both the national and international approach for conflict management in DRC, including ongoing peace processes.

This reporting year the UK remained one of a small number of key primary donors (UK, Sweden, Switzerland, Germany, EU) in the peace and security space in DRC. While other international donors are more involved in defence and security partnerships (Belgium, France, EU) and in facilitating peace processes (US, Qatar), the UK remains a primary partner taking a nexus approach to conflict prevention, management and resolution at the local level. BEK personnel continued to advocate for this approach in key multi-donor funds, steering committees and working groups, including the Peace and Security Working Group, the Peacebuilding Fund Steering Committee, the Stabilisation and Coherence Fund governance structures and the newly formed Groupe Inter-Bailleur (GIB) Security and Stabilisation, as well as engaging with the International Financial Institutions (World Bank, African Development Bank) on their conflict prevention and resilience strategies.

The UK leveraged the evidence generated by the PACS portfolio to advocate for more effective peace and security policy and interventions. Regular conflict analysis produced by RESET, UNDP and the CSH provided evidence that in the most conflict-affected areas in the east, high-value economic interventions such as infrastructure construction and long-term initiatives to improve governance and conflict resolution structures carried significant conflict sensitivity and contextual risks, as a result of high levels of armed group activity, population movements, criminality and social tensions. In this context RESET interventions adapted to focus on dialogue, mediation, trust-building and communication interventions to address immediate tensions as a necessary pre-requisite ahead of any large-scale economic injections. The UK used this evidence to successfully advocate for the Stabilisation and Coherence Fund (SCF) to reprioritise remaining budget and allocate this to the Rapid Response Mechanism, which is able to make short-term stabilisation interventions designed to address short-term drivers of conflict and instability, creating a bridge for longer-term interventions.

The UK also used technical expertise to advocate for a more human-rights compliant approach to FDLR repatriation supported by the SCF. In addition the UK championed and demonstrated use of evidence for peace and security interventions in all donor coordination mechanisms and government engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major changes were made but language was adjusted following the theory of change workshop. The “GoDRC and other key stakeholders have access to expertise and capacity building and are better coordinated on PDDRCS” was changed to “…on peacebuilding efforts and peace processes”. As outlined in the previous annual review, the PDDRCS has faced significant institutional, political and contextual challenges. These have increased during this review period (see Theory of Change section for detail). As such, UK expertise and programming has continued to engage with the PDDRCS but has also diversified its stakeholders to better reflect the reality of where conflict policy, influence and finance is rooted in DRC systems. The corresponding indicators have also been updated to capture UK advocacy and use of evidence to inform peacebuilding and peace processes, as well as PDDRCS. In future financial years, a more realistic and comprehensive indicator of UK security and stabilisation evidence-based diplomacy should also measure specific UK engagement with land law reform, security sector governance and conflict-sensitive livestock management, currently being delivered by the UNDP project.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

All targets for this output were met by PACS within the reporting period. However, a number of activities did not progress as anticipated and/or generated learnings that the programme should apply in future.

No specific output recommendations from the previous Annual Review.

Recommendation: Consider updating these output indicators to reflect the specific work being done on land law reform, security sector governance and conflict-sensitive livestock management, currently being delivered by the UNDP project.

## C. DETAILED OUTPUT SCORING

Output Title	Increased and improved access to training and materials that facilitate conflict sensitivity of partners (analysis, toolkits, etc)
Output number:		3	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 # of conflict analyses, synthesis notes or toolkits/ research databases produced	5 (target for March 26)	2 / - Land conflict research (delivery date: 25 March 2026) / - Involuntary returns – (delivery date: 31 March 2026) / - Lake Albert – (delivery date: 31 March 2026) / - Technical notes on integrating CS with FONGI and OCHA (1/2 completed) / - MONUSCO withdrawal research (completed)
3.2 # of organisations/HDP actors that have participated in targeted technical support activities	35 (target for March 26)	13 / A workshop was organised in Ituri, from 27 to 28 November 2025, with 13 organisations, for the development and updating of a guidance note intended for the Cash Working Group (CWG). / 4 specific training sessions were organised in the provinces of Ituri, Tanganyika, and South Kivu to prepare for the provincial meetings.

Briefly describe the output’s activities and provide supporting narrative for the score.

The CSH was in part based out of offices in Goma and Bukavu, both captured by M23. While the overall output remained the same, the activities and workplan of the CSH for FCDO-funded activities were therefore delayed and shifted in response to the change in context, both the intensification of conflict and widespread budget cuts to HDP actors. This created a significant operational challenge, including rapid work to ensure sanctions compliance. The conflict sensitivity needs of HDP actors also changed significantly in response to the change in conflict dynamics and wider funding reductions by partners. The CSH pivoted to meet these needs, for example for increased work with stakeholders involved with humanitarian cash distribution and research on land conflict and displacement. This was in line with the objectives of the FCDO contribution to the fund, which focused on outputs on research and its dissemination; support to platforms and coordination groups of HDP actors to influence strategic and technical thinking; flexible funds for specific support to high-risk areas; specific support to HDP actors responding to the North Kivu crisis, through coordination with the UN Humanitarian Coordinator’s office and OCHA (UN Coordination Office for Humanitarian Affairs); and support to sustainability of the CSH.

3.1 – Research

This year the research on the impact of the MONUSCO withdrawal from South Kivu in 2024 was finalised. Dissemination and discussion of findings included embassies, donors, agencies, NGOs and the UN Resident Coordinator’s Transition Team, as well as GoDRC stakeholders such as the Technical Secretariat for the MONUSCO transition. Discussions identified specific, evidence-based recommendations to inform future interventions, such as the need to include local security committees in post-withdrawal analyses in order to anticipate risks and as part of post-withdrawal local security governance management.

Ahead of MONUSCO’s mandate renewal in 2025, the CSH met with stakeholders in Kinshasa so that the report’s findings on how better to prepare for withdrawals could inform plans for potential changes to MONUSCO’s geographic footprint as part of the new mandate. The new MONUSCO mandate reflected a number of recommendations from the research report, notably the importance of preparing ahead of withdrawal, involving civil society earlier and preparing GoDRC institutions for transition. This suggests that dissemination of findings with key stakeholders may have had a direct impact on mandate renewal. It also informed the UK engagement.

Three other pieces of research were planned for delivery this year: research on the impact of involuntary returns on the lives of displaced persons, research on land conflicts and HDP interventions; and conflict analysis on the Lake Albert area to inform conflict-sensitive responses. The first two pieces of research were new and in response to HDP actors needs following the escalation of the conflict in the east. The timelines for this research were shifted later in the financial year as a result of the additional pressures on the CSH from the initial conflict response and the need to fast-track their sustainability strategy. These research products are all due to be finalised within the calendar year but this will now take place in Q4 of FY 25-26, outside the scope of this review period.

Development of technical notes to support the integration of conflict sensitivity into high-level policy development with FONGI (Forum for International NGOs) progressed throughout the review period, with one completed for Ituri and two more planned for South Kivu and North Kivu in Q4. Strategic meetings were held with both FONGI and OCHA to define priority areas for the development of technical notes and key actions identified to strengthen conflict sensitivity in humanitarian coordination policies and strategy. These notes will serve as a reference to guide high-level discussions, harmonize inter-agency practices and ensure that humanitarian, development and peace interventions are adapted to local dynamics and contribute to social cohesion.

During the review period, the programme brought on two additional partners to provide conflict research and analyses: CIR and IPIS. CIR provided high quality conflict monitoring and incident verification. CIR reporting and analysis provided the programme management team with up to date knowledge of the situation on the ground, vital for managing programme risk. Analysis was also shared with key international partners in order to promote a conflict sensitive response by the wider international community. IPIS successfully completed its inception activities in order to start collecting data on artisanal mining sites and armed group presence in Q4 of FY 2025-26.

3.2 Technical support activities

The CSH focused on technical support to strengthen the capacity of Cash Working Group (CWG) in Bukavu, Bunia and Kalemie to integrate conflict and sensitivity into their humanitarian cash interventions. Four training sessions and sectoral workshops were delivered in Ituri, Tanganyika and South Kivu, tailored to the specific needs of HDP actors: conflict sensitive planning (31 participants, 10 women); conflict-sensitive cash transfers (over 110 participants, from 15 organisations); and basic training on conflict sensitivity. Strong participant feedback was provided on the quality and relevance of the training. Ongoing monitoring and evaluation should ensure that outcome level results from these trainings are collected and assessed.

Sustainability strategy

Our support to the CSH was intended to fund development of a blueprint for the sustainability of the CSH, setting out options and pathways for moving beyond bilateral donor funding. A key assumption for our contribution to the CSH was continued funding by the UK and other current donors to the CSH. In the course of this review period, it became clear that other donor contributions were coming to an end and not being renewed, as a result wider funding cuts. The decision was taken to end the FCDO contribution to the CSH after FY 25-26. This will result in the closure of the CSH in its current form. The CSH sustainability strategy will be finalised in 2026 and the BEK programme team should continue to work closely with the CSH and the other donors to ensure maximum value for money from our contributions to the CSH and continued availability of conflict sensitivity advice and support to HDP actors as much as possible in the context of globally reduced resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to Output language this year. An additional indicator was added at programme level, to capture technical assistance and capacity building delivered with FCDO funding, as well as research and conflict analysis captured in 3.1. This does not constitute a major change as this indicator measures the desired output as previously stated.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2025 AR recommendation	Actions/ progress
8. Consider a monitoring visit with the CSH as a priority in the next reporting period, ideally to observe trainings, along with other donors. Hearing from beneficiaries in sectoral working groups would be highly informative.	Not achieved. This recommendation was not achieved for a number of reasons. Firstly, the conflict context in the east prohibited BE Kinshasa from visiting most of the CSH delivery locations. Secondly, significant UK and other donor capacity in relation to the CSH was taken up with change management, in particular early closure of the CSH and its sustainability strategy. Thirdly, once we had reached a decision to close our contribution to the CSH, a monitoring visit was judged not to be the most effective use of team capacity. The programme team compensated for the lack of capacity to conduct a monitoring visit by requesting feedback on CSH partnership from beneficiary organisations, such as Give Directly, and cross-referencing this with their reporting and information shared with other donors. We also increased the rigour of reporting on outcome level results in quarterly reports, and held multiple dedicated meetings with the CSH team to understand the evidence-base at this level. The project closure process should include a robust assessment of outcome-level results from the CSH, so this can inform future conflict sensitivity interventions both in DRC and globally.

The key lesson learnt this year was the need for clear expectation management on reporting, including on monitoring and evaluation, for projects funded by multiple donors. While the CSH was intended to be a multi-donor Hub, efforts to co-finance were not successful (see previous annual review recommendations). All donors moved to bilateral grants, which placed a significant management burden on the CSH and varying quality in reporting. While the Canadian grant continued to receive robust reporting, including monitoring and evaluation of outcome-level changes, it continued to be a challenge to receive this as part of UK grant reporting. This made the evidence base for CSH claims sometimes unclear and limited our understanding of the FCDO contribution’s impact and outcome pathways. For any future interventions, moves to multiple donor bilateral grants should be accompanied by a shared or more clearly complementary monitoring and evaluation plan to ensure consistency and quality for all donors.
## D: VALUE FOR MONEY

Key cost drivers and performance

During the reporting period, several contextual factors reduced the programme’s overall value for money. As discussed throughout this report, M23’s expansion in early 2025 required reprogramming activities, resulting in lost time and additional expense as preparatory work was undertaken to implement activities in different locations. Further, the conflict disrupted partner supply chains and restricted the movement of personnel, especially in M23-controlled territory. Finally, these developments resulted in inflation, putting additional pressure on budgets.

Despite these changes in the external context, partners continued to seek out opportunities to strengthen value for money, through their financial and project management systems, as assessed at proposal and due diligence stages. To take the example of RESET, they were able to produce cost savings through the joint planning of activities with local authorities, enabling them to use venues without paying rent. RESET achieved greater efficiency by consolidating nine partner-radio contracts under a single performance-based agreement, reducing administrative costs by 18% and ensuring continuous broadcasting of peace and governance messages. They maintained effectiveness by taking an adaptive approach to project management, using the data gathered from their early warning network and sentiment analysis to assess and adapt their approach. The area-based project approach enabled RESET to invest in relationships with local authorities and ensure a politically-informed approach.

International Alert and RESET have gender analyses which identified barriers to women’s inclusion in programme activities and how to address these (for example, RESET took measures to enable breastfeeding women to attend events). International Alert, RESET and UNDP organised activities specifically addressing gender, for example UNDP supported women-led peacebuilding community initiatives and developed six gender-based violence prevention action plans. Partners typically provided disaggregated data, however it was not always possible to achieve gender parity. Women typically made up 30 – 50% of participants in project activities, from training on conflict sensitivity to ‘cash for work’ livelihoods activities. RESET have set a minimum 30% participation quota for their activities.

The programme has been less successful at being disability inclusive, with only RESET providing some results disaggregated according to disability status, with a relatively low reach (for example, in Beni, 2% of participants in RESET-supported activities were persons with disabilities.

VfM performance compared to the original VfM proposition in the business case

You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 5 E’s of FCDO’s value for money framework – economy, efficiency, effectiveness and equity (including gender equality, disability inclusion, LGBT+ and other equality considerations), and overall cost-effectiveness. Referring back to the relevant text in the approved Business Case’s Strategic Case and agreement with the implementing partner(s) may be relevant.

Where an emissions assessment and shadow carbon pricing were required for the original appraisal case, this will need to be periodically reviewed and updated during implementation. Any review or updated estimates of emissions, and any implications these have on value for money once shadow carbon pricing has been applied, should be included here.

The PACS business case proposed to ensure value for money by:
- Reducing the geographical and thematic focus of the programme therefore maximising the potential impact of the UK’s inputs and influence;
- Keeping the total number of components and partners at a level which is manageable for the existing BEK Humanitarian, Peace and Stability team;
- Limiting the number of selectable delivery partners to only those with the strongest ability to deliver quality programmes in their area of expertise and mitigate risks effectively;
- Spreading and pooling risk and resource; and
- Capitalising and building on investments made under the previous PSP programme.

The changes to the programme over the last year have continued to focus the programme on areas of greatest value for money, maintaining a tight geographic scope and terminating activities, such as basic training of police that which significantly expanded project time and cost without delivering the intended outcomes. Further, the loss of other donor funding to the CSH meant that the VFM proposition of the hub reduced and this component of the programme was closed.

The addition of UNDP as a delivery partner, and two research partners under the technical assistance output, posed a risk to the team’s ability to manage the PACS programme with current resource. However, the decision to cease funding to the CSH will reduce this pressure.

Assessment of whether the programme continues to represent value for money

As assessed in Section B, the programme aligns with the UK’s objectives over the period in DRC, seeking to improve conflict prevention, management and response at the local level. The programme has adapted to the external context and taken steps to focus on the highest value for money components of the programme. The programme represents value for money and has presented sufficient evidence to continue.

E: RISK

Overview of risk management

The overall risk rating for this programme remains major and have been monitored and managed over the reporting period as set out in previous sections. Across all categories, 8 risks have a moderate residual risk rating, 2 are major and 2 are severe. All risks for this programme remain within the business case risk appetite.

Overview of key risks per categories:

Strategy and context risks rose from major to severe during the reporting period. This increase is due to the escalation of the conflict, in particular the expansion of M23’s territorial control. The deteriorating security situation forced PACS partners to reprogramme and adapt to the new operational environment. Uncertainty regarding UK funding and the reduced budget for PACS in FY 25/26 required the programme to adapt its theory of change.

Policy and programme delivery risk remained major throughout the reporting period. Although all partner projects are now operational, delivery risks continued to be driven by external factors. M23’s capture of large areas of eastern DRC and escalation in other conflict dynamics has significantly affected partners’ ability to operate in several targeted areas. In addition, potential limited partner M&E capacity as well as travel restrictions have reduced UK’s direct oversight and increased the likelihood of performance issues going undetected. To mitigate these challenges, PACS has reprogrammed activities where it was no longer possible to deliver them, had already selected partners with strong access networks across all targeted zones, and continues to monitor access issues. The BEK team has also provided information to partners on compliance with the UK’s sanctions regime as they navigate operating in areas under the control of de facto authorities.

PDDRCS remains a key partner for the ex-combatant reintegration component of the programme, but low PDDRCS capacity remains a delivery risk. This manifested within the review period as delays in providing demobilised combatants to programme partners to participate in reintegration activities. This was mitigated through deepening relationships with PDDRCS structures at the provincial level, collaboration with MONUSCO human rights section on vetting, and increased conflict sensitivity mitigations for delays to workplans. These mitigations have been successful and targets for ex-combatants were met this review period.

PACS has a moderate risk of worsening conflict dynamics precisely because it targets the systems, institutions and actors that are responsible for peace and security. It mitigates this risk through ensuring all partners have a conflict sensitivity plan and that each project’s impacts on conflict dynamics are monitored, reported on and discussed with FCDO.

PACS faced a high level of financial and fiduciary risk, which rose from moderate to major during this reporting period. There was a major risk of loss of value for money due to external economic factors. This risk is driven by:
- The appreciation of the Congolese Franc, which has raised the cost of operating in DRC and reduced partners’ ability to deliver activities, thereby lowering overall VFM.
- The escalation of conflict in eastern DRC and the effects of the government imposed banking restrictions in M23‑controlled areas, which have led to rising prices for goods and services.

To mitigate these increasing risks, the BEK team engaged with partners and encouraged them to adjust project expectations to better absorb these changes. The projects’ delivery chain maps also provide a comprehensive understanding of the flow of funds across all components.

DRC remains a high‑risk environment for fraud, corruption, and aid diversion and this is a moderate risk for the programme. As part of the due diligence process, partners’ financial systems were assessed to reduce the risk of misappropriation or loss of funds. We also requested the most recent audit reports from partners to evaluate their financial robustness. Partners were formally reminded of their obligation to report any suspicions of fraud to FCDO immediately. This issue is also regularly discussed during quarterly partner meetings.

Safeguarding risks concerning do no harm posed a moderate risk to this programme.
The DDAs for the three active projects are already in place. Follow‑up actions, including a review of safeguarding standards for the two largest projects, were carried out during the year. All partners were also formally reminded of FCDO’s zero‑tolerance policy and their obligation to report any safeguarding concerns immediately. This issue was also regularly communicated to partners during the quarterly meetings.

The Embassy continues to assess that the programme has a moderate risk of negatively impacting on the climate and environment.

The programme continues to promote women’s participation in peace and security governance structures, engages with women’s organisations, and addresses barriers to women’s participation in project activities. Partners provide gender and disability disaggregated results.

During the reporting period, the programme team followed up on partners’ DDA recommendations, with a focus on the following key partners:
- UNDP: Progress on fraud-related recommendations rated as major in the DDA.
- Mercy Corps: Progress on the implementation of all recommendations.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

During the review period, with all agreements in place, efforts were primarily focused on project implementation. This phase proved challenging for partners due to the presence M23 in some of the areas where PACS projects were meant to be implemented. This situation had significant impact on the performance of all implementing partners.

Although project implementation was underway during the review period, the escalation of the conflict in early 2025 and M23’s expansion of control necessitated reprogramming, which had a significant impact on financial management.

Performance of partnerships and reporting

International Alert	FCDO’s contribution to the CSH will end on 30 June 2026, 9 months earlier than initially planned. International Alert’s quarterly reports were consistently on time, and they were responsive to ad hoc requests. However, the partner consistently spent less than forecast, in part caused by security constraints in eastern DRC. / Some revisions to financial reports were required. BEK organised a meeting to reiterate FCDO’s financial reporting requirements.
Mercy Corps	As PACS largest partner, Mercy Corps was significantly affected by the M23 situation in the East which required an adaptation of the project’s geographic focus to align with evolving situation on the ground. Although the partner experienced various levels of spend throughout the reporting period, overall implementation remained on track. / Mercy Corps submitted quarterly reports on time and incorporated FCDO’s recommendations to improve the clarity and presentation of these reports. The team also demonstrated responsiveness to numerous ad hoc requests. / Regular catch-up meetings with RESET team to monitor the project continued; the frequency of these meetings was adjusted from fortnightly to monthly. Collaboration issues between Mercy Corps and IOM (consortium member) have improved over the same period.
UNDP	Similarly, UNDP’s project required significant reprogramming of activities due to the M23 expansion, which resulted in implementation starting only in FY 2025/26. Our collaboration with UNDP was satisfactory, however there were some delays in submitting a revised logframe and minor revisions to financial reports were required. / The partner submitted narrative and financial reports either on time or with only slight delays. There are opportunities to improve the clarity of reporting, including ensuring the narrative supports understanding of progress towards outcomes and is consistent with the logframe, which are under discussion with the partner.
Centre for Information Resilience (CIR)	BEK contributed to the CIR through a centrally managed programme starting in August 2025. Programme management is largely the responsibility of the central programme team, however outputs relating to DRC have been delivered in a timely manner to an appropriate standard.

Financial Management

During the review period, £ 3,798,040.74 was disbursed across all project components. The capture of Goma in January 2025 by M23 followed by the takeover of Bukavu had a significant impact. Partners were unable to implement planned activities in these locations and were compelled to revise their workplans and adjusts their budget forecasts.
Throughout the period, the PACS team maintained close engagement with all partners through regular meetings and email communication to remain informed of progress against workplans and to monitor budget utilisation.

Commercial management

In August 2025, the team began contributing to the Centre for Information Resilience (CIR)’s monitoring and verification of conflict-related incidents in eastern DRC. The project provided timely information and evidence. The team is satisfied with the added value that CIR’s work provides and is considering continuing its contribution in FY 2026-2027.

Assets management

Asset management is discussed with partners during quarterly check‑ins and by email. Although some partners have relocated part of their staff to Kinshasa, most assets remain in the eastern part of the country. BEK relies on partners to conduct asset checks and submit their asset register to FCDO, however virtual asset spot checks are being considered for the largest project to provide additional assurance, along with an in person visit.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

During this second year of implementation, the programme team was unable to conduct field visits to the East due to the fighting around Goma. Consequently, more meetings were organised with partners to monitor developments. The temporary relocation of partners along with the increased frequency of partner visits to Kinshasa, made it possible to hold more in‑person meetings.

The Annual Review was conducted by the BEK programme team, drawing on the information submitted in partner quarterly reports and gathered through regular meetings.

Evidence

Partner monitoring, learning and evaluation processes are expected to generate evidence over the course of the programme. However, given disruption to original programme the programme timeline, partners are beginning to generate outcome-level data and so any additional evidence generated will be reporting in later Annual Reviews and Project Completion Report.

Learning

All projects under the PACS programme are led by the British Embassy, with the exception of the CIR contribution, which is managed centrally. The PACS team has recognised the challenges of financial management when disbursements are handled at the central level. As a lesson learned, the team will work more closely with the central team on payment scheduling and disbursement.
In the programme’s final year, and as the Conflict Sensitivity Hub closes, we aim to gather lessons from PACS for the benefit of humanitarian, development and peace actors in DRC and other contexts.

Date of last narrative financial report	Mercy Corps: 02 Feb 2026 UNDP: 06 Feb 2026 / International Alert: 16 Jan 2026	Date of last audited annual statement	Mercy Corps: Dec 2025 / UNDP: Jan 2025 / International Alert: Jul 2025