## Annual Review

Title: Standards Partnership
Programme Value £ (full life): £35m (original budget) - Final outturn is likely to be under £10m		Review date: / 08/07/2025
Programme Code: / 300903	AMP start date: / 18/06/2020	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A+
Risk Rating	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005973.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004927.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Access to new markets can depend on a country’s ability to implement international standards. Improving a country’s approach to standards and technical regulations serves as a catalyst for economic growth and sustainable development, stimulating the upgrading of supply chains, improving skills, job opportunities and environmental practices.

The Standards Partnership (SP) Programme increases the capacity of developing countries, mainly utilising Official Development Assistance (ODA) funding to use international standards to enhance trade and boost sustainable and inclusive growth. This will increase economic stability, decrease aid dependency and, as a secondary benefit, the programme will also open trade opportunities for international businesses, including from the UK.

The programme Business Case was approved in 2020 (originally under the name:- UK Standards and Quality Partnership). The SP programme, which sits within the ‘Aid for Trade’ portfolio of programmes, was successfully piloted in FY 22/23 in Ghana and Rwanda (with additional Kenya and Uganda activities being added towards the end of the year). The Commonwealth Standards Network (CSN) is the predecessor programme of the SP (currently funded and managed by the FCDO Commonwealth Unit).

Following the success of the pilot, the programme expanded and in the period under review, FY 24/25, the programme encompassed thirteen beneficiary countries delivered through two delivery partners. The British Standards Institution (BSI) design and deliver the programme interventions in the ASEAN Member States, Bangladesh, the Caribbean, Egypt, Ghana, India, Kenya, Mozambique, Nigeria, the Pacific Islands, Pakistan and Rwanda, whilst TradeMark Africa (TMA) design and deliver the programme interventions in Uganda.

The programme is due to close, in line with the original Business Case timelines, in March 2026. At this stage, we currently anticipate that standards work will continue under a new delivery model as part of the Addressing Barriers to Trade Pillar of the new Trade Centre of Expertise.
[note] The Trade COE is one of five Economic Development Centres of Expertise which have all been designed to provide world-class technical expertise to governments and businesses in a way that is better coordinated, responsive, flexible and provides increased value for money. The Trade COE will provide trade-related technical assistance to support export-led growth and poverty reduction in developing countries.
About changes to UK ODA
At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.

The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.

ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.

We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme has scored an A+ at this Annual review. All of the 5 programme outputs have been achieved, with the main work area - Output 1 (which accounts for 60% of overall activity) and Output 3 - significantly exceeding last year’s performance. This strong performance has been achieved despite challenges in work taking longer to scale up than had originally been anticipated (which, to a large degree, was within the control of the programme – see recommendations), and the impact of external issues which resulted in programme activities being paused in 2 countries. The programme is deemed to be broadly meetings its Intermediate Outcome and Outcome targets, although it should be noted that this is largely based on qualitative evidence including stakeholder feedback, which is strong. There are still challenges in producing comprehensive statistical evidence demonstrating how the programme is having an impact in areas including Outcome Indicator 2 (See Section B).

Programme Achievements

The technical advice provided through Standards Partnership has been critical to improving the National Quality Infrastructure in several SP countries/regions in FY 24/25. SP has been able to convene and assist national governments, institutions and enterprises in countries/regions including Nigeria, Kenya and the Caribbean to develop and manage their quality and regulatory systems. This work is key to enhancing the competitiveness of local products and services, facilitating trade, protecting consumers, and promoting sustainable development. For example, with SP support, Samoa has developed its first National Quality Policy (NQP) which was approved by the National Policy Coordination Committee in March 2025.

SP has established and strengthened critical partnerships across the quality infrastructure landscape. It has built closer ties between National Standards Bodies (NSBs), encouraging newer NSBs – for example in the Pacific – to join the international standards-setting community (such as the International Organization for Standardization, ISO). Relationships with regional standards organizations like the Caribbean Regional Organisation for Standards and Quality (CROSQ) and the African Organisation for Standardisation (ARSO) have been deepened, enabling greater knowledge transfer and the sharing of international best practices among their member countries. These efforts have created a tangible ripple effect in promoting standards adoption. (See Section G).

During the reporting period, SP has successfully pivoted its technical assistance to more directly engage the private sector alongside public institutions and policymakers. This is reflected in the statistical increase in private sector entities being supported which have more than doubled compared with FY 23/24. A renewed effort has been made to support businesses in partner countries, exemplified by new collaboration with the Private Sector Federation in Rwanda. SP has also deepened its collaboration with other programmes in the Trade for Development portfolio that seek to help firms in developing countries that lack market access information and struggle to meet international standards. (See Output 3).

SP has achieved significant results across its diverse portfolio, delivering in line with thematic priorities in each country. In Ghana, SP supported the country’s ambition to become a major manufacturing and business hub. In India, the programme advanced work on global decarbonisation in support of the country’s net-zero future goals. In the Caribbean, SP focused on building resilient infrastructure, while in the Association of Southeast Nations (ASEAN) region it has strengthened e-commerce frameworks and digital trust to bolster regional digital integration. The programme has also supported Bangladesh’s national strategic plan for growth and socio-economic development.

The SP’s work in support of NSB inspectorate functions has helped to broaden their reach to perform competently against their mandates. The Director General of the Ghana Standards Authority (GSA) has been particularly effusive in his praise of the capacity building support provided to new Trading Standards Inspectors in Ghana:- “This programme has been a transformative force for GSA and Ghana as a whole, strengthening our national quality infrastructure. At GSA, our institutional capacity has grown significantly. Our workforce has expanded from 900 to 1,200 skilled professionals - and that growth is set to continue. Our teams have undergone extensive training, equipping us to better serve the needs of Ghanaian businesses, protect consumers, and ensure that our products meet international standards”.

The programme has increased the level of work it has undertaken on Green Trade Standards this year. This work, supporting the goal of global decarbonization and a net-zero future, has included standards support and training to reduce plastic waste and greenhouse gas emissions in Bangladesh, a Green Hydrogen event in India, and a strategic initiative in Egypt aimed at equipping exporters, policymakers, and industry leaders with the knowledge and tools needed to navigate the UK Carbon Border Adjustment Mechanism (CBAM) when it comes into operation. On a broader level, SP has also directly supported partner countries to help develop and adopt Net Zero Guidelines (see Outcome Indicator 1.1).

Equity considerations continue to be embedded in activity design, delivery, and results capture. Training and beneficiary support activities delivered across the SP portfolio have purposely ensured gender inclusion and focused on working with SMEs, and specific analysis has been undertaken in four geographies to assess how standards can benefit women, poorer and marginalised groups in developing countries. (See Output 5).

The programme was able to diversify its portfolio, whilst remaining in step with its original business case by initiating work with a new delivery partner, TradeMark Africa (TMA). This arrangement has helped the SP to continue impactful work in Uganda - a country where activities had been put of pause – and has broadened the programme’s delivery capacity through collaboration with a new regional partner. This collaboration was taken onto a new level in June 25 when the programme’s two delivery partners, BSI and TMA, signed their own joint MOU to facilitate closer working.

Logframe statistics indicate that the programme has become more cost-effective during this reporting period. SP has delivered more events and reached more people for the budget invested, which demonstrates that the programme is successfully building on the foundations laid in previous years. To this end, it has been possible to continue and build upon activities in several countries without extensive additional – and time consuming – planning activities resulting in better Value for Money (See Section D).

Lessons Learned

SP Theory of Change. The programme team undertook a light-touch review of the SP Theory of Change in January 25. The review affirmed that the ToC continues to reflect the business case and the evolving programme. In particular, the focus on GESI (output 5) remains relevant and the completed GESI assessments remain informative for FY 2025/26 as this aligns with the Trade COE priority country focus. The review found that a subsequent version of a ToC should have the intended “ripple-effect” of SP as a more prominent feature. (i.e. knowledge transfer and sharing of international best practices across SP countries. (See Recommendation 6).

Results & Impact. The programme should consider focussing on a key value chain or sector across streams where SP has had a strong impact, e.g. agri-business and/or food safety, or leather to show impact from output to impact level. This focus could support the SP impact with data and evidence and help identify and showcase scalable opportunities for the Trade CoE. (See Recommendation 2).

Work Plans & SP Logframe. The work plans for each stream are the main tool for managing activity delivery by the streams. They were adjusted to produce more uniform data on TA for the SP logframe. However, the work plans and the logframe are tools with distinct purposes which do not always work together seamlessly. The work plans are not uniform, which can make it more time-intensive for cross-cutting experts or FCDO to interpret them. Efforts have been made to present these in a more harmonised way for ease of use and interpretation.

MREL. More reflection on how best to confirm early in the FY precisely which data will be needed from each stream’s NSBs and when it will be requested has been beneficial. Streams were initially focused on design and then delivery, making it challenging to prioritise this critical area for outcome and impact level results with adequate consistency and advance notice to NSBs. NSBs also don’t have a central data repository where the requested data can be easily pulled; it needs to be collected piecemeal via various divisional staff working in those relevant technical fields. These issues were addressed by including an MREL data collection activity in each stream workplan.
General Programme Lessons

In-Country Disruption. The value of engaging national experts is critical and helps to maintain continuity and momentum when security issues hinder progress. It is also important to maintain flexibility within work plans. In countries that have been subject to disruption, future planning should allow for extended timelines and anticipate potential issues.

Stream Specific Lessons

Caribbean. The project continued its close collaboration with CROSQ which gave the project the opportunity to deliver our activities to a larger regional audience where applicable. Given the scale of the national economies, it is important to keep a regional perspective for future interventions. The expert team have met and successfully engaged the new CROSQ CEO, and continues to be invited to and participate in their routine Council meetings to present updates on the Standards Partnership programme.

Egypt. The number one factor contributing to the success of SP Egypt has been that of strong emphasis on localisation of materials and training content. The localisation approach has without doubt supported improved and more rapid engagement to the 200+ organisations targeted under the initiative and has helped maintain uniform training outcomes across the various mediums that were used. SP Egypt achieved this through the engagement of specialised subject matter experts from Egypt, adapting messaging and content to local contexts (e.g. using local case studies), and thoroughly testing and validating project outputs with pilot audiences throughout the development process.

Ghana. There is a significant demand for support to SMEs in Ghana, especially within the food sector, to encourage them to produce marketable and compliant products as well as to guide them through achieving various certification levels. A key part of the solution involves simplifying and where necessary, translating existing regulations and relevant standard extracts to ensure clear understanding and effective implementation.

Mozambique. The main challenge during this reporting period remained the widespread civil unrest following the contested results of the presidential elections celebrated in October 2024. As a result, the programme was compelled to suspend international missions scheduled for the quarter. In addition, the local Project Team, along with key stakeholders, faced significant disruptions to their day-to-day activities.

India. The need to engage at an earlier stage is important in expediting delivery speeds, allowing Government departments to more easily react and approve proposed project interventions.

Nigeria. Local coordination with SP’s main stakeholders, a national coordinator based in Abuja and the support of FCDO colleagues from post, has been key in the successful delivery of activities in a challenging environment (last minute changes and logistic challenges).

Recommendations for the year ahead

Programme Delivery Delays. The programme needs to be in a position to start all of its activities in earnest before the second half of the financial year. The late start last year resulted in the programme not being able to fully utilise its £2.65m original budget that had been set in June 25 and led to over 50% of programme spend occurring in the final quarter. This scenario also contributed to financial uncertainty at year-end, resulting in a small overspend when compared to its revised budget.

Monitoring, Reporting, Evaluation and Learning (1). The programme needs to:-

- revisit the logframe at Outcome level to determine where there are likely to be statistical gaps (and assess what is driving those gaps and whether they can be addressed) ahead of the next PCR.
- assess whether it will be possible to incorporate a sector level focus on programme work when reporting on results and impact.
- adopt a more systematic approach to following up with NSBs / other beneficiaries on whether its activities are delivering impact. (An example of this, explored at this Annual Review, would be ascertaining whether its work in restoring lab equipment had resulted in a significant increase in lab tests thereafter). This follow-up analysis will also provide important statistical evidence on programme impact for the PCR (due in June 26).

Monitoring, Reporting, Evaluation and Learning (2). The programme should strengthen the rationale for why the milestones for 25/26 are set at a certain level, informed by the stream ToR, work plan and annual budget. Although it is recognised that the focus of the stream and the budget vary year to year, the programme should use outputs delivered during FY 24/25 as an additional reference point for setting milestone targets in FY 25/26.

Finance:- The disparity between monthly forecast and spend has been too large on a monthly basis. This points to a disconnect between planning and actual delivery, which could be improved by:-
- Starting activities sooner, thereby creating a scenario where there is a more even distribution of work activities / spend across the year (see recommendation 1).
- Developing more detailed and costed work plans which underpin forecasts, and a
- Quicker and more streamlined approach to collating spend figures at the end of each month. (See Section F).

Programme Sustainability / Handover. The Standards Partnership programme is due to end on 31 March 26, although we currently anticipate that Standards work will continue under the new Trade Centre of Expertise programme from 01 April 26. SP is already focussed on ensuring a sustainable handover to beneficiaries when its programme activities come to an end. The programme will also need to ensure that it has sufficient capacity to deliver an effective handover to the incoming Lead Supplier during the final quarter of FY 25/26, whilst also successfully delivering activities during a peak period. (See Section E: Risk).

Theory of Change. The programme should consider updating the programme Theory of Change to increase the focus on the “ripple effect” – knowledge transfer and sharing of international best practices across SP geographies. (e.g., CROSQ in the Caribbean and ARSO in Africa).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

In September 24, the programme revisited its Theory of Change (ToC) and Logframe to ensure that it remained fit for purpose and aligned to the new work areas where post had highlighted demand. The programme had encountered challenges providing statistical data against some Outcomes and Intermediate Outcome level indicators at the last Annual Review, so the September review also aimed to address those issues. This resulted in the following changes to the logframe:-

The Number of regulatory import inspections indicator was moved from Impact Indicator 2 to Outcome Indicator 1.3 to provide evidence against the Outcome 1 Statement:- Growth of active sustainable and inclusive global & regional value chains in developing countries.
The Value of target country GDP and Value of UK goods and services exported to and imported from target stream joint indicators were re-inserted as Impact Indicator 2, on the basis that this would provide a more complete data set for all streams at impact level.

A new indicator - Pan-African Quality Infrastructure Score* (PAQI) - was added as Outcome indicator 2.3. This indicator, which is updated every 3 years, will help to determine whether partner African countries are making improvements to their National Quality Infrastructure as measured independently by the Pan-African Quality Infrastructure (PAQI) Index*.
[note] The PAQI Index is a composite tool launched in 2014 to assess and compare the quality infrastructure – standards, metrology, and accreditation systems – of African countries.

The over-arching programme logframe was updated to reflect this change, although the ToC remains unaltered.

Standards Partnership – Theory of Change

In November, a Business Case Addendum was produced in consultation with FCDO’s Centre for Delivery Dept, to enable the programme to undertake SP work via a second delivery partner, TMA, in Uganda. This has been important development as it has allowed the programme to continue activities that had previously been paused due to visa / work permit issues, whilst also enabling the programme to diversify its delivery model by collaborating with a new regional partner that brings additional expertise and experience. (See Section C – Outputs 1 and 3).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The scoring of the annual review focuses on the achievement of expected results at the output level and assesses the likelihood that outcomes and impact will be achieved within the planned time and budget. Section C - Detailed Output Scoring of this Annual Review confirms that the programme has achieved and in some areas exceeded its output targets. Although the statistical evidence suggests that FY 24/25 output targets that were set at the beginning of the year could have been more stretching, the performance compares favourably with the previous financial year in which the programme scored an overall A+.

Qualitative evidence demonstrates that the programme is making good progress to contribute to the outcomes and impact set out in the original business case, despite operating within a significantly reduced budget due to ODA reductions. N.B. We currently anticipate the programme will spend closer to £10m (as opposed to the original £35m budget) by the time of its scheduled closure in March 26.

Outcome Level Analysis

Outcome Indicator 1.1 - Number of regional and international standards [ISO/IEC/CODEX] adopted either as new or revised by target NSBs and NQI institutions.

Ghana and Bangladesh (two countries that have produced data against this indicator and where there is a milestone to measure performance) have reported an increase in the number of standards produced during this Annual Review period. The statistical evidence demonstrates adoption of international and regional standards, participation in International Workshop Agreements (IWAs) and Regional Trade Committee’s in partner countries.

Qualitative evidence also shows that Bangladesh, Egypt, Ethiopia, Kenya, Nigeria and Rwanda are moving towards adopting (and, in the case of Nigeria, influencing other countries to adopt) Net Zero Guidelines, by becoming involved in the International Standards Net Zero Working Group. This is a direct result of the support delivered via the SP programme.

Outcome Indicator 1.1 – National Quality Infrastructure Policy Work

One of the cornerstones for ensuring good governance of the National Quality Infrastructure (NQI) system is the National Quality Policy (NQP). NQPs and a related document – an Implementation Matrix - highlight strategic sectors for development in line with national, regional and international standards and specify steps to progress them. It also raises awareness at all levels about the principles and practices of quality management and informs markets on where to go for the specific NQI services.

The programme has helped to coordinate and build consensus on how a distributed NQI system (like in the UK) can function, whilst supporting the institutions to increase the national focus in this area. During this Annual Review period the Standards Partnership has supported:-

- Samoa to approve the country’s first National Quality Policy (NQP),
- Kenya to develop its NQP, and
- Belize and Nigeria to implement their NQPs, providing a focal point between the public and private sectors to increase trade.
Outcome Indicator 1.2 - Tangible examples of instances in which trade, sustainability and inclusion priorities of developing countries influence or are included in international and regional standards discussions and processes

Data provided by the International Standards Organisation (ISO) demonstrates that there has been an overall increase in the number of ISO technical committees in which Standards Partnership country National Committees are participating as members. Rwanda offers an example of a SP partner country that has had significant impact through its involvement in International Committees. Rwanda has taken its successful national standard (Gender equality – requirements for promotion, implementation and accountability) to the Africa Regional Standards Organisation with a view to potentially developing this into a continental standard. The programme continues to monitor this with interest as it would represent a unique and significant development / achievement.

Outcome Indicator 1.3 - Number of regulatory import inspections

Ghana and Bangladesh (two countries that have produced data against this indicator and where there is a milestone to measure performance) have reported an increase in the number of regulatory import inspections during this Annual Review period. The Caribbean, Kenya and the Pacific have also provided data this year which will enable performance to be measured against these workstreams for the Programme Completion Report (PCR) which is due in June 2026. The programme has supported the Ghana Standards Authority (GSA) in the area of market surveillance by continuing to train inspectors to ensure safety, compliance and quality standards of a range of goods. This work, which covers areas including food, electrical supplies etc, is critical in relation to enhancing consumer safety and creating a fair marketplace.

Outcome Indicator 2.2 – Number of certificates and sites issued by target NSBs and NQI institutions against product and system standards
[note] Certificate - the document issued by a certification body once the client has demonstrated conformity to a standard Site - a permanent location where an organisation carries out work or provides a service.

Most programme workstreams are demonstrating yearly increases in the number of certificates and sites each year, which is an indication of an improved business environment and sector competitiveness in targeted countries.

As was the case in the last Annual Review, the programme has continued to encounter some challenges in obtaining some statistical data for all workstreams at Intermediate outcome level. This is despite efforts being made to address issues / plug data gaps during the reporting period. This is partly attributable to the programme’s current reliance on National Standards Bodies in partner countries to provide this information, where capacity issues / the level of maturity of the NSB can have an impact. The programme should assess whether there is a better method of capturing statistical data for Outcome Indicator 2.2 - Number of product tests carried out (public and private where available) against the requirements of international and regional standards – where it has only managed to obtain statistical data for 5 workstreams. (See Recommendation 2).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

This Annual Review covers the second year of full delivery (noting that the programme was piloted in FY 22/23). In FY 23/24, ODA priority posts were given an opportunity to buy into work being delivered by the future Centres of Expertise and the Standards Partnership was a beneficiary of this initiative. In this reporting period (FY 24/25), those budgets were extended by a year and moved onto the Trade COE baseline. In addition to this central budget, SP received additional buy-in from countries/regions including the Pacific, India and Pakistan. This demonstrates that post remain keen to continue to prioritise work to develop standards and quality infrastructure as a means of addressing barriers to trade.

FCDO has recently updated its internal evidence to assess where it can deliver most impact in a 0.3% context. This evidence suggests that the SP programme is already operating in areas where it can deliver most impact, including “on policy, advice, collaboration with others (donors and governments), research and low-cost technical assistance”. Peer to peer links, which encompasses BSI’s work in support of partner country National Standards Bodies, is recognised to be a ‘good buy’ from an ODA funding perspective, along with the relatively low-cost work that the programme delivers in support of networking and mentoring those organisations (i.e. supporting NSB’s to engage with Regional and National Standards Organisations (i.e. ISO).

The programme is due to end in March 26, in line with the expectations set out in the SP Business Case. SP is currently focussing on delivering against an extensive and challenging set of activities in FY 25/26 whilst concurrently putting in place arrangements to provide an effective and sustainable handover of work at the end of the year. This will include work to transition to a new delivery model when the Trade Centre of Expertise becomes fully operational (currently expected to occur in April 26).

## C. DETAILED OUTPUT SCORING
Output Title	Quality and inclusive technical assistance provided to partner institutions to develop national quality infrastructure and trade related regulatory frameworks that meet the needs of women, poorer & marginalised groups.
Output number:		1.1	Output Score:	A+
Impact weighting (%):		60	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of entities / Number of capacity building (CB) events [trainings/workshops/courses/conferences – defined as group activities with an education or awareness element] / and Number of individuals (government officials / staff) across NSBs and administration agencies trained under the SP programme on five areas related to quality infrastructure and trade regulations, against individual stream focus areas and targets (which differ from stream to stream): 1. Standards 2. Conformity Assessment / Certification 3. Metrology 4. Market Surveillance, Inspection and Testing 5. Accreditation	ASEAN:- 10 entities / 1 CB events / 20 individuals targeted (10M 50% / 10F 50%) Bangladesh: 50 entities / 10 CB events / 200 individuals (140M 70% / 60F 30%) / Caribbean: 60 entities / 9 CB events / 250 individuals (125M 50% / 125F 50%) / Ghana: 5 entities / 22 CB events / 400 individuals (240M 60% / 160F 40%) / India: 7 entities / 2 CB events / 49 individuals (32M 65% / 17F 34%) / Kenya: 10 entities / 7 CB events / 60 individuals (30M 50% / 30F 50%) / Mozambique: 10 entities / 7 CB events / 88 individuals (45M 51% / 43F 49%) / Nigeria: 5 entities / 9 CB events / 200 individuals (120M 60% / 80F 40%) / PACER Plus/ Samoa: 3 entities / 3 CB events / 50 individuals (approx. 25M 50% / 25F 50%) / Pakistan: 20 entities (20 public, 0 private) / 3 CB events / 35 individuals (25M 71% / 10F 29%) / Rwanda: 5 entities / 13 CB events / 400 individuals (200M 50% / 200F 50%) / Uganda: 8 entities / 8 CB events / 179 individuals / Total: 193 entities / 94 CB events / 1931 individuals	ASEAN:- 32 entities / 2 CB events 87 individuals targeted / Bangladesh: 154 entities / 15 CB events / 461 individuals (346 M 75%, 115 F 25%) / Caribbean: 192 entities / 9 CB events / 344 individuals (159M 46% / 185F 54%) / Ghana: 1 entities / 26 CB events / 452 individuals (260 M 58%/ 192F 42%) / India: 43 entities / 3 CB events / 120 individuals (96M 80% / 24F 20%) / Kenya: 66 entities / 12 CB events / 208 individuals (114M 55% / 94F 45%) / Mozambique: 41 entities / 4 CB events / 110 individuals (55M 50%, 55F 50%) / Nigeria: 208 entities / 14 CB events / 495 individuals (278M 56% / 217F 44%) / PACER Plus/ Samoa: 104 entities / 18 CB events / 360 individuals (70M 49% / 74F 51%)] / Pakistan: 0 entities / 0 CB events / 0 individuals – not met. / Rwanda: 54 entities / 15 CB events / 388 individuals (200 M 52% / 188F 48% / 2 PWD / Uganda: 1 entities / 8 CB events / 169 individuals (119M 70% / 50F 30%) / Total: 1066 entities / 131 CB events / 3556 individuals
1.2 Monitor the acquisition of new skills and knowledge among participants through post-training assessment surveys.	An average score demonstrating highly satisfied, out of completed surveys.	Bangladesh: 4.78 out of 5 / Caribbean: 4.7 out of 5 / Ghana: 4.59 out of 5 / Kenya: 4.82 out of 5 / Mozambique: 4.53 out of 5 / Nigeria: 4.59 / PSIDS: 4.80 out of 5 / Rwanda: 4.74 out of 5 / Uganda: (90% above 60%)
1.3 Change in awareness level among target institutions (NSBs) of their understanding of, and ability to tailor their work and operations so that they benefit women, poorer, and marginalised groups.	1 qualitative statement per stream summarising to what extent target NSBs: a) perceive they have greater awareness of the specific needs and challenges faced by women, poorer, and marginalised groups and the opportunities this presents for them and b) how specific groups have been and will be targeted.	The qualitative statements have been used as part of the evidence base for the Annual Review.

Briefly describe the output’s activities and provide supporting narrative for the score.

BSI focused approximately 60% of its work on Output 1 in FY 24/25 providing capacity building institutional support to develop National Quality Infrastructure (NQI) and trade-related regulatory frameworks in partner countries. This activity has focused on aligning processes with international best practice in relation to Standards. The target audiences for this support have included auditors, trading standards inspectors and laboratory technicians working in the following NQI areas covered in more detail below.

SP has significantly exceeded its targets against this measure, although in retrospect it is clear that the targets that were set at the beginning of the year could have been more ambitious. The programme has scored an A+ on the basis that it has out-performed the results registered in the last Annual Review (which can be used as a proxy baseline for performance in FY 24/25) for individuals trained (38% more people reached) and events delivered (+39%) despite receiving only an 11% increase in budget. As is covered in the VfM section, the average cost per individual and cost per event were also lower this year.

Metrology: This work relates to implementing specifications and standards to ensure accuracy, validity and consistency. During the reporting period, GSA’s laboratory staff received technical training to identify metallic contaminants in food and environmental samples. One significant highlight of this intervention was the successful restoration of lab equipment that enabled GSA to clear a major backlog of outstanding tests to process fish products intended for local and international markets. GSA lab staff have also received training on microbiology methods for the testing of food and water intended for drinking, plus process water used in export products and in products intended for local consumption. This work is critical as accredited laboratories produce test reports that are less likely to be questioned or challenged, thereby facilitating trade. The ability to determine mercury and methyl mercury in food samples (in particular fish) is crucial for food safety.

Conformity Assessments / Accreditation:

- Conformity Assessment work, which includes testing, inspection and certification, is critical to providing the infrastructure needed to ensure that products, processes, and services meet international standards and regulations.
- Accreditation ensure that those who carry out testing, certification and inspection are competent to do so.
SP ran a 4-day training course for the National Physical Laboratory of India (NPLI) to strengthen their capacity to implement proficiency testing schemes based around the related International Standards (ISO 17043 & ISO 13528). This training has enhanced NPLI’s credibility and its role in supporting laboratory accreditation in India, as it plays a critical role in enhancing the accreditation process through its research, technical expertise and development of standards. This work has contributed to the overall goal of improving the quality and reliability of conformity assessment bodies in India, promoting international trade, and supporting economic stability. The training also fosters closer regulatory alignment between India, the UK and the global accreditation community.

Market Surveillance: The programme has further strengthened the capacity of the Ghana Standards Authority (GSA) by training an additional 75 new inspectors in market surveillance, building on the 350 inspectors trained prior to FY 24/25. These trained inspectors are now deployed nationwide to carry out market surveillance and inspections, ensuring that goods comply with safety, quality and regulatory standards. This work is vital for enhancing consumer protection and fostering a fair marketplace. The programme is collaborating with GSA to establish a sustainable, in-house system for skills development and knowledge transfer by supporting newly qualified inspectors to train future cohorts.

National Quality Policy (NQP): During this reporting period the programme has delivered work to support the development, adoption and implementation of NQP’s in Nigeria, Kenya and Belize. Through this work, the programme has helped National Standards Bodies to identify and address gaps in target sectors in each country, using the appropriate NQI solutions (i.e. testing, accreditation, metrology). In Nigeria, SP has supported the work of the National Quality Council (NQC), which was established to oversee the implementation of the NQP. This work has involved coordinating with regional contacts to develop an Implementation Matrix, which is now nearing completion and facilitating public sector workshops and train-the-trainer events that are focussed on empowering Nigerian stakeholders to take ownership of the NQP.

In Kenya, the government has been actively developing its NQP to enhance the quality and competitiveness of its products and services. This initiative aligns with the country's long-term development blueprint, Kenya Vision 2030. SP’s work focussed on NQP from the perspective of the leather and meat sectors. One workshop, delivered in conjunction with the Ministry of Trade and involving the participation of a working group from the leather sector, aimed to build an understanding of the whole value chain, from the identification of the genes in the herd for assuring the right quality in cattle for leather production. This event underscored the vital role of accreditation in enhancing Kenya’s industrial and trade sectors while aligning with global sustainability and competitiveness goals.

NQP activity in the Caribbean has focussed on the Agro-processing sector. This is a key pillar of the Belizean economy, supporting a significant proportion of the workforce including women, women led Micro, Small and Medium-sized Enterprises (MSMEs) and poorer and marginalized groups. The programme has delivered workshops in conjunction with the Belize Bureau of Standards that have targeted the hot pepper sauces, honey and coconut and coconut derivatives sectors. This work is by identifying strengths and gaps in the NQI System, thereby building a stronger quality culture. This intervention has informed a work plan produced for the National Quality Council (NQC). Separately, an NQC Paper, which is focussed on improving the region's NQI through strategic collaborations, has been submitted for review and approval to the Cabinet.

Digital Standards: Programme work in the ASEAN region has focussed on strengthening cross-border e-commerce and digital trust, to boost the digital economy and support the growth of a unified digital market. To this end, SP has undertaken research and has produced recommendations to bridge gaps and streamline e-commerce standards adoption across the region. This work supports an agreement reached by ASEAN-UK Economic Ministers in 2021 to collaborate on digital innovation through the ASEAN-UK Digital Innovation Partnership.

A virtual capacity-building workshop brought together policymakers, standards developers and private and public sector representatives from across 10 ASEAN member states, to raise awareness and understanding of the critical role e-commerce standards play in digital economy integration. Workshop participants shared insights on digital trade standards and the key areas that most effectively promote trade and foster closer cooperation among countries within the ASEAN region. Other outputs from this work have included a Standards Landscape report, and an ASEAN Cross-Border E-Commerce Standardization Framework which can be used as a roadmap and harmonization plan going forward by regional stakeholders.

Green Trade:- In May 2025, the UK and Indian Governments signed a free trade agreement (FTA) following a pause (for respective general elections in 2024). Against this backdrop, the Standards Partnership delivered three important activities for a variety of different Indian stakeholders focussing on supporting India with its decarbonisation journey. In January, the programme brought together a pool of technical experts to deliver a two-way dialogue enabling over 70 participants from public and private sectors to discuss and understand the interaction between industry, government, and standards bodies to support net zero commitments through a whole-of-system approach to green hydrogen technologies.

The workshop received positive participant feedback and was a good example of the UK mobilizing key stakeholders including the Department for Energy Security and Net Zero, UK Government (DESNZ) who presented the UK’s new Low Carbon Hydrogen Standard and its accompanying certification scheme. The International Renewable Energy Agency also presented their new Quality Infrastructure roadmap for green hydrogen (published in November 25) setting out how countries can develop their quality infrastructure to effectively support the green hydrogen sector. The impact of this event has been to develop key networks, contacts and ideas on how the UK and India can work together in achieving our respective net zero ambitions.

In Egypt, the programme delivered a strategic initiative aimed at equipping Egyptian exporters, policymakers, and industry leaders with the knowledge and tools needed to navigate the UK Carbon Border Adjustment Mechanism (CBAM). To achieve this, the project:

- produced a guidebook (The Little Book of UK CBAM) to be used as a trusted reference for Egyptian manufacturers and stakeholders. This has been published in both digital and hardcopy formats with over 200 hardcopies distributed during the Quarter, and over 1,000 downloads registered;
- delivered targeted training workshops to industry leaders, policymakers, and financial institutions, to help build knowledge of CBAM’s operational framework and compliance strategies, and
- has produced a recommendations report to guide future policy actions. The success of this initiative opens the possibility of mirroring this approach in other regions

TMA Activities in Uganda: The programme started working with TMA as a new delivery partner in November 24 in order to address a gap in support in Uganda. TMA performed well to procure and deliver activities that were well-received by beneficiaries within a very constrained timescale. Activities for Output 1 included:-

GlobalG.A.P. capacity-building training that has helped to equip stakeholders with the knowledge and skills to implement and oversee Integrated Farm Assurance (IFA) standards effectively. The training featured two sessions, each hosting 15 participants from the Uganda National Bureau of Standards (UNBS), the Ministry of Agriculture, Animal Industry, and Fisheries (MAAIF), and private sector organizations which focused on key components of GlobalG.A.P. standards, including compliance principles, auditing processes, and risk management strategies.

Lead Auditor training to enhance the auditing capabilities of UNBS staff and ensuring compliance with international food safety standards. (FSSC 22000).

Introduction to ISO/IEC 17020: 2012 for Inspection Bodies:- This training was delivered to 21 inspectors who had recently joined UNBS to enable them to identify gaps in documentation. The training equipped the new inspectors with knowledge and skills to enhance implementation of value-added inspection activities while supporting MSMEs to meet requirements of the standards thereby promoting local, regional and global trade and protecting the public from unsafe products.

Indicator 1.2 – Monitor the acquisition of new skills and knowledge among participants through post training assessment surveys

Post-training assessment surveys were used to monitor levels of satisfaction registered by the National Standards Bodies and stakeholder groups regarding the new skills and knowledge acquired through the training received. Those assessments reveal very positive participant feedback, with scores exceeding 4.5 out of 5 across all workstreams. This is generally an improvement on the scores that were registered in the previous Annual Review, which may be a reflection of the increased maturity of the programme in its second year of delivery. This positive feedback is also replicated in the Survey feedback provided by stakeholders as part of this Annual Review.

Indicator 1.3 Change in awareness level among target institutions (NSBs) of their understanding of, and ability to tailor their work and operations so that they benefit women, poorer, and marginalised groups.

Target institutions (NSBs) are increasingly aware of the needs of marginalized groups. Performance against this output indicator was based on a qualitative report produced by each workstream, which highlighted the extent to which the target NSBs a) perceived they have greater awareness of the specific needs and challenges faced by women, poorer, and marginalised groups and the opportunities this presents for them and b) how specific groups have been and will be targeted. Most workstreams were able to provide a breakdown of the number of Males and Females trained under Output 1. Statistically there was a 39% average participation rate for women, which was lower than the 43% target, although the number of females trained in total was double the target (as the output was significantly exceeded).
Highlights from stream level interventions include:-

Bangladesh: BSTI officials participated in the ISO Gender Focal Point Network Meeting, and the IEC Webinar on “Empowering change: Investing in women to accelerate progress in electrotechnology.” The organisation is steadily enhancing its understanding and capacity to tailor its work and operations to benefit women, poorer, and marginalised groups.

Ghana: The programme has begun working with the GSA Certification Department to identify a number of largely women-led SMEs in the food sector that would benefit from targeted training and coaching in Good Manufacturing Practices (GMP) and the application of the HACCP (Hazard Analysis and Critical Control Points) methodology. The aim is to support selected SMEs in progressing towards certification under the forthcoming HACCP standard, which is expected to be harmonised across Africa. This work will also contribute to enhanced public protection by improving food safety and enabling more effective removal of non-conforming products from the market.
Mozambique: The NSB has recently appointed a Gender Focal Point for the UNECE’s Declaration on Gender-Responsive Standards and Standards Development. There is a gradual but significant shift in NSBs’ understanding of the need to adapt their practices to specifically benefit women, as well as the poorest and most marginalized groups.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The two changes this year have been:-

- A slight shift in country focus. At the start of the year, it was agreed that work would stop in Ethiopia (which had been previously commissioned by post) due to concerns regarding the pace and likely impact of the intervention. Later in the year, the programme responded quickly to demand and started new work in ASEAN and Egypt when it became clear that underspends were emerging across the wider portfolio.
- Work in Uganda being undertaken by a new delivery partner, TMA.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The programme has registered an overall percentage increase in the number of events delivered and individuals reached, when compared to budget. This is an encouraging sign that SP is building on the foundations already laid in its first year of implementation (i.e. many activities were already clearly defined so could be continued / scaled up), resulting in a more cost-effective delivery approach.

The programme must take on board recommendations to set more challenging targets for output indicator 1.1 in FY 25/26 as they have been significantly exceeded for the second year running. The results achieved in FY 24/25 should be used as a baseline for activities to be delivered in FY 25/26 (in line with a recommendation in last year’s Annual Review). Recommendation 3.

## C. DETAILED OUTPUT SCORING
Output Title	Quality and inclusive technical assistance supports, facilitates and enables participation and engagement by partner institutions with international and regional standards bodies.
Output number:		2.0	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Number/level* of engagements** related to or with ISO, IEC and relevant regional standards bodies (e.g. ARSO, CROSQ) / *Levels of engagement: / - Low: 0-3 engagements / - Medium: 3-8 / - High: 9+ / **Engagements - attendance at an event or training by ISO, IEC or other relevant regional bodies, virtually or in person; key meetings and discussions can also be included.	Bangladesh: Medium Caribbean: Medium Ghana: Medium India: Medium Kenya: Medium Mozambique: Medium Nigeria: Medium / PSIDS (Samoa/Kiribati): Low Pakistan: N/A (Supporting engagement with ISO, IEC or regional standards bodies not part of the ToR or work plan) Rwanda: Medium	Bangladesh: Medium Caribbean: High Ghana: High India: Medium-High Kenya: Medium/ High Mozambique: Medium Nigeria: High (hosted ARSO GM in June 2024) PSIDS: Samoa: Medium; Kiribati: Low Pakistan: N/A / Rwanda: High (hosting ISO GM in October 2025, planning underway in late 2024/ early 2025)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on supporting National Standards Bodies to participate and engage with international & regional standards bodies. This is key to ensuring that discussions and processes in organisations such as the International Organization for Standardisation (ISO), the African Regional Standards Organisation (ARSO) and Caricom Regional Organisation for Standards and Quality (CROSQ) reflect trade, sustainability and inclusion priorities of developing countries. The programme has surpassed its milestone targets against this output in six of the nine country workstreams, with the remaining three (Bangladesh, PSIDS, Mozambique) all meeting their targets.

There has been an overall increase in the number of ISO technical committees in which Standards Partnership country National Committees are participating as members. This indicates that those SP countries are developing the necessary administrative infrastructure to engage actively, provide technical input, contribute to drafts and vote on the work carried out by the technical committees.

Developing countries need to engage audiences with impactful messages that will ensure that their priorities are understood and acted on. To this end, two representatives from the programme chaired breakout groups with a range of developing countries at the ISO annual general meeting to develop case studies demonstrating how storytelling can improve the impact of messaging for marketing or reporting purposes. Feedback indicates that the case studies, based on SP support, have increased capacity in this area whilst shining a light on the work of the SP programme.

At country level, the Ghana Standards Authority (GSA) engaged in 19 programmes at both the regional (ARSO) and international (ISO/CODEX) level between April 2024 and March 2025, as well as a number of annual conferences. These engagements took place across six continents and included technical committees, working groups meetings and annual meetings and conferences on a range of themes such as healthcare service, pesticides residue, clothing sizing systems and food import and export inspection. Ghana’s continued Presidency of ARSO has also contributed to their ‘high’ level of engagement, due the very nature of this organisation.

Rwanda has increased its Observing Member roles from 51 to 74 (a 45% rise). The country is increasingly seeking a leadership role in both regional and international standards bodies, as evidenced by its participation as a Council Member of ARSO and co-chair of CSN. Rwanda also participates in 27 ISO Technical Committees, reflecting its growing engagement in the development of international standards. At the 2024 ISO Annual General Meeting, Rwanda played a prominent role as a key speaker, highlighting the critical link between climate change and occupational health and safety. Rwanda is set to host the ISO General Meeting in October 2025 and is also pursuing membership of the ISO Council for the 2025–27 term.

The National Standards Body of Mozambique (INNOQ.IP) has remained engaged in international standards fora, with support and counselling from SP, meeting their expected level of engagement despite post-election disruption. Highlights included the INNOQ.IP Director General participating at the UNIDO Multilateral Industrial Policy Forum in October 2024 in Saudi Arabia and the Deputy Director General participating as a panellist at the UNIDO Expert Group Meeting on “Rethinking Quality Infrastructure: Quality Policies for a Sustainable Future” in Austria in November 2024. Whilst SP funding was not provided for INNOQ colleagues to attend these meetings, coaching and networking opportunities were provided ahead and during the two events.

Describe any changes to this output during the past year and any planned changes as a result of this review.

No changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

SP is keen to monitor progress in this area beyond engagement level and will be monitoring initiatives including Rwanda’s work on Gender and Inclusion and wider SP country contributions in relation to the Net Zero agenda. The programme will also do more work to engage with beneficiaries to identify the key blockers to attend and participate in meetings at International and regional level.

Output Title	Training and awareness raising with private sector firms including support to SMEs and women-owned businesses seeking to export regionally & globally (including to the UK)
Output number:		3	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No
Indicator(s)			Milestone(s) for this review	Progress
3.1 Number of private sector entities, SMEs and women-owned businesses that have received training or support* from SP programme on identified themes such as food safety. / *Support may include awareness raising on a specific standard, for example, or networking events for businesses and policy makers to discuss issues and challenges.			ASEAN::- No target set at the beginning of the year as work commenced in Q3. / Bangladesh: 50 / Caribbean: 25 / Ghana: 3 / India: 1 / Kenya: 5 / Mozambique: 15 / Nigeria: 3 / PSIDS (Samoa/Kiribati): 10 (including small holder farmers) / Pakistan: 1 / Rwanda: 6 / Uganda: 419 / Total: 537	ASEAN: 6 enterprises (including 2 SME). / Bangladesh: 121 enterprises (including 72 MSMEs [60%] and 30 women-owned businesses. / Caribbean: 59 private enterprises / Ghana: 20. / India: / Kenya: 44 private enterprises / Mozambique: 23 enterprises / Nigeria: 191 private enterprises / PSIDS: 173 smallholder farmers + 42 firms (4 from NQP Workshops + 9 from Kiribati Standard Training + 20 from Fiji Standard Training + 9 from Good Hygienic Practices Training) / Pakistan: 0 (Delivery was not possible during FY 2024/25 Q4) / Rwanda: 30 / Uganda: 642 (Private Enterprises and Farm Enterprises).- not included in total. / Total: 667

Output 3 is focused on providing standards training and raising awareness with private sector firms, SMEs and women-led businesses seeking to export regionally and/or globally. Evidence confirms that developing country firms are more able to comply with import requirements of key regional, global and UK markets when utilising International Standards, as well as then being able to take advantage of the UK’s preferential access Developing Country Trading Scheme (DCTS).

The planned distribution of activity was changed for the year under review compared to the previous year, with a greater target number of private sector entities, SMEs and women-owned businesses to receive training in the Caribbean, Ghana, Mozambique, Pacific Islands and Rwanda and a lesser number in Bangladesh and India. Additional to the planned countries, six enterprises, including two SMEs, received training in the ASEAN nations. A capacity building workshop, originally intended for policymakers and standards developers, was expanded to permit each ASEAN member nation to invite up to three private sector stakeholders in response to strong private sector interest. (See Output 1).

The milestone in Bangladesh was significantly exceeded, with 2.4 times the number of enterprises receiving training, including an additional 15 SMEs and 20 more women-owned businesses, than originally planned. The original target had been conservative, due to budget limitations and concerns about the feasibility of planning international missions, given the unstable political situation in Bangladesh. Through the use of local but internationally recognised trainers, much of the training was able to be performed without the expense of flying in international experts, enabling more training to be provided within budget.

In Ghana, the milestone was significantly exceeded when 20 SMEs received HACCP and Good Manufacturing and Labelling practice training from GSA, working in conjunction with the programme’s project expert. This success was a result of an initiative to identify suitable SMEs to receive further coaching in these areas, to aid them to ultimately achieve relevant certifications.

TMA Activities in Uganda

Regional Seminars:- The programme provided support to UNBS and the Ministry of Agriculture, Animal Industry and Fisheries to conducted the MSME regional workshops to raise awareness about Standards, certification and market requirements in the Central Region (108 participants), Northern Region (86), Western Uganda (144), Eastern Region (161) and Jinga City (133).

Farm Enterprises trained on Global Gap:- Gap Analysis was conducted in Central Uganda for 5 farms (3 farms were owned by females and 2 farms by males) selected from 14 that had received GlobalG.A.P. training. The analysis identified compliance gaps and provided recommendations to align farms with GlobalG.A.P. standards, in order to enhance their access to premium markets. The program focused on bridging knowledge gaps and enhancing farm operations to prepare for certification. Key challenges, including resource limitations and infrastructure issues, were identified alongside opportunities to leverage existing strengths like good agricultural practices and pest management.

Describe any changes to this output during the past year and any planned changes as a result of this review.

As covered above, the most significant change was the new activities delivered via TMA in Uganda.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Results significantly exceeded milestones in the majority of countries. This would indicate that more ambitious targets need to set for the coming year. (Recommendation 3).

Logframe statistics demonstrate that the programme has more than doubled the level of support provided to SME’s during FY 24//25, delivering in line with a recommendation to increase support in this area from the last Annual Review. SP has also delivered remote workshops in support of DCTS (in line with another AR Recommendation) although the programme (and beneficiaries) have continued to demonstrate a preference for in-person technical assistance – as evidenced through Annual Review stakeholder feedback.

Output Title	Compliance issues in agri-food value chains and their root causes are identified and tackled via SPS technical assistance and support.
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No
Indicator(s)			Milestone(s) for this review	Progress
4.1 Number of NQI institutions supported* to upgrade operations to minimise occurrence of SPS issues. / *TA or training provided on a topic to improve understanding which can help the NQI address specific issues			Format below per stream: / Stream: # SPS TA and support activities / # materials identified or developed / Bangladesh: 2 / 2 / Caribbean: 3 / 2 / Ghana: 2 / 2 / India: 1 / 1 / Kenya: 1 / 1 / Mozambique: 1 / 3 / Nigeria: 1 / 1 / PSIDS (Samoa/Kiribati): 1 (Identify the priority products for SPS standards) / 0 / Rwanda: 2 / 2 / Total: 14 / 15	Bangladesh: 2 / 2 Examples are included in the Logframe Qualitative Report. / Caribbean: 5 / 5 / Ghana: 4 / 6 / India: 0 / 0 / Kenya: 2 / 1 / Mozambique: 1 / 2 / Nigeria: 2 / 4 / PSIDS: 2 / 0 / Rwanda: 4/4 / Total: 22 / 24

Output 4 is focussed on delivering SPS technical assistance and support to address compliance issues in agri-food value chains and to ensure that root causes of issues are identified and tackled. As is the case with output 3, improving performance in this area is critical to enabling developing country firms to comply with import requirements of key regional, global and UK markets. 10% of the programme’s overall activity has been weighted towards this output. Results met or exceeded milestone targets for both SPS technical assistance delivered and number of materials identified or developed in all countries except for India and Mozambique.

The agri-food sector is one of Bangladeshi’s most promising industries towards export diversification and is a key intervention area. The programme has more recently pivoted to food safety management basics to help attract more would be agrifood exporters and is also working with trade support organisations with the aim of multiplying outreach. At institutional level, the programme has worked with the Department of Agricultural Extension (DAE), which supports exporters of fruit and vegetables to the UK/EU market, with microbial and biochemical testing. Several officials participated in training on Quality Management Systems as part of the process to achieve accreditation to ISO/IEC 17025; an international standard focussed on the competence of testing and calibration laboratories. SP has also delivered training on to DAE on ISO 22000 – Food Management Systems - to help underpin the work it is undertaking on developing a Good Agricultural Practices (GAP) certification scheme. These initiatives are designed to address the phytosanitary aspects of SPS requirements.

In the Caribbean, programme activities have included regional trainings and workshops in the content and use of food safety standards and support to CROSQ in the regional harmonisation of the standards. Delegates were given the background of how food safety standards adopted by Saint Lucia compare to international frameworks such as Codex and ISO 22000. A regional needs assessment and impact analysis was also undertaken which explored whether the Saint Lucia Bureau of Standards (SLBS) standards should be advanced as regional standards and the potential benefits of regional standardization on food safety practice. This work has helped to inform a joint CROSQ/BSI action plan to guide future collaboration, address regional food safety challenges and support CROSQ member countries in food safety standardization efforts. In Belize, materials produced included three draft National Quality Policy matrices for hot sauces, coconut products and honey for Belize; and two approved workplans for the harmonised CROSQ food safety standards. NQP Matrices were also delivered in Nigeria covering the tea, coffee and cashew sectors (covered in more detail in Outcome Indicator 1.1 and Output 1 – National Quality Infrastructure).

In Ghana, the programme delivered two technical assistance activities for SMEs seeking certifications (with a focus on the food sector). These were small food producers already on the books of GSA as potential candidates for certification. The training, over three days, also allowed GSA some time to explain about certification plus labelling and packaging requirements in Ghana, against which GSA’s inspectors are likely to inspect. An expert is also putting together the outline of a training course for those GSA inspectors on how to inspect food producers.

Delays in India resulted in SPS work being re-purposed to other activities and issues beyond the programme’s control in Mozambique prompted a reduction in materials activity compared to plan. SP was able to produce training materials on International Standards and Certification Schemes in the agri-food sector (covering ISO 22000 and GLOBALG.A.P) that were used during the delivery of a 5-day training course in March in Mozambique.

Within the Pacific Small Island Developing States, two SPS-related activities were delivered in Kiribati, which included a Good Hygienic Practices (GHP) training event and coconut value chain assessment for organic certification. In Rwanda, SPS TA and support activities to RSB and the National Agricultural Export Board (NAEB) were provided.

Describe any changes to this output during the past year and any planned changes as a result of this review.

No changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were / are no specific outputs against the indicator.

Output Title	Stronger evidence base on how standards can benefit women, poorer and marginalised groups in developing countries, on what works; and in identification of trade barriers and/or bottlenecks and mitigation responses.
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No
Indicator(s)			Milestone(s) for this review	Progress
Progress towards a wider evidence base on standards benefitting GESI groups (i.e. implementation of the evidence strategy), and examples* of evidence-based decisions to adapt programming for standards to benefit GESI groups within targeted sectors, and of what works in terms of standards benefitting GESI groups. *Examples may reflect work directly with specific groups such as Women in Business Development Inc (WIBDI) in Samoa, or indirect benefits such as training on GESI standards and products with target NSBs.			Streams monitor and document the implementation of their work plan activities which are focused on GESI, quantitatively and qualitatively each quarter. E.g. Flex 236 webinars and ISO 53800 (guidelines for promotion and implementation of gender equality and women's empowerment). / 3 to 4 streams to be selected in year 2 for focus (Bangladesh, Mozambique, Rwanda and PSIDS (Samoa/Kiribati). Initial assessment within focus streams on the context for GESI (e.g. policy status, GESI situation in targeted sectors or value chains, including bottlenecks and trade barriers) and on stakeholder mapping.	GESI initial assessment completed for PSIDS, Mozambique and Rwanda; and in draft for Bangladesh. / A licensing agreement for the Flex 236 webinar was progressed with INNOQ in Mozambique. / BSI provided a gap analysis between the Rwanda Gender Equality Standard. / The remaining streams incorporated GESI activities and monitoring into their work, and is mainstreamed in the reporting against the other indicators.

Briefly describe the output’s activities and provide supporting narrative for the score.

During this Annual Review period, the programme has produced three documents entitled “Initial assessments of the Gender and Social Inclusion (GESI) context” covering the Pacific Small Island Developing States (PSIDS), Mozambique and Rwanda. A draft document has also been produced for Bangladesh. Each of these documents seeks to identify entry points for integrating gender equality and social inclusion (GESI) considerations into SP programming. They provide a comprehensive overview of existing gender and social inequalities related to trade and standardisation in each geography, helping to inform the SP programmatic interventions and the design or review of National Quality Policies.

The initial assessment papers have the potential to guide stakeholders in Quality Infrastructure and trade by shedding light on the unique challenges faced by women and marginalized groups, paving the way for inclusive and equitable actions. As a next step, surveys will be conducted to evaluate the integration of GESI into standards or assess the impact of these standards on GESI at the individual level. By collecting this evidence, stakeholders and the SP teams can gain insights into gaps or challenges, ensuring that future actions are well-informed and tailored to promote gender equality and social inclusion more effectively. Additionally, the findings will help identify areas for improvement and guide targeted interventions.

In addition to the above, SP is already implementing examples of adaptive programming to sharpen focus on women, poorer and marginalised groups. Some of these examples – relating to a change in awareness level among NSBs – have already been provided under Output 1.3 but a selection of other examples at country/regional level include:-

Mozambique.

The Mozambique stream has been selected as one of the focus geographies, because it focuses on cashew nut as the target sector, with around 30% of the farm households producing cashew nut at small scale are headed by women.
Despite the continued volatility in the country following the presidential elections on 9 October 2024, the following outcomes were achieved during this reporting period:
- Successfully concluded a licensing agreement between BSI and INNOQ, IP for the publication of BSI Flex 236 “Enabling the development of inclusive standards. Understanding the role of data and data analysis – Guide” standard, which has now been translated into Portuguese and will be distributed to INNOQ, IP’s TC members.
- Incorporation of GESI-related topics into the Guide on GSP developed under Activity 2 of the project.
- We have engaged with the World Bank-funded project, which is developing a National Standardization Strategy (NSS) together with INNOQ, IP, to ensure that GESI considerations are integrated and effectively addressed.
- The Project Team maintained close collaboration with leaders of the ITC/ SheTrades programme to explore synergies and ensure that the enterprises selected for the “mentoring” pilot programme under Activity 1 were included in the rescheduled Trade Mission to Mozambique – first planned for January and later moved to March 2025.
At the same time, we continued to engage remotely with the four selected SMEs to ensure their commitment throughout this period of civil unrest in Mozambique, with the aim of reactivating project activities with them in the next phase.
Rwanda

Rwanda is the only country to have adopted a dedicated national Gender Equality Standard (RS 560:2023). The standard offers guidance and best practices for organisations and companies to implement gender-sensitive policies and practices internally, with the option to pursue certification. As the first of its kind in Africa, it represents a significant step towards advancing gender equality across all sectors in Rwanda. This milestone reflects the country’s sustained commitment to institutionalising gender parity at all levels.

In March, SP delivered a webinar which provided a gap analysis between the Rwanda Gender Equality Standard (RS 560-2023) and ISO 53800 Gender Equality Guidelines. The webinar, involving assessors from the Rwanda Standards Board (RSB) in addition to delegates from the National Gender Monitoring Office of Rwanda, Private Sector Federation and UNDP, detailed the key differences between ISO 53800 and RS 560, exploring how the new standard could enhance assessments in public institutions and companies. Feedback from the event was very positive, and assessors have been keen to integrate these insights into their own awareness sessions for Rwandan organizations that have yet to be certified.

SP has significantly supported women-led SMEs in Rwanda by promoting gender equality through targeted awareness and training on standards certification, in partnership with the Private Sector Federation (PSF) in Rwanda. A total of 30 entrepreneurs benefited from the initiative, with women making up the majority in both certification schemes: 14 out of 18 participants in the HACCP scheme and 9 out of 12 in the S-Mark scheme. These schemes focused on food processing and cosmetic product manufacturing respectively. The training enhanced participants’ skills improved their competitiveness and increased their access to markets. The initiative included young women entrepreneurs, further supporting inclusive and sustainable economic development.

Ghana

The programme has engaged and supported women-led SMEs in the food sector through tailored mentoring, consultancy and HACCP / GMP awareness training. This work is directly supporting several women entrepreneurs to build their capacity to meet food safety requirements and move towards certification readiness. These SMEs were selected in coordination with the Ghana Standards Authority (GSA) and represent a significant segment of the local food industry. The support included on-site visits to assess current practices, identify areas for improvement and begin the development of action plans to implement food safety management systems aligned with international standards. Feedback from participants indicated high levels of engagement and interest in continuing support through a structured mentoring programme.

Pacific Islands

In collaboration with the British High Commission Suva, the programme delivered training on “Standards to Support International Trade: ISO 9001 & 14001” mainly targeting women-led small businesses in Kiribati and Fiji. The training aimed to equip leaders with knowledge and skills to improve efficiency, customer trust, and environmental responsibility, that enhance their organisations’ competitiveness in international trade. The training in Fiji, especially, was delivered in partnership with the Women Entrepreneurs Business Council (WEBC) under the Fiji Commerce and Employers Federations and received great enthusiasm and appreciation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme may need to revisit its plans to further develop its “Initial assessments of the Gender and Social Inclusion (GESI) context” analysis in view of country prioritisation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The programme has made significant progress in relation to its GESI work in FY 24/25, and creating a workstream / output in direct support of this work has been beneficial. The programme should look to retain funding in this area and continue key pieces of work which could have wider impact (i.e. Rwanda).

## D: VALUE FOR MONEY

The following section assesses the Value for Money delivered by the Standards Partnership programme against the economy, efficiency, effectiveness, equity, and cost-effectiveness criteria.

Key cost drivers and performance

The major cost drivers of the programme rare technical assistance, and travel expenses. The programme’s cost management approach leverages the use of local/regional expertise where available, the co-hosting of project events with beneficiary organisations, negotiated supply rates with training venues and hotels, and co-locating project operations within partner institutions/ premises. Expert missions of a duration greater than one week are preferred where indicated, owing to the savings on flights and reductions to carbon emissions. The use of regional airlines instead of the more expensive global airlines is proving cost-effective. For sophisticated and traditionally expensive activities e.g. IRCA Lead Auditor Courses; the programme seeks to ensure that classroom sizes are maximised whilst remaining within the IRCA course size parameters.

Economy

The programme spend in FY24/25 was £2.715m. This was an overspend of £86k when compared to the final revised budget due to an unforeseen overspend. The reason for the overspend is covered in more detail under Financial Performance in Section F.

Chart 1: Spend in target countries
`
Chart 1 shows the spend in the countries supported through the programme. Ghana was the country with the highest spend with £423k. The second largest was Nigeria with around £280k. Only a small amount of spend occurred in Pakistan as a result of delays generating work plans caused by BSI capacity issues in the region.

Efficiency

107 capacity building events were organised which were attended by 864 entities and 2,808 government officials and staff were trained across the NSBs and administration agencies on areas related to quality infrastructure and trade regulations. This exceeded the overall programmes target: number of capacity building events exceed target by 24%, entities by 367% and individuals trained by 6%. The target of 760 women trained was also exceeded.

The number of private sector entities, SMEs, and women-owned businesses that have received training or support from the SP programme greater exceeded the target. 373 entities received training or support compared to the target of 119, 213% above the target.
BSI state they employed regional trainers (e.g. from Kenya and South Africa in Ghana) and experts who were experienced in priority technical areas (such as inspection, market surveillance and metrology) and were also experienced in providing technical assistance in Africa. They also stated that integration of related activities (e.g., inspection body and market surveillance training) into a properly designed work programme also showed benefits in terms of the clear impact made on both the trainees and their institution.

Effectiveness

The intended impact of the programme is to increase sustainable trade and growth of targeted developing countries through greater income generated by SMEs and private firms.

The Theory of Change clearly sets out the mechanisms through which the technical assistance provided by BSI and TMA support the intended final impact. The effectiveness of the programme as measured by the outcome indicators set out in the logframe was monitored by efforts of both FCDO and the delivery partners BSI and TMA at various stages during the year There is evidence (particularly qualitative) that the programme is:

- Delivering on Outcome 1: Growth of active sustainable and inclusive global & regional value chains in developing countries. This is partly demonstrated through work delivered to public sector institutions (with increasingly more involvement from private sector businesses also) in relation to National Quality Infrastructure.
- The programme’s work on developing a quality culture in other areas (i.e. market surveillance) is also showing progress, although this impact is more at output level at this stage.
- Beneficiary feedback on the programme’s effectiveness, delivered via deep dive sessions, testimonials, surveys and in-person feedback (ARSO Conference) continues to be very positive.
Equity

Output 5 on the SP logframe is specifically designed to monitor the impact of the programme’s Gender, Output 1.1 also sets targets for female staff in NSBs and administration agencies who would receive training. Across the countries, the overall target of 760 was exceeded.

In Ghana, the programme has placed a strong emphasis on inclusive participation, particularly through targeted support for women-led SMEs in the food sector. The SMEs targeted received HACCP and GMP training, as well as certification support to help improve market access and product safety. Across standards development, laboratory work, and regulatory training, efforts were made to encourage gender-balanced participation.

Mozambique: Within the standards and laboratory sectors, relatively large numbers of female staff make up the workforce and will benefit from receiving the training they need to advance. The gender balance for the various project activities can be seen in the MREL data. As the project progresses, the benefits of participating in the formal QI for small and micro enterprises, particularly in the selected value chains (Macadamia and Cashew nuts), many of which are run by women and marginalised individuals, have started to become apparent.

In Jakarta a session was held at the ASEAN Research Launch event called “Empowering Women Entrepreneurs and MSMEs through Regulatory Reforms”, which was co-funded by SP and the ASEAN-UK Economic Integration Programme (EIP) project and raised awareness on the role and importance of standards and quality compliance in empowering women entrepreneurs and MSMEs in ASEAN.

Cost-effectiveness

Logframe statistics demonstrate that the programme has delivered more events and reached more individuals pro rata than last year. Examples of this include an in increase in the number of events delivered (up by 39%) and individuals reached (up by 38%) for output 1, which significantly exceeds the 12% outturn increase received in FY 24/25. The cost per event and cost per individual have also reduced as a result. A similar trend can be seen for Output 3 – where the number of private sector entities trained has more than doubled. These achievements, as set out in the ToC, can lead to an increase in exports from beneficiary countries to the UK and EU and hence contribute economic growth. On a broader level, the programme has received positive feedback from SMEs on how the programme is unlocking market access through meeting standards.

Recommendations

Current impact indicators cannot assess the impact of the programme. We can’t make a causal link between the interventions of the programme with GDP and total trade of the countries. This is because there are too many other factors which influence a countries total trade and GDP. An alternative way to measure the programmes impact could be to assess the increase in trade, particularly exports, from the SMEs that were supported by the interventions.

E: RISK

The SP Programme adopts a balanced risk appetite, which varies across different risk categories. For operational and financial risks, the programme maintains a cautious risk appetite, reflecting FCDO’s willingness to accept only the risks necessary for effective delivery, a focus on value for money and a commitment to managing public money well.

From a strategy and context perspective, the programme has a receptive risk appetite, tolerating some risk on a changing context, which is consistent with the programme branching out to work in new geographies. This includes risks relating to external factors that affect operational delivery such as security instability caused by national and international events – a scenario which was heightened in FY 24/25 due to the prevalence of elections across most SP geographies, and which was connected to the civil unrest in Bangladesh and Mozambique. The programme’s efforts to track those risks, and respond accordingly, enabled SP to temporarily pause activities whilst maintaining relationships with stakeholders. This created the circumstances to allow work to start up again quickly again when in-country conditions allowed.

The programme has a receptive risk appetite in relation to policy and programme delivery. This reflects our acceptance of risk in order to drive long-term change in diverse and challenging contexts, building strategic partnerships to promote shared global prosperity and eradicate poverty. The programme started working with a second delivery partner, TMA towards the end of the financial year. Although diversifying the portfolio in this manner represented a minor risk to programme coherence, this has been mitigated through effective collaboration from all parties, ultimately leading to an MOU being signed between BSI and MOU in June 25. (See Section F – Delivery).

The main risk across the programme during this Annual Review period has been the potential for implementation delays due to activity rephasing, unforeseen operational circumstances or capacity constraints. Although this risk was recognised – and mitigated by BSI in FY 23/24 – the programme encountered some delays scaling up activities after the main MOU had been signed between FCDO and BSI in June, and ultimately struggled to meet increased demand in the South Asia region due to over-reliance on key personnel who were over-stretched. Monthly forecasts indicate that this issue (covered in more detail in Section F – Delivery) was partly attributable to optimism bias that activities would be brought back on track. These issues have been analysed and discussed, and further mitigations have been put in place. (See Recommendation 4).

The lack of trade-facilitating policies and practices by host Governments and Institutions is being directly mitigated via programme activities and also by improved data collection from beneficiaries on other barriers to trade. Close coordination with other donors operating in host countries has also been an important factor. The risk of perceived or actual misuse of programme funds and expert resources has been mitigated through robust financial and control systems which have included internal and external audits, VFM updates provided in quarterly reports, and BSI staff completing Ethics and Code of Conduct training including anti-corruption and anti-bribery practices. A Safeguarding information pack has also been shared with experts and suppliers.

The main risk for the programme in FY 25/26 will be ensuring that delivery partners set aside sufficient time and resources to facilitate a successful handover of programme activities/artefacts to beneficiaries, and also to Trade Centre of Expertise Lead Supplier, once appointed. We anticipate that timescales will mean that handover activities will occur in the final quarter, which has traditionally been the peak period for delivery on the Standards Partnership programme. (See Recommendation 5).

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Standards Partnership started the year with an overall budget of £2.65m, which represented a 25% increase on the final outturn (£2.118m) delivered in FY 23/24. In line with a recommendation from the last Annual Review, FCDO and BSI signed a new MOU at an earlier stage (June 24) with the intention that more work would be delivered in the first half of the year. Unlike the previous financial year which had seen activities scale up significantly from 4 to 13 geographies, FY 24/25 offered more stability / continuity with activities continuing in many of the same countries/regions (Bangladesh, Caribbean, Ghana, India, Mozambique, Nigeria, Rwanda and the Pacific). Some activities, including Ethiopia, that had been less impactful in FY 23/24, were not continued in this reporting period.

Due to unforeseen delays, programme delivery work did not start in earnest until August 24 (monthly spend of £151k). This scenario meant that the programme was playing catch up throughout the year when attempting to deliver in line with its work plans and financial targets. An analysis of spend vs forecast throughout the year shows that the forecasts submitted by BSI (up until the final quarter) were overly optimistic. The underspend risk was also compounded by challenges beyond the programme’s control, including civil unrest in Bangladesh and Mozambique. It should be noted that BSI were highly effective in monitoring and responding to these specific issues and were successful in adapting their portfolio by developing new, impactful workstreams (i.e. ASEAN / Egypt / Ghana DCIC textiles work) in quick time.

During the year, the programme also absorbed new buy-in funding with mixed results. Work in the Pacific has been very successful yielding positive results in areas including NQP development in particular. Some important activities were delivered in India, resulting in positive feedback from participants. A constrained timeframe, resource constraints, and a challenging operating context meant that it was not possible to deliver in line with expectations in Pakistan. The circumstances outlined above meant that the programme ultimately resulted in £300k of Standards Partnership budget being re-purposed to other suppliers / non-Standards workstreams. The programme overspent by £85k against its revised budget as the scale of delivery achieved in the final quarter (and the associated cost) was under-estimated.
In the final quarter of the year, SP entered a new MOU arrangement to start working with TMA for the first time. TMA successfully delivered £245k of work in Uganda, an arrangement which has enabled the programme to revisit activities that had been paused the previous year, whilst piloting a delivery model involving multiple suppliers. Although fairly limited in its scale, this has been an interesting test case for the new Trade Centre of Expertise approach that will be employed in FY 26/27. BSI and TMA are exploring opportunities (and signed an MOU to this effect in June 25) to collaborate at regional level.

The programme has benefitted from deep local knowledge and relationships and sector expertise. BSI’s use of local consultants in countries has underpinned a sustainable approach that will continue once programme activities come to an end. This approach also created an environment in which it was possible to re-engage with Bangladesh and Mozambique and resume activities quickly once the circumstances permitted. (It should be noted that, as at June 25, the wider operating context in these two countries continues to be a challenge). Despite the challenges flagged above, output targets (and results delivered in FY 23/24) have been exceeded and positive feedback confirms that the programme has delivered in line with beneficiary requirements / expectations.

G: MONITORING, EVIDENCE AND LEARNING

The Standards Partnership has continued delivering against its MREL plan from last year. This has included a range of actions from refining the logframe to reviewing data collection and the theory of change alongside the standard programme quarterly and annual reporting. The supplier has also led sensitisation sessions with its country teams and partners on reporting templates and data requirements to ensure consistency across the programme. There have also been deep dives into each country stream to support this as well. In addition, the supplier has looked to draw lessons learnt from one country to another through regional learning (e.g. exporting the NQP approach in St Lucia to other CROSQ members) and measuring over time using a matrix to understand institutional change and its progress.

The supplier continues to engage a senior MREL Expert to drive the programme’s related plans. They are also involved across the work streams to ensure the programme delivers MREL activities including data collection and documentation against indicators, improves their process for identifying and documenting quick wins, success stories and ensures learning is taken on board. During the year additional ISO data was included to improve an outcome indicator alongside other adjustments on data gathering. The supplier’s MREL plan will continue to be delivered, with an updated timeline, for the next year of delivery.

The programme SRO has also commissioned anonymous feedback direct from beneficiary firms and officials to understand supplier performance and support improvements to the programme. In June 25, the programme SRO combined an opportunity to attend the ARSO Conference in Zanzibar with meetings with representatives from all of the African NSB’s being supported by the programme. This trip enhanced team learning and provided an opportunity to discuss the regional context (and associated challenges) whilst also gaining valuable in-person feedback on progress being made.

During the period under review, the theory of change was reviewed and sense checked to ensure logic remained correct for the programme and affirmed the original business case with no need for amendments. There has also been a focus on GESI where output 5 has remained highly relevant with completed assessments to inform the programme.

Date of last narrative financial report	11 June 25	Date of last audited annual statement

List of Acronyms

AQP	African Quality Policy
AR	Annual Review
ARSO	African Regional Standards Organisation
ASEAN	Association of Southeast Nations
BAB	Bangladeshi Accreditation Board
BIPD	British Investment Partnerships Directorate
BSI	British Standards Institution (Programme Delivery Partner)
BSTI	Bangladesh Standards and Testing Institution
CB	Capacity Building
CBAM	Carbon Borders Adjustment Mechanism
COE	Centre of Expertise
CODEX	Codex Alimentarius – International Recognized Food Standards
CROSQ	Caricom Regional Organisation for Standards and Quality
CSN	Commonwealth Standards Network
DCIC	Developing Countries Import Campaign
DCTS	Developing Country Trading Scheme
DESNZ	Department for Energy Security and Net Zero
ETIP	Enhanced Trade and Investment Partnership (UK-Nigeria)
FCDO	Foreign, Commonwealth & Development Office
FDA	Food and Drugs Authority
FY	Financial Year
GAP	Good Agricultural Practices
GESI	Gender, Equality and Social Inclusion
GLOBAL GAP	Global Good Agricultural Practice
GNI	Gross National Income
GoB	Government of Bangladesh
GSA	Ghana Standards Authority
HACCP	Hazard Analysis and Critical Control Point
INNOQ	Instituto Nacional de Normalização e Qualidade / (Mozambique National Standards Body)
IEC	International Electrotechnical Commission
ISO	International Organization for Standardization
IWA	International Workshop Agreements
MOU	Memorandum of Understanding
MREL	Monitoring, Reporting, Evaluation and Learning
MSME	Micro, Small and Medium-sized Enterprises
NEPC	Nigerian Export Promotion Council
NPLI	National Physical Laboratory India
NQC	National Quality Council
NQI	National Quality Infrastructure
NQP	National Quality Policy
NSB	National Standards Bodies
ODA	Official Development Assistance
OPSS	Office for Product Safety and Standards
PACER	Pacific Agreement on Closer Economic Relations
PAQI	Pan-African Quality Infrastructure
PCR	Programme Completion Review
PRO	Programme Reporting Officer
PSF	Private Sector Federation
PSIDS	Pacific Small Island Developing States
QR	Quarterly Report
RSB	Rwanda Standards Board
RTDA	Regional Trade and Development Advisors
SDO	Standards Development Organisations
SIDS	Small Island Developing States
SLBS	Saint Lucia Bureau of Standards
SON	Standards Organization of Nigeria
SP	Standards Partnership
SPS	Sanitary and PhytoSanitary (Food Safety)
SRO	Senior Responsible Owner
SME	Small Medium Enterprise
TA	Technical Assistance
TBT	Technical Barriers to Trade
TMA	TradeMark Africa
TC	Technical Committee
TOC	Theory of Change
TfD	Trade for Development Department (within FCDO)
TSI	Trading Standards Inspectors
UNBS	Uganda National Bureau of Standards
UNDP	United Nations Development Programme
UNECE	United Nations Economic Commission for Europe
UNIDO	United Nations Industrial Development Organization
VFM	Value For Money
WIBDI	Women in Business Development Incorporated