## Annual Review

Title: Somalia Stability Fund III
Programme Value £ (full life): Maximum BC value is £200m. Noting: / - £20m earmarked for the UN Window as required. / - UK commitment up to £60m and targeting to leverage £140m from other donors		Review date: May 2025
Programme Code: 300916	AMP start date: / 23 Mar 2022	AMP end date: / 31 Mar 2029

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	B	B
Risk Rating	Severe	Severe	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0002930.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005056.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

The Somalia Stability Fund (SSF/the Fund) III is a multi-donor[1] flagship programme, which builds on two previous phases of programming. The six-year programme (with a possibility of a two-year extension) seeks to support more inclusive political agreements at multiple levels of government and to address historic grievances that have undermined trust and contributed to the ongoing democratic deficit in Somalia.
[1] SSF III is funded by seven donors (Denmark, EU Delegation in Somalia, USA, Netherlands, Germany, Sweden and UK as the Lead Donor). The US contributed $2m at the start of the programme, but the recent pause on development assistance will result in that likely being the only disbursement to the Fund. Sweden has not fulfilled its initial commitment.

It does this by creating the necessary space to establish democratic processes at the national and sub-national level; supporting more representative, inclusive and effective local governance structures; investing in efforts to strengthen the social contract between citizens and the state to increase legitimacy; and ensuring that new institutions are more accountable. SSF III delivers through: i) government entities at the FGS level and in all FMSs; ii) thematic consortia as delivery partners throughout the lifecycle of the Fund; and iii) entities contracted for one-off initiatives.

Context:
Over the past year, Somalia has continued to grapple with deep-rooted instability, driven by strained federal-state relations, stalled governance reforms and persistent security threats from Al-Shabaab (AS).

The programme was designed at a time of optimism, anticipating that the 2021 elections would offer an opportunity for the emergence of a broadly legitimate Federal Government of Somalia (FGS). The delayed start of the programme until 2023 resulted in the programme operating in a different context and with a new government. This led to further delays in years 1 and 2 in order to agree a governance framework for the SSF with the FGS and to stand up a delivery modality that could work through government and in support through non-governmental partners. Changes included restructuring within the fund manager to develop a technical unit that could better bring thematic coherence to fund activity.

The time lag also presented challenges to underpinning assumptions. The programme was designed to support delivery of the Constitution and other national frameworks[2], which seek to guide local government formation and function, including District Councils, whilst recognising also that communal reconciliation would be a critical element. However, more recent political fragmentation has undermined efforts to advance reconciliation and implement ‘one-person, one-vote’ elections, particularly with Puntland and Jubaland states, where disputes over electoral processes and federal overreach led to institutional boycotts.
[2] SSF III activities seek to operationalise the vision of Somalia’s Constitution and the Government’s Vision 2060, as well as the objectives articulated under the National Transformation Plan, the Wadajir Framework, and the National Reconciliation Framework.

Meanwhile there have been security setbacks. The transition from the African Union Transition Mission in Somalia (ATMIS) to the Africa Union Support and Stabilisation Mission (AUSSOM), the growing influence of Egypt, and the Ethiopia–Somaliland Memorandum of Understanding (MoU) in 2024 strained regional dynamics. These uncertainties and political fragmentation have provided an opportunity for Al-Shabaab (AS) to maintain its operational momentum, launching coordinated attacks across Hirshabelle and Southwest State in early 2025, regaining key territories, and posing a threat to Mogadishu.
Further, the funding environment is changing. The programme design anticipated that a £60m investment from the UK would leverage an additional £60m - £120m from international partners[3]. The programme has currently spent £14.2m; and while not subject to budget cuts to date, resource constraints mean it is unlikely that the programme value will reach £180m, impacting on the level of ambition and scope.
[3] The BC was designed on an estimated value of £200m, with £20m to potentially disbursed through the UN window.
These changes go beyond the scale of this one programme. The SSF was intended to complement and coordinate with multilateral investments and other bilateral programmes, including the UK’s PREMIS (ending this year) and USAID’s People Centered Governance (PCG) programme. Since the last AR, the pause on USAID funding has led to the closure of key USAID programmes, weakening federal government service delivery and reform capacity and resulting in programming gaps, as well as a cessation of US support to the Fund.
Nevertheless, there are opportunities. The World Bank’s $20m grant (with an additional $20m in anticipated counterpart funding from communities, the private sector and the Somalia Multi-Partner Fund) to the government’s Bulsho programme (Strengthening Community and Local Institutions for Social Cohesion, Inclusion and Resilience) has recently been approved. Bulsho shares SSF III’s objectives and seeks to fund similar activities, including capacity building assistance for local officials and community leaders to support decentralisation objectives; support for a local social contract platform, and provision of matching grants to incentivise collaboration and deliver sustainable adaption and service delivery solutions. The IDA grant, however, is on-budget; it is unlikely to have the flexibility of the SSF or provide the same platform for political discourse. It does though provide valuable opportunities for collaboration.

Review Scope

This review should cover the period of the second year of implementation from July 2024 until June 2025. However, data was only available for the period until the end of the third quarter.

The review team comprised of a Senior Governance Adviser and two Conflict Advisers, one of whom had legacy experience of working on SSF III as well as its predecessors. The review draws on quarterly reports, key programme documents and examples of programme outputs, as well as discussions with Fund and Technical Unit staff, implementing partners, government stakeholders and development partners held between 22 May – 8 June 2025.

Summary supporting narrative for the overall score in this review

The programme scores a B for the year under review. Although the majority of milestones were assessed as met or on track to be met, the score takes into consideration the late setting and approval of targets (within a month of the review); the limitations of the evidence provided; challenges with measurement; and limited focus on impact. This is covered in greater detail in Section B.

The programme was assessed across five weighted outputs and one unweighted output. The weighted outputs included Political Settlement, Conciliation, Democratisation and Local Governance, Social Contract, and Research. A new output, Coordination, was introduced but remains unscored and unweighted for this review cycle.

The scoring breakdown is as follows:

	Output	Weighting	Score
1	Political Settlement	30%	B
2	Conciliation	10%	B
3	Democratisation and Local Governance	20%	A
4	Social Contract	20%	A
5	Research	20%	A
6 (new)	Coordination	unweighted	Not scored

Using the FCDO Annual Review calculator, the overall weighted programme score is 2.60, which falls between a B and A rating – but in agreement with the Development Director and SRO the rating was set as a B, indicating that the programme is broadly on track to achieve its outputs, with some areas demonstrating stronger performance, but with significant improvements required elsewhere.

As noted above, the year under review has seen a deterioration in stability in Somalia, driven by strained federal-state relations, stalled governance reforms, and persistent security threats from Al-Shabaab (AS). Whilst being the underpinning justification for the programme, these issues have equally presented challenges for delivery. An FGS-imposed pause, which commenced in April 2024 and was covered by the last Annual Review, was only lifted on 2 September 2024. To reach this agreement, the Fund had to demonstrate its alignment with the FGS, through revised programme governance structures, and build trust, primarily through the introduction of a project-based approach. This has introduced a tension between whether the FGS should be the sole entry point for the programme or whether a multi-level approach, as envisioned by SSF III Business Case (BC) in line with the Constitution and other national frameworks, is more appropriate. The lack of a settled consensus between the FGS and the FMS, amplified by the similar lack of unified vision of how the SSF should be a part of the political economy of state formation, has impacted on the programme’s ability to operate.

Major lessons and recommendations for the year ahead

Approach to State building. Given the slow progress of reform and continued contestation around the Somali state, the programme and its donors need to consider whether the design approach of supporting reform delivery continues to be appropriate. The programme has strengths in being able to work directly with national actors on issues on the fundamentals of resource distribution in the state. At the same time, it works across Somalia at the district level working to foster stability in critical geographies. At best, the programme will continue to operate across multiple levels avoiding being badged as one or the other and flexing as opportunities arise. The confusion between a top-down or bottom-up approach is partly informed by the lack of a clear articulation of what the programme aims to achieve and pathways to deliver it meaning the workstreams remain conceptual in nature and open to interpretation.

Partnerships. The new governance structures introduced following the last AR have had a beneficial impact. The High-Level Steering Committee (HLSC) and Technical Joint Steering Committee (TJSC) meetings have provided an opportunity to rebuild relationships with government partners and for sensitive issues to be discussed in a formal collective forum. Although necessary to regain the buy-in of the FGS and build their ownership, the HLSC has reduced senior participation of the FMS governments, but more critically, has removed one opportunity for consortia members to participate strategically in the programme. The Partner Days held in May were a positive initial step and demonstrated appetite from all implementing partners for greater involvement in programme design and delivery which should be capitalised on.

Delivery Modalities. Despite building on two previous phases, the programme has not yet integrated all of the key lessons of this previous programming in its delivery. The BC allowed for a programme duration of 7-10 years in recognition of the need for longer-term, sustained delivery to achieve the ambitious results. In the context of the FGS-imposed pause, the Fund introduced a requirement for concepts concept notes to be drafted and approved for each project intervention as the key delivery modality, with the aim of enhancing transparency of programme activities and building trust with the FGS. This enabled implementation to quickly commence as soon as the pause was lifted and has contributed to the results delivered during this review period. That said, as well as being cumbersome for partners, this modality undermines a longer-term outlook and risks the Fund being ‘projectized’ with investments failing to contribute to results that are more than the sum of their parts. Furthermore, the programme failed to capitalise on the opportunity presented by this modality to break down workstream and implementing partner silos. However, some level of results reporting will always be required over the short-term merging both a longer-term ambition with shorter milestones to build confidence among donors on partners on delivery.
Adaptation. Although designed as a Problem Driven Iterative Approach (PDIA) - based programme, SSF III is currently flexible, but not adaptive. Flexibility and adaptation, informed by an agreed end-state, are critical, enabling the programme to test what works. Given the contextual variety in Somalia, ‘one size’ will not ‘fit all’ and the programme needs to utilise the PDIA approach to assess and test what combination and sequencing of interventions from across the workstream deliver sustainable results. Linked to the previous point, agreement is required on whether the programme can flex between delivering the Federal frameworks where feasible and working with and improving the governance mechanisms that currently operate, noting the resilience of informal or clan-based authorities in local spaces. This decision should be informed by available global and Somalia-specific evidence.
Scale. Although the programme has not been directly[4] affected by reductions in Official Development Assistance (ODA) to date, it is anticipated that at this time of profound change, with conflicts overseas undermining security and prosperity, this will manifest itself in the next programme year. For the UK, the ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, and it is likely that other Fund development partners will also see impacts on their ODA. As such, it is unlikely that the anticipated overall programme budget will reach its target value of up to £200 million. The UK’s Country Business Plan’s anticipated shift to a smaller number of ‘portfolio’ programmes in Somalia offers an opportunity to revisit the scope of SSF III and for the Fund architecture to provide a platform for this transition.
[4] The programme has indirectly been impacted by the withdrawal of USAID and the closure of complementary programming. The US is unlikely to make a further commitment to the Fund, which is also the case for Sweden.

Recommendations:

1. Theory of Change: To allow the programme to deliver intended outcomes, the ToC should be revisited. The Fund should hold a ToC workshop before the end of the programme year to bring together all consortia members and implementing partners, enabling the Fund to benefit from this combined expertise, support co-creation and enhance communication and coordination. Concepts need to be interrogated to build common understanding and agreement on pathways, recognising the interconnectedness between the workstreams and moving away from the current hierarchical format. The revised ToC should be reviewed by donors and utilised to build consensus regarding the programme’s approach to enabling inclusive dialogue, stabilisation and building stability, and what can be achieved with a realistic programme value. As part of this, the SSF should articulate how its supports equality and inclusion towards its stability objectives. Clarity on the envisaged impact of the programme will enable the programme to better follow a PDIA modality.
SSF Team by end of August 2025

2. Alignment between the Annual Review and Programme Reporting Cycle: Another AR should be conducted to reset the date and align with programme reporting cycles. Informed by a revised ToC, this proposed timeframe would enable the AR to assess the programme’s potential to deliver the UK’s refined Somalia Business Plan and to adapt to deliver additional workstreams identified as important to deliver improved stability in Somalia.
FCDO Somalia by end of October 2025

3. Results Framework: Informed by the ToC, the Results Framework should be revised with appropriate annual targets for the life of the programme, to support a long-term focus and greater objectivity. There should be an appropriate balance between qualitative and quantitative indicators which seek to capture results and impact, transitioning from process and activity targets. As the programme matures, the RF needs to assess the impact of activities and each output’s contribution to the wider programme. For example, the RF should seek to capture dialogue work at all levels and the Fund’s influence, drawing on existing work on how this can best be done. The RF should take gender equality and social inclusion into account with indicators that can be used to track progress on how far the SSF is supporting inclusion.
SSF Team by end of August 2025

4. Improve Partner Coordination: To enable the programme to harness the collective expertise of implementing partners new coordination mechanisms should be introduced that enable their strategic participation in programme design and delivery, as well as improve information-sharing. The proposed ToC workshop offers a good entry point for this and should be followed up by regular thematic and problem-based coordination meetings to promote co-creation and genuine collaboration. Partners should also be invited to present to the HLSC and TJSC, supporting visibility of analysis and activities and informing discussion and agreement.
SSF Team by end of August 2025

5. Evidence: A step change is required so that SSF III can position itself as a thought-leader. Research investments should be based on existing global and Somalia-specific evidence, strategically responding to gaps in understanding and capturing learning generated through programming. This approach should be determined as part of the ToC review and should inform a more ‘propositional’ approach; the Fund should shift from presenting papers to considered, evidence-based recommendation submissions to the donors and wider.
SSF Team by end of August 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (ToC) was last updated in 2023, and the results framework (RF) was updated shortly before the Annual Review. There are four interconnected workstreams/outputs informed by a fifth, research focused, workstream:

1. Political Settlement: Supporting political processes at multiple levels to effectively address contentious issues as part of transforming the political settlement to be more inclusive and sustainable. The programme has shifted its language to ‘Political Dialogue’ to better reflect the objective and to reduce misunderstanding.
2. Conciliation: Progress towards a strategic/cohesive approach to social conciliation/healing in support of a more sustainable political settlement.
3. Democratisation and local governance: Progress towards increased representation, access to services, and support for democratic processes in governance.
4. Social contract: Support improved accountability (including transparency and visibility) of authorities at federal, state & district levels through support for internal and external policy development/review and mechanisms.
5. Research: An informed SSF, donor community, and partners contribute to a strengthened, more inclusive, and more sustainable political settlement in Somalia.

A new sixth workstream on coordination has been included in the revised RF but has not been scored as part of this AR.

The assumptions underpinning the programme are that If
1. Somali political and civic actors actively engage in collaborative and inclusive political processes in a genuine effort to transform political settlements;
2. National and subnational policies, systems, and institutions contribute towards and facilitate inclusive governance and civic-ness;
3. Government institutions work towards being more accountable and responsive to citizens, and citizens from all backgrounds are more capable to and actively engage in holding government institutions to account;

Then political and inter-communal contention in Somalia will unfold in a more formally rule-based, inclusive, and non-violent manner.

The programme is a political instrument designed to enable conciliation between communities, between political actors, and between communities and political actors, leading to a political settlement. This was ambitious and has been subject to a fast-changing context. Similarly, the assumption that there is a linear relationship between political settlement at the federal level and progressing stability through the other programme workstreams has not held and needs to be revisited to inform a context-specific approach able to test and adapt what delivers stability in different conditions and geographical areas.

There is a lack of consensus among the international community as well as Somalis on what state building should look like which renders impossible a common understanding of what SSFIII should aim to achieve. An agreed consensus between the donors, engaging with the government at all levels, is an important next step. Then, an updated coherent and contextual vision for SSFIII should be agreed. Alongside this, there should be an assessment as to whether the positive benefit assumption still holds despite the multiple challenges in Somalia. The risk of making things worse in light of changing assumptions needs to be continually assessed to ensure the positive benefit assumption still holds.

Evolving security challenges, shifts in political dynamics and a mixed relationship with the FGS reveal that the output statements are too ambitious. Outputs should be simpler and more realistic. The workstreams would benefit from greater interconnectivity and indicators should properly capture all relevant activity undertaken across the workstreams, key examples being political analysis and conciliation efforts. The language of workstream/output one is particularly challenging. It should be reframed in more tangible ‘SMART’ language.

The move to identifying opportunities where SSFIII is able to support was a pragmatic response to delays and blockages in wider delivery but has the potential to become too disparate, losing sight of the overall aim of the programme and failing to add up to more than the sum of its individual parts. Although designed to be an adaptive programme, this has yet to materialise given the lack of clarity and consensus on programme aims and the pathways to achieve them.

The focus on restarting delivery has also been at the expense of consideration of the ‘Leave no one Behind’ agenda. Information in the Results Framework is not disaggregated by age, sex, disability or geography. Initiatives that seek to include and empower women and youth to participate in conciliation and democratic processes have recently commenced, providing a foundation to build on but requires scaling up and an inclusion focus needs to be mainstreamed across the programme.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The ability to assess progress over the last year and impact has been challenging for a number of reasons, in addition to the external challenges set out above. The Annual Review is not aligned with the programme’s reporting cycle, which ends in July. As such, results for the year were not available at the time of the review; and some preliminary reports were drafted to cover three quarters of implementation. This AR therefore only assesses activities conducted from 1st July 2024 to 31st March 2025.

Progress against outcomes[5] is assessed by the external MEL partner as slightly off track, except for Outcome 2 where all the indicators are assessed as on track. This suggests optimism bias given that delivery has been paused on two separate occasions during the life of the programme and output delivery is not on track to meet expectations. To address this risk, external, quantitative measurements should be identified to complement the methods of measurement currently included. Although there has been activity towards each of the programme outcomes it has not been at a scale or with the impact required.
[5] Outcome 1: Somali political and civic actors are actively engaging in collaborative and inclusive political processes in a genuine effort to transform political settlements Outcome 2: National and subnational policies, systems, and institutions contribute towards and facilitate inclusive governance and civic-ness Outcome 3: Government institutions work towards being more accountable and responsive to citizens, and citizens from all backgrounds are more capable to and actively engage in holding government institutions to account

The purpose and approach of the programme needs to be accepted by key stakeholders for real progress to be made. Although an accommodation with the FGS was found to enable implementation to recommence in September, the agreements limit the ability for the programme to be delivered as designed and workstream one remains on hold. The implementation pause enabled the Fund to address capacity gaps and prepare for implementation. Important foundations for delivery are now in place, but the strategic direction and pathways need to be agreed before results can be delivered.

According to the Results Framework (RF), the programme is ‘on track’ to deliver 13 out of 15 milestones. However, the RF is incomplete and fails to capture the entirety of the work being delivered under the programme, the synergies between them or the results they have delivered. Despite recommendations in the last Annual Review, the RF has not been adequately simplified or revised to include a sensible balance between qualitative and quantitative indicators to assess performance. It presents a reduced form of ‘progress markers’ without all the levels for marking progress, including expected results. Whilst appropriate for a rapidly changing context such as Somalia, progress markers should form the basis for structured conversations to track progress. In addition, the RF currently only has milestone targets set for this year under review, and these were only agreed and approved in March 2025[6], raising questions on the extent to which they were set according to the activity which was in progress. The underpinning partner log frame targets were only agreed in April.
[6] Milestones were not submitted to the FCDO for approval until February due to the need for certain operations (such as setting up partnerships, agreeing the new programming model) to be completed before this was possible.

Although the programme has not been affected by budget cuts during the reporting period, as noted above, in the context of shifting global development assistance, SSF III is unlikely to meet the lifetime funding value envisaged in the BC. In the period under review, USAID’s withdrawal has resulted in the closure of key programmes that the Fund sought to complement and coordinate with. The UK Spending Review and related business planning process will also require that reduced funding be rigorously prioritised and streamline the number of programmes. This provides an opportunity to assess whether SSF III is positioned to be a vehicle to deliver on other workstreams, such as security and justice, as the Somalia programme transitions to a portfolio approach.

An independent evaluation was not planned, but given the level of investment, the complexity of the programme and its operating context as well as the severity of risk, it is recommended that this be explored.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

SSF III seeks to work on the most fundamental and challenging issues faced by Somalia and continues to be central to the delivery of the current FCDO Somalia Business Plan. As the Business Plan evolves into a portfolio approach, the programme has the potential to support this transition and accelerate implementation.

There is consensus that the programme provides a valuable platform for sensitive issues to be discussed and debated, with some development partners seeing it as the only forum for this. The very process of reaching an accommodation with the FGS to allow implementation to recommence should be viewed as part of programme delivery, enabling discussion with the FGS on how the programme should be implemented and how far it should be focused on the needs of the centralized state. This tension will continue to require management, ensuring that the Fund delivers genuine impact and does not simply respond to requests from government (at all levels), recognizing that the programme was designed around a formal governance structure and political will that has not materialized.

The programme has made good progress since the FGS-imposed pause[7] was lifted in September, informed by preparations made during those five months. This includes recruitment to the Technical Support Unit (TSU), delivery of new programme governance arrangements[8], and implementation against the agreed MoUs with the FGS and FMS. The consensus amongst Fund donors interviewed was that the programme has delivered well given the challenging context in which the Fund operates. However, as an objective assessment of year two of programme implementation, these activities feel more like inception phase activities rather than what would normally be expected in terms of delivery at this point in programme maturity. It is critical that the Fund builds on the accommodation that has been reached and on this foundational activity for outer year programming, in line with the intended long-term and PDIA approach. There is a risk that an annual approach that is not built on an agreement on what success looks like for the programme will result in repetitive input activity throughout the programme lifetime.
[7] This is the second FGS-imposed pause since SSF III commenced.
[8] The High-level Steering Committee was established to improve communication, provide a strategic steer and oversight of the programme. The Technical Joint Steering Committee provides a forum for the FMS to also engage.

Although the Fund has invested significantly in the collection of evidence on programme activity and the external context, it has yet to mature into a PDIA programme which harnesses these inputs effectively to inform design and delivery. The only area where the programme operates adaptively is the work being conducted by the state coordinators, where real-time political economy analysis is organically being applied, but this operates outside of the MEL framework. The investment is further undermined by the fact that it is not informed by evidence of ‘what works’, drawing on extensive existing analysis of what is required to achieve the programme objectives both globally and in Somalia.

Although the creation of the TSU has been positive, the Fund should consider whether this expertise should be expanded. Value for Money (VfM) should assess effectiveness as well as economy, and further consideration should be given to whether further expertise is required. The programme does not have access to Gender Equality and Social Inclusion advice or a political settlement adviser to oversee the dialogue.

## C. DETAILED OUTPUT SCORING

Output Title	Political Settlement: Supporting political processes at multiple levels to effectively address contentious issues as part of transforming the political settlement to be more inclusive and sustainable.
Output number:		1	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1.1. Extent to which the support provided is relevant to reaching a more sustainable and democratic national settlement	At least ‘Amber’ rating	Full Output Assessment unavailable at time of review (due July)
1.1.2. Extent to which support provided promotes both vertical and horizontal inclusivity	At least ‘Amber’ rating
1.1.3. Evidence of effective uptake of, engagement with, and/or participation in support activities and outputs among target audiences	At least ‘Amber’ rating
1.2.1. Extent to which the support provided is relevant to reaching a more sustainable and democratic sub-national settlement	At least ‘Amber’ rating
1.2.2. Extent to which support provided promotes both vertical and horizontal inclusivity	At least ‘Amber’ rating
1.2.3. Evidence of effective uptake of, engagement with, and/or participation in support activities and outputs among target audiences	At least ‘Amber’ rating

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 scores a B. The output is challenging to assess as the milestones are not sufficiently tangible to enable genuine measurement[9] and do not capture results or impact. The methods of measurement, a self-assessment by the Somalia Dialogue Platform (SDP)[10] and an annual assessment by the MEL partner, were not available at the time of the review. The output only measures the work of the SDP, failing to capture the full range of aligned delivery. The score for this output is informed by the extended FGS-imposed pause on delivery of this workstream, which is still in force.
[9] The milestone of ‘at least Amber rating’ was the same target for Year 1
[10] An interim report was developed by a consultant covering the period 1st July 2024 to 31st March 2025 and was shared with the FCDO at the end of the review. This has informed assessment of this output.

Over the first three quarters of the programme year, the Somali Dialogue Platform (SDP) Political Advisers conducted nine missions to Mogadishu, Puntland, Kismayo, and Garowe, engaging senior officials from the FGS and FMS to strengthen bilateral relationships and enrich analysis. They also produced 32 Weekly Political Updates, authored two ad hoc political analysis papers addressing electoral dynamics and instability in the Gedo region, and delivered five in-depth briefings and political exchanges to the Joint Donor Committee (JDC) and SSF, addressing issues such as the ATMIS transition, trends in Somalia’s political settlement, the viability of elections, and fiscal federalism. Additionally, SDP published two comprehensive six-month Political Settlement Trends Analysis Reports (September 2024 and February 2025).

SDP’s analytical products (a combination of timely/rapid analysis on topical issues and in-depth research reports) continue to be valued by SSF III donors. They have provided the Fund and donors with strategic understanding of Somalia’s complex political environment. However, the review found that these products were not consistently or comprehensively shared with other SSF implementing partners.

The Fund is generating significant quantities of analysis, with the risk of overlap and an imbalance between analysis and activity. There is limited evidence on how it has informed positions or activity, or how it will be integrated into the adaptation process as more analysis is generated.

The FGS agreement that the Fund could recommence implementation did not cover this politically sensitive workstream; at the time of the review direct implementation of activities remained paused. The FGS has cited their concern that SDP is not a neutral actor[11]; SDP claim that they continue to enjoy good access and that this is an ‘instrumentalization’ of the FGS’s wider concern about the workstream.
[11] A previous member of the SDP had political aspirations but has since distanced himself from the platform to preserve their neutrality.

The importance of clarity on programme pathways and agreement on the balance between the programme’s ambition and risk appetite is seen most keenly in relation to this output. Direction from donors not to work on the delivery of elections impacted on planned electoral dialogues and support to elections and is limiting the Fund’s ability to work on some of the contentious issues that are fundamental to making the political settlement more inclusive and sustainable. Agreement is needed on whether the programme continues to be guided by Federal Frameworks and guided by the FGS or also provides wider support to improve democratic governance where the context is not yet conducive for One Person One Vote elections[12] .
[12] The question revolves around whether the programme should work towards ‘good enough’ governance with the aim of creating the conditions and demand for democratic governance in line with national frameworks, working with and improving the representation, accountability and responsiveness of existing governance structures.

Although not currently assessed, activities across the workstreams also support delivery of this output, as well as the analysis and work delivered by the SSF Coordinators to drive activity at the State and District levels. In the last year, implementation under the Memoranda of Understanding (MoU) has commenced, with all five States as well as the Regional Administration of Mogadishu and the Ministries of Interior (MoI) and Planning (MoP) at the Federal level. The process of agreeing these MoUs and the delivery of associated projects are assessed by this review to be the primary vehicle for delivering across the indicators of this Output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As noted above, the RF was only updated to set milestones for Year 2 and approved in March.

The term ‘Political Settlement’ is sensitive and is interpreted differently by stakeholders. The Fund has transitioned to ‘Political Dialogue’ which feels more appropriate at output level. Contribution to a political settlement is more appropriate at the outcome or impact level. This should be further considered as part of the recommended revision of the ToC.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Any activity under the UN window of the SSF needs to be fully captured in the relevant workstream results, as was not the case this year. Further, the governance arrangements of when to use the UN window to fund activity should be reviewed to ensure limited funds are used most effectively in line with SSF objectives.

Not applicable: There has not been activity under the UN window during this period.

SDP’s performance should not be measured by input-based activities (number of reports, briefings, workshops, and meetings etc.) but should also be assessed from a value for money (VfM) perspective.

Not delivered: Although SDP reports on VfM in quarterly and annual reporting, this recommendation has not been sufficiently responded to. The Fund does not currently assess the results and impact of activities, with measurement continuing to focus on inputs. Given the maturity of the programme, this must be prioritised going forward.

This output delivery should be linked to two key processes: (i) the Somali transformation process for example the Constitutional review process, the Somalia Transformation Plan, National Reconciliation Framework (ii) development partners engagement on state building.

Partially delivered: In terms of implementation, SDP activity has been aligned with this recommendation. The SDP has engaged in the Constitutional Review Process, briefing key actors and lobbying for a more inclusive process. The SDP also provides valuable studies and political trend analysis to inform and facilitate discussion on state building, its trajectory, and partner engagement. It is recommended that the balance between these two processes needs to be adjusted if the output is to be delivered, with less emphasis on reporting and greater investment in the actual process of political dialogue, if feasible. At the time of writing, SDP’s activities under this output continue to be under discussion with FGS MOIFAR. Measurement should focus on the outcomes of dialogues, attempting to capture influence, as well as the extent to which analysis is used beyond the programme by partners.

Collaboration between the Fund Manager and SDP has shown promising results. However, there is scope for further alignment and cohesion. But efforts to bring more cohesion in the programme should be calibrated with the importance of giving SDP a degree of autonomy. SSF III should ensure that SDP preserves its distinct identity.

Not delivered: The Fund’s position is that it is not feasible for SDP to maintain a distinct identity from the programme on the ground that their outputs need be integrated in the project cycle process. This review recommends that this be subject to further discussion and review, thoroughly assessing the advantages and disadvantages as well as how and where SDP is best placed to support delivery under a revised ToC. The perception, real or imagined, that SDP is a political opposition body has certainly provided the FGS with an argument to pause the programme, impacting on delivery in year 2 and continuing to impact on this output. In parallel, the SDP have been able to continue their direct engagement with the FGS and report that their efforts supported the agreement on implementation to recommence.

Recommendations:

ToC and RF: it is inaccurate to assume that there is a linear relationship between political settlement at the federal level and progressing stability through the other programme workstreams. An expanded understanding of both the wider activities that contribute to this output and the inter-connectedness of the workstreams, that does not privilege or rely on national dialogue, is needed to recognise the contribution the whole programme makes to stability in Somalia and to test what works to create the incentives for Somalia's political leaders to engage meaningfully to inclusive political dialogue to address key drivers of conflict, including centre-periphery tensions. The RF should be revised to capture relevant political dialogue work from across the workstreams, including the work of the state coordinators which is currently not reflected anywhere. Milestones should be measurable with SMART indicators.
SSF by August 2025

Recommendations from the Year 1 AR: should be reviewed. The Fund should clearly articulate how they will be delivered and by when. If it is determined that a recommendation is not applicable, this should be explained in writing to the FCDO.
SSF by August 2025

Output Title	Conciliation (Dhab-u-heshiin): Progress towards a strategic/cohesive approach to social conciliation/healing in support of a more sustainable political settlement
Output number:		2	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 2.1: Support to design & implementation of national & subnational policy & processes to address grievances
2.1.1. Supported (re)conciliation frameworks, policies, and plans are more harmonised and aligned at regional and federal level	At least three state-level strategies supported to harmonise with state and federal-level frameworks, with at least five permissive or two non-permissive districts for implementation identified with government partners.	Moderately did not meet expectation / SSF III supported four state-level strategies aligned with the National Reconciliation Framework (NRF): / State Strategies: Banadir Regional Administration (BRA) and Hirshabelle / Galmudug Reconciliation Framework / Support to Jubaland to launch and disseminate the Dispute Settlement Strategy / Support to SWS - MoILGR to develop conflict resolution mechanisms / Draft Galmudug’s fiscal-decentralisation bill / Puntland’s district roll-out covers only three permissive districts / The self-assessment states that partners have flagged implementation districts that meet — and in Galmudug exceed — the numeric target, but this is not included in reporting. Identification of districts provides confidence of momentum under this output.
2.1.2. Evidence that key actors have participated in the consultations and review events around the design and implementation of national and subnational policies, and are aware of their availability as a result	SSF III uses state and federal-level policies, frameworks, strategies, and legislation to engage a wide range of stakeholders to deepen and strengthen (permissive) or maintain (steady/permissive) relations across divisions that are likely to deepen in the lead-up to elections across Somalia	Moderately did not meet expectation / Whilst activities are aligned with existing state or federal policies, strategies and legal frameworks and engage ministries, councils, clan elders, women’s groups and civil-society coalitions, it is not possible to assess whether the milestone has been met given the way it has been articulated. / Related activities included: / support to district-council formation which was aligned with Jubaland’s Local Government Law No. 4 / finalisation of Galmudug’s State Reconciliation Framework, / Support to South-West State’s MoILGR-led accountability agenda.
Output 2.2: Support for local, state, trans-state & national networks & coalitions that can support social healing/trust-building, as well as conflict prevention & de-escalation
2.2.1. Evidence that supported stakeholders do or consider themselves more able to engage to de-escalate and/or mediate dormant and/or active inter-communal conflicts	At least two (2) (re)conciliation processes supported either for direct cessation of violence or in preparation for local governance support	Moderately exceeded expectation / SSF III supported four reconciliation processes during the period to either stop violence directly or to pave the way for inclusive local-governance work: / Jubaland — 12 consecutive inter-regional dialogues convened by the Ministry of Interior (MoI‐JSS) to calm clan tensions ahead of district council (DC) formation. / Puntland MoIFAR reconciliation initiatives in Galdogob District resulting in settlement of a case that had divided communities. / Banadir Administration held public forums on electoral and representation issues to reduce political friction and support the DC formation. / Supported development of the Galmudug State Reconciliation Framework (SRF), bringing together state officials, elders and CSOs to agree on conflict-resolution priorities prior to DC formation process.
2.2.2. Evidence that civic actors and traditional mediators (in ADR centres or separately) are interacting and building relations across communities as part of support	At least two (permissive/steady) or one (non-permissive) dialogue processes(s) supported that address active conflicts and see active participation from members of both communities, communal and political leadership, and other relevant stakeholders	Moderately did not meet expectation / One peace-building dialogue was supported in Puntland (Herojalle corridor): a structured dialogue among clan leaders, Internally Displaced Person (IDP) representatives and district authorities to promote peaceful co-existence and reconciliation.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 scores a ‘B’, with one indicator moderately exceeding expectation and three indicators moderately not meeting expectations. Although expectations have largely been met, there are no substantive examples demonstrating the engagement or early results of the aim of deepening and strengthening or maintaining relations. This is concerning given that divisions are likely to deepen in the lead-up to elections.

Slower than expected implementation can be attributed to the government-imposed pause and the slow appointment of the Conflict, Conciliation and Climate Lead position to the Technical Support Unit. In addition, the RF currently only seeks to capture explicit conciliation inputs, failing to capture the entirety of the programme investments in reconciliation. For example, support to conciliation activities were a foundational investment under the local governance workstream to enable acceptable and sustainable local governance leadership to emerge. This review has sought to capture this where possible.

Although there is relevant technical expertise in the Fund team and FCDO, the programme has lacked focused expertise or dedicated time from the FCDO Conflict Adviser. The Compound Risk Assessment Mapping (CRAM) introduced this year is a positive introduction. Once recruited, the Conflict, Conciliation and Climate Lead should improve cohesion across the workstream, enhance conflict-sensitivity across the programme and strategically assess how the programme should respond to localised drivers of conflict. The Conciliation Barometer (Heshiin Beeg) offers an opportunity to inform this. Although paused by the Fund this year, it is also important that the dynamics between conflict and worsening resource scarcity driven by climate change are considered and inform the work under this output.

The following highlights are assessed as providing a promising foundation for implementation at pace in the next programme year:
- Support to government counterparts to draft/finalise reconciliation strategies and frameworks aligned to the National Reconciliation Framework (NRF).
- Reconciliation initiatives conducted to enable space for local governance investments. Activities included dispute settlement strategies, decentralisation policy development, and 12 consecutive inter-regional dialogues to address clan grievances and build trust between communities (from Gedo region) and Jubaland State government.
- The Puntland/Galmudug Peace Initiative (PL/GM PI), implemented by a consortium led by CARE International, started in late January[13]. The stakeholder mapping exercise brought together government officials, members of parliaments from Puntland and Galmudug and regional officials to discuss cross-border conflict and increase cooperation.
  [13] A one-year contract was signed 6 September 2024, but implementation was delayed due to extensive negotiations, led by local consortia partners, with government on the modality.
- Multi-stakeholder participatory conciliation efforts requested by SSC-Khatumo, including coordinating inclusive consultations with key conflict actors, addressing active conflicts, capacity building in conflict resolution and prevention, and supporting local coalitions for peace.
- The Conciliation Barometer (Heshiin Beeg), led by Research Centre for Sustainable Peace and Democratic Development (SeeD) in collaboration with Dhaxalreeb, Puntland Development Research Centre (PDRC), and Build Up commenced in January. The survey tool was completed and pilot implementation started, with data expected to be available before the end of the programme year. Engagement to date has been focused at the district level, with civil society and local government.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the indicator descriptions for this output, but targets were set for year two. The limitations the recent approval of the targets has imposed on this review are discussed elsewhere.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations were made in the last AR, other than to recommend that milestones be delivered.

Recommendations:

Measurement: The ToC and RF should both capture the linkages between the reconciliation output and other outputs, recognising that reconciliation, negotiation and dialogue are utilised across the programme to open the space for other activities. This Output should measure all investments (currently the Conciliation Barometer is not included). Milestones should be simple, plain and measurable, capturing both short and long-term results. The weighting of this output should also be re-assessed.
SSF by August 2025

Coordination: Linkages and collaboration between the activities covered by this output and across the programme require strengthening. For example, the Conciliation Barometer operates as a standalone activity, raising questions on data utilisation and sustainability. Over the next year the SSF should explore how to layer this information with CRAM data and political insight to ensure risk-based approaches are more tailored to individual areas.
SSF by October 2025

Sustainability and Technology: AI and other data tools should increasingly analyse the data to produce insights that can support decision making and inform programme activity. The team should clarify what sustainability looks like for the Barometer including supporting or being used by the International Community or government ownership[14] and a roadmap for achieving that incorporated into any scale up.
[14] Currently there are varying views on this. These include: i) government ownership and institutionalisation (SSF) and ii) wider donor funding.
SSF by October 2025

Output Title	Democratisation & local governance: Progress towards increased representation, access to services, and support for democratic processes in governance
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1.1. Evidence that supported policy frameworks guide and/or are used by management institutions to sup- port and/or over- see democratic organisations, processes, and engagement	At least three state-level strategies supported or harmonised with regional and federal-level frameworks, and at least five (permissive/steady) or two (non-permissive) priority districts identified for implementation	Met expectations / SSF has supported the development of eight FMS strategies, harmonised with higher level frameworks, and priority districts have been identified.
3.1.2 Evidence of coordinated support for fiscal decentralisation and local government sustainability	At least 8 (permissive) or 5 (steady) districts assessed for local technical and financial capacity and systems, with findings integrated into plans for support coordinated with key partners	Met expectations / Assessments conducted in eight districts in Galmudug. / District-level diagnostics in Puntland and SWS informed capacity-strengthening plans with partners.
3.2.1. Evidence that SSF III and partners align and/or deconflict support for local governance institutions, including the assessment of districts for district council viability	At least two mapping exercises to identify existing structures, gaps, and support efforts SSF III can build on or sequence with for support to local governance	Met expectations / Two mapping exercises are informing SSF III support in SWS and Jubaland.
3.2.2 Evidence that supported communities engage in dialogue on power and resource sharing with increasingly less resort to the threat or use of violence as part of the district council formation or governance process	At least ten (permissive/steady) or five (non-permissive) newly formed or re-elected district councils supported in training and 'seating' for service delivery and community engagement with evidence that trained councillors engage with constituencies	Met expectations / Support to ten councils in permissive/steady districts and two in non-permissive districts.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 scores an A when scored against the recently agreed milestone targets. However, the targets are primarily input-focused and do not reflect the expected delivery of the second year of implementation; they are more appropriate for inception-phase activity, for example, strategy development, identification of districts to operate in and mapping exercises and are assessed as providing a good foundation for implementation in the next year. However, a rigid assessment of the milestone targets risks discounting valuable contribution to the output.

A technical lead for this workstream has been recruited to the TSU and Democratisation, Local Governance and Accountability (DLGA) partners have also been onboarded: two consortia provide geographic coverage and complementary expertise, one led by Finn Church Aid (FCA), with the Horn Center and the Somali Youth Development Network and the other led by the International Cooperation Agency of the Association of Netherlands Municipalities (VNG), with KAALO Aid and Development, Puntland Non-State Actors Association, Somali Family Services, Centre for Peace and Democracy, and Somali One. The introduction of this expertise has driven the performance of this output.

The activities delivered by these consortia seek to complement the work with government partners to enhance service delivery, strengthen accountability, and deepen local government legitimacy. SSF III has adopted a partnership modality, where government partners co-design projects with State Coordinators, procure vendors, and manage implementation and the Fund oversees procurement, reviews documentation, and pays vendors directly. This has improved government ownership, the quality of implementation, and the alignment between government and non-government led initiatives; performance has been strongest with Puntland, Galmudug, and SWS performing the most strongly. SSF III’s partnership approach has the potential to strengthen government systems and service delivery, as well as positioning the Fund’s to deliver its political objectives.

The pilot support to Puntland to strengthen government capacity and oversee SSF-supported projects has delivered clear delivery improvements. Two staff have been funded by the SSF in the year under review. This model of providing salaries to dedicated staff at civil service rates with an agreement that these positions will be sustained by the State in the future promises a sustainable injection of capacity. The programme will need to monitor that this agreement is honoured as the approach is rolled out to other States. There is clear demand for this type of support. SSF has already agreed to finance one dedicated staff member in the MOIFAR FGS, and based on the positive results in Puntland will offer to support one, maximum two, positions in each FMS.

District Council formation and capacity development is a central focus of this output. It highlights some of the tensions that need to be addressed for the programme to deliver against its objectives. Firstly, formation generally requires conciliation and negotiation, illustrating the artificial separation between workstreams. Secondly, as already noted, a decision needs to be made on whether the programme is limited to delivering government frameworks or has the flexibility to also work to generate an enabling environment for this by working with existing representative bodies.

Highlights of the work delivered in year 2 of implementation include:
- In Puntland, the Electoral Support Facility supported the Puntland Electoral Commission (PEC) to conduct the final round of local council elections.
- Puntland, activities included comprehensive local authority capacity assessments, participatory community forums, and joint community-government workshops. These ensured effective governance and indirectly supported peace and reconciliation by promoting dialogue and local accountability.
- Capacity development through MOIFAR-JSS and implementing partners to local officials and community leaders to enhance their technical and administrative capacity to form and manage the district council’s formation preparations activities in Belet-Hawa and Afmadow districts[15].
  [15] non-permissive Jubaland districts
- Ten councils in Galmudug completed workshops for councillors and cabinet members.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Although the indicators have not been changed, the milestones were only recently set. These revisions have altered the nature of how this Output is measured from a focus on how SSF III engaged externally with other actors and processes, such as the Wadajir Framework review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Team to focus on completing the activities within agreed time.
This is measured above.

Team to articulate the intended objective by coordinating with other key stakeholders i.e. WB, PREMIS, USAID and JPLG and other key actors. This will ensure the coordination is deliberate and intended to further a specific agenda.
The Fund has identified opportunities to coordinate with other key donors, but the impact of these discussions has been limited because of the changing donor landscape. District-focussed activity was initially aligned with USAID's PCGA programme, which has since been terminated. The UK’s PREMIS programme will also close at the end of this year. The World Bank's BULSHO programme remains in design, which the team has sought to inform. Coordination with IOM and TIS3 is ongoing.
SSF III has identified the termination of USAID programmes and the wider reduction in donor funding as risks. The flexible delivery modality enables the programme to pivot and fill gaps but, given finite resources, more extensive assessment of where the Fund should prioritise and the extent to which it can support local governance will be required. This should be considered as part of the proposed ToC workshop as it will influence the scale and scope of the programme.

Recommendations:

The key recommendations for this output are covered by the overall programme recommendations related to the ToC, RF and coordination.
Output Title	Social contract: Support improved accountability (incl. transparency & visibility) of authorities at federal, state & district levels through support for internal & external policy development/review & mechanisms
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1.1 Evidence that supported mechanisms and policies are or likely will be useful to policy makers and public officials/civil servants to engage with citizens and civic actors	Community members actively engage in at least two SSF III supported platforms (town halls, forums etc) or mechanisms that facilitate greater and more inclusive access to government institutions	Met expectations / Three platforms providing community members with an opportunity to engage meaningfully with government institutions: / - Public Accountability Platforms in Galmudug (operating in ten districts) providing citizen–government dialogue spaces / - Town-hall meetings in Puntland supported by PUNSAA and VNG in Qardho, Ufeyn and Galkayo / - State-level accountability forums in SWS convene citizens with ministers, the Baidoa Mayor and district-council members
4.1.2. Evidence that supported mechanisms and policies are or will likely be used by key institutions and actors to hold other government institutions and actors accountable	Key stakeholders in local governance actively engage in at least two SSF III supported platforms/forums for inter-governmental accountability	Moderately exceeded expectations / Three inter-governmental accountability platforms meet regularly to review performance and resources: / - Galmudug: formal coordination meetings that bring together state officials and donors / - Banadir/Jubaland: women- and youth-led accountability forums engaging with district councils / - Coordination meetings in South-West State.
4.2.1 Evidence that support to non-state actors renders them more capable to engage with government actors, voice community input (grievances, needs, or support), and/or be viable/sustainable as an organisation	At least two platforms or platform initiatives set up to empower marginalised groups, including women and youth, to more actively participate in or engage with administrations	Met expectations / Two mechanisms set up to empower marginalised constituencies to engage with local administrations: / - Galmudug: district-level public-accountability forums that have dedicated speaking time and decision-tracking for women, minority-clan representatives and youth leaders / - Jubaland: community programmes in which women and young people co-manage peace-committee meetings and raise service-delivery priorities with district officials

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 scores an A with all milestones met or moderately exceeded. The initiatives delivered in the year under review have supported marginalised groups to engage in administrative affairs, but these are small, standalone investments; the ability to deliver at greater scale or for the activities to be sustained or deliver impacts is unclear. The RF does not include milestones beyond this year to inform how delivery will build on progress to date. As part of the proposed RF revision, targets for the remaining years of the programme should be agreed, ensuring that these capture results and a higher level of ambition.

The Dawlad Wanaag project, implemented by a ‘horizontal’ consortium[16] under the coordination of VNG International commenced this year. It seeks to foster inclusive community engagement to strengthen local governance, democratisation, and accountability across 12 districts in Puntland, Jubaland, and SWS. By involving diverse groups, including marginalised voices, the project builds trust and ensures that local perspectives shape project activities. In the period under review, the project supported district-level town hall meetings which allowed local government to set out the resources available and what they have delivered and for communities to ask about initiatives that have not been delivered.
[16] The Consortium’s includes: VNG International, with global experience of working on local governance; KAALO Aid and Development Organisation, focused on inclusive development within Puntland; Puntland Non-State Actors Association (PUNSAA), an advocate for civil society engagement in Puntland; Somali Family Service, which provides essential social services and sustainable development in Jubaland; Somali One, a leader in peacebuilding within South West State; and the Centre for Peace and Democracy, an advocate for human rights and democratic governance.

Capacity-building efforts equip local government officials with conflict resolution skills, enabling proactive responses to emerging challenges and reinforcing stability.

Highlights of the work implemented in the year under review:

- SWS: MoILGR assisted to organise a series of public debates on enhancing government accountability and transparency in Baidoa (August) and Barawe (September), with inclusive participation from over 350 attendees.
- Galmudug: Public Accountability Platform forums held in ten Districts. Engagement with women from minority clans, disabled women, and disadvantaged groups improved inclusivity, while partnerships with the MoWHRD and local NGOs strengthened institutional support for gender equity.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the indicators of this output, but targets were only recently set for Year 2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Only one recommendation was made in relation to this output in the last AR:
Focus on completing the work by June 2024
Work has commenced and is building pace under the output. The long-term nature of relationship-building at the local level to improve governance and development outcomes means that activities should be seen as ongoing.
Moving forward, SSF and partners should articulate the longer-term investment pathways and anticipated impact with milestone targets to track progress for the remainder of the programme. The level of ambition should be increased and measurement transitioned from inputs to results.

Recommendations:

The key recommendations for this output are covered by the overall programme recommendations related to the ToC, RF and coordination. However, the following recommendation is especially relevant for this output:

Measurement: Milestones should be simple, plain and measurable, capturing both short and long-term results.
SSF by August 2025

Output Title	Research: An informed SSF, donor community, and partners contribute to a strengthened, more inclusive, and more sustainable political settlement in Somalia
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1.1 Evidence that assumption testing informs SSF III’s PDIA process	SSF III commissions at least two research products in support of its learning and adaptation processes, which are used by the team to review programming strategy and practice / SSF III commissions and implements at least two research products that inform the implementation of key aspects of SSF III's programming, with a view to inform coordination with partners and sequenced implementation of conciliation and decentralisation strategies going forward	Met expectations / Two research products were commissioned: / - Puntland: Project launch & planning workshop report, which has guided state-level work-plan adjustments; / - Jubaland: Governance diagnostic study, which is informing sequencing of support to district councils and reconciliation activities. / Two research products commissioned and utilised to inform the programme: / - Benadir: “Enhancing Democratisation in Benadir: Strategies, Challenges and Recommendations” – analytical paper providing options for inclusive governance in Mogadishu to inform sequencing of reconciliation and council-formation support with BRA and other actors. / - Galmudug: “CARE Project Launch & Planning Workshop Report[17]” – workshop synthesis that distils lessons on partner roles, risk management and district sequencing informing reconciliation and decentralisation activities.
5.2.1 Evidence that partners and stakeholders engage in discussion and more informed practice on the basis of research products	SSF III actively engages partners on discussions of at least two research products designed to inform coordinated, evidence-based implementation	Two research products have provided a foundation for dialogue with government and non-government partners: / - Banadir: “Summary Report on the Public Forum on Electoral and Representation Issues” – findings inform discussions with BRA officials and civil society partners to refine district-council formation timelines and inclusion safeguards in Mogadishu. / - SWS: “Report for the Accountability in Baidoa” – recommendations discussed with SWS ministries, the Baidoa mayor and district council members, to guide roll-out of an accountability forum and phased service-delivery support.
[17] 17 November 2024

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 5 scores an A when assessed against the milestones. However, these milestones would benefit from clear criteria to assess the scale, significance and reach of the deliverables; some of the research deliverables to date are relatively narrow in scope. As the programme matures, this output needs to increasingly assess the impact of the research and its contribution to the wider programme.

Decision making is not obviously informed by evidence; assumptions informing the approach are not grounded in evidence and the programme is not building on wider evidence of what works. What analysis and research to undertake is also not grounded in an assessment of existing evidence and does not build on the foundation it could provide, undermining both the economy of the substantial investment in analysis and research under SSF III and its effectiveness. Partially informed by the early stage of this workstream, there is limited evidence that analysis and research is informing delivery.

SSF III has established a research community of practise with other practitioners working on Somalia. This is a positive step and should be sustained going forward to identify potential duplication of effort or synergies. In addition, collective ways to improve dissemination and uptake should be identified. On a basic level, this should include learning sessions with SSF implementing partners and presentations to the TJSC and interested donors. Research should be a public good and the VfM of this output will be enhanced if findings have an impact beyond the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the indicators of this output, but targets were revised for Year 2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations were made in the last AR in relation to this output.

Recommendations:
All research concepts must demonstrate that a desk review of existing global and Somalia-specific research has been undertaken and articulate how the research will build on this exiting evidence and respond to gaps in understanding. All proposals for research must include a dissemination plan and identify how the findings will inform decision-making or delivery, primarily within the SSF but also more broadly as relevant.
SSF and Research partners – August 2025

The SSF needs to shift towards a more propositional approach, building on analysis and research to justify recommendations to the TJSC and HLSC on the direction of the programme or for activities to be approved. This should work in both directions, also informing research commissions as required.
SSF – with immediate effect

Linkages with other relevant FCDO-funded research should be identified and engagement with other research actors working on Somalia sustained.
SSF, Research partners and FCDO – October 2025

Output Title	Coordination: SSF III, partners, and stakeholders among governments, civic actors, and international partners engage in deliberative coordination to align or deconflict approaches and are informed about each other’s strategic priorities.
Output number:		6		Output Score:		Not scored
Impact weighting (%):		Not set		Weighting revised since last AR?		New output – not established

Indicator(s)			Milestone(s) for this review		Progress
Evidence that SSF III engages with partners and stakeholders among governments, civic actors, and international partners to align or deconflict approaches and inform each other of strategic priorities.			SSF III engages in at least three community of practice-wide coordination mechanisms on implementation relevant or adjacent to SSF III's mandate		New programme governance mechanisms introduced: the High-Level Steering Committee and Technical Steering Committee / Three coordination mechanisms (Galmudug, Jubaland and SWS).

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 has not been scored. This is a new output, approved in March 2025 as part of the revisions to the RF. As such, it is not being formally assessed as part of this review but referenced for information.

The JDC continues to meet, but governance arrangements have been revised since the last AR. The HLSC was established to improve communication, provide strategic steer and oversight of the programme and has met twice in the period under review[18]. The HLSC brings together the federal government, SSF and Ambassadors, and was instrumental to addressing the FGS’ perception that they had been sidelined, enabling the programme to restart implementation. The TJSC, which meets quarterly, complements the HLSC and enables representation of the member States (FMS) and development partners, as well as SDP.
[18] The second meeting took place in April after some delay, impacting on the ability for the meeting to set the strategy for Year 3.

This expansion of the Fund’s governance mechanisms has delivered clear benefits, including providing a forum for debate on the sensitive issues the programme is aiming to address, but has also increased the management burden and resourcing requirements by the FCDO.

The Strategic Advisory Group envisaged in the programme design has not been initiated. With the introduction of the new governance arrangements, participation of consortium partners was removed, with the aim of reducing opportunity for Conflict of Interest and enable them to bid for funds under the programme. Although the fund continues to meet with consortium members monthly to share information, there is no mechanism that brings together all the implementing partners involved in programme delivery. This impacts negatively on coordination and collaboration and, more importantly, the programme’s ability to harness expertise or support co-creation to inform design. The Partner workshops in April were welcomed by partners and demonstrated the demand to be more engaged in the strategic direction of the programme.

In addition, three state-level coordination mechanisms have been initiated to improve evidence-based coordination:
- Galmudug: Government and Development Partner Coordination Meetings, involving around 60 participants, seek to align donor inputs and synchronise activities with Galmudug’s stabilisation plan.
- Jubaland: Technical Committee Process for District Council Formation, convenes MOIFAR-JSS, local CSOs and SSF partners to steer evidence-based implementation in Belet-Hawa and Afmadow.
- SWS: regular Multi-stakeholder Governance Forums where SWS ministries, Baidoa municipality and SSF partners to improve cohesion of interventions.
As in many contexts, the international community is disjointed. With the inclusion of this new output focussed on improving coordination, SSF could position itself as a thought-leader and, utilising knowledge and evidence generated under output 5, seek to improve alignment of the international community, which would also be beneficial for stability.

SSF III describes itself as an ‘integrator’, collaborating closely with other development programmes. This output could also seek to measure how the Fund has coordinated with other investments, such as Bulsho, or informed the approach. This is currently assessed under output 2 but might be better integrated here.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is a new output; there are no previous recommendations.

Recommendations:
Clarity on what this output should include and what it measures should be considered as part of the ToC and RF revisions. This should focus on the results these activities seek to deliver; the mechanisms themselves should be seen as a means to an end.
SSF by August 2025

SSF should position itself as a thought-leader and, using knowledge and evidence generated under this output, seek to improve alignment of the international community at the state level and national level in SSF themes, which would also be beneficial for stability.
FCDO and SSF by October 2025
## D: VALUE FOR MONEY

Key cost drivers and performance

Fund Management: The key cost is technical fees. These are managed through adherence to contractual rates and limits, and review of key performance indicators (KPIs) on a quarterly basis, linking this to a milestone approval and payment modality. The KPIs and milestone payment modality are graduated to incentivise quality performance as well as protect the Fund Manager (FM) from unrealistic expectations and unmanageable risks. Only significant under-performance would trigger 50% of the technical fees to be withheld. During the reporting period, the FM scored the required aggregated score to enable them to claim 100% of the technical fees.

Core Funds: The key cost drivers include accommodation, trainings/workshops/conferences, travel and security. Comprehensive benchmarks enable the programme to review budgets and claims from partners. Currently, savings and trends are not tracked, making it challenging to reflect on the trajectory of the cost drivers.

VfM performance compared to the original VfM proposition in the business case.

Business case proposed measures	Progress made
Effectiveness (outputs to outcomes) / Regular review and stress-testing of Fund-level theory of change / In-built research hub and MEL unit to ensure evidence-based investment design / Strong advisory capability and in-country footprint	The TOC needs to be urgently reviewed in line with recommendations made in this review / MEL and research hub in place, but limited evidence to date to demonstrate how the products have informed decision making or programme design. Evidence is not uniquely produced by the hub, with the most relevant analysis produced by other parts of the programme e.g. the elections paper. / Recruitment to the TSU has significantly improved technical expertise, but key positions remain vacant. The team includes strong local expertise with in-depth context understanding. However, the expertise, experience and relationships of consortia and framework partners as well as new implementing partners is not being harnessed despite the fact that they were included in the programme to enable that.
Efficiency (inputs to outputs) / Effective leadership and coordination with other donors in-country to develop shared agenda on stability and avoid duplication / Fund works to scale achieving key cost savings	The SRO and Head of SSF lead International Community (IC) engagement, complemented by the JDC and new TJSC. The Fund Manager and Head of SSF coordinate with other programmes to promote complementarity and layering of activities across the stabilisation spectrum. This could be further enhanced, including internally with other FCDO programmes. The proposed portfolio approach may present an opportunity to improve cohesion of UK effort if SSF III is assessed as a suitable vehicle. Inclusion of a new output on coordination could also incentivise greater investment in this and influencing larger scale programmes, such as the WB’s Bulsho, to build on and align with SSF III. / Cost savings recorded during the year (see below) however the programme is not yet working at scale due to the two programme pauses in the last two years.
Economy (cost of inputs) / Overhead costs compared to other similar programmes with a high focus on PDIA approaches (Fee rates estimated to be circa 20%) / Cost of consultancy inputs benchmarked for high quality assistance / Evidence of the economy of inputs sourced through competitive and procurement systems and price negotiations with suppliers / Measure time/cost to generate reliable evidence to validate key assumptions	Evidence of good practise in relation to this dimension, but information on what savings these measures had delivered was not available. / The programme is not operating as a PDIA programme and as such should not be compared with programmes that are genuinely adaptive. / Consultancy costs are benchmarked but the team has identified incidents of consultancies for work expected to be delivered in-house, such as M+E and workplans. Similarly, some consultancy inputs have not delivered results, but led into further consultancy requests, such as related to communications.
Equity / Gender and social inclusion central to design of Fund-level theory of change and individual investments	The programme does not have a GESI policy to guide implementation and there isn’t a dedicated adviser to ensure that this remains central.

Effectiveness:
- The programme was intended to operate with a PDIA approach . As noted above, whilst the programme is flexible, it is not an adaptive programme. Flexibility has enabled the programme to adapt to Somalia’s rapidly changing context and has been central to the effectiveness of the programme to date. A PDIA approach is still assessed as appropriate; the FM needs to articulate how this will be implemented, now that the programme is in full implementation, efforts should be made to re-align with the programme design or redefine its PDIA approach.
- The programme has generated large amounts of high-quality analysis and research but there is also little evidence that the MEL system is feeding data and information into the decision-making process in a timely fashion and therefore able to inform the direction of the programme or any adaptions. While analysis and evidence have informed elements of the programme, this was not delivered by the MERL mechanism. This may partially reflect the relatively early stage in implementation if the pauses are taken into consideration. The effectiveness of these investments requires that they genuinely inform the programme and wider understanding and practise. The SSF should make sure that they identify ways to capture what has changed in response to this investment.
- The MERL approach is overly complex and does not demonstrate the impact of the programme or support learning; the lack of accessibility means that it is not used to manage the programme. It is not fit for purpose for a PDIA programme and will require revising to support this as the programme re-aligns with the PDIA design.
- The ToC needs to be updated; some of the recommendations from the last AR (2024) were not actioned and the assumptions underpinning the ToC no longer hold. In addition, political dynamics and the lack of agreement on the programme modality has impacted on implementation. The delay in reviewing the ToC and updating assumptions to reflect changes in the context raises concerns on the overall VFM consideration of progress towards the outcome and impact targets.
Efficiency:
- Dynamic Efficiency: Conducting real-time monitoring through third party monitoring; periodic context assessments and having a network of state coordinators has provided real-time information and contributed to allocating resources where they yield the highest returns as part of the programme’s flexibility.
- Relational Efficiency: The programme has benefited from having jointly agreed risks and priorities by working alongside Somali counterparts as part of the mid-year review in the second quarter, as well as the joint annual plan and budgeting process in the last quarter
- Technical Efficiency: The consortium model ensures that the required expertise and capability is available within the programme to support effective delivery. However, the review has demonstrated that this expertise, and that of other implementing partners delivering outputs, is not being adequately drawn on and there are no fully established mechanisms to enable this expertise to inform decision making or the strategic direction.
- The SSF Fund Manager shares the platform with other Adam Smith programmes delivering savings on operational costs, including related back-office staff support.
The analysis and research commissioned under the programme does not include a desk review of existing evidence which is not efficient (and also has related impacts on economy and effectiveness).Economy:
- Cost benchmarking enables the Fund to assess core service delivery costs, providing confidence that costs are realistic and deliver savings. These benchmarks are reviewed regularly to ensure the costs are reflective of context. Through benchmarking, the risk and assurance team assessed budget submissions for reasonableness and prevented inflated costs in partner concept notes and proposals.
- Savings amounting to $731,296 (approximately £540k) were negotiated as part of procurements during the year under review. In addition to savings from the infrastructure CDEL project procurements in late 2024, government partner procurement activities were also subject to SSF III review to ensure transparency and market competitiveness. These savings are reinvested into the programme, enabling more results to be achieved.
- FM will need to track benchmark costs trajectory (either upwards or downwards) during implementation.
Equity:
There are good examples, especially under outputs 2 and 4, of support to enhance the inclusion of marginalized voices in governance. This has been done systematically, although there is no structured way to ensure equity elements are considered during implementation. There has not been a GESI or Conflict Lead in place during the year under review to ensure that inclusion and conflict sensitivity have been adequately considered. A Conflict lead is currently under recruitment. The programme makes use of the GESI capability in implementing partners and also draws on advisers in the FCDO for additional technical support as necessary. As the RF is revised, data should be disaggregated where possible to measure this dimension.

Assessment of whether the programme continues to represent value for money.

SSFIII’s approach to Value for Money is based on a programme VfM policy, informed by data, In the period under review, VfM has been upheld through competitive procurement for infrastructure projects, benchmarked costing in agreeing project budgets, shared services, and. The fund continues to refine its VfM practices, using lessons learned to further enhance cost-conscious programming and outcome-focused delivery in consideration of the dynamic operating environment.

This is covered more above in section B: Theory of Change.

Recommendations:
The key recommendations are largely covered by the overall programme recommendations related to the ToC and RF, essential for the effectiveness of the programme to be assessed.

In addition:
Team to comprehensively track all VfM elements and particular measures proposed under the economy sections and the cost drivers to inform in-year conversations on VFM and enable a correct assessment in the next review.
SSF by August 2025

E: RISK

Overview of risk management

The overall SSF III risk appetite remains ‘eager’ with a current overall risk rating of ‘severe’. The operating environment has remained challenging, impacting on the ability to drive the risks down. However, a lot of effort was invested in managing the risks from materialising and impacting the programme negatively. Somalia is witnessing a lot of pre-elections activities which will make the environment more volatile and therefore will require a more proactive approach to risk management in the coming period.

The risks are defined in categories that align to FCDO’s risk framework and appetites are all in line as well. Risk identification and mitigation is discussed and escalated through the weekly Senior Management Team meetings, monthly ASI-FCDO meetings or through direct communication. The Head of SSF will also escalate risks to the JDC in line with established governance and reporting arrangements. Risk escalation is informed by the various appetites and escalation protocol set within the SSF III Risk Appetite guide.
Recommendations from downstream partner due diligence and annual audit reviews are tracked by the Finance, Risk and Procurement team, with 80% of actions responded to and closed following the last audit process. At the time of this review, audit planning was underway for the June 2024-July 2025 delivery year.

The team utilised both the FCDO third party monitor (TPM) and the programme third party monitor to monitor and flag possible risks emerging or materialising. The FCDO TPM carried out quarterly verification exercises directly informed by with SSF programming and plans and developed verification reports and learning summaries. These have been utilised towards MEL briefings with the internal FCDO team and onward with the Fund Manager in providing feedback and recommendations on inclusion and ensuring tangible outcomes

Strategy and context: As with last year, risks under this category materialised. The six-month delivery pause imposed by the FGS impacted on implementation. The pause strained relationships between the programme and the FGS, requiring intensive diplomatic engagement at senior levels to resolve the issues. A working relationship was re-established, and implementation largely recommenced in September 2024.
Mitigation: The risk was escalated and is now within acceptable risk appetite (receptive). The programme team to (continue to) ensure agreed committees are held to the agreed rhythm to ensure issues are addressed through the established mechanisms without impacting on programme implementation.

Policy and delivery: Capacity challenges were identified in several government institutions, including inadequate human resources or capability to deliver.
Mitigation: Capacity building interventions were introduced, including on-the-job training and workshops to address capability gaps. Additional human resources, paid civil servant salaries, were provided to two federal states to support delivery of programme activities. This has had a positive impact on delivery and will be expanded to other FMS in Year 3. This remains within the acceptable risk appetite (receptive).

Reputational: there are significant reputational risks related to working on sensitive and contentious issues.
Mitigation: Continued proactive communication to increase understanding of the programme and reduce biased views in order to stay within the minimal-cautious risk appetite

Finance and fiduciary: The programme has minimal risk appetite for fiduciary and financial risk. The FM continues to monitor risks and build partner capacity through quarterly Risk and Assurance Reviews (RARs) which serve as due diligence follow up, contract compliance and expenditure verification spot-checks, and partner capacity building exercises. Two potential fraud cases were identified at an early stage. No funds were lost. The cases just highlight the challenge in implementing in inaccessible locations, but critically that the current systems are working.
1. The first case was the proposal of a non-existent service provider as the preferred bidder and was discovered during the due diligence process. The procurement was cancelled.
2. The second case was a claim for a workshop which didn’t have supporting documents. The claim was not honoured.
The FM is currently conducting 100% expenditure verification. Whilst this is possible at the current pace of implementation, it is time consuming for both the Fund and partners. Somalia is a high-risk environment but given accessibility issues and resourcing in the FM, this approach may need to be modified and criteria to guide verification put in place.

Mitigation: Continue to actively monitor and mitigate these risks. As the number of activities increases a risk-based approach may need to be adopted.

Safeguarding: No cases have been reported during the period under review. However, FCDO’s Third-Party Monitoring partner flagged concerns about inclusion of vulnerable and marginalised groups in certain programme activities, which could generate safeguarding risks. The FM has received safeguarding training and a proposed approach to safeguarding is included in all concept note template and proposal assessment. This category has a minimal risk appetite.

Mitigation: Safeguarding training should be cascaded to all partners. A Partner Day would provide a good opportunity for this, alongside other due diligence and compliance requirements.

People: Nothing significant to report during the review period. This category has a cautious risk appetite.

The fund manager (FM) has maintained a rigorous due diligence process with all partners, both government and non-government. They have adopted a risk-based approach by regularly identifying, assessing and implementing appropriate mitigation measures.

Although partners are required to sign a Code of Conduct for terrorist finance risk, it should be acknowledged that this is a risk that can never be fully mitigated in Somalia. The programme relies on the Navex screening tool to identify risks with partners, including terrorist finance risks.

Update on Partnership Principles

Not strictly applicable as none of the funding is on-budget or flows through government systems. However, the programme seeks to support improvements related to the Partnership Principles, including enhancing government transparency, accountability and responsiveness and improving inclusivity. In addition, capacity building investments seek to improve public financial management, including procurement, and service delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

SSF is a multi-donor fund with six contributing donors (EU Delegation to Somalia, Denmark, Netherlands, Germany, US and UK as Lead donor). The fund is managed through a fund manager (FM) – Adam Smith International (ASI) - who is contracted to provide both programme management and strategic leadership of the programme. The contract was signed in March 2023 with a value of up to £180m but with approval to spend up to £79.9m.

Management:
The programme continues to deliver in a very challenging, fast-moving and complex environment. The capacity injections to the FM and clarification on roles and responsibilities[19] since the last AR have delivered clear improvements.
[19] This refers to the FM senior leadership team: efforts to improve oversight and participation of the Head of the SSF (FCDO programme funded post) and the Team Leader in decision making.

During the period under review, the FGS imposed a six- month delivery pause with the aim of renegotiating their role in the programme delivery. This was the second pause in two years. The renegotiation included a revision to the programme governance arrangements, with the following structures created:
- the Technical Joint Steering Committee brings together technical representatives from the FGS, FMSs and donors. SDP also participates in these meetings.
- the High-Level Steering Committee brings together senior FGS officials and donors’ diplomatic representatives.
Despite delays to implementation due to this FGS-imposed pause, the programme has delivered solid achievements during the year under review. These are captured above as part of the assessment of output delivery.

Given the complexity of the programme, the wide delivery chain, and the challenging operational context it is critical to ensure robust programme management practices are maintained. Related risks require close management, including ensuring cross-cutting costs, such as communications, MERL and overheads, are managed responsibly. The FM engages directly with consortium leads but has limited engagement with consortium members; enhanced oversight will be necessary moving forward.

The technical support unit (TSU) has largely been onboarded and the capacity of the FM strengthened, enabling the team to deliver on the core management and strategic leadership tasks. The FM needs to now ensure that core tasks and responsibilities, such as drafting reports and workplans, are delivered by the team and to a high quality. There should be a high bar to justify outsourcing, with clear criteria to inform this. When consultants are engaged the FM must ensure VfM and clear deliverables. In the period under review, a number of consultants were brought in but with limited impact.

Relationships:
The programme has established a robust partnership framework involving the FCDO, the Fund Manager, contributing donors and the government of Somalia.

Within the FCDO, there have been personnel changes since the last AR, with a new Senior Responsible Officer (SRO) and Programme Responsible Officer (PRO). The programme structure, which includes a programme-funded Senior Governance Adviser, can be confusing externally and could benefit from renewed explication. The programme benefits from the senior expertise this management arrangement has. Beyond the direct programme team, the programme also significantly engages the Development Director and Ambassador, particularly in the critical role they play in the HLSC. This senior level engagement has been critical to unlocking the pause on implementation and plays an important role in delivering the political dialogue at the heart of the programme. The resource and political capital investment is covered above and should not be underestimated. The risk of having multiple faces of the FCDO involved in the programme should be mitigated through continued regular internal engagement, ensuring that this FCDO expertise is harnessed and that external engagement is consistent.

The JDC, comprising of all contributing donors is a key governance decision-making partner. The JDC has been pivotal in steering joint messaging to Somali beneficiaries, as well as informing prioritisation within workstreams.

The modality of having a programme-funded post (PFP) supports and ensures the partnership and risk-sharing approach the programme requires. Given the severity of the risk, this role is critical to allow the FCDO (and other donors) to have early visibility of issues before they escalate. In response to challenges and capacity constraints, this role has been focused on addressing operational and programme management challenges, delivering tangible improvements over the year and a foundation for improved operation going forward. However, this was not the intended role of the PFP and their engagement in these areas limits the ability to hold the FM to account[20]. Additionally, it has impacted on their ability to focus on programme strategy and external relationships. In response to recommendations made in this review to clarify and align what the programme seeks to achieve, it will be important that the Head of the SSF has the time and space to engage donors to improve alignment on programme deliverables and strategies.
[20] This refers to the Quality Assurance role that the position has needed to adopt to ensure that deliverables are of an adequate standard to be shared externally to avoid reputational risk.

Within the Fund, a partnership between the Fund Manager and the FCDO is essential. Over the year under review relationships within the Fund Management Senior Leadership Team have improved, reducing some of the discord that has been referenced by external partners. Efforts to enhance oversight and involvement of the FCDO-Head of the SSF and FM Team Leader should improve programme alignment going forward.

Stakeholder management:
Changes to the governance arrangements are covered earlier in this review.

Substantial time and effort are invested in managing relationships, especially with the FGS, to deliver a conducive implementation context. Positive relationships have been maintained with all key stakeholders; the relationship with FGS was difficult for the majority of the review year, due to communication issues, divergent views on the governance structure and respective roles. Efforts to build trust and respond to the FGS’ requirement for greater oversight, such as the concept note modality and new governance structures, have enabled the fund to develop a cordial working relationship with the FGS.

Delivery, PDIA and collaboration:
As noted earlier, the concept note modality and approval processes have been flagged as a bottleneck by both implementing partners and government counterparts. The introduction of this modality was required to build trust with the government and improve transparency and was useful to kickstart delivery. However, a transition to annual workplans should be considered to support smoother, longer-term planning and implementation. Where there is a rationale for concept notes, for example to enable the programme to respond to opportunities, the process should be simpler and with clear timelines for feedback and approval to ensure agility.

Recommendations related to the MEL system and an assessment of whether the programme can develop into PDIA programme are covered elsewhere in the review and will not be repeated here.

Various implementing partners are largely working in silos; there are no mechanisms to coordinate within the programme outside of the fund manager meetings which often are on need bases and not structured. The infrastructure is available to set up these coordination mechanisms at various levels to ensure there is co-creation and complementarity in delivery. It is critical to set up structured engagement mechanisms between implementing partners, especially at state level, to coordinate and collaborate on delivery.

Timelines and quality:
The FM maintained consistent engagement with key stakeholders in accordance with agreed regularity, and ensured inputs and papers were prepared in time to inform major decisions.

Although reporting quality has improved, challenges remain with timeliness and clarity. Reports emphasise spending over results, making it hard to assess impact, and delays reduce their relevance in a rapidly changing context.

Timeliness has also impacted on other processes, including setting targets for Year 2 and milestone-invoice processing.

Delivery chain management:
The delivery chain is complex but relatively short, with several consortiums bringing together international non-governmental organisations (INGOs), for profit organisations and civil society organisations (CSOs) and MoUs with relevant government institutions. Learning from SSF II, SSF III has adopted a simpler implementation structure with fewer grants and contracts. However, the number of organisations involved in programme delivery still exceeds 39, with six partners holding more than one contract. ASI has limited oversight of the third layer in the delivery chain (consortium members); this currently comprises 26 organisations, the majority of which are local. This is identified as the most vulnerable part of the FM’s programme and financial management and oversight and should be strengthened; the FM is required to ensure they have appropriate oversight of the full delivery chain.

While this delivery chain requires a complex management arrangement, the model delivers potential benefits in the longer term, including improved coordination, more nuanced PEA, and potential skills transfer to local partners, enhancing the sustainability of local organisations.

Recommendations:
Coordination and collaboration: establish a structured engagement mechanism in each FMS led by FM state coordinators to enhance coordination and collaboration between implementing partners, to break down silos and enable investments to add up to more than the sum of their parts.
Fund Manager through State Coordinators by October 2025

Management: now that the capacity of the FM has been strengthened through the restructure, the team should: (i) review and ensure that they are delivering on all core tasks; (ii) where core tasks have been outsourced, such as reporting, they should bring these back in-house; and (iii) review and rationalise the approval process to ensure it is facilitating smooth planning and implementation, not adding any unnecessary bureaucratic process.
Fund Manager by October 2025

Oversight of the entire delivery chain: to ensure quality programme management practices are maintained across the delivery partners. Each consortium lead should ensure quality programme management delivery and capacity building of their consortium members while FM is required to maintain active oversight and ensure quality is maintained across the programme.
Fund Manager and Consortium Leads by October 2025
Financial management:
The BC approved spending through two windows: (i) up to £180m through the Fund Manager and (ii) up to £20m to be utilised through the UN window. No funding was channelled through the UN window during the reporting period; all expenditure under the review period was through the Fund Manager. The spend to date is at approximately £14.2m/$19.3m.

The delivery gap related to Fund Management costs was acceptable[21], but the variance in relation to the Core Funds averaged 30% . The pause in implementation was identified as the greatest contributor to this significant variance due to delays in procurement. However, the variance was also informed by the FM team financial management practices, which did not adequately account for risk, procurement and realistic implementation timelines across the delivery chain.
[21] +/-5% variance is acceptable per FCDO financial guidelines

The practice of pro-rating forecasts from the higher level workplan budget rather than basing this on the planned pipeline of activities has since changed. This mainly happened earlier on during the year’s implementation period prior to fully established and operationalised project activity. Performance is expected to improve now that this forecasting practice has been rectified (October 2024) and procurements have been finalised. Based on lessons, some of the improvements that the fund has instituted include improved reporting tools agreed between FCDO/ASI, annual profiles supported by quarterly forecasts, monthly forecast updates in consultation with the wider delivery chain and standing finance meetings.

July 2024- June 2025 / Budget lines Forecast Actual (excluding April-June 2025 spend) / GBP GBP / Fund Management Cost/Milestones 1.2m 0.9m / Expenses 0.3m 0.3m / Core funds - RDEL 9.4m 4.6m / Core fund – Capital Expenditure 0.9m 0.5m / Total Spend 11.8m 6.3m / Notes: / Forecasting is based on monthly-quarterly engagement with programming. Therefore, total forecasted amount may not match SSF III’s overall budget. / Quarter four implementation was ongoing during the time of the review.

Overall financial outlook
Fund manager approved spend	£79.9m
Donor commitment	£ 89 m* (Including UK £60m BC value)
Cash received	£ 24.9m**
Spend to date	£ 14.2m
Gap (This will reduce as more contributions are received)	£64.1m

*These are counted based on signed MOUs and the FCDO SSF BC. Funding contexts from all donors may affect the disbursement schedules from these commitments and pledges.
** Approximately £4m of this is an anticipated amount of UK FCDO CDEL in 25/26 required to honor commitments on legacy infrastructure in Jowhar, Hirshabelle and newer small-scale infrastructure projects across the Federal Member States.

Donor contributions
Name	Amount signed in MOU	Contribution to date (in local currency)	Estimate in GBP (£)**
UK commitment	£60m	£ 10.1m	10.1m
EU Del’ in Somalia	€8m	$ 2.9m	2.2m
Denmark	DKK 89.5m	DKK 49.5m/ $7m	5.3m
Netherlands	$10.5m	$ 5m	3.8m
Germany	€2.5m	€ 2.5m / $ 2.6m	1.9m
USA	$2m	$ 2m	1.5m

**These funds have not been fully utilised. Balances are to be carried forward to Year 3 and utilised alongside additional donor funding to deliver on the newly developed annual workplan.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Significant resourcing for MEL has been put in place, aligned with the design as a PDIA programme. SSF III MEL and research partners conduct the programmes’ M&E activities. The MEL partner holds the pen on the RF and ToC. They are responsible for assessing the quality of SSF III’s interventions and delivery approach, including providing evidence of how SSF III’s interventions are contributing towards outputs and outcomes. They provide quarterly syntheses of partner reporting, engage with all SSF III implementing partners to ensure reporting is aligned to the RF and summarise contributions to programme outputs across each FMS.

Tetra Tech, FCDO’s independent Third-Party Monitoring (TPM) partner, is also supporting MEL, including reviewing the RF and providing learning reports. At the time of the review, Tetra Tech was undertaking the GESI review and will also review the Learning and Adaptation strategy.

Third Party Monitoring (TPM): one verification visit was conducted a month between November 2024 and March 2025; none of the five activity level verifications flagged any major findings. In addition, Tetra Tech completed 19 verifications between July 2024 and March 2025. Although no major flags were raised, there were concerns related to inclusion, including concerns regarding the fair selection of participants, exclusion of minorities and women groups in some activities and respondents providing differing responses on the length of some workshops (between 2-5 days) despite having attended the same workshop.

In the current constrained ODA environment, the programme’s TPM requirements should be assessed and efficiencies identified. It is likely that the two TPM partners could play complementary roles, complemented by a bigger role for the MEL partner in activity level verification.

Evidence

SSF III is informed by multiple evidence streams that keep the team up to date on the conflict, political, social, economic, and environmental context. The research partner GIST, provides weekly, quarterly and annual context assessments and SDP delivers weekly political updates and annual analysis on dialogue and political settlements under Output 1. In the year under review a compound risk assessment mapping (CRAM) exercise was undertaken, enabling risks to be overlayed.

As flagged above, there are concerns about the utility of some of the products and the extent to which they feed into the decision-making processes. A rationalisation process is necessary to ensure the investment in evidence building is appropriate and genuinely adding value to the programme.

Learning

The Learning and Adaptation strategy was only approved in the last quarter (Q3 of Y2) and as such no formal learning activities have yet been conducted. However, learning and adaptation are embedded into each weekly team meeting, partner coordination meeting, as well as through donor and government steering committees, conducted quarterly.

In Year 3, SSF III aims to explore the following Learning Questions:
What evidence is there that SSF III’s approaches to increase more inclusive governance are working or not working?
What evidence is there that SSF III’s approaches to make government institutions become more accountable and responsive to citizens are working or not working?
What evidence is there that policies and frameworks supported by SSF III in review or drafting have found uptake and shown impact?
What evidence is there that SSF III have been able to support citizens’ and civic actors’ voices to hold government to account and do so safely?

Previous recommendation: Learning aims for the coming year should capture adaptation to context, comparative learning and include building partnerships for dissemination of learning with other programmes and within FCDO: fiscal decentralisation programme, the political team as well as OCSM and the Research and Evidence Division (RED).

This recommendation was not actioned and should be revisited.

Recommendations:
      1. Complementarity between the MEL partner and Tetra-Tech as well as GIST and SDP needs to be reviewed and rationalised to ensure there are no duplications, the products are complementary or utilised to triangulate information. As noted above, investments in learning should build on existing evidence as appropriate and used to directly guide and inform implementation.
SSF by August 2025

Date of last narrative financial report	April 2025	Date of last audited annual statement	Sep/Oct 2024