## Annual Review

Title: Somalia Stability Fund III
Programme Value £ (full life): Maximum BC value is £200m. Noting: / - £20m earmarked for the UN Window as required. / - UK commitment up to £60m and targeting to leverage £140m from other donors		Review date: October 2025
Programme Code: 300916	AMP start date: / 23 Mar 2022	AMP end date: / 31 Mar 2029

Summary of Programme Performance
Year	2023	2024	2025 / (I)	2025 (II)
Overall Output Score	A	B	B	A
Risk Rating	Severe	Severe	Severe	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0002930.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005056.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
The Somalia Stability Fund (SSF/the Fund) III is a multi-donor[1] flagship programme, which builds on two previous phases of programming. The programme is managed by a consortium led by Adam Smith International (ASI) which comprises First Call Partners, Laasfort Consulting, and Interpeace. As the Fund Manager, ASI provide strategic leadership, procure delivery partners, manage the funding, oversee implementation of workplans and programming across the delivery chain, and lead on day-to-day relationships with government(s).
[1] SSF III is funded by seven donors-the Joint Donor Committee (JDC). These include Denmark, EU Delegation in Somalia, USA, Netherlands, Germany, Sweden and UK as the Lead Donor. The US contributed $2m at the start of the programme, but the recent pause on development assistance will result in that likely being the only disbursement to the Fund. Sweden has not yet fulfilled its initial commitment.

The six-year programme (with a possibility of a two-year extension) seeks to support more inclusive political agreements at multiple levels of government and to address historic grievances that have undermined trust and contributed to the ongoing democratic deficit in Somalia.

It does this by creating the necessary space to establish democratic processes at the national and sub-national level; supporting more representative, inclusive and effective local governance structures; investing in efforts to strengthen the social contract between citizens and the state to increase legitimacy; and ensuring that new institutions are more accountable. SSF III delivers through: i) government entities at the Federal Government of Somalia (FGS) level and in all Federal Member States (FMSs); ii) thematic consortia as delivery partners throughout the lifecycle of the Fund; and iii) entities contracted for one-off initiatives.

Review Scope
This is the second SSF III annual review process in 2025 and complements the one conducted in May 2025 (Review I), which covered the July 2024 to March 2025 period. This review responds to the recommendation to reset the FCDO annual review cycle, aligning it to the SSF programme year and reporting schedule. This adjustment will facilitate more coherent performance tracking and ensure consistency between programme and donor reporting cycles. It will also ensure future reviews are informed by the revised Theory of Change and enable assessment of the programme’s contribution to the UK’s refined Somalia Business Plan.
The review particularly focuses on i) delivery in the last quarter (Q4/April-June) and ii) assesses programmatic and strategic SSF end-of-year processes that may have been missed in the last review. The report not only updates on progress, extracting key achievements and actionable lessons covering the full programme year, but also assesses progress against previous recommendations while providing further steer where required.

The review team comprised of an Evaluation and Conflict Adviser, a Senior Programme Manager and a Programme Officer. The process of review draws on the programme annual and quarterly reports, results and evidence, and discussions with the Head of SSF, programme SRO and Fund staff, held in early-mid October 2025.

Context
The political, economic and security environment in which SSF operates did not fundamentally change during Q4, therefore the overall assessment in Annual Review I 2025 remains valid. For the period under review, there continued to be challenging state-level political dynamics including the contested emergence of SSC-Khatumo, intra-state instability in Hirshabelle, and continued power-sharing uncertainty in Banadir. These challenges constrained progress on specific deliverables as is outlined in the output section below. The political and security context constrained implementation of some dialogue deliverables in Galmudug, Jubaland, and South West State, reducing geographic coverage; and SSF’s scope to engage on elections-related programming at the national level was affected by lack of political consensus on the elections model.

Overall, systemic, structural and contextual constraints and limitations at the institutional and community-level continued to pose a risk to the ability to realise sustained outcomes linked to the various workstreams. In response to this, this review noted that there were ongoing processes to re-assess pathways and embed risk and evidence-based approaches. These are articulated in more detail in the sections below.
Internal Context
To note, at the time of this review, the British Embassy Mogadishu is conducting a cross-office process aimed at consolidating its ODA portfolio into (four) integrated portfolio programmes. This initiative seeks to strengthen coherence, enhance operational flexibility, and maximise overall strategic impact; and reflects current UK ministerial priorities, in addition to FCDO Somalia priorities. As part of this transition, a dedicated portfolio programme on stability and security will be established, commencing in April 2026, into which the SSF III programme will fit. This programme will be operationalised through an amendment to the Somalia Stability Fund III business case.

Summary supporting narrative for the overall score in this review
The programme scores an A for the year under review based on the set annual targets. These were agreed in December 2024, though approval was delayed to February 2025 . This review considered Review I findings, bolstered by an assessment of results from the last quarter of the programme year -which were not available for assessment during the initial review- as well as annual implementing and MEL partner output and outcome reporting.
The programme was assessed across five weighted outputs and one unweighted output. The weighted outputs included Political Settlement, Conciliation, Democratisation and Local Governance, Social Contract, and Research. A new output, Coordination, was introduced but remains unscored and unweighted for this review cycle.

The scoring breakdown is as follows:
	Output	Weighting	Score
1	Political Settlement	30%	B
2	Conciliation	10%	A (assessed upwards from B)
3	Democratisation and Local Governance	20%	A
4	Social Contract	20%	A
5	Research	20%	A
6 (new)	Coordination	unweighted	Not scored

Major findings, lessons and recommendations for the year ahead

In addition to those from the previous review, this review made the following key observations for the period under review.

FGS/FMS ministries took the lead in setting priorities for Year 3, utilising a risk-centred approach. The Year 3 annual workplan and respective partner annual delivery plans were directly informed by and linked to government priorities, in addition to SSF strategic, policy and programmatic lessons and objectives. The planning process also drew on context assessments conducted by the Research Partner - GIST - which enhanced the overall understanding of risk in each workstream.

In developing the annual workplan, SSF ensured adherence and alignment to Technical Joint Steering Committee (TJSC) and High-level Steering Committee (HLSC)[2] mandates, requirements and timelines, securing technical endorsement and eventual approval in a timely manner. The HLSC formally acknowledged the efficiency of the process and endorsed both the methodology and the proposed plan without reservation. The progressing partnership with the FGS was exemplified by agreement to engage with two new Memoranda of Understanding (MoUs) at federal ministry level (Ministry of Justice and Constitutional Affairs and Office of the Prime Minister), in addition to existing MoUs with FGS, FMSs and Banadir Regional Administration (BRA).
[2] TJSC provides technical oversight to the implementation programme and is the primary point of engagement between stakeholders on SSF III progress. It comprises representatives from the donor countries, representatives of the Somali Federal Member States (FMS) and Federal Government of Somalia (FGS), and the SSF fund manager. HLSC provides the overall strategic direction of the programme and is a forum for mutual accountability for donors, Government and SSF III fund manager. It comprises Ministries from the FGS, Ambassadors and / or Heads of Development Cooperation from the SSF III donor countries, TJSC co-chairs and SSF Fund Manager representatives.

Risk-based approach to design and delivery: The Compound Risk Assessment Map (CRAM) highlights compound risk clusters where multiple threats overlap and is designed to enable SSF III and its partners to prioritise efforts, target rapid assessments, and watch-list areas showing early signs of escalation. The CRAM was expanded and updated in Q4 with May - July reporting capturing shifts in risk following the ‘Gu’ rains, while incorporating cumulative spatial data and near-real-time context reporting from the programme’s weekly context updates, United Nations Office for the Coordination of Humanitarian Affairs (OCHA), and other open sources. CRAM will be used in Y3 to support SSF III’s overall risk-based approach to delivery.

Recommendations:
SSF is encouraged to utilize the mid-year period and learning workshops to evaluate and document the effectiveness of the new delivery modality. This includes assessing its impact on operational tempo, technical and programmatic performance, and overall continued alignment with government priorities and assumptions that informed the annual objectives and individual delivery workplans.
SSF by end January 2026

The Theory of Change half-pager should be filled out with an accompanying narrative that explains the theory behind SSF’s chosen approach (including what the problem is, why the chosen approach will tackle the problem, how the approach will work, how this compares to other donors/actors, why the UK is the right donor/partner for this approach, the assumptions underpinning the theory, and the risks involved).
SSF by end March 2026

SSF should articulate its contribution to Gender Equality and Social Inclusion (GESI) outcomes and report against disaggregated results in annual reporting. SSF is clearly working with women’s organisations, thinking about inclusion in its relationship to stability and building evidence of the contribution of its youth engagement to reducing risks. This now needs be captured more clearly to support Donor reporting on their contributions to GESI at the portfolio level.
SSF by end of June 2026

Further refinements should be made to the Results Framework to improve it.
SSF by end December 2025

Future SSF Annual Reports should include reporting of evidence against all three outcomes.
SSF by the end of June 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (ToC) was revised in 2025:

IF Somali political and civic actors are equipped to conduct productive political dialogue at the federal, state, and district levels, enabling more effective and inclusive political settlements (Workstream/WS1);

IF policies and frameworks to address conciliation are designed and implemented, and civil society and community actors are empowered to prevent, manage, and address conflict or its legacies (Workstream 2);

AND IF formal policies and mechanisms are established to improve accountability and responsiveness at state and district levels, inclusive processes are created for citizens to actively participate in local governance, and the capacity of districts and local institutions to be responsive to citizens’ needs is improved (Workstream 3);

THEN Somali political actors will engage in productive dialogue that improves the resolution of political settlements (Workstream 1), trust and conciliation between communities and states will be strengthened (Workstream 2), and state and local governance will become more capable, accountable, and inclusive (Workstream 3);

BY using research and evidence to address core evidence gaps and identify risks to stability, and ensuring deliberative coordination among SSF III, donors, partners, and stakeholders;

LEADING TO reduced risks to stability in Somalia through the development of more rules-based, inclusive, and peaceful political and governance systems.

The changes in SSF III over time are set out in Review I and so are not revisited here.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact: Risks to stability in Somalia reduced through more rules-based, inclusive, and peaceful political systems.

Review I did not assess SSF III’s progress towards its impact statement. However, given the challenges to implementation that the Fund faced during the year under review, a fair assessment is that it did contribute to a rules-based, inclusive and peaceful political system and is well placed to support greater impact in future years, but a major contribution was not yet in scope.

Outcome 1: Somali political actors’ engagement in productive dialogue improves resolution of political settlements.
Indicator/Target	Progress
1.1.1 At least two new dialogues in permissive spaces, or one in a semi-permissive space in which political elites across levels of governance and/or international partners engage in regular strategic dialogue	SSF III conducted dialogue sessions including Somali Dialogue Platform (SDP) political engagements and the formation of two steering committees comprising donors, the FGS, and FMSs.
1.1.2. Expanded (permissive) or continued (steady/non-permissive) briefing and convening for international and/or local government partners to inform dialogue and cooperation	SSF III and partners found opportunities to continue cooperation, convening and engaging with the FGS and FMSs.
1.2.1 Strategic analysis for potential engagement in dialogue.	The analytical products on the political and contextual landscape of Somalia developed by SDP and the Research Partner are valuable tools for the Joint Donor Committee (JDC) to enable them to engage in informed dialogue and negotiations with the FGS and FMSs.
1.2.2. Agreement for continued work on political dialogue with government counterparts obtained.	SSF III faced challenges in its work on political dialogue, most notably due to the lack of an explicit agreement from the FGS to continue engaging in political dialogue.

The full ambition of this outcome was not achieved during the year under review, so it was off track. Review I covers the issues in detail, but in summary, progress towards this outcome was hindered by the FGS instigated pause in implementation which was framed by the FGS as opposition to the Somali Dialogue Platform (SDP) leading the dialogue around stability issues. In practical terms it meant SDP could not deliver progress towards Outcome 1. At the end of the programme year, the Fund was still in the process of working out the right approach to dialogue on political settlements given the changes in the context.

Outcome 2: Trust and conciliation between communities, and states and communities improved.
Indicator/Target	Progress
2.1.1. Government partners actively engage on the basis of national and state-level strategies to cohere SSF III, implementing partner, and government work on reconciliation and the social contract	In Y2, SSF III's work focused on state level strategies. / Galmudug, Hirshabelle, and SWS reconciliation plans were drafted between September 2024 and April 2025. / The BRA strategy was in its initial stage of drafting by March. / Jubilant Dispute Settlement Strategy was in its initial stages of implementation by March 2025. / Government partners demonstrated active engagement on policy development and promising signs that this will continue through implementation.
2.2.1 Targeted investment on peacebuilding in key conflict corridors incepted and rolled out.	Initial investment in peace building was rolled out in Heerojale, Jiicboor and Sacad-Saleban.
2.2.2 Key stakeholders initiate discussion and engage with SSF-led pilot study for peace index/conciliation barometer to gather evidence on what works in peace and conciliation designed, implemented, and report in draft stage in the context of the wider conciliation strategy implementation.	Information not available as the pilot study draft report was pending finalisation.

A delayed start -owing to the implementation pause-had a negative effect implementation and outcome assessment timelines. Mixed achievement of the outputs under this outcome (see relevant section below) means that though there has been some notable progress towards this result, there is more to come. In addition to the progress achieved, key steps taken during the review period included the appointment of the Conflict, Conciliation and Climate Lead position to the Technical Support Unit. Overall, the evidence-base largely came from self-reported data from SSF III and their facilities, as well as third-party monitoring of a small number of activities by the MEL partner. The reviewers needed to see more evidence from the Fund Manager against the results framework Outcome 2 indicators to provide a comprehensive assessment of progress.

Outcome 3: State and local governance is strengthened through improved capacity and accountability of leadership, and more engaged citizens.

Indicator/Target	Progress
3.1.1 Eight government partners at the national and state level engage with SSF III to renew partnerships via which they have, and continue to roll out implementation in democratisation, local governance, conciliation, and accountability, based on agreed objectives/priorities	SSF III had working partnerships with four government bodies at national or state level: / Ministry of Interior, Jubaland – co-owns the programme’s risk-mitigation and dialogue portfolio. / BRA - meets regularly with SSF III to review and set new priorities in democratisation and accountability. / Ministry of Interior, Local Government & Reconciliation, South-West State (MoILGR-SWS) – aligns SSF III investments with state-level accountability and reconciliation priorities. / State institutions in Galmudug jointly identify capacity gaps and resources for decentralisation roll-out. / Four more envisaged renewals (Puntland, Hirshabelle, FGS line ministries) were still in negotiation, so the eight-partner benchmark was not yet fully met.
3.1.2 Ministry of Planning, Investment and Economic Development (MoPIED) continues to hold Aid Coordination Forums with accompanying assessments based upon SSF III support	The DG for Aid Coordination within MoPIED remains actively engaged with SSF III and references SSF III-financed coordination structures (notably the Pillar Working Groups). However, the workbooks do not contain specific assessment reports from a formal Aid Coordination Forum during the current period. This suggests that the coordination architecture continues, but the flagship forum and assessment cycle is only partially maintained.
3.2.1 Democratisation, Local Governance, and Accountability (DLGA) partner consortia roll out implementation in multiple geographies via local implementing partners (Somali civic actors) to support capacities (among citizens, local Civil Society Organisations/Community Based Organisations, implementing partners) to engage with governments on best practices for service delivery, coordination, and accountability.	Evidence from three FMS shows that SSF III’s DLGA facilities are operating in multiple geographies and through Somali civic actors to strengthen citizen, CSOs/CBOs and local-authority capacity for service-delivery, oversight, and accountability: / Galmudug – CARE’s consortium works with local civil-society organisations to deliver training on reconciliation and trauma-healing that feeds directly into district-governance rollouts. / Puntland – Puntland Non-State Actors Association (PUNSAA) & VNG’s consortium runs capacity-building investments that align international expertise with community leaders and local implementers across several districts. / Banadir – BRA–civil-society platform ensures that Mogadishu-based Civil Society Organisations and youth groups co-design and monitor democratisation and accountability activities with the regional administration. / Work led by the facilities was delayed getting started, with some partners properly starting implementation in January 2025.

The initial outcome statement has since been revised; however, and assessment of a similar outcome prior to changes to the RF, ‘National and subnational policies, systems, and institutions contribute towards and facilitate inclusive governance and civicness’ shows SSF made progress, albeit sometimes delayed, towards this Outcome in the following ways:
- Government interaction with communities on reconciliation improved, in part due to the support provided through SSF III. Government interaction with the community is more interconnected and coordinated, and the Government is interacting with communities more directly.
- There is improved and more inclusive community participation, including women playing a more active role in peacebuilding activities. However, there were some suggestions that women are still being underutilised in reconciliation efforts.
- SSF made good progress towards the drafting and revision of policy and frameworks supporting engagement and participation. SSF played a substantial role in drafting these documents. Strategies have led to a more aligned approach, and there have been some early examples of new or adapted policies supporting dispute settlement in specific locations.
Overall Outcome Assessment

The assessment of results leads to an Amber/Red outcome confidence rating, reflecting moderate to significant concerns that require further review and action.

While some evidence supports partial compliance to requirements, there are notable gaps that limit overall ability to assess outcome progress and programme effectiveness. To strengthen assurance, the programme should prioritise refinement of outcome statements to be specific and measurable. They should reinforce the Theory of Change to clearly articulate causal pathways, risks and assumptions and reflect strategic priorities and the operational context. There should also be an increased focus on learning and strengthening of the overall quality and reliability of the results framework by improving the completeness and credibility of evidence.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

There have been no developments in Q4 that would justify a change to the assessment in Review I that while improvements in some areas of programme approach and management are needed, SSF remains a critical component of HMG’s approach to Somalia’s complex security and stability challenges.

## C. DETAILED OUTPUT SCORING

Output Title	Political Settlement: Supporting political processes at multiple levels to effectively address contentious issues as part of transforming the political settlement to be more inclusive and sustainable.
Output number:		1	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 1.1. Somali political actors, civic actors and external actors are provided with support to enable collaborative and inclusive political processes towards reaching a more sustainable and democratic national settlement			Moderately did not meet expectations / B
1.1.1. Extent to which the support provided is relevant to reaching a more sustainable and democratic national settlement	At least ‘Amber[3]’ rating	Moderately met expectations. Vertical inclusivity -tracking and engaging women, youth, and minority groups-remained limited. / Lack of consensus over the constitutional review process; the model of elections; and FGS–FMS tensions constrained sustainability prospects.
1.1.2. Extent to which support provided promotes both vertical and horizontal inclusivity	At least ‘Amber’ rating
1.1.3. Evidence of effective uptake of, engagement with, and/or participation in support activities and outputs among target audiences	At least ‘Amber’ rating
Output 1.2. Somalia political actors, civic actors, and external actors are provided with support to enable collaborative and inclusive political processes towards reaching more sustainable and democratic sub-national settlements			Moderately did not meet expectations / B
1.2.1. Extent to which the support provided is relevant to reaching a more sustainable and democratic sub-national settlement	At least ‘Amber’ rating	Moderately did not meet expectations including on vertical inclusivity. / Challenges in implementation owing to political and contextual challenges seen at state level limiting overall contribution toward more sustainable sub-national political settlements
1.2.2. Extent to which support provided promotes both vertical and horizontal inclusivity	At least ‘Amber’ rating
1.2.3. Evidence of effective uptake of, engagement with, and/or participation in support activities and outputs among target audiences	At least ‘Amber’ rating
[3] Amber-On track but some doubts whether full milestone/target will be met

Output 1 scores a B

This output maintains a score of B for the year under review.

In addition to the previous review’s key observations, further developments related to this output are outlined below.

National-level engagement:
Somali Dialogue Platform advisory and analytical inputs aligned with relevant key developments on the electoral process, and the emergence of SSC-Khatumo, supporting informed policy engagement.
FGS Ministry of Planning, Investment and Economic Development (MOPIED) led the coordination of pillar working group meetings aligned with the National Transformation Plan (2025–2029) bringing together government, civil society, donors, and the private sector to identify policy and funding gaps and align interventions.

Challenges:
Reporting confirmed continued limited engagement with women, youth, or minority groups at the national level, reflecting wider contextual exclusion.
Lack of political consensus on the elections model limited SSF’s scope to engage on elections-related programming at the national level.
Sub-national engagement:
Overall, while the scope and quality of activities and stakeholder engagement were strong in the geographic areas outlined below, lack of scale elsewhere as well as delayed deliverables and limited inclusion moderated the overall contribution toward more sustainable sub-national political settlements.
Key progress included:
- Roundtables in Garowe and Lasanod, which brought together elders, former officials, and academics to explore pathways for peaceful coexistence between Puntland and SSC-Khatumo.
- Capacity-building training delivered to Banadir Regional Administration (BRA) staff on negotiation, media handling, and inclusive power-sharing
- Political analysis paper drafted, outlining internal instability risks and entry points for mediation in Beledweyne informed by a mission which engaged local stakeholders on appetite for dialogue.
Challenges
- There continued to be challenging political dynamics including the contested emergence of SSC-Khatumo, intra-state instability in Hirshabelle, and continued power-sharing uncertainty in Banadir.
- Political and security context constrained implementation in Galmudug, Jubaland, and SouthWest State, reducing geographic coverage.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

At the time of this review, SSF had adopted the recommendation to expand the scope of deliverables contributing to the political dialogue output. This recognises the role of other partners at the output level as well as contributions from the programme donor representatives at strategic and diplomatic levels.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This review upholds previous recommendations and the respective implementation timelines and assesses that progress has been made in expanding on the contribution of broader programmatic and strategic interventions to this to this output.

Recommendation
Evidence of these interventions’ overall contribution to the political settlement outcome as well as assumptions on the context should inform continual adaptation. The key assumptions should be clearly articulated and discussed at least bi-annually during the mid-year and end-year review points within the programme cycle. Going into year 3, the programme should continually engage with sustainability including assessing evidence of uptake following training and dialogue related interventions, so as to monitor effectiveness.
SSF by June 2026
Output Title	Conciliation (Dhab-u-heshiin): Progress towards a strategic/cohesive approach to social conciliation/healing in support of a more sustainable political settlement
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 2.1: Support to design & implementation of national & subnational policy & processes to address grievances
2.1.1. Supported (re)conciliation frameworks, policies, and plans are more harmonised and aligned at regional and federal level	At least three state-level strategies supported to harmonise with state and federal-level frameworks, with at least five permissive or two non-permissive districts for implementation identified with government partners.	Moderately did not meet expectation / SSF III supported four state-level strategies aligned with the National Reconciliation Framework (NRF): / State Strategies: Banadir Regional Administration (BRA) and Hirshabelle / Galmudug Reconciliation Framework / Support to Jubaland to launch and disseminate the Dispute Settlement Strategy / Support to SWS - MoILGR to develop conflict resolution mechanisms / Draft Galmudug’s fiscal-decentralisation bill / Puntland’s district roll-out covers only three permissive districts / The self-assessment states that partners have flagged implementation districts that meet — and in Galmudug exceed — the numeric target, but this is not included in reporting. Identification of districts provides confidence of momentum under this output.
2.1.2. Evidence that key actors have participated in the consultations and review events around the design and implementation of national and subnational policies, and are aware of their availability as a result	SSF III uses state and federal-level policies, frameworks, strategies, and legislation to engage a wide range of stakeholders to deepen and strengthen (permissive) or maintain (steady/permissive) relations across divisions that are likely to deepen in the lead-up to elections across Somalia	Moderately did not meet expectation / Whilst activities are aligned with existing state or federal policies, strategies and legal frameworks and engage ministries, councils, clan elders, women’s groups and civil-society coalitions, it is not possible to assess whether the milestone has been met given the way it has been articulated. / Related activities included: / support to district-council formation which was aligned with Jubaland’s Local Government Law No. 4 / finalisation of Galmudug’s State Reconciliation Framework, / Support to South-West State’s MoILGR-led accountability agenda.
Output 2.2: Support for local, state, trans-state & national networks & coalitions that can support social healing/trust-building, as well as conflict prevention & de-escalation
2.2.1. Evidence that supported stakeholders do or consider themselves more able to engage to de-escalate and/or mediate dormant and/or active inter-communal conflicts	At least two (2) (re)conciliation processes supported either for direct cessation of violence or in preparation for local governance support	Moderately exceeded expectation / SSF III supported four reconciliation processes during the period to either stop violence directly or to pave the way for inclusive local-governance work: / Jubaland — 12 consecutive inter-regional dialogues convened by the Ministry of Interior (MoI‐JSS) to calm clan tensions ahead of district council (DC) formation. / Puntland MoIFAR reconciliation initiatives in Galdogob District resulting in settlement of a case that had divided communities. / Banadir Administration held public forums on electoral and representation issues to reduce political friction and support the DC formation. / Supported development of the Galmudug State Reconciliation Framework (SRF), bringing together state officials, elders and CSOs to agree on conflict-resolution priorities prior to DC formation process. / Four inclusive district-level peace committees were established in conflict-affected areas of Galmudug and Puntland, alongside two joint Puntland–Galmudug Peace and Security Committees, with defined mandates.
2.2.2. Evidence that civic actors and traditional mediators (in ADR centres or separately) are interacting and building relations across communities as part of support	At least two (permissive/steady) or one (non-permissive) dialogue processes(s) supported that address active conflicts and see active participation from members of both communities, communal and political leadership, and other relevant stakeholders	Moderately exceeded expectations / One peace-building dialogue was supported in Puntland (Herojalle corridor): a structured dialogue among clan leaders, Internally Displaced Person (IDP) representatives and district authorities to promote peaceful co-existence and reconciliation. / Puntland-Galmudug: / Outreach activities resulted in concrete de-escalation outcomes, including a formal reconciliation agreement between the Sacad and Lelkase clans, grounded in ADR mechanisms / 16 peace committee members were trained as trauma healing training of trainers (ToTs), who then facilitated dialogue and healing sessions for over 270 community members, reinforcing cross-community engagement and social recovery. / In Galmudug, MoIFAR delivered integrated conflict resolution training, while trauma healing and reconciliation platforms were activated in partnership with the Galkayo Trauma Healing and Reconciliation Center. / FGS MOIFAR hosted Somalia’s first National Conference on Recurrent Clan Conflicts, producing actionable recommendations on land governance, justice sector engagement, and social cohesion.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 scores an A

Reporting and assessment reviewed from annual reporting provides for a change in scoring with two (rather than one) indicators moderately not meeting expectations and two indicators exceeding expectations, elevating the overall score.

The previous review findings and highlights are maintained, with additional notable progress in the last quarter having been realised particularly on output 2.2.
- In Puntland, partners coordinated the establishment and support of peace structures, led trauma healing efforts, and facilitated outreach dialogues, including a joint communiqué from the January Galkayo interstate meeting.
- In Galmudug, MoIFAR delivered integrated conflict resolution training, while trauma healing and reconciliation platforms were activated in partnership with the Galkayo Trauma Healing and Reconciliation Center.
- FGS MOIFAR hosted Somalia’s first National Conference on Recurrent Clan Conflicts, producing actionable recommendations on land governance, justice sector engagement, and social cohesion.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No further changes proposed as part of this review. At the time of the review the partner had developed an updated results framework with refreshed, measurable indicators and milestones. The reviewers recommend bolstering this further by having a review methodology developed for each of the respective milestones.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Strengthen linkages and collaboration between activities covered by the reconciliation output and across the programme and explore how to layer Heshiin Beeg with CRAM and political insight.

In response to this, the Fund Manager is tightening up their workstreams 2 and 3 linkages and collaboration. This is being done through: 1) review of all Year 3 activities with country team and the Climate Conciliation and Conflict(CCC)/Democracy, Local Governance and Accountability (DLGA) leads; 2) revision of a project activities tracker which includes a metric that denotes whether an activity has linkages across workstreams; and 3) further coordination conversations with other partners such as IOM.

Use AI and other data tools to analyze data and produce insights that can support decision-making and inform programme activity. Clarify what sustainability looks like for the Barometer.

In order to strengthen evidence linkages to activities that then drive decision making and design, SSF is initiating: 1) further revisions to the primary activities tracker to denote data/evidence feeding into and between activities and outputs; 2) utilization of the Conciliation Barometer and CRAM for activity design for CCC small grants and the Puntland/Galmudug peace initiative extension; 3) utilizing weekly project delivery meetings with technical leads and country team to examine activity and consider refinement/changes and other decisions to be made based on quarterly CRAM; 4) work with the MEL partner to input these analyses into their quarterly Third Pary Monitoring (TPM) activities; 5) identification of new locations for possible extension of Barometer and discussing locally-led sustainability plans with FMS/FGS partners; and 6) design and delivery of targeted research studies to address any evidence gaps or unexamined assumptions.
Output Title	Democratisation & local governance: Progress towards increased representation, access to services, and support for democratic processes in governance
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1.1. Evidence that supported policy frameworks guide and/or are used by management institutions to sup- port and/or over- see democratic organisations, processes, and engagement	At least three state-level strategies supported or harmonised with regional and federal-level frameworks, and at least five (permissive/steady) or two (non-permissive) priority districts identified for implementation	Met expectations / SSF has supported the development of eight FMS strategies, harmonised with higher level frameworks, and priority districts have been identified.
3.1.2 Evidence of coordinated support for fiscal decentralisation and local government sustainability	At least 8 (permissive) or 5 (steady) districts assessed for local technical and financial capacity and systems, with findings integrated into plans for support coordinated with key partners	Met expectations / Assessments conducted in eight districts in Galmudug. / District-level diagnostics in Puntland and SWS informed capacity-strengthening plans with partners.
3.2.1. Evidence that SSF III and partners align and/or deconflict support for local governance institutions, including the assessment of districts for district council viability	At least two mapping exercises to identify existing structures, gaps, and support efforts SSF III can build on or sequence with for support to local governance	Met expectations / Two mapping exercises are informing SSF III support in SWS and Jubaland.
3.2.2 Evidence that supported communities engage in dialogue on power and resource sharing with increasingly less resort to the threat or use of violence as part of the district council formation or governance process	At least ten (permissive/steady) or five (non-permissive) newly formed or re-elected district councils supported in training and 'seating' for service delivery and community engagement with evidence that trained councillors engage with constituencies	Met expectations / Support to ten councils in permissive/steady districts and two in non-permissive districts.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 scores an A, maintaining the previous score while considering the full programme year achievements.

Progress during the final quarter of the year under review includes

Support to state-level strategies
- Community Monitoring Groups established in Abudwak, South Galkayo, and Bahdo: Youth, elders, local officials, and representatives from the Ministry of Interior trained on civic education, conflict resolution, environmental stewardship, and inclusive governance.
- Public Participation Forum held in Banadir on governance structures, citizen rights, electoral processes, and social accountability.
Challenges: Systemic and contextual constraints limiting higher-level institutional change and state-level policy reporting.
District-level technical and financial capacity
- Local government officials across six districts in Puntland trained on fiscal transparency, decentralisation, and social accountability
- MOIFAR-led inclusive community forums held in Abudwak -Galmudug to raise awareness on tax compliance, accountability, and local revenue mobilisation—activities aligned with the State and Fiscal Decentralisation Policy.
- District-level consultations conducted by Hirshabelle Ministry of Interior and Local Government (MoILG) to inform a participatory fiscal decentralisation policy.
- Workshop with partners and sectoral ministries in Southwest State, resulting in an eight-pillar action plan including digitised tax systems, performance-based transfers, and citizen engagement platforms.
Challenges: Limitations on legislative clarity, particularly in newly decentralised areas.
Mapping on district council viability
- Civic education and community dialogues in Adale, Jalalaqsi, and Buloburde conducted by Hirshabelle MoILG: 1,200 stakeholders reached with emphasis on inclusion of women, youth, and marginalised groups in district formation processes.
- Political dialogue in Lower Shabelle-SWS: 138 participants from eight districts co-developed locally grounded governance roadmaps and formally establish a District Political Dialogue Committee (DPDC) to coordinate implementation.
- Stabilisation Context Project supported in Puntland
Support to district councils for service delivery and community engagement
Over 30 inclusive dialogue forums, engaging more than 2,000 community members across Galmudug, Hirshabelle, and South-Central Somalia implemented. These resulted in formation of nine Community Monitoring Groups, 38 social integration and peace dividend initiatives, and youth-led civic actions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes within the year under review but changes proposed for the new results framework will be taking effect in Year 3.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Articulation of results
Previous recommendations were linked to the overall recommendations related to the TOC, RF and coordination, whereby progress is discussed in the last section of this review and assessed as ongoing.

Output Title	Social contract: Support improved accountability (incl. transparency & visibility) of authorities at federal, state & district levels through support for internal & external policy development/review & mechanisms
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1.1 Evidence that supported mechanisms and policies are or likely will be useful to policy makers and public officials/civil servants to engage with citizens and civic actors	Community members actively engage in at least two SSF III supported platforms (town halls, forums etc) or mechanisms that facilitate greater and more inclusive access to government institutions	Met expectations / Three platforms providing community members with an opportunity to engage meaningfully with government institutions: / - Public Accountability Platforms in Galmudug (operating in ten districts) providing citizen–government dialogue spaces / - Town-hall meetings in Puntland supported by PUNSAA and VNG in Qardho, Ufeyn and Galkayo / - State-level accountability forums in SWS convene citizens with ministers, the Baidoa Mayor and district-council members
4.1.2. Evidence that supported mechanisms and policies are or will likely be used by key institutions and actors to hold other government institutions and actors accountable	Key stakeholders in local governance actively engage in at least two SSF III supported platforms/forums for inter-governmental accountability	Moderately exceeded expectations / Three inter-governmental accountability platforms meet regularly to review performance and resources: / - Galmudug: formal coordination meetings that bring together state officials and donors / - Banadir/Jubaland: women- and youth-led accountability forums engaging with district councils / - Coordination meetings in South-West State.
4.2.1 Evidence that support to non-state actors renders them more capable to engage with government actors, voice community input (grievances, needs, or support), and/or be viable/sustainable as an organisation	At least two platforms or platform initiatives set up to empower marginalised groups, including women and youth, to more actively participate in or engage with administrations	Met expectations / Two mechanisms set up to empower marginalised constituencies to engage with local administrations: / - Galmudug: district-level public-accountability forums that have dedicated speaking time and decision-tracking for women, minority-clan representatives and youth leaders / - Jubaland: community programmes in which women and young people co-manage peace-committee meetings and raise service-delivery priorities with district officials

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 scores an A with all milestones met or moderately exceeded.

Highlights from the last quarter include
Engagement in platforms for greater and more inclusive access to government institutions
- Jubaland: Comprehensive service charters and stakeholder communication strategies re-established in Luuq, Dhobley, and Kismayo.
- FGS-led: Inaugural Government–CSO Engagement Forum on responses to global aid shifts, focusing on domestic resource mobilisation.
Intergovernmental accountability
Statewide Government Accountability Forum convened by MoILGR in Baidoa, Southwest State, focusing on promoting transparency, deepening institutional responsiveness, and co-developing citizen-led solutions to governance challenges.

Inclusive accountability platforms
- Four District Youth Caucuses formally established in Dhobley, Luuq, Afgoye, and Barawe.
- Civic education forums and community conversation sessions in Badhan and Dangorayo, with inclusive representation (40.2% women, 71.8% youth, 10.2% (Internally Displaced Persons/Persons living with Disability).

Challenge: Reporting shows limited evidence of institutional uptake or sustained use of some charters and communication platforms owing to contextual challenges in upholding social contract, and; structural and political constraints affecting medium to long-term viability of formal accountability mechanisms.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes within the year under review but changes proposed for the new RF taking effect in Year 3.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Articulation of results
Previous recommendations were linked to the overall recommendations related to the TOC, RF and coordination, whereby progress and recommendations are discussed in the last section of this review and assessed as ongoing.

Output Title	Research: An informed SSF, donor community, and partners contribute to a strengthened, more inclusive, and more sustainable political settlement in Somalia
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1.1 Evidence that assumption testing informs SSF III’s PDIA process	SSF III commissions at least two research products in support of its learning and adaptation processes, which are used by the team to review programming strategy and practice / SSF III commissions and implements at least two research products that inform the implementation of key aspects of SSF III's programming, with a view to inform coordination with partners and sequenced implementation of conciliation and decentralisation strategies going forward	Met expectations / Two research products were commissioned: / - Puntland: Project launch & planning workshop report, which has guided state-level work-plan adjustments; / - Jubaland: Governance diagnostic study, which is informing sequencing of support to district councils and reconciliation activities. / Two research products commissioned and utilised to inform the programme: / - Banadir: “Enhancing Democratisation in Banadir: Strategies, Challenges and Recommendations” – analytical paper providing options for inclusive governance in Mogadishu to inform sequencing of reconciliation and council-formation support with BRA and other actors. / - Galmudug: “CARE Project Launch & Planning Workshop Report[4]” – workshop synthesis that distils lessons on partner roles, risk management and district sequencing informing reconciliation and decentralisation activities.
5.2.1 Evidence that partners and stakeholders engage in discussion and more informed practice on the basis of research products	SSF III actively engages partners on discussions of at least two research products designed to inform coordinated, evidence-based implementation	Two research products have provided a foundation for dialogue with government and non-government partners: / - Banadir: “Summary Report on the Public Forum on Electoral and Representation Issues” – findings inform discussions with BRA officials and civil society partners to refine district-council formation timelines and inclusion safeguards in Mogadishu. / - SWS: “Report for the Accountability in Baidoa” – recommendations discussed with SWS ministries, the Baidoa mayor and district council members, to guide roll-out of an accountability forum and phased service-delivery support.
[4] 17 November 2024

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 5 scores an A.

This review maintains the previous observations, findings and recommendations.

Additional direct and supportive deliverables were progressed and/or initiated in the final quarter and will contribute to this output in Year 3.
- Programme Learning and Adaptation Strategy finalised: This will embed a culture of adaptation and reflection in delivery.
- First Learning Workshop held: This gathered implementing partner feedback; and agreed ways to better integrate partners into the decision making of the fund.
- CRAM tool updated: This will allow for data sets and predictive capacity in support of decision making.
- Rapid research report completed: This focused on youth engagement in local governance. The findings of this research were used to inform Democratisation and Local Governance (DLGA) project designs and workplans for Year 3.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the indicators of this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Research and evidence gathering, dissemination and utility.
The Fund manager has responded to this recommendation through implementation of a Learning and Adaptation Strategy, expansion of evidence sources and adoption of a research and evidence utilisation tracker; and embedding of a risk analysis tool, the Conflict Risk Assessment Map (CRAM), to enable an adaptive, risk-based programme management approach. This is discussed in more detail in the Evidence and Learning section of this review.

Output Title	Coordination: SSF III, partners, and stakeholders among governments, civic actors, and international partners engage in deliberative coordination to align or deconflict approaches and are informed about each other’s strategic priorities.
Output number:		6		Output Score:		Not scored
Impact weighting (%):		Not set		Weighting revised since last AR?		New output – not established

Indicator(s)			Milestone(s) for this review		Progress
Evidence that SSF III engages with partners and stakeholders among governments, civic actors, and international partners to align or deconflict approaches and inform each other of strategic priorities.			SSF III engages in at least three community of practice-wide coordination mechanisms on implementation relevant or adjacent to SSF III's mandate		New programme governance mechanisms introduced: the High-Level Steering Committee and Technical Steering Committee / Several coordination mechanisms (Galmudug, Puntland, Jubaland and SWS, and FGS MOIFAR).

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 has not been scored. This output is not being formally assessed as part of this review but referenced for information.

Key SSF coordination priorities in Q4 included
- Southwest State Inter-Governmental Learning Forum on Early Recovery and Stabilisation in Baidoa.
- Engagement with the Puntland Minister for Youth on economic development, civic engagement, and migration; leading to submission of their priorities to Puntland MoIFAR, for inclusion under objectives and workplans for Year 3.
- Bilateral meeting with the newly appointed minister for Public Works, Housing & Infrastructure in Hirshabelle, focused on updates to the on the ongoing Jowhar legacy project.
- Coordination meeting with the World Bank Bulsho project which identified complementarities, particularly on support for district-level capacity building and conciliation efforts.
- Participation in FGS MoIFAR-organized local governance coordination meeting that brought together FMS MoIFAR Director Generals, BRA Department of Planning, and external partners including SSF III, the United National Development Programme, UN HABITAT, International Organization for Migration, FCA and VNG. The meeting resulted in a National Coordination Platform term of reference and a detailed plan for tracking and communicating local governance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Articulation of results
Previous recommendations were linked to the overall recommendations related to the TOC, RF and coordination, whereby progress and recommendations are discussed in the last section of this review and assessed as ongoing.

SSF’s role as a thought-leader seeking to improve alignment of the international community at the state level and national level in SSF themes

Under its Policy Garage initiative, the programme has advanced strands of analytical and policy work that drive thought leadership. This included a Political Economy Analysis (PEA) on returns, as well as research and an international partner roundtable discussion on irregular migration.

SSF III aims to further support engagement and discussion on indirect electoral models and state affordability research. In the course of Year 3, SSF aims to sharpen its narrative around its core mandate—supporting stability in Somalia, defined as “helping communities, states, and regions develop by managing conflict and change peacefully” (FCDO, Building Stability Framework, 2016), targeting its resources, while leveraging the efforts of partners such as the World Bank and IOM, whose mandates complement SSF’s stability objectives
## D: VALUE FOR MONEY

Key cost drivers and performance
Core Funds:
This covers budget and expenditure associated with the four main SSF III workstreams, including short term technical assistance (STTA), as well as infrastructure support for local governance. For Quarter 4, the main costs were expenditures under MoUs with government counterparts, particularly driven by costs of accommodation, training/ workshops/ conferences, travel, and security. Additionally, there were significant capital expenditure (CDEL) commitments related to infrastructure development in Hirshabelle, particularly the construction of the Finance Building, State Office & Residence, and Jowhar Parliament.
The programme uses comprehensive benchmarks to assess partner budgets and claims. However, there is currently no system in place to track savings or cost trends, which limits the ability to assess the trajectory of these expenditures.
Fund Management Costs:

These include contractual fees and expenses incurred in managing the SSF III Fund including the fund management fee, and reimbursable expenses. The primary cost driver is technical fees, which are managed through strict adherence to contractual rates and ceilings. Fund management performance is reviewed quarterly against agreed key performance indicators (KPIs), which are linked to a milestone-based approval and payment structure. This structure is designed to both incentivize high-quality delivery and protect the Fund Manager (FM) from unrealistic expectations or unmanageable risks. In the year under review, KPIs underwent a review process informed mutual agreement on re-calibrating assessment criteria. Overall, the fund manager achieved the required aggregate score for the full year under review.

VfM performance compared to the original VfM proposition in the business case.

Economy in Quarter 4 was achieved through competitive procurement and subsequent rate negotiations. As part of Year 3 planning, SSF III negotiated long-term agreements with suppliers and vendors. Further cost savings were generated through the Risk and Assurance team’s review of partners’ budgets to ensure price reasonableness. This process leveraged benchmarked costs across all Federal Member States funded by SSF III, resulting in total savings of US$22,681.
Efficiency
The programme continued to demonstrate operational efficiency through effective resource sharing, strong coordination, and well-managed implementation processes that optimised costs and enhanced collaboration. Some specific examples include:
• Operational Efficiency: The SDP project continued to leverage shared corporate resources, including office space, utilities, and internet, allowing for flexible use of part-time personnel and reduced overhead costs. This model ensured resources were applied as needed, supporting adaptive management without maintaining full-time positions.
• Implementation Efficiency: Monitoring Evaluation and Learning (MEL) Partner verification of key activities, including the Peace and Reconciliation Committees engagement in Mudug and the Youth Councillors’ Exchange Visit, confirmed that events were well-organised, inclusive, and effectively facilitated, reflecting strong coordination and efficient use of resources.

Effectiveness
Interventions made progress on addressing partner priorities, strengthening local governance, and promoting peacebuilding outcomes through relevant, well-structured, and outcome-oriented activities. Specifically,
• Relevance and Alignment: Project activities remained strongly aligned with local and regional priorities, particularly in peacebuilding and governance. Participants in the SSF-organised Consultative Engagement Meeting with the Peace and Reconciliation Committees in Mudug Region recognised the importance of strengthening Peace and Reconciliation Committees in managing clan conflicts and fostering local stability.
• Outcome Orientation: The Galkayo consultation resulted in tangible commitments, including community mobilisation campaigns, reconciliation dialogues, and enhanced coordination between peace committees and local authorities. Similarly, the SSF-led cross-learning and exchange visit for youth councillors from Dangorayo and Badhan Districts led to agreements on improving revenue oversight, collaboration between local councils and executive departments, and the adoption of practical planning tools observed in host districts.
• Knowledge and Capacity Building: The Fiscal Decentralisation Workshop in Warsheikh was viewed as timely and highly relevant. Participants, who included government officials, Civil Society Organisations (CSOs), women, youth, elders, persons with disabilities, and minority clans such as Axmed Faarax, Arab, and Eelaay gained clearer understanding of taxation, local revenue generation, and fiscal accountability, identifying follow-up actions such as improving tax compliance and strengthening service delivery oversight.
Equity
The programme’s approach to equity focused on maintaining gender balance within the core team, ensuring regional representation across Federal Member States, and promoting inclusive participation in all engagements. At the intervention level,
• Gender Balance: Projects maintained a gender-balanced core teams –e.g. SDP’s current team is 50/50 - reflecting commitment to gender equality and inclusivity. This representation sets a positive example for partners and Somali stakeholders.
• Inclusive Participation: Participants in the consultative engagement meeting with the Peace and Reconciliation Committees in Mudug Region were inclusive and representative. Participants across all events reported that the right individuals and key community groups were involved, with balanced opportunities to contribute. Female and youth representation was also noted as adequate, reflecting consistent attention to inclusivity in activity design and delivery.
Assessment of whether the programme continues to represent value for money.

For the review period, SSF III maintained good value for money performance through efficient use of shared resources and activity delivery, and equitable implementation approaches in terms of upholding gender balance, regional representation, and inclusive participation across interventions. Collectively, these measures reflect prudent resource use, promoting accountability, and a continued focus on achieving results in a cost-effective and inclusive manner.

Recommendations:
Previous recommendations on updating the TOC and RF as well as tracking VfM indicators and measures across delivery modalities continue to apply.

E: RISK

Overview of risk management
The overall SSF III risk appetite remains ‘eager’ with severe risk rating. Overall risks are owned by the SRO, with Head of SSF and PRO supporting to monitor and mitigate risks and escalated to JDC as necessary. The programme management team have actively monitored risks, mitigated to minimise impacts and escalated. During the reporting period, all the risks escalated were related to context, policy and reputational risks. The Fund Manager monitors a detailed risk matrix; however, this is consolidated to top risks while reporting to donors.
During the reporting period, the key risks realised were:
Fiduciary Risk: Inconsistencies in participant reporting for a SWS-implemented activity under the Government Accountability Forum in Hudur highlighted weaknesses in activity verification and partner reporting accuracy. Mitigation involved seeking reimbursement for the ineligible expenditure.

Programme Delivery Risk: The Engineering Supervision Firm’s verification exercise identified quality and compliance concerns in the Jowhar parliamentary building support interventions, including deviations from approved designs and materials. These deficiencies posed both fiduciary and delivery risks to the project. SSF III formally halted construction pending corrective action and required the contractor to submit and implement an approved rework plan. The contractor has since committed rectified the defects and mobilized additional resources to ensure adherence to specifications and timely completion. The supervision firm is maintaining enhanced technical oversight throughout implementation.
Corrective measures have since been strengthened to address these issues in subsequent periods. Additional escalated risks related to context, policy, and reputational factors were also noted. To ensure timely escalation and discussion, SSF III and FCDO teams now hold regular risk review meetings, including dialogue on risk appetite. The Fund Manager continues to monitor a detailed risk matrix.
Other key risks monitored during Quarter Four, which the programme will continue to track in Year 3, include:
Delivery Risk – Political & Security Instability: Instability could disrupt Year 3 workplans, as seen in Year 2. Mitigation: SSF III continues to apply conflict-sensitive planning, risk-based approaches, and adaptive programming. Tools like CRAM, dashboards, and research inputs support proactive risk management.
Delivery Risk – Government Objections: Past objections to political dialogue and elections work limited SSF III’s mandate. Mitigation: A new governance structure and regular engagement with FGS/FMS now provide forums for mediation and reduce likelihood of recurrence.
Delivery Risk – Funding: Year 3 has a robust budget from multiple donors, but future funding shortfalls may affect implementation or expansion. Mitigation: Careful financial planning and prepositioning to ensure funds are available for Year 4, reducing medium-term uncertainty.
Political Risk: Pressure to fill funding gaps could strain relationships with national and sub-national governments, threatening SSF III’s ability to deliver its Year 3 mandate. Mitigation: SSF III has clarified its mandate, established annual budgets, and validated Year 3 workplans with government partners to manage expectations and limit additional funding requests.
Update on Partnership Principles
Not strictly applicable as none of the funding is on-budget or flows through government systems. However, the programme seeks to support improvements related to the Partnership Principles, including enhancing government transparency, accountability and responsiveness and improving inclusivity. In addition, capacity building investments seek to improve public financial management, including procurement, and service delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

SSF is a multi-donor fund with six contributing donors (EU Delegation to Somalia, Denmark, Netherlands, Germany, US and UK as Lead donor). The fund is managed through a fund manager (FM) – Adam Smith International (ASI) - who is contracted to provide both programme management and strategic leadership of the programme. The contract was signed in March 2023 with a value of up to £180m but with approval to spend up to £79.9m.

Delivery:
Delivery capability was stronger in the latter half of the year once implementing partners were fully onboarded and the FGS-driven implementation pause had been lifted. In order to manage inefficiencies in lead time, arising to the drafting and approvals processes involved, more efficiency on the concept note modality was pursued and realised, with the final quarter being the highest in deliverable/activity and expenditure performance.
Overall, with this acceleration, the fund met 84% of the annual forecast; with democratisation and local governance accounting for over a quarter of total spend.
Programme Partnerships
The programme delivers through a multi-tiered delivery chain further clustered based on thematic workstreams. The delivery chain has differentiated non-government and government partners leading on core workstream interventions; as well as non-facility partners who deliver on bespoke foundational and/or one-off interventions aligned to the overall outcomes. In maintaining overall accountability, all programme interventions are assigned to and rely on oversight and direction from the ASI Technical Support Unit, programme management unit leads and state coordinators. These mechanisms continue to meet delivery and oversight requirements. That said, particular attention should be paid to managing compliance and performance of partners at the second and third tier, as is contractually mandated. This in particular relates to due diligence, risks and issues identified in the Year 2 annual narrative and audit reporting including on expenditure and activity verification, procurement practice and robust documentation.
Financial Management

Budget and Expenditure
In Year 2, SSF III achieved 84% budget utilisation, spending £10.1 million against a forecast of £11.9 million. Q4 expenditure reached £4.0 million, representing 40% of the annual spend and a 68% increase from Q3, indicating strong delivery momentum. During Q4, the Unit continued to implement activities through the Concept Note approach, which enhanced forecasting accuracy by allowing more granular, activity-level planning resulting no underspend for the quarter. Workstream partners, led by International Cooperation Agency of the Association of Netherlands Municipalities (VNG) and Finn Church Aid (FCA), accounted for the largest share of expenditure, delivering strongly despite initial induction delays and the temporary FGS implementation ban. In contrast, SDP and Build Up recorded slower spend due to political headwinds affecting dialogue and electoral programming.
Non-workstream investments—including the Puntland and Galmudug Peace Initiative, Conciliation Barometer, local government infrastructure support, and legacy construction in Jowhar—totalled £1.93 million ($2.52 million), with 64% realised in Q4. Government partners demonstrated steady improvement, spending £664,665 ($869,867)—40% of their annual total—in Q4. Stronger delivery capacity and familiarity with SSF III systems supported increased government allocations for Year 3, led by Puntland, Galmudug, and Southwest State.
Overall, the programme closed the year with total donor commitments of £38.5 million ($50.4 million) in addition to the UK business case allocation.
The Year 2 annual expenditure overview is outlined below
Budget Category	Spend in USD	Estimate in GBP
Milestone Fund Management Fees	1,629,918	1,245,583
Fund Management Expenses	485,930	371,348
Core fund (RDEL and CDEL)	10,986,575	8,395,940
Total Spend	13,102,423	10,012,871

Further, direct core fund project costs accounted for 89% of total expenditures, with 11% attributed to indirect support, demonstrating cost-efficiency and adherence to value for money principles within the delivery chain.
Audit and Compliance
At the end of Q4, the July 2024-June 2025 SSF annual project audit was completed, and the auditor issued an unqualified opinion confirming that the financial statements and operations were fairly presented and complied with applicable standards. Building on lessons from the previous year’s delayed audit report, the unit proactively commissioned an interim audit covering the first three quarters of the year, which enabled the timely completion and submission of the annual audit. The total ineligible amount identified was £7,038 (approximately $9,212), which is scheduled for recovery in Year 3. This amount primarily arose from weaknesses in supporting documentation and inconsistencies between cheque payees and deposit slip recipients.
Stakeholder management:
Mid-year Review, SSF Partner Day(s) and Learning Workshops provided a platform to share programmatic and thematic lessons; present perspectives from the FMS level; identify evidence and research gaps and priorities; highlight coordinated efforts across various SSF instruments; and explore developments beyond SSF, including identification of complementary initiatives. These processes served to pilot and shape a more integrated model of coordination and encourage cross-functional collaboration. The key emerging decisions outlined below should be tested in year 3 and assessed in the next review
- Key Decision 1: Partner Days will evolve into structured Learning Sessions, where all stakeholders can review workplans, assess progress, highlight achievements, and continue bridging the donor-partner space through presentations at the Joint Donor Committee (JDC) meetings.
- Key Decision 2: FMS Leads/State Coordinators will be repositioned to consolidate engagement at the state level for both government and non-government partners, promoting ownership and reducing duplication. They will also be the assigned communications focal points, working with the Communications Lead to identify significant interventions for donor visibility through targeted communications and case studies.
- Key Decision 3: Direct interaction between delivery partners and donors, including presentations at Joint Donor Coordination (JDC) meetings, will be initiated. This is designed to amplify and promote stronger engagement with delivery and outcomes, providing the opportunity to influence and support a continued unified donor approach.

Delivery, PDIA and collaboration:

Annual Delivery plans: The previous review identified persistent challenges associated with the concept note modality. In response, and informed by feedback received across the delivery chain -including at the partner days - Technical Support Unit leads, State leads, the programme management unit, and SSF leadership took the joint decision to transition to a more efficient planning and delivery approach. Building on the overall annual work plan development and budgeting process, both ASI and its partners collaborated to formalize annual delivery plans for government and non-government stakeholders, aligned to the formal Annual Workplan. For government partners, it was agreed that the previous concept note modality would be retained in some circumstances requiring payments to third parties, with state leads reviewing and approving these plans accordingly.

This revised approach is expected to rebalance the programme’s engagement, placing greater emphasis on the involvement of technical and state coordinators leads during the implementation phase. This adjustment reflects lessons learned from previously disproportionate engagement during the design phase.

Progress on recommendations:

Strengthening partner coordination
The Fund has introduced structured partner days and learning workshops as key coordination mechanisms. These present and opportunity for joint reflection, thematic exchange, and adaptive planning. These measures have significantly improved information-sharing, partner visibility, and strategic alignment, including through engagement with the Joint Donor Committee (JDC).

Oversight of the entire delivery chain
The audit and risk and assurance review reports showed areas of strength and weakness in delivery chain compliance and capability. These have been able to serve as the basis for reinforcing good practice as well as putting corrective action plans in place where required.

State-level coordination and collaboration
As stated above, State Coordinators will now be repositioned to consolidate engagement and communications at the state level for both government and non-government partners.

Recommendations:

Improving accountability within the delivery chain: The audit report showed recurrent gaps in documentation among some implementing partners highlighting the need for stronger delivery chain management. ASI and Consortium leads should institute more robust partner oversight mechanisms, including targeted capacity support, clearer documentation standards, and periodic compliance reviews. The Fund Manager should ensure that improvements are embedded and addressed across all delivery chain partners and that progress is systematically tracked throughout the year through a robust and timely corrective action plan and reported on in subsequent reviews.
Fund Manager and Consortium Leads by February 2026

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Theory of change: Review I recommended an inclusive ToC workshop be held to revisit and revise this critical part of programme documentation, prior to the updated ToC being used to ‘build consensus [amongst donors] regarding the programme’s approach to enabling inclusive dialogue, stabilisation and building stability’. This was argued to be essential for SSF to realise an adaptive management modality.

In response, an inclusive process for developing the ToC and the results framework was held by the Fund management team, including FCDO, facility partners and the Fund’s MEL partner.

Despite the work put into developing it, the revised ToC is far from good practice in the sector. As a half page IF/THEN type statement it only partially does the job a theory of change should do. It is clear about what SSF will do and about the change it hopes those inputs will bring about, but there is no articulation of the problem and why it exists; why these interventions (rather than others) will work; or the assumptions underpinning the logic for the chosen interventions. Rather than a theory, the revised ToC is a series of simplistic and not very credible cause and effect statements, e.g.

IF Somali political and civic actors are equipped to conduct productive political dialogue at the federal, state, and district levels, enabling more effective and inclusive political settlements, THEN Somali political actors will engage in productive dialogue that improves the resolution of political settlements.

This is simplistic because there is no accompanying ‘because’ to explain why a lack of capability is stopping Somali political and civic actors from engaging in productive dialogue, and lacks credibility because you do not have to be an expert on Somalia to know that there is likely to be a lot more going on (politically, economically and socially) that prevents productive dialogue than can be fixed though external ‘equipping’. The statement above is also confused, nesting a THEN statement in the IF one, and referring both to effective political settlements and to their ‘resolution,’ which is hard to make sense of.

This is not simply a compliance with standards issue; without a complete and credible theory of change there is a significant risk of different expectations developing amongst stakeholders of how SSF works and what it is trying to achieve. That will make it harder for the programme to demonstrate results.

The recommendation is therefore that the ToC be filled out with a narrative that explains the theory behind SSF’s chosen approach. This theory will be known to programme team working on SSF but should also be written down so that there is an agreed and single version that everyone can refer to.

Results Framework: Review I was critical of the SSF RF and while some of those criticisms have been addressed in an updated version, some remain relevant. There is a reasonable balance between qualitative and quantitative indicators, but at Output level there remains too much measurement of inputs rather than the immediate results of activities. There is disaggregation within Output indicators and some measure gender and social inclusion, but there are no measures of the roles that women and marginalised groups play in dialogue or other activities (and the RF does not reveal SSF’s ambition for GESI more generally). The outcomes of dialogues and reconciliation are being measured as Review I recommended, but the RF is not obviously trying to capture the linkages between the Outputs.

In addition to Review I’s comments, the lack of indicator baselines is a major weakness of the RF. Although the SSF has adapted its approach and some activities will be new and baselines therefore ‘0’, given this is the third iteration of SSF it seems odd that there are no baselines at all. More problematic is the lack of targets. These were still to be decided at the time of this review (September), already one quarter into the year.

The lack of baselines and targets is of a piece with a general lack of specificity in the RF. This is probably unavoidable with the risk-based approach that SSF has taken; being nimble and responding to risks and opportunities when they emerge means it is difficult, if not impossible in some instances, to predict what will be achieved in advance. There are obvious advantages to this approach in a fluid and unpredictable context, but a downside is that without more specific objectives, the RF will be more a record of changes achieved and less a tool for accountability, because vague indicators make it hard to know what success will look like. That may create a challenge for FCDO’s management of its implementing partner.

Reporting against the RF has mostly been at the output level (the Year 2 Annual Report has a ‘Results Framework Reporting’ annex, but all the evidence provided is against the outputs, not the outcomes), with only formal reporting for Outcome 3 (though an Annual Report annex). This may reflect the challenging implementation context during this period, but should be rectified in future, with complete reporting against the three outcomes provided as part of the Annual Report.

Evidence and Learning

Review I was critical of the SSF MERL approach for not supporting learning. The reviewers argued that SSF evidence generation did not engage with the wider literature and existing evidence, and not enough utility was being made of research and analysis. This was argued to be stopping the programme from being adaptive.

The Fund Manager has responded to this critique; implementation of a Learning and Adaptation Strategy has been taken forward through: quarterly learning workshops, weekly meetings on risks and challenges, use of a tracker of adaptation by SSF partners, use of a tracker for utilisation of research, and adoption of a risk analysis tool, the Conflict Risk Assessment Map (CRAM), to enable an adaptive, risk-based programme management approach. The research utilisation tracker will be expanded to include all available evidence, such as from quarterly reports or third-party monitoring, while a requirement for all research outputs will be the inclusion of actionable recommendations. At the time of this review the Fund Manager was also working to identify existing evidence and work out where primary data collection is needed and where literature reviews will suffice. In parallel, the Fund is establishing a Strategic Advisory Group (SAG), under the Policy Garage business case, to support the Fund’s positioning as a thought leader and enhance the uptake of evidence-based recommendations within donor and partner forums.

While these are all positive developments, it was beyond the scope of this light touch review to assess whether the approach to adaptive management was effective. This should be a key focus of the next full annual review of the Fund in 2026.

Recommendations:

The Theory of Change half-pager should be filled out with an accompanying narrative that explains the theory behind SSF’s chosen approach (including what the problem is, why the chosen approach will tackle the problem, how the approach will work, how this compares to other donors/actors, why the UK is the right donor/partner for this approach, the assumptions underpinning the theory, and the risks involved).
SSF by end March 2026

Further refinements should be made to the Results Framework to improve it.
SSF by end December 2025

SSF should articulate its contribution to GESI outcomes and report against disaggregated results in the Annual report. SSF is clearly working with women’s organisations, thinking about inclusion in its relationship to stability and building evidence of the contribution of its youth engagement to reducing risks. This now needs be captured more clearly to support Donor reporting on their contributions to GESI at the portfolio level.
SSF by end of June 2026

Future SSF Annual Reports should include reporting of evidence against all three outcomes.
SSF by the end of June 2026

Date of last narrative financial report	October 2025	Date of last audited annual statement	September 2025