## LIFT 2025 Annual Review Template

Title: Learning and Inclusion for Transformation (LIFT) [formerly Girls in Rwanda Learn (GIRL)]
Programme Value £ (full life): £[1]60M		Review date: 1st December 2025
Programme Code : 300922	AMP start date: 1st September 2023	AMP end date: 30th June 2030
[1] To note, programme value will be adjusted downwards due to 0.3% decisions. Further information available below.

Summary of Programme Performance
Year	2024	2025
Overall Output Score	B	A
Risk Rating	Major	Moderate

DevTracker Link to Business Case:	D0003590.odt
DevTracker Link to results framework:	S3009229.xlsx

# Acronyms

BESWG	Basic Education Sector Working Group
CSOs	Civil Society Organisations
CPD	Continuing Professional Development
ODA	Official Development Assistance
CwD	Children with Disabilities
GPE	Global Partnership for Education
DDG	Deputy Director General
DDE	District Director of Education
DEU	District Education Units
ESSP	Education Sector Strategic Plan
EDET	Extended District Education Team
EF	Education First
GS	Groupe Scolaire
GOR	Government of Rwanda
HoD	Head of Department
JADF	Joint Development Action Forums
LIFT	Learning and Inclusion for Transformation
MINEDUC	Ministry of Education
MINALOC	Ministry of Local Government
NESA	National Examination and School Inspection Authority
OOSCY	Out of school children and youth
PEA	Political Economy Analysis
RENCP	Rwanda Education NGO Coordination Platform
REB	Rwanda Basic Education Board
RTB	Rwanda TVET Board
TA	Technical Assistants
CoP	Community of Practice
TDM /CGC	Teacher Development and Management Unit/Career Guidance and Counselling (a unit within REB)
VFM	Value for Money
ZOOSC	Zero Out of School Children (a MINEDUC project implemented by Save the Children)

## A: SUMMARY AND OVERVIEW

Description of programme
The Learning and Inclusion for Transformation (LIFT) programme (formerly known as Girls In Rwanda Learn (GIRL)) programme is the UK’s flagship education programme in Rwanda to improve learning opportunities for girls and boys, including highly marginalised out of school children and youth (OOSCY).

Many children in Rwanda, especially girls and children with disabilities (CwD), are not acquiring foundational skills, not progressing through school, not achieving their potential and are unable to thrive. Given this situation, the LIFT programme focuses on two main programme outcomes:

1. Improved foundational learning outcomes in lower primary schools for girls and boys.
2. Reduced drop-out/OOS rates and improved transition to lower secondary or alternative learning pathways, particularly for girls and CwD.

LIFT will achieve these outcomes through five programme outputs,[2] implemented in seven of the most disadvantaged districts in Rwanda. These LIFT outputs contribute to Rwanda’s Education Sector Strategic Plan, National Strategy for Transformation 2, Vision 2050, and the Ministry of Education’s Zero-out-of-School Policy.
[2] Outputs 1-3 are implemented by Cambridge Education, output 4 is implemented by UNCEF, and output 5 is implemented by TetraTech.

1. Teacher Professional Development: To improve foundational learning outcomes through stronger instructional practice, improved classroom English and inclusive pedagogies.
2. Decentralised Education Systems: To strengthen data-driven decision making to improve efficiency and provide better support for the most disadvantaged schools and students.
3. Return to Learning for OOSCY: To support marginalised OOSCY to re-enter, thrive and stay in school or alternative learning opportunities.
4. Support to CwD: To improve inclusion and accessibility in schools for CwD, through improved infrastructure and provision of assistive devices and other resources.
5. Monitoring, Evidence, Research and Learning (MERL) to drive advocacy: Utilising evidence to ensure programme impact at scale for foundational learning and opportunities for OOSCY and CwD.

While some work began under LIFT with UNICEF in 2023 (Output 4), the remaining outputs got underway in 2025 after procurement of Cambridge Education and Tetra Tech. This Annual Review therefore covers a period of procurement, inception and implementation, with different suppliers at different stages.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition - ramping up activities with Cambridge Education this year to increase the likelihood of legacy for the UK’s decades of partnership with Rwanda on education, while also planning for early closure.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
- Summary supporting narrative for the overall score in this review
The period covered by this Annual Review has been set against an unprecedented backdrop of changing politics, priorities and budgets. At the global level, the aid sector saw significant cuts by major donors, which included the rapid dismantling of USAID and a reduction in UK ODA spend from 0.5% to 0.3% of GNI. At the country level, increased conflict in neighbouring DRC has marked a significant escalation in tensions for Rwanda regionally and internationally. In the commercial landscape, in August 2025, Cambridge Education announced the termination of its UK and global operations[3].
[3] However, it has committed to responsibly delivering the remainder of the LIFT programme.

These shifts have necessitated a redesign to accommodate a reduction in the overall funding envelope for the programme[4]. This has decreased the duration of the programme from six to three years, meant early closure of UNICEF and Tetra Tech outputs[5], and a wind-down, rather than scale-up of Cambridge Education’s outputs.
[4] Exact figures yet to be agreed by FCDO HQ.
[5] The closure of Tetra Tech’s contract and reduction in its scope of work has delayed the implementation of baseline data collection, which has not been completed at the time of the writing of this report.

This Annual Review will reference and track progress against the Logframe that was agreed upon completion of the programme’s inception phase, in July 2025 and is available on DevTracker. The milestone targets were mistakenly misaligned with the Annual Review timeline, instead reflecting the first full year of implementation (from April 2025 – March 2026). As such, we have decided to judge progress based on our assessment of likely progress by March 2026, rather than penalise the programme for underperformance.
The current logframe does not adequately reflect UNICEF’s contributions in remedial education, life skills, and child safeguarding. To ensure these interventions are fully recognized within the programme framework, an annex will be incorporated.
A major recommendation of this review to revise Logframe indicators and targets to reflect the restructuring of the programme. The misalignment of milestone timing will be addressed in the revision of the Logframe and new milestone targets will be agreed which align with our Annual Review timeline.
Despite this instability, LIFT has had many successes in the last 15 months￼ and scores an A overall for this Annual Review. Since all partners have come on board, significant collaboration and consultation with government, civil society and implementation partners has quickly positioned LIFT as an influential part of the education system in Rwanda. Critically, REB, NESA and MINEDUC are key partners, providing real-time inputs on evolving priorities and developments within the sector. A major highlight has been LIFT’s ability to flex to address Government of Rwanda priorities. Annex 1 summarises some of these achievements, beyond what is set out in the Logframe.

Major lessons and recommendations for the year ahead
The major lesson learned in this Annual Review period is the need for flexibility and adaptability. LIFT is in a period of considerable flux, with different external factors provoking major design shifts. Handling this transition responsibly and strategically will be critical.
Key recommendations include:
- FCDO to confirm budget profile for remaining years of LIFT as soon as possible. FCDO and Cambridge Education to agree on a responsible and strategic exit plan, retaining flexibility to respond to requests from GoR to maximise impact and secure sustainability in the remaining years of the programme. Careful management will be required to mitigate specific programme exit risks, including fraud and loss of key staff.
- FCDO and Cambridge Education to continue careful communication and collaboration with relevant government stakeholders to manage reputational risks and safeguard gains to maximise the chance of meetings the assumptions set out in section B below.
- Tetra Tech to stay closely engaged with MINEDUC to ensure useful research outputs before the end of contract.
- FCDO and partners to review and revise LIFT’s MEL framework and Logframe based on finalised funding and programme design and to address milestone misalignment.
- FCDO to consider developing a Business Case Addendum given the substantial departures from the original business case, and to ensure public documentation accurately reflects the final programme design, amount and timeline.
- FCDO to consider how best to continue to support CWD through Output 3, in the absence of UNICEF as a programme partner, and with Output 4 closing in December 2025.
- FCDO to develop an engagement plan to safeguard gains in education under a reducing resource envelope, and to support effective policy engagement in education in Rwanda.
- FCDO to rapidly design a new development portfolio, including education, to ensure continuity of partnership with MINEDUC after Mott MacDonald Cambridge Education’s contract ends. This will adapt to a low ODA settlement while maintaining support for improved learning outcomes, strategically influencing major funding sources (domestic, World Bank, GPE), and leveraging the full range of UK partnerships and expertise. Despite ODA reductions, BHC Kigali has identified human capital - education and skills - as a key emerging priority, with a pivot toward a whole-of-UK offer. Drawing lessons from LIFT will be critical to inform future plans and strengthen the UK’s role in driving supporting progress.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Overall, the LIFT programme is contributing to children and adolescents, including the most disadvantaged, having the knowledge and skills to realise their potential and contribute to Rwanda's economic development, as envisaged in Vision 2050. It is doing this by improving foundational learning outcomes in lower primary schools for girls and boys, supporting OOSCY to re-enter, thrive and stay in learning, and supporting CwD to achieve their full potential. LIFT’s success, therefore, is dependent on ensuring:

1. Teachers have strong foundational learning instructional practice, improved language of instruction (English), and inclusive, gender-responsive and non-violent pedagogies.
2. District education actors prioritise support and make decisions based on data that illustrates who and where the most disadvantaged schools and students are.
3. OOSCY are given the holistic support they need - at the school, family and community levels - in order to meaningfully re-enter, thrive and stay in learning.
4. CwD can flourish through provision of assistive devices, supportive learning resources and inclusive infrastructure.
5. The Government of Rwanda owns, scales and sustains this work so that foundational learning and opportunities for OOSCY and CwD continue beyond the life of the programme.

Success amongst these stakeholders and beneficiaries are reflected in LIFT’s outcome indicators[6]:
[6] These outcome indicators reflect the programme design as of May 2025 and will be revised as part of the Logframe refresh in 2026.

1. Outcome 1 - Number of children supported by the LIFT Programme with improved foundational learning outcomes in English literacy and maths.
2. Outcome 2 - Percentage of children repeating a grade in primary schools supported by the LIFT Programme.
3. Outcome 3 - Number of out-of-school children supported by the LIFT programme who enrol and complete one year of school or complete an alternative learning opportunity module.
4. Outcome 4 - Number of LIFT Programme initiatives with commitments from GoR/ Development Partners/ other partners to scale up.
To achieve these outcomes, change needs to occur in the barriers that prevent teachers, district actors, OOSCY and CwD from realising their full potential. Therefore, LIFT interventions aim to address the most salient barriers for teachers (i.e., inconsistent professional development); district actors (i.e., insufficient data collection and analyses); OOSCY (i.e., the myriad of factors that push/pull them OOS); and CwD (i.e., inadequate/ exclusionary resources and environments).[7]
[7] It should be noted that there are a number of assumptions that underpin the theory of change around these interventions/inputs, which are outlined in Annex 1.

When LIFT interventions demonstrate success, the results will be better quality teaching, district support to schools that need it the most, and reduced barriers that prevent OOSCY and CwD from realising their full potential.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Major revision is needed to the Theory of Change and associated Logframe to reflect the reduced programme scope and timeline. The overall impact and outcome remain, but with a shorter time span and reduced geographical and programmatic scope the contribution LIFT will make to these will be lower, and less likely to sustain, and milestones and targets will be updated to reflect this. Outcomes for CWD will be particularly affected due to early closure of UNICEF’s Output 4. However, LIFT is a systems strengthening programme, and FCDO and partners will continue to use all levers at our disposal to support the Government of Rwanda to accelerate progress towards all children, including the most marginalised, being in school and learning.

While Tetra Tech had originally been contracted to conduct a full evaluation of LIFT, the decision has been taken to prioritise resources for implementation. Before the end of their contract (March 2026), we will work with Tetra Tech to set out an evaluation approach for Cambridge Education to undertake, to ensure learning from LIFT. The first step is to collect the baseline data, to be completed by the end of November 2025.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
In normal circumstances, the LIFT programme would be in an excellent position to continue. The remaining partner, Cambridge Education, is delivering well and holds great promise, particularly due to the engagement of GoR stakeholders. However, the UK 0.3% funding position as set out in ‘About changes to UK ODA’ in Section A and Cambridge Education’s exit from the sector, makes this impossible, and so we are in a period of responsible exit.

## C: DETAILED OUTPUT SCORING

Output Title	Cambridge Education: Effective continuing professional development (CPD) implemented through REB to support transition to English as a Medium for Instruction (EMI), literacy and numeracy instruction, and to enhance the inclusivity, safety and gender-sensitivity of classroom environments
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	N/A (new output)

Indicator(s)	Milestone(s) for this review	Progress
Percentage of P1-P3 teachers in programme schools participating in active Community of Practice (CoP) as a core school based CPD modality	First round of baseline data collection completed	Achieved: / First round of baseline data collection completed in November 2025.
Percentage of programme schools delivering active Community of Practice (CoP) as a core school based CPD modality	-LIFT CPD Advisor embedded in REB TDM / - CoP guidelines and monitoring tools are developed and tested / 50% of schools have formed P1-P3 English and Maths CoPs and 10% of them are active	On track: / A CPD Advisor has been successfully embedded in REB’s Teacher Development and Management (TDM) department, with additional advisors expected to join soon. / LIFT has supported the development of Communities of Practice (CoP) guidelines and monitoring tools. / LIFT helped finalize the CPD implementation guidelines, which define the government's strategy for sustainable and high-quality teacher professional development. Training sessions for school leaders based on these guidelines are underway and we expect CoPs to be active by March 2026 milestone.
Percentage of P1-P3 teachers in programme schools trained through in-person workshops	Milestone for the number of teachers to be determined before the first training workshop in 2025. / 70% of teachers complete training on 2 out of 3 topics; / (1) Using English more consistently and accurately during lesson delivery; / (2) explicit literacy instruction to develop students’ reading skills; / (3) inclusive and non-violent pedagogy	On track: / Trainings are scheduled to take place before March 2026 milestone. To note, English proficiency is no longer in scope for LIFT due to an alternative development partner providing this.

Briefly describe the output’s activities and provide supporting narrative for the score.
The LIFT programme has made significant strides in strengthening teacher professional development through REB. Key activities included the co-development and validation of a national CPD framework and implementation guidelines, training of REB Master Trainers, and cascading orientation sessions for school leaders and CPD coordinators across seven districts. Communities of Practice (CoPs) were introduced as a core school-based CPD modality, with guidelines and monitoring tools developed to support their rollout. The programme also embedded a CPD advisor and an ICT Specialist working on REB e-learning platform within REB to ensure sustained implementation and monitoring.

Cambridge Education has flexed to meet new requests from GoR. This was undertaken quickly, and strategically, and has received high praise from REB and MINEDUC. Specifically, LIFT supported the revision of the lower primary English curriculum to include explicit literacy instruction and is developing phonics workbooks using both existing resources and AI-generated content. These materials will be used in upcoming teacher training workshops and represent a critical reform in the lower primary curriculum to improve literacy outcomes. The education sector has been advocating for such a shift for several years, and so LIFT’s ability to quickly grasp the opportunity and support government’s ambition is a major value-add. LIFT has also shown adaptability in responding to MINEDUC’s request for scale. Despite the decision to remain only in seven districts substantially, LIFT will support REB to implement the new approach to CPD across all districts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Over the past year, the CPD output shifted focus from a broader foundational learning agenda to a targeted emphasis on English literacy instruction, in response to MINEDUC’s priorities and budget constraints. Numeracy was removed from the scope, and CPD activities were frontloaded to maximise impact within the shortened implementation period. Planned changes include revising Logframe indicators to reflect the removal of maths, combining similar output indicators for efficiency, and expanding literacy support from two to seven districts. Additionally, REB has proposed extending CPD coordination to secondary education, prompting internal discussions on resource allocation and programme boundaries.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Lessons learned include the importance of flexibility and frontloading activities to mitigate budget reductions, and the value of strategic engagement with REB and MINEDUC to ensure ownership and coherence.
For the year ahead, recommendations are:
Cambridge Education to:
1. Support REB in scaling school-based CPD and strengthening coordination mechanisms with key stakeholders in CPD to avoid delays in implementing the CPD framework.
2. Focus learning on assessing the effectiveness of literacy-focused CPD in improving instructional practice and foundational learning outcomes, to inform future programming and sector-wide reforms
FCDO to:
Revise the Logframe to reflect changes to programme scope and align milestones with Annual Review.
Output Title	Cambridge Education: Strengthening the decentralised education system by improving coordination across government levels and building capacity to implement data-driven decision-making to improve efficiency and provide better support for the most disadvantaged schools and students.
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A (new output)

Indicator(s)	Milestone(s) for this review	Progress
Percentage of programme schools providing monthly data on the agreed key performance indicators critical to improved learning	Data collection system and routines established at school level / (i) 785 school leaders trained on the core priorities critical to improved learning / (ii) 196 out of 785 (25%) schools report monthly data to EDETs	On track: / School leader training will be completed in January 2026. / Schools are reporting data to EDETs, but data to demonstrate whether the 25% target is reached will be collected in December.
Percentage of Extended District Education Teams (a) convening regularly and (b) operating effectively	- District TA embedded in the district office to support the establishment of EDETs / - 7 EDETs established, and first meeting convened. / - EDET guidelines developed and rolled out to EDET members in districts.	Achieved: / All seven District Technical Advisors (DTAs) were successfully recruited. / Seven EDETs were formed, with initial meetings held to disseminate guidelines and align on priorities, including presentations on the new Education Sector Strategic Plan (ESSP). / Validated EDET guidelines were rolled out to team members, and mechanisms for district-level data collection and analysis were introduced to support planning and capacity-building, including workshops on out-of-school children mapping.
Percentage of programme districts that develop and implement data informed action plans	7 EDETs supported on developing and implementing the district data approach	Achieved: / District education units supported to use district-level data for decision making and establishing mechanisms for data collection and analysis of emerging data priorities

Briefly describe the output’s activities and provide supporting narrative for the score.
In the last year, LIFT led efforts to strengthen Rwanda’s decentralised education system by supporting the operationalisation of Extended District Education Teams (EDETs) across seven districts. These teams were established to improve coordination between sector, district and central government actors and to facilitate data-driven decision-making. Key activities included the recruitment and embedding of seven District Technical Advisors (TAs), development and validation of EDET guidelines, and facilitation of regular EDET meetings. These meetings enabled district leaders to analyse education data, identifyunderperforming schools, and take targeted action. For example, Karongi District used EDET data to prioritise school visits and standardise observation tools.

Additionally, Cambridge Education supported the development of district dashboards and trained education officials in data analysis and interpretation. These efforts have laid the groundwork for more responsive and equitable education planning, though challenges remain in scaling the model nationally and ensuring consistent data input across districts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The original plan stipulated that LIFT would operate in seven districts in the first year, scale up to another eight districts in the second year and then to the remaining 15 districts in the third year. The most significant change is the narrowing of geographic scope and the shift from national scale-up to targeted district-level support. This has implications for the programme’s ability to influence systemic reform at scale. Revised indicators and milestones will reflect the reduced scope, and efforts will focus on consolidating gains in the seven districts due to funding constraints and strategic prioritisation. Future efforts will focus on strengthening the student data management system (SDMS) data input and enhancing district-level data use for planning and accountability.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Lessons learned include the importance of tailored district-level strategies and the effectiveness of “thinking and working politically” approaches to foster ownership and reform. The programme also learned that proactive relationship management and regular coordination among district actors are essential for decentralised system strengthening.
For the year ahead, recommendations are:
Cambridge Education to:
1. Support NESA and districts in designing standardised school observation tools, training district teams in data analysis
2. Strengthen communication channels between Provincial Education Coordinators and districts.
3. Gather learning on district-level data use influences planning and resource allocation, to inform broader education sector reform and FCDO’s systems strengthening agenda.
FCDO to:
Revise the Logframe to reflect changes to programme scope and align milestones with Annual Review.

Output Title	Cambridge Education: Effective interventions implemented by CSOs to address multi-dimensional barriers to support OOSCY to access and stay in school/ alternative learning opportunity.
Output number:		3	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	N/A (new output)

Indicator(s)	Milestone(s) for this review	Progress
Percentage of OOSCY who are on track with the ILPs after six months	-Disadvantage assessment completed for 10,404 OOSCY / -ILPs developed for 10,404 OOSCY (Return to mainstream schools and special schools: 3,715 and alternative learning opportunities: 6,689)	Achieved: / The disadvantage assessment has been completed for 10,404 children and ILPs have been developed for all learners.
Number out-of-school children and youth (OOSCY) reached and supported by the LIFT programme	OOSCY targeted: 10,404 / - Return to mainstream schools and special schools: 3,715 / - Alternative learning opportunities: 6,689	On track: / In September 2025, significant progress was made toward reaching out-of-school children and youth (OOSCY), with 7,937 recruited—76.3% of the 10,404 target. Of these, 2,865 children were enrolled in mainstream and special schools out of a goal of 3,715, while 5,072 were identified for alternative learning programmes, achieving 75.8% of the 6,689 target. We expect the remaining 2,500 OOSCY to be reached by March 2026.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focused on enabling CSOs to implement targeted interventions that address the complex barriers faced by out-of-school children and youth (OOSCY) in Rwanda. Through a competitive and collaborative co-creation process, 16 local CSOs were selected and supported to design and deliver context-specific projects. These interventions were informed by a comprehensive disadvantage assessment and a detailed mapping of OOSCY conducted by Cambridge Education, which identified key drivers of dropout such as poverty, violence, and social norms. Individual Learning Plans (ILPs) were developed by CSOs for over 10,000 OOSCY, guiding tailored support across mainstream schools, special schools, and alternative learning pathways.

Originally, the intention was to gradually bring OOSCY back to school across the course of the academic year, but MINEDUC asked LIFT to prioritise quick re-enrolment for the September start of school year. As a result, the programme is ahead of schedule, with 75% of children already back in education. LIFT continues to work closely with other partners supporting OOSCY, such as the Zero Out of School Campaign – led by Save the Children. LIFT’s tailored support model is praised by partners, as it provides holistic support to meet OOSCY where they are and ensure they can continue learning and strengthens district-level coordination through engagement with local government.

‘LIFT has built collaboration between local authorities, schools, and community structures. Verification of out of school children was done carefully, allowing the most vulnerable to be reached. Transition activities have motivated learners to return to class, while community mentorship has reinforced ownership and sustainability. This initiative brings real hope for reducing school dropouts and promoting inclusive education in our District.’ Gregoire Rucamumihigo, Executive Director of ADEPE

To ground interventions in the realities of OOSCY in Rwanda, LIFT conducted a comprehensive research initiative to identify the drivers of dropout. Using key informant interviews and focus group discussions, the study culminated in a detailed report shared with grantees and stakeholders. This research has directly shaped the intervention framework, making it holistic, context-sensitive, and scalable. Growing external interest has also created opportunities to share findings globally through education.org, ADEA, and UKFIET.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was originally due to operate as a pilot, scaling in later years of the programme. However, due to the programme transition we went immediately to implementation, to maximise impact. This compressed timelines and increased pressure on CSOs to deliver quickly, necessitating rapid capacity assessments and tailored support.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Challenges include compressed timelines, limited capacity among some CSOs, and the need to balance support across different age cohorts.
Lessons learned include the value of co-creation in building ownership and readiness, and the importance of flexible, evidence-informed design. The disadvantage assessment tool has proven critical for targeting support and assessing value for money.
Importantly, under the OOSCY component, we will capture lessons learned on how to effectively work with out-of-school children so that future programmes and partners can build on this experience.
For the year ahead, recommendations are:
Cambridge Education to:
1. Continue tailored technical support for CSOs.
2. Ensuring older youth in alternative pathways are adequately served, working with the RISE programme.
3. Collect robust evidence to demonstrate impact and contribute to better understanding of how best to support OOSCY.
FCDO to:
Revise the Logframe to reflect changes to programme scope and align milestones with Annual Review.

Output Title	UNICEF: Improved accessibility in selected schools for children with disabilities through improved school infrastructure including the provision of assistive devices and other resources.
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A (new output)

Indicator(s)	Milestone(s) for this review	Progress
Number of programme-supported schools with improved inclusive learning environments, based on inclusive national school infrastructure standards	Original Logframe target: 89 / Revised agreed target due to early closure: 25	Exceeded: / The target was revised down due to the decision to close the output early. UNICEF is on track to exceed the revised target of 25 schools by the end of the calendar year, upgrading 57 schools.
Number of learners with disabilities supported in their learning through the provision of assistive devices /technologies	1249	Exceeded: / 1,372 assistive devices were distributed, because 93 of the beneficiary children had multiple disabilities that required more than one device. / With remaining funds, UNICEF will distribute 246 additional devices during the closeout period.

Briefly describe the output’s activities and provide supporting narrative for the score. This output, managed by UNICEF, procured and distributed assistive devices and delivered infrastructure upgrades to support some of the most marginalised learners, CwD. Following finalisation of the Logframe, a decision was taken by BHCK’s Development Director to close the UNICEF component early (in December 2025), following a formal Performance Improvement Plan (PIP) which concluded in May 2025. At this point, revised milestone targets for 2025 were agreed between FCDO and UNICEF. These updates were not reflected in the Logframe, due to FCDO guidance that Logframes should not be changed within six months of an Annual Review. Revised milestone targets for 2025 are on track to be met, and even exceeded.
UNICEF also led work to support safeguarding, inclusive education, life skills, and remedial learning, ensuring minimal disruption for learners, teachers, and communities. This output finished in August 2025 and is not reflected in the Logframe. UNICEF made notable progress in strengthening child protection systems, expanding adolescent health clubs, and delivering remedial education. Safeguarding committees were trained and equipped with toolkits, while interactive platforms like the YAhealth ChatBox and ISOOKO magazine enhanced access to accurate information. Teachers and peer educators demonstrated improved facilitation skills, and schools used learner assessment data to design targeted interventions. Annex 3 provides more detail on this area of work.
UNICEF’s achievements were undermined by programme management shortcomings. Key concerns included delays in infrastructure upgrades, underspending beyond the acceptable variance threshold, and technical shortcomings in the Monitoring, Evaluation and Learning (MEL) strategy and Social and Behaviour Change (SBC) campaign plan. These challenges led to a series of corrective actions through a Performance Improvement Plan (PIP), including revisions to the MEL and SBC strategies, exploration of alternative delivery modalities for infrastructure works, and improved financial reporting. However, due to limited progress against the PIP at the end of the period, the decision was taken in May 2025 to close the UNICEF project early, at the end of 2025, with adjustments to workplans and milestones as a result.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
As above, it has been agreed that UNICEF’s role on LIFT will end at the end of this calendar year. However, support for children with disabilities was maintained and integrated into Output 3, ensuring that interventions for out-of-school children also address the specific challenges faced by learners with disabilities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
UNICEF made partial progress on last year’s recommendations, with notable achievements in strengthening safeguarding systems, expanding adolescent health clubs, and distributing assistive devices to children with disabilities. However, some planned activities—such as infrastructure upgrades and comprehensive monitoring—experienced delays. With UNICEF’s project ending in December 2025, the programme is now focused on finalizing key deliverables, ensuring effective documentation, and preparing for a smooth transition.
For the year ahead, recommendations are:
UNICEF to:
1. Develop stronger internal quality assurance in reporting, clearer alignment between programme activities and measurable outcomes, and more effective use of data to demonstrate impact.
2. Ensure final reports – including required financial reporting - are accurate, complete and delivered on time.
FCDO to:
1. Revise the Logframe to reflect changes to programme scope and align milestones with Annual Review.
2. Ensure LIFT’s much reduced focus on inclusion is reflected in available documentation through any Business Case Addendum.

Output Title	Tetra Tech: Monitoring, Evaluation, Research, and Learning (MERL) drives the delivery of programme outcomes, responds to programme and policy evidence and learning needs and contributes to the global evidence base on what works.
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A (new output)

Indicator(s)	Milestone(s) for this review	Progress
Number of people reached through disseminated reports /knowledge products /events that support the uptake and use of evidence in response to programme and policy evidence /learning needs	60 people reached through dissemination	On track: / First knowledge product – Component 1 research – due to complete in January 2026. Dissemination to take place in February/March 2026. / Two remaining knowledge products to be disseminated by March 2026.
Number of FCDO-approved MERL, evaluation and research reports, knowledge products, and events delivered	April 2025 to September 2025 milestones: / Evaluation Design Note / QPR 1 / September 2025 to March milestones: / Baseline Research (now C1 Research) Fieldwork Report / Baseline Research (now C1 Research) Report / Baseline Research (now C1 Research) Learning Brief / Baseline Research (now C1 Research) Webinar / IP coordination/ learning workshops / 2x QPR/ APR / Reflection workshop	On track: / All deliverables up to point of Annual Review delivered, and remaining deliverables on track. / Inception Report – Approved / Evaluation Design Note – Approved / Revised C1 Research Design Note – Approved / LARS Pilot Report – Approved / Quarterly Report 1 – Approved
Quality of technical advisory support provided to the FCDO and IPs to support monitoring, reporting, and test-learn-adapt approaches to drive programme learning, adaptation and improvements.	Overall performance ≥70%	On track: / Survey to be conducted with FCDO, CE and UNICEF in February to inform MERL Programme Completion Report (PCR).

Briefly describe the output’s activities and provide supporting narrative for the score. During the inception phase of the LIFT programme for components implemented by Tetra Tech and Cambridge Education, Tetra Tech played a pivotal role in fostering collaborative coordination with UNICEF and Cambridge Education to co-develop Monitoring, Evaluation, Research, and Learning (MERL) frameworks. This included joint development of Logframes and theories of change, ensuring alignment across partners. In response to anticipated reductions in Official Development Assistance (ODA), Tetra Tech provided strategic technical guidance to FCDO, enabling evidence-informed decision-making and adaptive programme design.
A key achievement during inception beyond expected outputs, was Tetra Tech’s rapid mobilisation to support NESA in piloting the Learning Achievement in Rwandan Schools (LARS) test. With limited time to procure a supplier, the MERL team trained enumerators and delivered the pilot test report, enabling NESA to proceed with the full assessment before school closures.
Substantial revisions to the Theory of Change, Logframe, and Inception Report were necessary due to changes in FCDO’s ODA cuts. Research topics have since been endorsed by MINEDUC, FCDO, and Cambridge Education, and discussions are underway to secure a waiver for Institutional Review Board (IRB) protocols. This would allow Tetra Tech to complete studies within the LIFT MERL contract period, now ending 31 March 2026.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The LIFT MERL output was adapted to reflect a shortened programme timeline and evolving donor priorities, including the reduction of the planned five-year impact study to a rapid research format, and closure of Tetra Tech’s contract in March 2026.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The previous year’s review highlighted procurement delays, notably the non-concurrent onboarding of the MERL Supplier alongside the GIRL Lead Supplier. This misalignment created initial challenges for inception-phase activities. However, since the commencement of the MERL contract, these delays have been substantially addressed. The MERL Supplier was successfully mobilised, and coordination with the Lead Supplier (Cambridge Education) was enhanced through structured joint planning workshops, regular meetings, and harmonisation of workplans.
Although the delayed start compressed timelines for certain baseline activities, targeted mitigation strategies—implemented during the design phase—ensured that inception deliverables were met without compromising technical quality. Lessons learned include the importance of early supplier alignment, flexible sequencing during inception and coordination between suppliers.
For the year ahead, recommendations are:
For Tetra Tech:
1. Stay closely engaged with MINEDUC to ensure useful research outputs before the end of contract.
2. Ensure final reports – including required financial reporting - are accurate, complete and delivered on time.
3. Ensure Cambridge Education, as the only remaining supplier for LIFT, is well capacitated to enable learning and knowledge transfer before the LIFT programme ends.
FCDO to:
Revise the Logframe to reflect changes to programme scope and align milestones with Annual Review.

## D: VALUE FOR MONEY

Key Cost Drivers and Performance
As a full programme, with all partners on board, LIFT is still in the early stages of implementation, making it premature to fully assess VfM performance and key cost drivers. However, initial procurement activities and strategic partnerships have already demonstrated strong value for money. Key cost savings include:
- Training delivery: costs have been reduced by leveraging government infrastructure and staff (e.g. CPD and EDET workshops held in district offices, avoiding hotel venues and external facilitators).
- Procurement: Local procurement though bulk printing will achieve economies of scale.
- Digital innovation: Tools like the YAhealth ChatBox and school-based mentors have extended reach at low marginal cost.

VfM Performance Compared to the Original Proposition
The programme’s VfM proposition, as outlined in the Business Case, remains valid. A VfM framework aligned with the 5 Es (Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness) has been developed by the LIFT MERL team. VfM metrics were paused due to ODA budget uncertainties and will be agreed before the end of the financial year. However, the programme has shown strong early performance.
Economy: Payments are aligned with planned activities, and procurement procedures are strong. Achieved low costs relative to benchmarks by using government master trainers and zonal training sites. Economies of scale were realised through bulk printing and competitive procurement. CPD and EDET workshops were held in cost-effective venues (e.g. schools, district offices), avoiding hotel costs.
Efficiency: The programme demonstrated adaptive management in response to ministry requests including the distribution of CPD framework to 23 districts out of LIFT target. The programme successfully delivered EDET activities and maintained efficient processes. However, underspending and delays on UNICEF’s side over the last fiscal year highlight a key lesson around financial control and performance management across other partners
Effectiveness: Strong sector relationships including leveraging co-chair position and LIFT staff who have been supporting the sector in the past have facilitated planning and alignment with government priorities.
Equity: The programme has prioritised marginalised districts and co-created interventions with adolescents. The Innovation Fund has targeted ultra-marginalised groups, including children with disabilities and street children.
Cost-effectiveness: It is too early to judge cost-effectiveness as we do not yet have data on learning outcome improvements. The assessments made in the Business Case will need revising due to reduced programme scope and timeline. However, early progress suggests the programme remains cost-effective.

Assessment of Whether the Programme Continues to Represent VfM
There is sufficient evidence to conclude that the programme continues to represent acceptable VfM. While some outputs are still in early stages, procurement and implementation practices have demonstrated commitment to VfM principles. Key recommendations for the coming year include:
Finalising and tracking VfM metrics with remaining implementing partner.
Accelerating implementation to avoid further delays and underspend.
Continuing to embed sustainability and equity in programme design.

The programme remains aligned with FCDO’s strategic priorities and contributes to broader HMG goals on inclusive education and gender equality. As such, continuation is recommended, with ongoing monitoring and adjustments to ensure VfM is maximised.

E: RISK

Overview of risk management

The overall programme risk rating is assessed as Moderate, based on a combination of likelihood and impact across key programme outputs. This rating reflects the cumulative effect of individual risks, most of which fall within the moderate category.

Recent developments, including the reduction in Official Development Assistance (ODA) from 0.5% to 0.3% and the withdrawal of Cambridge Education (CE) from development activities have introduced new risks. These risks pose potential threats to programme delivery, sustainability, and accountability. Mitigation strategies have been developed to address these challenges through structured planning, stakeholder coordination, and proactive risk management. A dedicated risk matrix has been used to assess and monitor each risk and close oversight will be essential to safeguard programme outcomes and ensure a responsible transition.

With mitigating actions in place, the programme remains Moderate risk.

Key risks identified and mitigating actions include:

ODA cuts and programme transition (Strategic and Context category): Strategic planning is underway to realign activities with reduced resources. Priority is being given to sustaining previous gains, while partnerships with government and key development partners are being strengthened.

The early closure of the MERL component and Cambridge Education’s withdrawal (Programme Delivery) could lead to insufficient evidence on what works to inform policy and weaken technical assistance due to staff attrition. To minimize these impacts, Tetra Tech is coordinating closely with FCDO to maintain MERL continuity beyond March 2026, redistributing responsibilities, and leveraging existing data sources. Structured planning and proactive documentation of lessons learned will help preserve institutional knowledge and ensure actionable insights despite reduced timelines

Cambridge Education’s early exit (Fiduciary and Safeguarding) may compromise continuity of oversight and internal controls, increasing the risk of weakened financial management and safeguarding protocols during transition. To address this, a structured exit strategy is being implemented with stakeholder involvement, reassignment of key responsibilities, and enhanced monitoring to maintain compliance and mitigate capacity gaps

Safeguarding in out of school CSOs: Safeguarding protocols are well-integrated across the programme, with training and audits conducted, but ongoing monitoring and refresher trainings are recommended to maintain standards. No safeguarding or fraud incidents were reported during the review period from CSOs. However, continuous monitoring and periodic refresher training are recommended to maintain vigilance and compliance.

The shortened implementation period for the Out-of-School Children and Youth (OOSCY) component (Programme Delivery), could limit opportunities to generate robust evidence and fully test approaches, reducing insights for future programming. To address this, the team will prioritize rapid baseline data collection, leverage existing secondary sources, and document lessons learned throughout implementation. Early stakeholder engagement and piloting scalable interventions within the available timeframe will help ensure actionable findings despite time constraints

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The programme has made encouraging progress in its first year with a full complement of partners, with strengthened delivery systems and improved commercial and financial performance. The transition from UNICEF as a sole partner to a multi-partner model introduced new energy and enhanced coordination, with implementing partners demonstrating commitment to contractual obligations and responsiveness to FCDO priorities. There has, however, been variable standards of programme management across different suppliers, outlined below. Safeguarding and compliance were well-integrated into programme operations. Ethics and anti-bribery training were completed; safeguarding policies were operationalised. Gender equity was prioritised, with balanced representation in key teams and inclusive approaches to delivery.

Cambridge Education and Tetra Tech

Cambridge Education and Tetra Tech successfully completed their inception phases, submitting all deliverables on time and to the required quality standards. Financial forecasting was generally accurate. Both partners showed flexibility in adapting to evolving scopes of work, including the integration of demand-led research and adjustments to MERL activities.

Quarterly financial reports were submitted consistently, providing clear breakdowns of expenditure, value for money, and forward-looking forecasts. Budget revisions were handled collaboratively, with partners responding to FCDO queries and proposing reallocation to priority areas. Governance mechanisms such as delivery chain maps were maintained in line with FCDO requirements.

Coordination across the delivery chain was effective, supported by regular joint planning sessions and regular catchups. The governance framework, including National Steering Committees, Advisory Groups, and Consortia Forums, enabled coherent planning, risk management, and strong engagement with government stakeholders.

Strategic relationship management scorecards for the commercial partners Cambridge Education and Tetra Tech highlighted shared strengths in responsiveness, technical expertise, and stakeholder engagement. Both partners contributed to sector-wide initiatives and maintained open communication with FCDO, supporting continuous improvement and alignment with programme objectives.

UNICEF

While UNICEF engagement helped initiate key activities, challenges emerged around reporting quality and financial forecasting. These were addressed through a Performance Improvement Plan (PIP), and following constructive dialogue, the contribution arrangement was concluded earlier than planned. The transition was managed collaboratively to ensure continuity and minimal disruption.

A safeguarding case was reported by UNICEF, but the investigation was conducted and closed with strict confidentiality, and only our central focal team was kept informed in line with UNICEF’s established procedures.

In summary, the programme has benefited from the professionalism and strategic engagement of its partners. While adjustments were necessary during the year, they were managed constructively and transparently. The foundations laid during this period provide a strong basis for continued delivery, learning, and impact.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation

Monitoring activities during the review period focused on establishing foundational systems for performance tracking and adaptive management. Key activities included:
- A field visit by Tetra Tech during inception, which informed programme design and stakeholder engagement strategies.
- Collaborative development of the Theory of Change, Logframe, and MEL strategy by all suppliers, ensuring alignment with FCDO reporting and strategic priorities.
- Baseline tool development across workstreams, with early data collection underway (e.g. CAMIS-based learning outcomes).

The LIFT team at FCDO took opportunity to visit schools in Gakenke, Gasabo, Huye and Kirehe in the course of completing the Annual Review to meet headteachers who have benefitted from training, to monitor UNICEF efforts in assistive devices and school infrastructure upgrades, and to discuss the decentralised model with EDETs[8]. We also held discussions with CSO partners and informal interviews with colleagues in MINEDUC and REB. The feedback from stakeholders was overwhelmingly positive. There was widespread appreciation both for the collaborative, co-creative approach of partners, the flexibility demonstrated in response to changing contexts, and the quality of assistance provided.
[8] Recommendations from these field visits can be found at Annex 3.

Now that the programme will not have a dedicated evaluation or MERL supplier beyond March 2026, it will be important to agree appropriate channels for monitoring and evaluation for Cambridge Education to undertake. These discussions are underway.

Evidence
Evidence generation has been affected by the early termination of the MERL contract and implementing partner agreements, which disrupted planned data collection. However:

- UNICEF collected Year 2 monitoring data, including CAMIS-based learning outcomes and programmatic visit reports.
- The Mapping of Out-of-School Children and Youth (OOSCY) and CAMIS data reviews have informed targeting.
- Discussions are ongoing to refine baseline strategies and explore alternative data sources (e.g. end-of-year exam results).

The programme is committed to strengthening inclusive data systems and aligning MEL with government-led assessments such as LARS.

Tetra Tech has refined its deliverables, and will now produce three pieces of research before contract closure in March 2026. These include:
- Research on teacher professional development
- Research on climate and education
- Research on OOSCY
Learning
Learning has been embedded through regular reflection sessions, partner exchanges, and technical workshops facilitated by the MERL supplier. These platforms have enabled the programme team to capture operational lessons and adjust approaches in real time.

Key lessons include:
Sustained coordination and joint reflection between implementers, government, and FCDO improves programme coherence and responsiveness.
Multi-supplier programmes benefit from contingency planning in procurement and inception design.
Programmes can increase sustainability by aligning baselines and MEL systems with government-led assessments (e.g. LARS), rather than developing parallel evidence systems.
More investment in inclusive data (age, sex, disability, geography) is necessary to operationalise the “Leave No One Behind” agenda and inform policy dialogue.

Looking ahead, the programme aims to deepen its learning agenda through participatory monitoring approaches and strengthen evidence use in adaptive management.

Date of last narrative financial report	- Cambridge Education:14th November 2025 / - Tetra Tech: Q2 report on 14th October 2025 / - UNICEF: Q2 report on 20th October 2025	Date of last audited annual statement	Not yet conducted

ANNEX 1

Table 1. Summary of Cambridge Education achievements beyond the Logframe

Achievement	Detail of Success
Establishment of a strategic LIFT technical governance structure	The LIFT Strategic Oversight Committee (SCO) and Advisory Group (AG) were established to provide high-level strategic direction and guidance to the programme. These bodies serve as critical platforms for coordination, decision-making, and stakeholder engagement. The SCO is chaired by the Minister of Education, reflecting its role in steering national education priorities. The AG, meanwhile, is chaired by the Director General of the Rwanda Education Board (REB), ensuring alignment with implementation and operational frameworks. / Membership of both groups includes key stakeholders and institutional leaders, such as The Education Advisor from FCDO, Director Generals from REB, the National Examination and School Inspection Authority (NESA), and Rwanda TVET Board (RTB), Heads of Departments from REB and NESA, The Provincial Education Coordinator for Kigali, and Representatives from Cambridge Education and Tetra Tech.
Successful stakeholder engagement to increase ownership of LIFT with system actors	Engagements with senior stakeholders - including Ministers, the Permanent Secretary, Directors General, and Heads of Departments - were complemented by workshops with decentralised education leadership from LIFT districts of intervention and active participation in technical working groups and taskforces such as BESWG, RENCP, and the NESA Quality Assurance TWG, strengthening coordination and driving progress in teaching quality and learning outcomes.
Responsiveness to GoR requests and going beyond LIFT’s intended scope	In response to GoR requests and priorities, we supported REB to rapidly review the lower primary English curriculum to include a systematic and explicit focus on literacy and phonics, to align with ongoing government reforms. Moreover, our approach includes national-level scale up of CPD delivered across 23 districts using a light-touch model, with deeper engagement in 7 LIFT districts. By directly addressing government priorities, this strategy has strengthened GoR engagement and ownership of the initiatives.
Successful influencing of system actors	Strategic engagement with REB leadership resulted in the request for LIFT to prioritise literacy-focussed trainings and materials that take a more evidence-based, systematic approach to developing students reading and writing skills in English. This again demonstrates buy-in and trust in the LIFT programme from government.
Capacity building and implementation support to the education system	District Technical Advisors (TAs) have been deployed through LIFT to strengthen capacity and provide hands-on support to District Education Offices, ensuring effective implementation of education initiatives. At the regional level, LIFT has also recruited and embedded two Technical Advisors within REB. One advisor, positioned in the TDM/CGC department, is driving the implementation and monitoring of the CPD Framework, ensuring teacher professional growth is systematically supported. The second advisor, placed within the ICT department, is leading the development and management of the REB’s e-learning platform and digital education systems, enhancing access to technology-enabled learning solutions.
Leveraging resources and synergising with key players	Coordination with similar interventions, such as the ZOOS Project implemented by Save the Children, the World Bank supported English programme by EF, and the Mastercard funded RISE Project to be implemented by UNICEF, has been instrumental in leveraging resources and expertise across the education sector. These collaborative efforts have helped ensure strategic alignment, minimize duplication, and promote synergy among stakeholders working toward shared goals.
Effective design and launch of a complex innovation fund to support OOSCY	Building on lessons learned from the Girls’ Education Challenge (GEC), we successfully designed a holistic innovation fund to support OOSCY, contracted CSO implementing partners, and initiated implementation within a relatively short timeframe. In addition, GEC templates and insights have been systematically applied to mitigate risks and avoid costly mistakes in future programming.
Rapidly responding to FCDO requests	In February 2025, we made a significant contribution to the Inclusive Education Symposium, providing thought leadership as well as presenting and facilitating key sessions. In addition to this, we also delivered scenario planning exercises addressing budget reductions on three occasions and provided two additional exercises focused on absorbing supplementary budget allocations. Additionally, we supported a number of high level visits for the British High Commissioner.

ANNEX 2 – Theory of Change

Annex 3 – Further detail on UNICEF work missing from Logframe

Progress Report (September 2023 to December 2025)
Learning and Inclusion for Transformation (LIFT) Programme
 Funded by the Foreign, Commonwealth and Development Office (FCDO), UK

Programme Overview

The LIFT programme aims to accelerate improvement in learning outcomes and primary completion for vulnerable girls, boys, including those with disabilities in selected schools in Rwanda. It comprises five components[1], two of which are implemented by UNICEF. These are Component 2 (Child safeguarding, life skills and remedial education in upper primary) and Component 4 (Inclusive learning environments for children with disability). The two components were subdivided into five outputs. Since September 2023, UNICEF implemented the programme in 155 primary schools across Ngororero, Gakenke, Rusizi, Gisagara, and Karongi Districts.

In May 2025, FCDO took a decision to wind down UNICEF-managed Component 2 by 31 August and Component 4 by December 2025. UNICEF committed to continue critical interventions in the 155 primary schools to minimize disruption and sustain gains achieved by the programme.

The summary below provides an overview of the progress made during the partnership under each of the five outputs.

Output 1: Programme schools are safe, protective and inclusive learning environments for girls, children with disabilities and other vulnerable learners.

Under this output, the programme improved learning environment in the 155 primary schools where an estimated 29,500 primary four (P4) and five (P5) students improved their knowledge about safeguarding risks, and actions they can take to mitigate safeguarding risks. Further, child protection and safeguarding measures were integrated in school improvement plans, thereby ensuring sustainability of interventions.

A cadre of 33 skilled master trainers was organised and capacitated to provide technical support to establish and operationalise school-based child protection and safeguarding mechanisms. The pool of 33 skilled master trainers were drawn from key government institutions, including Rwanda Basic Education board (REB), National Child Development Authority (NCDA), Rwanda Investigation Bureau (RIB and key non-government organizations, including Save the Children, Inspire, Educate, Empower (IEE), Collectif des Ligues et Associations de Défense des Droits de l'Homme (CLADHO), Plan International, Right to Play and Chance for Childhood. These trainers provided sustained technical support to establish, operationalize and maintain school-based child protection and safeguarding mechanisms.

Child Protection and Safeguarding committees were established and fully functional in 155 schools, to provide safe environment for children and a mechanism for reporting any child protection concerns in schools, at home and/or on the way to school. The committee, comprising of eight members in each school, include representatives of students, teachers, the head teacher and parents-teacher association. Members are intentionally inclusive to ensure diverse representation and support for children as well as stronger community accountability. The committee members were oriented on their roles and responsibilities, equipping them with skills on how to identify and handle child protection and safeguarding matters occurring within school settings, as well as child protection and safeguarding measures, like reporting and referral mechanisms. As a result, 155 schools supported under the LIFT programme now provide safer, enabling and inclusive learning environments for vulnerable children, especially girls and children with disabilities.

Output 2: Girls enrolled in upper primary are equipped with vital knowledge and life skills and enabled to access integrated sexual reproductive health and rights (SRHR), human immunodeficiency virus (HIV) and gender-based violence (GBV) services.

The programme enhanced adolescents’ knowledge and safe practices related to sexual and reproductive health and rights (SRHR), HIV, and gender-based violence (GBV). Across five districts, 310 school Health and Life Skills Clubs were established in 155 schools to provide structured platforms for continuous learning and behaviour change.

Peer educators and teacher mentors were trained to lead holistic, youth-centered health education. A total of 420 peer educators (250 girls and 170 boys) and 584 teacher mentors (269 men and 315 women) were equipped with skills to address SRHR, HIV prevention and care, GBV, and mental health and other issues affecting adolescents’ wellbeing. Club activities use interactive, play-based learning methods supported by a dedicated information, education, and communication package to enhance engagement and build practical life skills, confidence and assertiveness.

A digital platform- YAhealth ChatBox-expanded access to safe and reliable information for adolescents. The ChatBox provides secure, youth-friendly guidance on child protection and safeguarding, violence against children (VAC), gender-based violence (GBV), and online risks such as cyberbullying. The ChatBox offers a secure space for young people to ask questions anonymously, access verified information and connect to referral services for support. The tool is now live on WhatsApp and will soon be integrated into Facebook, Instagram, and the YAhealth app, expanding its reach and accessibility to more adolescents across the country.

These combined efforts have improved knowledge and life skills for 9,082 children. In total, 6,664 girls and 2,418 boys, including 68 children with disabilities (35 girls and 33 boys) benefited from strengthened life skills, safer learning environments, and improved access to information. UNICEF remains committed to sustaining these gains despite early termination of the LIFT programme. Support will continue to ensure that all the health clubs remain operational, and continue empowering adolescents, especially girls- towards healthier, safer transitions to responsible adulthood.

Output 3. Girls and boys, including those with disabilities, are engaged and supported to achieve grade-appropriate learning benchmarks.

The programme strengthened the delivery of remedial education to help girls and boys achieve grade-appropriate learning benchmarks. A total of 310 teachers (122 female and 188 male) received continuous coaching and mentoring from remedial learning advisors and school-based mentors. The consistent support and mentoring improved learning outcomes for 30,335 children (15,394 girls and 14,941boys).

Learning outcomes improved significantly within one academic year. End-of-year results for 2024/2025 show the primary five English mean scores increased from 41 to 47 per cent, while Mathematics scores also rose from 42 to 49 per cent - a gain of six and seven percentage points respectively indicating a significant improvement in learning outcomes in just over a year.

School leaders were equipped to sustain quality remedial instruction. To ensure sustainability, the capacities of 310 Head and deputy head teachers (39 per cent female), were strengthened in supportive supervision, use of assessment data, and monitoring of learning progress. Emphasis on gender-responsive pedagogy and differentiated instruction helped support teachers to design tailored support to diverse learning needs of students, particularly struggling learners who received support to improve learning outcomes.

Teachers are increasingly applying effective and inclusive pedagogical practices. Preliminary results of lesson observations undertaken by remedial learning advisors show that 71 per cent of teachers consistently use gender-responsive and differentiated teaching approaches to identify and meet diverse learning needs of students. This anecdotal evidence suggests improvement in teacher competencies on effective pedagogical practices and contributes directly to more effective learning support for all children, including those with disabilities.

Output 4. Intervention schools provide improved inclusive learning environments for children with disability.

Infrastructure accessibility was improved in 57 schools. The programme advanced inclusive education and laid critical groundwork to close school infrastructure accessibility gaps, ensuring children with disabilities can fully participate in learning. The LIFT programme enabled 57 schools to address key physical barriers, creating safer and more accessible learning environments for children with disability.

Assistive devices expanded children’s ability to learn and participate. A total of 1,218 children with disabilities received critical assistive devices, including wheelchairs, hearing aids, and white canes-enhancing their mobility, communication, and participation in learning activities. Among them, 81 children requiring specialized devices received advanced care to improve both access to and quality of learning. An additional 256 devices procured later are currently under distribution to further expand support.

Output 5. Effective advocacy and behaviour change communications campaigns contribute to the reduction of barriers to education for girls and children with disability.

The programme strengthened knowledge, positive attitudes and practices that shape equitable access to educational opportunities for the most vulnerable children, especially girls and children with disabilities.

Evidence from the Knowledge Attitudes and Practices (KAP) survey highlighted persistent gaps and harmful norms in Rwanda. Survey findings show that limited awareness of sexual and reproductive health, menstrual hygiene, and disability among students, parents, and teachers continues to restrict girls’ participation in school and the support available to children with disability.

Community mobilisation, driven by pragmatic human-centred design, reached 8,000 parents across 52 villages (aligned with 37 schools) in two districts, to promote parental involvement in education while allaying socio-cultural barriers.

Negative attitudes and stigma remain core drivers of exclusion. Adolescent girls often face pressure and expectations related to early marriage, household duties, and fear of GBV, while CWDs are frequently viewed as “unable” or “different,” contributing to discriminatory practices and reduced learning engagement.

[1] [1] The five components are Output 1: Programme schools are safe, protective and inclusive learning environments for girls, children with disabilities and other vulnerable learners; Output 2: Girls enrolled in upper primary are equipped with vital knowledge and life skills and enabled to access integrated SRHR, HIV and GBV services; Output 3: Girls and boys, including those with disabilities are engaged and supported to achieve grade-appropriate learning benchmarks ; Output 4: Intervention schools have improved inclusive learning environments for children with disability ; Output 5: Effective advocacy and behaviour change communications campaigns contribute to the reduction of barriers to education for girls and children with disabilities

Annex 4 – Recommendations from field visits for Cambridge Education and UNICEF

Cambridge Education:

- Encourage proper use of learning materials, including books and readers stored in the library, in classrooms.
- Continue to support partners to address English language proficiency gaps among teachers.
- Advocate for streamlined administrative requirements for CPD Coordinator teachers to reduce workload.
- Advocate for strengthened monitoring of remedial education and attendance.
- Explore alignment between district level mapping/tracking activities and the Karame system.
- Advocate for NESA to provide standardised tools and methodologies to support SEIs in their school monitoring.
- Investigate gaps in EF English training access to ensure inclusivity.
- Maintain coordination through EDET and sector-level teams for sustained impact.
UNICEF:

- Engage Government Stakeholders to explore options for integrating non-government-aided centres into public support systems.
- Follow up to ensure the child with mobility or other physical accessibility needs is placed in a classroom that accommodates their requirements.
- Ensure cost-effectiveness and optimal value for money in all infrastructure upgrade expenditures.