Evaluation Report for Programme Name: / FCDO’s World Health Organization (WHO) Core Voluntary Contribution (CVC) / Programme

Response to FCDO’s World Health Organization (WHO) Core Voluntary Contribution (CVC) / Programme / Recommendations from evaluations / We appreciate the thorough evaluation conducted by DAI Global and the valuable insights provided in the report. The recommendations are crucial for FCDO learning from the current programme and enhancing the effectiveness of future further programming with WHO. / The report highlights several key findings. The top line findings focus on whether the programme supported WHO reform and delivery, whether the programme design responded to WHO needs and contributed to the wider sustainable funding agenda. Findings included: / The design of the overall programme was fully aligned with the objective of strengthening WHO institutional performance. / There was clear recognition by FCDO of the challenges associated with the transition to a different funding model. A range of mechanisms were put in place to mitigate risks and to manage the transition. These included the Payment by Results (PBR) tranche, a high-level dialogue and new cross-FCDO and cross-Whitehall coordination mechanisms. / The programme has been implemented against a challenging backdrop that included the response to the COVID-19 pandemic and its aftermath and the creation of FCDO as a new department. Against this backdrop, it is easy to lose sight of the fact that a step-change in the WHO flexible funding agenda has been achieved. / This programme has played an important anchoring role in progress in the achievement of WHO’s flexible funding agenda. Further, it is also clear that WHO has worked to deploy its increased flexible funding in a strategic manner that supports priority objectives, such as transforming the technical capacity of WHO Country Offices. While progress has been slower than needed, a strong platform is now in place which promises accelerated progress in the 2024/25 biennium and beyond that into the fourteenth General Programme of Work (GPW14). / Overall summary: / The primary emphasis of the independent evaluation of the WHO CVC programme is learning that can inform the design, management, oversight and delivery of future FCDO engagement and funding of the WHO. It supports learning around specific aspects of WHO transformation and delivery over the period of the programme. This learning will be reflected in the next round of programming to WHO and future FCDO engagement and funding of the WHO. / The evaluation was carried out through a desk-based review, literature review and key informant interviews. While the validity was strengthened through triangulation, the compressed timeline and lack of country visits has implications for the overall validity of the report.

Evaluation Report Title: FCDO’s World Health Organization (WHO) Core Voluntary Contribution (CVC) Programme

Recommendations: FCDO	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
Strengthening WHO Reform, Delivery and Accountability
Recommendation 1: Flexibility. Continue to provide the large majority of the UK’s support to WHO flexibly into the future to support ongoing reform and delivery.	Accepted	FCDO noted the evaluation’s recommendation that the UK continues to provide flexible funding to WHO to support ongoing reform and delivery. Reform of WHO is a top priority for the UK. Flexible funding is critical to delivering essential reform that will make WHO more effective. A strong WHO that is more flexible, fit for purpose, effective and able to respond with agility to global health priorities, including current challenges and future threats is critical. The UK has to date been a strong supporter of fully flexible funding to drive efficiency and effectiveness. Development of further programming will continue to focus on supporting WHO’s reform journey.
Recommendation 2: Reporting. Encourage WHO to integrate Core Voluntary Contributions Account (CVCA) reporting into wider flexible funds reporting approach.	Accepted	In our latest annual assessment of our WHO core funding programme (2020-24) we have recommended WHO share a flexible funding report, that explains how the organisation has prioritised and allocated all flexible funding (assessed contributions, voluntary contributions and PSC costs) from all donors. This should also include how regions have prioritised their allocations, as well as how HQ have allocated across the regions. Ensuring clarity of WHO’s processes for prioritising is critical for the UK and other Member States to understand given the move to increasing membership fees.
Recommendation 3: Results. Push WHO to develop clear metrics for success in funding and reform, particularly in terms of country performance. These should be integrated into the GPW14 results framework, which currently does not cover this area.	Accepted	WHO is taking important steps towards improved results-based management. FCDO is engaging with the WHO on its indicators for GPW14, to ensure a stronger focus on output and outcome indicators – anticipated to be completed by end of 2024.
Recommendation 4: Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders. This could be part of a wider major funder engagement approach that includes some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return.	Accepted	FCDO are exploring options to establish a mechanism which brings together flexible funders or those focused on reform in WHO. Collective oversight through an agreed route/mechanism will be used to hold WHO to account particularly on flexible funds but not limited to this.
Recommendation 5: Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round.	Accepted	See management response at 2 & 4 above.
Strengthening UK Influence, Oversight and Assurance
Recommendation 6: Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities.	Accepted	In the development of further programming, we will reinstate the logframe with multi-year reform targets for monitoring purposes.
Recommendation 7: Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns.	Accepted	We will use strengthened levers to hold WHO to account for UK funds.
Recommendation 8: Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted funding to UK high priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement.	Rejected	We have considered the benefits of earmarked/holdback funding in the context of the importance UK places on reform underpinning all UK priority thematic areas. It is likely to require a significant resource to administer this earmarked funding. Additionally, the capacity within the FCDO team who hold the institutional relationship with WHO and current overarching contractual agreement with WHO would require annual results reporting on each individual grant. This would contribute to the reporting burden on WHO undermining the principle of flexible funding reducing reporting burden and freeing up WHO staff time.
Recommendation 9: FCDO/WHO Dialogue. Widen and regularise Strategic Dialogue on an annual basis and spanning the full range of institutional reform, policy priorities and opportunities for review of the targeted funding. / .	Accepted	We will continue to use levers adopted in the previous WHO core funding programme, including technical and annual strategic dialogues with WHO.
Recommendation 10: Coordination. Reinvigorate internal FCDO and HMG coordination mechanism to ensure the establishment of clear policy priorities, a clear management strategy, and the engagement of the FCDO country network.	Accepted	An FCDO wide portfolio board is being explored to bring a more coordinated approach to engagement with WHO, encompassing regional health leads, all SROs of bilateral funding to WHO, the WHO hub and the WHO team for the UK mission.
Recommendation 11: Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders	Accepted	The WHO hub has grown in size and capacity since the WHO Core funding programme began in 2020. We will continue to explore opportunities to dialogue with likeminded and potential flexible donors.
Recommendation 12: FCDO roles. Ensure clearer delineation and understanding of roles between WHO Hub, UKMIS Geneva and other relevant HMG focal points.	Accepted	Agreed. We will continue to liaise closely with both DHSC and UKMIS in advance of further programme to ensure clarity of roles and to foster a One HMG approach on our engagements.
Recommendation 13: Monitoring, Evaluation and Learning (MEL). Consider retaining an external MEL provider to monitor progress (both financial and performance metrics) on an ongoing basis as part of future programme to support oversight, accountability and dialogue.	Accepted	We will explore a range of options to respond to the monitoring, evaluation and learning in relation to future programming.