Evaluation of FCDO’s World Health Organisation (WHO) Core Voluntary Contribution (CVC) Programme
Final Report, July 2024

Framework ECM No: ecm_4755 /// Round Robin/Direct Award ITT: project_10213

Submitted by DAI Global UK in partnership with Halcyon Consulting Limited

#### Authors
Anna Hazelwood, Carole Presern, James Droop, Judie Mbogua and Meghan Bishop

#### Disclaimer
The views expressed in this document do not necessarily represent the Foreign, Commonwealth & Development Office’s (FCDO) views or policies, or those of DAI.

# Acronyms

3YS	Three-Year Strategy
AC	Assessed Contributions
ADG	Assistant Director General
AFRO	Africa Regional Office
AMR	Antimicrobial resistance
ARG	Action for Results Group
COP26	26th Conference of the Parties
CPCP	Core Predictable Country Presence
CVC	Core Voluntary Contribution
CVCA	Core Voluntary Contribution Account
DG	Director General
DHSC	Department of Health and Social Care
DoA	Delegation of Authority
DRC	Democratic Republic of the Congo
EMRO	Eastern Mediterranean Regional Office
EQ	Evaluation Question
EQuALS	Evaluation Quality Assurance and Learning Service
EURO	European Regional Office
FCDO	Foreign Commonwealth and Development Office
FENSA	Framework for Engagement with Non-State Actors
GAP	Global Action Plan
GEMFA	Global Evaluation Monitoring Framework Agreement
GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria
GPW	General Programme of Work
GPW13	Thirteenth General Programme of Work
GPW14	Fourteenth General Programme of Work
HMG	His Majesty’s Government
HQ	Headquarters
HR	Human Resources
HRP	Human Reproduction Programme
HSS	Health Systems Strengthening
ICAI	Independent Commission for Aid Impact
IOAC	Independent Oversight and Advisory Committee
IPHA	Intermediate Public Health Alert
IPSN	International Pathogen Surveillance Network
KII	Key Informant Interview
MEL	Monitoring Evaluation and Learning
MNCH	Maternal, Newborn and Child Health
MOPAN	Multilateral Organisation Performance Assessment Network
MoU	Memorandum of Understanding
MRP	Management Response Plan
NGO	Non-Governmental Organisation
NPO	National Professional Officers
ODA	Official Development Assistance
PASM	Preventing and Addressing Sexual Misconduct
PBAC	Programme, Budget & Administration Committee
PBR	Payment by Results
PMNCH	Partnership for Maternal, Newborn and Child Health
PRS	Prevention of and Response to Sexual misconduct
PRSEAH	Preventing and Responding to Sexual Exploitation, Abuse and Harassment
PSC	Programme Support Costs
RD	Regional Director
RMNCH	Reproductive, Maternal, Newborn, and Child Health
SAGO	Scientific Advisory Group on Origins of Novel Pathogens
SDG	Sustainable Development Goal
SEA	Sexual Exploitation and Abuse
SEARO	South-East Asia Region Office
SIP	Secretariat Implementation Plan
SRH	Sexual and Reproductive Health
SRO	Senior Responsible Owner
TA	Technical Assistance
TDR	Special Programme for Research and Training in Tropical Diseases Research
ToR	Terms of Reference
UHC	Universal Health Coverage
UHPR	Universal Health and Preparedness Review
UK	United Kingdom
UKMIS	UK Mission
UN	United Nations
UNAIDS	Joint United Nations Programme on HIV/AIDS
UNDS	United Nations Development System
UNFPA	United Nations Population Fund
VC	Voluntary Contributions
WASH	Water, Sanitation and Hygiene
WHA	World Health Assembly
WHO	World Health Organisation
WPRO	Western Pacific Regional Office
WR	WHO Representative

# 1. Executive Summary
In 2020, the Foreign Commonwealth and Development Office (FCDO) approved £340m of funding to the World Health Organisation (WHO’s) Core Voluntary Contributions (CVC) account over four years. CVCs provide a means for WHO member states and other donors to provide additional flexible funding over and above their core Assessed Contributions (countries’ membership dues). CVCs are distinct from the other voluntary contributions that make up the majority of WHO’s funding base in that they can be used flexibly rather than being earmarked for specific diseases, health issues or geographies. In December 2023, FCDO appointed DAI Global UK to evaluate its CVC funding. Evidence-gathering took place from mid-December 2023 to end-March 2024 and the evaluation was finalised in July 2024.
###### Context and background
The WHO stands at the heart of the international health system with a unique role as the United Nations (UN) lead agency for global health. In one way or another, all entities active in global health depend on functions delivered by WHO. It creates and sustains a wide range of health-related global public goods including norms, standards and guidelines around disease management and health priorities, shaping the health research agenda, providing policy and regulatory support around access to essential health products, and monitoring and assessing health trends. It gives technical assistance to countries to advance health and provides services and operational support in health emergencies or as a last resort – as evidenced by its role during the COVID-19 pandemic.
WHO's capability has been compromised by operational and organisational shortcomings. One key factor is its complex and fragmented funding base, which has become progressively dominated by donor funding earmarked for specific disease or geographic priorities (known as Specified Voluntary Contributions). This trend has negative consequences for WHO: it increases its reporting burden, creates institutional inefficiencies and skews organisational priorities – which in turn undermines governance mechanisms and strategic coherence.
In 2017, WHO Director-General (DG) Tedros launched a transformation process. His central ask of donors was to provide more multi-year, flexible funding. This would be achieved in two main ways. The first was collective agreement to increase Assessed Contributions (ACs): fully flexible core funding that is contributed by every Member State based on economic size. The second was to increase funding through Core Voluntary Contributions (CVCs) – a mechanism that allows Member States and other donors to provide flexible, unallocated funding over and above the level of ACs.
The United Kingdom (UK) government has been a longstanding leader in advancing global health. As such, a high-performing, adequately funded and effective WHO is critical to the UK government’s global health priorities, as well as wider security, development and poverty reduction aims. The UK has therefore been a consistent major donor to the WHO, as well as a champion of institutional reform.
In 2020 the UK took the decision to significantly increase the level of its flexible funding to the WHO via a WHO CVC ‘programme’ that had the objective of enhancing WHO performance and global health leadership. A budget of £340 million over four years was approved. The budget represented a large increase over the UK’s existing level of CVC funding and was structured into a 70% core element and a 30% payment by results (PBR) component, conditional on the delivery of five key policy asks agreed upon annually.
The FCDO’s WHO CVC programme is the focus of this evaluation. This should not be confused with the WHO’s CVC Account (CVCA) which is the wider multi-donor mechanism through which WHO receives CVCs, including FCDO WHO CVC programme funds. Designed and approved during the acute phase of the COVID-19 pandemic, the programme’s objectives were to enable WHO, supported through further reform, to:
- Coordinate a more effective and integrated global approach to health security, ensuring better pandemic preparedness and emergency response;
- Play a stronger coordination and convening role in building back resilient health systems worldwide with better health for all; and
- Provide the highest-quality technical advice to its Member States, tailored to their different contexts.
###### Purpose of the evaluation
The primary purpose of this evaluation is to generate learnings to inform the design, management, oversight and delivery of future FCDO engagement and funding of the WHO, as well as specific aspects of WHO transformation and delivery. Alongside other sources, FCDO will use the evaluation, to shape future WHO support through the course of 2024. A 2022 evaluability assessment found the programme to be evaluable. It stated that there was sufficient existing data (and further qualitative and quantitative data could be gathered) to make a robust evaluation. The Terms of Reference (ToR) were reviewed and endorsed by FCDO’s Evaluation Quality Assurance and Learning Service (EQuALS). They define a learning approach with four objectives:
- To explore the relative importance of WHO CVC programme funding and other UK inputs, and the way these synergies have affected or limited change;
- To explore the extent to which the flexibility of CVC funding has contributed to the delivery of the reform agenda and WHO’s thirteenth General Programme of Work (GPW13), and how the WHO CVC programme and PBR mechanism has affected the political economy of decision-making at WHO;
- A short analysis of how FCDO has approached evaluation of the current programme and issued recommendations on how to incorporate evaluation into the next programme;
- To support the development of specific pieces of analysis to enhance FCDO’s understanding of priority areas and how the UK might address these better in future.
The primary target audience for this learning evaluation is His Majesty’s Government (HMG) stakeholders (the FCDO Global Health Directorate, the UK Mission (UKMIS) in Geneva, the Department for Health and Social Care (DHSC) and WHO stakeholders as well as other WHO donors and Member States who provide, or are considering providing, CVC funding.
###### Approach, design and methodology
The evaluation team used a utilisation-focused and theory-based mixed-methods approach, with emphasis on qualitative exploration complemented by quantitative descriptive analysis of available and relevant secondary data. The timeline had to be rapid and condensed to align with FCDO’s learning utilisation objectives. Despite these constraints, the team reviewed over 110 documents and articles, and conducted 39 Key Informant Interviews (KIIs). Given the learning nature of this evaluation, the design relies primarily on descriptive analysis of qualitative data. It could not (and does not seek to) establish a direct causal relationship between UK funding and the delivery of the WHO reform agenda but seeks to understand the plausible contribution of the programme.
Findings
The evaluation found that the design of the overall programme was fully aligned with the objective of strengthening WHO institutional performance. Consolidating funding into a single, large-scale funding envelope to the CVC account was an evidence-based, principled and forward-looking approach by the UK. It responded to the needs and requests of the WHO for greater flexible funding to better advance global health goals.
There was clear recognition by FCDO of the challenges associated with the transition to a different funding model. In broad terms, the new approach traded off greater flexibility for WHO to pursue reform and delivery against reduced direct UK control and accountability over the use of its funding. A range of mechanisms were put in place to mitigate these risks and to manage the transition. These included the PBR tranche, a high-level dialogue and new cross-FCDO and cross-Whitehall coordination mechanisms.
The programme has been implemented against a challenging backdrop that included dealing with the COVID-19 pandemic and its aftermath and the creation of FCDO as a new department. Against this backdrop, it is easy to lose sight of the fact that a step-change in the WHO flexible funding agenda has been achieved. This programme has played an important anchoring role in that progress. Further, it is also clear that WHO has worked to deploy its increased flexible funding in a strategic manner that supports priority objectives, such as transforming the technical capacity of WHO Country Offices. That said, progress has been slower than needed. But a strong platform is now in place which promises accelerated progress in the 2024/25 biennium and beyond that into the fourteenth General Programme of Work (GPW14).
Beyond these high-level findings, the evaluation identified a set of further learnings that included:
- The costs of the PBR mechanism exceeded its benefits. It represents too small a share of total WHO funding to shift behaviour and it significantly constrains WHO’s budget and planning flexibility.
- The programme’s five annual ‘key asks’ were too narrow to accommodate the full range of UK priorities.
- The transition away from direct UK funding to individual thematic areas was abrupt and complicated UK influence and engagement in some cases.
- The UK remains an outlier in terms of how flexibly it funds the WHO. Other donors have stepped up but not as significantly as hoped.
- WHO’s reporting arrangements and systems, and accountability to flexible funders fell short. Reporting in terms of the use of CVC funds alone was misleading. The metrics for capturing progress on organisational reform were inadequate.

Findings are summarised below. Section 4 of the report goes systematically through the EQ clusters setting out more detail on findings, recommendations and the evidence underpinning them.
###### Table 1. Summary of Findings
Did the UK deliver inputs coherently?
EQ 1 / EQ 2 / EQ 3	Programme design was coherent. It explicitly recognized the fundamental trade-off between greater flexibility for WHO against reduced direct UK control around funding. A number of measures were put in place to manage this trade-off, most importantly the structuring into a core element (70%) and a PBR tranche (30%) conditional on delivery of five annual policy asks.
Did the programme design respond to WHO needs?
EQ 4 / EQ 10	The programme is an evidence-based, principled and forward-looking approach that ensures that the composition of UK funding to WHO is supportive of WHO reform and delivery
Did the programme support WHO reform and delivery?
EQ 5 / EQ 7	There is good evidence that CVC funds have been deployed as part of a clear strategic approach to use flexible funding for organisational reform objectives, principally enhancing country office technical capacity.
Did the PBR component contribute towards the overall programme goals?
EQ 6 / EQ 8	Evaluation found that PBR mechanism costs exceeded its benefits. Further, limiting to just five asks was too narrow for the full range of UK priorities (particularly during Covid-19).
Did the programme contribute to the wider sustainable funding agenda?
EQ 9	The UK is a significant outlier compared to other donors in the way it funds the WHO. / Following stagnation in the last decade, recent years have seen a significant rise in CVC funding and a landmark agreement to increase Assessed Contributions. The programme has contributed.
How did the programme impact on UK influence in WHO?
EQ 11	The programme may have enhanced UK influence with WHO leadership although other levers, such as level of political engagement, were more important. Transition away from direct UK funding to individual thematic areas was abrupt and disrupted UK engagement in some cases. Capacity fluctuations within FCDO were an additional complication
What was learned from the results approach?
EQ 12 EQ 13	WHO reporting was inadequate for CVC funders to assess performance effectively. GPW13 results were too high-level. CVC reporting was too narrow. Proposed GPW14 results framework evolution promises improvement. FCDO reporting of this programme focused on the five key asks. These were not linked to progress on WHO reform and performance

###### Recommendations
The UK approach to providing such a significant share of its WHO support through flexible CVC funding should be applauded and maintained. However, the evaluation draws from review learnings to propose a number of recommendations for FCDO to consider. These aim to support a better balance between supporting WHO reform, delivery and results and ensuring UK influence, oversight and assurance. These 13 recommendations are summarised in Table 2 below and explored in more detail in the report. Annex 6 includes a Theory of Change for a potential future programme that reflects these recommendations.
###### Table 2. Evaluation Recommendations to FCDO
Recommendations
Strengthening WHO Reform, Delivery and Accountability	Flexibility. Continue to provide the large majority of the UK’s support to WHO flexibly into the future to support ongoing reform and delivery. / Reporting. Encourage WHO to integrate Core Voluntary Contributions Account (CVCA) reporting into a wider flexible funds reporting approach. / Results. Push WHO to develop clear metrics for success in funding and reform, particularly in terms of country performance. These should be integrated into the GPW14 results framework, which currently does not cover this area. / Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders. This could be part of a wider major funder engagement approach that includes some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return. / Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round.
Strengthening UK Influence, Oversight and Assurance	Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. / Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. / Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted[i] funding to UK high priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement. / FCDO/WHO Dialogue. Widen and regularise Strategic Dialogue on an annual basis and spanning the full range of institutional reform, policy priorities and opportunities for review[ii] of the targeted funding. / Coordination. Reinvigorate internal FCDO and HMG coordination mechanism to ensure the establishment of clear policy priorities, a clear management strategy, and the engagement of the FCDO country network. / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders. / FCDO roles. Ensure clearer delineation and understanding of roles between WHO Hub, UKMIS Geneva and other relevant HMG focal points. / Monitoring, Evaluation and Learning (MEL). Consider retaining an external MEL provider to monitor progress (both financial and performance metrics) on an ongoing basis as part of future programme to support oversight, accountability and dialogue.

[i] This is not a recommendation for tightly earmarked VCs, it would be more targeted, multi-year funding in support of WHO work in priority areas. Precise modalities would need to be defined.
[ii] This review would be against whatever regular reporting the Department/Unit would have to do in its normal systems/procedures. The idea would not be to add to WHO’s reporting burden
# 2. Introduction
## Structure of the report
This section (section 2) sets out the global health backdrop for the Foreign Commonwealth and Development Office’s (FCDO) funding to the World Health Organisation (WHO): including WHO’s role and mandate, FCDO’s health priorities, as well as the rationale, design and theory of change for the CVC programme. It also describes the purpose and scope of this evaluation. The following section (section 3) lays out the questions addressed by the evaluation and methods adopted. Section 4 presents responses to the 13 Evaluation Questions (EQs), drawing on both document review and informant interviews. EQs are grouped into thematic categories for ease of reference and understanding. Each EQ response identifies recommendations that are numbered and presented in tables in the later Recommendations section and the Executive Summary. Section 5 lays out the key findings and lessons learned. Section 6 makes a set of recommendations for FCDO to consider in its future engagement with the WHO. The conclusion (section 7) summarises findings and recommendations. The main report is complemented by a set of annexes. This includes the four Discrete Learning Analyses (on GPW13, the WHO sustainable financing agenda, WHO staff trends and Preventing & Responding to Sexual Exploitation, Abuse and Harassment (PRSEAH), which provide context and insight to the evaluation and are included in Annex 1. Also included as annexes are additional information on the evaluation methods and approach (including Key Informant Interviews (KIIs) undertaken, KII guides, bibliography, the Evaluation Framework and the Evaluation Terms of Reference).
## Background and context
FCDO has appointed DAI Global UK to deliver an evaluation of its WHO Core Voluntary Contribution (CVC) programme. The primary emphasis is learning that can inform future FCDO engagement with the WHO, as well as informing the wider dialogue between WHO and its donors around funding. This section sets out the background to the evaluation and draws from initial discussions with selected stakeholders and an initial review of literature, including the mapping exercise undertaken in the Inception Phase.
The United Kingdom (UK) government has been a longstanding leader in advancing global health. It recognises that, for individuals and societies, good health is an intrinsic good in and of itself as well as acting as a critical enabler of economic development and stability. The UK also has a strong comparative advantage in global health, as a significant donor of multilateral and bilateral efforts, as a global leader in health research, innovation and industry and as a centre of expertise within government, academia, the private sector and civil society. This was illustrated through the UK’s leading role in the international response to COVID-19, shaping multilateral responses and driving global innovation and access to COVID-19 vaccinations and treatments.
Global health has a prominent place in the UK government's international priorities. The 2021 Integrated Review of Security, Defence, Development and Foreign Policy committed to strengthening global health resilience and security. The 2022 UK Government Strategy for International Development and the November 2023 White Paper on International Development both flag strengthening and reforming the international health system as a priority – expanding access to healthcare for all and building stronger health systems.
The WHO stands at the heart of the international health system, with a unique role as the lead United Nations (UN) agency for global health. WHO provides leadership and coordination on global health, including health emergencies and disease outbreaks as shown by its leadership role in the COVID-19 pandemic. It creates and sustains a wide range of global public goods for health, including norms, standards and guidelines around disease management and health priorities, shaping the health research agenda, providing policy and regulatory support around access to essential health products, and monitoring and assessing health trends. It provides technical assistance to countries to advance health and services and operational support as a last resort or in emergencies.
A high-performing and effective WHO is therefore a critical enabler for all other global health agencies, partnerships and stakeholders, as well as for national governments in their efforts to strengthen health policies, systems and services. By extension, the WHO is also central to the UK government’s global health priorities, as well as wider security, development and poverty reduction aims. The strategic priorities of WHO are closely aligned with the global health priorities of the UK. The Thirteenth General Programme of Work (GPW13) (approved by all 194 Member States, including the UK) 2019-2023, (now extended to 2025) aims to:
- Protect 1 billion more people from health emergencies
- Provide 1 billion more people with access to universal health coverage; and
- Enable 1 billion more people to live healthier lives.
However, there is consensus that the achievement of WHO goals is compromised by shortcomings in operational and organisational performance. Some of these are within WHO’s control, such as culture and internal ways of working. Others stem from the challenges, experienced by all multilateral organisations, in securing consensus among multiple (in WHO’s case, 194) Member States and other funders. In the case of WHO, the multiplicity of objectives that its funders ask of it are mirrored in an extremely fragmented landscape of funding which significantly compromises its coherence as an organisation, its ability to fund and execute its programme of work, capacity to recruit and retain staff on long-term contracts and to be nimble and responsive in the face of new priorities or emergencies. It also significantly increases the burden of negotiating and reporting to donors. The share of the WHO budget funded by Member States’ Assessed Contributions (ACs) – fully flexible core funds – has progressively fallen to less than 20% of the total. The remainder is funded by Voluntary Contributions (VCs). VCs constitute a very wide range of funding mechanisms, ranging in flexibility from CVCs, which are fully flexible (and which include the funding provided by the UK under this programme), to Specified VCs (of which there are several thousand across the organisation). Specified VCs account for almost 90% of all VCs and are frequently tightly earmarked to specific programmatic activities and/or geographic locations. Additional detail on WHO funding can be found in Section 6B and Annex 1.
The WHO recognises the need for reform and Dr Tedros launched a transformation process following his appointment as Director General (DG) in 2017. Key priorities included strengthening of financial, Human Resources (HR) and administrative management, strengthened leadership and governance and greater effectiveness and results orientation at country level. A new Health Emergencies Programme was also established in 2016 in response to the lessons from the 2014 Ebola epidemic.
The UK has been a strong supporter of the transformation agenda and has long recognised the challenges of earmarked funding. DHSC, which is the lead UK government department in relations with the WHO, is responsible for payment of the UK’s AC which currently stands at around US$20 million per year. A 2016-20 CVC programme provided £83m over 4 years in flexible funding with the aim of supporting the WHO transformation process and increasing the organisation’s ability to deploy funds in support of General Programme of Work (GPW) priorities. The 2016-20 programme was also seen as a means to enhance the impact of UK’s earmarked funding programmes to the WHO at global, regional and country levels. It is estimated that there were 20-30 active earmarked funding programmes over this period. By contributing to strengthening the organisational performance of WHO as a whole, the CVC programme would foster better delivery of the earmarked programming.
While transformation certainly progressed up to 2020, the constraints associated with the funding structure steadily increased in prominence. To continue and complete reform efforts, WHO asked all donors to provide multiyear, flexible funding. This would be achieved in two main ways. The first was collective agreement to increase ACs and the second was an increase in funding in the form of CVCs. The combination of lessons learned from the 2016-20 programme, together with the significant shift in focus on WHO performance and leadership against the backdrop of the COVID-19 pandemic, underpinned an FCDO decision to increase its CVC funding (in the form of this WHO CVC programme which received ministerial approval in March 2021).
Maintaining the status quo of a relatively small CVC programme with multiple earmarked programmes was rejected because it would not significantly shift the enabling conditions for WHO reform. Instead, the decision was made to signal to partners that the UK was prepared to ‘walk the talk’ and bundle its funding to WHO into a unified funding framework. The £340m budget over four years was equivalent to the previous level of CVC funding and the budgets of several earmarked programmes that were consolidated into it, together with a 30% increase. In total, it was estimated that, once combined with all other UK funding to the WHO (including for example, the £17m per year funded by Department of Health and Social Care [DHSC] as an AC) the overall UK burden-share would be around 12% and the UK would be the third largest funder.
Annual funding was structured into a core element (70%) and a PBR tranche (30%) conditional on the delivery of five key policy asks agreed on an annual basis. Reflecting the evidence on PBR in multilateral settings, these ‘key asks’ were aligned with WHO’s own priorities (i.e. GPW13) and intended to focus on long-term strategic reforms rather than short-term operational actions. The rationale for the PBR tranche was to increase WHO focus on UK priorities, strengthen incentives to deliver the GPW and strengthen accountability for performance. Alongside funding, the FCDO programme also envisaged significant engagement from UK government technical and policy specialists in dialogue around reform and delivery. This included ongoing technical advisory engagement in thematic areas previously supported through earmarked UK programmatic funding. Additional detail on the programme design, including the PBR component, is in Sections 6A and 6D.
The overall objectives of the WHO CVC programme as outlined in the FCDO Business Case, align with the priorities of GPW13. These objectives are to enable WHO, supported through further reform, to:
- Coordinate a more effective and integrated global approach to health security, ensuring both better pandemic preparedness and emergency response;
- Play a stronger coordination and convening role to build back resilient health systems world-wide with better health for all; and
- Provide the highest-quality technical advice to its Member States, tailored to their different contexts.
## Theory of change for programme
During the evaluation’s inception phase, in line with the evaluability assessment recommendations, the team revised the causal pathways in the Theory of Change in the FCDO Business Case to clarify scope.15 Revisions were made at input and output level, particularly on the importance of building support among Member States around reform priorities and how UK inputs aim to ensure synergies between UK health priorities and WHO activities.
###### Figure 1. Theory of Change (ToC) adapted from Business Case ToC for use in the evaluation
###### (Larger scale version available at Annex 6)

The revised Theory of Change (Annex 6) posits that UK inputs (expertise and influence, CVC funding and Monitoring Evaluation and Learning [MEL]) will interact to drive WHO delivery and WHO transformation, which are mutually reinforcing. Inputs also ensure that UK health priorities are reflected in WHO’s activities, while serving as a model to influence other donors to increase the level and flexibility of their funding. As WHO reforms are implemented and delivery improves, WHO will more effectively progress towards the outcomes and impacts defined in the GPW. This revised theory of change defines the scope for this theory-based evaluation.
## Purpose and scope of the evaluation
The four year FCDO ‘WHO CVC programme’ is the focus of this evaluation. This should not be confused with the WHO’s CVC Account (CVCA), which is the wider multi-donor mechanism through which WHO receives CVCs, including the FCDO ‘WHO CVC programme’ funds.
The primary emphasis of the independent evaluation of the WHO CVC programme is to generate learning to inform the design, management, oversight and delivery of future FCDO engagement and funding of the WHO. Learning around WHO transformation and delivery over the period of the programme is also part of this work. Aspects of the approach such as the PBR element and internal programme management within FCDO post-merger, will provide learning for UK investment in other UN agencies and multilaterals. This learning focus has implications both for the timeline of the evaluation and selection of methods, is clearly set out in the Terms of Reference (ToR) and was confirmed in conversations with FCDO during inception.
An evaluability assessment was conducted in 2022 to provide an assessment of the feasibility and proportionality of likely methods needed to evaluate the WHO CVC programme effectively. The assessment found that the WHO CVC programme is evaluable; there is sufficient existing data and further qualitative and quantitative data that can be gathered to make a robust evaluation of the WHO CVC programme as it ends in March 2024. The ToR (which were reviewed and endorsed by EQuALS) drew from the evaluability assessment to define a learning approach with four objectives:
1. To explore the relative importance of WHO CVC programme funding and other UK inputs, and how these synergies affected or limited change (learning review of synergies between CVC funding and other UK inputs);
2. To explore the extent to which the flexibility of CVC funding has contributed to the delivery of the reform agenda and GPW13, and how the WHO CVC programme and Payment by Results (PBR) mechanism has affected the political economy of decision making at WHO (learning about CVC as a funding mechanism);
3. To conduct a short analysis of how the FCDO has approached the evaluation of the current WHO CVC programme and issue recommendations on how best to incorporate evaluation effectively into the next programme (Learning about evaluation); and
4. To support the development of specific pieces of analysis to enhance FCDO’s understanding of priority areas and how the UK might address these better in future (Discrete Learning Analyses).
The scope of the evaluation was further defined by the 13 Evaluation Questions (EQs) set out in the ToR. These EQs focus on the links and relationships between UK inputs (in the form of funding, programme modalities, expertise and influencing) and the way that those inputs support WHO operational and institutional capability (both directly and through other donors) to deliver outputs. In line with these EQs, and with discussions during the Inception Phase with FCDO, the evaluation focused on these steps in the Theory of Change and did not seek to follow the causality through to outcomes and impact at country and population-level.
The focus of the evaluation reduced the potential to explore more fully dimensions such as equity, poverty, gender equality and inclusion. These dimensions are reflected principally in the outcome and impact stages of the programme’s theory of change (how WHO activities ultimately affect conditions within countries and populations). However, this evaluation focuses on questions of operational and institutional effectiveness and funding modalities at the input and output stages of the theory of change. Nevertheless, the team sought to ensure gender-responsiveness and integrate considerations of equity and human rights, for example in the proposed Discrete Learning Analyses, which included an assessment of staffing trends, including analysis by gender, and reviewing the Preventing & Responding to Sexual Exploitation, Abuse & Harassment (PRSEAH) agenda, which has important rights dimensions. This approach was discussed and agreed with FCDO. Gender composition of the team and of key informants interviewed was also tracked.
The primary target audiences for this learning evaluation are His Majesty’s Government (HMG) stakeholders (the FCDO Global Health Directorate, UK Mission [UKMIS] Geneva, DHSC) and WHO stakeholders. The target audience also includes other WHO donors and Member States who provide, or may be considering providing, CVC funding. Presentations were held with FCDO and WHO stakeholders in London and Geneva to generate additional feedback and disseminate findings more widely. A presentation to selected donors to WHO is also being scheduled. FCDO is using the evaluation, alongside other sources, to inform and shape the design of future support to the WHO. In line with FCDO policy, the evaluation will also be published and made publicly available.
# 3. Evaluation Approach
## Evaluation overview
The primary emphasis of the independent evaluation of the WHO CVC programme is learning that can inform the design, management, oversight and delivery of future FCDO engagement and funding of the WHO, as well as learning around specific aspects of WHO transformation and delivery over the period of the programme. The evaluation followed a utilisation-focused and theory-based mixed-methods design, comprised of qualitative data collection through Key Informant Interviews (KIIs), complemented by quantitative descriptive analysis of available and relevant secondary data. This report is the central deliverable of the evaluation but will also be accompanied by complementary communication products, including a slide deck for presentation.
## Evaluation questions
The evaluation was guided by a set of evaluation questions (EQs) that were derived from the original ToR and expanded during the inception phase, based on the Theory of Change and discussions with FCDO. The EQs are listed in Table 3 below, along with EQ clusters, as applicable. The full evaluation framework, with expanded evaluation questions, data sources and analytical methods used for each question, can be found in Annex 5.
###### Table 3. Evaluation Questions
EQ Clusters	Questions
EQs
A. Did the UK deliver inputs coherently?	EQ1. How coherently have the different elements of the programme worked together?
	EQ2. What are the synergies between the different UK inputs (flexible funding, PBR, MEL, and expertise and influencing)?
	EQ3. To what extent has FCDO optimised the synergies between UK inputs?
B. Did the programme design respond to WHO needs?	EQ4. How well did the design of the FCDO’s CVC programme (including the PBR element) respond to WHO’s reform agenda?
	EQ10. How well did the design of FCDO’s WHO CVC programme (including the PBR element) respond to WHO funding issues?
C. Did the programme support WHO reform and delivery?	EQ5. To what extent has the WHO CVC programme funding facilitated the more effective delivery of the WHO reform agenda?
	EQ7. To what extent has WHO CVC programme funding facilitated the more effective delivery of the GPW13 by WHO (global, regional, country)?
D. Did the PBR component contribute towards the overall programme goals?	EQ6. What role has the PBR component had in incentivising organisational change?
	EQ8. What might the WHO have done differently, had the UK’s CVC funding been 100% flexible?
E. Did the programme contribute to the wider sustainable funding agenda?	EQ9. How well has the UK approach to funding the WHO aligned with other donors funding practices and has it led to an improved funding environment for WHO?
F. How did the programme impact on UK influence in WHO?	EQ11. To what extent has CVC funding to the WHO changed the UK’s influence vis-à-vis WHO and how?
G. What was learned from the results approach?	EQ12. To what extent has FCDO used the information gathered through the WHO Results Framework?
	EQ13. What are the lessons learnt from the approach to MEL?
Discrete learning questions
H. What has WHO’s progress been on selected priority areas?	EQ14. To what extent have the organisational changes [supported through CVC funding] contributed to the sustained delivery of WHO’s GPW Triple Billion programme, in particular the improved access to quality health services and the rapid detection of and response to health emergencies?
	EQ15. How has the WHO sustainable financing agenda advanced since 2020?
	EQ16. Since 2020, what have been the key trends in WHO’s staffing, including contractor-to-staff ratio, contract length, technical gaps, gender balance and country representative gaps?
	EQ17. What has been achieved in strengthening critical systems and processes, such as Preventing and Responding to Sexual Exploitation, Abuse and Harassment (PRSEAH), since 2020?

## Methods
The key components of our approach entailed a desk review, academic literature review and KIIs. In this section, we describe these methods, their purposes and outputs.
###### Desk review
The purpose of the desk review was to consider existing evidence on how the CVC funding mechanism works and its history to inform the design of KII guides. Key foundational documents shared by FCDO at the start of the evaluation were reviewed, as well as additional documents identified through a search of the WHO website and recommended during the KIIs. In total, 110 documents were reviewed of which 70 were found to be relevant. They are set out in the Bibliography in Annex 2.
###### Literature review
The purpose of the literature review was to look at models of flexible funding to glean insights into how these models have responded to questions like those posed in this evaluation. Using key search terms, a search of various academic research databases was conducted to identify relevant literature (see Annex 7 for the full list of search terms). In total, 358 articles were identified, of which 12 were found to be relevant following a scan of titles and abstracts. A search of the bibliographies of identified articles produced a further seven articles. One other article was identified through the initial inception phase document review and another through an internet search. An additional article was recommended during the KIIs. In total, 22 articles were reviewed.
###### Key informant interviews (KIIs)
KIIs were not envisaged as part of the original ToR but were identified as a necessary complementary source of evidence in the Inception Phase. Conducted between 14 February 2024 and 25 March 2024, the purpose of the KIIs was to explore interviewees’ thoughts, opinions and experiences regarding the perceived effectiveness of the CVC funding mechanism, in line with the EQs. Semi-structured interview guides with open-ended questions were developed based on the EQs and tailored to the relevant experience of different informant groups (see Annex 9). Appropriate probes were included for each EQ and were used when dialogue was not forthcoming and to guide the discussion. No formal pre-testing of KII guides was undertaken due to time constraints. However, the first interviews scheduled were with people most familiar with the programme and evaluation (e.g. the FCDO hub), which allowed the team to review and adjust the guides in advance of the rest of the interviews.
Interviews were largely conducted remotely, though 12 of the interviews with WHO informants were conducted in person in Geneva. Interviews were mainly conducted by the Team Leader and WHO Reform Specialist for consistency, with a note-taker in attendance.
###### KII sampling strategy Guided by FCDO, informants were purposively selected and included:
- Donors/Member States: individuals involved in decision-making around funding of the WHO (particularly flexible funders), who would be able to give context to funding decisions made by donors and member states.
- FCDO country: individuals who are working in FCDO's diplomatic and development network worldwide who would be able to speak to WHO performance at the country level.
- FCDO technical: individuals working in technical health areas at the FCDO, including responsibility for engagement with the WHO in that area.
- FCDO WHO Hub: individuals at FCDO who are currently, or were previously, responsible for oversight of the CVC programme and lead the FCDO’s institutional relationship with the WHO.
- Independent Expert: experts who can provide insights into WHO financing and reform. This includes former WHO staff, political scientists, health economists and other academics with deep experience of the WHO.
- WHO politics/budget/financing: individuals within the WHO with a good understanding of budget allocation, donor funding dynamics, external relations, governance, and the UK's role and influence.
- WHO reform: individuals within the WHO who are involved in different aspects of institutional transformation and organisational change.
- WHO Technical: individuals within the WHO who are responsible for policy or research on defined technical health areas or leadership of specific critical systems, such as PRSEAH.
Snowball sampling was also used, with informants asked to suggest other relevant stakeholders to interview. The number of interviews targeted by category, and the number of interviews conducted is provided in Table 4. In total, we interviewed 39 key informants for this evaluation. Forty percent of those interviewed were female.
###### Table 4. KII Samples
Key informant type	Number of informants targeted	Number of informants interviewed
Donors/member states	11	6
FCDO country	2	1
FCDO hub	6	5
FCDO technical	8	5
Independent Expert	18	10
WHO politics/budget/financing	10	5
WHO reform	6	3
WHO technical	5	4
Total	66	39

###### Ethical considerations
The FCDO’s ethical standards served as the reference point for ethical considerations including those related to the selection of key informants (ensuring gender balance and representation of diverse groups), obtaining informed consent, conducting interviews, maintaining informant confidentiality, data protection and timely dissemination of findings to relevant stakeholders.51 Given the nature of interviewees, safeguarding measures to ensure no harm was done, or to mitigate against power imbalances, were not considered necessary.
With respect to informed consent, at the start of each interview, informants were provided with sufficient and accurate information about the evaluation to allow them to give informed consent. This included consent around the audio recording of the interviews. To maintain their confidentiality, audio-recordings and transcriptions were stored in a Microsoft (MS) SharePoint folder that had permissions assigned only to team members involved in the data collection and analysis processes.
###### Data analysis and strength of evidence
As noted earlier, data analysed for this evaluation was collected through three data collection methods: desk review, literature review and KIIs. Triangulation of methods was used to increase the validity of the findings. The desk and literature reviews provided useful background information, while the KIIs allowed for elaboration and discovery of new information.
Thematic analysis was used to explore and test data.133 Emerging themes from the desk and literature reviews were identified and inputted into MS Excel, organised by EQ. KIIs were recorded and transcribed, and transcripts were assigned to team members to review and code thematically by EQ in a separate MS Excel document. The themes identified through the three methods were continuously refined and expanded upon, as additional documents, articles and transcripts were reviewed. Finally, the findings were integrated and interpreted.
The use of thematic analysis enabled the team to corroborate findings across the three methods and assess the strength of evidence based on the number of KIIs or documentary sources that identified the theme. To the extent possible, findings were derived from evidence from more than one source. Because the literature on the FCDO CVC funding programme specifically was limited, some of the answers to the EQs were drawn primarily from KIIs. Where evidence was mixed and findings uncertain, this was clearly highlighted. Conversely, where there was consensus or multiple sources, this was also stated within the responses. This pragmatic approach was set out in the Inception Report and agreed with FCDO.
Further, during the analysis and report writing phases, daily team meetings were held among the evaluation team to discuss, challenge and converge on emerging findings and recommendations, thereby limiting the possibility of investigator bias. The findings were sense-checked, and recommendations were further developed and refined, through validation meetings held with FCDO and WHO key stakeholders.
###### Limitations and mitigation strategies
The main limitation of the evaluation was the short timeframe for data collection and analysis. The findings from this evaluation were intended to align with the closure of the programme and to inform the Business Case for future programme of support to WHO. This meant that the timing between data collection, analysis and reporting was quite short (with data collection initiated in mid-February, and data analysis and report writing completed by the first week of April). We mitigated this by conducting analysis in parallel with final interviews, and then reviewing the initial analysis to ensure any findings from the final interviews were incorporated into the report. We also divided the analysis and report writing across the evaluation team, with the Team Leader responsible for reviewing across all EQs to ensure coherence and comprehensiveness, and to avoid duplication. The team also held a meeting with the FCDO Senior Responsible Officer (SRO) midway through data collection to discuss emerging findings and ensure initial analysis aligned with FCDO’s needs.
Additionally, the data collection period coincided with an intensive phase in negotiations on strengthened international pandemic preparedness and response arrangements. This meant that the availability of some key informants was limited. As such, some perspectives may have been excluded or not widely represented. Our mitigation strategies for this are described below.
- WHO interviews were conducted at the WHO headquarters (HQ) level but to ensure that the country perspective was well-represented in the evaluation, we selected some key informants at HQ level who had also worked at the country level, and we triangulated responses at the country level with data and information gathered through the desk and literature reviews.
- Similarly, the large majority of FCDO interviewees were HQ-based. The evaluation coincided with work by FCDO’s WHO hub to survey the country network and it was decided that it was not sensible to duplicate that effort. Further, the level of awareness of the programme among country-based staff reduced the number of potential KIIs. As mitigation, where HQ-based informants had recent country-level experience that was explored in interviews. The triangulation described above was also applied.
- The short timeframe for data collection meant it was not possible to interview informants across the full range of WHO’s and FCDO’s priority thematic areas. We therefore selected informants who could speak across different thematic areas and/or could speak deeply to specific priority thematic areas.
- Some key donors were not available to be interviewed, including Germany. In cases of unavailability, informants who worked closely with donor governments were interviewed wherever possible.
Key informants were solicited for ideas regarding other informants to interview, especially in cases where there were gaps in perspectives. Given that many of the key informants were either donors of CVC funding (i.e. FCDO) or recipients of CVC funding (i.e. WHO), it is possible that responses were subject to positivity bias, whereby respondents focused on the more positive aspects of the CVC programme and less on the negative ones. To mitigate this and encourage free and unbiased responses, we assured respondents that they would be anonymous and that their responses could not be traced back to an individual. For this reason, quotes from KIIs are attributed only to representative institutions or informant groups. Many respondents provided both positive and negative feedback on the CVC programme which provides a level of assurance that positivity bias should not be a material concern.
The focus of the evaluation reduced the potential to explore more fully dimensions such as equity, poverty, gender equality and inclusion. These dimensions are reflected principally in the outcome and impact stages of the programme’s theory of change (how WHO activities ultimately affect conditions within countries and populations). However, this evaluation focuses on questions of operational and institutional effectiveness and funding modalities at the input and output stages of the theory of change. Nevertheless, the team sought to ensure gender-responsiveness and integrate considerations of equity and human rights, for example in the proposed Discrete Learning Analyses, which included an assessment of staffing trends, including analysis by gender, and reviewing the Preventing & Responding to Sexual Exploitation, Abuse & Harassment (PRSEAH) agenda, which has important rights dimensions. This approach was discussed and agreed with FCDO. Gender composition of the team and of key informants interviewed was also tracked.
## Evaluation Team structure, governance and management arrangements
The core team is structured as follows. Annex 8 provides a detailed description of roles and individuals.

- Team Leader: [redacted]
- Lead Researcher: [redacted]
- Research Consultant: [redacted]
- UK Evaluation Specialist: [redacted]
- WHO Reform Specialist: [redacted]
- Senior Advisers: [redacted]

The contract is managed by DAI, with technical support from Global Evaluation Monitoring Framework Agreement (GEMFA) partner Halcyon Consulting. [redacted] is DAI’s Project Director/Contract Officer. [redacted] is supported by Project Manager [redacted]. [redacted], is acting as Co-Project Director for this call down and [redacted], Knowledge Management and Learning Lead, is providing additional quality assurance.
The team received support from both FCDO and WHO to deliver the evaluation, such as identifying and arranging KIIs. Drafts of the report were shared with both FCDO and WHO to provide an opportunity to comment on emerging findings and recommendations. However, the team was able to work freely and without interference to derive and present findings and recommendations. No conflicts of interest were identified among team members.

# 4. Responses to Evaluation Questions

This section sets out responses to the EQs. The EQs are grouped into 7 overarching clusters (as described in the previous section) for ease of analysis and reference. These are as follows:

Did the UK deliver inputs coherently?
- EQ1. How coherently have the different elements of the programme worked together?
- EQ2. What are the synergies between the different UK inputs (flexible funding, PBR, MEL, and expertise and influencing)?
- EQ3. To what extent has FCDO optimised the synergies between UK inputs?
Did the programme design respond to WHO needs?
- EQ4. How well did the design of the FCDO’s CVC programme (including the PBR element) respond to WHO’s reform agenda?
- EQ10. How well did the design of FCDO’s WHO CVC programme (including the PBR element) respond to WHO funding issues?
Did the programme support WHO reform and delivery?
- EQ5. To what extent has the WHO CVC programme funding facilitated the more effective delivery of the WHO reform agenda?
- EQ7. To what extent has WHO CVC programme funding facilitated the more effective delivery of the GPW13 by WHO (global, regional, country)?
Did the PBR component contribute towards the overall programme goals?
- EQ6. What role has the PBR component had in incentivising organisational change?
- EQ8. What might the WHO have done differently, had the UK’s CVC funding been 100% flexible?
Did the programme contribute to the wider sustainable funding agenda?
EQ9. How well has the UK approach to funding the WHO aligned with other donors funding practices and has it led to an improved funding environment for WHO?
How did the programme impact on UK influence in WHO?
EQ11. To what extent has CVC funding to the WHO changed the UK’s influence vis-à-vis WHO and how?
What was learned from the results approach?
EQ12. To what extent has FCDO used the information gathered through the WHO Results Framework?
Each of the EQ cluster responses draws from evidence from all three of the data collection methods. It was agreed to present responses in this integrated, thematic manner to respond to the needs of policy-makers in line with the utilisation orientation of the evaluation. EQ responses depend to differing extents on literature review, document review and KIIs. Each cluster section begins with a summary of key findings and ends with key relevant recommendations, which are numbered and gathered together into a single table in the findings section which follows.
## Did the UK deliver inputs coherently?

Relevant EQs
EQ1. How coherently have the different elements of the programme worked together?
EQ2. What are the synergies among the different UK inputs (flexible funding, PBR, expertise and influencing)?
EQ3. To what extent has FCDO optimised the synergies among UK inputs?

Key findings / The design of the overall programme is coherent in support of FCDO’s aim of strengthening WHO institutional performance. The design also manages the range of risks associated with the transformation in channels of accountability, influence and funding of activities. / The approach has reduced programme management costs and brought a clearer articulation of top UK priorities. However, several factors, from both inside and outside the programme’s sphere of control, have also limited effectiveness gains and the rapid transition to a new model created problems. / Looking ahead to a future programme there are several options for design that could strike a better balance between supporting WHO performance while also maintaining UK influence and assurance.

###### Coherence and synergies
WHO’s fragmented funding environment represents a barrier to institutional performance. The literature and KIIs confirm the multiple ways that WHO’s fragmented funding landscape poses challenges to organisational impact. The earmarking of funds undermines the organisation’s ability to execute its GPW and to recruit and retain staff on long-term contracts. It also affects the WHO’s agility and responsiveness in the face of new priorities or emergencies, and significantly increases WHO’s donor reporting and negotiation burden.
FCDO’s programme represents a coherent response to these core challenges. The provision of £340m flexible funding to WHO over four years sought to reduce the bureaucratic burden on both the WHO and the UK, to reduce programme management costs and create space for FCDO and WHO to advance strategic health priorities.15 By shifting away from earmarked funding, FCDO sacrificed control over narrow, shorter-term priorities in favour of longer-term WHO transformation. This principled, bold step demonstrated the UK’s leadership on sustainable financing and was commended by multiple key informants.
Individual programme components were designed coherently to mitigate risks associated with flexible funding. The FCDO Business Case highlights potential risks in the transition from earmarked to flexible funding, including the loss of direct influence on WHO activities.15 Various complementary programme mechanisms were therefore designed to increase accountability and influence.15
The 30% PBR component sought to support institutional performance by providing an accountability mechanism and incentivising WHO performance. Over the course of the programme, the UK disbursed all PBR tranches. The PBR payments were based on WHO performance against ‘top asks’ agreed between FCDO and WHO. The PBR component sought to improve accountability by elevating UK priorities amongst WHO’s senior leadership. This performance-based approach was consistent with incentive mechanisms used for other multilateral organisations at the time.
“The key ask structure should have been providing some leverage at the kind of higher political level in the organisation. So higher level officials should have been able to use those top asks…at the height of the level of DG…to have the conversations that they might not have been able to have, had we not had a PBR mechanism.” (KII, FCDO)

“Instead of engaging directly with your director, you're now able to point to a UK WHO performance agreement…the implication being that this is a priority of the Director General, who will be closely monitoring the work of that particular part of the organisation and making sure that their activities are met, with the obvious threat that if that objective is not met, then funding may decrease or at the very least it will be the subject of a very high-level discussion between the UK and WHO.” (KII, FCDO)

Cross-FCDO and cross-Whitehall coordination and influencing mechanisms sought to support institutional performance by surfacing shared UK priorities and engaging WHO counterparts at senior and technical levels.15 An annual UK-WHO Strategic Dialogue was established as a forum to replace sector-by-sector engagement with WHO. The Strategic Dialogue consisted of a split engagement, including UK ministerial engagement with the WHO DG and his Senior Team in London, and separate technical-level engagement structured around WHO’s performance and progress against priority areas.15 An internal coordination platform was also established for thematic leads to update the WHO Hub on performance in different technical areas, and to agree on the UK’s ‘top asks.’ In addition, the UK engaged routinely via the cycle of governance bodies, such as participation in the Programme, Budget & Administration Committee (PBAC).14
The inputs described are synergistic in design and have unlocked benefits, including greater efficiencies. The consolidation of previously earmarked funds under a single framework reduced oversight costs over the course of the programme. Moreover, the cross-HMG annual Strategic Dialogue and PBR approach have provided an important channel for defining and elevating UK priorities within WHO and for increasing accountability.14
“From a programme management perspective, it's quite simple. You just have one MoU [Memoranda of Understanding] and big payments every now and again. There are some efficiencies gained with that kind of model.” (KII, FCDO)

“Performance-based priorities have been useful in articulating UK priorities to the WHO.” (KII, FCDO)

###### Limiting factors
The transition from multiple programmes to a single framework was abrupt, rapid and unsystematic. In some areas, a single year of funding was preserved but beyond that there was no clear transition plan or purposeful consideration of impacts. Therefore, FCDO has only partially optimised synergies amongst UK inputs, with impacts constrained in several ways.

“There is one extreme and another extreme, and there's been no thought process to the transition.” (KII, FCDO)

Additionally, the ‘key asks’ approach is considered too high-level and narrow to incorporate the full suite of FCDO priorities. Several informants reported that the ‘key asks’ approach provided insufficient space for detailed discussion on UK reform and thematic interests. This challenge was compounded by the lack of a multi-year logframe, as well as the (understandable) focus on COVID-19 and pandemic preparedness and response.

“Everything was bundled under that one thing (‘key ask’). I think we could have unpacked it. It's not beyond the realms to unpack it a bit and say, you know, within this, these are things we think are important, or even get quite specific if we want to, but we never really did that.” (KII, FCDO)

Further, the shift to flexible funding in many ways reduced the visibility of the UK’s support to WHO. This lack of visibility manifested itself among WHO thematic counterparts but also within FCDO at the country level. Indeed, several informants highlighted limited engagement with the FCDO country network (largely due to lack of capacity) as having undermined programme synergies.

“Without the financing, they're (FCDO thematic leads) not getting the look in…it is good to have the financing and the results together.” (KII, FCDO)

“FCDO advisers or people in country might not have a real understanding of it [the programme]. They might…[not] realise that actually there's a huge amount of money that goes to WHO, which is also spent in their countries.” (KII, FCDO)

“Particularly with respect to country advisers, I think the hub wasn't structured to engage the countries anything like as well as it could. I think it was quite inward facing.” (KII, FCDO)

UK ministerial engagement was less intensive than envisaged in programme design. It had been seen as an important channel to maintain UK influence in the context of the transition to flexible funding. However, due to UK domestic political factors and the impact of the FCDO merger, it was much lower than many other significant donor countries.

“Engagement with Tedros is absolutely key to making things happen in the WHO. It was a real challenge that ministers were not engaging and definitely impacted on the overall effectiveness of that CVC model.” (KII, FCDO)

Finally, FCDO capacity and internal change processes have constrained the impact of programmatic synergies. FCDO’s WHO leads have been drawn heavily into policy issues (e.g. pandemic preparedness and response) over the course of the programme, with more limited engagement on institutional issues, leaving the institutional reform influencing agenda underserved. Added to the burden of policy demands, there has also been high staff turnover. The HQ programme SRO changed several times over the course of the programme, affecting the momentum of engagement. The merger and internal reorganisation processes also resulted in a shifting of responsibilities internally. Together, these factors have reduced FCDO’s consistency of engagement and coordination with WHO and other funders. As a result, FCDO invested less time convening and coordinating other donors than was originally proposed in the Business Case.

###### Opportunities
There is consensus across a wide range of informants that flexible funding remains the right way forward. The abrupt transition from earmarked to flexible funding under the UK’s WHO CVC programme, coupled with the wider context of the COVID-19 pandemic and the merger created specific challenges as outlined in the previous section. However, key informants largely recognise the shift towards flexible funding as a principled approach and that the broad course of direction should be retained.

“The flexible financing was incredibly important for WHO, during the pandemic and emerging from the pandemic, so...it has contributed to keeping the WHO show on the road, which is really important.” (KII, FCDO)

Moving forward, widening the Strategic Dialogue, at both senior and technical level, to ensure sufficient space for a broader set of conversations will help to optimise programme synergies. The current dialogue has been focused too narrowly on ‘key asks,’ and institutional reform must be on the agenda, alongside policy issues.

“(The Strategic Dialogue should be) an entry point for having broader conversations around the issues of the day and not static on what we agreed a year, two years, three years ago.” (KII, FCDO)

The PBR mechanism (which is assessed in greater depth under (D) later in this section is widely seen within FCDO as not critical to effective dialogue and may detract from the quality, breadth and depth of the WHO-HMG partnership. Some felt that the Strategic Dialogue, if strengthened, could be sufficient as an accountability mechanism. This would depend on reinvigorating internal FCDO coordination mechanisms to ensure clear policy priorities are established, a clear management strategy, and engaging the FCDO country network.

“If we just be clear with them about our priorities…We would have to get our act together as a group because we've all got different priorities and say we're going to choose ten priorities or five priorities or whatever. And we signal them really clearly in the Annual Review and we talk about them in the dialogue. I think those are ways of getting attention on our issues without having to earmark. We do it in all sorts of different fora.” (KII, FCDO)

“We have strategic dialogues with other UN institutions that are not to do with health, and (for those) we don't have the approach of the top asks and the money being tied to them.” (KII, FCDO)

“(PBR can) distort towards a set of priorities and clamouring around reporting for those priorities that then moves away from the bigger objectives and doesn't allow for that slightly wider common understanding of where things are going and dialogue around that.” (KII, FCDO)

Reinstating a logframe with multi-year targets will help to optimise synergies between inputs and to deliver a longer-term perspective. Several informants highlighted the need for a longer-term approach, rooted in a logframe to ensure accountability. The logframe should include clear institutional benchmarks as well as technical priorities.

“I think that having them (the ‘key asks’) agreed sort of piecemeal each year is…quite un-strategic. It would be good to have a clear…framework for what we want the WHO to deliver over the next four years and to have clear benchmarks…very clearly say, this is what we want to happen over the four years. So more like a logframe.” (KII, FCDO)

Retention of a proportion of funds to support key UK priorities could provide greater HMG control, influence and accountability, and a useful, more systematic way to manage the transition to fully flexible funding. Several key informants noted that new HMG funding has been ring-fenced for certain areas with critical resource gaps (e.g. clinical trials, DHSC patient safety support, and a new FCDO climate change and health programme). Though funding for many programmes was consolidated into the CVC programme, the approach was not entirely consistent. Earmarked funds were still retained for several areas such as the Special Programme for Research and Training in Tropical Disease (TDR), the Human Reproduction Programme (HRP), polio and the Partnership for Maternal, Newborn and Child Health (PMNCH). Some informants proposed retaining a small pot of catalytic funding, or a soft-earmarking approach for different thematic priorities. A range of options exist, and this evaluation assessed them against a range of criteria (set out in Section 6 on Recommendations).

“The opportunity to still have a relatively small amount of money to get things off the ground to try and get it higher up in the agenda...can be catalytic, but they need to be very clearly defined.” (KII, FCDO)

“Some kind of accelerator funding where basically we would have a pot for earmarking ourselves…It's a way for us to kind of continue leadership on CVC funding.” (KII, FCDO)

“Catalytic funds...for short term…catalytic pieces of work…proof of concept type things. I think it's useful to have because WHO is not very flexible…I think we need a bit more thinking about how the country programmes can access that too.” (KII, FCDO)

“Soft earmark, that's another way…you'd say, okay, [a] certain amount of money has to go to UHC, PHC.” (KII, FCDO)

“We need to do a mixed approach.” (KII, FCDO)

Relevant recommendations
Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. [#6] / Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. [#7] / Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted funding to UK high priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement. [#8] / FCDO/WHO Dialogue. Widen and regularise Strategic Dialogue on an annual basis and spanning the full range of institutional reform, policy priorities and opportunities for review[ii] of the targeted funding. [#9] / Coordination. Reinvigorate internal FCDO and HMG coordination mechanism to ensure the establishment of clear policy priorities, a clear management strategy, and the engagement of the FCDO country network. [#10] / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include pro-active dialogue with like-minded and potential flexible funders. [#11] / FCDO roles. Ensure clearer delineation and understanding of roles between WHO Hub, UKMIS Geneva and other relevant HMG focal points. [#12]

## Did the programme design respond to WHO needs?

Relevant EQs
EQ4. How well did the design of the FCDO’s CVC programme (including the PBR element) respond to WHO’s reform agenda?
EQ10. How well did the design of FCDO’s WHO CVC programme (including the PBR element) respond to WHO funding issues?

Key findings / The design of the UK’s CVC programme aligns very strongly with WHO needs and requests. / The shift to flexible funding, in particular, responds directly to WHO’s challenging financial landscape and is a necessary (though insufficient) condition for strengthened institutional performance. / The PBR element of the programme is more problematic. WHO considers the UK’s PBR tranche ‘at risk’ meaning the PBR mechanism significantly reduces WHO’s budget and planning space.

###### WHO funding landscape
WHO’s overall level of funding has been inadequate for a long time. WHO's 2018-19 budget of US$4.4 billion (bn) was approximately equal to that of the University Hospital in Geneva.48 As long ago as 1998 the low rate of collection of ACs from Member States fuelled speculation that the organisation was running out of money.36 In the context of the Ebola epidemic, Checchi and colleagues highlighted that WHO lacks sufficient flexible funding to respond to health emergencies.48 The inadequacy of WHO’s budget came apparent during the COVID-19 epidemic.

“I think during Covid everyone also saw how important a strong, effective, credible WHO was for trying to lead the world through this pandemic and I think everyone saw that the financing is a complete mismatch with what we actually rely on this entity to do.” (KII, independent expert)

The composition of funding has also progressively evolved over time. VCs have become increasingly important since the 1970s.53 In 1975 extrabudgetary resources made up just over one quarter of WHO’s budget. However, the introduction of ‘zero growth’ policies during the 1980s to suppress increases in ACs saw extrabudgetary resources exceed the regular budget for the first time in the 1988–89 biennium. Over the next 30 years, ACs remained roughly constant in inflation-adjusted terms while VCs continued to grow. 9 The share of ACs in the total budget has continued to decline over the past decade. VCs increased from 75% of WHO's budget in 2010 to 88% in 2021.35 As Charts 1, 2 and 3 below show, ACs have remained constant while Specified VCs have grown rapidly (particularly outside the Base Programme). It is also argued that bypassing the regular budget through use of extra-budgetary contributions demonstrates a lack of collective confidence in the WHO.

###### Impact on WHO institutional performance

The negative consequences for WHO institutional performance are well-established. The consequences of a high share of specified VCs include limited predictability, reduced purchasing power, and undermining of long-term investments.22 They also divert WHO’s focus away from core priorities, undermine “ostensibly democratic structures” of the World Health Assembly (WHA) and make coordination difficult.35 Additionally, specified VCs can reduce and fragment institutional focus,27 while earmarking for programmes and priorities driven by donor preferences skews global health priorities.48 Member States try to set priorities, but funds are provided for specific issues, selected by a small number of donors who have a decisive role in deciding what the organisation does or does not pursue.52 This dynamic has been described as “trojan multilateralism” and can result in the diminishing of organisational capacity in other areas.9 For example, global health funder priorities have tended to skew towards infectious diseases in comparison to underserved global health areas like mental health, noncommunicable diseases, injuries and disabilities.25 Earmarking also imposes a very significant reporting burden associated with thousands of individual grants.6
WHO, supported by Member States has made the case for increased, and more sustainable financing. The low share of flexible funding threatens impartiality, operational planning, integrity, independence, efficiency and accountability.84 Sustainable financing would be more flexible, predictable, medium/long-term, diversified in terms of donor base, and predominantly aligned to the base segment of programme budget.84 The Absence of sustainable financing complicates HR, operational planning, budget allocation.84

###### Opportunities around flexible funding
WHO has argued that a higher share of sustainable, flexible funding would support better delivery and institutional reform. Flexible funding could be deployed in various ways. For example, it could be used to ‘green’ the heat map, essentially allocating funding to areas that specified VCs neglect (also referred to as ‘pockets of poverty’). It could also be used to ensure that all normative work is funded flexibly. This would eliminate risks to WHO integrity and independence that arise where activities in specific disease or health areas are funded by individual or very few donors. It could be used to strengthen critical corporate functions (such as PRSEAH) where individual donor funding is hard to secure (since donors tend to prefer to fund specific health outcomes). It could be used to manage challenging transitions, such as the Country Office funding drop associated with the decline in polio funding. In this example, elimination efforts focus on fewer countries and responsibility for immunisation becomes integrated into country systems. It could also be used to fund core capability such as defined staff roles in Country Offices.84 Importantly, the objective is not to achieve a 100% level of flexible funding but instead attain the necessary level needed to avoid a "toxic level of non-core" funding which creates a vicious cycle of institutional weakness and fragmentation.36
Some key stakeholders challenge the idea that funding is the binding constraint to reform and delivery. Instead, they highlight the importance of evolving HR structures and mandates.

“Why would it [flexible funding] enable reform? Why does the way that money is provided to an organisation have an ability to help it reform? I don't think so. Actually, I think reform has to come from inside an organisation...It's an unassailable, unchanging, inflexible organisation at country level. The backbone of the institution is very much secured in the human resources and its formal mandate. That wasn't changed by £340m.” (KII, FCDO)

However, the strong balance of evidence and opinion supports the view that funding is a critical binding constraint. In addition to the literature cited above, findings from the Multilateral Organisation Performance Assessment Network’s (MOPAN) 2019 assessment, 41 as well as the ongoing 2023 assessment, stress that Member States and other funders need to continue to transform the funding model as a key driver of effectiveness. The case for increased flexible financing is also set out clearly in a range of documents from bodies such as the WHO Working Group on Sustainable Financing,84 and the Independent Expert Oversight and Advisory Committee (IEOAC).85 It was also echoed in many KIIs.

“The IEOAC said the single most important impediment in the efficiency of WHO is the high-level earmarking, because that is translated into enormous red tape and administrative costs imposed by the bilateral donors.” (KII, WHO)

“Less-tightly controlled financing of WHO…would allow the organisation to have a bit more autonomy and policy space, especially vis-a-vis member states” (KII, Independent Expert)
“An organisation that feels secure in its financing can just work in a totally different manner than an organisation that constantly has to ask ‘Will I have enough for this? Will I have enough for that?” (KII, Independent Expert)
Others also argue that flexible funding is not just critical for reform but also for greater political independence. It would empower WHO to be able to be frank with Member States when appropriate. One example given was the West African Ebola outbreak of 2014-15.
“Alongside a management rationale, there is a political rationale. We thought that at the time of the West African Ebola crisis, that the DG needed to be much more willing to call out her Member States when they were not sharing information early on about the extent of the outbreak.” (KII, Independent Expert)
The CVCA is a channel that allows donors to provide additional flexible funding. CVC was introduced in 2004 as a way to allow donors to contribute additional flexible funding over and above their AC level. The UK was an early contributor alongside other donors. However, momentum was not sustained and contributions fell back significantly before rising again from 2016/17. Driven principally by this UK programme, the CVCA reached almost US$400m in the 2022/23 biennium. Chart 4 shows the evolution of contributions.

The CVCA expands the total flexible funding available for allocation. At the start of the biennium, WHO’s Strategic Planning and Budget team estimates all available flexible funding (AC, Programme Support Costs [PSC] and CVC) and determines allocations as part of a single process. The PBR element of the UK programme cannot be included in this estimation process since it is at risk. This reduces the planning envelope of flexible funding at a magnitude of US$60m per biennium (which is significant at around 30% of the recent US$200m increase in ACs).
The design of the UK CVC programme, particularly in terms of the shift to flexible funding, was clearly intended by FCDO to support ongoing reform and better institutional performance, as well as respond to calls from the WHO DG.
“It brought together lots of different earmarked strands of funding into one big programme to support WHO to address the problem of its funding being very specifically earmarked. This ties its hands and means it is unable to make specific strategic decisions and also just demands huge amounts of reporting” (KII, FCDO)
“It's responding to Tedros’ very specific request for more flexible funding and predictable funding to deliver their transformation agenda. So much of what they need is money for staff to get the right people in the right place at the right time and to rely less on piecemeal staffing like consultants or short-term positions. To be able to invest in their people in a predictable way.” (KII, FCDO)
“What I care about is whether the UK CVC funding is filling the gaps that makes the organisation work better and therefore deliver on UK priorities. That's the point of flexible funding. It allows you to fill critical gaps that would otherwise not be filled by donors who want to earmark their funding to projects that they can report that they got nice results on.” (KII, FCDO)
Relevant recommendations
Flexibility. Continue to provide the large majority of the UK’s support to WHO flexibly into the future to support ongoing reform and delivery. [#1] / Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. [#7]

## Did the programme support WHO reform and delivery?

Relevant EQs
EQ5. To what extent has the WHO CVC programme funding facilitated the more effective delivery of the WHO reform agenda?
EQ7. To what extent has WHO CVC programme funding facilitated the more effective delivery of the GPW13 by WHO (global, regional, country)?

Key findings / Multiple factors mean that a definitive answer to these questions is not possible, and there is a striking divergence of views between those in and outside WHO. / Assessing and reporting the use of CVC on a standalone basis is misleading. Flexible funding overall is a more appropriate unit of account and oversight. The WHO approach to deploying flexible funding has been strategic and further improvements have been made. / The deployment of CVC funding was not well communicated and did not match the expectations of many in FCDO, particularly technical leads. / Sustaining support will depend on a much more effective definition and communication of results.

The previous section (EQs 4 and 10) addressed the extent to which the programme design responded to WHO funding and reform needs. This section examines whether the programme actually contributed to delivering WHO delivery and reform objectives. These questions are central to assessing the value for money and effectiveness of the programme approach. The evidence is not definitive, and opinions were mixed. Of particular note, is the difference of perspective from those in and outside WHO, particularly within FCDO. This underpins some important recommendations.
###### Difficulty in tracking the impact of UK funding The literature and document review highlighted several factors that make it difficult to provide definitive answers to questions EQ5 and EQ 7, as described below:
- Flexible funding is not the only constraint to reform and delivery. A range of other well-documented factors exist. They include WHO’s governance and constitutional structure which limits the ability of HQ to guide and manage Regional Office and Country Office activities and to hold them accountable for performance. HR procedures and other critical systems and processes also complicate reform and delivery for several reasons, some common to the UN as a whole. For example, it can be challenging to manage poor performance and move staff on, and the pension structure incentivises people to stay on as long as possible (making it challenging to get fresh blood and healthy turnover). Multi-year initiatives to strengthen organisational performance have pre-dated this programme and have delivered improvements. An example of this supported WHO’s response during the pandemic.32 In many cases these initiatives are interwoven with funding, making separation and attribution of effects challenging.
- The CVC account makes up only a small share (4%) of total WHO programme funding (and 8% of the base budget). The UK funding was 60% of the CVC account in 2022/23. Attribution for overall organisational performance back to CVC funding (and the UK programme within that) is not appropriate nor possible.
- In a large and complex multilateral organisation, transformation occurs gradually, including in areas such as budget allocation. It is likely to take longer than a single programme cycle of 4 years for many substantive effects to manifest.
- The metrics for assessing reform and delivery are by their nature hard to define (particularly so in the WHO structure, with autonomous Regional and Country Offices). This results in data weaknesses which rule out clear measurement of progress.
- Much of the programme period was dominated by the COVID-19 pandemic which had a significant disruptive and distorting effect on both reform and delivery activities.

These analytical challenges were recognised by KIIs, who perceived the small relative size of CVC funding and the decentralised governance structure as particular complications in tracking use of UK funding:
 “It's a bit of a chicken and egg because until they get enough of a pot or flexible funding, they don't have the means to demonstrate how well they could do...One donor at scale isn't going to be enough or hasn't been enough over the last four years.” (KII, FCDO)
“There's been a lack of accountability and transparency on the allocation of the flexible pot, because you allocate a certain amount to regional directors and then it's totally at the behest of those regional directors to be able to allocate it.” (KII, FCDO)
###### Facilitation of reform and GPW13

In spite of the above caveats, it is possible to unpick the relevant factors and provide some insight. Analysis of the data is instructive and the KIIs also offered a rich and diverse set of opinions. The first step is to analyse how the CVC funding has been deployed.

Charts 5 and 6 above set out the distribution of the three elements of flexible funding (AC, PSC, CVC) in the 2022/23 period. The initial impression is of a very diverse allocation between the three parts – with only a limited share (30%) of CVC being spent at HQ compared to AC and PSC. The Africa Regional Office (AFRO) (US$71m) and South-East Asia Region Office (SEARO) (US$73m) received the largest quantities among Regional Offices. In terms of allocation by outcome, the difference is even more marked, with only a small share of CVC (16%) being deployed to a ‘more effective and efficient WHO’ compared to 46% for ACs and 96% for PSC.
These disparities principally reflect the use and accounting rules for the different funding streams, most notably for CVC, which can be deployed for technical and programmatic outputs but not administration and management.
In practice, these three streams of flexible funding are pooled together for allocation at the beginning of each biennium based on the best estimate of flexible funds to be received. Allocation is decided by the Global Policy Group (made up of the DG and Regional Office heads). The objective for flexible fund use is to ensure operational capacity for staff costs and critical activities within the approved Base Programme budget. Flexible funds can also be shifted towards under-funded areas over the course of the biennium based on patterns of other donor contributions.98 As noted previously, the estimation process is based on conservative assumptions and the 30% ‘at risk’ tranche of the UK CVC programme is not included.
The three elements of flexible funds are therefore allocated as a single envelope and should therefore be considered fungible with each other. An increase in the budget for one of the three areas increases the overall flexible funding envelope. However, it is important to note that technical or programmatic activities identified as priorities for the overall flexible funding pool are generally allocated to CVC. Therefore, when streams of funding are reported individually, a distorted and partial view is given. This seems to be exactly what happened with the 2023 CVCA report.98
The 2023 CVCA report98 was a relatively short, principally narrative, document which described a range of programmatic and geographic activities that the CVC funds supported. These included neglected tropical diseases, polio transition, mental health, antimicrobial resistance (AMR) and many more. Extracted from the wider context of total flexible funds, this approach created a picture of a somewhat disconnected portfolio of (albeit high value) interventions that lacked strategic coherence. This contributed to the perception that CVC was deployed to fill gaps, balance competing interests, and/or satisfy political demands rather than to strategically advance reform and delivery. This perspective was reflected in several KIIs with FCDO as well as other donors.
“I don't think the CVC was used strategically. It still funds a myriad of worthwhile projects around the world. But they don't add up to a strategic goal. The decision-making process on why to fund a diabetes project over here or a mental health project over there or cancer somewhere else is very unclear. What does all that add up to in terms of their transformation programme.” (KII, FCDO)
“Some very good, very worthy projects around the world but no clear sense at all around prioritisation or what they were all adding up to. And that wasn't the intent of flexible funding.” (KII, FCDO)
However, when viewed through the more appropriate lens of flexible funding as a whole, a very different and much more strategic narrative emerges. As Chart 7 shows, following several years of stagnation, the growth in flexible funding in the first half of this decade is striking. It grew by US$300m in 2022/23. The UK CVC programme, which contributed around US$200m per biennium accounted for a significant share of this increase. With the agreed increase in ACs, which will add around US$200m in additional resources, the level of flexible funding is estimated to surpass US$2.1bn in the 2024/25 biennium.

As flexible funds have grown this decade, the allocation process has also been developed. The overarching objective for the use of flexible funds is to ensure funding of critical programme budget priorities. The Global Policy Group (a committee made up of the DG and Regional Directors [RDs]) determines the allocation of flexible funds by the major office at the start of each biennium. In 2022/23 an important priority was to increase resources for Regional and Country Offices to enable them to strengthen the advice and capacity-building support that they provide to countries. This is an objective that is central to the FCDO CVC programme.16 As Chart 8 shows, this objective has been achieved with flexible funds growing for all Regional Offices and faster than the growth in HQ allocation.
Reviewed by GPW objective (see Chart 9), it can also be seen that flexible funding was principally deployed towards objective GPW13 Objective 4, ‘More effective and efficient WHO providing better support to countries’ in line with the aim of ensuring core foundational institutional functions are supported. A powerful specific example of the criticality of flexible funding to organisational reform has been the importance of the US$50m allocated in the 2022‒2023 biennium to transform PRSEAH performance. WHO has committed to maintaining at least US$50m per biennium for PRSEAH work at HQ, and Regional and Country Offices going forward. Chart 10 reinforces the picture that flexible funding is used for the base programme. Chart 11 shows the functional use of flexible funds, which is principally taken up by staff costs as would be expected.

With flexible funding rising into GPW14, the flexible funding approach is being developed further. These are set out in the 2024/25 programme budget. Flexible funding allocation will be focused on high priority outputs, with particular emphasis on strengthening technical capacity at the country level and with a target of attaining at least 80% budget coverage.
The key process that will guide this allocation is the Core Predictable Country Presence (CPCP) process established and guided by the internal Action for Results Group, set up to accelerate Country Office empowerment and transformation. The CPCP model identifies core positions needed in every Country Office (according to different country archetypes) to deliver WHO support ranging from lighter-touch policy dialogue to full support, including field operations, for countries with health emergencies or humanitarian crises. The need for a total of over 2,500 CPCP positions has been identified across all 152 WHO offices. Many of these positions already exist and are funded from a range of sources. Over 800 of them do not exist and will be created and filled. The goal is to provide stable and predictable funding for all CPCP positions by 2027.
The CPCP agenda is perhaps the core transformational ambition for the organisation over the coming years and flexible funding, including adequate CVC, is critical to it. Success will see country work embedded in cross-cutting, systems-led engagement.
“In each country that core presence has got to be anchored around UHC [Universal Health Coverage], healthier populations and emergencies. All the additional money that might come in for HIV or TB or whatever else then falls into a structure that's more predictable and that governments can really rely on.” (KII, WHO)
###### Challenges Implementation will be challenging, and recruitment will take time. However, supported by additional flexible funds, the CPCP agenda offers the promise of much more effective country engagement from the 2024/25 biennium onwards. The links, however, between flexible funding, including CVC, and this transformation agenda are not well communicated and understood. Certainly, the practice of reporting CVC on a standalone basis has not helped. Voices in both WHO and FCDO recognised the benefits of widening the reporting approach.
“If 80% of the flexible funding is going to the top country priorities that seems to me like a really strategic way of allocating the funding. But I don't think we've had the reporting that we needed. We should say to them that we don't need a CVC report. What we want is a flexible funding report.” (KII, FCDO)
The deployment of flexible funding, including CVC, in support of the country transformation agenda was therefore strategic. However, it did not match the expectations of some in FCDO on how it would be deployed. This has created some tensions and challenges, particularly in managing the FCDO exit from individual thematic programmes such as for Health Systems Strengthening (HSS) and Water, Sanitation and Hygiene (WASH), which were consolidated into the single CVC programme. In the first year of the programme, flexible funding was allocated by WHO to help manage the transition away from individual programmes (e.g., to support critical staff until replacement funding sources could be found). However, this was not sustained, and the transition was described as abrupt by some in FDCO.
The expectation of some thematic leads on both the WHO and FCDO side that the increased UK flexible funding to the centre of WHO under this programme should be used, at least to some degree, to replace the discontinued direct funding persists. The fact that it does not continues to cause frustration amongst both WHO and FCDO policy leads.
“We're now giving flexible money...for some reason that’s not filtering down.” (KII, FCDO)
A systematic analysis of the budgetary and operational implications across the different thematic areas is outside the scope of this evaluation. However, it is clear that impacts differed by area, based on responses by WHO and FCDO policy leads. In the area of climate change and health, a new FCDO programme (linked to the Conference of the Parties [COP] 26 agenda) was created which includes support to WHO to allow for kickstarting capacity and leadership. In HSS, the breadth of the donor base has ensured that critical WHO roles are sustained, as is FCDO engagement and influence on the basis of technical expertise. For both WASH and maternal, newborn and child health (MNCH), WHO capacity is still compromised due to the end of the direct FCDO programming that existed prior to 2020. In research, specific FCDO programmes have continued and additional DHSC programming has supported emerging priorities such as clinical trials. Beyond the availability of funding, the transition away from individual programme funding also generated an active discussion around its implications on UK influence. This is addressed in more detail under EQ11.
Overall, it can be concluded that there is a clear sense of strategic purpose and clarity in terms of use of flexible funding by the WHO. But progress has been slower than optimal and weaknesses in communication and reporting, as well as mismatched expectations, have obscured that purpose. Nevertheless, strong conditions are set for a step-change in country technical capacity into the future provided adequate flexible funding can be secured. In the words of one informant:
“It's a big, bold bet that the UK has made. But you’ve got to stay the course and hold your bet long enough to see this play out. And you know we had to get through a pandemic.” (KII, WHO)
Of course, sustaining support will depend on much more effective definition and communication of results. Many FCDO informants stress the importance of WHO to improve the reporting of results if sustainable funding is to be a success.
“They're really going to have to up their game and present a compelling narrative, including around accountability and transparency, and how decisions are made, and you know where that money goes.” (KII, FCDO)
“This is an organisation which at the time was making the case over and over and over again that we need more flexible funding. But you still need to be able to show to your Parliament, to your ministers that you're getting good results. You're not going to get any flexible funding if donor countries aren’t able to claim a result for what they're putting in.” (KII, FCDO)
Relevant recommendations
Flexibility. Continue to provide the large majority of the UK’s support to WHO flexibly into the future to support ongoing reform and delivery. [#1] / Reporting. Encourage WHO to integrate Core Voluntary Contributions Account (CVCA) reporting into a wider flexible funds reporting approach. [#2] / Results. Push WHO to develop clear metrics for success in funding and reform, particularly in terms of country performance. These should be integrated into the GPW14 results framework which currently does not cover this area. [#3] / Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders as part of the Investment Round offer. This could be as part of a wider major funder engagement approach that could also include some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return. [#4] / Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round. [#5] / Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO’s own indicators to deliver a longer-term perspective across a wider set of priorities. [#6] / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include pro-active dialogue with like-minded and potential flexible funders. [#11]

## Did the PBR component contribute towards the overall programme goals?

Relevant EQs
EQ6. What role has the PBR component had in incentivising organisational change?
EQ8. What might the WHO have done differently, had the UK’s CVC funding been 100% flexible?

Key findings / Attributing effects to the PBR component is impossible given the complex dynamics of change and the multiple sources of pressure on WHO to deliver progress. / Benefits in terms of UK domestic accountability and priority signalling were identified. A wide range of downsides, including high transaction costs and restrictions to WHO on the deployment of funds, were also identified. / The evidence suggests that PBR can accelerate progress on multilateral reform or policy priorities only in specific conditions. These conditions are not met in this context. / If the UK had not used a PBR component, more flexible funding would have been available for WHO’s budget and planning exercise. However, in this counterfactual, FCDO would also have lacked a narrative on accountability.

Annual funding was structured into a core element (70%) and a PBR tranche (30%) conditional on the delivery of five key policy asks agreed on an annual basis. The key asks for 2021 and 2022 were met14,18 and PBR tranches were paid in full. At the time of this evaluation, the process for assessing progress against 2023 indicators was still ongoing.
The rationale for the PBR tranche was to increase WHO focus on UK priorities, strengthen incentives to deliver the GPW and strengthen accountability for performance. This was part of a strong trend of greater use of PBR in the UK’s multilateral funding. The previous 2016-20 programme had included a 50% PBR tranche. PBR had also been used in UK funding to other health agencies such as the Joint United Nations Programme on HIV/AIDS (UNAIDS), the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM), Unitaid, the United Nations Population Fund’s Supplies programme, and multiple other UN agencies. Despite these historical disbursements of PBR tranches, there was recognition that the evidence supporting PBR in multilateral contexts was not definitive.
“It wasn't a mature evidence base, so we didn't know too much about how it would work in this context.” (KII, FCDO)
The peer-reviewed evidence on the use of PBR in multilateral reform remains limited, and evaluating influence is difficult.13 As with other EQs, identifying definitive attribution to the CVC programme is impossible given the complexity of the dynamics of change and the multiple sources of pressure on WHO to deliver progress. As recognised by FCDO, PBR represents "one incentive in a complex system of incentives."14
Benefits provided by PBR
The evaluation identified a range of benefits associated with PBR. It created and sustained a cross-Whitehall process to define UK priorities for the WHO and served to clearly signal those priorities. A structured HMG-WHO Strategic Dialogue, with both senior and technical levels, discussed progress towards targets and some informants considered that this was a helpful platform for dialogue and deepened relationships. It was a mechanism to provide assurance to UK ministers and to wider UK domestic accountability channels that appropriate oversight was being applied. In the areas where targets were set, they could empower both WHO and FCDO thematic leads in their efforts to advance their agendas.
“I think it is a helpful way that the UK can indicate what is important” (KII, FCDO).

“That [PBR] really kept us on our toes, but it also helped to put pressure on the rest of the organisation. Because it's not just about our department’s funding. It's about funding to the organisation” (KII, WHO).

“(Top asks) helped to enable the directors to come directly to us to talk about their issues with senior management because they knew that I would have conversations at the higher level and that some of their grievances would be brought up…the staff in WHO valued having the spotlight on their technical area because for them they saw it as an opportunity to be heard.” (KII, FCDO)

Downsides associated with PBR
A wide range of downsides also emerged. Firstly, the way in which it essentially narrowed the dialogue to just five ‘key asks’ did not adequately reflect the full range of UK engagement and interest in the WHO and multiple priority areas could not be covered. This effect was exacerbated during the pandemic. As Table 5 shows, in the first year of the programme all five of the ‘key asks’ related to pandemic preparedness or health emergencies. This meant a reduced focus on organisational change metrics even though that was at the heart of the programme theory of change.
Some suggested that the focus on health security not only compromised engagement on organisational issues but also that the ‘key ask’ framework was not fit for the fast-moving nature of the pandemic policy engagement.

 “In COVID, the global reform conversation was so rapid that by the time that you'd set your top asks of the organisation, you'd come round to assessment and a lot of them were not that relevant anymore...Over time they shifted back to their original intent. We pivoted away and got a bit more of an FCDO footprint on them.” (KII, FCDO).

The transaction costs were very high on both sides. Initial objectives required agreement across HMG then approval by senior management and ministers. Objectives would then be negotiated with WHO, resulting in a revised proposal requiring approval by ministers on the UK side and the DG on the WHO side. The process was time-consuming.

 “That often took so long that you found yourself well into the reporting year in question before you had a finalised set of PBR objectives.” (KII, FCDO)

Additional transaction costs included disproportionate prominence and scrutiny compared to other programmes.

“It felt like you were constantly justifying the existence of the programme every six months as opposed to every four years.” (KII, FCDO)

Next, as flagged elsewhere in this report, the PBR element of the UK programme could not be included in the WHO flexible fund planning and budget process, as it was deemed a risk. This significantly compromises the reform and delivery benefits from the programme.

###### Table 5. Evolution Of Key Asks Over Time
2021	2022	2023
Scope and Design an Intermediate Public Health Alert (IPHA) and/or graduate alert system for health emergencies	Deliver at least 85% of planned budgetary support and activities through the UHC-Partnership programme	At least 85% of support through the UHC-Partnership to 40 countries implemented
An implementation plan for recommendations from the COVID-19 reviews agreed by Member States	Implement at least 80% of PRSEAH management response plan with 100% of implementation underway	At least 80% of the 2023 targets of the Three-Year-Strategy (3YS) Output Monitoring chart will be met and WHO will ensure adherence to the Accountability Framework for PRSEAH (once finalised in 2023).
Design of Universal Health and Preparedness Review (UHPR) mechanism	Publish a framework to strengthen clinical trials capacity building on lessons from COVID-19	Secretariat Implementation Plan (SIP) actions planned for completion by end-2023 are implemented
Progress Global Study of the Origins of SARS-CoV-2	WHO Pandemic Hub to ensure that International Pathogen Surveillance Network (IPSN) ready to start by end-2022	90% of Country Offices report performance through Scorecard exercise
Prioritisation of available resources - in light of COVID-19 to demonstrate how to achieve greater impact through a clear results framework	Publish reports of Scientific Advisory Group on Origins of Novel Pathogens (SAGO) within a month of delivery to the DG	3 targets from World Health Assembly (WHA) report to Member States

Health emergencies = Transformational change = Universal Health Coverage =
PBR pushed the WHO-FCDO relationship towards the transactional and away from the strategic. There were also instances of the negotiation process causing tension in the FCDO-WHO relationship.

“There was a lot of having to wait for people to calm people down internally because they were so furious at the UK for being what they felt was so demanding.” (KII, FCDO)

 “What it's achieved is it's probably added stress to everybody.” (KII, FCDO)

Many felt that a political decision to withhold the PBR tranche was unlikely given the wider relationship considerations between the FCDO and WHO. This eliminated the credible threat of enforcement which is a condition for effective PBR.

“From everything I saw, the decision was made well in advance to provide 100% of that PBR, even if WHO had failed on at least one category and possibly several categories.” (KII, FCDO)

Beyond these issues, other downsides flagged included that the negotiating process frequently reduced the level of ambition of targets to the point where they simply aligned with current progress and therefore added little value; that the framing of the PBR was in terms of downside risk rather than upside reward for good performance and; that the bilateral nature of the mechanism undercut efforts to strengthen institutional channels of accountability (such as through the governing bodies and collectively with other funders).

Overall, these concerns are consistent with the experience that is emerging from the growing evidence base around the use of PBR in multilateral settings. A 2020 FCDO study concluded that "Evidence suggests PBR had a marginal if any impact and has been costly in terms of management and relationship quality."13 Elsewhere it is found that the contribution of PBR in achieving programme outcomes is “marginal” and “there was little direct evidence of PBR changing behaviour, systems or outcomes.”12 A recent Independent Commission for Aid Impact (ICAI) report on the African Development Bank recommended discontinuing unilateral arrangements such as the Performance Improvement Plan, which included a PBR tranche.13
The evidence also suggests that PBR works best when core funding forms a substantial part of overall funding and UK burden share is high. While this strengthens the incentive, these conditions do not apply in this context. The CVC programme accounts for around 4% of the WHO base budget and 2% of total WHO programming.
Considering the counterfactual of 100% flexible funding
EQ8 asks what would have been different had the UK’s CVC funding been 100% flexible. This is a hypothetical and therefore cannot be answered concretely. However, a number of factors should be considered.
As mentioned elsewhere and above, the PBR mechanism significantly reduced the amount of flexible funding that could be used in the WHO budget and planning exercise (as compared to a 100% flexible model). The 30% PBR tranche was not included since it was ‘at risk’. This is a very significant factor which reduced the planning envelope of flexible funding at a magnitude of US$60m per biennium (which is significant at around 30% of the recent US$200m increase in ACs).
As noted elsewhere, FCDO policy and programme management capacity has been very scarce throughout the period. In the absence of the PBR, more time would have been available for other engagements, potentially in areas such as organisational reform.
“If we were not spending as much of our time on that we could have been spending it a bit more wisely elsewhere influencing” (KII, FCDO).
Nevertheless, the PBR has undeniably served as a means of providing assurance domestically of adequate oversight and accountability. In its absence, it is very likely that WHO shortcomings in reporting and communicating progress, such as the limitations of the CVC report, would have been more problematic and discussion on how to strike the right balance between flexibility and accountability would have been much more intensive.
“It's clear that WHO needs to have a reform agenda. There are significant weaknesses in their performance that need to be improved and if we just left that to flexible financing and just working on the General Programme of Work, I don't think we'd achieve those objectives.” (KII, FDCO)
The evidence highlights a rich set of ideas of alternative mechanisms for influencing multilaterals other than through PBR. These include:
- Strategic and coordinated use of multiple levels and modes of influence from the board- to country-level, and both formal and informal channels;
- Internationally acknowledged thought leadership and a solid evidence base on matters of policy concern;
- Sustained, long-term, technical engagement from respected and well-qualified technical staff; including secondments;
- A limited number of key policy objectives over the long-term;
- A reciprocal and partnership-based approach to the relationship, as opposed to a transactional one; 34
- Sustained coordination with other important donors on key issues;
- Strategic catalytic funding through additional VCs and engagement. 13

These ideas have been used to develop a number of alternative mechanisms to enhance UK influence and accountability in any future UK flexible funding programme. They are assessed in the Recommendations section.

Relevant recommendations
Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. [#6] / Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. [#7] / Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted funding to UK high priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement. [#8] / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders. [#11] / FCDO roles. Ensure clearer delineation and understanding of roles between WHO Hub, UKMIS Geneva and other relevant HMG focal points. [#12]

## Did the programme contribute to the wider sustainable funding agenda?

Relevant EQs
EQ9. How well has the UK approach to funding the WHO aligned with other donors' funding practices and has it led to an improved funding environment for WHO?

Key findings / The UK is a significant outlier in relation to other donors in terms of the way it funds the WHO. / There have been positive developments in WHO flexible funding in recent years. AC reform is the obvious example but progress on CVC should not be underestimated. / FCDO advocated less with other donors around flexible funding than originally envisaged. There is a striking lack of awareness among the wider set of key informants on the scale of UK CVC funding and how critical it is to the flexible funding agenda.

As set out in the responses to EQ4 and EQ10, there is strong consensus around the need for an increase in the level and share of flexible funding to the WHO. This consensus has underpinned the recent landmark agreement to steadily increase the level of ACs over the course of this decade. The CVCA is a channel that allows donors to contribute additional flexible funding over and above their AC level. The UK’s CVC programme does this and is therefore strongly aligned with WHO’s needs and requests. Despite the broad-based consensus on the importance of flexible funding, the UK remains a significant outlier in terms of its CVC contributions, as shown in Chart 12.
Chart 13 illustrates how the UK pattern of funding differs from other donors. The UK’s CVC funding accounted for 58% of its total WHO funding in the 2022/23 biennium. When the UK’s AC funding is added (11% of the total), the share of flexible funding in total UK funding to WHO is 69%. Among all funding contributions to the WHO, CVC and AC account for just 5% and 12%, respectively.

The increase in ACs combined with the rise in CVC and increased PSC associated with higher overall VCs has pushed flexible funding above US$2bn for the 2024/25 biennium (see charts in section EQ5/EQ7). UK CVC contributions were greater than all others combined in both 2020/21 and 2022/23, as shown in Chart 14.

###### Positive developments in CVC funding

The scale of the UK contribution can easily mask some positive developments in CVC funding in recent years. The number of donors contributing more than US$4m per biennium rose from 7 to 12 since 2018/19, as shown in Chart 15. Germany entered as a new funder contributing US$34m in 2022/23, while France, Spain, Switzerland and Ireland also increased their contributions significantly in recent years, albeit at lower levels. Sweden, Australia, Netherlands, Denmark, Norway and Belgium remain consistent funders.

###### Factors that influence donor contributions

Nevertheless, there are significant barriers to donors shifting their funding practices. The literature highlights that persistent preferences for Specified VCs are influenced by a range of factors that apply to all donors including:

Desire for tangible results: Some donors have to demonstrate results which they can attribute to their funding.40

Desire to increase influence: Specified VCs can provide privileged access to information and influence. The existing funding system and culture within WHO encourage Member States to earmark funding. As long as such practices exist there will be an incentive for governments to continue providing earmarked contributions.40 According to one interviewee from a separate study:

“If you don’t earmark [...] then you tend to know less about what’s going on, you tend to have less access to Secretariat information...So that’s interesting because in one way, they [WHO] say, ‘Please give us less earmarked money,’ and then on the other hand, if you have this programme on maternal health that is a high priority of theirs, only those who give specific money are invited [to the meetings]”39

Potential consequence of the one Member State, one vote governance model: Since each member state has one vote, there is no obvious benefit in formal governance in terms of investing more in core funding. Most donor countries therefore opt for specified VCs to complement their ACs rather than additional flexible funding. High-income countries and donors based within them provided 90% of VCs in 2020.36 Non-state actors outside the formal governance system also prefer specified VCs, as demonstrated by the Gates Foundation. In some biennia, Gates provided the WHO with more funds than the US and China combined.27

Behaviour of other donors: The decisions of larger countries, such as the US, can set the tone for smaller countries.40 It is probable that this effect could work in reverse. If a coalition of ‘like-minded’ countries were willing to seriously shift to unearmarked funding, a positive crowding-in effect could be created.40

Lack of transparency and trust: The practice of earmarking funds can be understood as an indication of a lack of trust in the operational, delivery and reporting capacity of the organisation as a whole, which manifests itself in a decision to ring-fence as a risk management strategy.48
Specific factors drive individual country choice over funding modality. In the US, congressional earmarking rules out US participation in CVC. In contrast, the Netherlands commits to providing a minimum of 30% of its contributions to WHO, as well as other UN and humanitarian agencies, in flexible funding in line with the UN Secretary-General's funding compact.
Among those close to the WHO funding debate, the prevailing view is that the UK CVC programme has been influential in encouraging other donors to shift towards greater flexibility. However, there is a stark lack of awareness among the wider set of key informants on the scale of UK CVC funding and its criticality to the flexible funding agenda.
FCDO advocated less with other donors around flexible funding than envisaged in the Business Case. This can be attributed to the limitations of capacity in the FCDO Hub and the extensive turnover in SROs. Additionally, the demands of the pandemic (with virtual meetings replacing the informal opportunities for influence that go with in-person forums) and the post-pandemic period competed with WHO-related policy agendas and priorities. Several voices felt that greater UK advocacy with donors would be beneficial, for example with parliamentary committees in Germany.
2024 will be an important year for CVC and the wider flexible funding agenda, with optimism around the Investment Round planned for later in the year. While informants pointed to signs of movement in several key countries, there are also significant risks. Political changes in many countries are not helpful to the WHO's flexible funding agenda, especially with upcoming elections in 2024. Additionally, there is competition for health resources with a range of replenishments on the horizon.

Relevant recommendations
Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders as part of the Investment Round offer. This could be as part of a wider major funder engagement approach that could also include some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return. [#4] / Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round. [#5] / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders. [#11]

## How did the programme impact on UK influence in WHO?

Relevant EQs
EQ11. To what extent has CVC funding to the WHO changed the UK’s influence vis-à-vis WHO and how?

Key findings / The programme may have enhanced UK influence with WHO’s leadership, however non-financial factors, such as political engagement, are equally or more important. / The programme complicated UK engagement in thematic issues but many policy leads managed to retain influence. / At all levels, the degree of UK influence depends on more than just financing instruments. Technical expertise is particularly critical. / A more structured WHO approach to communicating and reflecting the role of CVC funders across the organisation, particularly at country-level, is needed.

###### Evidence supporting increased UK influence
A key factor driving programme design was the perception that UK influence in WHO had diminished. This was due to the fragmented and uncoordinated nature of HMG programmes supporting multiple WHO departments in different areas:
“My key lesson [from the 2016-20 programme] was that we were still not having the level of strategic influence we wanted in WHO” (KII, FCDO)
The consolidation of different funding vehicles into a single programme, accompanied by an overarching framework for policy prioritisation and dialogue intended to enhance UK influence, particularly on reform.
“The idea was that this would give us a significant amount of influence...we would then be able to really drive forward the reform and really demand and get better understanding of the reform and really help influence where we wanted WHO to be taking action.” (KII, FCDO)
Informants on all sides felt that the CVC added to UK influence with WHO leadership. Contributing factors include its significant contribution volume and responsiveness to WHO requests.
“It gave it outsized influence and it gave that first mover advantage. By moving, the UK captured the high ground right on flexible financing and championing WHO. It gives the UK a very strong platform to operate in both the governing bodies and with the organisation” (KII, WHO)
“As a major CVC funder, I think maybe it gave us more access at the top of WHO. Because it's a single headline funding figure and...because we're also responding to a specific call from Tedros to Member States” (KII, FCDO)
###### Evidence supporting reduced UK influence
Nevertheless, there were voices asserting that UK influence was reduced. The long-term, predictable, flexible nature of the programme meant that the UK funding was considered ‘banked’ by WHO leadership.
“I think you never really got from WHO the sense that okay, you’re our biggest flexible financier and we are going to take you very seriously. Instead, what you got is okay well, that's the UK money secured and now we're going to worry about X, Y and Z from other donors.” (KII, FCDO)
The risk associated with flexible funding is the weakening of influence and control over policy and funding choices. This is especially true in a context where many others are providing tightly earmarked funding linked to requests for WHO.
“If you don't put strong incentives but someone else does put strong incentives, your money can be used to meet the strong incentives...because they'll know that you're going to keep paying...So they're not very strongly obliged to meet your grant objectives, but they do have these very hard objectives from someone else.” (KII, independent)
Other factors affected high-level UK influence at the centre of WHO, including the level and intensity of political engagement.
“If you don't have the political engagement behind those UK priorities, which we didn't have for quite a while for lots of very good reasons, then impact will always be limited. So, you have Macron and Merkel and a whole host of others regularly on the phone to Tedros. But you didn't have that coming from ministers in the UK.” (KII, FCDO)
The impact of the programme on UK influence at the thematic level was perceived as negative by some.
“The influence we had originally when we were running a project was very good...We could influence things. Maybe it was a bit anachronistic but because we had the project-type influencing and also quite good technical capacity, we could influence. Because other countries putting more resources in didn't have the same technical capacity, we could leverage their funds as well.” (KII, FCDO)
“I think it's fair to say that there were some challenges in engaging with WHO around this shift to core flexible funding away from what we had. Some in WHO felt and still feel that we walked away from investing in specific areas even though we're putting in our money, as part of the strategy requested by WHO, into flexible financing. That has affected some of the more official-level relationships and also our ability to influence WHO at the policy level.” (KII, FCDO)
Many stressed that programme funding is not the sole mechanism for UK influence on thematic areas. UK expertise together with long-standing relationships and trust also contribute to thematic influence. In many thematic areas, leads adjusted to the new conditions with their influence intact (with successful WHO delivery depending on required funding flowing from other donors). This was especially true among FCDO leads with longer tenures and strong track records on thematic funding. Among new policy leads, influence was more challenging.
"That influence depended on existing relationships and trust...That's partly because those relationships have been built up over the years of financing directly to that department.” (KII, FCDO)
UK expertise and relationships are the dominant drivers of influence.
“There was no designated financing, but the UK was remaining involved and playing an even bigger role in many ways and no loss of influence whatever in what was a high priority area” (KII, WHO)
“I'm not talking to FCDO because they give us money. I'm talking to them because they have expertise or they have been on the journey longer than us” (KII, WHO)
The impact of the CVC programme on UK influence at country-level is not significant. There is little awareness of the programme within countries as flexible funding represents a small share of country-level funding. Further, mechanisms are not in place – either on the WHO or FCDO side – to communicate the importance of flexible funding, and the UK’s role in it, to the country-level. As no individual UK funding programmes ended or consolidated into the central CVC programme, the direct country-level impact of the programme was not meaningful. WHO influencing efforts by FCDO officials at the country-level would benefit from a stronger link to the central funding.
“Within the country we really had very little influence to say to WHO ‘We are a core contributor, we have questions around performance, capabilities’ etcetera. There was no mechanism for us to link [with the CVC programme].” (KII, FCDO)
The link to country-level engagement and influence is a perennial challenge associated with other large-scale multilateral health contributions.
“It's really frustrating because from our director’s point of view, we're spending big money on WHO, on Gavi, on the Global Fund but you get down to the missions and the Head of Mission isn't aware that a huge amount of UK money is being spent in that country.” (KII, FCDO)
Overall, it is widely recognised that the UK is highly influential and has much to offer the WHO agenda beyond funding.
“The UK is an extraordinary country in terms of the technical expertise that it brings to the global health agenda, the experience that it brings, the footprint that it has in so many countries that are important to us.” (KII, WHO)
Better communication and coordination on both sides could help harness the UK offer across policy areas and in country-level dialogue.
“I think it's about the allocation model being really clear and the internal communication around how the UK funds WHO to be really clear across all the different teams so that we can continue to have that influence.” (KII, FCDO)
Relevant recommendations
Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round. [#5] / Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. [#6] / Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted funding to UK high-priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement. [#8] / FCDO/WHO Dialogue. Widen and regularise Strategic Dialogue on an annual basis and spanning the full range of institutional reform, policy priorities and opportunities for review of the targeted funding. [#9] / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders. [#11]

## What was learned from the results approach?
Relevant EQs
EQ12. To what extent has FCDO used the information gathered through the WHO Results Framework?
EQ13. What are the lessons learnt from the approach to MEL?

Key findings / The WHO Results Framework is set at too high a level and provides too little detailed information at the country level. In its current format, it cannot be used by FCDO for decision-making about its CVC funding programme. WHO’s proposed improvements to results reporting, which have yet to materialise, will be welcome. / FCDO’s MEL approach to its CVC programme is centred on monitoring achievement of the key asks which are generally not linked to WHO’s reform agenda. This means that FCDO (and other donors providing flexible funding) cannot clearly demonstrate the impact of flexible funding on outcomes. This risks discouraging other donors from providing new and/or increasing existing levels of flexible funding.

The utility of the WHO’s Results Framework for MEL of the CVC programme is limited. In the 2021 Annual Review, FCDO committed to reviewing its approach to assessing the CVC programme, including incorporating the WHO Results Framework into the scoring.15 This has not materialised, as the results framework is not suitable for FCDO to use for MEL of CVC programme performance. In its current form, the Results Framework is too high level and provides insufficient information about reform, particularly at the country level.
“The problem with the Global Programme of Work, it’s very high level. Most of those results are very, very high level in terms of, for example, the three billion.” (KII, FCDO)
“I think over the course of the CVC, there’s been so much change and [the] WHO results framework hasn’t bedded in. And I think it’s a really complicated framework and in particular it is really difficult to understand the reporting at the country level. So, I’ve found that [it’s been] almost impossible to get any really good data or snapshots of performance at the country level.” (KII, FCDO)
Moreover, there are questions about the relevance of the impact results reported.90
FCDO’s MEL of the CVC programme focuses on monitoring achievements of the ‘key asks.’ However, these do not reflect WHO’s progress on the broader reform agenda. The limited utility of the Results Framework and lack of a logframe means that monitoring data on the CVC programme funding rounds is restricted to achievements against the ‘key asks.’ While some monitoring data for the ‘key asks’ is relevant, they do not directly reflect the WHO Results Framework and are an insufficient proxy for tracking progress against the institutional reform agenda (which is the objective of the CVC programme).
In order for MEL of the CVC programme to better focus on progress against the reform agenda, WHO needs to articulate the pathways to reform more clearly (e.g. in providing a more detailed Theory of Change accompanied by clearer metrics). This will enable the UK to draw out indicators to measure the impact on reform rather than creating new definitions. The desire to work within WHO’s own MEL systems to avoid creating an additional burden on WHO was emphasised in FCDO’s 2022 Evaluability Assessment of the UK CVC 18,127, as well as echoed by an informant:
“And…my biggest thing is that we should be aligning logframes with the general reporting systems, however, weak they are…I think one of the issues we have with our reporting…is our reporting periods often do not align with WHO reporting periods.” (KII, FCDO)
The Evaluability Assessment of the UK CVC suggested strengthening the Annual Review by focusing on broader outcomes/results, rather than performance by indicator. 18 However, shortcomings in WHO’s MEL structures, including challenges with the results framework and a lack of Output Scorecards, constrain FCDO’s ability to do this.
In response to stakeholder requests, WHO proposed initiatives to generate more detailed country level results. The 2021 Annual Review identified the need to improve the WHO’s Results Framework and recommended that WHO publish more granular results at the country level and/or by sub-units of thematic departments. The Annual Review also recommended publishing country-level scorecards, 15 of which WHO committed to providing by 2022 (a commitment not yet fully met). This need was underscored by FCDO in the interviews.
“By and large, we failed to measure impact at the country-level, and it wasn’t for lack of trying. It was the incredibly difficult business of navigating down through the three levels of WHO and understanding how CVC funds injected in Geneva cycle down through the regions and to Country Offices and how that led to improved country performance.” (KII, FCDO)
The 2022 Evaluability Assessment of CVC Funding to WHO 18,127 noted that the lack of country-level Scorecards is problematic. Without Scorecards, countries with slow or stagnating progress will not be identified (publicly available information is only at the regional level). This limits the ability of FCDO Country posts to “hold WHO Country Offices to account effectively for the achievement of results.”18 There is great interest among donors in the Output Scorecard initiative, which was seen as a “major step forward in how the organisation is delivering its outputs,”63 and was anticipated in the FCDO’s 2022 WHO Evaluability Assessment to be a “key evidence source for assessing the success of the CVC.”18 There has been some progress in delivering this initiative at the WHO HQ level, but less beyond. This is a gap also noted in the Evaluability Assessment.
“There’s a much more intense focus now amongst FCDO to try and look at what the outputs of GPW14 are because it’s all very well having these multiple billions at the outcome level…but we’re taking a much harder look at actually the output. What will WHO actually deliver here?” (KII, FCDO)
More information is needed on how flexible funding contributed to reform progress. Information on WHO’s progress against its reform agenda, and how flexible funding contributes to it, is limited. Several respondents noted the difficulties in obtaining such information.
“It’s actually very difficult to tease out WHO’s value add…How do you really articulate what you did that made this change?” (KII, FCDO)
“I think [WHO]…at times didn’t feel it could cope with flexible funding because it couldn’t articulate the impact it was having…in a way that it could sell that to donors.” (KII, FCDO)
Some informants maintain that flexible funding inevitably means donors must accept less detailed reporting.
“We accept that because we are giving flexible funding that we can’t know the level of detail that you would on an earmarked, you know, outcome/output-based reporting…[WHO] can’t possibly give us the detail we would love to have, but that’s the price we pay for being a flexible funder.” (KII, Donor)
“The principle of supporting the flexibility of funding for WHO means that we relieve WHO of the burden of reporting in detail against its grant.” (KII, Donor)
More visibility on the impact of flexible funding on outcomes, especially among donors, is needed to justify increases in flexible funding contributions to the WHO. This is acknowledged by the WHO, which they have attempted to address in the CVC report but, as described in Section B, the scope and level of detail in the report is insufficient.
“WHO needs to do a much better job in reporting how we’re impacting change in the country.” (KII, WHO)
Improved MEL capacity is also required on the FCDO side. Capacity constraints, exacerbated by the FCDO merger, were noted during interviews as a factor contributing to weak results monitoring.
“There’d been an intention to kind of build in a MEL approach. And then by the time I came into the job, ...everything was just very far behind. And it’s because of some of the internal dynamics at FCDO around turnover of SROs.” (KII, FCDO)
###### Relevant recommendations
Reporting. Encourage WHO to integrate CVCA reporting into a wider flexible funds-reporting approach. [#2]

Results. Push WHO to develop clear metrics for success in funding and reform, particularly in terms of country performance. These should be integrated into the GPW14 results framework which currently does not cover this area. [#3]

Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders as part of the Investment Round offer. This could be as part of a wider major funder engagement approach that could also include some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return. [#4]

Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. [#6]

Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. Excluding PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. [#7]

Monitoring, Evaluation and Learning (MEL). Consider retaining an external MEL provider to monitor progress (both financial and performance metrics) on an ongoing basis as part of any future programme to support oversight, accountability and dialogue. [#13]
# 5. Key Findings and Lessons

Overall, the evaluation found that the design of the overall programme was fully aligned with the FCDO’s objective of strengthening WHO institutional performance to enable it to better deliver global health leadership and impacts. The consolidation of funding into a single, large-scale funding envelope to the Core Voluntary Contributions Account (CVCA) represented an evidence-based, principled and forward-looking approach. It responded to WHO needs and requests for greater flexible funding to better advance global health goals.
The evaluation also found a clear-eyed recognition by FCDO in the programme design of the risks and potential challenges associated with the transition to a model which, in broad terms, traded off greater flexibility for WHO to pursue reform and delivery for reduced direct control and accountability around the use of UK funding.
A range of mechanisms were put in place to mitigate these risks and to manage the transition. Annual funding was structured into a core element (70%) and a PBR tranche (30%) that was conditional on the delivery of five key policy asks agreed on an annual basis. A Strategic Dialogue mechanism was created, consisting of a senior ministerial/DG level and a technical level, as a forum for structured engagement around the full set of UK priorities and WHO performance. Cross-FCDO and cross-Whitehall mechanisms were created to strengthen HMG coordination and it was agreed to expand the WHO Hub within FCDO to strengthen capacity for policy engagement, oversight and advocacy with other funders. A senior secondment into the WHO was also envisaged as well as complementary investment in MEL activities to help guide implementation. Evaluating the secondment was out of the scope of this evaluation.
The programme has been implemented against a challenging backdrop. The demands of dealing with the COVID-19 pandemic placed an intense burden on WHO staff and distracted attention from reform. It also led to a very heavy, and ongoing, policy agenda around health security that continues to demand significant capacity within both WHO, FCDO and the wider UK government. Further, the already complex dynamics of WHO transformation were added to by a wide range of additional funding and organisational reform initiatives. On the UK side, the creation of FCDO meant significant restructuring that led to fluctuations in staffing and capacity in the FCDO team. This, together with wider domestic UK political factors, also meant a lack of continuity in UK ministerial responsibility for the relationship with WHO and this programme.
These issues all complicate evaluation. Shortfalls in reporting and communication, as well as mismatches in expectations, have also led to a wider variety of different views on the programme. These emerged strongly in the KIIs and other evidence sources and are covered in more detail in this report. However, these factors should not obscure the fact that since the start of FCDO’s programme, there has been a step-change in WHO’s flexible funding agenda. The agreement to increase ACs was a landmark decision, and CVC funding has also risen significantly. The UK has been the single biggest contributor by far, but the number of other donors has also risen, as has the volume of their funding. The FCDO programme played an important role in the progress of the flexible funding agenda and the 2024 Investment Round will be a critical point to build on that momentum.
Analysis shows that this increased flexible funding has been deployed by WHO in support of agreed organisational strategic objectives, principally the objective of transforming the technical capacity of Country Offices. It has also allowed for corporate priorities, such as stronger PRSEAH to be effectively advanced. Progress on WHO reform (e.g. on budget, Country Office transformation, results reporting and HR) required to harness the benefits of flexible funding has been slower than needed and should have been faster. But a strong platform is now in place, promising accelerated progress in the 2024/25 biennium and beyond into the GPW14 period.
The evaluation therefore concludes that the UK approach to transition the large majority of its funding to the flexible CVC funding was strongly supportive of WHO transformation and wider UK global health objectives. Additional benefits included a contribution to enhanced UK influence in WHO, at least at the leadership level. The programme provided, through the ‘key asks,’ a clear narrative for UK domestic accountability purposes. The consolidation of funding streams also reduced overall programme financial management burdens. However, a wide set of further findings and learnings were also identified:

- The costs of the PBR mechanism exceeded its benefits. It did serve to clearly signal UK priorities and supported UK domestic accountability. However it involved very heavy transaction costs, significantly constrained the availability of flexible funding for WHO planning, represented too small a share of total WHO funding to shift behaviour caused tensions, and at times focused the FCDO-WHO relationship on transactional issues at the expense of strategic priorities and lacked the credible threat of enforcement.
- The key asks associated with the PBR mechanism proved to be too narrow to accommodate the full range of UK priorities (particularly in the context of the pandemic).
- The transition away from direct UK funding to individual thematic areas was abrupt and complicated UK influence and engagement in some cases, as well as compromising WHO performance. The situation was exacerbated by mismatched expectations on both sides as to the extent to which UK CVC funding would replace discontinued direct programming.
- The UK remains a very significant outlier in terms of how flexibly it funds the WHO. While others certainly have stepped up and the overall picture is more positive than many perceive, faster progress was expected. FCDO engaged much less actively on this agenda than envisaged.
- There is a striking lack of visibility and awareness beyond those closest to the issues around the scale of UK CVC funding, its criticality to the flexible funding agenda and the leadership that it is showing.
- The programme has not yet meaningfully affected the nature of engagement of FCDO with WHO at the country-level. The scale of FCDO support is not leveraged to improve FCDO access and influence at this level.
- WHO arrangements and systems for reporting and accountability to flexible funders fell short. Reporting in terms of the use of CVC funds alone was misleading. Flexible funding overall is a more appropriate unit of account. Beyond that, the metrics for capturing progress on organisational reform, particularly at the country-level are inadequate. The GPW Results Framework was set at too high a level to be used by FCDO for oversight. This means that FCDO (and other donors providing flexible funding) cannot clearly demonstrate the impact of the flexible funding they provided.

The findings of the evaluation are summarised in Table 6 below.

###### Table 6. Summary of Key Findings
Did the UK deliver inputs coherently?
EQ 1 / EQ 2 / EQ 3	The design of the overall programme is coherent in support of FCDO’s aim of strengthening WHO institutional performance. The design also manages the range of risks associated with the transformation in channels of accountability, influence and funding of activities. / The approach has reduced programme management costs and brought a clearer articulation of top UK priorities. However, several factors, from both inside and outside the programme’s sphere of control, have also limited effectiveness gains and the rapid transition to a new model created problems. / Looking ahead to a future programme there are several options for design that could strike a better balance between supporting WHO performance while also maintaining UK influence and assurance.
Did the programme design respond to WHO needs?
EQ 4 / EQ 10	The design of the UK’s CVC programme aligns very strongly with WHO needs and requests. / The shift to flexible funding, in particular, responds directly to WHO’s challenging financial landscape and is a necessary (though insufficient) condition for strengthened institutional performance. / The PBR element of the programme is more problematic. WHO considers the UK’s PBR tranche ‘at risk’ meaning the PBR mechanism significantly reduces WHO’s budget and planning space.
Did the programme support WHO reform and delivery?
EQ 5 / EQ 7	Multiple factors mean that a definitive answer to these questions is not possible, and there is a striking divergence of views between those in and outside WHO. However, there is good evidence that the WHO approach to deploying flexible funding has been strategic and further improvements have been made. / Assessing and reporting the use of CVC on a standalone basis is misleading. Flexible funding overall is a more appropriate unit of account and oversight. / The deployment of CVC funding was not well communicated and did not match the expectations of many in FCDO, particularly technical leads. / Sustaining support will depend on a much more effective definition and communication of results.
Did the PBR component contribute towards the overall programme goals?
EQ 6 / EQ 8	Attributing effects to the PBR component is impossible given the complex dynamics of change and the multiple sources of pressure on WHO to deliver progress. / Benefits in terms of UK domestic accountability and priority signalling were identified. A wide range of downsides, including high transaction costs and restrictions to WHO on the deployment of funds, were also identified. / The evidence suggests that PBR can accelerate progress on multilateral reform or policy priorities only in specific conditions. These conditions are not met in this context. / If the UK had not used a PBR component, more flexible funding would have been available for WHO’s budget and planning exercise. However, in this counterfactual, FCDO would also have lacked a narrative on accountability.
Did the programme contribute to the wider sustainable funding agenda?
EQ 9	The UK is a significant outlier in relation to other donors in terms of the way it funds the WHO. / There have been positive developments in WHO flexible funding in recent years. AC reform is the obvious example but progress on CVC should not be underestimated. / FCDO advocated less with other donors around flexible funding than envisaged. There is a striking lack of awareness among the wider set of key informants on the scale of UK CVC funding and how critical it is to the flexible funding agenda.
How did the programme impact on UK influence in WHO?
EQ 11	The programme may have enhanced UK influence with WHO leadership, however non-financial factors, such as political engagement, are equally or more important. / The programme complicated UK engagement on thematic issues, though many policy leads managed to retain influence. / At all levels, the degree of UK influence depends on more than just financing instruments. Technical expertise is particularly critical. / A more structured WHO approach to communicating and reflecting the role of CVC funders across the organisation, particularly at country-level, is needed.
What was learned from the results approach?
EQ 12 EQ 13	The WHO Results Framework is set at too high a level and provides too little detailed information at the country level. In its current format, it cannot be used by FCDO for decision-making about its CVC funding programme. WHO’s proposed improvements to results reporting, which have yet to materialise, will be welcome. / FCDO’s MEL approach to its CVC programme is centred on monitoring achievement of the key asks which are generally not linked to WHO’s reform agenda. This means that FCDO (and other donors providing flexible funding) cannot clearly demonstrate the impact of flexible funding on outcomes. This risks discouraging other donors from providing new and/or increasing existing levels of flexible funding.

Looking ahead to a future programme, these findings generate a number of options to strike a better balance between the different objectives. These are set out in the following section.
# 6. Recommendations

The previous section set out findings and lessons. This section draws on the lessons learned to consider options for how to optimise the programme design in support of objectives. A simple framework is used to assess those options and generate recommendations for consideration.
The framework bundles objectives into two dimensions. First is ‘support for WHO reform, delivery and reporting.’ This is the fundamental goal of the CVC programme and underpins the rationale for providing flexible funding in the form of CVC. It is a measure of the extent to which funding supports WHO’s institutional performance and ability to measure that performance. Secondly, funders also require effective oversight over the use of their funds and assurance that they are used properly. They are also interested in the level of control and influence over WHO activities that their funding provides them. The framework bundles these factors together as ‘donor influence, oversight and assurance.’ Chart 16 views funding WHO through this lens. The bubbles capture the relative magnitude of total WHO funding. ACs are highly flexible but offer relatively low control and assurance to donors given the fragmentation in budget and reporting. At the other end of the scale, specified VCs are tightly earmarked to donor preferences but unsupportive of overall institutional reform and delivery.

Some wider conclusions can be drawn from the framework. The first is that the attractions of Specified VCs are clearly much greater to funders than CVC. The reasons for this are set out elsewhere in this report, for example under the response to EQ9. A central challenge for WHO is to extend the appeal of flexible funding channels, like CVC, for donors. As Chart 17 shows, CVC currently only fits the preferences of a small portion of funders and of potential funding. The challenge is to extend the appeal to cover a much larger share of potential funding.

Table 8, later in the section, contains recommendations that include actions (Recommendations 1-5) that are mainly for WHO and would contribute to making CVC a more attractive channel for funding. This is the ambition of the WHO and is part of a wider sustainable funding agenda that seeks to strengthen the performance of all funding modalities while also progressively shifting a greater share of funding into flexible channels. Chart 18 illustrates this comprehensive sustainable funding and reform agenda.

The UK would benefit from this agenda as it enhances both impact of flexible funding, as well as assurance around it. In addition, the UK needs to consider the design of its own programming and its overall portfolio of WHO funding. Chart 19 shows the composition of current UK funding (using latest available figures from 22/23). It represents a sharp contrast with the overall pattern of funding and shows that the UK prioritises WHO reform and delivery and is willing to trade off a level of direct control in support of that longer-term transformational objective.

The evaluation has found that the UK approach to providing such a significant share of its funding in the form of CVC is strongly supportive of WHO transformation. That overarching approach should be maintained. However, the evidence also suggests that there may be better ways to achieve the desired levels of UK influence, control and assurance. As stated above, a range of WHO actions in strengthening the management of flexible funding will help. But FCDO should also consider alternative elements for its own programme design. Table 7 assesses a number of options, including the existing programme model (marked as Option 1 in the table) against a number of criteria. The table also assesses a number of non-PBR models, including the 100% core model which is covered in EQ8 (Option 3), the fully earmarked model (Option 2), as well as other design options that informants proposed during the course of the study. These include allocating a portion of funding as Thematic VCs (Option 6), holding back a portion (10-20%) for investment in initiatives in UK priority areas (Option 4) and retaining a smaller hold back for ‘catalytic’ technical activities (Option 5).

Table 7. Relative Benefits Of Different Mechanisms To Balance Programme Design Objectives
Design objective 1. WHO reform, delivery & results
Design objective 2. UK influence, oversight and assurance

As the scoring in Table 7 shows, the current model (Option 1) scores strongly with the exception of its narrowing effect on policy engagement, the constraints it poses on the UK's ability to support thematic priorities and the limited line of sight it provides into UK-funded results. Most of the other options have serious downsides in one or more areas that rule out their viability. A fully earmarked model (Option 2) would have huge transaction costs, would give a strong signal from an influential donor about a lack of confidence in WHO and, more importantly, would serve to undermine WHO institutional performance. A 100% core funding model (Option 3) could not deliver the accountability needed. The use of thematic VCs (Option 6) would seem unattractive since it risks leaving donors with a scattered portfolio of activities and results. Further, it is not an approach that would obviously provide additional flexibility for the UK to respond to emerging priorities. This is because, while the high-level theme is determined by donors, the precise allocation is determined by WHO. All that said, there may be scope for flexibility in thematic VC design that could be explored and negotiated. If so, the case for some targeted use of thematic VCs may become stronger.
[note] Thematic Voluntary Contributions are earmarked by donors for use in broad thematic areas – essentially global programme budget outputs or higher. An internal WHO process then determines the detail of how funds will be used within that thematic area. WHO then reports back to the donor on the detail of how funds have been used. Thematic VCs provide more flexibility to WHO because it can allocate them to priority or unfunded areas within the agreed programme budget. However, the reporting burden can be as significant as it is for specified VCs and activities reported to donors can appear fragmented since the context of the overall budget that is required to make sense of the allocation decisions is not clear. Thematic VCs may be a more useful tool for funders committed to reducing the share of specified VCs in their portfolio, rather than for funders, such as the UK, who are already committed to flexible funding.
Nevertheless, the two ‘hold back’ models that retain a portion of funding are more promising. Of these, the model (Option 4) that envisages 10-20% of total programme funds being invested in UK priority areas is preferred. The funding would support WHO-led activities and programmes (rather than WHO-hosted partnerships) and would allow for larger-scale support for UK priorities in a strategic, multi-year manner, with a clear line of sight into UK-supported results. The concern with a smaller-scale catalytic fund (Option 5) is that transaction costs could be high and predictability low. Based on this analysis, Table 8 includes Option 4 as a recommendation, alongside the fuller set of recommendations, that are drawn from the evaluation. Together these recommendations have the potential to strengthen both ‘WHO reform, delivery and results’ as well as ‘UK influence, oversight and assurance’. Annex 6 includes an indicative Theory of Change based on a programme that reflected these recommendations.
[note] Option 4 envisages 10-20% of funding being allocated in the form of multi-year commitments to UK priority areas where funding gaps exist and where the UK does not have dedicated programming in place. Allocation would be determined at the beginning of the programme based on a systematic analysis of UK priorities and WHO roles, capabilities and funding gaps. These complementary, targeted funding flows would provide the UK with the ability to support specific policy areas and strengthen UK influence and engagement in those areas. Precise funding modalities would need to be determined. Option 5 envisages a smaller share of the programme being held back for smaller-scale, catalytic interventions in support of specific technical needs in priority areas. The modalities for management and delivery of these interventions would need to be determined.
###### Table 8. Evaluation Recommendations
Recommendations
Strengthening WHO Reform, Delivery and Accountability	Flexibility. Continue to provide the large majority of the UK’s support to WHO flexibly into the future to support ongoing reform and delivery. / Reporting. Encourage WHO to integrate Core Voluntary Contributions Account (CVCA) reporting into a wider flexible funds reporting approach. / Results. Push WHO to develop clear metrics for success in funding and reform, particularly in terms of country performance. These should be integrated into the GPW14 results framework which currently does not cover this area. / Accountability. Work with WHO to propose a stronger collective mechanism for accountability to, and oversight by, flexible funders as part of the Investment Round offer. This could be as part of a wider major funder engagement approach that could also include some kind of ‘flexible funding friends’ group and clarity in the Investment Case that flexible funding delivers a higher return. / Communication. Engage with WHO to ensure that key flexible funders are better recognised both internally (especially with thematic leads and country offices) and externally and that their access and engagement around policy dialogue reflects their contribution. This should form part of the donor offer at the Investment Round.
Strengthening UK Influence, Oversight and Assurance	Logframe. Reinstate logframe with multi-year reform and policy targets aligned to WHO indicators to deliver a longer-term perspective across a wider set of priorities. / Drop PBR. Exclude PBR from the future programme. The costs of PBR were found to exceed the benefits. The exclusion of PBR would still allow FCDO to retain the right to cease or pause funding in the event of serious concerns. / Targeted ‘holdback’ funding. Use 10-20% holdback to provide targeted[i] funding to UK high-priority thematic areas that could benefit from an additional boost/or catalytic stimulus. These would be identified via a systematic process and provide more direct channels for UK support and engagement. / FCDO/WHO Dialogue. Widen and regularise Strategic Dialogue on an annual basis. spanning the full range of institutional reform, policy priorities and opportunities for review[ii] of the targeted funding. / Coordination. Reinvigorate internal FCDO and HMG coordination mechanisms to ensure the establishment of clear policy priorities, a clear management strategy, and the engagement of the FCDO country network. / Human Resources (HR). Invest in greater HR (potentially in Hub) for engagement in WHO funding and reform agenda. This should include proactive dialogue with like-minded and potential flexible funders. / FCDO roles. Ensure clearer delineation and understanding of roles between WHO Hub, UKMIS Geneva and other relevant HMG focal points. / Monitoring, Evaluation and Learning (MEL). Consider retaining an external MEL provider to monitor progress (both financial and performance metrics) on an ongoing basis as part of the future programme to support oversight, accountability and dialogue.

[i] This is not a recommendation for tightly earmarked VCs, it would be more targeted, multi-year funding in support of WHO work in priority areas. Precise modalities would need to be determined.
[ii] This review would be against whatever regular reporting the Department/Unit would have to do in its normal systems/procedures. The idea would not be to add to WHO’s reporting burden.

Chart 20 returns to the framework and sets out what a UK portfolio could look like under this model. ACs would grow in line with collectively agreed AC rises. A better-performing CVC would remain the largest element. Finally, a set of new investments would allow for targeted support to UK priority areas. Annex 6 contains a Theory of Change for a potential future programme that reflected these recommendations.

# 7. Conclusion
The evaluation supports a high-level set of findings, lessons and recommendations for FCDO.
Findings and Lessons
- The design of the overall programme was fully aligned with the objective of strengthening WHO institutional performance. The move to consolidated, large-scale CVC funding was evidence-based, principled and forward-looking. It responded to the needs and requests of the WHO for greater flexible funding.
- FCDO clearly understood the risks and challenges associated with the transition to a different funding model. These arose from the trade-off between providing greater flexibility for WHO and reducing direct UK control around the use of UK funding. A range of mechanisms were established to address the risks and trade-offs and to manage the transition. These included the PBR tranche, a high-level dialogue and new cross-FCDO and cross-Whitehall coordination mechanisms.
- The programme has been implemented against a challenging backdrop. This included the demands of dealing with the COVID-19 pandemic, the subsequent intense scrutiny of health security policy and the creation of FCDO as a new department. This backdrop should not obscure the fact that this programme has seen a step-change in the WHO flexible funding agenda and played an important anchoring role in that progress. Further, it is also clear that WHO has worked to deploy its increased flexible funding in a strategic manner that supports priority objectives, such as transforming the technical capacity of Country Offices.
- Progress has been slower than needed and could have been faster. But a strong platform is now in place which promises accelerated progress in the 2024/25 biennium and beyond that into GPW14.
- The costs of the PBR mechanism exceeded its benefits. It represented too small a share of total WHO funding to shift behaviour and it significantly constrained WHO’s budget and planning flexibility. The programme’s five annual ‘key asks’ were too narrow to accommodate the full range of UK priorities. The transition away from direct UK funding to individual thematic areas was abrupt, which complicated UK influence and engagement.
- The UK remains an outlier in terms of how flexibly it funds the WHO. Other donors have stepped up but not as significantly as hoped. WHO’s arrangements and systems for reporting, and accountability to flexible funders fell short. Reporting in terms of the use of CVC funds alone was misleading and the metrics for capturing progress on organisational reform were inadequate.
Looking ahead to a future programme these findings generate recommendations that could strike a better balance between the different objectives and more effectively contribute to intended goals.

###### Recommendations
- The evaluation makes a set of 13 recommendations. The topline recommendation is that the UK approach to providing a very significant share of its WHO support in the form of flexible CVC funding should be maintained.
- However, FCDO should work with WHO and other CVC donors to strengthen the performance and accountability of the CVC instrument. Improvements would include a shift to a comprehensive flexible funding model, stronger metrics for success in reform, enhanced mechanisms for oversight by flexible donors and more visible recognition of flexible funder contribution both internally and externally.
- FCDO should also consider adjustments to the design of its programming. This would include the reinstatement of a comprehensive results framework, an end to the payment by results component, strengthening internal and external coordination mechanisms and additional capacity for programme management, technical dialogue and results monitoring. Finally, the team also recommends consideration of a targeted ‘holdback’ of 10-20% of flexible programming to support high-priority thematic areas where catalytic stimulus may add value. A Theory of Change for a potential future programme that reflected these recommendations is in Annex 6.
# Annex 1. Discrete Learning Analyses

Progress on selected priority areas
Relevant EQs
EQ14. To what extent have the organisational changes (supported through CVC funding) contributed to the sustained delivery of WHO’s General Programme of Work Triple Billion programme, in particular the improved access to quality health services and the rapid detection of and response to health emergencies?
EQ15. How has the WHO sustainable financing agenda advanced since 2020?
EQ16. Since 2020, what have been the key trends in WHO’s staffing, including contractor-to-staff ratio, contract length, technical gaps, gender balance and country representative gaps?
EQ17. What has been achieved in strengthening critical systems and processes, such as PRSEAH, since 2020?
### Delivery of the General Programme of Work (EQ14)

###### GPW13 Progress

At the end of 2023, WHO reported on its progress in delivering GPW13 and its Triple Billion targets.97 Although projections show that targets for healthier populations will be met by 2025,97 there are challenges in addressing obesity in children, nutritional health issues persist, and millions still die due to inadequacies in WASH.90 Progress towards UHC and emergency preparedness are off-track. There has been uneven progress in health services coverage and, despite some reforms brought about due to the COVID-19 pandemic, many health emergency and preparedness systems remain inadequate or weakened.90 The COVID-19 pandemic is cited as a key reason for missing targets, as well as curtailing the transformation agenda.

###### Transformation progress

The GPW13 Theory of Change illustrates that achievement of the Triple Billion targets is dependent on WHO transformation,55 although a key shortcoming of the Theory of Change is that it does not clearly articulate what the end state of reform would look like or how to get there.62 The WHO transformation, launched in 2017, was conceived as an organisational change initiative to equip WHO to achieve the GPW13 by optimising its use of resources, streamlining processes and ensuring it is fit for purpose in a rapidly changing world.62 While GPW13 explains the “what” and lays the groundwork for “how” it will achieve the Triple Billion targets, the transformation has aimed to translate the “how” into a specific set of change management initiatives.62 These are categorised under the seven workstreams of the reform agenda:

- Impact-focused, data-driven strategy
- A new, aligned three-level operating model
- A new approach to partnership
- New results-focused, collaborative and agile culture
- Ensuring the predictable and sustainable financing of WHO
- Building a motivated and fit-for-purpose workforce
- Redesigning technical, business and external relations processes

The 2021 evaluation of WHO transformation found that substantial progress had been made, particularly around organisational structure, strategic planning, results focus (including the development of a results framework, progress in tracking outputs and outcomes and an enhanced commitment to results-based management)42—albeit at a slower timescale than anticipated, due to COVID-19.62 Since 2021, other key developments around the transformation agenda have included:90
- Procurement and HR processes were simplified in response to COVID-19, and staff were redirected to work in areas of highest need and new ways of working were mainstreamed e.g., remote working;
- Results-based approaches are ramping up and being piloted, with a view to greater focus on impact.
- The creation in 2023 by the DG of an Action for Results Group (ARG);
- Further development of partnerships, after those developed for the Sustainable Development Goal (SDG) Global Action Plan in 2019 and the launch of the WHO foundation in 2020; and
- The decision in May 2022 by the WHA to gradually increase ACs to represent 50% of WHO’s core budget.

However, progress to foster a motivated workforce and reduce administrative burdens have been less pronounced, and the transformation’s impact at the country level remains limited.90 Challenges include resourcing Country Offices, increasing staff mobility and addressing the top-heavy nature of staffing. The WHO CPCP is a promising initiative that aims to address some of these issues by:

- Strengthening the capacities that serve as the foundation to make WHO Country Offices fit-for-purpose;
- Ensuring that Country Offices have the technical, leadership and managerial capacities to support the country based on their needs for WHO support; and
- Ensuring these capacities are reliable, predictable, sufficient and high quality by providing stable funding and support from all levels of the organisation.

Key informants consistently noted that the unpredictability of financing at the country level is a critical factor complicating more effective performance.

“90% of resources are unpredictable at country level. I think only maybe 10-12% is very predictable…So in that environment, if you want people to work and provide some impact, the result I think is pretty tough.” (KII, WHO)

Nevertheless, key informants highlighted that even limited growth in flexible funding at country level was beginning to allow for more strategic and systems strengthening at the country level.

“Because of this, we’re more able to focus on systems rather than programmes, systems like health systems with which will have a broader impact on health outcomes…Before we could not follow our priorities…and now we can at least have the confidence to say, ‘we set our priorities and maybe we have some money to fund...those priorities.’” (KII, WHO)

###### Linking reform to GPW13 and its impact

While WHO has certainly made progress in introducing results-based approaches, there is still a significant gap in linking reform results to the delivery of GPW13. As described above, while the GPW13 Theory of Change shows that delivery is reliant on transformation, it is not clear how and in what ways this will happen. Directly linked to this, the evaluation of GPW13 found “a lack of clear metrics for measuring outcome level results, making it difficult to assess the transformation’s overall effectiveness.”90 Monitoring and evaluation of reform to date has focused on what has been achieved, but “milestones for how and by when WHO can be considered transformed as a result of implementation are not defined, tracked or reported against.”62 Perhaps as a result of this gap, the literature review, desk review and KIIs focused less on how organisational changes supported the sustained delivery of GPW13 and more on the fundamental institutional question of WHO comparative advantage and how to maximise impact. This highlighted the ongoing breadth of opinion which inevitably complicates organisation reform priorities and definition of results. Selected viewpoints are set out below.

Some suggested focusing on WHO’s technical and normative function and letting others lead more on the provision of direct TA to introduce that technical and normative guidance at country level:

 “Still not sure it should be doing large amounts of TA. It has incredible reach, so perhaps it needs to be doing something in the countries that don’t tend to get TA…(or) maybe it’s a provider of TA as a last resort…It needs to have a mechanism for connecting with countries, but it doesn’t need to deliver everything at the country level because there’s so many others that are doing that. It needs to make its global function generally useful to countries.” (KII, Independent Expert)

Others suggested WHO should still focus intensively on supporting countries, leveraging their relationships and influence.

“I think their [WHO’s] compelling case is the support to help developing countries to really improve their own health systems…WHO is about the coordinating role that is working with country governments on the National Health plans, you know, really being able to demonstrate that they are a key player with country governments, which is really quite different from the way that the (vertical) funds work.” (KII, Donor, Member State)

Some suggested a focus on tailoring guidance to country context. One informant suggested that the development of global guidelines is limited in utility if it is not adapted and ‘right-sized’ to country contexts and resources.

 “[WHO] should try and recommend how you optimise the right care for your right resources, which is just different in Malawi to what it is in India and what it is in the UK…because otherwise, you’re wasting money …it misses a whole section of poor countries.” (KII, Independent Expert)

The Sustainable Financing Agenda (EQ15)

For decades observers have noted that the WHO’s funding is incommensurate with its mandate.22,48 For example, in the biennium 2022-2023, the organisation’s budget was US$6.72bn – smaller than that of a large teaching hospital in the United States.25 WHO allocates planned spending through its biennial Programme Budgets (disaggregated by major office, level, category and programme area).

The WHO is funded by ACs - dues paid by countries (normally from Ministries of Health) and VCs. There are different categories of VC which vary significantly by flexibility and quality. CVCs are fully flexible; Thematic VCs provide flexibility in allocation to WHO within GPW outcome areas; and Specified VCs are generally tightly earmarked to donor specifications in terms of activity, output or geography.

WHO is dependent on earmarked contributions39 which have increased proportionally and significantly over time. 35,40,22 Less than 20% of WHO funding comes from flexible contributions.6,22,40 Securing sufficient and sustainable financing remains problematic, especially with the proportion of earmarked funds increasing yearly.42

Financing gaps and the nature of the funding received make it difficult for the Secretariat to implement Member State priorities, as expressed in the GPW. Setting aside the multiple debates about whether the mandate has expanded unrealistically – and particularly in operational areas – shortfalls in funding across programme areas41 imply that the work cannot be fully delivered.32,94 The COVID-19 pandemic highlighted the major risks to the organisations associated with an unpredictable and earmarked funding base. This led to intensified calls for financing reform on the basis that WHO is the most important global coordination mechanism for responding to public health threats, including pandemics, providing a vital public good that serves all countries.131

###### Challenges with the current financing model

A driving force for change is WHO’s overreliance on earmarked funding. While earmarked funding fosters accountability and allows donors to fulfil their commitments on strategic priority areas, this approach has consequences, as highlighted below:

High number of donor agreements is burdensome and inefficient. Funding to WHO is highly fragmented resulting in significant administrative and reporting burdens on the organisation.41 Current funding mechanisms are inefficient and constrain WHO’s ability to address priority issues42 (commonly called ‘pockets of poverty’). The WHO is currently managing around 3,000 grants, each requiring separate reporting. For example, in Germany (which does provide CVCs) there are eight different government bodies providing VCs to WHO, many of which are earmarked in line with their different mandates. The top ten Member State contributors, and the Gates Foundation, together have over 1,000 separate agreements. The remaining 200 or so contributors are responsible for a further 2,000 agreements.41

WHO lacks autonomy over resource allocation. Some have argued that VCs make it easier for WHO to withstand variability of financial support. VCs can be mobilised rapidly in an emergency and bolster multilateralism by making international organisations less vulnerable to political change and unilateral (in some cases, unlawful) decisions of Member States.8 However, earmarking also limits the WHO’s capacity and opportunities to adjust to change68 and poses a risk to the integrity and independence of the work of the organisation.32 Overreliance on earmarked funding skews priorities towards the preferences of select donors,40 resulting in the Secretariat having limited control over its own funding decisions.6,32,35, 132 Many activities prioritised in programme budgets have elicited little interest from donors40. This results in underfunding. An example is non-communicable diseases which are responsible for 74% of global mortality. Other areas where funding gaps can be significant are reproductive, maternal, newborn and child health (RMNCH)6 and emergency operations.42 Reliance on VCs means substantial fundraising is devolved to individual departments and offices. Key informants interviewed during the evaluation spoke openly of ‘silos’ or ‘internal empires.’ Directors are admired by their peers (and staff) for their ability to bring in funds, resulting in more accountability to their external donors than to WHO leadership.

“...we cannot follow... our priorities...because we've been dictated, right? I mean, some of our priorities, nobody even gives money, right?" (KII, WHO)

Significant challenges therefore persist in matching resources to requirements with ‘pockets of poverty’ (in high priority areas) recognised throughout the organisation.

###### Advances in the sustainable financing agenda (post-2020 efforts)

Since 2020, after decades of discussion and limited progress, the sustainable financing agenda has advanced significantly. The COVID-19 pandemic was a major trigger. Member States became more invested in finding solutions for WHO’s financing and reform issues, recognising WHO’s pivotal leadership role in global health and health security.

In resolution WHA73.1 (2020), the WHA called on Member States to “provide sustainable funding…to ensure that [WHO] can respond fully to public health needs in the global response to COVID-19.” In decision EB148(12) the Executive Board established a Working Group on Sustainable Financing in January 2021, which looked at how to enable WHO to have the robust structures and capacities needed to fulfil its core functions as defined in the Constitution.47 The spotlight was on the challenge of highly earmarked and short-term VCs, especially for Country Offices.79 As a result of this, during 2021 and onwards concrete and unprecedented agreements have been made by the WHA on AC increases (in May 2022)126 and putting in place an Investment Round (to be held in Nov 2024) to reduce WHO’s reliance on extrabudgetary funding.47

###### UK Influence on the sustainable funding agenda

Although cause and effect are challenging to determine, there is anecdotal evidence, that the strong signal sent by the UK to untie significant funding was a major enabler for the sustainable financing dialogue. The Agile Member States Working Group took forward the work on strengthening WHO’s budgetary, programmatic and financing governance, resulting in the Secretariat Implementation Plan (SIP) on reform in November 2022. While concrete results are yet to be realised in the form of more flexible funding, the building blocks are now in place for increased quality and volume of funding. The UK has made an important contribution to this, with its unified cross-departmental voice on funding approaches formally in WHO governing bodies and offline conversations. However, to sustain momentum and progress, the UK government, alongside other major donors to WHO, will need to have structured conversations on financing for global health ‘in the round.’128

It is important to recognise that reliance on voluntary/earmarked funding is not unique to WHO, it is a problem across the UN.26 As part of UN Development System reforms, the UN Secretary General initiated a funding compact agreed in 2019.17 The UN Development System (UNDS) committed to improving its accountability, efficiency and coherence, while the Member States committed to reducing earmarking, among other changes.3

###### A landmark achievement – a commitment to increase Assessed Contributions

In May 2022, the WHA agreed to overhaul WHO's outdated financial model,48, 26, 32 a “system neither fit for purpose nor sustainable,”87 and to establish a more flexible and predictable sustainable financing structure,126 by fully adopting the recommendations of the Sustainable Financing Working Group, as originally envisaged in the WHO Constitution.47 Members voted to incrementally increase the mandatory contributions from 22% to 50% of the base segment of the 2022–23 Programme Budget by 2028–29, resulting in an increase to US$2.18bn for 2028–29,35 or by 2030-31 at the latest. The first increase took place in line with the approval of the Programme Budget in May 2023 (for 2024–2025).77 A freeze on base segment of the programme budget for 2024–25 may temporarily cap the amount of funding in the near-term35 however the changes mark a historic move towards a more empowered and independent WHO.94

In contrast to the assumption that only the wealthiest partners can increase their funding, it was noted that most Members have experienced two decades of economic growth and the increase in ACs could be achieved.40 However, while most agreed that higher quality funding is needed there are still challenges. These include requests from the United States (and others) for WHO to improve its efficiency before funding is committed;44 persistent underfunding linked with Member States falling into arrears;8,20 difficulties in terms of enforcing Member States’ financial obligations;34 and broader financial challenges exacerbated by COVID-19;77 anti-aid sentiment in the context of economic pressure;44 withholding of AC payments to secure policy influence;8 and speculation that some countries might use the AC increases as a justification to reduce what they might have otherwise given in VCs.

###### WHO investment round

When the WHA adopted the Working Group’s recommendations, it included a request for the Secretariat to explore the feasibility of a ‘replenishment’ mechanism to further broaden the financing base,47,126 although there have been concerns that this could exacerbate ‘philanthrolateralism’ (outsourcing funding and decision-making to donors external to the UN system).35 At the WHA in 2023, the DG was asked to proceed with the planning of a WHO investment round and to develop an evaluation element and a target funding envelope.95

In adopting this approach, the Secretariat also suggested a change in the definition of thematic flexible funding, the allocation mechanism and the way the funds are reported to allow the provision of flexible funds to outputs (e.g. non-communicable disease preparedness) and at country level. The hope is that more donors will shift to more flexible funding.47 The success of the investment round will not only be funding, including increases from existing funders, but also predictability, flexibility, broadening of the donor base and increased efficiency.94 The ambition is to raise US$7.1bn for the base segment of GPW14 budget 2025-28, costed at US$11.1 bn.47

###### Remaining challenges to address

Apart from the efforts being made to increase financing to the organisation commensurate with its responsibilities, there is an urgent need still to:40
- Build on the principles and rules set out in the Framework for Engagement with Non-State Actors (FENSA) and set out clear conditions on the terms under which the organisation will accept VCs;8
- Address the incentives that come with earmarked funding e.g. internal and external communications. There is a perception that there is more recognition for ‘tied’ funding (for example, in the last three DG speeches to the WHO EB and WHA, only France was mentioned by name for the Academy in Lyon) and a perception that earmarked funders may have more privileged access to WHO forums and technical debates.
- Revisit the idea of "critical mass" of core funding needed, but base this on avoiding a "toxic level of non-core" rather than a minimum level of core funding.3
- Continue efforts to rebuild trust in the transparency and independence of decision-making such that the current and emerging funding model does not attract criticism that it gives rise to conflicts of interest (e.g. undue private sector influence).132
- Recognise that the majority of WHO’s voluntary funding is coming from Official Development Assistance (ODA) yet WHO's work goes far beyond development and aid and space for a possible increase of ODA is shrinking. Financing global public health goods should be viewed more as analogous to what is happening in climate financing.32
### STAFFING TRENDS AT THE WHO (EQ16)

By July 2023, the total number of WHO staff members was 9,261,112 representing an 11% increase since 2020.72,74,106,112 Considering the six Regional Offices, the highest proportion of staff worked at HQ although there was a 3.8% decline from 2022 to 2023. The largest regional office is AFRO, followed by the Eastern Mediterranean Regional Office (EMRO), SEARO, the European Regional Office (EURO) and lastly, the Western Pacific Regional Office (WPRO). Looking at the three levels of the organisation (HQ, regional, countries), nearly half of all WHO staff work in the Country Offices. As of December 2022, 25% of the WHO’s total international professional (P-level) staff worked in Country Offices, representing a three percentage-point increase from the last report. This suggests that WHO is steadily strengthening technical capacity at the country level. In total, 49% of all WHO General Service staff and 92% of all National Programme Officers (NPOs) worked in Country Offices. The highest proportion of all country-level staff worked in the African Region (42%). The proportion of international professional and national professional staff in WHO Country Offices has increased steadily.96
###### Expenditure on staff

From 1st January to 31st July 2020, staff costs amounted to US$567m or 34% of the organisation’s total expenditure of US$1,645m. For the period from 1st January to 31st July 2023, staff costs amounted to US$754m, representing 36% of the organisation’s total expenditure of US$2,107m. It should be noted that staff costs as a percentage of organisation spending was highest in 2022 (41%).72,74,106,112
###### Consultants, individuals on agreements for performance and special service agreements

There was an overall increase in consultants, individuals on agreements for performance and special service agreements between 2020 and 2023.72,74,106,112 Significant increases can be attributed to increased capacity for WHO’s work in emergencies and the polio transition process.112
###### Gender parity

In 2023, the WHO Gender Parity Policy (2023–2026) was launched, replacing the WHO Gender Equality in Staffing Policy. Progress towards gender parity among international professional staff can be seen across most WHO regions. At the country level there is still room for improvement. Overall gender parity among international professional staff in Country Offices declined. Enhancing efforts towards gender parity of international technical staff remains a challenge that WHO needs to address at the country level. 96
Overall, there was an increase in the percentage of women in the professional and higher categories between July 2020 and July 2023 from 46.2% to 47.4%. The same was noted in each of the major offices during this same period except for Europe which saw a decline. Similarly, there was an increase in the percentage of women in P4 grade and above (long-term appointments) from 43.8% to 44.5%. There has been an overall decline in the percentage of women as Heads of Country Offices from 37.9% to 36.8%, and the percentage of women at the D1 and D2 grades (long-term appointments) from 37.1% to 34.4%.112
###### WHO representatives’ region of origin

WHO Representatives (WRs) represent the organisation at the national level and can often be a significant interlocutor with Ministries of Health. 32 In 2012, the WHO leadership determined that at least 30% of WR positions must be filled by personnel from outside the duty station’s region. As of December 2022, only WPRO and EMRO had met this threshold. More efforts towards this target must be made in other WHO regions. 112
###### Mobility

The WHO Global Geographic Mobility Policy took effect in June 2023. Under this policy, staff at HQ in Geneva are required to relocate every five years, while staff in duty stations every two years.112 There has been significant staff resistance, and the voluntary phase has been extended through to end 2024.
"I think the kind of richness that brings through the mobility, the learning, understanding…that kind of cross fertilisation across [the] three levels will really make the organisation much stronger.” (KII, WHO)
Despite implementation of the new policy, the percentage of moves from one major office to another remains constant between the period from January to July 2023 and the period from January to December 2022 (41.3%).112 The mobility policy has been criticised for failing to address Country Office needs by not offering job security and professional development for national staff. Secondly, relocation of staff is expensive.9
"...there's no commitment from the Member States, unfortunately…without the Member States really committing, I'm not sure it's going to work...There is staff resistance.” (KII, WHO)
###### Changes in Regional Directors (RD) selection

There has been a change in the selection process for Regional Directors (RDs) where the DG is being presented with three names.
".. in the past RD nominations, DG was just rubber-stamping and sending...They used to send only one nomination to DG for approval. Now... each region should send... three candidates, and let the DG and ADG discuss…we can give DG our views among those three who are good and who are not good.” (KII, WHO)
However, it is still seen as a highly political process, with the DG very unlikely to overturn the preferred candidate of the regional Member States, who vote during the regional committee meeting.129
###### WR capacity is highly variable

The performance of WRs was seen as highly variable, and concern over gaps in permanent WRs was expressed in a number of contexts.14 There is a need for merit-based WR selection, improved performance management, increased accountability, and more direct and frequent interaction between the HQ and the country level.32 WHO is making attempts to strengthen Country Offices (e.g., mobility policy and re-profiling exercises), however evidence suggests embedding the necessary changes in working practices has been more difficult, with historical practice often remaining the predominant way of working.42
###### Staff assignment and technical capacity

In terms of assignment country-level technical staff to strategic areas, 6% were assigned to ‘healthier populations,’ 33% to UHC, 43% to health emergencies, and less than 2% to data, delivery and innovation. In terms of delivering results, 32% of staff reported insufficient workforce for ‘healthier populations,’ 24% reported insufficiency for health emergencies, and 43% reported insufficient staff for data, delivery and innovation. UHC workforce insufficiency was more strongly felt by Country Offices in AFRO (40%), WPRO (40%), EMRO (38%) and SEARO (36%).
“… there's no one technical that we can liaise with…and SRH [sexual and reproductive health] would say the same thing…they've only got in some countries, just like a handful of people, and they take on every technical issue...I see that they struggle to do the work.” (KII, FCDO)
It was also noted that there is limited resource mobilisation capacity, including, specialised donor engagement skills, understanding the overall funding landscape, and inadequate staff dedicated to resource mobilisation and to implement potential funds.96
###### How sustainable funding agenda interacts with WHO staffing
Overdependence on VCs constrains the ability to recruit and retain the best talent, and to deliver high-quality technical work.12
“… it I think it also reduces our attractivity as an employer because we sometimes we can only offer short -term contracts. Three months, six months…constantly sending people on contract breaks…earmarking is really driving us away from... concentrating on the work.” (KII, WHO)
Further, the current financing model is administratively burdensome, as it forces staff to manage thousands of awards across hundreds of budget centres taking time away from already strained technical teams.84 Lastly, experts noted that it is difficult for the WHO to control the organisation, including staffing decisions, as influential VC donors have a strong influence on appointments.32
The CPCP includes the essential and predictably funded positions that every WHO Country Office should have to facilitate impact. It has been established in all WHO Country Offices to ensure the organisation is impactful at the country level. The availability of flexible funding has been instrumental to CPCP.
“…without that flexibility, you would not have been able to do this... core predictable country presence. Because that money is really coming from flexible funds. It's not coming from specified-voluntary contributions.” (KII, WHO)
Attempts are being made to strengthen the delegation of authority (DoA) from the DG and RDs to WRs/heads of Country Offices, allowing them to be more agile and responsive to the Member States’ needs and priorities.108 Flexible funding has been instrumental in these efforts.
“... I think we have more confidence to put more authority to the WRs because we know we can support them to exercise that authority…You're not constrained by somebody telling you…you can't use your money for that.”" (KII, WHO)
### PREVENTING & RESPONDING TO SEXUAL EXPLOITATION, ABUSE AND HARASSMENT (EQ17)
###### Background
In 2020, an Independent Commission was established by the WHO DG to review allegations of sexual exploitation and abuse (SEA) in the Democratic Republic of the Congo (DRC) during the 10th Ebola response.100 The Commission reported in October 2021, noting over 80 reports of SEA by WHO personnel. The Independent Commission identified failures in reporting, interpretation of policies, and around the culture of addressing SEAH. The Independent Commission made several recommendations and urged WHO to establish an independent mechanism to monitor progress.14

###### Key elements of the PRSEAH Agenda
In 2021-2022 WHO responded with a new approach set out in its Management Response Plan (MRP). The MRP laid the foundations for a strengthened approach to PRSEAH. The MRP had an initial outlook of 15 months (October 2021 – December 2022) and included a recommendation to develop the 3YS for PRSEAH. The MRP initially focused on short-term actions (October 2021-March 2022) to address the commission’s recommendations, but also included medium term actions (November 2021 – December 2022) focused on adopting a victim- and survivor-centred approach; developing an accountability framework; and reforming WHO’s culture, structures, systems.69

WHO established an IOAC Subcommittee to drive the implementation of the MRP. The IOAC sub-committee highlighted the need for more predictable funding to sustain progress and the need for meaningful cultural and structural change.73 They also highlighted concerns with the feasibility of implementing the MRP within the allocated timeframe. The subcommittee’s consultation highlighted WHO’s complex, ambiguous policy framework, the need to do more to build community knowledge with regards to WHO policy and reporting on PRSEAH, and organisational culture challenges including around the lack of global mobility, women in leadership roles and staff diversity. 76

To support work on PRSEAH, a US$50m request for the 2022‒2023 biennium was included in the proposed revision of the programme budget.89 WHO committed to making this budget available to support the establishment of a victim-centred approach; to strengthen staff capacity and accountability on PRSEAH; and to reform WHO’s organisational culture, accountability functions and policies.93 WHO also recognised that additional resources would need to be mobilised for prevention, detection and response activities in field operations and community-facing programmes. Of the programme portion of the MRP funds (approximately US$30m), 46% was allocated to Country Offices, 18% to Regional Offices, 13% to HQ and 23% to cross-organisation activities for all levels of the organisation, including a victims’ assistance fund. Approximately US$10m was to be allocated to creating institutional capacity for investigation services, and the remainder for reforming, streamlining and strengthening related accountability functions.89

###### WHO’S three-year strategy
After laying the foundation for change through the MRP, WHO sought to institutionalise safeguarding approaches through a new 3YS (2023-2025). Year one of the strategy was to focus on institutionalising a new accountability framework, tools and policies, whilst year two focusses on organisational culture and impact at country level.89 In 2025 there will also be a comprehensive independent evaluation of the 3YS100.

As part of the 3YS, WHO launched the Preventing and Addressing Sexual Misconduct (PASM) policy which sets out WHO’s approach to support victims and survivors, and to ensuring accountability of perpetrators. As part of PASM, WHO makes various commitments on transparency; UN collaboration; addressing root cause; updating partnership agreements and contracts to reflect the values; and implementing robust recruitment processes. As part of the 3YS WHO also published its Prevention of and Response to Sexual misconduct (PRS) Accountability Framework (2023-2025). This seeks to clarify roles and responsibilities and includes processes for end-to-end misconduct incident management.
###### Progress to date
WHO’s institutional capacity around PRSEAH has been significantly strengthened. The organisation has committed to maintaining at least US$50m for work on PRSEAH at HQ, and Regional and Country Offices. P5 level regional coordinators have been appointed to Regional Offices to lead work on PRSEAH in their respective regions. WHO also now has full-time technical officers in several priority countries. In addition, a global network composed of mostly part-time personnel, totalling 407 by October 2023, has been set up to address sexual misconduct. Monthly capacity building events are held by the global team in addition to capacity building work conducted by regional coordinators.100 So far, 340 WHO country PRSEAH focal points are also engaging with the UN country team to proactively contribute to UN PRSEAH action plans. 18

Predictable funding has been a key driver of success on the PRSEAH agenda within WHO. This has been particularly the case with regard to staffing. Informants highlighted unpredictability of funding as a key challenge in the past regarding staffing and attracting quality staff. However, increased levels of flexible and predictable funding have enabled the recruitment of high-level staff in Regional Offices to support the PRSEAH agenda, including assessing risk, establishing mitigation plans, driving standardised training approaches and screening staff. Aside from recruitment, core funding was also key for the establishment of systems.

“Knowing this money is coming and is available on the 1st of January allowed [us] to have these six people in the regions and 15 people in the country. One of the biggest issues with funding is it comes late...and it's not reliable. One of the best things that we've had for institutionalisation is the guarantee of (predictable funding). That allowed us to create fixed-term positions.” (KII, WHO)

“All of this [progress on PRSEAH] was made possible with core funding” (KII, WHO)

The flexibility of funding has also been important, by allowing WHO to target resources at roadblocks.

“Having the flexibility, that's what really helps, because you can say, ‘okay, here's a roadblock, we need to do something about that.’ We can put in the resources…(this) has been really critical, because there are many beautiful policies out there in the UN, but people still don't report. Whereas we have seen the figures going up, because we have been able to address the issues that were really on staff's hearts and minds.” (KII, WHO)

“There's no question that this work would not have happened without the sufficient flexible funding” (KII, WHO)

###### UK’s role in driving progress
The UK’s WHO CVC programme played a key role in supporting this progress. Since PRSEAH is not considered technical work, it is funded via WHO’s flexible funding. The funding used to drive action on PRSEAH therefore cannot be officially labelled as FCDO’s CVC funding, since WHO’s accounting rules only permit CVC to be allocated to programme activities. PRSEAH therefore does not appear in WHO’s CVC report, which shows CVC flowing to countries whilst AC is retained for more strategic activities. However, the UK’s CVC allowed for flexible funding to be freed up to support PRSEAH. WHO is therefore considering moving to a flexible fund reporting approach which would better capture the impact of flexible funding in its totality.

“Because of the CVC, we had the means to create the space to roll out and invest in PRSEAH.” (KII, WHO)

The UK’s PBR was also seen to play a role in influencing progress on PRSEAH by providing a clear incentive across the organisation.

“You do things also because there is those criteria to be met, the 80%, for example, that also strengthens the coordination and collaboration…(countries) understood, ‘so we need to do the 82%’ and that's spilled over in their own offices.” (KII, WHO)

The UK’s technical support was also welcomed.

“For us, FCDO is not just a funding partner, it's a technical partner…[FCDO] started the concept of safeguarding before us. So, we've had technical collaboration, technical missions…We really appreciate that” (KII, WHO)

This has enabled WHO to make strides in strengthening critical systems and processes for PRSEAH. Key achievements include:

- Embedding a victim- and survivor-centred approach (including establishing WHO’s Survivor Assistance Fund);
- Institutionalising safeguarding in all relevant policies, procedures and practices;
- Enhancing safeguarding in WHO’s community-facing operations;
- Enhancing safeguarding of implementing partners via training and information sharing with other agencies;
- Integrating PRSEAH into risk assessment and mitigation, including at country level;
- Workforce training and engagement from external learners including governments and non-governmental organisations (NGOs);
- Stronger transparency and accountability including quarterly and ad hoc updates to Member States, media briefings, monthly newsletters, and the joint commissioning of a review of PRSEAH work in health emergencies;92 and
- Country Office progress, including the roll out of trainings, the appointment of focal persons, and inductions for new staff, with 57% of Country Offices worldwide reporting an increase in the PRSEAH capacity in 2021–2022.96

# Annex 2: Bibliography

Anonymous (2020) Withholding funding from the World Health Organization is wrong and dangerous and must be reversed. Nature, 580: 431-432. Available at: DOI: 10.1038/d41586-020-01121-1.

Baker, P. (2023) The Future of UK Global Health Policy- Challenges and Opportunities. Available at: https://www.cgdev.org/sites/default/files/The%20Future%20of%20UK%20Global%20Health%20Policy_0.pdf.

Baumann, M. (2021) How earmarking has become self‐perpetuating in United Nations development co‐operation. Development Policy Review, 39 (3): 343-359. Available at: DOI: 10.1111/dpr.12504.

Brown, P. (1999) WHO budget set to reflect new priorities. BMJ, 318: 212. Available at: DOI: 10.1136/bmj.318.7178.212a.

Center for Global Development (2023) How the UK Can Make the Best Use of the Multilateral Development Finance System. Available at: https://www.cgdev.org/publication/how-uk-can-make-best-use-multilateral-development-finance-system#:~:text=The%20UK%20could%20offer%20to,meta%E2%80%9D%20Board%20for%20the%20system.

Clift, C. (2018) New approaches to WHO financing: the key to better health. Globalization and Health, 14 (119). Available at: https://doi.org/10.1186/s12992-018-0436-8.

Cullinan, K. (2023) WHO Needs to Explore Incentives for Flexible Donations - Health Policy Watch. Available at: https://healthpolicy-watch.news/who-needs-to-explore-incentives-for-flexible-donations.

Daugirdas, K. (2019) Financing the World Health Organization: what lessons for multilateralism? International organizations law review, 16(2):299-338. Available at: https://ssrn.com/abstract=3434603.

DEVEX (2023) WHO postpones mandatory employee rotation after pushback from staff.	Available at: https://www.devex.com/news/who-postpones-mandatory-employee-rotation-after-pushback-from-staff-105861.

DFID, et. al. (2013) International Development Evaluation Policy (May 2013) (WHO CVC Evaluation ITT. Available at: https://www.oecd.org/derec/unitedkingdom/DFID-Evaluation-Policy-2013.pdf.

ePact/OPM/ITAD (2020) Evaluation, Learning and Verification for Agency Reform (ELVAR) Comparative Report. Available at: https://iati.fcdo.gov.uk/iati_documents/90000108.pdf.

1. FCDO (2020a) Influencing Multilateral Reform Including Payment by Results (internal document).
2. FCDO (2020b) WHO Project Completion Review (internal document).

FCDO (2021a) Annual Review 2021 (internal document).

FCDO (2021b) Business case (internal document).

FCDO (2021c) Memorandum of Understanding (FCDO and WHO 2021) (internal document).

FCDO (2022) WHO Evaluability Assessment (internal document).

FCDO (2023) Annual Review 2022 (internal document).

FCDO and Department of Health and Social Care (2023) Global Health Framework: Working together towards a healthier world. Available at: https://assets.publishing.service.gov.uk/media/646b2646628371000c3a896a/Global_Health_Framework__working_together_healthier_world_May2023.pdf.

Frenk, J. (2016) Finance and governance: critical challenges for the next WHO director-general. Am J Public Health, 106(11):1906–1907. Available at: https://www.ncbi.nlm.nih.gov/pmc/articles/PMC5055779/#:~:text=In%20terms%20of%20finance%2C%20the,in%20line%20with%20their%20growing.

GIZ (2022) Catalyst dialogue on global health architecture: Towards a global health architecture that works for all. Available at: https://www.globalhealthhub.de/fileadmin/user_upload/Output_Catalyst_Dialogue_Global_Health_Architecture_English_20220919.pdf.

Gostin, L. (2022) Financing the future of WHO. The Lancet, 399(10334): 1445-1447. Available at: DOI: 10.1016/S0140-6736(22)00533-5.

Gostin, L. (2023a) Making the World Safer and Fairer in Pandemics. Hastings Center Report 53, (6): 3-10. Available at: https://scholarship.law.georgetown.edu/cgi/viewcontent.cgi?article=3588&context=facpub.

Gostin, L. (2023b) The Global Health Architecture: Governance and International Institutions to Advance Population Health Worldwide. Milbank Quarterly, 101(S1): 734-769.	Available at: https://pubmed.ncbi.nlm.nih.gov/37096621.

Gostin, L. (2023c) The World Health Organization on Its 75th Anniversary. JAMA Health Forum, 4(4): e231568. Available at: https://jamanetwork.com/journals/jama-health-forum/fullarticle/2804483.

Gulrajani, N. (2022) Fixing UN financing: a Pandora’s box the World Health Organization should open. Available at: https://odi.org/en/publications/fixing-un-financing-a-pandoras-box-the-world-health-organization-should-open.

Harmer, A. (n.d.) Sustainably funding the World Health Organization? People’s Dispatch. Available at: https://peoplesdispatch.org/2022/06/11/sustainably-financing-the-world-health-organization/

HMG Cabinet Office (2021) Global Britain in a competitive age: the Integrated Review of Security, Defence, Development and Foreign Policy. Available at: https://www.gov.uk/government/publications/global-britain-in-a-competitive-age-the-integrated-review-of-security-defence-development-and-foreign-policy.

HMG Cabinet Office (2023) Integrated Review Refresh 2023: Responding to a more contested and volatile world (March 2023). Available at: https://www.gov.uk/government/publications/integrated-review-refresh-2023-responding-to-a-more-contested-and-volatile-world.

ICAI (2020) The UK’s support to the African Development Bank Group. Available at: https://icai.independent.gov.uk/html-version/uks-support-to-afdb-group-3/

Independent Commission on Allegations of Sexual Exploitation and Abuse during the Response to the 10th Ebola Outbreak in DRC (2021) Final Report of the Independent Commission on the review of sexual abuse and exploitation during the response to the 10th Ebola virus disease epidemic in DRC. Available at: https://www.who.int/publications/m/item/final-report-of-the-independent-commission-on-the-review-of-sexual-abuse-and-exploitation-ebola-drc.

Independent Panel for Pandemic Preparedness and Response (2021) The World Health Organization - an Institutional Review. Available at: https://theindependentpanel.org/wp-content/uploads/2021/05/Background-paper-15-WHO-Institutional-review.pdf.

Interagency Standing Committee. Senior PSEA Technical Support Mission to the Democratic Republic of the Congo. Available at: https://library.alnap.org/help-library/senior-psea-technical-support-mission-to-the-democratic-republic-of-the-congo.

Ip, E. (2021) The constitutional economics of the World Health Organization. Health Economics, Policy and Law, 16(3): 325-339. Available at: DOI: 10.1017/S1744133120000249.

Iwunna, O. (2022) Flexibly funding WHO? An analysis of its donors’ voluntary contributions. BMJ Global Health, 8(4):e011232. Available at: https://doi.org/10.1136/bmjgh-2022-011232.

Jayaraman, K. (1998) Budget cut indicates policy changes at the WHO. Nat Med., Aug, 4(8): 874-875. Available at: https://pubmed.ncbi.nlm.nih.gov/9701225.

Kapp, C. (2000) WHO staff members express concerns over internal restructuring. The Lancet, 355(9219):1978. Available at: https://doi.org/10.1016/S0140-6736(05)72919-6.

Kapp, C. (2001) WHO faces funding squeeze as richer countries make a stand. The Lancet, 357(9269):1683. Available at: https://www.thelancet.com/action/showPdf?pii=S0140-6736%2800%2904872-8.

Kurihara, F. (2020) How European countries fund global health: unpacking decision-making and priority-setting processes. Available at: https://repository.graduateinstitute.ch/record/298819?_ga=2.70499024.1599426875.1711373409-1976684033.1711373408&v=pdf.

M'ikanatha, N. (2021) Strengthening the WHO in the pandemic era by removing a persistent structural defect in financing. Globalization and Health, 17:1-11. Available at: https://doi.org/10.1186/s12992-021-00780-7.

MOPAN (2019a) MOPAN World Health Organization (WHO) 2017-18 Performance Assessment. Available at: https://www.mopanonline.org/assessments/who2017-18/WHO%20Report.pdf.

MOPAN (2019b) MOPAN 2017-2018 Assessment. Organisational Performance Brief World Health Organization (WHO). Available at: https://www.mopanonline.org/assessments/who2017-18/WHO%20Brief.pdf.

MOPAN (2023) Member States briefing on the preliminary findings of the MOPAN assessment of WHO. Available at: https://who.zoom.us/rec/play/UUUW5V-uIWnnNb1fvy92orQHzqdfhch6Padh4NBRtLwoLl2iwBM2ts0wLypf8vkvBoWFUU1gBSc0N6c_.gD2YJV3MWt-XJ-mQ?canPlayFromShare=true&from=share_recording_detail&continueMode=true&componentName=rec-play&originRequestUrl=https%3A%2F%2Fwho.zoom.us%2Frec%2Fshare%2Fz5QvrwQzjDxcNb27BKSTXDbYEShoEqQWnjpjRGY8mNV_QUK0juQqDISAIAYsfsgk.OWbgEKcMttUOt_oa.

Nature (2022) The WHO deserves more money for its core mission — and more respect (Editorial). Available at: https://www.nature.com/articles/d41586-022-00227-y#:~:text=01%20February%202022-,The%20WHO%20deserves%20more%20money%20for%20its%20core%20mission%20%E2%80%94%20and,opposing%20a%20new%20funding%20plan.

No author (n.d.) The UK’s High-Level Performance Framework for WHO CVC 2020/21 to 2023/24 (Internal Document).

OECD (2014) Making earmarked funding more effective: current practices and a way forward. Available at: https://www.oecd.org/dac/aid-architecture/Multilateral%20Report%20N%201_2014.pdf.

Patnaik, P. (2024) WHO Seeks to Raise US$7 Billion in First Ever Investment Round in 2024, Executive Board to Consider Proposal This Month. Available at: https://genevahealthfiles.substack.com/p/who-replenishment-investment-round-billion-2024.

Reddy, S. (2018) The financial sustainability of the World Health Organization and the political economy of global health governance: a review of funding proposals. Globalization and Health, 14:1-11. Available at: https://doi.org/10.1186/s12992-018-0436-8.

Sheehan, P. (2022) WHO Investment Case 2.0: Technical Report (March 2022). Available at: https://content.vu.edu.au/sites/default/files/who-investment-case-technical-report-march-2022.pdf.

The Lancet (2018) The case for investing in WHO (Editorial). Available at: https://www.thelancet.com/journals/lancet/article/PIIS0140-6736(18)32289-X/fulltext.

Thorley, L. (2019) DFID ethical guidance for research, evaluation and monitoring activities (May 2019). Available at: https://assets.publishing.service.gov.uk/media/5d9ee055e5274a5a29d7c26a/DFID-Ethics-Guidance-Oct2019.pdf.
.
Velasquez, G. (2020) The World Health Organization Reforms in the Time of COVID-19. Vaccines, Medicines and COVID-19: How Can WHO Be Given a Stronger Voice?, 93-108. Available at: https://link.springer.com/chapter/10.1007/978-3-030-89125-1_6.

Vaughan, J. (1996) Financing the World Health Organisation: global importance of extrabudgetary funds. Health Policy, 35(3): 229-245. Available at: https://www.sciencedirect.com/science/article/abs/pii/0168851095007865.

WHO (1946) Constitution of the WHO. Available at: https://www.who.int/about/accountability/governance/constitution.

WHO (2018a) 13th General Programme of Work 2019–2023. Available at: https://iris.who.int/bitstream/handle/10665/324775/WHO-PRP-18.1-eng.pdf?sequence=1.

WHO (2019) GPW13 Results Framework. Available at: https://iris.who.int/bitstream/handle/10665/324775/WHO-PRP-18.1-eng.pdf?sequence=1.

WHO (2020a) External and internal audit recommendations: progress on implementation. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA73/A73_29-en.pdf.

WHO (2020b) Report of the External auditor. Available at: https://iris.who.int/bitstream/handle/10665/339556/A73_27-en.pdf?sequence=1.

WHO (2020c) Report of the Internal Auditor. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA73/A73_28-en.pdf.

WHO (2020d) Thirteenth General Programme of Work (GPW13) Methods for impact measurement. Available at: https://iris.who.int/bitstream/handle/10665/341371/9789240012776-eng.pdf?sequence=1.

WHO (2020e) WHO Basic Documents, 49th Edition. Available at: https://apps.who.int/gb/bd/pdf_files/BD_49th-en.pdf.

WHO (2021a) Evaluation of WHO transformation Volume 1- Report. Available at: https://cdn.who.int/media/docs/default-source/evaluation-office/who-transformation-final-report.pdf?sfvrsn=c20b7baa_5.

WHO (2021b) External and internal audit recommendations: progress on implementation 2021 (A74/37). Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA74/A74_37-en.pdf.

WHO (2021c) Report of the External Auditor. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA74/A74_34-en.pdf.

WHO (2021d) Internal audit reports at WHO. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA74/A74_35-en.pdf.

WHO (2021e) Synthesis of Country Programme Evaluations. Available at: https://cdn.who.int/media/docs/default-source/evaluation-office/cpe-synthesis-final-report.pdf?sfvrsn=400a58b1_1&download=true.

WHO (2021f) WHO output score card scoring dimensions, attributed, criteria. Available at: https://cdn.who.int/media/docs/default-source/results-reports/output-scorecard-12-may-2021-final-instrument-1.pdf?sfvrsn=29b5e19b_5&download=true.

WHO (2021g) WHO transformation - Transforming for enhanced country impact (2021 Report by the Director-General). Available at: https://apps.who.int/gb/ebwha/pdf_files/EB148/B148_32-en.pdf.

WHO (2021h) Management Response Plan 2021-2022. Available at: https://cdn.who.int/media/docs/default-source/ethics/who-management-response-20211020-finalv2.pdf?sfvrsn=591a9adf_12&download=true.

WHO (2021i) A74/51 External and internal audit recommendations: progress on implementation. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA74/A74_51-en.pdf.

WHO (2021j) EB 148/4 Preventing sexual exploitation, abuse, and harassment. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA74/B148_REC1_EXT-en.pdf.

WHO (2021k) Human Resources: update. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB148/B148_44-en.pdf.

WHO (2021l) IOAC sub-committee on the prevention of sexual exploitation, abuse and harassment (PRSEAH). Available at: https://www.who.int/groups/independent-oversight-and-advisory-committee/subcommittee-on-prseah.

WHO (2021m) Human Resources: update. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB150/B150_45-en.pdf.

WHO (2022a) A healthy return: investment case for a sustainably financed WHO. Available at: https://www.who.int/about/funding/invest-in-who/investment-case-2.0.

WHO (2022b) Report of the IOAC for the WHO Health Emergencies Programme’s Subcommittee for the Prevention and Response to Sexual Exploitation, Abuse and Harassment. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB150/B150_34-en.pdf.

WHO (2022c) Bureau proposals on the outstanding recommendations of the working group to the seventy fifth world health assembly. Available at: https://apps.who.int/gb/wgsf/pdf_files/wgsf7/WGSF_7_3-en.pdf.

WHO (2022d) Deliberations of the Bureau of the Working Group on Sustainable Financing on options for an increase in assessed contributions - Background document. Available at: https://apps.who.int/gb/wgsf/pdf_files/wgsf7/WGSF_7_INF2-en.pdf.

WHO (2022e) External and internal audit recommendations: progress on implementation. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_37-en.pdf.

WHO (2022f) Internal audit reports at WHO. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_35-en.pdf.

WHO (2022g) External audit reports at WHO. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_36-en.pdf.

WHO (2022h) Meeting report of the Working Group on Sustainable Financing. Available at: https://apps.who.int/gb/wgsf/pdf_files/wgsf7/WGSF_7_4-en.pdf.

WHO (2022i) Programme budget 2022–2023: revision Extending the Thirteenth General Programme of Work, 2019–2023 to 2025. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_8-en.pdf.

WHO (2022j) Rationale for an increase in assessed contributions: Background document. Available at: https://apps.who.int/gb/wgsf/pdf_files/wgsf7/WGSF_7_INF1-en.pdf.

WHO (2022k) Report of the 37th meeting of the Independent Expert Oversight Advisory Committee, 6-8 April 2022. Available at: https://apps.who.int/gb/ieoac/PDF/37/37th_Report.pdf.

WHO (2022l) Report with recommendations of the Agile Member States Task Group to recommend long-term improvements. Available at: https://apps.who.int/gb/amstg/pdf_files/AMSTG3/EB_AMSTG3_4-en.pdf.

WHO (2022m) Strengthening WHO’s budgetary, programmatic and financing governance - Secretariat implementation plan on reform. Available at: https://apps.who.int/gb/amstg/pdf_files/AMSTG3/EB_AMSTG3_3-en.pdf.

WHO (2022n) Sustainable financing: report of the Working Group (Report by the Director-General). Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_9-en.pdf.

WHO (2022o) Prevention of sexual exploitation, abuse and harassment Report by the Director-General. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_29-en.pdf.

WHO (2023a) Independent Evaluation of WHO 13th General Programme of Work. Available at: https://cdn.who.int/media/docs/default-source/evaluation-office/evaluation-report-gpw13.pdf?sfvrsn=215b2a79_4&download=true.

WHO (2023b) Financing and implementation of the Programme budget 2022–2023 and outlook on financing of the Programme budget 2024–2025. Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA76/A76_18-en.pdf.

WHO (2023c) Prevention of sexual exploitation, abuse and harassment. Available at: https://www.who.int/initiatives/preventing-and-responding-to-sexual-exploitation-abuse-and-harassment.

WHO (2023d) Proposed programme budget 2024–2025. Available at: https://www.who.int/about/accountability/budget/programme-budget-digital-platform-2024-2025.

WHO (2023e) Results Report 2022 (Programme budget 2022–2023: performance assessment). Available at: https://apps.who.int/gb/ebwha/pdf_files/WHA76/A76_16-en.pdf.

WHO (2023f) Sustainable financing: WHO investment round. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB154/B154_29-en.pdf.

WHO (2023g) WHO presence in countries, territories and areas 2023 Report. Available at: https://iris.who.int/bitstream/handle/10665/367811/9789240073272-eng.pdf?sequence=1.

WHO (2023h) WHO Results Framework: Delivering a measurable impact in countries. Available at: https://cdn.who.int/media/docs/default-source/documents/ddi/23112023_who-results_framework_delivering-a_measurable_impact-in-countries.pdf?sfvrsn=1354088c_3&download=true.

WHO (2023i) Core Voluntary Contributions Account 2022 Annual Report. Available at: https://iris.who.int/handle/10665/371360.

WHO (2023j) Independent evaluation of WHO's results-based management framework, Final Report. Available at: https://cdn.who.int/media/docs/default-source/evaluation-office/rbm-final-evaluation-report.pdf?sfvrsn=2663b1c1_3&download=true#:~:text=The%20evaluation%20considered%20RBM%20as,to%20prioritize%20and%20deprioritize%20actions.

WHO (2023l) Preventing and responding to sexual misconduct. WHO’s three-year strategy, 2023 - 2025. Strategy Framework. Available at: https://iris.who.int/bitstream/handle/10665/366300/9789240069039-eng.pdf?sequence=1.

WHO (2023m) Preventing and responding to sexual misconduct. WHO’s three-year strategy, 2023 - 2025. Strategy Framework. Available at: https://iris.who.int/bitstream/handle/10665/366297/WHO-DGO-PRS-2023.1-eng.pdf.

WHO (2023n) WHO Policy on Preventing and Addressing Sexual Misconduct.	Available at: https://cdn.who.int/media/docs/default-source/campaigns-and-initiatives/prseah/who-policy-on-preventing-and-addressing-sexual-misconduct.pdf?sfvrsn=7bb1dd5b_28&download=true.

WHO (2023o) Preventing and responding to sexual misconduct. WHO‘s three-year strategy, 2023-2025 - Accountability Framework. Available at: https://iris.who.int/bitstream/handle/10665/366299/WHO-DGO-PRS-2023.2-eng.pdf?sequence=1.

WHO (2023p) Preventing and responding to sexual misconduct. WHO’s three-year strategy, 2023 – 2025 - Monitoring and evaluation framework, Year-1 implementation plan. Available at: https://cdn.who.int/media/docs/default-source/campaigns-and-initiatives/prseah/who-dgo-prs-2023.3-eng.pdf?sfvrsn=2738f6cb_3.

WHO (2023q) Implementation Plan (IP) of the WHO Management Response to the Report of the Independent Commission to investigate allegations of sexual abuse and exploitation during the response to the 10th Ebola Virus Disease epidemic in the provinces of North Kivu and Ituri, the Democratic Republic of the Congo. Available at: https://cdn.who.int/media/docs/default-source/documents/ethics/implementation_plan_sexual_exploitation_response_ebola_epidemic.pdf?sfvrsn=add0e790_4&download=true.

WHO (2023r) Human Resources: update. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB152/B152_47-en.pdf.

WHO (2023s) WHO Gender Parity Policy, 2023-2026. Available at: https://cdn.who.int/media/docs/default-source/documents/gender/gender_parity_policy_march_2023.pdf?sfvrsn=7d3393cc_1#:~:text=The%20updated%20WHO%20Gender%20Parity,and%20HQ%20departments%20of%20WHO.

WHO (2023t) Transformation of the regional office including organization and workplace culture change. Available at: https://cdn.who.int/media/docs/default-source/wpro---documents/regional-committee/session-74/rc74-inf-2-transformation-of-ro-and-wpc.pdf?sfvrsn=1b5df3a3_1.

WHO (2023u) GPG Meeting Agenda (31 July 2023): Action Plan by the ARG (internal document).

WHO (2023v) Core Predictable Country Presence (internal document).

WHO (2024a) Draft fourteenth general programme of work. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB154/B154_28-en.pdf.

WHO (2024b) Human Resources: update. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB154/B154_46-en.pdf.

WHO (2024c) Matters emanating from the Agile Member States Task Group on Strengthening WHO’s Budgetary, Programmatic and Financing Governance. Available at: https://apps.who.int/gb/ebwha/pdf_files/EB154/B154_33Add3-en.pdf.

WHO (2024d) Making WHO reliable, impactful, relevant in every country (internal document).

WHO (n.d.) Programme Budget Web Portal. Available at: https://open.who.int/2022-23/budget-and-financing/flow.

WHO (n.d.) How WHO is funded: Programme Budget Explainer. Available at: https://www.who.int/about/funding.

WHO (n.d.) Allocation of flexible funds and proposed key performance indicators for sustainable financing. Available at: https://www.who.int/about/accountability/budget/programme-budget-digital-platform-2024-2025/allocation-of-flexible-funds-and-proposed-key-performance-indicators-for-sustainable-financing.

WHO (n.d.) Evaluation workplan 2022-2023. Available at: https://www.who.int/about/what-we-do/evaluation/resources/evaluation-workplan-2022-2023.

WHO (n.d.) WHO Governance. Available at: https://www.who.int/about/accountability/governance.

WHO (n.d.) WHO structure. Available at: https://www.who.int/about/structure.

WHO (n.d.) Triple Billion Dashboard. Available at: https://www.who.int/data/triple-billion-dashboard.

WHO (n.d.) WHO Governance. Available at: https://apps.who.int/gb/gov.

WHO (n.d.) PBAC39. Available at: https://apps.who.int/gb/pbac/e/e_pbac39.html.

WHO (n.d.) EB154. Available at: https://apps.who.int/gb/e/e_eb154.html.

WHO Foundation (No date) WHO Foundation Strategy 2023-2025. Available at: https://strategy.who.foundation/wp-content/uploads/2023/03/WHO_Foundation_Executive_Summary.pdf.

Zarocostas, J. (2022) WHA sees changes to health regulations and WHO funding. The Lancet, 399(10341):2090-2091. Available at: https://www.thelancet.com/journals/lancet/article/PIIS0140-6736(22)01007-8/fulltext.

Zuurmond, I. (2022) Evaluability assessment of the UK Core Voluntary Contribution to the WHO: Light touch mapping of evaluations and reviews (Internal Document).

Keller, J., Landers, C. and Martinez, N. (2024) The 2024-2025 Replenishment Traffic Jam: Are We Headed for a Pileup? Centre for Global Development. Available at: https://www.cgdev.org/blog/2024-2025-replenishment-traffic-jam-are-we-headed-pileup

Mukesh, K. (2023) Shenanigans in WHO South-East Asia as Politician’s Daughter Contests Regional Director Election. Health Policy Watch. Available at: https://healthpolicy-watch.news/shenanigans-in-who-south-east-asia-as-politicians-daughter-contests-for-election-as-regional-director/

Kickbusch, I. (2020) No “Back to Normal” for the WHO. CIGI. Available at: https://www.cigionline.org/articles/no-back-normal-who/.

Mazzucato, M. and Kickbusch, I. (2021) The WHO's Penny-Wise and Health-Foolish Members. Project Syndicate. Available at: https://www.project-syndicate.org/commentary/world-health-organization-needs-adequate-financing-by-mariana-mazzucato-and-ilona-kickbusch-1-2021-12?barrier=accesspaylog.

Moser, F. and Bump, J. (2022) Assessing the World Health Organization: What does the academic debate reveal and is it democratic? Social Science & Medicine, 314:115456. Available at: https://doi.org/10.1016/j.socscimed.2022.115456.

Braun, V. and Clarke, V. (2006) Using thematic analysis in psychology. Qualitative Research in Psychology, 3(2):77–101. Available at: doi: 10.1191/1478088706qp063oa.
# Annex 3: KII Questions

	FCDO WHO hub	FCDO Technical	FCDO Country	WHO reform	WHO Technical	WHO politics/budget/financing	Donors/MS	Independent
Q1	x	x	x			x
Q2	x	x	x
Q3	x	x	x
Q4	x	x	x	x		x
Q5				x		x
Q6a						x
Q6b	x	x			x	x
Q7a		x	x	x	x	x
Q7b				x		x
Q7c				x	x	x
Q8a				x		x
Q8b				x		x
Q9a				x		x	x	x
Q9a				x		x	x	x
Q9b							x
Q10.				x	x	x
Q11a				x	x	x	x
Q11b				x	x	x
Q12	x	x	x
Q13	x	x	x
Q14a	x					x	x	x
Q14b				x		x	x	x
Q14c	x	x	x	x		x	x	x
Q14d	x	x	x	x		x	x	x
Q15a	x	x	x	x	x	x	x	x
Q15b	x	x	x				x	x
Q16a			x	x
Q16b			x	x	x	x		x
Q17a	x				x	x		x
Q17b					x	x
Q17c						x

# Annex 4: Key Informants Interviewed
Donor/member state
1	Senior Policy Officer, Netherlands Ministry of Foreign Affairs
2	Counsellor (Development), Permanent Mission of Australia to the UN in Geneva
3	Health Adviser, Permanent Mission of Australia to the UN in Geneva
4	Director, Global Health Agencies and Funds (GHAF), Gates Foundation
5	Deputy Director for Multilateral Engagement and G&/G20, DHSC, UK government
FCDO country
6	Former Health Adviser, FCDO Pakistan
FCDO hub
7	Deputy Permanent Representative, Global Health, UK Mission, Geneva
8	Deputy Head, Global Health Institutions Dept.
9	Former Senior Responsible Officer, WHO CVC programme,
10	Former Head/Deputy Head of Global Health Institutions Dept and former Senior Responsible Officer, WHO CVC programme
11	Senior Responsible Officer, WHO CVC programme, Global Health Institutions Dept.
FCDO technical
12	Policy Lead, Climate Change and Health
13	Policy Lead, Health Systems Strengthening
14	Policy Lead, Global Health Security
15	Policy Lead, WASH,
16	Head of Profession, Health
17	Policy Lead, RMNCH
Independent expert
18	Former Head of the Global Health Centre Graduate Institute, Geneva
19	Former Global Health Ambassador, Sweden
20	Senior Lecturer, Queen Mary University, London
21	Former Director of Replenishments, Gavi
22	London School of Hygiene and Tropical Medicine
23	Deputy Head, Global Health Program, Center for Global Development (CGD)
24	Senior Research Fellow, Chatham House
25	Co-Director, Global Health Centre, Graduate Institute, Geneva.
26	Director Global Health Diplomacy, Joep Lange Institute
27	Founding Editor, Geneva Health Files
WHO Reform
28	WHO Representative, Thailand and member of Action Results Group (ARG)
29	Senior Adviser, Organisational Change
30	Director, Country Support and Strategy
31	Head, Country Strategy and Transformation
32	WHO Representative, Nigeria and member of Action Results Group (ARG)
WHO Politics/Budget/Financing
33	Director, Planning, Resource Coordination and Performance Monitoring
34	Technical Officer, Strategic Engagement, External Relations and Governance
35	Assistant Director General, UHC/Life Course
WHO Technical
36	Director, Preventing and Responding to Sexual Exploitation
37	Director, Research for Health/Special Programme for TDR
38	Technical Officer, Preventing and Responding to Sexual Exploitation
39	Technical Officer, Preventing and Responding to Sexual Exploitation

# Annex 5: Evaluation Framework

The table below presents the Evaluation Framework which collates all the overarching and expanded evaluation questions (EQs), and lines of enquiry mapped to each objective. Further, the framework identifies each of the sources of evidence and research tools that was used to evaluate each of these questions.
Criteria	Evaluation question	Expanded evaluation question	Analytic methods	Data sources
Objective 1: To explore the relative importance of WHO CVC programme funding and other UK inputs, and the way these synergies have affected or limited change (learning review of the synergies between CVC funding and other UK inputs)
Coherence	How coherently have the different elements of the programme worked together?	In what ways do the different UK inputs interact? How well have these inputs interacted?	Thematic analysis / Primary data analysis - descriptive	Desk review / KIIs / Online survey
Coherence	What are the synergies among the different UK inputs (flexible funding, PBR, and expertise and influencing)?	What have been the benefits to these synergies? Have there been any downsides?	Thematic analysis	KIIs
Coherence	To what extent has FCDO optimised the synergies among UK inputs?	Are the synergies among the inputs optimised? What are ways for FCDO to optimise these synergies?	Thematic analysis	KIIs
		What challenges has FCDO encountered to optimizing these synergies?	Thematic analysis	KIIs
Objective 2a: To explore the extent to which the flexibility of CVC funding has contributed to the delivery of the reform agenda and GPW13, and how the WHO CVC programme and PBR mechanism has affected the political economy of decision making at the WHO: i) whether the UK has influenced other funders of WHO, e.g., to increase the flexibility and level of their funding (learning about CVC as a funding mechanism)
Relevance	How well did the design of the FCDO’s CVC programme (including the PBR element) respond to WHO’s reform agenda?	How was the FCDO’s CVC programme (including the PBR element) intended to support the WHO’s reform agenda?	Triangulation / Thematic analysis	Desk review / KIIs
		Was the FCDO’s CVC programme well-suited to support the delivery of the WHO’s reform agenda?	Thematic analysis	KIIs
		What would make the CVC programme support more responsive to the WHO’s reform agenda?	Thematic analysis	KIIs
Effectiveness	To what extent has the WHO CVC programme funding facilitated the more effective delivery of the WHO reform agenda?	In what ways did the CVC programme funding support the reform agenda (at global, regional & country levels)?	Triangulation / Thematic analysis / Primary data analysis – descriptive	Desk review / KIIs / Online survey
Effectiveness	What role has the PBR component had in incentivising organisational change?		Thematic analysis	KIIs
Effectiveness	To what extent has WHO CVC programme funding facilitated the more effective delivery of the GPW13 by WHO (global, regional, country)?	In what ways did WHO’S CVC programme funding support the more effective delivery of GPW13 by WHO (at global, regional & technical levels) compared to when the UK’s previous model was in place?	Thematic analysis / Primary data analysis – descriptive	KIIs / Online survey
		Has the CVC funding mechanism influenced or enabled WHO staff and decision-making units to allocate funding differently, compared to when the UK’s previous model was in place?	Secondary data analysis – descriptive	Desk review / KIIs
		How did the WHO make decisions about funding allocations prior to the introduction of flexible funding? How are decisions about funding allocations made now?	Thematic analysis	KIIs
		What has changed in the political economy of decision-making at the WHO since the introduction of flexible funding? Has this affected the efficiency of decision-making / resource allocation?	Thematic analysis	KIIs
Effectiveness	What might the WHO have done differently, had the UK’s CVC funding been 100% flexible?	What might the WHO have done differently with regards to the implementation of their reform agenda, had the UK’s CVC funding been 100% flexible?	Thematic analysis	KIIs
		What might the WHO have done differently with regards to the implementation of GPW13, had the UK’s CVC funding been 100% flexible?	Thematic analysis	KIIs
Coherence	How well has the UK approach to funding the WHO aligned with other donors funding practices and has it led to an improved funding environment for WHO?	Has the WHO seen an increase in flexible funding since the UK’s CVC funding programme began?	Secondary data analysis – descriptive	Desk review
		Has donor interest in providing flexible funding to the WHO increased since the UK’s CVC programme began? To what extent has the UK’s CVC programme approach influenced any shifts?	Thematic analysis	KIIs
Objective 2b: To explore the extent to which the flexibility of CVC funding has contributed to the delivery of the reform agenda and GPW13, and how the WHO CVC programme and PBR mechanism has affected the political economy of decision making at the WHO: ii) whether this model of funding has influenced or enabled WHO staff and decision-making units to allocate funding differently internally, compared to the UK’s previous earmarking models. (learning about CVC as a funding mechanism)
Relevance	How well did the design of FCDO’s WHO CVC programme (including the PBR element) respond to WHO funding issues?	In what ways did the availability of flexible funding from FCDO’s WHO CVC programme enable the WHO to be more agile and responsive to emerging and evolving needs?	Thematic analysis	KIIs
		What have been the benefits to the WHO of having this funding?	Thematic analysis	KIIs
		Have there been any negative or unintended consequences of CVC funding?	Thematic analysis	KIIs
		Have there been any unintended consequences (positive or negative) of CVC funding?	Thematic analysis	KIIs
Objective 2c: To explore the extent to which the flexibility of CVC funding has contributed to the delivery of the reform agenda and GPW13, and how the WHO CVC programme and PBR mechanism has affected the political economy of decision making at the WHO: iii) the relative importance of PBR and the UK’s annual ‘top deliverables’ on influencing WHO’s prioritisation of work and resource allocation within GPW13. (learning about CVC as a funding mechanism)
Coherence	To what extent has CVC funding to the WHO changed the UK’s influence vis-à-vis WHO and how?	How is work prioritised in the WHO and has the availability of CVC funding (fully flexible vs PBR) influenced this prioritisation?	Thematic analysis	KIIs
		Has the PBR mechanism specifically influenced what WHO works on? For example, has the WHO tackled issues/outputs they may not have otherwise tackled without the PBR mechanism (both on the WHO reform agenda and within the GPW13)?	Thematic analysis	KIIs
		How has FCDO’s influence on the WHO’s decision-making/prioritisation changed since the introduction of CVC?	Thematic analysis / Primary data analysis – descriptive	KIIs / Online survey
Objective 3: To conduct a short analysis of how the FCDO has approached the evaluation of the current WHO CVC programme and issue recommendations on how best to incorporate evaluation effectively into the next programme (Learning about evaluation)
Effectiveness	To what extent has FCDO used the information gathered through the WHO Results Framework?	How has FCDO used monitoring, evaluation and learning to inform the design and implementation of the WHO CVC funding programme? What types of information have been most helpful? What information do you wish you had?	Thematic analysis	KIIs
Efficiency	What are the lessons learnt from the approach to MEL?	What lessons have been learned from the existing MEL approach, and how have they informed any changes to their approach?	Thematic analysis	KIIs

# Annex 6: Theory of Change
The Theory of Change (ToC) below revises the ToC in the original Business Case and was used as a basis for the evaluation.

The Theory of Change (ToC) below represents a ToC for future UK flexible funding support to the WHO that reflects the recommendations of the evaluation.

# Annex 7: Literature Review Search Terms

Concept of interest	Search Terms
FCDO	FCDO / NB: ‘Foreign, Commonwealth Development Office’ not included as the search results were too many and irrelevant
WHO	WHO OR World Health Organization OR World Health Organisation
Core Voluntary Funding	Core Voluntary Funding OR Core Voluntary Funding Account OR Voluntary contributions OR Flexible funding OR CVC OR CVCA OR VC OR Funding OR Financing
Reform agenda	Reform agenda OR Transformation OR Organisational change OR Enabler
GPW13	General Programme of Work OR GPW13 OR Thirteenth General Programme of Work OR GPW OR GPW14
PSREAH	Preventing and Responding to Sexual Exploitation, Abuse Harassment OR PRSEAH OR Sexual Exploitation, Abuse Harassment OR SEAH OR Preventing Sexual Abuse Harassment OR PSEAH
Staffing	Staffing OR Human Resources OR Contractors OR HR OR Staff
Payment by Results	Payment by Results OR PBR
Budget	Budget OR Budget allocation

# Annex 8: [redacted]

# Annex 9: Key Informant Interview (KII) Guide

Key Informant Category:

[Begin recording]

Introductory Statement

Hello, my name is _______________. Thank you for agreeing to participate in this interview today. Let’s start with introductions beginning with the evaluation team.

The purpose of the interview is to understand your thoughts, opinions, and experiences around the effectiveness of the Core Voluntary Contribution (CVC) funding mechanism from the UK Foreign Commonwealth and Development Office (FCDO) to the World Health Organisation.

To give you some background, the UK government has been a longstanding leader in advancing global health. The WHO stands at the heart of international health, therefore, a high-performing and effective WHO is critical to the UK government’s global health priorities. In 2021, FCDO allocated £340m CVC funding to WHO over 4 years, from 2020/21 to 2023/24.

We have been appointed to conduct an evaluation of this funding programme to strengthen FCDO’s knowledge on whether and how the UK’s commitment to CVC funding is contributing to effective reform of the WHO and ultimately better health impact. This evaluation will inform the design, management, oversight and delivery of future FCDO engagement and funding of the WHO, as well as learning around specific aspects of WHO transformation and delivery over the period of the programme.

As part of this evaluation, we are carrying out interviews to understand key informants’ thoughts, opinions and experiences. You have been selected for this interview because we feel that you would be able to share some valuable information. However, please know that there are no right or wrong answers. We just want to hear your opinion.

We will be taking some notes and recording the interview as we speak to help with analysis. However, what is said here will remain confidential and we will anonymise the use of any material such as quotes from the interviews.

Are you content to proceed on that basis and do you have any questions before we begin?

To start I’d ask you to describe your role, as well as how you interact with the WHO.

Interview questions

We will start off by discussing the relative importance of WHO CVC programme funding and other UK inputs.

Question 1. FCDO provides WHO with expertise and influencing alongside the flexible funding and PBR element. How do these different inputs interact or work together?
Q1 Probe 1: How well do they interact?
Q1 Probe 2: In what way has this changed over time?
Q1 Probe 3: Please list any inputs that have worked together especially well?
Q1 Probe 4: Please describe any inputs that you do not feel are useful or are not working well and why?

Question 2. Can you tell me your thoughts about the synergies among the different UK inputs, such as flexible funding, PBR, and expertise and influencing?
Q2 Probe 1: What benefits have you noted?
Q2 Probe 2: What challenges have you noted?

Question 3. Can you tell me your thoughts about whether these synergies are optimised?
Q3 Probe 1: What mechanisms or interventions could deliver greater coherence into the future?
Q3 Probe 2: How can the benefits be maximised going forward?
Q3 Probe 3:  What challenges has FCDO encountered with optimising synergies?
Q3 Probe 4: How can they be minimised in the future?

Now I would like us to talk about the impact and influence of the CVC programme, including whether the UK has influenced other donors.

Question 4. Could you share your thoughts on the design of FCDO’s CVC programme and how well suited it has been to support the WHO’s reform agenda?
Q4 Probe 1: What were the intentions around the design of the programme?
Q4 Probe 2: How might future CVC programming be designed to support ongoing WHO transformation?

Question 5. How and to what extent has the FCDO CVC programme facilitated more effective delivery of the WHO reform agenda across the organisation?
Q5 Probe 1: In what ways did the CVC programme support the reform agenda at global, regional & country levels?
Q5 Probe 2: What were the key mechanisms of support (e.g. funding, influencing, technical engagement)?

Question 6a. What role has the PBR component had in incentivising organisational change?
Q6a Probe 1: How are the key asks defined?

Question 6b. How should the PBR component be designed in the future to appropriately balance the WHO need for flexibility against the FCDO desire for accountability and policy influence?

Question 7a. Compared to when the UK’s previous model was in place, to what extent has the CVC funding model facilitated more effective delivery of the GPW13?
Q7a Probe 1: How has it facilitated more effective delivery of the GPW13 at the global, regional, technical, thematic levels?

Question 7b. How does decision making about funding allocations differ compared to the previous model?
Q7b Probe 1: What has changed in the political economy of decision-making at the WHO?
Q7b Probe 2: How has it affected the efficiency of decision-making / resource allocation?
Q7b Probe 3: How has it influenced or enabled WHO staff and decision-making units to allocate funding differently?

Question 7c. What have been the positive and negative consequences of the introduction of CVC funding on the work you personally do at WHO?

Question 8a. What might the WHO have done differently had the UK’s CVC funding been 100% flexible?
 Q8a Probe 1: How would 100% flexible funding affect implementation of the reform agenda?
Q8a Probe 2: How would 100% flexible funding affect implementation of GPW13?

Question 8b. What would be the future implications of a shift to 100% flexible funding?

Question 9a. How would you say interest in providing flexible funding to the WHO has changed since the UK’s CVC programme began?
Q9a Probe 1: To what extent, if any, has the UK’s CVC programme approach influenced any shifts in flexible funding from other donors
Q9a Probe 2: How would you say the introduction of the UK's CVC programme has made other donors consider providing more flexible funding to WHO?
Q9a Probe 3: Has the WHO seen an increase in flexible funding since the UK’s CVC funding programme began?

Continuing on the topic of impact and influence, I would like us to talk about whether the CVC programme has impacted WHO staff and decision-making units with respect to internal allocation of funds.

Question 10. How would you say the design of FCDO’s WHO CVC programme (including the PBR element) responded to WHO funding issues?
Q10 Probe 1: in what ways has it enabled the WHO to be more agile and responsive to emerging and evolving needs?
Q10 Probe 2: What benefits to WHO have you noted?
Q10 Probe 3: What negative or unintended consequences to WHO have you noted?

Next, we will discuss the relative importance of PBR and the UK’s annual ‘top deliverables’ on influencing WHO’s prioritisation of work and resource allocation within GPW13.

Question 11a. How is work prioritised at the WHO and has the availability of CVC funding (fully flexible vs PBR) influenced this prioritisation?

Question 11b. To what extent has CVC funding to the WHO changed the UK’s influence vis-à-vis WHO and how?
Q11b Probe 1: In what way has the availability of CVC funding influenced this prioritisation?
Q11b Probe 2: How has UK influence on thematic WHO priorities changed?
Q11b Probe 3: Has the PBR mechanism specifically influenced issues WHO chooses to work on?

Question 12. How has FCDO used monitoring, evaluation and learning to inform the design and implementation of the WHO CVC funding programme?
Q12 Probe 1: Can you tell me about your experience with the WHO results framework to assess WHO performance in your area of focus?
Q12 Probe 2: What other WHO sources of information do you use to assess performance and progress?
Q12 Probe 3: What types of information have been most helpful?
Q12 Probe 4: what gaps in information have you noted?

Question 13. What lessons have been learned from the existing MEL approach, and how can they inform any changes to the approach?
Q13 probe 1: What changes have been made?
Q13 Probe 2: How could MEL be strengthened in a future programme?

I will now ask you questions about the process of evaluating the current WHO CVC programme and how learnings can be incorporated into the next programme.

Question 14a. WHO has sought funding that is more predictable, flexible and diversified. To what extent has that been successful over the programme period?

Question 14b. In your opinion, to what extent has better funding supported overall WHO transformation and GPW delivery?

Question 14c. Alongside better funding, what additional reforms, including from WHO, do you think are needed to ensure sustained progress into the future?
Q14c Probe 1: What is needed from WHO to complement better funding and deliver sustainable progress?

Q14d What should funders expect to see in terms of progress and on what time-frame?
Q14d Probe 1: How can progress be measured?
Q14d Probe 2: How should progress be measured in the future?

Question 15a. How has the WHO sustainable financing agenda advanced since 2020 and what driving forces have there been?
Q15a Probe 1: What have been the key triggers that have shifted behaviour and unlocked progress?
Q15a Probe 2: What have been the key trends, decisions and commitments around sustainable financing?

Question16b. In what ways does the sustainable funding agenda interact with WHO staffing?

Question 17a. What have been the key elements of the Preventing and Responding to Sexual Exploitation, Abuse and Harassment (or PRSEAH) agenda over the past few years and which have been most important?

Question 17b Since 2020, what has been achieved with respect to strengthening the critical systems for PRSEAH?
Q17b Probe 1: How is progress measured?
Q17b Probe 2: How should progress be measured in the future?

Question 17c. In what ways does the sustainable funding agenda interact with PRSEAH progress?

Concluding remarks

Those are all the questions that I have for you today. Is there anything else that you would like me to know or would like to ask me?

Thank you for sharing your thoughts and experiences with me. We value your input – if there is anything that comes to mind after the interview please do reach out. And, to remind, this interview and any follow up is confidential and nothing will be attributed that could identify you.

Annex 10: Terms of Reference for the Evaluation (Please see the next page)

ITT Vol. 2

Project_10213

Terms of Reference

Evaluation of WHO Core Voluntary Contribution (CVC) programme.

Contents

Abbreviations/Acronyms ....................................................................................................................3

1. Introduction ....................................................................................................................................4

2. Context ............................................................................................................................................4

3. Recipient & Beneficiaries ................................................................................................................4

4. Background to the WHO Core Voluntary Contribution (CVC) programme.....................................4

5. The Purpose of Evaluation ..............................................................................................................5

6. Evaluation objectives ......................................................................................................................5

7. The Scope ........................................................................................................................................6

8. Methodology..................................................................................................................................8

9. Contract Duration and Formal Review Point ..................................................................................8

10. Skills and Competency Requirements.........................................................................................10

11. Payment Mechanism..................................................................................................................10

12. Reporting Requirements .............................................................................................................11

13. Risk management requirements.................................................................................................11

16. General Data Protection Regulations (GDPR) .............................................................................11

17. List of Annexes ............................................................................................................................12
Abbreviations/Acronyms

AR Annual Review

BC Business Case

CVC Core Voluntary Contribution (Fully flexible funding) CY	Calendar Year
DFID Department for International Development

ELVAR Evaluation, Learning and Verification for Agency Reform EQuALS Evaluation Quality Assurance and Learning Services FCDO Foreign, Commonwealth and Development Office
FY Financial Year

GPW General Programme of Work

HMG His Majesty’s Government

KPI Key Performance Indicator

MEL Monitoring, Evaluation & Learning

MOPAN Multilateral Organisation Performance Assessment Network

MOU Memorandum of Understanding

PBR Payment by Results

PCR Programme Completion Report

PF	Performance Framework SRO Senior Responsible Owner ToC	Theory of Change
ToR Terms of Reference

UN United Nations

VfM Value for Money

WHO World Health Organization

1. Introduction

1.1 The Foreign Commonwealth and Development Office (FCDO) is seeking a Supplier to deliver an evaluation of FCDO’s core voluntary funding programme to World Health Organisation (WHO) from
2020 to 2024.

1.2 This Terms of Reference outlines the objectives, requirements and, expectations of the Supplier. The evaluation is expected to run for up to five months between the end-November 2023 – end of April
2024.

1.3. The budget for this Contract is limited to up to £300,000 inclusive of all government taxes.

2. Context

Programme Context and Budget

2.1 WHO plays an important role in the achievement of the UK’s global health policy objectives. WHO has, as the lead UN agency dedicated to promote health, a unique mandate to coordinate Members States and advance health and well-being for all, and to set global guidelines and standards. A strengthened WHO is an objective in the HMG Global Health Framework (2023) (Annex C.3).

2.2 The 2017-18 MOPAN Assessment of WHO noted increasing flexible funding as a key strategic issue for WHO given that a high proportion of the organisation’s funds were subject to tight earmarking and therefore driven by donors’ requirements and by disease area1. It noted that the heavy reliance on earmarked funding has limited the organisation’s ability to flexibly respond to country-level needs and changes in context. There is mounting evidence of the reduction to efficiency caused by earmarking2 3.

2.3 To support and strengthen WHO in addressing these longstanding challenges, in 2020, the UK Government announced a £340 million core voluntary contribution (CVC) to WHO for 2020-24. This new programme, hereby referred to as ‘WHO CVC programme’, consolidated several previously earmarked funding streams, into a new, and overall increased, single flexible (unearmarked) contribution. 30% of this annual funding is defined as Payment by Results (PBR) and conditional on the achievement of annually agreed indicators (“top deliverables”, set out in the programme Performance Framework) with the remainder as fully flexible funding4. More information can be found in the WHO CVC Business case (Annex A.3).

3. Recipient & Beneficiaries

3.1. The primary recipient of this evaluation is FCDO (Global Health Directorate and the UK Mission in
Geneva).

3.2 Beneficiaries who will benefit from this evaluation include other donors of WHO, particularly those who provide CVC funding who may benefit from the lessons, and the Department for Health and Social Care (DHSC) who lead the UK Government relationship with WHO. Reports may also be shared with WHO as the partner funded under the UK’s WHO CVC programme.

4. Background to the WHO Core Voluntary Contribution (CVC) programme.

1 WHO MOPAN Assessment 2017-18, 2019
2 Heinzel, M., Cormier, B., & Reinsberg, B. (2023). Earmarked funding and the control–performance trade-off in
international development organizations. International Organization (forthcoming). Online appendix.
3 Iwunna O, Kennedy J, Harmer A. Flexibly funding WHO? An analysis of its donors’ voluntary contributions, BMJ Global Health 2023. Available at: https://gh.bmj.com/content/8/4/e011232
4 The UK’s High-Level Performance Framework for the World Health Organisation Core Voluntary Contribution 2020/21 to 2023/24

4.1 The WHO CVC programme 2020-24 builds upon, and applies the lessons learnt, from the FCDO’s predecessor CVC programme that ran between 2016 and 20205. Since 2020, the UK has been the largest contributor of fully flexible core voluntary contributions6. At the heart of the design of the WHO CVC programme is:

•	increased flexible funding; one pre-requisite for WHO to be the agile, strategic organisation the world needs (especially in response to emerging health threats).
• a clear, prioritised set of UK asks and the use of a performance-conditional funding tranche
(30% of the total) to incentivise WHO’s achievement of specific UK priorities.

4.2 The objectives of the WHO CVC programme as outlined in the FCDO Business Case7 are to support further reform of WHO, especially implementing lessons from the COVID-19 pandemic, to enable WHO to emerge stronger, as an organisation that can:

•	Coordinate a more effective and integrated global approach to health security: ensuring both better pandemic preparedness and emergency response.
•	Play a stronger coordination and convening role in building back resilient health systems world-wide with better health for all; and
•	Provide the highest-quality technical advice to its Member States, tailored to their different contexts.

4.3 In addition, the UK objectives are closely mirrored in WHO’s own 13th General Programme of
Work (GPW) (which has been approved by all 194 Member States, including the UK) and which aims, by end 2023, (now extended to 2025) to:

• Protect 1 billion more people from health emergencies.
• Provide 1 billion more people with access to universal health coverage; and
• Enable 1 billion more people to live healthier lives.

To date, against the £340 million programme budget, a total of £306m has been disbursed.

5. The Purpose of Evaluation

5.1 An evaluability assessment (see Annex A.6) was conducted in 2022 to provide an assessment of the feasibility and proportionality of likely methods needed to evaluate the WHO CVC programme effectively8. The assessment found that the WHO CVC programme is evaluable; there is sufficient existing data, and further qualitative and quantitative data that can be gathered to make a robust evaluation of the WHO CVC programme as it ends in March 2024. The initial assessment was supplemented by a light touch mapping of evaluations and reviews (Annex A.7) to assess the extent to which these evaluations and reviews can be used as key inputs into the evaluation of the WHO CVC programme9. The consolidation of the two reports has informed FCDO’s decision on whether and how to evaluate the WHO CVC programme.

5.2 The primary emphasis of the independent evaluation of the WHO CVC programme is learning. An evaluation focused on learning for FCDO will be beneficial, enabling consideration of how the UK have, and how the UK can in future, effectively support and influence WHO.

6. Evaluation objectives

5 Project Completion Review (PCR)
6 https://www.who.int/about/funding
7 WHO CVC 2020-24 Business Case
8 Evaluability assessment of the Core Voluntary Contribution (CVC) funding to the World Health Organization (WHO)
9 Evaluability assessment of the UK Core Voluntary Contribution to the WHO: Light touch mapping of evaluation and reviews.

6.1 There are four learning evaluation objectives, each with the following outputs:

a) Learning review of the synergies between CVC funding and other UK inputs: To explore the relative importance of WHO CVC programme funding and other UK inputs, and the way these synergies have affected or limited change. The WHO CVC programme Business Case (Annex A.3recognises that CVC is one of several tools for the UK to support and influence WHO. It states that “on its own, the CVC will clearly be insufficient in achieving the UK’s reform objectives. To achieve our objectives, we need to help to build Member State
consensus on meaningful reforms to WHO and the wider health architecture”. Other UK inputs include advocacy, engagement and influencing by HMG staff, for example at WHO’s
governing bodies and bilaterally. The programme planned but did not use a secondment.

b) Learning about CVC as a funding mechanism: To primarily focus on to what extent the flexibility of CVC funding has contributed to the delivery of the reform agenda and GPW13 and how the WHO CVC programme and PBR mechanism has affected the political economy of decision making at the WHO: i) whether the UK has influenced other funders of WHO, e.g. to increase the flexibility and level of their funding; ii) whether this model of funding has
influenced or enabled WHO staff and decision making units to allocate funding differently internally, compared to the UK’s previous earmarking models; and iii) the relative importance
of PBR and the UK’s annual ‘top deliverables ’ on influencing WHO’s prioritisation of work and
resource allocation within GPW13. This component will inevitably be constrained given the following factors: the scale of WHO’s operations; delays in seeing changes occur at outcome
level, which will go beyond the lifetime of this programme and the evaluation; and the
relevance of wider contextual factors that contribute to changes, meaning measuring the UK’s attribution is challenging. As such, it is not possible to fully evaluate the contribution of PBR to incentivising change or outcomes achieved by WHO. However, referring to the Evaluation, Learning and Verification for Agency Reform (ELVAR) study, the aim is to maximise the potential learning around the role of PBR in bringing attention to issues and its ability to support change champions.

c) To support the development of specific pieces of analysis to enhance our understanding of priority areas and how the UK might address these better in future though the delivery of Discrete learning analysis: E.g. Since 2020, what has been the key trends in WHO’s staffing including contractors to staff ratio, technical gaps, gender balance and country representative gaps.

d) Learning about evaluation: To conduct a short analysis of how the FCDO has approached the evaluation of the current WHO CVC programme and recommendations on how best to incorporate evaluation effectively into the next programme. (This analysis should also deliver a Theory of Change (TOC) to ensure facilitation of a future evaluation).

7. The Scope

7.1. The evaluation is a desk-based review during the final year of the WHO CVC programme.

7.2. The evaluation will only cover the core funding component of the programme. It will not include the secondment to WHO which was originally included in the WHO CVC programme Business Case but was closed.

7.3. Whilst the WHO CVC programme is Global, the evaluation will be desk based.

7.4. The evaluation of the WHO CVC programme will be guided by the Organisation for Economic Co- operation and Development Assistance Committee (OECD DAC) criteria in particular – relevance, coherence, effectiveness, and sustainability. The evaluability assessment provides an articulation of the evaluation questions relevant to learning, the primary purpose of the evaluation of the WHO CVC programme.

Evaluation questions

RELEVANCE
	How well did the design of the FCDO’s WHO CVC programme / (including the PBR element) respond to WHO funding issues.
	How well did the design of the FCDO’s WHO CVC programme / (including the PBR element) respond to WHO’s reform agenda.
COHERENCE
	How coherently have the different elements of the programme worked / together?
	What are the synergies between the different UK inputs (flexible / funding, PBR, evaluation, engagement and influencing)?
	To what extent has FCDO optimised the synergies between UK / inputs?
	To what extent has CVC funding to the WHO changed the UK’s / influence vis-à-vis WHO and how?
	How well has the UK approach to funding the WHO aligned with other donors funding practices and has it led to an improved funding environment for WHO?
EFFECTIVENESS
	To what extent has WHO CVC programme funding facilitated the more effective delivery of the WHO Reform agenda?
	To what extent has WHO CVC programme funding facilitated the more / effective delivery of the GPW 13 by WHO? / -At global level / -At Regional level / -At country level
	What would have been different if the UK’s CVC funding had been / 100% flexible?
	What role has the PBR component had in incentivising WHO / organisational change?
	What are the lessons learnt for FCDO to shape the next FCDO WHO / CVC funding programme?
EFFICIENCY
	To what extent has FCDO used the information gathered through the / WHO Results Framework?
SUSTAINABILITY

7

To what extent have the organisational changes supported through CVC funding contributed to the sustained delivery of WHO’s General Programme of Work (GPW) Triple Billion programme, in particular the improved access to quality health services and the rapid detection of
and response to health emergencies

7.5 Discrete learning analysis: in addition to the questions above, the Supplier will develop specific pieces of analysis which will enhance understanding of priority areas and how the UK might address these better in future. E.g., Since 2020, what have been the key trends in WHO’s staffing, including contractor to staff ratio, technical gaps, gender balance, and country representative gaps?

8. Methodology

8.1. The Supplier will submit a draft evaluation design and methodology as a part of their Concept Note proposal. It is expected that a mixed methods design combining analysis of primary and secondary quantitative and qualitative data will be appropriate to respond to the evaluation questions.

8.2. The following data collection methods can be used but shall be agreed during the inception period:

8.3. A desk review of key FCDO programme documents, such as:

a) FCDO, Annual Review, Core Voluntary Contribution (CVC) funding to the World Health
Organization (WHO), 20/21 to 23/24
b) FCDO: Memorandum of Understanding with WHO, Core voluntary contribution (CVC)
funding to the World Health Organization (WHO) 2020/21 to 2023/24, c) FCDO: WHO CVC 2020-24 Business Case,
d) FCDO: WHO CVC 2016-20 Project Completion Report,
e) FCDO: The UK’s High-Level Performance Framework for the World Health
Organisation Core Voluntary Contribution 2020/21 to 2023/24,

8.4 Desk review of WHO reporting, such as:

• WHO MOPAN Assessment 2017-18, 2019
• WHO: Thirteenth General Programme of Work 2019-2023
• WHO Budget Portal
• WHO governing body reports.

8.5 Desk review of relevant academic literature, including analysis and commentary on WHO’s funding model.

8.6 Virtual interviews and/or surveys with key internal stakeholders within FCDO and wider external stakeholders e.g. select WHO staff, donors and civil society/academic experts.

9. Contract Duration and Formal Review Point

The Contract shall run between the end of November 2023 and the end of April 2024 and will be split in two phases Inception and Implementation.

The Contract will have a formal review point at the end of the inception phase to determine whether the Contract should proceed to its implementation. Continuation of the Contract beyond the review point will be subject to Supplier’s performance and acceptance of Inception phase deliverables by FCDO.

Inception phase [end of November 2023- early January 2024 up to 6 weeks]
During the Inception phase, the Supplier shall conduct mapping and review of key relevant programme and policy documentation available to support the evaluation.

The submission of an inception report is expected by the end of week 4, with 2 weeks for iteration and finalisation. During the inception phase the Supplier will have an opportunity to further understand the programme and theory of change.

9.1 The Supplier will deliver the following outputs during the Inception Phase of the Contract:

Outputs/Deliverables		Activities			Completed by end
Draft inception report		a) Initial mapping and review of key relevant programme and policy			Week 4
(no more than 10		documentation available to
single sided pages)		support the evaluation
Final evaluation plan		b) Detail and finalise the evaluation			Week 4
and methodology		design and methodology (a draft
including finalised		design and methodology to be

		Concept Note proposal) to
		include:
		i. Finalised evaluation
		questions, updated
		evaluation workplan to
		deliver the overall scope of work; methodologies
		to answer questions;
		approach to analysis and quality assurance;
		ii. Assessment of the
		overall theory of change
		underpinning the
		programme
Discrete	learning		•	Development and	Week 4
analysis				agreement of approach to discrete learning pieces of analysis as outlined above
				(see 6b and 6c) and
				prioritisation on how far
				resources will be divided
				between focus areas,
				recognising that it will not be possible to examine all in equal depth.
Risk register		c) Update evaluation risk register			Week 4
Final Inception report		d)	Detailed content of the final		Week 6
taking account of			ev	aluation report to be agreed
FCDO comments on / draft.			during the Inception phase after
draft.			the inception report and
			questions have been finalised

evaluation questions.
submitted as a part of the

Implementation Phase [January – April 2024]
9.2 During the implementation phase, the supplier will deliver in line with the agreed evaluation workplan including the discrete learning pieces of analysis as agreed in the inception phase. The submission of the final evaluation report is expected by the end of March 2024 with a month for the final feedback and iteration before finalisation in April 2024. The Supplier will then share and disseminate the final report before the end of April 2024.
9.3 The following final evaluation report products are required:
a. Final summative evaluation report– no more than 50 pages
b. Final evaluation summary (‘evaluation digest’) with key findings and recommendations of the finalised evaluation report – 2 pages.
c. Slide pack/presentation summarising the evaluation findings.

9.4 In terms of dissemination, the Supplier shall deliver at least 2 presentations with internal FCDO stakeholders and WHO. FCDO will lead on dissemination beyond FCDO stakeholders and WHO e.g. the target audience includes other donors/WHO member states who provide Core voluntary funding or who may consider core funding to WHO.

9.5 For the final evaluation summary with key findings and recommendations the FCDO’s template for publication available on FCDO’s website can be used. FCDO/OGD will have unlimited access to the material produced by the supplier.

10. Skills and Competency Requirements

10.1 The Supplier should outline in its Concept Note proposal the proposed team structure they intend to employ and why they believe this to be the best way to deliver the outputs of the Contract. The proposal should demonstrate how the proposed team structure will work to deliver the expected objectives in practice and the distribution of effort between international and national experts.

10.2 The evaluation team must have a broad range of technical subject matter expertise (including experts in organisational change) and mixed methods evaluation methodology expertise. The evaluation will require strong team leadership with excellent technical capabilities and client relationship management skills; and a tightly coordinated approach to programme and data management.

10.3 The team must comprise a wide range of technical skills and expertise across multiple areas including.

a. Qualitative and quantitative evaluations.
b. Competency and expertise in value for money approaches and methodologies for evaluating development programmes.
c. Expertise in organisational change
d. Strong analytical skills and the ability to think strategically and concisely analyse and integrate information from a diverse range of sources into practical and realistic
recommendations.
e. Effective communications skills, written and spoken English.

10.4 The Supplier should also think about how to bring in inclusion and gender-awareness into the evaluation team. This is an important cross-cutting them to have awareness of.

11. Payment Mechanism

11. 1. The maximum budget for this Contract will be up to £300,000 (inclusive of all government taxes). The Supplier will be required to commence services under this Contract within 2 weeks from the Contract award date.

11.2 A payment by results approach will be used to enable effective delivery of the Evaluation Contract.

11.3 The inception phase payments will be output-based and linked to the successful delivery and acceptance of the inception phase deliverables as per Commercial ProFormas Tab 4.0-Payment. The expenses shall be reimbursed on a monthly basis and shall be based on actuals. The value of payment for each deliverable should be based on the realistic requirement of staff input and associated expenses

in line with the payment Tab 4. of cost ProFormas. The deliverables will become eligible for inclusion in invoice upon FCDO’s acceptance and approval.

11.4 The inception phase deliverables are the deliverables to be completed by the end of the inception phase (see Inception Phase Deliverable Table). Note, the deliverables listed within the Inception Phase Deliverable Table do not cover all the requirements of the Inception Phase but are the expected payment KPIs for the Inception Phase.

11.5 The implementation phase payments will be output based and linked to the successful delivery and acceptance of the implementation phase deliverables as per Commercial ProFormas Tab 4.0- Payment. The expenses shall be reimbursed on a monthly basis and shall be based on actuals. The value of payment for each deliverable should be based on the realistic requirement of staff input and associated expenses in line with the payment Tab 4. of cost ProFormas. The deliverables will become eligible for inclusion in invoice upon FCDO’s acceptance and approval.

12. Reporting Requirements

12.1 The Supplier will report to the FCDO Senior Responsible Officer and Programme Manager of the
FCDO WHO CVC programme.

12.2 The Supplier will be required to provide the following regular updates to the FCDO Programme
Manager (in addition to the key deliverables/outputs described earlier):

a) Monthly update email providing an overview of key activities, any initial evaluation reflections and findings, any early recommendations to feed into the WHO CVC annual review/ project completion review process in 2024 and the development of a successor WHO CVC programme which will commence in January 2024, and risks and issues. The first of these updates shall be provided in December 2023.

12.3 the Supplier shall submit the following under the following deliverables:

a. Final summative evaluation report should be no more than 50 pages
b. Final evaluation summary (‘evaluation digest’) with key findings and recommendations of the finalised evaluation report should be 2 pages using the FCDO’s template for publication available on FCDO’s website.
c. Slide pack/presentation summarising the evaluation findings should be no more than 10 slides covering key takeaways and areas for the UK to strengthen engagement.

13. Risk management requirements

13.1 During the inception phase the Supplier will develop and keep up to date throughout the Contract a Risk Register that shall outline any perceived / actual risks, risk probability, impact and mitigation actions,

13.2 Key risks and/or constraints that the Supplier should be aware of:

a. Building an understanding and approach for a complex organisation and programme,
b. Ensuring robust data collection, knowledge management, and approach to analysis the evaluation is likely to draw on programme documentation and monitoring
information.
c. Lack of financial transparency of CVC funds specifically how budget decisions are made and why, and how CVC funds are prioritised for activities.
d. Consider risks around safeguarding and any ethically considerations around issues such as confidential data collection, safe storage of data, informed consent of key
informants etc.

16. General Data Protection Regulations (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Appendix 1 Schedule of Processing, Personal Data and Data Subjects.

17. List of Annexes

Annex A: Programme documents

1. 2021 Annual Review, Core Voluntary Contribution (CVC) funding to the World Health
Organization (WHO), 20/21 to 23/24
2. 2022 Annual Review, Core Voluntary Contribution (CVC) funding to the World Health
Organization (WHO), 20/21 to 23/24Memorandum of Understanding with WHO, Core voluntary contribution (CVC) funding to the World Health Organization (WHO) 2020/21 to
2023/24
3. WHO CVC 2020-24 Business Case (including Theory of Change)
4. WHO CVC 2016-20 Project Completion Report:
5. The UK’s High-Level Performance Framework for the World Health Organisation Core
Voluntary Contribution 2020/21 to 2023/24
6. Evaluability Assessment
7. Evaluability assessment document review.

Annex B: Other supporting documents
1. WHO MOPAN Assessment 2017- 2018, 2019

2. WHO, Thirteenth General Programme of Work. 2019 – 2023

Annex C: FCDO policy and guidance
1. Integrated Review of Security, Defence, Development and Foreign Policy
2. Integrated Review refresh
3. Global Health Strategy
4. UK International Development Evaluation Policy (May 2013)
5. FCDO Ethical Guidance for Research, Evaluation and Monitoring Activities (2020)
Appendix 1 of Call-down Contract
Schedule of Processing, Personal Data and Data Subjects

This schedule must be completed by the Parties in collaboration with each-other before the processing of Personal Data under the Contract.

The completed schedule must be agreed formally as part of the Contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.

Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this Call- down Contract. / 1) The Parties acknowledge that Clause 33.2 and 33.4 (Section 2 of the Contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 33.3 in respect of the following Personal Data: / - For the avoidance of doubt the supplier shall provide anonymised data sets for the purposes of reporting on this project and so FCDO shall not be a Processor in respect of Personal Data necessary for the administration and / or fulfilment of this Contract.