## What Works Hub for Global Education Annual Review 2024/25

Programme Title: What Works Hub for Global Education (WWHGE)
Programme Value £ (full life): £55M		Review date: Sept 2025
Programme Code: AMPID 300936	AMP start date: 14.06.2021	AMP end date: 31.03.2029

Summary of Programme Performance

Year	2022	2023	2024	2025	2026	2027	2028	2029
Overall Output Score	A	A	A	A+
Risk Rating

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90001008.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The What Works Hub for Global Education (WWHGE, 2021-2029) is an international research and policy programme and partnership on how to implement education reforms at scale. Its aim is twofold: to develop a rigorous new field of implementation science in education - exploring how governments can successfully roll out effective reforms at scale - and to help governments and international partners coordinate around, access and use evidence-based approaches to improve foundational learning outcomes for children. By generating essential new evidence, and equipping governments and partners with effective approaches, WWHGE will contribute to addressing the global learning crisis, where many children attend school without achieving basic literacy and numeracy due in part to insufficient evidence on what works, or use of proven methods.

The WWHGE is jointly funded by FCDO’s Research and Technology Department (£39m CDEL) and the Girls’ Education Department (£16m RDEL). It works with a range of funded and unfunded partners, leveraging their networks and expertise to strengthen evidence generation and use and maximise impact.

The WWHGE is delivered through three pillars:
Pillar 1 – Synthesis and evidence translation: Synthesise, translate and curate evidence on how to implement foundational learning at scale for policymakers and implementers. This pillar includes support to the Building Evidence in Education (BE2) donor coordination group on research, and secretariat support to the Global Education Evidence Advisory Panel (GEEAP). Pillar 1 operates globally with options for country-specific insights.
Pillar 2 - Institutionalise the use of evidence: Strengthen capability of government and local stakeholders to use data and evidence to implement foundational learning reforms effectively. Over this reporting period, P2 work includes:
- Evidence Labs (EdLabs): Government-embedded units that facilitate evidence use to help test and scale interventions and support education system strengthening. The Hub supports EdLabs in Ghana, Rwanda, Tanzania, South Africa, Pakistan, and India.
- Community of Practice: The WWHGE Community of Practice (CoP), brings together more than 100 organisations spanning 30 countries and six continents. The CoP will serve as a robust platform for technical dialogue to support uptake and use of implementation evidence in foundational learning programmes and to influence governments to use evidence.
- WWHGE Policy Fellows, managed by the Blavatnik School of Government, engages mid-level government officials from various institutions (including some Ed Labs) to enhance skills and assist with analysis, reflection, evidence generation, and application for implementing government education interventions. The programme also facilitates a network among Fellows for lesson learning.
Pillar 3 - Implementation science: Build a new field of implementation science research in education, building on ‘what works’, to understand how approaches should be implemented in practice, and at a scale necessary for transformative and cost-effective outcomes. The four focus countries are: India, Pakistan, Rwanda, and Tanzania with smaller studies in Botswana, Bangladesh, Ghana, Kenya and Sierra Leone.
The WWHGE has three main delivery channels: 1) £30m main contract with the Blavatnik School of Government at the University of Oxford (BSG), their 40 consortium partners in focal countries from across academia, civil society and government to deliver the new field of implementation evidence and support institutionalisation of evidence use; 2) £12.5m for six funded Strategic Partners (SPs) – detailed below;
3) Three FCDO staff Implementation Roles (IRs), responsible for leading: i) coordination of Strategic Partners globally and nationally; ii) country uptake of evidence with partners; and iii) buy in and collaboration from country offices and centrally managed multi-lateral and bilateral education programmes.

Funded Strategic Partner agreements: Strategic Partners are key education sector stakeholders chosen for their strengths in delivering large-scale impact, based on independent analysis. They support all pillars:

Table 1: Strategic Partner delivery agreements
	Strat. partner	Dates, budget		What they will deliver
World Bank (WB) Pillar 1, 2, 3		2021–2027, £4.2m (Signed 2021)		Build government capacity via Education Policy Academies. / Strengthen foundational learning through investment cases and dashboards. / Fund implementation research for WB teams.
Learning Generation Initiative (LGI) / Pillar 1, 2		2023 -2029. £2,541,111 (Signed November 18th 2024)		Provide Global South Learning Champions for advocacy. / Translate research into country education plans, focusing on workforce and delivery.
British Council Pillar 2		2024–2028, up to £1.6m (MoU, Signed May 2024)		Support evidence use and leadership in India, Pakistan, Tanzania, Rwanda, South Africa, Ghana, regional support in Kenya. / Coordinate technical evidence exchanges and stakeholder alignment.
UNICEF Innocenti / Pillar 1, 2, 3		2024–2026, up to £1.5m (Signed May 2024)		Conduct implementation research in focus countries. / Strengthen evidence use in UNICEF education programmes (West, East & Southern Africa, South Asia) / Synthesise and share research via the FLN (foundational literacy and numeracy) hub.
UNESCO IIEP Pillar 1, 2		2024–2028, £900k (Signed July 2024)		Develop sector simulation tools for government spending prioritisation. / Provide evidence on government middle-tier’s impact / Support use of data to improve learning.
	Global Education Evidence Advisory Panel (GEEAP) and BE2 donor group Pillar 1, 2		2024-2028, £1,810,389 / (Signed 23 Jan 2025)		GEEAP: Produce cost-effectiveness and thematic reports, country syntheses. / BE2: Coordinate education research, develop research standards and tools.

WWHGE aims to achieve large-scale change by collaborating with strategic partners who share common goals, focusing on coordination and complementarity to avoid mandate overlaps and inefficient use of resources. There are three types of partners:
- FCDO-funded WWHGE delivery partners: BSG, World Bank, Learning Generation Initiative (LGI), British Council, UNICEF Innocenti and UNESCO International Institute for Educational Planning (IIEP).
- WWHGE Funders: FCDO, Gates Foundation, British Council, Marshall Foundation are providing funding for the WWHGE.
- Aligned funding partners: GPE KIX, Gates Foundation, and Jacobs Foundation are WWHGE Strategic Partner Board members and coordinate their programmes with WWHGE but do not fund the programme directly (or receive funding).

Summary supporting narrative for the overall score in this review

This review covers the period 1 May 2024 to 31 March 2025. The programme scored an A+ as it met or exceeded all outputs, laying a strong foundation for future delivery. Early delivery has demonstrated the Hub’s potential to shift how evidence is used to inform education reform at scale. Through increasingly coordinated efforts across BSG and Strategic Partners, WWHGE is showing early signs of supporting evidence use in government systems, catalysing policy uptake, and building a coherent narrative around implementation science. Highlights include:
Strengthening Capacity, supporting systemic Change: The establishment of EdLabs in Rwanda, Tanzania, and South Africa is starting to effectively integrate evidence generation into government systems, directly informing strategic plans and curriculum reforms, for example the EdLab in Rwanda contributed to the Ministry of Education’s strategic plan, with its outputs shaping national curriculum and teacher policy reforms. The launch of BSG’s Policy Fellows Programme for mid-level Government officials; multiple influencing meetings with government officials, and better coordination between stakeholders in country have begun to institutionalise evidence use and support policy uptake in focus countries. There are initial signs of systemic change in countries including Rwanda, India, and South Africa, including the formation of formal research collaboration groups and increased visibility of implementation science.

Policy Influence: WWHGE's evidence products and technical assistance are starting to influence national education reforms, example, in Kenya, early communication of the Global Education Evidence Advisory Panel (GEEAP) smart buys led to a joint engagement with the President’s adviser, resulting in a technical assistance request and ongoing collaboration with the new Presidents delivery unit. In Pakistan, WWHGE-supported outputs have informed national planning, budgeting, and reform. For example, technical dialogues and evidence sharing contributed to the refinement of Punjab’s learning assessment framework and supported the scale-up of Teaching at the Right Level (TaRL) approaches in provincial education systems.

- Research and dissemination: Early WWHGE research products surpassed the milestone, advancing the field of implementation science in education. These included working papers, insight notes, and a peer-reviewed article, covering diverse geographies and methodologies. In Year 1, 65.9% of outputs were authored by women, and 77.3% included Global South authors.
- Collective country-level theories of change were developed for India, Kenya, Pakistan, and Tanzania, each incorporating three to four national reform pathways. These were drafted through 2-day workshops in each country, convened jointly by the IRs, FCDO country advisers, BSG and British Council, with strategic partners, academics and government policy makers. These events were to strengthen in-country coordination and collaboration, minimise duplication, and align collective efforts with government-led foundational learning initiatives.

While the programme has built a strong platform for delivery, further work is needed to sharpen its strategic focus and accelerate outcome-level change around target reform pathways: Pillar 1 must become more agile and responsive to policy demand, with clearer mechanisms for rapid synthesis and uptake. Pillar 2 requires a more ambitious and coherent strategy, with defined objectives, outcomes, and alignment to national reform pathways.

Please note that momentum has been built by the recruitment of the new Policy and Partnerships Director in BSG (which had been vacant) in May 2025 - after the AR review period, who is leading the development of a new pillar 2 strategy and strengthening collaboration between BSG and the Strategic Partners. Going forward, technical dialogues and insight products need to be more clearly linked to policy influence, and there needs to be a more systematic approach to policy influence. Internally, FCDO must strengthen its own uptake of WWHGE tools and evidence across existing centrally managed education research programmes and improve coordination to prioritise delivery mechanisms with the greatest potential for impact, behind the new Centre of Expertise.

Major lessons and recommendations for the year ahead [1/2 page]

No:	Lesson	Recommendations	Owner date
1	Strengthen the ambition and outcome-focus of programme indicators and Theory of Change: Current output targets are largely met or exceeded, but the link between outputs and meaningful, sustained impact is inconsistent. The Theory of Change and logframe should be revised to ensure outputs are not only ambitious but also demonstrably lead to policy uptake, institutionalisation, and system-level reform.	Revise log frame. Revise the logframe and Theory of Change to set more stretching, outcome-focused targets that also explicitly track the quality, relevance, and influence of outputs. Ensure indicators capture how synthesis products, technical dialogues, and EdLab engagements contribute to policy uptake, institutionalisation and system-level impact, with clearer assumptions and pathways for influence including the role of Strategic Partners, IRs, LMIC leadership in shaping reform outcomes. / The Independent MEL team should progress a programme learning agenda to surface what’s working, for whom, and under what conditions.	Simon Blower with BSG MEL team and the Strategic Partners contributing to outputs 1.1 and 1.3 – by Dec 26 / BSG Noam Angrist, Becky Hatch and IRs to review assumptions and mitigations for TOC.
2	Strengthen the connection between outputs and outcomes. There is a disconnect between programme outputs and intended outcomes. While some separation is expected at this stage of the programme, there is concern that this may reflect a broader, systemic implementation issue. Strengthening the link between outputs and outcomes is essential to ensure that synthesis, networks, and implementation science deliver tangible improvements to national and sub-national education systems.	Conduct a strategic review in the next quarter to assess and strengthen the connection between outputs and outcomes. / The Theory of Change (TOC) should be revised to unpack risks associated with translating outputs into outcomes, and a risk mitigation strategy should be developed, including the identification of champions and spoilers for achieving desired outcomes. / Continue developing the pathways to impact protocol, with input from the MEL team, to examine 3–4 reform pathways for each core country and clarify how outputs will lead to outcomes.	Rachel overall lead on the review of outputs to outcomes. By March 2026 / Simon lead on the TOC risks and mitigation strategy with the focus on the outputs to outcomes. By March 2026 / Rachel and Simon will lead the pathways to impact work. Rachel: India and Kenya, Ghana. Simon: Pakistan and Tanzania.
3	Enhancing Programme Responsiveness: Responsive support has provided by the Hub has been valued and strategically impactful. However, instances have relied on available capacity rather than a formalised rapid response mechanism and process, limiting the programme’s ability to respond consistently and at pace to emerging policy needs.	Development of responsive Technical Assistance. FCDO and BSG should jointly design and operationalise a formal Technical Assistance (TA) mechanism that forms part of the FCDO Centre of Expertise for Education (CoE) to ensure alignment with broader technical support offers – note this must be aligned/framed with the wider FCDO Education research offer and inputs to the CoE. It should: / Span all pillars. / Include a focus on pillar 1 (quick responsive evidence synthesis and evidence translation, tailored to the individual needs of countries as demanded via advisers and strategic partner in-country leads). / Includes strategic partner contributions. / Be accessible: with clear entry points for FCDO and government stakeholders. / Be responsive: able to deliver timely, policy-relevant support where feasible. / Include a tracking system of all requests both internal and external with usage tracked and evaluated for strategic value with GEDSI lens. / Establish pillar 2 TA triage board. / Establish criteria for prioritising requests given limited funds.	Michelle Kaffenberger, Rachel Hinton, Sabina Morley. / Oct 2025
4	Reform pathways: More is needed working with the Global Coalition for Foundational Learning (GCFL), to improve coherence strategic partners at the country level. While individually delivering strong technical outputs, greater coherence around key reform opportunities is required.	FCDO (GED and RED) should create a WWHGE policy engagement framework to coordinate Strategic Partners’ influence at country level, including the wider education research portfolio. This could involve an MOU for systematic links with GPE and clarify GCFL Principals’ support via country visits and Secretariat capacity.	Rachel Hinton and Janice Dolan and Sabina Morley by November 2025 / Simon Blower as policy IR on the links with GPE September 2025
5	A more systematic approach is required to strengthen internal dissemination and assess strategic uptake within FCDO. The WWHGE programme is developing evidence products, briefs, and tools for both Hub countries and FCDO's broader education portfolio. Coordination is evident through regular interaction with the SCALE team and the use of WWHGE’s framework in pilot evaluations. (IRs) have shared findings via FCDO events, CPD training, seminars, and newsletters. However, there are gaps and more could be done.	FCDO uptake and dissemination. As part of WWHGE’s contribution to the Centre of Expertise on Education, FCDO should strengthen internal uptake of WWHGE outputs by developing a dissemination and uptake strategy, taking learning from the Girls Education Challenge Uptake strategy linked to the broader education policy and research portfolio and offer. We should coordinate across RED and GED, and through the CoE, ensuring WWHGE products are accessible, and providing learning sessions for relevant staff. For key countries, tailored communication plans aligned with government priorities should be developed, and the MEL team should monitor the impact and usage of WWHGE evidence and tools.	Simon Blower and Becky Hatch October 2025 / BSG communications team (Simon working with Janice Dolan) / Pillar 1 and 2 / MEL team and Simon Blower, September 2025
6	Policy influence and uptake: / WWHGE has generated high-quality, policy-relevant research—especially in Pillar 3—but translating this into system-level reform has been inconsistent. Outputs often stay within academic or donor circles, with minimal involvement from senior decision-makers, reflecting a structural challenge. Although WWHGE is designed to link knowledge to implementation, its delivery model still leans heavily toward knowledge generation. Greater investment is needed in the relationships, coordination mechanisms, and incentives to drive sustained policy uptake.	Update Output 2 to focus more on co-production and policy engagement, ensuring research is embedded in national reforms and aligned with policy opportunities. This includes clearer use of media, annual strategy reviews, integration with the Theory of Change and MEL framework, and a system for assessing the quality and influence of technical dialogues.	BSG communications leads with Becky Hatch and Rachel Hinton and Sabina Morley October 2025 MEL – Simon Blower with MEL team and British Council country plans. November 2025
7	Gender and Equity: The WWHGE programme articulates a strong commitment to equity and inclusion, including gender. However, this commitment is not consistently operationalised across its pillars, research agenda, or measurement frameworks. Gender is referenced in vision statements and guiding principles but is insufficiently embedded in the programme’s core delivery mechanisms, particularly in the logframe indicators, research design, and capacity-building components.	Mainstream gender as a cross-cutting priority across all pillars of the WWHGE programme by embedding it into the programme’s results framework, research agenda, and capacity-building efforts by: / Requiring Pillar 3 research studies to include gender analysis and report on differential impacts. / Utilising GEDSI framework across the programme cycle. / Commissioning dedicated synthesis product on gender/equity-responsive implementation of foundational learning reforms. / Embedding gender/equity modules and participation targets (for example x% women) in Executive Education, Fellows, and Ed Lab programmes. / FCDO, BSG, all Strategic Partners British Council, GEEAP, LGI, IIEP, UNICEF and World Bank.	FCDO Rachel Hinton, BSG Becky Hatch, SP leads March 2026
8	South-South engagement and localisation: Stronger integration of southern leadership and LMIC partners in policy, governance, and research activities, ensuring their roles in decision-making, data collection, and dissemination are institutionalised and supported. In particular, to ensure the work on national coalitions is integrated into the policy strategy.	Strengthen involvement of southern leaders in policy strategy and joint publications, including through fellows and exchanges. / Integrate pillar 2 enhancement fund work with overall policy strategy and planning. / Coordinate with Gates Foundation (Lighthouse initiative) to avoid overlap in national coalitions. / BSG/ FCDO develop framework to institutionalise LMIC partner leadership in upstream governance and product scoping. / Promote localisation by involving local researchers at all stages, using culturally relevant approaches (learning from RISE Ethiopia). / Share insights through a dedicated Community of Practice and website. / Enhance the Community of Practice with peer exchanges and government feedback. / Ensure all activities captured through the MEL process.	Katie Coooper and Rebecca Trupin with Rachel Hinton and Stefan Dercon, August 2025 MEL – Simon Blower, Aug 2025
9	Enhanced strategic prioritisation: The WWHGE delivery model is ambitious and wide-ranging, involving over 40 consortium partners and multiple Strategic Partners working across different geographies and thematic areas. While this has enabled breadth and innovation, which is WWHGE’s true strength, it has also introduced a degree of complexity and coordination challenges. / In the context of constrained ODA budgets and the need for greater responsiveness and prioritisation, the programme must rapidly shift from expansion to consolidation in certain areas of delivery.	FCDO and BSG should work with the external evaluator OPM, to conduct a strategic prioritisation exercise in 2025–26. This should assess which components, countries, and delivery mechanisms are most likely to deliver outcome-level change and value for money. The exercise should include a mapping of partner activities against the ToC, identify areas of duplication, and recommend options for streamlining (FCDO, BSG, OPM). / The programme to also explore how to further utilise the role of BE2 to help reduce risk of duplication.	MEL team and BSG MEL lead ongoing and Noam Angrist, Sabina Morley Rachel Hinton. Jo Cooke February 2026

See Annex A for further emerging lessons. Summary of outstanding recommendations from previous AR – WWHGE AR recommendations.docx
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

This AR measures WWHGE’s progress in its first 10.5 months of implementation (May 2024 – March 2025). WWHGE’s Theory of Change (ToC) has been updated since the original Business Case and now focuses on three main pillars: 1) translating evidence, 2) building government capacity to use evidence, 3) and generating new evidence on implementation and scaling. This flexible, actor-driven approach is designed to work across different countries and partners, including governments, global organisations, and researchers.

The latest ToC was refined through workshops and consultations, and approved by the Strategic Partnership Board in May 2024, with further validation in May 2025. Nested ToCs were also developed for each pillar to strengthen the MEL alignment and adaptive programming components of the programme.
The log frame was revised during the reporting period to strengthen indicator definitions and disaggregation, and while nearly all output targets were met or exceeded, the link between output delivery and outcome-level change remains uneven. This suggests that the current ToC may overemphasise volume and delivery, without sufficiently capturing the quality, strategic relevance, or influence of outputs (i.e. on ecosystems/networks, conceptual shifts, policy changes or implementation changes). To address this, a recalibration of the ToC is recommended to better reflect the mechanisms through which outputs such as synthesis products, technical dialogues, and EdLab engagements translate into policy uptake, institutionalisation, and system-level reform. The revised ToC should incorporate clearer assumptions and pathways for influence, including the role of Strategic Partners, Implementation Roles, and LMIC leadership in shaping reform outcomes. Gender and equity (which includes children with disabilities) should be reflected at the output and outcome level as well as the outcome level.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains broadly on track to contribute to its intended outcomes and impact. Early signs of outcome-level change are emerging, particularly in Pakistan and Rwanda, where WWHGE-supported outputs have informed national planning, budgeting, and reform coordination. Global engagement is also increasing, with WWHGE evidence cited in major reports and used by actors such as UNICEF Innocenti and the World Bank. See for example VoxDev’s overview on the policy-practice gap and Brookings Foresight Africa 2025-30, articles in the Journal of Development Economics (2025), UNICEF and GPE programme documents (eg Transformation Grants), Smart Futures (EAP) From learning recovery to education, UNICEF’s ESA’s structured pedagogy framework. ICAI report, Kenya Presidential Working Party report, CGD and R4D.

However, delivery has revealed a gap between output volume and systemic influence. While the programme exceeded most output targets, the extent to which these outputs have catalysed policy shifts, funding reallocations, or institutional uptake remains uneven. This reflects a broader challenge: the programme’s delivery model has prioritised breadth and momentum but now requires a sharper focus on strategic alignment. Platforms such as the WWHGE Community of Practice (CoP) and technical dialogues have generated strong participation, but their contribution to reform pathways is not yet visible or articulated.

In Year 2, the programme must strengthen delivery while also increasingly focussing on strategic influence. This will include embedding outputs within national reform cycles, strengthening the policy relevance of convenings, and ensuring that learning platforms and technical assistance are directly linked to decision-making. FCDO contracted the independent MEL partner, Oxford Policy Management (OPM), in January 2025 which will be critical in assessing the quality and contribution of outputs to outcome-level change and should inform a mid-course revision of the programme’s strategic logic. The formative baseline evaluation is due in late 2025.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme has demonstrated strong progress, successfully meeting complex milestones, delivering good value for money, and increasing its influence on the use of evidence in education reform. The programme is well aligned with FCDO’s strategic priorities, including foundational learning, strengthening education systems, and promoting evidence-based policymaking. It also complements other centrally managed investments in education research and technical assistance.

To maximise impact in its second year, WWHGE should actively strengthen collaboration with other centrally managed programmes. Specifically, promotion of the adoption of its tools—such as the Delivery Toolkit, which translates DeliverEd research into practical guidelines and checklists—within initiatives like SCALE. This will help ensure that evidence-based approaches are embedded across FCDO-supported education programmes, enhancing coherence and effectiveness in education reform efforts.

C. DETAILED OUTPUT SCORING
Output Title: Research synthesis and evidence translation outputs generated and disseminated globally and in project countries
Output number:	1	Output score: A+
Impact weighting (%):	20%	Weighting revised since last AR? No
Indicator(s)	Milestone(s) for this review	Progress - Exceeded
1.1: # of evidence synthesis products produced by WWHGE / Disaggregated by type, e.g.: research vs policy oriented, insight notes, academic synthesis papers, case studies	BSG: 1 / LGI: 3 / Innocenti: 4 / IIEP: 1	Target = 9 / Achieved = 19 / BSG (4): Exceeded: incl. a conceptual framework paper, a synthesis brief on structured pedagogy, an insight note on scaling structured pedagogy programmes, and a synthesis report on 10 years of Early Grade Reading Studies in South Africa. / LGI (1) I: Met: three evidence synthesis products: 1) foundational learning team; 2) problem-solving in education reform 3) equity and inclusion in Smart Buys studies. / Innocenti (8): Exceeded. Incl. regional and country-level syntheses, technical papers, complemented with multimedia outputs to enhance accessibility and engagement. / IIEP (4): Exceeded. Incl. a jointly published position paper with LGI, a conceptual framework and tools for middle-tier capacity assessment, and a Pakistan case study based on field research.
1.2: # of tools produced as global public goods / (Incl. system diagnostics tools, middle tier assessment tools, etc. Does not include synthesis products)	LGI:1	Target = 1 / Achieved = 1 / LGI: Met = 1. LGI successfully produced one tool as a global public good: the Delivery Approach Toolkit synthesis evidence on delivery approaches into practical guidelines and a checklist for governments to use – there is interest from 5 countries in piloting the approach (in Sindh (Pakistan), Nigeria, and Sierra Leone to pilot this toolkit) which LGI are supporting.
1.3: # of events to disseminate global goods / (Including dissemination events for P1 products. Can include global events, regional events, national, SP institutional events)	BSG: 2 / BC: 3 / LGI: 13 / Innocenti: 15 / Total: 33	Target = 33 / Achieved = 37 / BSG: Met (2). 1) the WWHGE Annual Conference 2024, a two-day event that engaged 222 stakeholders; 2) and a panel session at Comparative and International Education Society (CIES) 2025 where they presented synthesis on TaRL and structured pedagogy. The Annual Conference also included a half-day Community of Practice (CoP) workshop 121 participants. / British Council: Met (3):1) hosted a technical discussion with key education leaders in India Nov 2024 to discuss disseminating global goods, including a potential Community of Practice. 2) In Dec, hosted a national conference with 150 participants in India, incl. representatives from UNICEF, UNESCO, and National Council of Educational Research and Training (NCERT). 3) In Feb, co-organised a Government Dinner in Tanzania with WWHGE partners during the Utafiti Elimu conference. / LGI: Met (13). Delivered 13 dissemination events incl. a policymaker forum in Ghana, sessions at the EAC Regional Education Conference in Tanzania, event at the WWHGE Conference in Oxford. They also presented at British Council and CIES events and convened a Development Partner Roundtable in Tanzania. / Innocenti: Exceeded (19). Delivered 19 dissemination events including regional education meetings, major global convenings like CIES and WWHGE, and national events such as Ghana National Education Week. They also contributed to global networks like GEEAP and BE2 and hosted a high-level event (33 Ministers of Education, 5 Heads of State).

Briefly describe the output’s activities and provide supporting narrative for the score. This Output is scored A+ as a total of nineteen evidence synthesis products were produced across four strategic partners - BSG, LGI, Innocenti and IIEP, against a combined milestone of nine for this reporting period. These included conceptual frameworks, policy briefs, technical papers, and country case studies, with several products already informing policy dialogue and programme design. Innocenti and BSG exceeded two of their targets, while LGI and IIEP met theirs, with additional outputs in the pipeline. Dissemination was strong, with 33 events (virtual and in-person) held globally, regionally and nationally, including the WWHGE Annual Conference, CIES, and participation at the Education World Forum.
However, evidence on the strategic value of these events is mixed. Some events, such as the Annual WWHGE Conference and regional policy dialogues, successfully engaged key stakeholders and contributed to conceptual change. For example, dialogues in Bangladesh, Oxford, and Kenya generated demand for the Smart Buys reports. In Kenya, the President’s Adviser specifically requested technical support from WWHGE to help implement the new foundational learning policy.
In contrast, for other events, there is no evidence showing how they influenced reform decisions or contributed to systematic learning. Additionally, the current log frame does not effectively measure the quality of outputs or the impact of activities at the outcome level, which could lead to an overstatement of progress. This will be addressed during the next year.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No formal changes were made to Output 1 indicators during this reporting period; however, the scope of delivery has expanded in the last year with greater emphasis placed on considering the reform pathways to change. The synthesis workstream has evolved beyond traditional research outputs to include multimedia formats like co-created videos, rapid response briefs, and country-level implementation insights. This has reflected a shift from a narrower focus and demand on academic evidence synthesis to a broader and more policy-responsive model of evidence translation, as envisioned in the updated (2024) Strategic Plan.

Dissemination milestones under Output 1 have expanded to more extensive dissemination across global, regional, and national platforms (e.g. WWHGE Conference, CIES, Education World Forum). The introduction of new synthesis types such as evidence application guides and implementation insight notes have also diversified the product mix. As such, the current indicator definitions and milestone targets may no longer be fully stretching and capture the breadth of activity under Output 1.

Recommendation 1: This review recommends that the log frame be revised and updated by October 2026 and set more ambitious and stretching targets that go beyond number of events to also track quality and outcome level contribution for the Output, particularly for 1.1 and 1.3. Led by FCDO and BSG MEL team and the Strategic Partners contributing to outputs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last year’s Annual Review for Output 1 recommended six key actions: (1) catalyse collaboration on harmonised evidence repositories and coding frameworks with partners like 3iE, EEF, and the World Bank; (2) ensure synthesis work systematically informs FCDO’s central investments and policy priorities; (3) conduct a synthesis survey to guide a product pipeline; (4) support World Bank dashboard work in ways that build sustainable government capacity; (5) promote wider adoption of the synthesis conceptual framework; and (6) tailor synthesis formats to specific user needs.

Notable progress has been made on 3 of last year’s AR recommendations: the synthesis survey was completed and directly informed a more structured and demand-driven product pipeline for BSG; new synthesis formats such as insight notes and evidence application guides were introduced and tailored to user needs; and early coordination on evidence repositories began among BSG, LGI, Innocenti, GEEAP, and BE2.
Recommendation 1) - collaboration with 3iE and Education Endowment Foundation (EEF) on harmonised frameworks are still at a nascent stage, integration of World Bank dashboards with national systems is uneven, and broader uptake of the synthesis framework is still emerging. Systematic integration of products, tool kits and learnings across central and bilateral FCDO investments in education has made good progress but will require a stronger internal dissemination strategy to be fully realised.

Key Lessons learned this year:
1. There is growing demand from partners and governments for rapid, policy-responsive synthesis products that can inform real-time decision-making. For example, BSG delivered a synthesis brief on foundational learning and later life outcomes in response to a direct request from FCDO and provided timely technical assistance to the World Bank (e.g. for Ghana Education Outcomes Project (GEOP)) and to implementers in India and Pakistan. However, current systems lack the resource and agility to meet demand. Given the growing demand and focus on Centres of Expertise within the FCDO, a more efficient delivery mechanism for quick evidence synthesis and translation is required and a clear process for prioritising requests.
2. The diversity of synthesis types being produced requires clearer guidance on quality assurance and intended use. Moreover, with a high volume of outputs and events delivered in Year 1, there is limited visibility on how these have translated into outcome-level change or influenced decision-making.
3. Dissemination is strongest when it is embedded in existing policy processes or convenings, rather than standalone events. For example, the uptake of the Supporting Teacher Achievement in Rwandan Schools (STARS) research in Rwanda was strengthened by aligning dissemination with the Ministry of Education’s strategic planning process and through direct engagement with senior officials. In contrast, while the Annual Conference and other events generated strong interest, there is limited evidence on how these engagements have translated into outcome-level change. To maximize influence, a strong internal dissemination strategy is needed to ensure that the synthesis products and tools are used across FCDO programmes central and bilateral.

Recommendations for the year ahead (aligned with overarching programme recommendations):
1. Recommendation 3 (Pillar 1 responsive synthesis and translation): The rapid response helpdesk function should be formalised as a distinct sub-output in the log-frame and resourced to be more agile and meet a few targeted and urgent policy needs. This would enhance the Hub’s responsiveness, increase policy influence, and better align evidence delivery with real-time decision-making windows
2. Recommendation 6 (External Policy uptake): BSG and FCDO should jointly review the synthesis typology and develop clearer guidance on product quality and standards, clarify intended audiences, and establish use cases for each product type. This would support more targeted dissemination and improve the likelihood of uptake by policymakers and implementers. It would also help FCDO and Strategic Partners to better align synthesis products with policy windows and programming needs.
3. Recommendation 6 (External Policy uptake): The Hub has delivered a high volume of events and dissemination workshops but there is limited evidence on how these engagements have translated into policy uptake or outcome-level change. To maximise influence, the programme should prioritise embedding dissemination within government and multilateral processes and strengthen internal dissemination within FCDO (as part of the wider education research portfolio) to ensure evidence informs broader UK education policy and programming.
4. Recommendation 10 (Enhanced strategic prioritisation): Strategic Partners should continue to refine ways of working to coordinate on overall data and repository alignment, to reduce duplication, improve discoverability of evidence, and lay the groundwork for a more integrated global evidence infrastructure. This would also support cross-partner synthesis and facilitate more efficient evidence translation for governments and donors.
Output Title	Governments and implementers better able to access & use evidence
Output number:		2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1: # of examples of WWHGE EdLabs that have synthesised or shared evidence and/or data	BSG: 2	Target = 2 / Achieved = 2 / BSG: Exceeded (6). BSG reported 6 examples including synthesis and sharing activities from Tanzania Institute of Education (TIE), IPA Rwanda, and South Africa Department of Basic Education DBE EdLabs.
2.2: # of EdLabs established and functioning with support from WWHGE	BSG: 3	Target = 3 / Achieved = 3 / BSG: Met (3) BSG established and supported three EdLabs during the review period, including the IPA Rwanda Embedded Lab (with staff embedded in Ministry of Education MINEDUC and NESA), the Tanzania Institute of Education Lab, and the South Africa Department of Basic Education Lab. Each lab is reported to be operational and contributing to evidence generation and use within government systems.
2.3: # of influencing meetings with senior government decision makers / Definition: Includes meetings with evidence champions. Meetings primarily target country government representatives though may include some other key stakeholders. Examples include: EWF side meetings, LGI champion discussions with MoFinance.	BC: 6 / LGI: 3	Target = 9 / Achieved = 23 / BC: Exceeded (10). Ten engagements with senior government decision makers across seven countries. These included a ministerial briefing in Tanzania, strategic consultations with NCERT and Karnataka officials in India, and policy workshops in Kenya and Pakistan. However, the nature of these engagements varied from one-on-one briefings to large multi-stakeholder convenings - making it difficult to assess their relative depth, influence, or contribution to outcome-level change. / LGI: Exceeded (13): Engagements with senior government decision makers across multiple countries. These included bilateral meetings at the Education World Forum, strategic dialogues with ministries in Ghana, Kenya, Pakistan, and Nigeria, and targeted engagements to support reform planning and delivery toolkit uptake.
2.4: # of technical dialogues that support country government representatives, implementers and other stakeholders to access, understand and apply/use evidence	BSG: 3 / BC: 1 / IIEP: 1 / LGI: 3 / UNICEF Innocenti: 20	Target = 28 / Achieved = 41 / BSG: Exceeded (6) including strategic workshops in Rwanda and Pakistan, a multi-country series on A/B testing, and advisory board-led dissemination in Tanzania. . / BC: Exceeded (2): In India, a multi-stakeholder convening mapped the national evidence ecosystem and identified pathways for improved evidence use. In Pakistan, a national conference on Teaching at the Right Level (TaRL) facilitated South-South learning and catalysed dialogue on embedding evidence into provincial education systems. / IIEP: Met (1). technical dialogue in Pakistan engaging over 65 stakeholders to validate findings and co-develop action plans based on the middle-tier capacity assessment. / LGI: Exceeded (9). Technical dialogues across Ghana, Kenya, Nigeria, Pakistan, and Sierra Leone. These included high-level policymaker forums, evidence ecosystem convenings, and delivery toolkit consultations, all aimed at enabling government and stakeholder uptake of evidence. / UNICEF Innocenti: Exceeded (23) engagement across 23 countries including Ghana, Rwanda, Bangladesh, Ethiopia, and Madagascar.
2.5: % of executive education participants who are more confident in their ability to use evidence for programming, policy or planning. (Targets to be disaggregated)	BSG: N/A	BSG: N/A targets for 2025
2.6: # of learning sessions focussing on enhancing government capability to use and/or generate evidence	WB: 2	Target = 2 / Achieved = 4 / WB: Exceeded (4): The World Bank delivered 4 structured in-person engagements under the Education Policy Learning Exchange (EPLE) Foundational Learning stream including in El Salvador, Ghana, Colombia, and Nepal, with convenings hosting between 50 and 140 participants from Ministries of Education and other stakeholders.
2.7: # of country coalitions and evidence networks convened / Examples: research rep on LEG, national coalitions, S-S learning	UNICEF Innocenti: 2 / BC: 5	Target = 7 / Achieved = 9 / UNICEF Innocenti: Exceeded (3). Convened 3 country coalitions, including implementation research working groups on remedial education in Rwanda, structured pedagogy in Sierra Leone, and a joint research plan with the University of Rwanda. / BC: Exceeded (6). 6 country coalitions and evidence networks, incl. ToC workshops and working groups in India, Pakistan, Rwanda, and Tanzania, as well as a research advisory group meeting in Pakistan and the formal launch of an Education Evidence Working Group in India.
2.8: # of BSG fellows who are more confident in their ability to use evidence for programming, policy or planning (Targets to be disaggregated).	BSG: 0	BSG No targets set this year.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output is scored A+ as the programme met and/or exceeded all milestone targets across a broad and complex set of indicators. WWHGE operationalised EdLabs in Rwanda, Tanzania, and South Africa, which served as platforms for evidence generation and use. These labs convened advisory board meetings and technical workshops that were directly aligned with national reform priorities such as curriculum reform in Rwanda and teacher professional development in Tanzania ensuring relevance and uptake.

WWHGE convened five technical dialogues and eight influencing meetings with senior government officials across Rwanda, Pakistan, Tanzania, Karnataka, Punjab, and Malaysia. Partner reporting provided some qualitative evidence of strategic alignment to align with reform windows and policy priorities. For example, LGI reported dialogues in Punjab contributed to the refinement of the state’s learning assessment framework, while British Council reported that engagements in Malaysia supported the Ministry’s review of evidence use in policy planning. Some indicators (2.5, 2.6, 2.8) were not due for reporting this year, foundational work took place such as onboarding the Policy Fellows and developing M&E tools to track capability outcomes.

While partner reporting provides some topical examples of strategic alignment, it remains difficult to fully gauge the quality and influence of these events particularly in terms of what they led to, how they were curated, and whether they contributed to sustained policy uptake. In year 2, quality and impact of events will be monitored through the log frame review, and through our external evaluator and internal monitoring.

Case Study: Rwanda EdLab – Embedding Evidence in National Reform

EdLabs are mechanisms for embedding evidence into the heart of reform processes. Their success depends on co-location within government, alignment with national priorities, and the ability to respond rapidly to urgent policy needs. / The Rwanda EdLab, supported by BSG and IPA, exemplifies how embedded technical assistance can strengthen government capacity to use evidence in real time. Hosted within the Ministry of Education (MINEDUC) and the National Examination and School Inspection Authority (NESA), the EdLab has become a focal point for evidence generation, synthesis, and application in Rwanda. / In 2024–25, the EdLab produced three key outputs: a national strategy for the Curriculum and Assessment Management Information System (CAMIS), a Year 3 impact report from the STARS pilot on performance-based teacher incentives, and a labour force analysis of the teaching profession. These outputs were not standalone; they were directly integrated into Rwanda’s national education strategy and used to inform planning and budgeting decisions. / The CAMIS strategy, for example, achieved 89% uptake across districts, demonstrating how EdLab-generated evidence can be institutionalised within government systems. The STARS findings were presented at a high-level policy dialogue and are now informing the national scale-up of performance contracts for teachers.

Impact story – Evidence champions lead to new reforms in Ghana Dr. Sam Awuku, the LGI Country Lead in Ghana was appointed by the President to serve on the education committee. As a result of evidence he shared, reforms were included that focus on early childhood development framed around innovative pedagogies, and learning teams. Further strengthening the middle tier for accountability and quality learning outcomes featured strongly under the regulatory bodies, accountability and governance pillar. The technical inputs provided by Dr Awuku resulted in shifts in the focus and financing of the sector -particularly the commitments of the President that “we will: (1) increase allocation of resources to critical areas, including foundational learning, teachers education and capacity development, infrastructure development, and education technology; (2) deepen partnerships with parents, traditional authorities, and local communities to support every child’s journey through the practice of learning teams; (3) ensure school leaders have the autonomy to perform their duties against a national school leaders’ standards”.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During this review period, Output 2 expanded significantly in scope and delivery. Two new indicators, 2.3 (influencing meetings) and 2.8 (BSG Fellows, which are government policy makers and researchers), were added to better capture the breadth of engagement and capacity-building activities. Compared to the previous year’s inception phase, which focused on planning and typology development, this year marked a clear shift to implementation and systems strengthening and institutionalising the use of evidence. Additionally, FCDO and BSG agreed that an overarching strategy for Pillar 2, outlining objectives, intended outcomes, and alignment with in-country reform pathways needed to be developed. Which would provide further clarity about how technical dialogues and insight pieces contribute to policy impact.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2024 Annual Review highlighted several lessons: that EdLabs needed to move beyond access to institutionalisation; that technical dialogues should be better aligned with reform cycles; that the Community of Practice (CoP) risked becoming a networking platform without clearer reform linkages; and that the Policy Fellows programme and capability-building efforts needed to be tied to live reform priorities to ensure uptake. It also noted the need for a typology of technical dialogues, stronger cross-partner coordination, and better use of Implementation Roles (IRs) for strategic learning.

Decent progress has been made on most of these recommendations. BSG operationalised three EdLabs with embedded mechanisms for evidence sharing and early signs of institutional uptake, partially addressing the call to institutionalise evidence use. The Policy Fellows programme was launched with seven Fellows onboarded, and Monitoring & Evaluation tools were developed to track capability outcomes.

While a formal global working group on capability strengthening has not yet been established, cross-partner collaboration on EdLabs and technical dialogues has increased. A typology of technical dialogues has not been finalised, but a diverse set of engagements have been delivered, offering a foundation for this work. The CoP was activated through the Annual Conference and CIES, though clearer pathways to outcome-level change remain to be articulated. The World Bank delivered four Education Policy Learning Exchange (EPLE) sessions, but further integration of case methods and broader government participation is still needed. BE2 also contributed to technical dialogue through two sessions at CIES 2025, focused on evidence uptake and implementation research.

Key Lessons learned this year:

1. EdLabs are gaining traction but need clearer models for institutionalisation. While EdLabs have been successfully established in Rwanda, Tanzania, and South Africa, their long-term value depends on embedding evidence use into government systems. Rwanda’s EdLab, for example, contributed directly to the Ministry of Education’s Strategic Plan and supported data use through CAMIS, with 89% utilisation—demonstrating the importance of government ownership and integration into planning and delivery systems.
2. The volume of technical dialogues is high but vary in quality and strategic alignment. While the programme exceeded its targets for technical dialogues, the quality and policy relevance of these engagements varied. Some were clearly linked to reform processes (e.g. STARS in Rwanda, TIP in Pakistan), but others lacked evidence of follow-up or influence. There is a need for a shared typology to distinguish between awareness-raising, policy-influencing, and decision-shaping engagements, and to assess their contribution to reform outcomes.
3. Capability-building efforts are promising but uneven across partners. The Policy Fellows programme has laid the groundwork for tracking capability shifts, but other partners have yet to embed similar tools. Without consistent monitoring across partners, it remains difficult to assess whether capacity-building efforts are translating into institutional change.
4. The Community of Practice (CoP) has been reactivated but lacks strategic focus. While participation has been strong, the CoP risks becoming a networking platform unless it is more clearly linked to reform pathways and decision-making spaces.
Recommendations for the year ahead:

Recommendation 6 (External Policy uptake): Introduce a typology of technical dialogues to assess quality and influence and revise the log frame indicator to be sufficiently ambitious. BSG and FCDO should agree upon and apply a typology of technical dialogues across partners that distinguishes between awareness-raising, policy-influencing, and decision-shaping engagements. For example, Rwanda’s STARS workshop directly informed national scale-up plans (decision-shaping), while Pakistan’s TIP dialogues helped identify uptake opportunities (policy-influencing), and India’s stakeholder mapping session clarified the evidence ecosystem (awareness-raising). This typology should be used to assess the quality and strategic value of dialogues in the next Annual Review and inform milestone setting for the year ahead.

Recommendation 8 (South-South engagement and localisation): Strengthen the strategic function of the CoP. BSG should pilot a reform-linked CoP workstream in one focus country, co-designed with LMIC partners and aligned to a live reform priority. This workstream should include structured peer exchange, synthesis of local insights, and a feedback loop into government decision-making. Lessons from the pilot could inform a scalable model for CoP engagement across the programme.

Recommendation 10 (Enhanced strategic prioritisation): Harmonise capability development approaches across partners. FCDO should convene a time-bound working group with BSG, UNICEF Innocenti, British Council, and the World Bank to harmonise approaches on capability development. The group should produce a shared capability framework, map existing initiatives, and identify opportunities for joint delivery or sequencing by Q2 of 2025–2026. This is critical to reduce duplication and enhance coherence across all of Pillar 2 investments.

Output Title	Pillar 3 Output: Researchers generate robust evidence on implementation at scale (and systems)
Output number:		3	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	Yes (40% last year)

Indicator(s)	Milestone(s) for this review	Progress
3.1: #research products that focus on improving student learning	BSG: 4	BSG: Exceeded (10). BSG delivered ten outputs that directly contribute to understanding and improving student learning outcomes. These include working papers, blogs, insight notes, and a peer-reviewed journal article covering diverse geographies and methodologies.
3.2: Substantive progress towards the development of common metrics and methods from BSG consortium led projects	BSG: 1 Framework and draft tools developed	BSG: Met (1). BSG has met this milestone by submitting a slide deck on the implementation measurement framework and approach in March 2025. This framework was developed and piloted with partners including the World Bank and Pratham Education Foundation.
3.3: # of education system diagnostics completed with a primary focus on learning outcomes	WB: 1	WB: Met (1). The World Bank commenced work on the global education policy dashboards (GEPD) across all provinces in Pakistan in FY23/24, successfully completing the national system diagnostics in FY24/25.https://www.educationpolicydashboard.org/practice-indicators/pba

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output is scored A+, reflecting strong delivery on research products, implementation measurement metrics and national system diagnostics. BSG exceeded its target by delivering ten research outputs that directly contribute to understanding and improving student learning outcomes. These included three working papers, two blogs, four insight notes, and a peer-reviewed article in Nature Human Behaviour. The research covered diverse geographies and themes such as A/B testing in India, cost-effectiveness analysis in Botswana, and implementation insights from Rwanda’s STARS pilot, which informed national scale-up discussions. In Pakistan, a working paper using the LEAPS dataset explored long-term effects of school quality, while in India, a study examined WhatsApp-based preschool reforms.

BSG also met its milestone on common metrics and methods by submitting a draft implementation measurement framework, piloted with the World Bank and Pratham. This framework is expected to be refined and integrated into the Hub’s technical assistance offering in Year 2.

The World Bank met its milestone for implementation science. They have been responsive to UK requests to initiate implementation science to strengthen the impact of their investments, with data starting to inform policy adaptions in Nigeria.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, Output 3 evolved from a foundational focus on research planning to active delivery of implementation science outputs. Compared to last year, where Output 3 focussed on pipeline development and conceptual framing, this year there was a significant increase in the volume and diversity of research products, including the introduction of A/B testing studies, cost-effectiveness analyses, and a peer-reviewed framing paper on implementation science. The indicator on common metrics and methods was retained, but progress accelerated with the piloting of an implementation measurement framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The programme made strong progress on most recommendations from the previous Annual Review. BSG advanced the intellectual leadership of implementation science by publishing a peer-reviewed framing paper in Nature Human Behaviour and began engaging Strategic Partners through events and technical exchanges. While a formal co-development mechanism for the framework has not yet been established, the groundwork for broader adoption has been laid. BSG and FCDO IRs also mapped planned studies onto the intellectual framework during ToC workshops, helping to identify thematic gaps and inform the research pipeline. Financial tracking indicates that Pillar 3 investments remain broadly aligned with the 60% strategic allocation, and new studies have prioritised large-scale implementation and mixed methods, although more transparency on partner-level allocations would strengthen this further.

The log frame was revised to clarify distinctions between indicators 3.1 and 3.3. 3.1 now focuses on research products and 3.3 on diagnostics. However, the World Bank did not meet its milestone for diagnostics, and further clarification is needed on how these are defined and tracked. Engagement from the World Bank’s implementation science team has been limited, with no outputs reported under Output 3 despite ongoing work under the Implementation Science in Education (ISE) and Education Policy Learning Exchange (EPLE) programmes. Strengthening collaboration between the Bank and the WWHGE consortium should be a priority to ensure alignment and knowledge sharing in the next reporting cycle.

Key Lessons learned this year:
Research outputs are diverse but lack a shared definition and classification.
BSG exceeded its milestone by delivering ten research products, including working papers, blogs, insight notes, and a peer-reviewed article. However, partner reporting did not consistently distinguish between research, synthesis, and commentary outputs. This has led to confusion about what qualifies as a research product under Output 3.

Diagnostics delivered although a shared conceptual vision is required.
The World Bank met its milestone for diagnostics with the Pakistan dashboard. Further work is required to gain wider buy-in and a shared conceptual vision to maximise their uptake. While activities under the ISE and EPLE received strong evaluations from country participants.

While this milestone scored A+, because it overachieved against the output indicators, The WB and BSG need to engage the policy leads and IRs more closely to ensure strong demand and active engagement from government to secure uptake. While the volume of research outputs is high, further work is needed to systematically track their influence on policy and reform uptake and strengthen monitoring.
Recommendations for the year ahead:
Recommendation 6 - Clarify and standardise the definition of research products: FCDO and BSG should agree on a typology of research outputs under Output 3, distinguishing between original research, applied studies, synthesis products, and commentary. This typology should be used to guide reporting, quality assurance, and milestone setting in future review cycles.

Recommendation 3 (reform pathways): Define and operationalise diagnostics as strategic tools: FCDO and the World Bank should jointly define what constitutes a diagnostic under Output 3, including minimum standards, use cases, and integration pathways into national systems. At least two completed diagnostics should be delivered in 2025–26, linked to reform priorities such as EMIS in Kenya or middle-tier reform in Pakistan.

Recommendation 1: revise log frame to set more ambitious and stretching targets that also track quality and outcome level contribution for the Outputs.
Output Title	Cross cutting: learning, engagement and LMIC leadership
Output number:		4	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	Yes (40% last year)

Indicator(s)	Milestone(s) for this review	Progress
4.1: # of CoP members who have opportunities to access new evidence, share expertise and/or learn from each other to improve practice Disaggregate by: LMIC, organisation type	BSG: 50	Target = 50 / Achieved = 121 / BSG: Exceeded (121). 121 members of CoP to have participated in structured learning and exchange opportunities. Two key events supported this progress: a half-day CoP workshop during the WWHGE Annual Conference in September 2024, and a networking session at the CIES Conference in March 2025. BSG’s reporting did not disaggregate participation by LMIC status and organisation type to strengthen monitoring of equity and inclusion for this indicator.
4.2: # of research and learning products and/or events/sessions that are led, co-authored or co-hosted with LMIC partners / Disaggregation: gender, location and type of product/event	LGI: 3	Target = 3 / Achieved = 20 / LGI: Exceeded (20). 20 research and learning products or events co-developed with LMIC partners. These included co-authored research with institutions in Ghana, Kenya, Nepal, and Tanzania; co-hosted policy dialogues and forums with regional bodies such as The Association for the Development of Education in Africa (ADEA) and Institute for Educational Planning and Administration, University of Cape Coast (IEPA-UCC); and co-presented panels featuring LMIC-based speakers and NGOs. However, LGI’s report does not disaggregate contributions by gender, location, or type of product/event as required by this indicator.
4.3: Cumulative # of in-country government representatives, stakeholders, implementers and global education community who engage with WWGHE evidence / Disaggregation: type of engagement, audience, in-person/online	Target = 165 / BSG: 20 / IIEP: 145	BSG: Exceeded. 222 individuals from government, implementing agencies, and the global education community engaging with WWHGE evidence during the 2024–2025 period. This figure is drawn from attendance at the WWHGE Annual Conference, which served as a key platform for dissemination and engagement. There is no evidence provided that these attendees engaged with WWHGE evidence beyond being present as the number includes all public conference attendees and not just those from in-country or those who engaged substantively with evidence. This data is also not yet disaggregated by type of engagement, audience, or modality (in-person/online), as required by the indicator, hence the depth and diversity of engagement remain slightly unclear. / IIEP: Not met 65 stakeholders, including government officials, implementers, and education partners participated in a three-day technical workshop in Pakistan in April 2025. However, here too, the report did not disaggregate participants by type of engagement, audience, or modality.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 4 has been scored A+ as it delivered strong engagement across learning, LMIC leadership, and cross-cutting communications. While the volume of activity reported in this Output was high, the strategic contribution of these engagements to outcome-level change and cross-cutting leadership remains underdeveloped. Outputs 4.1 and 4.3 risk being interpreted as ad hoc participation rather than structured, reform-linked leadership. The CoP could risk becoming a networking platform rather than a vehicle for peer learning and reform influence. The score reflects strong delivery on existing milestones, but future reporting should include clearer definitions and indicators of cross-cutting leadership, alongside disaggregated monitoring of engagement quality. Moreover, disaggregation by gender, location, and engagement type was not consistently reported for these engagements, which limited the ability for this review to assess the equity and inclusion component. It is also recommended for CoPs to have clear, reform-linked workstreams so that strong participation can be translated into decision making.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No formal changes were made to Output 4 indicators during the reporting period. However, the scope of delivery expanded significantly, particularly in LMIC co-authorship and engagement. The Annual Conference and CIES events demonstrated strong demand for cross-cutting engagement but highlighted the need for better tracking of participation and clearer links to reform pathways. This AR recommends reviewing the current indicator definitions and disaggregation requirements ahead of the next Annual Review period to ensure they reflect the breadth of activity and enable more strategic use of the CoP and LMIC partnerships as vehicles for reform influence and cross-pillar learning.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on Output 4 recommendations has been mixed, as reflected in the scoring. The Community of Practice (CoP) was reactivated as per the previous AR’s recommendation, but its strategic function remains under-leveraged. Events were well-attended, but there is limited evidence that they have catalysed sustained peer learning or reform influence. LMIC leadership has been more meaningfully embedded, Leadership from LMIC has improved, with a Community of Practice steering committee of LMIC leaders (from India, Kenya, and South Africa) now contributing to setting the CoP’s agenda and priorities. LGI’s co-authored outputs with institutions in Ghana, Kenya, and Nepal, and CERP’s facilitation of technical dialogues in Pakistan, reflect a shift toward more equitable collaboration. However, institutionalisation of a system for tracking disaggregated participation or LMIC-led contributions across partners is still needed. Notably, the Annual Conference’s strong female and Southern representation (57% female speakers, 30% from the Global South) signals progress on inclusion, but this has not translated into consistent practice across all engagement platforms. Overall, the programme needs to develop a typology that distinguishes events and engagements between visibility and influence outcomes. Going forward, the CoP and LMIC engagement mechanisms should tightly link to reform pathways and be monitored for strategic contribution, beyond participation.

Key Lessons learned this year:

1. Mechanism to ensure LMIC partners shape agendas: There is no consistent mechanism to ensure LMIC partners shape agendas; their voices remain underrepresented in upstream governance and product scoping, despite increased co-authorship and co-hosting.
2. Pathways to impact: While Output 4 shows strong participation metrics, there is limited evidence that these engagements have influenced reform design or uptake in focus countries. The pathway from engagement to impact is unclear.
3. Equity tracking: Equity tracking remains weak; only a small number of research products include disaggregated data, and reporting templates do not require consistent equity metrics.
4. Cross-cutting outputs such as CoP events and the Annual Conference lack consistent alignment with country reform priorities and outcome-level change.

Recommendations for the year ahead:

1. Recommendation 8 - South-South engagement and localisation: FCDO and BSG, in collaboration with Strategic Partners, should co-design and implement a structured framework by Q3 of the next Annual Review period to institutionalise LMIC partner leadership in agenda-setting and governance. This framework should be integrated into bodies such as the Strategic Partnership Board and Research Coordination Group, with progress tracked through disaggregated indicators on LMIC leadership and influence.
2. Recommendation 8 - South-South engagement and localisation: FCDO should commission OPM to conduct a targeted MEL review of Output 4 by Q2, focusing on the influence of CoP engagements, LMIC-led products, and convenings on reform design and uptake. Strategic Partners should support this review by providing country-level evidence and feedback. The findings should inform revised indicator definitions and milestone targets for the next Annual Review.
3. Recommendation 7 - Gender and Inclusion (equity): FCDO, BSG, and Strategic Partners should update reporting templates by Q2 to require systematic disaggregation of data on gender, disability, and other forms of disadvantage. Strategic Partners should ensure all new research products and events include equity metrics, with annual progress reviewed at the Strategic Partnership Board.
4. Recommendation 6 - External Policy uptake: Strategic Partners should work with FCDO and BSG to map engagement activities to national reform priorities and technical assistance pipelines by Q3. All cross-cutting outputs should include a clear rationale for their link to country-level outcomes, with alignment reviewed quarterly and adjustments made as needed.
## D: VALUE FOR MONEY (1 page)

Value for Money (VfM) is central to WWHGE, guided by FCDO’s 5E framework: Economy, Efficiency, Effectiveness, Equity, and Environment. The Blavatnik School of Government (BSG) has developed a VfM framework with indicators such as unit cost per research output, Southern authorship, and gender inclusion. Key metrics have been piloted and are informing management and engagement with strategic partners, with harmonised VfM reporting to be fully implemented in Year 2.

Economy: Year 1’s main cost drivers were staffing and international travel. WWHGE operates a fee-based, milestone delivery model, benchmarked against similar programmes to ensure competitive rates and expert leadership. BSG reviews strategic partner costs for VfM, with expenses paid on receipts. FCDO’s senior evidence leads and advisors (IRs) provide cost-effective, context-specific support, strengthening relationships with FCDO offices and governments. IRs have secured government buy-in, improved global coordination, supported country advisers, and enhanced national partner coherence. Of the £6,035,416 billed, 70% was directly linked to outputs. Oversight tools and detailed activity breakdowns have improved cost transparency and milestone design.

Efficiency: In Year 1, 23 research outputs were delivered by strategic partners, with average costs of £111,227 for Insight Notes, £91,602 for Working Papers, and £32,384 for Synthesis Reports (including management costs). BSG introduced standardised cost guidance and maximum effort levels for Year 2 to improve consistency and efficiency. The consortium secured £2,639,522 in external funding, expanding impact and leveraging resources. With reduced UK aid and the end of USAID funding, strategic partners increased fundraising efforts, securing new grants from the Marshall and Porticus Foundations to support GEEAP and BE². For example, GEEAP’s work on “smart buys” was supported by external funding and informed national education plans in eight countries.

Effectiveness: WWHGE has improved the use of evidence in education systems, leading to better cost-effectiveness and impact. Collaboration with strategic partners has expanded the programme’s reach:

- GEEAP’s “smart buys” report informed national education plans in eight countries and was referenced in policy discussions.
- UNICEF incorporated WWHGE research into its education programmes, shaping programme design and delivery.
- LGI piloted the Delivery Toolkit, supporting implementation in various contexts and sharing lessons learned.
- The British Council formed coalitions in several countries, building local capacity and reducing duplication.
- The Education Endowment Foundation (EEF) provided evidence synthesis and helped build capacity among local researchers.

However, as the programme is still in its early stages, overall effectiveness remains uncertain. In the coming year, efforts should focus on closing the gap between outputs and outcomes to provide stronger evidence that the programme is achieving its intended results. Recommendation 2 (page 4) will address this.

Equity: Gender, disability, and social inclusion (GEDSI) are included to some extent in programme design, delivery, and governance although there is more to do (see recommendations in the earlier sections). In Year 1, 65.9% of outputs were authored by women, and 77.3% included Global South authors. Seven outputs included disaggregated data. Quarterly meetings and a developing GEDSI strategy ensure ongoing integration. New assessment tools and frameworks are being developed to monitor inclusion, with continued efforts to strengthen Southern leadership and capacity through targeted support and training.

Environment: The programme should maintain a focus on the links between education, climate, and biodiversity. The programme can influence planning and practice in schools, as seen by partners already minimising environmental impact through alternative transport and remote participation. Environmental considerations should continue to be integrated into programme planning and delivery.

Assessment: WWHGE shows good value for money through strong financial management, efficient delivery of outputs, and effective use of resources. Equity is demonstrated by high levels of Southern and female authorship, as well as integrated inclusion. Continued focus on mainstreaming gender and equity is essential, as there is a risk the programme may not fully meet its ambitious gender goals without this. The milestone payment model and cost guidance help maintain ongoing efficiency.

Recommendations for Year 2:
- Fully implement the VfM framework and harmonised reporting across all strategic partners.
- Strengthen output quality and impact measures, including more rigorous monitoring and evaluation.
- Institutionalise support for Southern and female researchers, using disaggregated data to track progress.
- Formalise responsive support functions and improve strategic partner visibility and coordination.
- Enhance collaboration with other FCDO programmes to maximise impact and share best practice.
- Strengthen the IR role by developing structured approaches to generate internal demand for responsive synthesis and policy technical assistance.
E: RISK

Overview of risk management: The overall residual risk for the programme is moderate. A risk appetite statement for WWHGE has been agreed in line with FCDO’s risk appetite and the RED Risk Strategy (March 2022).
The FCDO risk register currently lists 22 risks: 0 major, 10 moderate, and 12 minor (after mitigation). Key risk areas include programme delivery and sustainability, policy alignment, reputational concerns, and safeguarding.
Risk is managed collaboratively across the main contract with BSG and strategic partners. FCDO and BSG maintain and regularly update risk registers, with BSG reporting to FCDO via monthly dashboards and formal reviews. Strategic partners and Implementation Roles (IRs) contribute to risk identification and escalation through quarterly meetings. The FCDO Programme Responsible Officer (PRO) holds weekly meetings with BSG managers to ensure rapid response. A centralised risk register, managed by FCDO, aligns all partner risks and improves transparency.
The programme’s overall residual risk is moderate, with the main risks being:
Programme Delivery & Sustainability:
Risk: Potential reduction or withdrawal of funding post-2027 dues to ODA reductions.
      Mitigation: FCDO and partners are aligning priorities, demonstrating value for money, and exploring cost-sharing and sustainability options. Monitoring and evaluation are used to evidence impact.

Policy Alignment:
Risk: Misalignment between BSG, FCDO, and strategic partners on roles and governance.
Mitigation: Roles are clearly documented and reviewed; regular management meetings and escalation to the Triage Board address changes.
Risk: Limited communication of research to policy audiences.
Mitigation: An engagement strategy is being implemented to maximise policy influence, including collaboration with donors and governments.
Reputational Risk:
Risk: Conflicts of interest among staff or poor coordination with other initiatives.
Mitigation: Conflict-of-interest policy and register are regularly reviewed; coordination is strengthened through Strategic Partnership Board meetings and close work with FCDO Education Advisers.
Safeguarding:
Risk: Non-compliance with safeguarding guidelines.
Mitigation: All suppliers comply with FCDO safeguarding policies, with clear complaints mechanisms and due diligence. Safeguarding standards are contractually enforced, with ongoing audits and training.
Forward Focus: Next year, the biggest risk will be around potential reductions in ODA impacting the programme delivery, which we will need to manage carefully. Additionally, the programme will prioritise improved research communication, strengthened FCDO oversight, and robust safeguarding to address key risks and support successful delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

Reporting, governance, and commercial requirements were met with progress on collaboration and resource management. A continued focus on GEDSI, approvals, and communication will enhance delivery quality.

Reporting: BSG and consortium partners met all reporting requirements in Year 1, delivering monthly dashboards and quarterly reports on time. KPI scores consistently exceeded 400, reflecting high delivery quality. GEDSI integration was flagged for improvement, with actions underway.

Governance: Regular governance meetings and Strategic Partnership Board (SPB) sessions ensured alignment and collaboration. The Research Coordination Group (RCG) Terms of Reference were finalised, and its first meeting is set for Year 2.

Commercial and Contracting: All strategic partner agreements and most grantee agreements were completed, laying a solid commercial foundation for delivery and compliance.

Collaboration: Partnerships and coordination between FCDO, BSG, and Strategic Partners improved. For Year 2, focus areas include greater integration of GEDSI, clear approval processes, and strengthened feedback mechanisms.

Approvals: Role clarification and targeted feedback streamlined deliverable submissions. The new peer review framework and milestone format ensure efficient approvals.

Resource Management: Strategic Partner management has become more efficient, with Implementation Roles leading technical work and reporting, and PRO and Programme Manager overseeing finances. To avoid misalignment, formal feedback loops between Implementation Roles and programme leadership are recommended.

The planned Policy Triage Board represents a positive step towards more robust decision-making and policy oversight in Year 2.

Finances
The programme’s joint funding from RED (£39m) and EdGE (£16m) totals £55m. Programme spend reached 9.7m (18% of budget), with a cumulative spend of £14.8m (27% of budget).

Partner Spend (Year 1 and Year 2):
Partner	23/4 AR Spend	24/5 (current) AR Spend
BSG	£2,417,047.53	£6,113,851.02
World Bank	£1,400,000.00	£1,400,000.00
GEEAP	N/A	£74,721.80
LGI	£179,477	£608,163.00
Staff cost (GED)	£56,663.58	£94,224.61
Staff costs (EGIR)	£220,600.97	£210,920.90
Evaluation OPM	N/A	£24,312.00
UNICEF	£93,750*	£400,000.00
British Council	N/A	£380,488.07
UNESCO IIEP	N/A	£419, 897.82

Blavatnik School of Government (University of Oxford)
Delivery: BSG and consortium delivery partners have maintained all reporting requirements in the reporting period. Monthly dashboards have been submitted on time and discussed with FCDO PRO and Programme Manager through regular meetings. Quarterly reporting has been delivered on time and with adaptations to ensure completeness of reporting. BSG and FCDO KPI assessments have aligned for each quarter. BSG KPIs have been consistently >400 marking significant delivery quality. Areas for improvement and lower scoring have been identified, namely in relation to GEDSI integration in the programme, and recommendations have been taken on board and began actioning.

Accuracy of forecasting: During financial year 2024/25 BSG spend reached £6,113,851 against a projected spend of £6,220,439.36, a variance of – 1.71% (see Table 2).

Budget line	FY 2024/25 budget	FY 2024/25 actuals	Variance (£)	Variance (%)
Milestones	£ 4,024,875.98	£4,267,496.08	£ 242,620.10	6.03%
Reimbursables	£ 2,195,563.38	£1,846,354.94	-£349,208.44	-15.9%
Total	£ 6,220,439.36	£6,113,851.02	-£106,588.34	-1.71%

The main cause of variance was lower than expected reimbursable expenditure. Particularly, in quarters 1-3 there were some blockers to progress/spending experienced by research teams in Ghana, India and Tanzania while finalising plans and seeking government partner approvals to commence data collection and research activities. Similarly, there were delays in contracting the P2 enhancement fund partners.
BSG’s underspend for 2024/25 is within acceptable risk limits. Proactive management through regular reporting and identification of additional deliverables helped reduce underspend and maximise use of available funds.
In Quarter 4, BSG introduced measures to reduce underspending for FY 24/25, including four additional milestones for the final quarter of Year 1. Earlier in the year, there was underspending in Quarters 1–3, especially in reimbursable costs. However, these costs were recovered in Quarter 4. The revised timeline and extra milestones resulted in a positive variance in milestone costs. Meanwhile, reimbursable costs, which had previously shown a negative variance, also improved in Quarter 4. This improvement was partly due to resolving delays faced by research teams in Ghana, India, and Tanzania, who had been waiting for government approvals to start data collection. These issues were resolved by the end of Quarter 3, enabling spending to catch up through careful financial and programme management.
British Council: Allocated grant from FCDO for financial year 2024-25 was £386,344 of which £305,700 was invoiced. This therefore represented a spend of just under 80% of the allocation but given that the British Council WWHGE team were only mobilised from Q3 some underspend was perhaps to be expected. Programme Management KPIs were introduced from Q4, with 10% tolerance for financial forecasting – British Council spend for Q4 was exactly as forecast.

UNICEF: UNICEF received a total contribution of GBP 750,000.00 (US$ 954,198.47), including GBP 7,426 remitted to the UN secretariat as 1% coordination levy, leaving a total of GBP 742,574.00 (US$ 944,750.63) for implementation of the programme. As of 31st March 2025, a total of US$ 88,540.06 has been expended including $ 5,049.57 in commitments. The figures below show the funds executed by period reported by the categories agreed upon by the parties. Delays in staff recruitment explain lower-than-expected execution. Please note, the financial figures are interim. Final figures will be provided in the Final Certified Statement provided by the UNICEF Comptroller.

IIEP: The total spend for the reporting period was £119,897.82

GEEAP & BE2: Manon Daniels the supplier overachieved on the number of uptake events for the GEEAP report and continued to lead the interest groups for the Building Evidence in Education Partnership including groups on education in emergencies and early childhood exceeding the targets and delivering value for money for their allocation of £74,721.8,

Learning Generation Initiative (LGI): The total spend for the reporting period was £608,163.00 (April 24 to March 25). This year, with the intention of ensuring the maximum impact and value for money in its WWHGE partnership, undertook a mapping of strategic partner work and agreed objectives which will improve co-ordination and amplification of each other’s work. This included working to bring together actors who had a shared interest in further research, insight and system-led action that furthers the impact of the middle tier of the education workforce. This involved the establishment of a new WWHGE working group on the middle tier bringing together partners like BSG, Gates Foundation, British Council, UNICEF Innocenti, and the World Bank. Other successes included enhanced collaboration amongst stakeholders in Kenya’s Evidence Ecosystem, and support to Ghana’s Presidential National Education Review Consultative Report

World Bank: FCDO WWHGE funding to the WB is £4.2m over five years (£700k per year) into the Foundational Learning Compact Trust Fund (FLC-TF). WWHGE funding contributes to a wider set of FLC activities and is informally/loosely earmarked to specific programmes and projects under the FLC-TF. There has been no variance as FCDO funds contribute to the Trust Fund and are not officially earmarked. New milestones are agreed annually. This AR, The WBG Implementation Science team is investing in knowledge exchange with WWHGE partners and contributing to the global research agenda on implementation science with analytical products and global public goods.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Annual Review 24/25: The annual review was led by the WWHGE Programme Responsible Owner, with input from FCDO’s Education Advisor in Nepal, Implementation Roles (IRs), and GED colleagues and self-reporting from the programme partners. The process included reviewing outputs, recommendations, and interviews with strategic partners.

Independent MEL Partner: Oxford Policy Management (OPM) was appointed as the independent Monitoring, Evaluation and Learning (MEL) partner in January 2025. OPM will monitor, evaluate, and support learning for WWHGE until May 2029, assessing achievements against the theory of change (ToC), log frame, and FCDO’s Pathway for Scaling Learning Outcomes. MEL workstreams cover monitoring, evaluation, value for money (VfM), and learning. OPM’s inception phase ends July 2025, after which formative evaluation begins. The draft inception report was rated Excellent by FCDO’s EQUALS team.

Country level Theories of Change: BSG, FCDO, and the British Council convened partners in Rwanda, Tanzania, India, and Pakistan for ToC workshops to align impact ambitions and co-develop country-level ToCs. These workshops produced draft ToCs, refined with partner feedback, which will guide programme strategy, monitoring, and adaptive management.

Logframe: The log frame was revised with BSG, strategic partners, and FCDO, streamlining indicators and focusing on gender, inclusion, government engagement, EdLabs, BSG tools, and system diagnostics. Event indicators now distinguish technical and high-level meetings. Additional indicators track country coalitions, BSG Fellows, and the Lemann Grant. The log frame now has 11 indicators, to be reduced to nine, with future revisions focusing on government engagement, policy influence, and equity. OPM reviewed the log frame and suggested further refinements.

Evaluation: OPM’s evaluation approach is comprehensive and adaptive, focusing on relevance, coherence, efficiency, effectiveness, equity, and sustainability. The work will begin in early summer 2025, using a rubric-based framework, evaluation will occur at baseline, midline, and endline, employing surveys, interviews, focus groups, and document reviews. Both formative (due Sept 25) and summative evaluations will support programme improvement and accountability.

Evidence: Year 1 of implementation shows early signs of progress, with impacts captured in stories of change and an impact log. Attribution to FCDO is currently anecdotal, relying on partner self-reports. OPM will strengthen evidence robustness and triangulation. BSG and partners have embedded mechanisms to track outcome data by gender, disability, disadvantage, and southern authors, ensuring inclusivity.

Learning: BSG holds quarterly learning sessions with partners to reflect on data quality, share experiences, and identify solutions. These sessions inform mid-course adjustments, technical assistance, risk management, and learning agenda refinement. Strategic partners document lessons in quarterly and annual reports, guiding programme adjustments and priorities. OPM has developed a programme-level learning agenda, building on BSG and partners’ lessons, with a learning log to be compiled.

Lessons from WWHGE Conference: Following the first WWHGE conference, BSG conducted a post-event survey and two learning sessions to gather feedback from stakeholders, including participants, speakers, and FCDO representatives. The conference was praised for its time management, high-quality content, and participatory workshops. However, challenges included venue limitations, a dense academic schedule, and technical issues. Suggestions for improvement focused on enhancing registration, session flow, and technical support, as well as increasing diversity and representation among panellists. Participants recommended expanding themes to include AI, mental health, and climate change. BSG is using these insights to improve future events and foster continuous learning.

See Annex A for learning insights from the programme.

Date of last narrative financial report		Date of last audited annual statement

Annex A

Learning across WWHGE has surfaced important insights that are already shaping the programme’s strategic direction and implementation approach:

1. Government Alignment Drives Impact: The strategic alignment with national priorities - such as Rwanda’s Teacher Policy and Tanzania’s curriculum reform agenda - greatly enhanced the relevance, uptake, and policy influence of partner interventions. This has informed the programme approach to early-stage engagement and agenda setting in other focus countries.
2. Embedded Models Foster Ownership: Embedding teams within government structures has shifted perception of the work from externally driven to domestically owned, improving policy traction. This model is now being actively replicated in additional contexts to support sustainability.
3. Adaptability is Critical in Politically Fluid Environments: Political transitions and administrative delays required flexible programming. The use of adaptive delivery strategies, including staggered rollouts and phased commitments, is now being formalised into BSG programme planning processes.
4. Sustained Engagement Yields Long-Term Results: Even with initially low conversion rates, continued relationship-building with government counterparts led to deeper partnerships and more substantive policy influence. The programme is investing more strategically in long-term stakeholder engagement pathways.
5. Digital Systems Enable Scalable, Inclusive Monitoring: Tools like Rwanda’s CAMIS and India’s real-time dashboards are proving effective in expanding the reach and quality of monitoring efforts. These technologies are being refined to include disaggregated data (e.g., gender, disability), supporting more inclusive evidence generation.
6. Government-Led Implementation Supports Sustainability: Programmes delivered through government personnel (e.g., Sector Education Inspectors) have demonstrated greater potential for scale and durability than externally delivered pilots. As a result, implementation design is increasingly focused on government-led delivery models.
7. Local Teams Are Essential for Effective Delivery: Local staff have played a critical role in navigating bureaucratic systems, maintaining relationships, and seizing emerging opportunities. This insight has reinforced BSG commitment to resourcing and empowering in-country teams.
8. Cross-Pillar Collaboration Requires Clearer Communication: While internal collaboration has improved, some external stakeholders continue to view the programme’s pillars in isolation. To address this, the team is working on clearer articulation of cross-pillar synergies, particularly around shared learning agendas such as foundational literacy and numeracy.
9. Timely, Context-Relevant Evidence Enables Policy Influence: Strategic engagement -such as J-PAL’s budget consultations in India demonstrates that relevant and timely evidence can inform decision-making and sustain scaled interventions. Going forward, the programme will prioritise adaptive, context-sensitive advocacy to align with shifting government priorities.
10. Technology Enhances Monitoring and Responsiveness: Investments in digital platforms have improved the speed and inclusivity of data collection (e.g., Youth Impact/Alokit’s tools). BSG plans to introduce high-frequency monitoring surveys in Year 2 that would enable faster course correction and more responsive implementation.
11. Political and Bureaucratic Changes Require Flexibility: Government transitions in several focus countries disrupted some activities. However, long-term partnerships and MOUs helped preserve programme continuity. Future work will continue to balance rigorous research timelines with dynamic policy needs, particularly where governments shift focuses on immediate implementation priorities.
12. Storytelling and Knowledge Translation Remain Underutilised: Stories of change and case studies (e.g., Karnataka) have proven powerful for communicating impact but are not yet systematically documented or disseminated. The research team will strengthen these outputs in Year 2 through more structured documentation, including podcasts and multimedia to reach wider audiences.