## Annual Review 2025

Title: Sahel Humanitarian Assistance and Protection Programme (SHAPP)
Programme Value £ (full life): £235m		Review date: 18 Oct 2025
Programme Code: 300943	AMP start date: 15 December 2021	AMP end date: 31 March 2028

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	LogFrame

A. SUMMARY AND OVERVIEW

Description of programme

The Sahel remains one of the world’s most fragile regions—marked by extreme poverty, climate vulnerability, and escalating insecurity. 22 million people now require humanitarian assistance, with over 8[1] million facing acute food insecurity and 1.6[2] million children suffering from severe acute malnutrition. The crisis is compounded by political instability. Military regimes in Mali, Niger, and Burkina Faso—formed after successive coups—have increasingly distanced themselves from Western and international partners, suspended elections, and consolidated power.
[1] OCHA Sahel Dashboard – 16 September 2025 – link; No data was published for Burkina Faso.
[2] Ibid

The governments of the central Sahel have rejected Western aid frameworks and restricted humanitarian access, including often imposing armed escorts requirements for humanitarian operations. Several humanitarian actors, including SHAPP partners, have been suspended or instructed to close down operations in Niger and Burkina Faso. At the same time, aid organisations face severe funding shortfalls, with only 18% of the $3.6 billion needed for 2025 secured (in the Sahel[3]). As a result, humanitarian aid has been scaled back to just 7.7 million people, despite broader needs[4].
[3] For the purposes of SHAPP and this review, the ‘Sahel’ includes Burkina Faso, Mauritania, Niger, Mali and Chad.
[4] OCHA Sahel Dashboard – 16 September 2025 – link; No data was published for Burkina Faso.

Over 6 years (2022-2028), and with an overall budget of £235 million, the Sahel Humanitarian Assistance and Protection Programme (SHAPP) seeks to deliver humanitarian assistance and protection to the most vulnerable people in geographic ‘hotspots’ of acute humanitarian need of the Sahel region. SHAPP delivers in Mali, Burkina Faso, Niger, and Chad through a combination of six partners:
The Danish Refugee Council (DRC), which set-up and manages the Sahel Regional Fund (SRF); a multi-year fund to international and national Non-Governmental Organisations (NGOs).
The International Committee of the Red Cross (ICRC).
The United Nations High Commissioner for Refugee (UNHCR), which in addition to work in eastern Chad, also set-up and is delivering harmonised protection monitoring across the region through Project 21 (also called P21).
The International NGO Safety Organisation (INSO).
The World Food Programme (WFP) and the United Nations Humanitarian Air Service (UNHAS), managed by WFP.
The Stand-By Personnel (SBP) roster, via an FCDO centrally managed mechanism.

In October 2023, a Business Case Addendum approved the new response to Sudanese refugees in eastern Chad (through WFP), an extension in the duration of the programme from March 2026 to September 2028, and an Internal Risk Facility (IRF) to flexibly respond to future crisis peaks if further funds become available. A further BCA was approved in March 2025 to allow for spend this financial year and to replenish the IRF (including the option to deliver in Mauritania if needs peak). This Annual Review reports on last financial year’s activities (April 2024 – March 2025) and is based on narrative reports issued by August 2025.

Summary supporting narrative for the overall score in this review

Not all indicator milestone targets were met by SHAPP partners for the period of this review, notably for the number of people assisted with protection activities and number of children treated for severe acute malnutrition. However, overall, SHAPP partners achieved or exceeded most of their expected outputs and did remarkably well, given the challenging context, particularly in terms of the numbers reached with humanitarian assistance. For this reason, the programme has scored an A, meeting expectations. The creativity, persistence and hard work of partners under such circumstances deserves respect and recognition.

The period in review (April 2024 to March 2025) corresponds to the fourth year of the programme (started in December 2021), and its third year of assistance delivery. Over this period, FCDO funded:
- £21,862,984 to the SRF, managed by DRC. This provided food assistance to 131,053 people, protection assistance to 69,146 people, healthcare to 211,653 people and other multi-sectoral assistance to 124,212 people (including water and sanitation, shelter and livelihoods creation)[5].
  [5] Through three NGO consortia: DEWRAL led by Catholic Relief Services (CRS); RALLIER led by Mercy Corps; The IRC consortium led by the International Rescue Committee (IRC); and FLASH led by DRC.
- £23.8m to ICRC for the provision of protection services to 5,184 people, food assistance to 78,328 people, and other multisectoral assistance to 406,548 people including support to food production, income generation, and water and sanitation.
- £28m to WFP to provide food assistance (in-kind and cash) to 261,818 people in eastern Chad affected by the Sudanese crisis (refugees and host communities); and £1.6m to transport 2,675 people through critical humanitarian flights operated by UNHAS.
- £1,501,738 to UNHCR to continue building the Project 21 regional protection monitoring mechanism and deliver protection analysis and advocacy, as well as £8m to UNHCR for its refugee assistance interventions to 114,659 people in eastern Chad.
- £292,506 to the Stand-By Personnel roster, which funded two positions:
- Chad Civilian-Military Coordination and Access Officer for 12 months;
- Burkina Faso – PSEA Coordinator for 6 months.
£1.2m to INSO to deliver security and safety advice and training to humanitarian organisations, international and national.

Major lessons and recommendations for the year ahead

Resilience: The flexibility of SHAPP programmes to incorporate a wide spectrum of interventions that cover both immediate humanitarian as well as early recovery or resilience building responses is a strength of the portfolio. However, FCDO needs to critically assess whether partner programmes are truly delivering lasting resilience outcomes, not just outputs, and whether partners are sufficiently questioning their impact and effectiveness. There is a need to gather evidence and learning together with partners on what works in terms of resilience interventions in the Sahel. In the short term this means requesting partners to share what evidence they are currently collecting to draw out learning. Looking forward to the future business case, we will seek to develop a common governance across the programme and portfolio with minimum requirements for a cross-component M&E framework and learning agenda, including an emphasis on resilience.

Relatedly, FCDO should consider bringing in social development, climate and conflict prevention considerations into an integrated Theory of Change when designing its next Business Case for the Sahel. This will ensure more intentional synergies across all Sahel programmes and more coherence in meeting both the short and long-term needs of vulnerable populations.

Localisation: The SRF has continued to evolve and establish itself as a strong and effective mechanism for delivering humanitarian assistance to hard to access parts of the region. It has increasingly made use of local NGOs and included them in its governance structure. This has proven to be essential to continue serving many parts of the central Sahel, particularly where UN and international actors are losing presence and credibility with the authorities, and where the traditional international humanitarian architecture is weakening. FCDO should ensure that the SRF can continue to strengthen its structure and functionality and help it to mature into a long-term pooled funding mechanism integrating local partners to the greatest extent possible. While SHAPP should continue to include the Red Cross and UN actors as well, these international agencies should be pushed towards more meaningful efforts to partner locally.

Humanitarian diplomacy: FCDO’s presence and engagement (both humanitarian and political) across the countries of the Sahel has been strongly welcomed by humanitarian stakeholders and should be maintained, including through regular country visits. FCDO’s discreet diplomacy—especially in Mali, Chad and Niger — has added significant value thanks to carefully coordinated messaging and advocacy. The UK’s support in Chad, including in relation to the Integrated Territorial Approach and National Response Plan, has been particularly appreciated. Ongoing dialogue remains possible, as shown by the recent inaugural AES Humanitarian Ministers’ Forum in Bamako in August 2025. FCDO should look at what came out of this event and see what opportunities there may be for further humanitarian engagement. FCDO could also make use of a social protection framing for dialogue to maintain constructive engagement.

FCDO expertise: FCDO’s effectiveness as a humanitarian donor in the Sahel depends on maintaining consistent levels of technical and programmatic capacity across the portfolio. This needs to be sufficient to enable regular in person engagement across the region and administrative oversight of FCDO resources. The current configuration of Humanitarian Advisors (HA) (one Senior HA and two HAs) together with programme management staffing needs to be maintained going forward. Additionally, if the future humanitarian Business Case is to incorporate a Theory of Change that also addresses social development and conflict prevention considerations, then technical advisors in these fields may also best be resourced within the structure of the programme, to avoid the risk of siloed interventions.

Geographic considerations: flexibility around the geographic allocation of funding within SHAPP and the use of the IRF has been key to its success. This is particularly true of the resourcing of the refugee response in Chad starting in 2023 and 2024, where FCDO’s support has been critical to the scale up of the response. However, with funding likely to be increasingly limited going forward, future business cases should be designed to avoid a disproportionate weighting of budgets going towards the relatively high-profile Sudan refugee response in Chad at the expense of ongoing and increasing needs and levels of displacement in more overlooked parts of the central Sahel. It is also important to continue monitoring humanitarian needs and gaps in the rest of the region, including Mauritania, to inform prioritisation decisions for future allocations.

Progress on cross-cutting recommendations from last AR:

AR 2024 recommendations	Progress
FCDO should continue identifying and deepening areas of complementarity with other programmes within the FCDO Sahel portfolio or in the same locations (for example, the provision of cash transfers[6]; or adaptation to climate change through the soil recovery and restoration activities that SHAPP delivers[7]).	Ongoing – complementarity being sought with other Sahel regional programmes JASS[8], CRISP[9] and SRP[10] as part of forward look and thinking on new Business Case.
Women and girls are disproportionately affected by the crisis in the Sahel, and the Programme had indicated its ambition to contribute significantly to Gender Equality (to comply with the Gender Equality Act). However, overall, partner reporting is gender blind with the exception of gender disaggregated data. FCDO should therefore work with partners to get more systematic information on gender considerations in the programme design and delivery.	Partial progress: P21 references Gender Based Violence (GBV) a lot – however, only 60% of P21 Sahel questionnaires target Age, Gender and Diversity issues. The SRF (at least in annual reporting) is not evidencing gender considerations in design beyond disaggregation of data and reference to GBV.
Currently, around 20% of SHAPP programme funds qualify as ICF. The FCDO should develop a whole-of-programme approach to climate and disaster risk resilience, that captures how the programme already contributes to climate outcomes and how it could do more. The FCDO should develop a method to report systematically on SHAPP’s ICF contribution.	On hold: this has been put on hold while FCDO works out what the Sahel portfolio will look like moving forwards - the current plan is to re-visit this at the end of 2025.
[6] FCDO funds the World Bank under the Shock Response Programme (SRP) to deliver safety nets and support the development of shock-responsive social protection programmes; Under the FCDO programme Justice and Stability in the Sahel (JASS), Mercy Corps delivers cash for work activities.
[7] Mercy Corps undertakes land restoration activities under the programme JASS.
[8] Justice and Stability in the Sahel – DevTracker link
[9] Climate Resilience in the Sahel Programme – DevTracker link
[10] Shock Response Programme – DevTracker link

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

ToC Assumptions:
Access and ability to effect HMG oversight and monitoring of partner implementation in the field; / Partner ability to attract, recruit and retain key staff is reinforced through multi-year funding; / Reinforced evidence and data base is sufficiently compelling and there are the space and opportunity to influence broader policy and programming; / Access is challenging but not impossible to hardest to reach areas and/or alternative modalities/ways of working can be innovated; / Partner ability to access not completely compromised by criminality, government admin and/or lack of acceptance of neutral and impartial humanitarian response, / Conflict will not be resolved in the lifetime of the project but geographic areas do not expand significantly and the wider region will not deteriorate significantly, further massively increasing need / Other key humanitarian donors do not reduce their contributions / Despite a significant reduction in humanitarian funding the UK continues to have a convening and advocacy role and remains credible to influence others. / There is scope to engage and influence how development actors and other stakeholders increase the flexibility and adaptive nature of programming in a volatile context as part of the humanitarian-development nexus. Where evidence and challenge are provided, stakeholders remain open to reform and adapt.

The SHAPP Theory of Change (ToC) is that a more effective, efficient and equitable delivery of humanitarian aid for the most vulnerable people in the Sahel is made possible because the most vulnerable people (including in the hardest to reach areas) in geographic hotspots of most acute need receive prioritised humanitarian protection and assistance. Safety and security for humanitarian actors enables them to access those in need (and for those in need to access humanitarian aid) whilst data and evidence inform policy and programme priorities (key enablers).

The FCDO Annual Review team has reviewed the ToC and assesses that it remains valid as included in the original business case.
- The humanitarian and protection crisis in the Sahel continued to deepen and spread over the reporting period, validating the need for a multisectoral programme response. Compared to 2021 when the Business Case was designed, there has been a steep increase in the number of people who are severely food insecure in the central Sahel, with a projection of 8.4 million people facing food insecurity in the region (IPC Phase 3+; no data published for Burkina Faso) compared to 2021, when 5.2 million people were severely food insecure in the same region. Displacement within the central Sahel and externally has continued to grow, with over 3.3 million IDPs or refugees in Burkina Faso, Mali, and Niger due to escalating violence and instability, now also spreading to coastal countries including Benin, Togo and Cote d’Ivoire. Numbers of refugees coming into Chad from Sudan have also continued to rise, with roughly 900,000 present as of June 2025[11].
  [11] IOM Displacement Tracking Matrix, central Sahel and Coastal countries, May 2025.
- The further withdrawal of humanitarian donors, notably the US in early 2025, has devastated an already overstretched system and sharpened the need to make hard choices about where to prioritise humanitarian aid to meet basic needs.
- Humanitarian access has further reduced, with increased restrictions and bureaucratic impediments imposed by the authorities. Several actors, including SHAPP partners, have been prevented from operating altogether and forced to leave parts of the region. Violence and extremism remain pervasive, and even enabling services such as humanitarian flights and security support are now being limited in places like Niger and Burkina Faso.
- Locally adapted and implemented programming is more vital than ever, as the previous pillars of the humanitarian system are increasingly unable to function and partners have to change their ways of programming to maintain their presence and relevance to continually shifting access conditions and emerging conflict and climate related crises. The need for flexible, data-driven approaches is paramount to ensure effective targeting and impact.
- In this context, several of the ToC assumptions are being challenged, notably that the geographic areas of the conflict do not expand significantly (massively increasing need) and that other key humanitarian donors do not reduce their contributions (which they are). However, if anything, this further sharpens the rationale for providing evidence-based prioritisation of protection and assistance in line with the ToC Outcome and Outputs. SHAPP’s flexible design has proven to be critical to flex to growing access impediments, to shift to or favour approaches that work (most obviously locally led action), and to address new or worsening needs.
- Adaptations during the review period have included the SRF operationalising its local partner rapid response mechanism (FLASH), launching localisation windows in Burkina Faso and Chad, and responding to new flood related emergencies in Niger and Chad. SHAPP has also provided additional IRF funding to UNHCR for the Sudanese refugee response in eastern Chad. NGO partners have adapted in innovative ways to new access restrictions, for example by upskilling staff of local NGO and community-based partners where access is not continuous, nimbly switching to in kind when cash transfers were blocked, and undertaking joint monitoring with government technical services to enable their subsequent take-over of programming and service delivery.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme’s impact is measured through two indicators:
- Impact Indicator 1: % of beneficiaries (disaggregated by gender / disability) reporting that humanitarian assistance is more accessible, timely and suitable to their multiple needs and vulnerabilities in Sahel compared to previous humanitarian assistance received.
- Impact Indicator 2: Humanitarian actors interviewed as part of evaluation and lessons learning processes report that the SRF enabled significant progress for principled and effective humanitarian response, access and localisation in Sahel.

As the SRF has been fully established and operational for more than two years, partners have been able to gather information to inform Impact Indicator 1. According to SRF monitoring, over 90.6% of SHAPP recipients interviewed reported that aid is more accessible, timely and suitable than before. This is above the milestone (80%) and a considerable achievement, especially considering it is the second year in succession of such a good result (in FY23/24, 87.4% was scored against this indicator). DEWRAL and RALLIER stood out, both exceeding 92%. These results reflect effective field strategies, strong coordination, and growing local capacity and illustrate the continuing strong performance of the SRF during the second year of the with the four implementing partners consistently exceeded expectations.

Impact Indicator 2 data coming from the SRF mid-term review indicates that most actors are reporting significant progress. AR interviews with a range of international and local SRF partners has confirmed the SRF’s capacity to implement a principled humanitarian response through maintaining principled access, and has continued to make progress in deepening its localisation of humanitarian response.

The programme’s outcome ‘The most vulnerable people in geographic hotspots of most acute humanitarian need - including in some of the hardest to reach areas – receive prioritised protection and assistance’ is measured through the percentage of SHAPP-funded humanitarian assistance going into hard-to-reach areas. Over the period in review, 72% of SHAPP assistance was delivered in hard-to-reach areas (the same percentage as the previous year) - slightly below the 75% target but nevertheless a significant achievement and in line with one of SHAPP’s key objectives. This ratio would have been higher (up to 89%) if SHAPP had not pivoted to doing more through partners in eastern Chad where access is better than in central Sahel.

Recommendation from the previous Annual Review	Progress
Now that all components of SHAPP are established, the FCDO and partners should consider capturing outcomes for people in the programme’s logframe (for example Food Consumption Score and Coping Strategy Index). This data is gathered in post distribution monitoring, but the relevance of including it in the logframe should be carefully assessed as it would require partners adopting the same indicators and analysing data in comparable ways.	For future consideration: WFP and SRF partners already collect this data, which is contained in their reports. ICRC is not providing this level of information. It is too late to try including in the logframe for this Business Case, related indicators could be included at outcome level in any future Business Case.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

SHAPP continues to be a relevant and effective programme to address the humanitarian situation in the Sahel. It is contributing and progressing towards outcome and impact objectives within the ToC. As assessed in Section D, the programme continues to represent VfM with partners continuously working on VfM gains, despite increasingly challenging operating conditions.

SHAPP partners are delivering vital support to the most vulnerable in remote and hard-to-reach areas, while also strengthening the overall operating and protection environment. They do this through essential shared services—core to the programme’s mission—ensuring humanitarian efforts are coordinated, impactful, and responsive to the needs on the ground. SHAPP aligns with key UK humanitarian policy priorities including: (i) providing flexibility and predictability through multi-year funding, (ii) driving efficiencies through as direct as possible delivery and use of cash transfers as a key modality where possible and relevant, (iii) taking a people-centred approach, focused on the most vulnerable and (iv) adopting a localised approach where possible. The programme is aligned to the Foreign Secretary’s Delivery Unit Humanitarian and migration priorities through support to lift vulnerable people out of crisis and build state and community resilience to shocks through stronger, more locally led humanitarian systems; and through its support to forcibly displaced people.

The worsening situation across the Sahel underscores the critical importance of continuing SHAPP. As instability deepens, humanitarian access shrinks, and vulnerabilities grow, SHAPP remains a vital mechanism for delivering targeted, life-saving support. Through strategic partner selection and focused interventions, SHAPP ensures that those most at risk receive timely and effective assistance, even in the face of rising protection threats and complex, long-term needs.

SHAPP should continue based on its own merits and in the context of the wider FCDO Sahel portfolio, which is also having to adapt to a rapidly evolving humanitarian and political context to remain relevant and effective.

## C. DETAILED OUTPUT SCORING

Output Title	Prioritised protection for the most vulnerable in areas of greatest need
Output number:		1	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of people (disaggregated by gender/disability) assisted with protection activities	218,100 (cumulative) / ICRC: 5,055 / SRF: 213,044 / UNHCR: 0	Total = 174,790 (cumulative) / ICRC = 7,232 / SRF = 147,906 (74,621 female) / UNHCR = 19,652
1.2 % of beneficiaries (disaggregated by gender/disability) reporting that humanitarian assistance is delivered in a safe, accessible, accountable, and participatory manner	70%	90.6%

Briefly describe the output’s activities and provide supporting narrative for the score.
This output measures the level of protection assistance provided by ICRC, the SRF and UNHCR as a result of FCDO contributions. This Output scores a B, having not met the agreed quantitative milestones. Rather than an issue of performance, this reflects an overestimation of targets by SRF partners. The SRF Fund Management Unit (FMU) is working with partners to ensure that targets remain realistic. Output 1.1 reached 80.1% of its milestone. Nevertheless, the number of people assisted by protection activities more than doubled compared to the previous reporting period from 80,808 to 174,790, confirming that programme delivery, particularly for the SRF, significantly expanded during the reporting period. Additionally, Output 1.2 (beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable, and participatory manner) scored 90.6%, well above its target.

With FCDO funding:
The SRF has provided protection services to 69,146 people during the period in review and 147,906 people (including 55.5% women) cumulatively since the start of the programme across Mali, Burkina Faso, Niger and Chad. This confirms the ongoing momentum of SRF-funded protection activities implemented through the three INGO-led consortia, who have continued to identify, manage and document cases of GBV and refer survivors to appropriate care structures, operate safe spaces for women and girls and Child-Friendly Spaces, and provide Psychological First Aid to individuals at risk in protection. DRC has also provided training to all FLASH consortium partners covering cross-cutting protection and case management, GBV, Protection from Sexual Exploitation, Abuse and Harassment (PSEAH), accountability and peacebuilding. Over 90% of SRF beneficiaries reported that humanitarian assistance was delivered in a safe, accessible, accountable and participatory manner. This is a considerable achievement in the complex contexts of the central Sahel and largely exceeded the milestone of 70%.

ICRC has provided protection services to 5,184 people during the period in review and 7,232 people since the start of SHAPP, including those deprived of their freedom, in Burkina Faso, Mali, Niger and Chad. This support includes tracing individuals, re-establishing family links through Red Cross messages and phone calls as well as visiting and monitoring detainees in places of detention. These figures do not fully reflect the ICRC’s critical work in promoting adherence to International Humanitarian Law and confidential bilateral dialogue with parties to the conflict, or the fact that all their service provision activities have protection of vulnerable individuals as their overall intended outcome. Taken together, this work and ICRC’s ability to reach locations and people where others cannot as well as its unique mandate continues to make the ICRC a critical actor in the region – despite the setback of being prevented from operating in Niger from February 2025.

UNHCR in Chad provided protection-related assistance to 19,652 children and caregivers during the reporting period. Including other donors funding, services provided included strengthened civil registration systems, enabling over 10,000 Sudanese refugees to obtain identity and legal status documentation through late birth registration and mobile court initiatives. Community-based protection interventions reached 5,000 individuals with GBV prevention and response services, while best interest procedures supported approximately 6,500 children and caregivers. Legal assistance was provided to over 1,500 individuals.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Milestones were revised to reflect existing partners updated delivery plans since the Business Case addendum. The UNHCR’s response in eastern Chad was originally not expected to provide for protection beneficiaries, however on receiving their report, it was noted that a number of beneficiaries were reached through protection activities and so were included in this AR. It is recommended that the milestone for Output 1.2 is increased from 2025 onwards to reflect the second successive year of strong results against this indicator.

Progress on recommendations from the previous Annual Review

Recommendations from the previous Annual Review	Progress
The three consortia funded under the SRF are delivering different protection approaches (analysis, type and diversity of activities, scale of interventions, level of details in reporting), though they sometimes operate in similar contexts. FCDO and SRF FMU should encourage deeper technical collaboration between SRF partners, including on Protection, to learn lessons from their experience and further improve the quality and impact of the SRF’s protection response.	Partial: partner collaboration over the reporting period has been strong, with positive feedback from partner surveys conducted both by the FMU and ICVA on the quality of collaboration within the consortium and in sharing learning experiences. However, there has not yet been specific technical engagement between partners on protection or efforts to harmonise approaches.

Lessons learned this year and recommendations for the year ahead

In addition to those carried over above, this year’s annual review has the following recommendations for the year ahead:
- FCDO and SRF FMU should encourage and support partners to explicitly engage in aligning their protection efforts and harmonise approaches, including via the P21 platform where relevant. FCDO could consider including a more protection specific indicator at outcome level in any future business case.
- Although there are good reasons why it is challenging, the SRF consortia leads still need to try and identify how they can reach more PWD and how their partners can address the shortcomings and inconsistencies of their tools when collecting data on disability status. Acknowledging the challenges associated with collecting health consultation data (as noted above), it could be more useful to ask SRF partners to focus their analysis of disability on more accessible data sets, especially for their protection and food security interventions.
- ICRC should provide more information on the implementation of its Disability Framework.

Output Title	Assistance for the most vulnerable in the areas of greatest need
Output number:		2	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	Yes (Up)

Indicator(s)	Milestone(s) for this review	Progress
2.1 Total number of beneficiaries (disaggregated by gender/disability) receiving appropriate calculated food (package) & cash-based assistance	600,743 (cumulative) / ICRC: 139,018 / SRF: 331,054 / WFP: 130,671	Total = 824,770 (cumulative) [137%] / ICRC: 116,657 (36,190 female) / SRF: 214,750 (106,091 female) / WFP: 493,363 (251,536 female)
2.2 Number of children (disaggregated by gender/disability) treated against severe acute malnutrition	69,974 (cumulative)	58,265 (cumulative) [83%] / SRF: 58,265
2.3 Number of supported individuals (disaggregated by gender/disability) who received health care services	161,801 (cumulative)	389,141 (cumulative) [241%] / SRF: 389,141
2.4 Number of people reached with non-food assistance including (i) Water, Sanitation and Hygiene, (ii) Shelter and Non-Food Items, (iii) Camp Management assistance, (iv) Livelihood creation opportunities and services (cumulative)	487,373 (cumulative) / Not disaggregated by individual partner as the indicator aims to capture SHAPP flexible support (which cannot be predicted in advance)	Total: 735,240 (cumulative) [151%] / ICRC: 587,656 (181,807 female) / SRF: 50,257 (27,393 female) / UNHCR: 95,007

Briefly describe the output’s activities and provide supporting narrative for the score.

This output measures the level of multi-sectoral humanitarian assistance provided by the SRF, ICRC and WFP as a result of FCDO contributions, excluding protection assistance covered under Output 1. This Output scores an A+, exceeding expectations. While the Output 2.2 milestone was missed, the three others were largely overachieved. Notably under Output 2.1, FCDO funded food and cash assistance reached 575,698 people during the reporting period, with the SRF, ICRC and WFP all reaching significantly more people than the previous year. Output 2.4 saw 510,432 individuals reached with non-food assistance during the period under review, which is well over double the previous year. The underachieving of Sub-Output 2.2 continues to relate to ongoing delays and access restrictions faced by SRF partners in Burkina Faso and Niger, which made nutrition programming particularly challenging due to the need for more time to effectively administer Severe Acute Malnutrition (SAM) treatment. That said, the number of children treated for SAM during the reporting period (38,405) was still double the number reached in 2023/24 (19,860).

With FCDO funding:

The SRF delivered multisectoral integrated assistance to 407,811 beneficiaries in Burkina Faso, Mali, Niger and Chad during the reporting period. As was the case in the previous year, 55% were female beneficiaries and just under 1% were people with disabilities, though this is likely to be a significant underestimate. Assistance included food security (122,593 people), malnutrition treatment (38,405 children), health (211,653 patients) and Shelter / WASH (1,619 people). Post-distribution monitoring revealed that 60.34% of surveyed beneficiaries achieved an acceptable Food Consumption Score (FCS) during the reporting period. Programmes were delivered by the same three INGO led consortia as in the previous year (Mercy Corps, International Rescue Committee (IRC) and Catholic Relief Services (CRS) each leading one) with an additional consortium led by DRC (FLASH) directing funding exclusively through six local partners operating across Burkina Faso, Mali and Niger. FLASH reached 27,689 individuals over the course of the year.

In its second full year of implementation, SRF partners faced increasing access and security constraints in all three countries of the central Sahel, but were able to continue delivering thanks to skilful negotiation and relationship management with local and national authorities, leveraging of community-based networks, and strong investment in working with and through local partners and decentralised procurement and technical services. This has increasingly set the SRF apart as a uniquely valuable humanitarian structure in the Sahel. It also proved its worth as a flexible and responsive mechanism for meeting evolving humanitarian needs, including during the increasing influx of refugees into eastern Chad in 2024, flooding in Niger and Chad, and numerous instances of small and medium scale displacement of communities across the region. Through the FLASH mechanism 68% of the assistance reached households in less than two weeks after the need was identified, which is a marked improvement on the 48% achieved last year.

WFP provided lifesaving food and nutrition assistance to 493,363 people, including 418,115 new refugees, 17,595 new returnees, and 57,653 host community members in eastern Chad. Through food and cash distributions, WFP provided 8,694 MT of food commodities and transferred £4.5m in cash to people of concern. It provided a 15-day food and nutrition assistance package to newly arrived refugees at the borders and transit site of Adré. Subsequently, in line with UNHCR and Government-led registration and relocation efforts, WFP supported refugees and returnees with monthly rations in relocation sites and 90 days of assistance targeting the most vulnerable host community households around new sites (10% of the number of refugees arriving in a new site).

During the reporting period, WFP’s assistance contributed positively to the food security of recipients. The analysis of the FCS trends indicates an improvement compared to 2023, particularly among new refugees (increasing from 32% in 2023 to 37% in 2024), returnees (from 38% to 62%), and host populations (from 54% to 68%). This improvement is likely due to the assistance provided by WFP. However, the results suggest that long term refugees continue to face difficulties in accessing an acceptable quantity and quality of food. It is therefore crucial to strengthen targeted interventions for this group to support them to better meet their food needs independently in the longer term.

ICRC delivered food assistance, WASH and livelihoods support (food production) to 484,876 people in Burkina Faso, Mali, Niger and Chad during the reporting period, and 704,313 people since the start of SHAPP. Due to global funding cuts in 2023, ICRC had already reduced the scale of its resilience activities but still managed to continue delivering essential services in hard-to-reach areas across the Sahel in 2024. It has continued to intentionally target harder to reach locations where other agencies are sometimes unable or unwilling to operate, even if this often more complicated and expensive. Unfortunately, ICRC operations in Niger were suspended in February 2025, a serious setback to humanitarian access in that country.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting of this output was revised upwards this year so that it better aligns with the overall proportion of the budget attributed to it.

Milestones were revised in 2025 based on updated partner plans, with estimates based on planned FCDO annual allocations and unit costs derived from the latest data provided by partners (ICRC’s 2023 annual reports, SRF project proposals and budgets, WFP’s 2024 Concept of Operation for Sudanese refugee response in Chad).

Progress on recommendations from the previous Annual Review

Recommendations from the previous Annual Review	Progress
[Rolled over from previous AR]. FCDO continued pressing on WFP Chad to better include crisis-affected people perceptions in PDMs. WFP confirmed that PDM questionnaires were amended accordingly. There are sensitivities around sharing the full results with FCDO, but WFP agreed in principle to share a summary of results. We continue to press to see these results and ensure their analysis informs programming and risk mitigation measures.	Ongoing: WFP is reporting on use of its community feedback mechanisms and demonstrating an improved commitment to Accountability to Affected People (AAP). WFP is not providing full Post Distribution Monitoring results but has shared PDM data for areas of specific FCDO interest upon request.
As stated in Output 1, the FCDO should continue pushing partners for disaggregated gender and disability data. The SRF should provide disaggregated data per sector, and support partners in addressing the shortcomings of their tools in collecting disability status.	Partial progress: SRF reporting does include disaggregated data, though numbers are low and not disaggregated by sector (mainly due to the national Ministry of Health templates used in medical consultations which do not collect this data). Moving forwards, FCDO should push the SRF to strengthen their analysis of disability in sectors such as food security and protection where they have discretion on data collection. In sectors where they don’t have that discretion, the SRF should explore alternative approaches (sampling or others) to produce decent estimates on disability. / WFP also reports on disability inclusion efforts in the narrative but not quantitatively. / ICRC reports disaggregate according to gender but not disability.
WFP should share and enhance its monitoring to account for outcomes and effectiveness. This should include Accountability to Affected Populations (e.g. rates of complaints addressed satisfactorily and in time).	Completed. 2024 reporting from WFP includes an overview of food security outcomes as noted above, alongside details of AAP efforts, including recording of satisfactory complaint resolution rate of 76%.
DRC should continue working internally and with FLASH partners to improve the proportion of responses delivered within two weeks of identifying needs.	Ongoing: 68% of responses are now delivered within two weeks, which shows a 20-point improvement compared to last year. DRC still have progress to make to reach their 100% target.

Sahel Regional Fund / DRC:

Recommendations from the previous Annual Review	Progress
Funding and pooled fund: To optimise its VfM benefits and agility, the SRF needs to become a pooled fund (as opposed to an accountable grant currently). The FCDO and the SRF Board should prioritise bringing other donors into the SRF now that results and learning are available. In doing so, the SRF Board will need to clarify the conditions for funding especially where funding is earmarked to certain countries.	Ongoing: donor engagement by FCDO, DRC, and board members has intensified, with efforts at country, regional, director and ministerial levels. Secured a small contribution from Denmark through high level lobbying of DRC's Secretary General. Other donors expressed interest but have not pledged. Sustained and more systematic engagement is now required. / SRF also still needs to further develop internal processes for becoming a multi-donor fund, including considering management of potential differences in donors earmarking, indirect cost recovery rates, risk tolerance and so on.
Learning: the SRF FMU should consider strengthening and resourcing the SRF regional learning function, between partners and countries covered, and even beyond (starting with other SHAPP partners). As part of that, the SRF FMU should continue identifying opportunities for partners to learn from each other, including on increasing and optimising VfM.	Ongoing: SRF FMU and partners have carried out ample regional level engagement and coordination, however no regional learning function per se has been set up (whether of VfM function or other) / Coordination of learning within SRF and across SHAPP by FMU has been secondary to setting up consortium structures and managing recent calls for proposals and an increasing number of grants. Action to be carried forwards to next year and to benefit from the contribution of the new partners. / SRF should recruit in house technical expertise to support partners and ensure cross learning.
Localisation: ICVA, in collaboration with the SRF and others, should consider consolidating a light-touch localisation strategy that captures the different efforts made to strengthen the role and voice of local and national organisations. This would provide a full picture of the work done and would allow the identification of further synergies between SRF funded activities and other initiatives.	Progressing: ICVA has supported the establishment of a regional coordination entity called FONGA (Forum des ONG en Afrique de l'Ouest et Centrale) whose membership is not limited to ICVA partners. Localisation is a key objective of FONGA, including through diagnosis (using its Localisation Barometer survey tool), support to NNGO platforms and helping NNGOs have a voice in relevant fora.
FCDO, SRF Board and ICVA should consider whether the SRF and ICVA could increase their ambition in their contribution to localisation, making the most of their regional role (e.g. support training mutualisation for NNGOs, complementing EU support to passporting due diligence; and / or resourcing to national NGO platforms which ICVA assesses as a fundamental gap).	Progressing: During the reporting period, ICVA continued to lead the regional community of practice on localisation, hosting a third event in May 2024. / It launched a new project to reduce the burden of Due Diligence (DD) procedures for local NGOs, seeking to enhance the complementarity of DD passporting initiatives. DD passporting was recently agreed to within SRF by FCDO. / An SRF localisation window was rolled out for NNGOs in Burkina Faso and Chad after the increase in funding to the SRF.
Climate resilience outcomes: The SRF is considering opening a climate resilience window if climate finance becomes available. In preparation, it should start building an understanding of the extent to which projects already contribute to climate resilience (a partner selection criteria). Learning from partners’ existing approaches and efforts (and their challenges) on climate resilience could inform the design of the dedicated window.	On hold: The climate resilience window has not yet been opened and relevant learning from partners on climate resilience is yet to be gathered to inform the design of the window. Until climate finance availability is confirmed (unlikely before the next Business Case is rolled out), this recommendation should remain on hold.

ICRC

Recommendations from the previous Annual Review	Progress
FCDO should follow ICRC’s implementation of its Disability Framework to understand the implications for the availability of disaggregated data.	On-going: ICRC does not share disaggregated data on PWD. Through their adoption of the Disability and Inclusion Policy, and the Age, Sex and Disability Disaggregation (SADD) Framework, ICRC are working towards disaggregation of disability data. The frameworks aim to ensure that disability data is systematically collected and analysed.
FCDO should follow evaluations of ICRC activities and foster exchanges with other SHAPP partners that deliver similar activities (e.g. food production).	Partial progress: ICRC conducted a decentralised evaluation on the Mali WatHab Water Systems between July 2024 and January 2025.[12] The exercise has supported continuous learning and improvement for the WatHab unit, however it has not yet been made available to FCDO or on the ICRC website. FCDO should continue asking ICRC to share what it can of M&E results.
[12] The ICRC’s Water and Habitat unit works to ensure access to essential services such as water, sanitation, and electricity, and strives to create or maintain a sustainable living environment. In Mali 2024, ICRC activities focused on broadening access to clean water, through improvements to infrastructure and technical support to maintain systems.

Lessons learned this year and recommendations for the year ahead

In addition to those carried over above, this year’s annual review has the following recommendations for the year ahead:

SRF
- The SRF FMU should proactively continue to court other donors as well as prepare the administrative and procedural groundwork to allow take off as a pooled fund. Direct funding from DANIDA is a promising start, but expansion needs to go further. This includes governance reforms to allow easier incorporation of other donors' compliance, due diligence and overhead spending requirements. It could also more explicitly align itself in its communications and pitch to donors with the push for locally accessible pooled funds by the Emergency Relief Coordinator, as a more effective, locally led and accountable alternative to Country Based Pooled Funds, and the UN’s Central Emergency Response Fund (CERF).
- As part of its outreach, SRF should sharpen its profile and evidence base as the leading mechanism for advancing locally led humanitarian response in the Sahel - especially considering declining leadership and access of international agencies. Its locally led nature underpins the SRF’s credibility with governments in the central Sahel, which have become increasingly sceptical of international organisations. Among the SRF’s distinctive strengths are the meaningful involvement of local partners in decision-making - not merely as funding recipients - and its strong and unapologetic commitment to capacity-building. This investment is vital to broaden the local humanitarian community beyond the small group of 4 – 5 well-established local agencies who tend to scoop up all funding available (as highlighted in the SRF mid-term evaluation).
- Efforts to document and disseminate programmatic learning have been neglected while the SRF understandably focuses on establishing itself as a viable fund management mechanism at scale. However, there have been missed opportunities resulting from a disappointing mid-term evaluation and some shortcomings in evaluations of individual partners. Rather than commissioning more evaluations, the SRF FMU would greatly benefit from having more in-house (or easily accessible) technical expertise, especially in the domain of food security and resilience, to better advise and monitor partners. This would improve the quality and impact of projects and could facilitate more learning both within the Fund and externally, including on how best to define and achieve effective livelihoods / food security programming in marginal and hard to access parts of the Sahel.
- Board oversight should be streamlined by the FMU to focus on reviewing strategic decisions rather than being involved in the details of fund allocations. Clearer guidance is required on what matters the Board is consulted on versus simply informed about. FCDO and DRC could also clarify their involvement in board discussions and FMU decisions to help address occasional misunderstandings about their role.
The policy of provision of short-term packages of food assistance when people are newly displaced has raised concerns that this incentivises additional displacement to access more resources than staying put would allow. FLASH /DRC should assess whether this is really the case and adjust their policies accordingly.

ICRC
ICRC is often one of the only effective humanitarian actors present in hard to access locations and has an essential role to play. That said, FCDO should work with ICRC to better understand the nature and effectiveness of its food security and livelihood interventions (especially compared to NGOs/ SRF). Appreciating the sensitivities around protection, FCDO should encourage ICRC to share its learning on the effectiveness and sustainability of its non-protection sectors of intervention, particularly economic security where ICRC’s unique added value and effectiveness compared to other partners can be harder to distinguish. This includes the nature and quality of its partnerships with local organisations, including the authorities as the long-term providers of social protection and the exit strategy over time for ICRC’s work.
WFP / UNHCR
Three out of four WFP partners in its Chad response are INGOs and there is no evidence of sufficient effort in supporting local organisations and investing in capacity-building of their core institutional capacities. Training seems strictly focused on partner compliance and delivery. FCDO should ask WFP and UNHCR to demonstrate specific efforts (potentially through indicators in the logframe of a future business case) to meaningfully deepen localisation in a context where local actors are essential for access, ownership and value for money.
- UNHCR in Chad should provide more details on its cash transfer programming (including VfM) and explain how complementarity with cash transfers by other actors (especially WFP) is managed. The links with social protection should be clarified, to ensure that cash transfer values and targeting are coherently designed, and there is clear agreement on who should receive which amount of cash, and how people transition from one to the other where this is applicable).

Output Title	Humanitarian aid organisations better able to fulfil their own mandates through the provision of essential safety cooperation, information and support services.
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Yes (Down)

Indicator(s)	Milestone(s) for this review	Progress
3.1 % of NGO respondents agree that INSO services are relevant to their needs and improve their understanding of the environment and their security practices.	>85%	Overall: >96% / Burkina Faso: 97% / Mali: 99% / Niger: 96%
3.2 Number of humanitarian air passengers transported	7,780 (cumulative)	8,355 (cumulative) / Of which 2,675 for the period in review.
3.3 Effective setup and operation of SRF	SRF Operational Framework is revised to introduce a tier approach to tailor control and monitoring system to the partner risk level	Completed

Briefly describe the output’s activities and provide supporting narrative for the score.

This output measures the level of support services provided by UNHAS and INSO, as a result of FCDO contributions, to improve the operating environment of humanitarian actors. It also covers the initial work (now complete) of setting up the SRF mechanism. This Output scores an A, as it meets FCDO expectations. All Sub-Output milestones have been achieved satisfactorily.

During the review period, INSO overachieved on logframe milestone targets. For most of the period in review, it provided the full spectrum of its core services to NGOs in an increasingly unstable context across Burkina Faso, Mali, and Niger (through 21 offices/branches). However, INSO’s operations were affected by the termination of its activities by the Government in Niger in November 2024. More recently (outside the review period), authorities in Burkina Faso have temporarily suspended INSO’s activities. In addition, the termination of US funding (which represented between 40% and 50% of INSO financial resources in the Sahel) forced the organisation to undertake a substantial restructuring, closing sub-offices and reducing staffing.
As a result, security training services were halved, and reporting of real-time security incidents reduced. The information vacuum – especially in Niger - has affected humanitarian aid delivery with several NGOs reporting reduced access to insecure areas due to lack of timely detailed security information. Partners also became increasingly conscious about sharing incident reports, fearing repercussions from the government. Smaller and national organisations which fully relied on INSO for security management are likely to be particularly affected in 26-27.

During the review period, and despite challenges, INSO provided services to 341 organisations[13] in Burkina Faso and Mali, including 84 national NGOs (compared to 511 organisations last year including 103 national organisations, across Burkina Faso, Mali and Niger), reaching over 23,607 staff with 1,464 benefitting from training during 2024/25.
[13] 174 NGO partners in Burkina Faso (16% national) and 167 in Mali (33% national).

The quality of INSO’s outputs remained very high, and above the target, ranging from 96% to 99% of respondents agreeing that INSO services are relevant to their needs and improve understanding of the environment and security practices. Gaps identified by partners after the withdrawal from Niger illustrated the criticality of INSO’s services.

INSO is establishing a regional hub in Abidjan to focus on transborder issues and start monitoring security incidents in Benin, Togo, and Cote d’Ivoire.

UNHAS, run by WFP, ensures humanitarian workers and cargo safely reach hard-to-reach locations. It provides an evacuation service for both security and medical emergencies. Over the period in review, based on the average cost per passenger, the UK contributed to the transport of 2,675 humanitarian air passengers in Burkina Faso, Chad, Mali and Niger. UNHAS was affected by global funding cuts but remained operational thanks to reducing fleets and/or flight frequencies and increasing passenger contributions (not without delays). FCDO worked with like-minded donors on UNHAS Steering Committees to continue the application of those cost saving measures. As a result, UNHAS met targets for the year in review.

Over the period in review, UNHAS flights continued to prove critical to reach those most in need, in hardest to reach areas:
- With three Chinook helicopters, UNHAS provided food aid in northern and eastern Burkina Faso, where land access was cut by the conflict. UNHAS deployed 20,112 humanitarian personnel and carried out 18 emergency evacuations.
- UNHAS pivoted its operation from the Lake Chad Basin to eastern Chad to support the response to the Sudanese refugee crisis. In Chad, UNHAS serves 140 partner organisations, transporting over 2,500 humanitarian workers per month (110% increase in demand compared to 2023). Due to funding cuts, UNHAS made changes to its fleet, streamlined routes, and increased passengers’ contributions to achieve 15% costs savings.
- In Mali, the UNHAS fleet was reduced to two aircrafts, ticket fares increased by 50%. UNHAS lost two aircrafts due to JNIM recent attack to the airport in Bamako.
- In Niger, UNHAS operated two aircrafts covering seven destinations. It enabled travels for 14,699 passengers and delivered 32 MT of cargo, serving 181 partners.

Both INSO and UNHAS have continued delivering services based on the humanitarian principles of acceptance and needs-based response. The adjustments implemented have not had a negative impact on the quality of service delivered. However, as the security and political environment continue deteriorating, more substantial changes to the two agencies’ operating models may be required.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting of this output was revised downwards this year so that it better aligns with the overall proportion of the budget attributed to it.

Progress on recommendations from the previous AR

INSO

Recommendations from the previous Annual Review	Progress
INSO should test more challenging indicators to measure effectiveness. Satisfaction surveys have scored extremely high and, while useful, are not capturing how INSO products and services might contribute to a change in clients’ practices.	On-going: quantitative reporting continues to be very perception focused, although strong qualitative validation is captured in comments from partners regarding how INSO and its products have enhanced their understanding and ability to operate safely and provided tailored support for specific incidents. / For FY25/26, the FCDO-INSO agreement will need renewal: INSO are working on more challenging indicators as per AR recommendations.
Given the INSO grant agreement is coming to an end in March 2025, the FCDO will consider its extension using the learning and recommendations from this Annual Review. regarding the partner’s performance and achievements.	Completed: FCDO extended INSO funding until March 2026, based on the 2024 AR assessment.

UNHAS

Recommendations from the previous Annual Review	Progress
Progress has been made by UNHAS to increase its financial sustainability, but more needs to be done. UNHAS / WFP should continue implementing its global air policy of increasing cost recovery, especially in Mali where this has not been done yet. UNHAS should continue to monitor occupancy rates and should assess whether further rationalisation is possible and relevant.	Completed: UNHAS has achieved this, – including implementing cost recovery in Mali (where ticket fares have increased 50% to achieve 25% cost recovery). However, efforts have not always been as comprehensive and timely as they could have been, and efforts should continue (this has been captured in a recommendation below).
WFP should share and enhance its monitoring to account for outcomes and effectiveness. This should include Accountability to Affected Populations (e.g. rates of complaints addressed satisfactorily and in time).	Completed: WFP has made good progress in reporting both on food security outcomes and AAP, as detailed in annual reporting.

Lessons learned this year and recommendations for the year ahead

In addition to the one carried over above, this year’s annual review has the following recommendations for the year ahead:

- FCDO should continue pushing UNHAS to consider further efficiencies, to keep adapting to reduced funding. Previous efforts have not always been as comprehensive and timely as they could have been (for example, swapping Niger’s Embraer with a Dash8 to achieve further savings).
- UNHAS and FCDO should document cost saving approaches as they are poised to generate lessons applicable to other contexts: a combination of reduced hours of flights, increases in passengers’ fares contribution, streamlined flights schedules and fleet have a positive effect on VfM, especially as the global humanitarian funding remains under pressure.
- FCDO should continue providing flexible funding to INSO and UNHAS, supporting services which are essential to the provision of humanitarian aid in the most out of reach areas of the Sahel. FCDO should consider increasing funding while not creating dependency (maintaining a reasonable burden share). FCDO should lobby other donors not to neglect such essential services.
- Where relevant, FCDO could advocate to ease some administrative impediments (even though not only limited to UNHAS/UN), like the visa issues UNHAS faced in Niger (which impact on staff rotations and ultimately flights availability).
- INSO should consider whether it can review its operating model to deliver remote services where it has no country presence. FCDO should support INSO’s relocation if the organisation demonstrate ability to maintain service delivery across the central Sahel, and services remains high quality.

Output Title	Regional harmonised interagency protection monitoring system for the Sahel
Output number:		4	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	Yes (Down)

Indicator(s)	Milestone(s) for this review	Progress
4.1 # of stakeholders citing P21 in their publicly available documents	24	23
4.2 # of training sessions on P21 methodology and tools	40	42
4.3 # of joint reports and dashboards disseminated	110	174

Briefly describe the output’s activities and provide supporting narrative for the score.

This output measures the performance of Project 21 (led by UNHCR, in partnership with DRC) in establishing and delivering a regional harmonised inter-agency protection monitoring system for the Sahel, as a result of FCDO contributions. This Output scored a B based on careful review. In terms of meeting milestone targets the project would have achieved an A, but as for the previous Annual Review, the reviewers felt that UNHCR could not demonstrate broader uptake of their methodology and products.

P21 began in December 2021 as a regional effort to harmonise protection analysis, including evidence of incidents, protection needs, and patterns of displacements. The initiative is coordinated by UNHCR and DRC from Dakar, across offices in Burkina Faso, Lake Chad Basin, Mali, and Niger. Complementing data collection and dissemination, UNHCR has delivered training to staff and partners, standardised data collection forms, and made protection monitoring more efficient overall. From 2023, UNHCR focused on localisation and increasingly relied on civil society to collect data. The objective was to improve data’s acceptance by host government. As part of that effort, UNHCR established protection-based committees including 50% displaced and 50% hosts community members and strived to achieve gender balance by working in safe spaces in camps and other sensitive locations. Stakeholders include local NGOs / CSOs but also National Human Rights Commission in Burkina Faso. Local State Authorities are involved to enhance transparency, and acceptance.

P21 collects and processes protection data across time and locations, complementing and streamlining the over 18 protection monitoring systems operational in the Sahel before it started. It enables comparison of data in a region affected by regular movements of vulnerable people across countries, providing regional-level data and analysis. Protection clusters across the Sahel have been equipped with systems for advocacy and, to an extent, response albeit indirectly.

The approach has been subject to criticism by NGOs and some donors because the mechanism focuses on perception rather than incident monitoring, lacks a participative approach or equal data sharing agreements. However, views diverged: a respondent consulted by the AR team suggested that P21 allows consultation and enables beneficiaries’ voices to be heard and captured in official reports, thus strengthening accountability. The mid-term review carried out on P21 suggested that quantitative and qualitative approaches are indeed complementary allowing anticipation and prevention. Ethics was flagged as another source of concern as P21 does not link directly incident identification to humanitarian response. Some thought that funds would be better spent on delivery, rather than complex analytics which UNHCR should fund with own funds.

UNHCR and partners’ efforts have been met with resistance by a few humanitarian actors, and uptake has not been as high as expected. Access to the central database, hosted by UNHCR, has also been flagged as a major issue by NGOs contributing data. Finally, the quality of P21 analysis and products is still below expectations, despite efforts. The issues around the advocacy strategy, source and use of products are not yet fully resolved so at the impact level, the project fails to deliver as expected.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As with Output 3, the weighting of this output was revised downwards this year so that it better aligns with the overall proportion of the budget attributed to it.

Progress on recommendations from the previous AR

Recommendations from the previous Annual Review	Progress
UNHCR should reflect the results of the Mid-Term Review (MTR) in its plans for the coming years, in particular a focus on data interpretation and quality, and advocacy going beyond the traditional humanitarian sphere. Caution should be exercised in not over-extending the tool geographically, methodologically or thematically before it delivers at a sufficient and consistent quality.	Partial: The FCDO team has worked very closely with UNHCR, DRC and key partners (including ECHO) to help P21 refine its approach, based on the MTR.
Given the UNHCR/P21 grant agreement is coming to an end in March 2025, the FCDO will consider its extension using the learning and recommendations from this Annual Review regarding the partner’s performance and achievements. FCDO should also take into account its assessment of the value added of P21 and its performance under the current grant.	Closed: FCDO is planning to extend P21 funding for one final year, with reduced funding, to accompany P21 in implementing MTR recommendations and as part of a responsible exit.
When considering potential future funding to P21, FCDO should factor its core comparative advantage towards P21 (i.e. the ability to add value at regional level). The UK should focus on addressing the main areas of improvement for P21 and where it has greatest transformational power (data interpretation and quality, and advocacy).	Closed (see above): FCDO has been following up with UNHCR and DRC on their work to improve P21 in line with MTR recommendations. FCDO has made sure to bring in other key actors (like key donors as ECHO) in the reflection, for P21 to directly address concerns and weaknesses.
FCDO and UNHCR should continue reviewing logframe indicators and milestones to a) increase the ambition on the uptake of products, b) capture the quality of analysis and c) measure the performance and uptake of advocacy.	Ongoing: Milestones for P21 were increased to reflect achievements from 2024. Logframe indicators will need to be updated with the next FY25/26 proposal.
UNHCR should ensure that benefits of multi-year funding are passed on to downstream partners.	Not applicable: UNHCR no longer receives multi-year funding from FCDO, however if this situation changes then the expectation would be for this recommendation to roll over into the next business case.

Recommendations for the year ahead:

In addition to those carried over above, this year’s annual review has the following recommendations for the year ahead:
- UNHCR should ensure that data collected is accessible on shared drives to all contributors.
- FCDO should consider reducing funding to P21 given pressure on funding for humanitarian action, and undertake a responsible exit from P21 while helping UNHCR / DRC apply the recommendations from this annual review over the coming year. The UNHCR should cover standardisation of protection monitoring tools, training, and data analysis with its own funds (to which the UK already contributes).
- UNHCR should review its Logframe indicators to better capture uptake of the methodology and products.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

ICRC: ICRC provides limited information on VfM. In line with the central agreement with the FCDO, ICRC do not report costs of inputs, making it challenging to assess cost drivers. The main cost drivers are likely to be procurement of inputs (food, seeds, tools, and vaccines, etc.) and services (cash transfers), staffing, transportation and security management.
- Economy: In 2024, ICRC reached an average cost per beneficiary of £33.60 across the four countries covered with FCDO funding[14]. This compares to £25.28 in 2023, £26.39 in 2022 and £28.27 in 2021. The average cost is higher this year as it includes the number of surgical admissions rather than the higher figure for hospital consultations which was used in previous years (especially in Mali and Niger) and the switch from food consumption to food production interventions (more expensive but with more durable results) in Burkina Faso. Despite this, the cost per beneficiary remains reasonable and given the difference in the way the beneficiaries are counted this year, the cost should not be compared directly to last year. Country variances ranged from £20.15 per beneficiary in Niger to £66.61 in Burkina Faso. These cost variations are influenced by differing security risks, procurement of goods nationally or internationally, and the ‘blend’ of activities in each country.
  [14] Based on 2024 Country Appeal final spend and results.
- Equity: 36% of beneficiaries were women, 33% were children and 31% were men. ICRC do not provide disability disaggregated data.

INSO:
- Economy: INSO provides economy of scale to partners through the services it provides that would cost a lot more for each NGO to procure individually. In 2024/25, the average cost per month for an NGO was £727, which is down from £988 last year. These costs were calculated prior to the closure of the Niger programme.
- Efficiency: In 2024/25, INSO served 341 partners – with 167 in Mali, 174 in Burkina Faso. This does not include the 114 in Niger, which if included shows that INSO served a total of 455 partners. This compared favourably with 511 and 495 in earlier years. However, the sudden closure of the Niger office in December 2024 and associated costs, and the cease of services to Niger NGOs, reduced the efficiency of the project in its final few months.
- Effectiveness: Level of satisfaction with INSO services remained high as assessed through INSO partner surveys. Partners continue to value INSO's services and the positive impact those have on security practices. Client satisfaction ranged from 97 – 100%.
- Equity: The number of national NGOs served has increased; rising to 23.7% of the total across the Sahel, from 20% in previous years. Female participation in training courses averaged around 26%, below the 38% achieved last year, but comparable to the 24% achieved in 2022/23.

SRF: After the second full year of implementation, some VfM data is available for the SRF:
- Economy: DRC’s overhead rate on pass-through funding up to March 2025 was 1.25%, which was within the Business Case target of 2% and represents better VfM than similar funding mechanisms in the region. In addition, at the end of March 2025, the cost of the FMU equated to 10% of the total budget spent, this is an increase on the 5.87% last year. Given the reporting period saw the preparation (including calls for proposals) to increase the number of consortia being managed, this increase was expected and should be reviewed again at the next AR once the new consortia are being managed.
- Efficiency: The SRF also aims to demonstrate efficiency by calculating the cost to transfer ratio of cash transfer activities in every project and location. The average ratio was calculated at 0.97 (range of 0.36 to 1.90), which means that for every £1 transferred to beneficiary households, on average it cost £0.97 to deliver, or a total cost of £1.97. This is an improvement on efficiency compared to FY23/24, when the average cost to transfer ratio was 1.23. Of note, this is at a similar level to other cash programmes in the Sahel where the ratio ranged from 0.26 – 2.03. It was also seen that lower cost to transfer ratios were found where larger amounts of cash were distributed, demonstrating economies of scale. The FCDO and FMU agreed at the last AR that understanding the cost per beneficiary ratio would be investigated further to ensure the metrics could be adequately used to assess efficiency across SRF-funded cash transfer activities and inform course correction where required. This was not done and will be followed up over the course of the next year.
- Effectiveness: Access issues influence the effectiveness of the programme, however despite these challenges, the SRF’s annual report and monitoring reports demonstrated more effective delivery at scale than in 2024. Interventions that transferred larger amounts of cash per household achieved better results. Feedback from communities showed that 90% (compared to 87% in FY23/24) of SHAPP recipients interviewed reported that aid is more accessible, timely and suitable than before.
- Equity: Equity is helped through the centrality of protection in programming, with specific attention given to the most vulnerable individuals. Priority is also given to hard-to-reach areas, where severe vulnerabilities exist, and which receive less or no humanitarian assistance. As last year, the SRF reached 55% female beneficiaries[15]. 0.77% of the total beneficiaries reached were recorded as having a disability and is a slight drop from the 0.85% reached at the last AR. Against a global average of 16% of people living with a disability[16] this is very low. We identified that this is because medical consultations contribute a large part of beneficiary numbers, and disability is not normally recorded in standard forms and data systems used by Ministries of Health facilities. A recommendation to address this is included in the cross-cutting recommendations section above.
  [15] Predominantly in the 0-17 age group which accounts for 70.45% of the total female beneficiaries.
  [16] 2023 Global Survey Report on Persons with Disabilities and Disasters | UNDRR

P21: P21 has developed a VfM framework which provides the following results:
- Economy is measured by the percentage of P21 meetings organised within existing coordination mechanisms to reduce logistical, administrative and governance costs. Compared to last year, this remained at 84% for regional meetings (it was 73% in 2023)[17], and 85% of country level meetings[18].
  [17] The meetings comprised 4 Inter-sector, 8 Regional Protection Working Group, 6 Advocacy, 1 Inter Agency Standing Committee, and 4 distinct analysis group meetings.
  [18] Most meetings were in conjunction with the cluster and protection monitoring working groups.
- One measure of Efficiency is staff retention as this preserves institutional knowledge and reduces P21’s training burden, which in turn helps to reduce costs. This year 94% of staff specifically recruited for P21 were retained, although this does not consider changes for posts covered in the interim. This metric shows stability since the last AR (when the percentage was 93.75%) and reflects the slight turnover of staff that is expected in any project in the long term.
- Effectiveness is measured by the number of visits and downloads of data and analytical products on the P21 online dashboard. Over the past two years, these have remained relatively stable with, on average, 400 page visits recorded per month.
- Equity is measured through the percentage of P21 questions that target gender and child protection issues. This has increased by a large amount with 60% of questions targeting gender issues[19] (16% last year) and 25% of questions targeting child protection issues[20].
  [19] 26 out of 163 questions across 2 questionnaires.
  [20] 40 out of 163 questions across 2 questionnaires.

UNHCR Chad:
- Economy: In their report, UNHCR state that procurement processes prioritise cost-conscious sourcing of goods and services without compromising quality. While UNHCR incorporated some cost-efficiency measures, such as piloting alternative shelter designs, it failed to systematically incorporate cost-efficiency in its decision-making and programme design, leaving key decisions insufficiently supported by evidence or market analysis. Local procurement and engagement of community labour for shelter construction have reduced costs and supported host community economies. For this annual review, the project cost an average of £33 per beneficiary spread across all beneficiaries that UNHCR counted, including protection, WASH, health and food / cash programming. Overall, this is in line with other organisations, however as this is the first year of implementation with FCDO funding, there is little by way of comparison.
- Efficiency: UNHCR aims to leverage existing delivery infrastructure and partnerships to minimise duplication and maximise reach. The use of cash-based interventions has improved delivery speed and reduced logistical overheads, although this will be further enhanced during FY25/26. To be able to understand more UNHCR should provide data on how cash-based interventions improve delivery speed and reduce logistical overheads.
- Effectiveness: Post-distribution monitoring and community feedback mechanisms show high levels of access for people to safe feedback and response mechanisms, with 90% of refugees and asylum seekers having access. This figure, however, drops to 20% for IDPs.
UNHAS:
Economy: The main cost drivers for UNHAS operations are the airplane leasing costs, maintenance, fuel and staffing. The main indicator for VfM is the cost per passenger. Disaggregated data for each country is included in the table below. Economy broadly improved between 2022 and 2023, but average costs per passenger have increased significantly in 2024, especially in Burkina Faso with the use of helicopters. Of note, in Niger, irregular supply and the higher cost of jet fuel also increases the cost. Discussions at UNHAS Steering Committees and bilateral meetings suggest that UNHAS operations in the region compare favourably to other geographies.
Country	Cost per passenger 2022 [GBP]	Cost per passenger 2023 [GBP]	Cost per passenger 2024 [GBP]
Burkina Faso	527	Not funded by FCDO in 2023	1,013
Chad	Not funded by FCDO in 2022	267	359
Mali	442	346	444
Niger	481	393	539

Efficiency: UNHAS has adapted its response in eastern Chad, making greater use of Short Take-off and Landing aircraft to improve operational efficiency. The recent increase in ticket fares (cost recovery in Mali is now at 25% due to the 50% increase in ticket fares) in line with WFP’s global aviation policy, creates a stronger financial incentive to rationalise the use of UNHAS, compared to the pre-existing situation when tickets were more heavily subsidised by humanitarian donors.
WFP Chad:
- Economy: During this reporting period, SHAPP continued to support a single food pipeline for Sudanese refugees in eastern Chad through WFP to allow economies of scale (compared to a food security response fractioned between multiple actors). The average cost per person reached £16 this year (compared to £19.8 last year).
- Efficiency: WFP is securing VfM through several approaches: cash transfers where possible to drive cost efficiencies and enhance effectiveness; pre-procurement and positioning of goods and services to reduce costs and enhance timeliness and quality; purchasing locally to reduce costs and protect local markets; using clean/green power sources to reduce costs and carbon footprint; purchasing goods through the WFP Global Commodity Management Facility for competitive pricing; and, using the UN partner portal platform to swiftly select downstream partners, and adopt a rigorous process for selecting Financial Service Providers, to ensure cost effectiveness.

Assessment of whether the programme continues to represent value for money
Overall, SHAPP and its partners continue to provide VfM. VfM is secured through a multi-sectoral approach targeting the most vulnerable, using the most efficient delivery modalities like cash transfers, and adopting as direct a delivery approach as possible. Multi-year funding also ensures VfM for some partners and should be considered where partners do not have access to multi-year funding currently. Despite the deteriorating operating context over the reporting period, a largely localised approach has enabled the programme to maintain its operations and its VfM. As shown above, partners have broadly maintained economy and efficiency, which is a substantial achievement in the current environment. Some costs have risen and are likely to continue to rise, but the flexibility of the programme has kept these to a minimum. While partners reporting on results and outcomes need to improve in measuring effectiveness and equity, earlier sections have demonstrated that the programme is effectively addressing needs.

Recommendations from AR 2024 - Revision of progress:

AR 2024 Recommendation	Update
To achieve greater cost effectiveness, SRF should secure another donor, which will provide greater flexibility and security for the fund in the long term.	Ongoing: Donor engagement by FCDO, DRC, and board members has intensified, with efforts at country, regional, Director and Ministerial levels. A small contribution has been secured from Denmark, with other donors expressing interest but not having pledged yet. FCDO should develop a donor engagement plan to drive more systematic and coherent influencing efforts at all relevant levels. / SRF also still needs to finalize preparations for a potential transition to operating as a multi-donor pooled fund. This requires DRC to design a new version of its Operations Manual capturing all new administrative and financial processes to receive funding from and report to multiple donors.
As specified in Section C.3, INSO should test more challenging indicators to measure effectiveness. Satisfaction surveys have scored extremely high and, while useful, are not capturing how INSO products and services might contribute to changes in clients’ practices.	Partial: at metric level reporting continues to be very perception focused – although strong qualitative validation is captured in the written comments from partners regarding how INSO and its products have enhanced their understanding and ability to operate safely and provided tailored support for specific incidents.
As highlighted in other sections, WFP should share and enhance its monitoring to account for outcomes and effectiveness.	Completed: WFP has made good progress in reporting both on food security outcomes and AAP, as detailed in annual reporting.
As stated in Section C.3., UNHAS/ WFP should continue implementing its global air policy of increasing cost recovery, especially in Mali where this has not been done yet. UNHAS should continue monitoring occupancy rates and assessing whether further rationalisation is possible and relevant.	Partial Progress: UNHAS took significant cost savings measures but continued to spend more than its income, rapidly consuming carry-over funds from 2024. UNHAS should adopt more cost reduction measures to reach financial sustainability.
FCDO and Partners should document the VfM of cash transfers compared to in-kind and vouchers in the region, where such comparison is possible.	Partial progress: ICRC and UNHCR do not report on this, while WFP does. The SRF documents the VfM of cash transfers through the cost to transfer ratio, however there is no comparison of cash compared to vouchers.

Recommendations for the year ahead:

In addition to those rolled over from above, the following recommendations are drawn from this year’s annual review:
- Multi-year funding ensures VfM for a few SHAPP partners. FCDO should consider multi-year funding where the Spending Review allows, for partners who do not currently have access to multi-year funding.
- INSO’s VfM metrics should be revisited. FCDO should push for the revision of indicators when INSO’s agreement is renewed.
- The SRF’s FMU should investigate the cost per beneficiary ratio for cash transfers to assess efficiency across activities and inform course correction where required.
- UNHCR should provide data on how cash-based interventions improve delivery speed and reduce logistical overheads.

E: RISK

Overview of risk management

The overall risk rating for the programme remains Major, in line with the risk appetite of the Sahel, Sudan and South Sudan Department (4SD) in the FCDO. The overall security situation in the Sahel has deteriorated, and several risks were escalated during the reporting period. The SHAPP risk register was updated quarterly, alongside the risk register for the 4SD portfolio, informed by updates from partners and conflict analyses after mitigation SHAPP carries two severe and five major risks, of which two are outside risk appetite.

After mitigation, SHAPP carries seven severe or major risks, including:

1. Crime, violence and insecurity in the Sahel also details the risk of abduction of staff, making it a safeguarding risk. In 2024-25, VEOs’ areas of operation have expanded and state security forces, other armed actors, as well as Africa Corps have intensified operations. This threatens humanitarian aid delivery. Project partners have mitigated some of these risks through enhanced security protocols, suspension of activities, and other measures (including localised delivery). INSO, which FCDO is supporting, had to cease operations in Niger during the review period, inevitably heightening security risk for delivery partners. This risk remains severe after mitigation and is outside the departmental risk appetite. This was escalated and approved by the Head of Department.
2. Acceptance of principled humanitarian response and actors (strategy and context) is increasingly challenged by lack of trust towards NGOs / UN, raising administrative requirements and attempts to minimise the impact of violent conflict by host nation governments. The expulsion of INSO from Niger, the requirement to use armed escorts in several Sahelian countries (Burkina Faso, Chad, Niger) has severely affected movements. The risk that international organisations may no longer be allowed to work in country has materialised in some cases. FCDO has supported dialogue between host governments and partners where possible and remains alert to the context to support aid delivery where useful. This risk remains severe after mitigation and is within appetite which is eager.
3. Supply of humanitarian inputs (strategy and context). The humanitarian supply pipeline has an impact on the delivery of supplies and treatment to beneficiaries due to, for example, insufficient funds, or increasing costs. This risk has increased following the substantial cuts to development and humanitarian aid in the Sahel. Humanitarian response plans are severely underfunded as a result. Costs have also increased due to lack of road access to certain areas under VEO blockades (for instance in Burkina Faso), where aid can only be delivered via air. While some NGOs (especially national organisations) have been able to mitigate this by contracting local transport companies and pre-positioning food/non-food items, the risk of higher operational costs and reduced access will require additional mitigation strategies. This risk is major as mitigation measures impact is reduced, it is therefore within the departmental risk appetite.
4. Programme receiving negative media attention (Reputational risk). During the review period, the residual risk rating for this risk was minor, however at the time of writing, the residual risk rating for this risk has been increased to moderate. The department carries a minimal risk appetite for this risk and therefore the risk is now outside of appetite. There is an increasing trend in events and media coverage that may undermine the reputation of the programme and FCDO. While these emerge from misinformation or fake news, the impact these may have on delivery is not insignificant. As a result, the reputational risk was updated in August 2025, which although outside the period in review, resulted in the risk falling outside of risk appetite, requiring escalation.

Over the period in review, one risk (FCDO staff capacity) was closed because the programme has remained adequately staffed, with an extra resource in place (Humanitarian expert) as per the latest Business Case Addendum.

The Due Diligence Assessments (DDA) for ICRC and UNHCR were updated during the period in review. Both organisations continued to meet the due diligence standards across all assessment pillars. The DDA for SRF (DRC) is due by September 2026.

Recommendations from AR 2024 - Revision of progress:

AR 2024 Recommendations	Update
FCDO should continue assessing partners risk mitigation and management approaches, and checking partners contingency plans in case access is further constrained.	Completed for year in review and included in new recommendations below. The team has been tracking partners risk registers through regular catch ups and has updated its risk register as a result.
FCDO should continue to work with partners to find the most appropriate responses to requirements that might compromise humanitarian principles. This includes leveraging humanitarian diplomacy and continuously clarifying compliance requirements.	Completed for year in review and included in new recommendations below. Posts have been meeting NGOs and other partners to mitigate the impact of certain host governments’ policies, including impositions of armed escorts or additional taxations. FCDO has engaged at country, regional and global level to mitigate this risk (including through the UK Sahel Envoy and Ambassadors). FCDO has an engagement strategy at country and regional level.

Recommendations for the year ahead:

The two main recommendations from FY23/24 remain actual and the team is encouraged to continue supporting partners with risk assessments and mitigations, escalating to Head of Department as necessary:

- FCDO should continue assessing partners risk mitigation and management approaches, and checking partners contingency plans in case access is further constrained.
- FCDO should continue to work with partners to find the most appropriate responses to requirements that might compromise humanitarian principles. This includes leveraging humanitarian diplomacy and continuously clarifying compliance requirements.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery: SHAPP partners are well established and delivering at pace. To meet increased needs in eastern Chad due to the conflict in Sudan, SHAPP added a further UNHCR component from December 2024. The SRF has coped well with the increased demand and has continued programming through the same three consortia as last year, as well as preparing for and issuing calls for proposals for INGOs across the Sahel and in eastern Chad and calls for NNGOs for Burkina Faso and Chad.

Commercial and Finances: The FCDO has signed agreements with each of the programme partners. Where possible, those are multi-year to provide visibility and flexibility to partners. During the period in review (financial year 2024/2025), SHAPP provided £86.257 million to 6 partners (see table below). From its start and up until 31 March 2025, the programme has spent £130.7 million. This equates to 56% of the total budget over 48% of the programme lifespan. When compared to last year, where the statistics showed 33% of the total budget having been spent over 40% of the programme lifespan, this shows a marked increase in spending. The programme is therefore ahead of schedule financially, which is due to increased needs in eastern Chad.

Component	Partner	FY 24/25 (£)	Funding Agreement
300943-101	ICRC	23,800,000	Annual Memorandum of Understanding (MoU)
300943-102	INSO	1,200,000	Accountable Grant Agreement (AGA) / (Apr 2022 – Mar 2025)
300943-103	UNHAS (WFP)	1,600,000	Annual WFP Contribution Arrangement (CA)
300943-104	P21 (UNHCR)	1,501,738	MoU (Dec 2021 – Mar 2025)
300943-105	SRF (DRC)	21,862,984	AGA (Jun 2022 – Mar 2028)
300943-107	SBP	292,506	AGA held Centrally
300943-401	WFP (Chad)	28,000,000	Annual CA
300943-403	UNHCR (Chad)	8,000,000	MoU (Dec 2024 – Mar 2025)
	Total	£86,257,228

Partner reporting and performance:
- ICRC: In FY24/25, the FCDO funded the ICRC’s country appeals for Burkina Faso, Mali, Niger, and Chad through an MoU. ICRC ceased operations in Niger in February 2025 based on authorities’ decision. As per the central agreement, ICRC does not produce tailored reports for donors but instead provides mid-year and annual country reports. Additionally, the ICRC provides a Field Financial Review, which covers all their operations globally. ICRC aims to arrange regular financial audits, however the audit for Chad was last completed in 2018. This is because audits of larger delegations were prioritised. ICRC have stated that they will prioritise an audit of Chad in 2026. Burkina Faso is no longer included in the 2025 schedule due to resource constraints and has been postponed to 2026. The last Sahel audit was Mali in 2023.
- INSO: During FY24/25, the FCDO funded INSO in Mali, Niger, and Burkina Faso through a multi-year Accountable Grant, which started in 2022 and ended in March 2025. In November 2024, INSO ceased activities in Niger – following expulsion by authorities - and closed their offices and operations during the remainder of the reporting period. INSO reports twice a year to FCDO. Both reports were received on time and covered results and expenditure in detail. Throughout, INSO have been good at communicating changes and consulting FCDO, despite a challenging situation.
- WFP / UNHAS: The FCDO provided £1.6m to support UNHAS services in Burkina Faso, Chad, Mali and Niger through an annual contribution arrangement for the period December 2024 – March 2025. A Progress and Financial Report was provided as planned at the conclusion of the funding.
- WFP (Chad): In FY24/25 a total contribution of £28m was provided to WFP to support Sudanese refugees in eastern Chad in two MoU contributions of £4m (Aug-Dec 2024) and £24m (November 2024-November 2025). Progress reports were received for both as planned.
- UNHCR / P21: P21 is funded through a multi-year MoU that ended in March 2025. A further MoU is being considered based off a proposal from P21 that has considered the feedback from last year’s AR and the external mid-term evaluation. In FY24/25, FCDO contributed £8m to UNHCR to support Sudanese refugees in eastern Chad, through an MoU arrangement for the period December 2024 - March 2025. Reporting for the Chad response was delayed and not up to the standard expected: we are working with UNHCR to ensure the report is at the expected standard.
- SRF (DRC): The FCDO funds the SRF through an Accountable Grant with DRC, which act as a fund manager. The SRF have shown their flexibility both in terms of accommodating further funding and in increasing the number of grantees that they manage. Overall, the reporting from partners into the SRF has improved this year and the reporting from SRF to the FCDO has been satisfactory.
FCDO owned assets:
- Under the terms of contributions to WFP (including UNHAS), UNHCR and ICRC, assets generated through donor funds become agency-owned and are subject to their own specific asset control measures.
- As FCDO is co-funding INSO, it retains a proportion of ownership of assets. Ownership transfer or disposal is agreed with INSO at project closure. Due to office closures in Niger and Mali (closure of sub-offices due to funding cuts) in FY24/25, INSO consulted with FCDO and other partners on asset disposal through sale or donation to local NGOs. This was completed satisfactorily and in compliance with FCDO guidelines.
- The SRF follows the standard FCDO Accountable Grant Agreement for assets[21]. The FCDO retains ultimate ownership of assets until ownership transfer or disposal is approved after DRC submits a disposal plan. None of the programmes under SRF ended during this reporting period and so this has not taken place this year. Three SRF programmes will finish at the end of 2025 and so we will comment on the process in the next Annual Review. INSO and the SRF keep inventories of assets, which the FCDO carries out spot checks on and reviews annually.
  [21] In this instance, assets are defined as items with a useful life of more than 1 year and a purchase value greater than £500 or where they are less than £500 but are considered attractive (e.g. mobile phones and food).

Recommendations from AR 2024 - Revision of progress:

AR 2024 Recommendations	Update
As discussed in Output 4; as both INSO and UNHCR / P21 grant agreements are coming to an end in March 2025, the FCDO will have to consider their extension using the learning and recommendations from this Annual Review regarding each partners’ performance and achievements.	Completed for year in review for INSO and currently ongoing for P21. Depending on the outcome of the current spending review, SHAPP should consider a multi-year funding agreement with INSO and confirm if it will fund P21 moving forwards.
SHAPP is a complex programme with multiple partners. The FCDO should ensure it keeps the programme team well-resourced and protects the programme funded position.	Completed for year in review. SHAPP has secured 3 x Humanitarian Advisers for the programme and has sufficient programme management provision.

Recommendations for the year ahead:
- As the programme is ahead of schedule financially, and as the increase in need across the Sahel was not predictable when the Business Case for the programme was originally written, it is recommended that SHAPP allows for headroom to accommodate this increase in need until the programme closes.
- As the last ICRC financial audit of Chad was completed in 2018, the SHAPP team are to ensure, where possible, that an audit of the Chad delegation is carried out as soon as possible.
- Given the large amount of funding that FCDO provided to UNHCR for the response in Chad, the FCDO team should ensure UNHCR report on time and to acceptable standard.
- Depending on future allocated funding, SHAPP should consider a multi-year agreement with INSO and confirm if it will fund P21 moving forwards.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation: A range of measures gives FCDO solid oversight of the programme performance in a complex operational context as follows:

FCDO monitoring
- FCDO SHAPP team in person monitoring: The SHAPP team is based in both the UK and Dakar, Senegal (Regional hub). Over the period in review, FCDO conducted six monitoring visits across the region, including one to Burkina Faso, one to Chad, three to Mali and one to Niger to enhance contextual understanding and to assess delivery. In Chad the visit reached programme locations and included engagement with affected people. In other countries, visits were limited to capitals following FCDO security protocols. Following each visit, the FCDO discussed any concerns, internally and with partners, to find strategies to address them.
- FCDO Development Counsellors: Based in country, Development Counsellors contribute to programme monitoring throughout the year. For example, they attend the UNHAS quarterly Steering Group meetings, where performance and access issues are discussed, along with strategic decisions. They also engage with partners and humanitarian coordination groups in country (donors, Humanitarian Country Teams). Through these, they identify and flag challenges in delivery and access. They support monitoring by the FCDO SHAPP team, both remotely and during visits.
- Regular engagement with partners: As a minimum, the FCDO programme team holds quarterly or bi-annual, and ad-hoc meetings with each partner to; assess their performance against agreed milestones; ensure continued Value for Money; and discuss challenges and risks. The FCDO meets with some partners more regularly, including fortnightly with the SRF and monthly with P21. This is supported by the review of regular partner reporting (see section F). Meetings happen either in person for those in Dakar, or online for partners based in Sahel countries or in headquarters elsewhere.
- Annual Reviews: This year’s Annual Review was conducted by two experienced FCDO advisors with humanitarian and conflict expertise, drawing on direct consultations with all the principal SHAPP partners and information compiled from reports. This included information from the externally conducted mid-term review of the SRF and of P21. Additionally, it drew on information from FCDO field visits as described above, and from FCDO teams in each of the countries where SHAPP operates. This AR covers the past financial year’s activities (April 2024 – March 2025).

Partner monitoring is central to FCDO oversight given the limitations for FCDO staff to access programme locations. This includes:
- Routine partner monitoring of their own activities: Challenges on travel continue to constrain access to programme sites, including the requirement to use armed escorts in Niger and Burkina Faso, and floods across the region, particularly in Niger between May and September and Chad in August and October 2024. Partners have adapted their approaches to maintain access operational areas, including monitoring through local staff at community level and flights to hard-to-reach areas.
- External monitoring: Given the separation between the FMU and organisations delivering SRF activities, the FMU provides an external assessment of performance and risks affecting delivery. It conducted two field visits (one in Burkina Faso and one in Chad) between April 2024 and March 2025 to assess partner performance and monitor risks. The FMU aims to visit 60% of project locations during the third year of SRF implementation.
- Third Party Monitoring: SRF and WFP are setting up third party monitoring for their activities. Results should be available for the next Annual Review.
Recipient and user feedback: WFP held several consultations with communities to better understand their perception regarding the assistance, preferred modalities, PSEA risks linked to humanitarian assistance, and protection. This informed decision-making and resulted in strengthening risk mitigation measures, adjusting the assistance ration to better meet dietary needs and preferences. WFP is also being held to account through multiple feedback channels, including a hotline, helpdesks, suggestion boxes, and informal face-to-face interactions. SRF partners implement their own accountability mechanisms, which typically include phone hotlines, complaint management committees, designated focal points, direct engagement with project staff, and beneficiary feedback surveys. As part of its AAP strategy in Chad, UNHCR established feedback and response mechanisms—including suggestion boxes, community meetings, and digital platforms to ensure that refugee voices informed programme planning and implementation. P21 and INSO both use perception survey tools to secure feedback from users on the quality, utility and uptake of their data, analysis and training.

External reviews and evaluations
- The ICRC is planning an evaluation of its Food Production activities in Chad, Niger (and Cameroon) with the French Development Agency (AFD). This will cover FCDO funded activities.
- The ICRC conducted a decentralised evaluation on the Mali WatHab Water Systems between July 2024 and January 2025. It assessed the operational status of WatHab department structures, with a focus on sustainability and strengthening monitoring systems. The exercise supported learning and improvement for the WatHab unit through enhanced reporting and both qualitative and quantitative monitoring. The report will be published on the ICRC website but was not available as of September 2025.
- Within SRF, the DEWRAL and RALLIER consortia underwent successful mid-term evaluations. There was also a broader external evaluation of the SRF as a mechanism which concluded in late 2024. Although this included some useful recommendations, disappointingly it was unable to offer the in-depth analysis and forward-looking guidance that had been hoped for. These evaluations have supported lessons from projects to share between SRF partners, and for lessons from establishing and operating a new NGO-led fund to be documented and disseminated. During the reporting period, significant strides were made in refining the governance framework of the SRF. Three key documents were developed or revised to guide the SRF’s operations during the scale-up phase: the Charter, the Operations Manual, and Vision 2030. These documents will serve as the foundation for SRF’s activities and its relationship with partners, ensuring clarity and alignment as the Fund evolves and expands.
- An external Mid Term Review was carried out for P21 during the reporting period. This found that, while the project had notable success in developing a digital infrastructure and good network, it still has some way to go towards establishing itself as a system for treating, analysing and disseminating protection data. Investment in data processing and data analysis would therefore enable P21 to build long-term technical understanding.

Overall, as noted earlier in this review, SHAPP does not have an overarching M&E framework to compare the results of its different components. This would require a joint governance which was not part of the design of SHAPP. This is something that FCDO intends to incorporate in the design of any future Business Case.

 Progress on recommendations from the previous Annual Review

AR 2024 Recommendation	Update
WFP should provide results from its monitoring.	Complete: WFP has made good progress in reporting both on food security outcomes and AAP, as detailed in annual reporting.
Now that all partners are established, the FCDO should consider developing a light-touch M&E framework for SHAPP: a) to capture how different monitoring, evaluation and learning activities contribute to cross-partner, regional and global learning; and b) to prioritise the policy and practice agendas it intends to influence. A pre-requisite will be to get support from an M&E Advisor from FCDO Headquarters.	Completed: This was carefully considered with an M&E advisor. To be fully effective the M&E framework would require joint governance, which was not established in the design of SHAPP. An overarching M&E framework will therefore be included within the design of the SHAPP successor Business Case. In the meantime, a stocktake on the learning to date amongst SHAPP partners will be carried out.
SRF Partners, SRF FMU and FCDO should share the SRF learning and good practice externally. In addition to routine learning exercises, the SRF Board, SRF FMU and FCDO should consider contracting an externally led case study to capture the SRF’s VfM and successes. This would contribute to global learning and policy thinking on localisation and support external communication and fundraising.	Partially addressed: There has been lots of regional level engagement and coordination by SRF FMU and partners (including a roundtable on humanitarian diplomacy and two regional localisation dialogues), however no set up of a regional learning function per se. Coordination of learning within the SRF and across SHAPP by FMU has been secondary to setting up consortium structures and managing recent calls for proposals and an increasing number of grants. FCDO has shared SRF lessons learnt externally (e.g. Germany-funded Nexus Funding Facility) and internally. This has included informing global policy discussions on the humanitarian reset, which triggered renewed interest in pooled funds. The FMU is currently finalising an in-house VfM analysis capability, which should be allowed to bed in before considering any externally led VfM case study. / This action is to be carried forwards to next year in order to benefit from the contribution of the new partners. SRF should recruit in-house technical expertise to support partners and ensure cross learning.
The SRF Board and SRF FMU should consider strengthening and resourcing the SRF regional learning function, between partners and countries covered, and even beyond (starting with other SHAPP partners). The review heard partners praise the learning benefits from the SRF regional approach. A learning event held by the FMU in Niamey was cited by all SRF members as best practice. SRF members felt that more can be done to make the most of the regional nature of the SRF and exchange good practice.	Ongoing: during the reporting period FMU has participated in several regional events including a roundtable on humanitarian diplomacy and two regional localisation dialogues. FCDO itself has shared SRF lessons learnt externally (e.g. Germany-funded Nexus Funding Facility) and internally, including to inform global policy discussions on the humanitarian reset, which triggered renewed interest in pooled funds. / The FMU is finalising an in house VfM analysis capability, which FCDO believes should be allowed to bed in before considering an externally led VfM case study.
FCDO should follow evaluations of ICRC activities and foster exchanges with other SHAPP partners that deliver similar activities (e.g. food production).	Ongoing: Output 2 above for the recommendation for ICRC to share learning from its food security and livelihoods interventions.

Date of last narrative financial report	ICRC: 30 June 2025 / WFP: 30 June 2025 / UNHCR: 18 Sept 2025 / INSO: 30 April 2025 / SRF: 16 June 2025	Date of last audited annual statement	ICRC: April 2025 / WFP: April 2025 / UNHCR: Sept 2024 / INSO: June 2024 / DRC: June 2025