## Annual Review Report

Title: FISCAL TRANSPARENCY AND ACCOUNTABILITY INITIATIVE (FTAI)
Programme Value: £16,500,000		Review date: April 2024 -August 2025
Programme Code: 300948	AMP start date: 08/08/2022	AMP end date: 30/07/2029

Summary of Programme Performance

Year	2023	2024	2025	2026	2027	2028	2029
Overall Output Score	A	A	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300948/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Fiscal Transparency and Accountability Initiative (FTAI) aims to deepen open, accountable, and inclusive public financial management. It supports governments to supply transparent fiscal data and information, and civil society to demand and use that, alongside audit institutions to strengthen oversight. FTAI strengthens global public goods such as the Open Budget Survey and the Open Contracting Data Standard, and delivers targeted country-level support where FCDO Posts identify reform opportunities. Core implementing partners include the International Budget Partnership, Open Contracting Partnership, and UK National Audit Office. A new project component was launched in March 2025 with a contribution to the World Bank’s Financial Management Umbrella Program. In 2025-26, the programme will include support to the World Bank, UK HM Treasury, and Transparency International Australia. FTAI is part of the FCDO’s Centre of Expertise for Public Finance, which provides flexible, high-quality advice on tax and public financial management.

Summary supporting narrative for the overall score in this review

The programme is rated A+ for achieving two output targets and exceeding the others. In a year marked by global fiscal uncertainty and shifting political landscapes, FTAI has demonstrated resilience, adaptability, and impact. This Annual Review highlights the programme’s strategic evolution, its contribution to global norms and public goods, and its tangible achievements in countries such as Indonesia, Rwanda, Tanzania, and Ukraine. From pioneering digital infrastructure platforms like DREAM (see Output 2 for details) to strengthening audit institutions and civil society engagement, FTAI remains an effective intervention in shaping transparent governance and equitable development outcomes.

Table 1: Output scores and weight
Output	Score	Weight
Effective capacity building partnerships between the UK NAO and SAIs.	A+	20%
Implementation of open contracting strategies and practices in focus countries.	A+	35%
Collaborative actions to promote budget transparency and citizen participation in focus countries.	A	35%
FTAI delivery partners engage globally to deepen and expand commitment to global norms on fiscal transparency and open contracting.	A	10%

Major lessons and recommendations for the year ahead

This review recommends:

Maintain flexibility in funding and support. While FTAI continues to maintain a set of focal countries, the programme should also remain open and responsive to emerging opportunities for reform in other countries of strategic interest to FCDO.

Build in horizon scanning. To enhance strategic responsiveness, the programme team should hardwire horizon scanning thinking to assess and prioritise countries. Implementation should align with FCDO’s approach to development partnerships, and focus on where the UK has comparative advantage, while partnering closely with others (e.g., World Bank, INTOSAI). Implementation should be incremental, leveraging existing processes and relationships, with a focus on results and outcomes.

Understand the ecosystem. To strengthen demand for fiscal transparency and citizen participation, the programme team and implementing partners should deepen understanding of the evolving nature of fiscal ecosystems in focus countries. This includes identifying which constituencies CSOs represent, their interest, and how they interact with political actors. CSOs vary in legitimacy, influence, and political alignment, and their ability to mobilise reform depends on these dynamics. Implementation should focus on feasible approaches that stick and are sustainable, such as stakeholder mapping workshops, rapid analysis commissioned from research analysts or programmes, and integrating ecosystem insights into partner reporting and learning sessions.

Strengthen MEL systems to match programme scale and complexity. The programme team should continue to standardise partner reporting, explore deploying AI for data analysis, and formalise beneficiary feedback mechanisms, as well as strengthening partner efforts to routinize preparation of programme stories of change. These steps will improve efficiency, ensure learning is captured, impact is well communicated, and support adaptive management within a constrained resource environment. This includes illustrating existing synergies between the FTAI logframe and the results framework of the World Bank’s Financial Management Umbrella Programme.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

In November 2024, FTAI’s theory of change, results framework, and logframe were revised and updated in response to recommendations from the Annual Review.

FTAI is grounded in the evidence that fiscal transparency and accountability lead to improved fiscal management, state capability, responsiveness, and development outcomes. Transparency enables citizens to participate more effectively in fiscal policymaking and to hold governments accountable for their performance. The programme is also informed by the theory that the most effective way to enhance fiscal transparency and accountability is through a dual approach: supporting both the supply and the demand for fiscal information. To this end, FTAI provides technical expertise, fosters coalitions, and supports digital reforms to support governments to supply fiscal information; and support civil society, the media, and parliaments in demanding transparency and using fiscal data to hold governments accountable.

Expected Outputs

The programme aims to deliver the following outputs:

- Effective capacity building partnerships between the UK NAO and Supreme Audit Institutions;
- Implementation of open contracting strategies and practices;
- Collaborative initiatives to promote budget transparency and citizen participation;
- Engagement at the global level to strengthen and expand commitment to international norms.

Expected Outcomes

If outputs are achieved and assumptions hold, the programme anticipates the following outcomes:

- Increased fiscal transparency and accountability in at least two focus countries, as evidenced by improved Open Budget Survey (OBS) scores on transparency and participation;
- Greater accountability for efficient and equitable tax and expenditure in at least four focus countries, demonstrated by improved oversight scores and eight case studies of enhanced SAI performance;
- Improved public procurement and reduced corruption risks through the adoption of open contracting policies, measured by better procurement data and new high-level normative commitments.

Impact

The expected impact of FTAI is to enhance the effectiveness and equity of public expenditure. This contributes to more sustainable and inclusive economic growth, and to societies where citizens are empowered to hold governments accountable.

The programme team has undertaken a systematic process, with the implementing partners, to revise the logframe and theory of change, including identifying and monitoring key assumptions. This revised framework reflects FTAI’s strategic evolution and commitment to evidence-based programming. By clearly articulating the pathways from activities to impact, and the assumptions underpinning each stage, the updated theory of change and results framework provide a robust foundation for monitoring progress and adapting interventions. The focus on both national and global engagement ensures that FTAI remains responsive to local context while contributing to broader systemic change in fiscal reforms.

Describe where the programme is on/off track to contribute to the expected outcomes and impact.

Table 2: Summary of the outcome assessment
Outcome Indicator	Baseline	Milestone / 2024/25	Target / 2029/30	Progress
1.1 Number of FTAI countries showing improvements in OBS rating on the budget transparency dimension.	Indonesia 70; Rwanda 50; Tanzania 41	-	2	Data expected in 2026
1.2 Number of FTAI focus countries showing improvements in OBS rating on the public participation dimension.	Indonesia 26; Rwanda 16; Tanzania 13.	-	2	Data expected in 2026
2.1 Number of FTAI focus countries showing improvements in OBS rating on the budget oversight dimension.	Ghana 28; Indonesia 59; Kenya 57; Rwanda 56; Tanzania 43; The Gambia 57.	-	4	Data expected in 2026
2.2 Cumulative number of case studies demonstrating improved SAI performance in the areas of NAO capacity building.	1 Case Study from Kenya in Year 1	2	8	4 new case studies: / SAI Rwanda introduced real-time performance audits, a preventive measure projected to save billions of Rwandan francs in public projects. / SAI Gambia modernised the overall quality approach to audits, with a renewed emphasis on policy and financial audit competencies. / SAI Ghana strengthened compliance with financial audit standards; advanced performance audit practices; and improved relationships with Parliament. / SAI Tanzania enhanced implementation of quality control standards and deepened collaboration with audited entities.
3.1 Cumulative number of meaningful and measurable improvements in public procurement data availability or use in FTAI focus countries.	na – new indicator	2	8	4 new improvements (Rwanda, Kenya, Uganda, and Ukraine)
3.2 Number of new high-level normative statements or guidance that supports open contracting.	2 new high-level normative statements in Year 1	1	5	1 - Blue Dot Network recognised open contracting as ‘superior’ practice, with both data standards (OCDS, OC4IDS) recommended
[note] The FTAI focus countries are Indonesia, Rwanda, Tanzania, and Ukraine. The largest share of programme resources has so far supported projects implemented in these four countries.

Given that the 2025 Open Budget Survey (a key data source) has not yet been published, it is too early to assess progress. The programme has made notable contributions to transparent public procurement, with three documented proof points and four measurable improvements in procurement data quality. FTAI has also influenced global norms through contributions to the OECD’s Blue Dot Network and UN processes. The institutionalisation of the DREAM platform in Ukraine stands out as a major achievement, now embedded in legislation and managing over £16.7 billion in infrastructure projects.
[note] “Proof points” are defined as documented evidence of significant changes in public procurement resulting from implementing the cornerstones of open contracting. Two recent examples are improvements in procurement audits in Indonesia, and improvements in SME inclusion and procurement fairness in Uganda.
[note] The Blue Dot Network, hosted by the OECD, provides an internationally recognised certification for quality infrastructure projects that are environmentally and socially sustainable, resilient, open and transparent, and economically efficient.

The theory of change assumptions underpinning FTAI appear broadly sound, with most holding or showing early signs of progress. Stakeholder engagement, capacity building, and global influence are well evidenced. However, behavioural change and direct benefits remain harder to verify, and attribution is complex due to multiple contributing factors and actors. The programme team should encourage adaptive learning and explore opportunities to improve attribution.

The programme is making meaningful progress, particularly in procurement reform and global influence. Given the early stages of some indicators and persistent contextual risks, the programme team can be cautiously optimistic that the programme is on track to achieve its intended outcomes and impact.

## C. DETAILED OUTPUT SCORING

Output Title	Effective capacity building partnerships between the UK NAO and SAIs
Output number:	1	Output Score:	A+
Impact weighting (%):	20%	Weighting revised since last AR?	Yes, revised down from 30%

Indicators	Milestones	Progress
Cumulative number of effective capacity building partnerships between the UK NAO and other SAIs established and delivered.	5	5 ongoing partnerships with SAI Ghana, Kenya, Rwanda, Tanzania, and The Gambia / 2 new emerging partnerships with SAI Jordan and Ukraine
Cumulative number and quality of capacity building activities delivered by the UK NAO.	10	10 engagements with SAI Ghana, Kenya, Rwanda, Tanzania, and The Gambia / 2 additional engagements with SAI Jordan and Ukraine

Briefly describe the output’s activities and provide supporting narrative for the score.

This output, delivered through the UK National Audit Office, aims to strengthen external scrutiny and audit by fostering peer-to-peer partnerships and delivering high-quality technical assistance.

The partnership indicator assesses the presence of strong peer-to-peer relationships, clear institutional leadership, defined goals, and evidence of committed resources and timeline. These partnerships provide high-level authorisation and a framework for applying international audit standards and building institutional capacity. In 2022, the NAO established partnerships with the SAIs of Ghana, Kenya, Rwanda, Tanzania, and The Gambia. These relationships continued to improve and mature in 2024-25, progressing more rapidly with Ghana, Kenya, and The Gambia, and more gradually with Rwanda and Tanzania. The NAO also initiated new partnerships with SAI Jordan and SAI Ukraine, expanding its global engagement.

The capacity building indicator evaluates the quality of technical assistance provided. In 2024-25, experienced NAO teams delivered ten out of eleven planned in-country training activities, plus follow-up mentoring, totalling two hundred person days - half of which were contributed by senior audit managers. Tangible results included SAI Gambia developing audit report style guides and SAI Kenya launching a newsletter to enhance internal communication. In addition, the NAO responded to unplanned requests by delivering responsive audit training to SAI Ukraine and hosting a study visit from SAI Jordan.

Given that both milestones were exceeded, the Output is rated A+.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two new partnerships were initiated during this period: SAI Ukraine and SAI Jordan.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Lessons Learned

Attribution remains complex: While partner SAIs report improved practices, isolating the impact of NAO’s technical assistance is difficult due to overlapping donor support and contextual factors.

Engagement timing matters: Aligning NAO support with SAI planning cycles improves uptake and relevance, but requires proactive coordination and flexibility.

Change is often incremental: Cultural and leadership dynamics within SAIs influence progress more than technical inputs alone.

Recommendations

Strengthen engagement with FCDO Posts and increase visibility and support - particularly at the Head of Mission and Development Director levels.

Introduce standardised post-engagement feedback tools, in partnership with FCDO Posts, for SAIs to capture perceived value and behavioural shifts. Integrate short feedback forms into wrap-up meetings or follow-up emails.

Prioritise case study development in selected countries to document change pathways and lessons learned, deepening design of templates to capture stories of change. Use existing documentation and partner input to build case studies gradually.

Coordinate with other donors to map overlapping support, improving attribution clarity and reducing duplication. Ask SAIs to share donor activities summaries during engagements; this can be captured informally without requiring new coordination structures.

Output Title	Implementation of open contracting strategies and practices in focus countries.
Output number:	2	Output Score:	A+
Impact weighting (%):	35%	Weighting revised since last AR?	Yes, revised up

Indicators	Milestones	Progress
Number of MVP of contracting data in focus countries.	3	7 new or restored publishers of contracting data from FTAI countries of interest: / 1. Rwanda: Public Procurement Authority (new) / 2. South Africa: National Treasury (new) / 3. Uganda: OC4IDS - CoST Uganda (restored) / 4. Nigeria: Ekiti State BPP (restored) / 5. Nigeria: Osun State (restored) / 6. Kenya: PIPP (new) / 7. Indonesia: CoST Nusa Tenggara Barat initiative
Number of robust mandates for implementation of policy changes involving budget, leadership and timelines, in focus countries.	1	5 mandates from FTAI countries of interest in reporting period: / 1. Tanzania (New procurement regulations issued) / 2. Ukraine (DREAM is now legally and procedurally embedded through the amendments to the Budget Code and PIM reform roadmap) / 3/4. Indonesia (2 sub-national mandates on procurement audits, MoU in Semarang and standard operating procedures in Maros) / 5. South Africa (New procurement law)
A sustainable digital solution for Ukraine’s reconstruction systems designed, built, and widely used.	Minimum Viable Product of the system launched / $bn projects on the system and funded	DREAM, an open-source, transparent and efficient framework for managing reconstruction and other major infrastructure projects, is operational and embedded in legislation. / As at March 2025, DREAM had 11,207 projects worth £16.71bn (of which 7.3% were fully funded and 25.8% partially funded).
[note] Minimum viable product (MVP) is defined as publication of good-quality open procurement data, including Open Contracting Data Standards (OCDS).

Briefly describe the output’s activities and provide supporting narrative for the score.

This output, delivered through the Open Contracting Partnership (OCP), seeks to establish open and accountable procurement as a global norm.

The robust mandates milestone covers high-level political support, clear institutional leadership, specific goals and framing for what partners want to achieve, and some evidence of committed resources and a timeline. Such mandates provide coverage and buy-in for open contracting implementation on the ground and provide a framework for both government and civil society to hold government to account for implementation. OCP took advantage of the window of opportunity for procurement reform in Tanzania to help craft ambitious and progressive procurement regulations. It also supported significant progress with the institutionalisation of DREAM in Ukraine, and two subnational audit reform mandates in Indonesia.

The data publication indicator is a more tangible output, contributing towards the higher-level outcomes (progress and documented evidence of impact) that indicate better procurement spending that delivers for citizens. There were seven cases of new or restored publication of contracting data (OCDS/OC4IDS) in target countries, two of which are attributable to CoST. The restored publication cases are from Nigeria where a World Bank eGP project resulted in a burst of OCDS publishers that was not sustained, due to weak change management and institutional strengthening. The lesson is to focus on both change management to secure long term buy-in to eGP and procurement data reforms and making use of the data to drive systemic performance improvements.

FY2024/25 saw the completion and operationalisation of Ukraine’s Digital Reconstruction Ecosystem for Accountable Management (DREAM), which FTAI has supported from the outset in 2022. Envisaged originally as a system to enable citizens to monitor how international funds for infrastructure reconstruction were being used, it has ended up as perhaps the most advanced Public Investment Management system in the world – embedded in legislation and covering all major projects regardless of funding source. DREAM’s success has been widely recognised, including through international awards.

With DREAM’s success in a conflict, challenging environment and the other two indicators exceeding their milestones, the Output is scored A+.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no substantive changes during the past year. FTAI support to DREAM concluded in March 2025, with UK support transferring to the British Embassy’s Digitalization for Growth, Integrity and Transparency (DIGIT) programme.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

The logical framework was refreshed, as recommended in the previous annual review.

Output Title	Collaborative actions to promote budget transparency and citizen participation in focus countries
Output number:	3	Output Score:	A
Impact weighting (%):	35%	Weighting revised since last AR?	Yes, revised up

Indicators	Milestones	Progress
Cumulative number of collaborative budget engagement actions undertaken in FTAI focus countries of Indonesia, Rwanda, and Tanzania and supported by IBP.	11	65 collaborative budget engagements / Indonesia: 29 actions at national and local level, including to influence national budget guidelines, enhance fiscal transparency and participation in national ministries, and improve access to water and health centres. / Rwanda: 16 engagements with ministries, national audit institution, and development partners focused on improving participation. Includes establishment of a taskforce for open and accountable budget, resulting in government’s commitment to document local public participation mechanisms and consultation processes, and provide feedback to citizens on spending priorities. / Tanzania: 20 engagements to improve transparency during budget implementation, helping civil society to monitor public service delivery. The finance ministry now produces a citizen's budget and local CSOs lead budget engagements at national level.
Evidence of increased fiscal governance capacity of target CSOs, in FTAI focus countries.	Most target CSOs have consistently demonstrated a basic level of technical and strategic capacity and have put these in practice to undertake modest or preliminary engagement or advocacy with government actors and processes.	Most target CSOs in the focus countries have demonstrated a basic level of technical and strategic capacities aligned with the working definition of fiscal governance capacity. / CSOs are (a) developing evidence-based advocacy plans; (b) formulating proposals and policy recommendations; (c) initiating engagement with government actors. / Indonesia: Capacity building activities focused on social audits of WASH services and accessibility audits of primary healthcare centres. / Rwanda: 12 CSOs targeted. Training covered budget transparency and participation; budget cycle intervention points; and OBS methodology and findings. / Tanzania: 15 CSOs targeted. Training focused on budget implementation and Public Expenditure Reviews.
Evidence of increased fiscal governance capacity of target gender-focused CSOs in FTAI focus countries.	Most target gender-based CSOs have consistently demonstrated a basic level of technical and strategic capacity and have put these in practice to undertake modest or preliminary engagement or advocacy with relevant government actors and processes.	Most target gender-focused CSOs (Indonesia: 4; Rwanda: 12; Tanzania: 15) have demonstrated foundational technical and strategic capacity in fiscal governance, with some moving from participation to influence. / Results include (a) improved access to services for women with disabilities in Indonesia; and (b) advocacy for adequate budget allocations to gender-based violence in Rwanda.
[note] Collaborative budget engagement action is the process where multiple local CSOs, coordinated by IBP, work together – exchanging ideas, knowledge, and resources – to promote budget transparency and citizen participation.
[note] Fiscal governance capacity of CSOs is the ability of civic actors to undertake the actions they need to achieve their set goals or objectives. Among target CSOs, it is the individual and collective ability of civic actors to strategically engage fiscal governance actors and spaces to advance their priority issues and reforms including both technical and strategic capacities. Technical capacity is defined by IBP as the ability to undertake research, develop analytical products, and generate proposals. Strategic capacity is defined as the ability to conduct political analysis, communicate and engage effectively, develop strategies, conduct monitoring and evaluation functions.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output, delivered through the International Budget Partnership (IBP), seeks to promote more equitable and accountable PFM systems. The work focuses on three priority areas:
The Open Budget Survey (OBS) is carried out in close collaboration with local civil society partners and features three core components as follows: strengthening civil society’s capacity to advocate for reforms; increasing dialogue between key actors in the fiscal accountability ecosystem (civil society, government, and oversight actors) on fiscal transparency and accountability; and securing progress toward improvements in fiscal transparency, participation, and oversight;
- Intensive Country Work, in three target countries (Indonesia, Tanzania and Rwanda);
- Global Advocacy to promote budget transparency and accountability through engagements with international financial institutions, UN bodies, and civil society.

The OBS remains the gold standard international indicator and benchmark for fiscal transparency. The OBS 2023 findings achieved over 700 media mentions globally in publications, with an approximate total circulation of more than 2.5 billion. The survey is having impact in changing global norms in relation to fiscal transparency, with national level responses including the publication of new Budget documents such as the Executive’s Budget proposal in Ethiopia and the Citizens Budget in Cambodia. Work on the 2025 OBS began during the reporting period, with a kick off meeting attended by forty-four countries.

IBP and partners’ work in Indonesia has achieved a total of twenty-nine collaborative budget engagement actions. This is in the face of increasing political headwinds, with the Government of Indonesia taking a less sympathetic approach to transparency. Milestones were met in both Rwanda and Tanzania where IBP has a more recent presence and delivers via local partners. In Rwanda, the team have a clear plan for using upcoming rounds of the OBS to incentivise reform using relationships built through the Taskforce for Open and Accountable Budget. In Tanzania, IBP and its local partners successfully lobbied the government into reinstating the Public Expenditure Review (PER). Since regular PERs ceased in 2010, the restoration of these important platform for civil society participation in budget implementation was a policy priority for local CSOs. We suggest establishing a separate conversation to discuss recommendations for further work in both countries proposed in IBP’s submission to the Annual Review.
[note] In April 2025, the government held its first PER for many years and local CSOs such as Policy Forum and HakiElimu participated in the review process.

The global advocacy workstream has over-achieved this year, principally through IBP contributions to the Financing for Development process and engagement with the World Bank’s “Reimagining Public Finance” initiative.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The termination of the US State Department grant has meant plans to accelerate the release of the 2025 OBS to enable greater time for civil society advocacy have been cancelled. In August 2025, IBP secured a new partnership with the Gates Foundation.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Last year’s annual review encouraged IBP to work with FCDO to identify new partners in priority countries and expand the number of thematic policy areas such as climate finance or debt transparency. There is little evidence of progress on the first point, seemingly because time has been spent deepening engagement on existing mechanisms (with some evidence of impact). An initiative to pilot a debt transparency module as part of the 2025 OBS was delayed and will start in 2025-26.

For the coming year, we suggest:

Conducting a detailed review of progress to date, identifying areas where gains have been made and how these can be consolidated - particularly by strengthening linkages with the other components of FTAI. Additionally, assessing areas with weaker progress and exploring how to reinforce them, including refining focus areas, especially in a context of limited resources.

Strengthening links between activity on the ground and UK missions in host countries. There is already evidence of contact, sharing of experiences, and use of UK missions for convening. The intensely political nature of the context in which public finance transparency sits means that a political influencing campaign that routinely draws on UK bilateral engagement could increase the impact of these engagement moments.

Output Title	FTAI delivery partners engage globally to deepen and expand commitment to global norms on fiscal transparency and open contracting.
Output number:	4	Output Score:	A
Impact weighting (%):	10%	Weighting revised since last AR?	Not applicable (new output)

Indicators	Milestones	Progress
Number of Open Budget Surveys completed by the end of the programme.	-	Since the OBS cycle did not include a survey in 2024, there is no milestone for this review period.
Number of clear endorsements of open contracting and action on the ground by International Financial Institutions.	1	2 endorsements of open contracting by the international community: / 1. In 2024 open contracting was recognised by the OECD Blue Dot Network as ‘superior’ practice, with the use of both data standards (OCDS and OC4IDS) recommended / 2. Financing for Development ‘Compromiso de Sevilla’. An issues paper on the role of better procurement in delivering the SDGs and OCP co-organising events at FFD meetings helped improve the language and ambition around procurement in the final outcome document.
Number of pilot studies completed by CoST.	2	2 pilot studies in Uganda and Jalisco State (Mexico) to model new data points developed by CoST.
[note] See Footnote 2.

Briefly describe the output’s activities and provide supporting narrative for the score.

While Outputs 1 to 3 focus on changes on the ground in focus countries, this output is about international norms and global public goods.

OCP provided extensive input into the OECD’s Blue Dot Network process, which resulted in a positive endorsement of two global norms developed by OCP (Open Contracting Data Standard and Open Contracting for Infrastructure Data Standard) in 2024-25. They also engaged extensively with the UN Financing for Development (FFD4) process contributing an issue paper on the role of better procurement in delivering the Sustainable Development Goals and organising side events at FFD4 meetings. These helped improve the language and ambition around procurement in the final outcome document (Compromiso de Sevilla): “we will promote budget transparency, including by implementing transparent data-driven procurement systems.”

The CoST Infrastructure Transparency Initiative successfully piloted new data points (standardised metrics) for their infrastructure sustainability and climate finance data modules in Uganda and Jalisco State, Mexico, demonstrating their value in improving project appraisal and selection.

All milestones were met or exceeded. Therefore, the Output is scored A.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In 2024, funding for CoST’s pilot studies was approved as part of the FCDO’s responsible infrastructure investment campaign. The project has now been completed, and FTAI support to CoST has concluded.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Although FTAI support to CoST has ended, the FCDO should continue to:
- Promote the integration of CoST data modules into public financial management systems to strengthen the link between infrastructure transparency and fiscal governance;
- Use international forums and donor coordination platforms to (a) raise awareness of the importance of data transparency, especially in early infrastructure development stages, and (b) position CoST data modules as a valuable tool for improving investment planning.
## D: VALUE FOR MONEY

Value Statement

“We will be rigorous in maximising the resources we deploy to making material contribution to our efforts to improve fiscal transparency and accountability in focus countries.” FTAI prioritises efficiency, fosters strong relationships with implementing partners, and gradually shifts resources from global goods to in-country support.

Key cost drivers and performance

IBP’s primary costs include staff time, the OBS researchers, subgrants, travel and meeting costs. These cost categories remained consistent during the reporting period. Due to ongoing funding pressures, IBP has implemented cost-saving measures over the past two OBS survey rounds. These included transitioning from in-person to virtual engagements, enabling broader participation while reducing expenses.

OCP’s biggest costs under FTAI were associated with the IT development of the DREAM platform. These expenditures were carefully monitored and continue to represent excellent value for money. OCP partnered with a Ukrainian contractor, offering lower rates than international firms. Despite the technical complexity, the project was delivered on time and within budget.

NAO’s fees strictly cover the actual cost of delivery, with no profit margin. Both Parliament and HM Treasury have approved these rates.

VfM performance compared to the original VfM proposition in the business case

The programme’s business case concluded that continued support for IBP, OCP, and NAO offers good value for money. This review found no evidence of underperformance or significant cost increases.

Effectiveness

Implementing partners delivered meaningful and measurable outcomes aligned with the programme’s objectives. Their interventions contributed to improved transparency, public procurement, public investment management, and citizen engagement across multiple focus countries. By translating strategic inputs into real-world change – such as legislative reforms, new institutional structures, enhanced data systems, and strengthened civil society participation – partners demonstrated their ability to generate sustained impact.

Significant progress was made on recommendations from the previous annual review. This included an updated theory of change and logframe. Additionally, OCP proposed generating new global evidence on digital platforms to track climate and development finance, building on the lessons from the DREAM project. This action research project will be implemented in 2025-26.

Efficiency

Implementing partners demonstrated strong efficiency by effectively converting resources into tangible outputs. Despite facing external challenges such as funding withdrawals and political disruptions, partners consistently delivered planned activities on time and within budget. Their strategic use of local expertise, adaptive delivery models, and streamlined operations ensured that inputs were optimally used to achieve programme goals. This performance reflects an important level of operational discipline and resourcefulness across the portfolio.

Progress has been made on previous recommendations to enhance efficiency. The programme team reviewed budget allocations and future forecasts to ensure alignment with the revised Theory of Change and logframe. The partnership between FCDO and NAO has strengthened, evidenced by regular monthly meetings, new initiatives, an expanded partnership portfolio, and successful collaboration during the INTOSAI annual meetings in London.

Equity Impact Assessment

FTAI supports the inclusion of women, people with disabilities, and other marginalised groups in decisions about public spending. IBP works globally to make national budgets more inclusive and equitable. A key focus of IBP is gender equity, ensuring public funds are raised and spent in ways that benefit everyone, especially women. In Indonesia, for example, collaboration between IBP, civil society, and local governments led to real change. In Medan, a proposal from women in coastal communities to build waste management facilities and improve water access was adopted in the 2025 regional development plan. FCDO will continue supporting IBP’s efforts to promote fair and inclusive public finance in the year ahead.

Assessment of whether the programme continues to represent value for money

Based on the evidence presented, the programme continues to represent strong value for money. Implementing partners have delivered impactful, efficient, and inclusive results within budget, despite external challenges. The programme has made meaningful progress on previous recommendations and continues to align resources with strategic objectives. Continued support for IBP, OCP, and NAO remains a sound investment in promoting fiscal transparency and accountability.

E: RISK

Overview of risk management

FTAI faces a range of strategic, operational, and contextual risks. All residual risks remain within the department’s risk appetite. Risks are reviewed and updated on a quarterly basis with partners, ensuring that the programme maintain a structured and responsive approach to risk mitigation with clear strategies aligned to FCDO policies and procedures.
The programme demonstrates a mature and responsive approach to risk management. The risk of budget shortfalls poses a significant challenge. Other major risks – such as volatility, delivery in fragile contexts, and reputational concerns – are being addressed through adaptive programming, strong partner engagement, and robust oversight mechanisms. Overall, the programme risk management framework is sound and supports continued delivery in complex environments.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Performance

The total cost of the programme to FCDO is £16.5 million over seven years including the £6.5 million cost extension and two-year time extension that was approved via a business case addendum in April 2024. All funding is ODA eligible.

Projects are paid in arrears based on progress against agreed workplans, in line with the Accountable Grant Agreements with OCP and IBP and the Memorandum of Understanding with the NAO.

Table 3: FTAI Budget Allocations and Spend by Implementing Partner
Partner	Agreement	Start Date	End Date	Value (£)	Spend (£)
IBP	Accountable Grant	01/08/2023	31/03/2027	2,350,000	1,200,002
OCP (1)	Accountable Grant	03/09/2022	31/03/2023	500,000	434,570
OCP (2)	Accountable Grant	19/05/2023	18/05/2027	5,149,925	4,849,383
NAO	MoU	15/08/2022	31/03/2027	1,450,000	574,509
CoST	Accountable Grant	01/08/2024	31/03/2025	97,071	78,591
FMUP	Administration Agreement	-	-	300,000	300,000
[note] Spend as of 31st March 2025, end of the 2024/25 fiscal year.

In this reporting period, the total approved budget from FCDO was £3,841,585. The total spend was £3,810,740. The small variance was due to delays in completing some in-country activities.

Table 4: FTAI Spend Breakdown
Project No	Project Name	2022/23 (£)	2023/24 (£)	2024/25 (£)	Total Spend (£)
300948-101	IBP	-	750,000	794,514	1,200,002
300948-102	OCP	434,570	2,065,178	2,349,635	4,849,383
300948-103	NAO	83,195	185,003	288,000	574,509
300948-401	CoST	-	-	78,591	78,591
300948-404	World Bank FMUP	-	-	300,000	300,000
		517,765	3,000,181	3,810,740	5,803,683
[note] Contribution to the World Bank Financial Management Umbrella Programme to shore up supply-side efforts on fiscal transparency and accountability.

Programme Management Performance

The programme team continued to manage the programme effectively coordinating with implementing partners. Funding and delivery were managed through accountable grants and MoUs, with payments linked to agreed workplans, helping ensuring flexibility and accountability. The programme remained on track financially with no major risks reported. The programme also secured a no cost time extension, reinforcing its commitment to long-term impact and learning

Performance of Implementing Partners

The programme team maintains an effective and well-established partnership with all implementing partners. Partners are responsive to requests for information from FCDO and quarterly meetings continue to take place alongside less formal communication throughout the quarter. All implementing partners performed well, delivering against their workplan and demonstrating clear progress in their areas. They have also remained on budget, adapted effectively to changing contexts and continued to show strong alignment with FTAI and FCDO’s goals.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring, Evaluation, and Learning (MEL)

All MEL activities are conducted by the programme team in collaboration with implementing partners. The review recommends:

- Review and adapt the MEL structure to ensure it remains fit for purpose. This may include revisiting staffing levels, tools, and processes to maintain effectiveness.
- Develop standardised templates for partner reporting to reduce the administrative burden on programme team and leverage AI technology for data analysis to improve efficiency.
- Formalise and potentially expand feedback mechanisms to ensure consistent inputs from beneficiaries (e.g., structured surveys, focus groups).

The Annual Review was conducted by the programme team with input from an FCDO Governance Advisor. The external input contributed to the analysis of governance-related outcomes and ensured an independent perspective on performance. The review assessed the Fiscal Transparency and Accountability Initiative from April 2024 to March 2025, focusing on progress against the updated logframe and theory of change. The process aimed to evaluate achievements, identify challenges, and recommend action to improve delivery and ensure value for money. The team examined a wide range of documents including programme delivery plans, partner reports and financial statements, and risk registers. Input was gathered through partner questionnaires and requests for feedback.

Beneficiary Feedback

The Ministry for Development and Communities of Ukraine expressed strong gratitude for UK support of the DREAM system. DREAM is transforming public investment management through transparent, data-driven processes aligned with Ukraine priorities. It hosts over 13,000 projects worth $40 billion and is institutionalised in Ukraine’s Budget Code. The platform is used by over 1,300 institutions and integrates climate resilience, citizen inclusion, and anti-corruption safeguards. The Ministry requested continued UK funding (from the British Embassy Kyiv DIGIT programme, not from FTAI) to sustain and expand DREAM and its ecosystem. The initiative is seen as a model for both Public Investment Management and aid transparency and represents a strategic investment in Ukraine’s recovery and regional stability.

The Ghana Audit Service (GAS) expressed deep appreciation for the Revenue Audit Training delivered by the NAO from 30 July to 7 August 2025. The training was timely, well-structured, and impactful, enhancing participants' skills in integrated financial and IS audits. Facilitators were praised for their expertise and engagement. The training materials and actionable next steps have already begun influencing internal practices. GAS looks forward to continued collaboration with NAO to strengthen audit competencies and promote transparency in public financial management.

NAO’s partnership with the SAI Rwanda was positively received by the Auditor General. The SAI Kenya were very appreciative of the support from the NAO - their reports were recognised as influential in promoting accountability, though parliamentary follow-through remains a challenge.

The review team collected the following feedback from FCDO Posts:

- Indonesia: Feedback highlighted the broad scope of activities under IBP and OCP. A recommendation was made to narrow focus to key themes, such as OECD accession, to enhance impact.
- Rwanda: Transparency International Rwanda’s role in the Open Budget Survey was commended, with suggestions to present findings in the PFM Working Group to incentivise government improvements. OCP’s support for e-procurement reforms was noted.
- Kenya: While OCP’s impact on procurement data was unclear due to limited engagement with the Post, there is interest in structured collaboration moving forward. UK support for Kenya’s e-procurement system was highlighted as a potential area for OCP involvement.

Evidence

The launch of the Reimagining Public Finance (RPF) initiative and the Strengthening Fiscal Ecosystem for Accountability and Equity project marks a significant shift in how fiscal governance is conceptualised and evaluated.

Reimagining Public Finance. Led by the World Bank, the RPF initiative rethinks how public finance can be better aligned with development goals. It moves beyond technical improvements in PFM systems to focus on removing bottlenecks in fiscal policy and service delivery. This initiative is backed by extensive global consultations and outcome-based research, providing broad and inclusive evidence base. In 2025-26, FTAI will contribute directly to the RPF initiative.

Strengthening Fiscal Ecosystem. The fiscal ecosystem project, led by TAI Collaborative, introduces a systemic approach to fiscal governance. It emphasises the importance of collaboration among diverse actors – finance ministries, oversight institutions, civil society, donors – to promote accountability and equity in fiscal decision-making. This project is grounded in action research across multiple countries, including Indonesia (a focal country), offering context-rich insights but still in initial stages of testing propositions. FTAI may benefit from adopting a more holistic, ecosystem-based approach to fiscal governance, aligning with emerging global thinking. The internal M&E system should evolve to capture relational systemic changes.
[note] The fiscal ecosystem approach is already integrated into the International Budget Partnership’s work.

Learning

Over the last year, the programme has employed a range of learning processes to capture and share lessons and new evidence. Implementing partners submitted detailed annual review documents outlining outcomes, challenges and lessons learned. These documents served as sources of programme learning. The programme team facilitated a workshop with all implementing partners, focusing on theory of change. IBP and OCP contributed to the UN Financing for Development IV, sharing insights and influencing the conference outcome document. The NAO produced a paper that explores outcomes and impacts through case studies and case examples from their peer support to SAIs.

The following lessons emerged across partners and geographies:

- Political economy awareness is crucial - Success in countries like Ukraine and Tanzania depended on navigating institutional dynamics and aligning reforms with political priorities.
- Adaptive management is essential - Partners responded to funding cuts (e.g., USAID withdrawal) and political transitions, maintaining momentum through flexible planning and delivery.
- Digital tools can reshape governance - The DREAM platform in Ukraine demonstrated how digital infrastructure can decentralise decision-making and accelerate project delivery.
- Structured engagement mechanisms drive reform - Platforms like Rwanda’s task force and Tanzania’s Public Expenditure Reviews have proven effective in translating technical findings into policy action.

Table 5: Financial Reports and Audited Annual Statements Summary
Implementing Partner	Latest Financial Reports	Audited Annual Statements
IBP	April 2025	IBP submitted audited annual accounts for 2024.
OCP	April 2025	OCP submitted audited annual accounts for 2024.
CoST	April 2025	CoST has not yet submitted annual audited accounts for 2024. This will be ready in September 2025.
NAO	April 2025	Not Applicable