## TaxDev Annual Review 2025

Title: Tax Analysis in Developing Countries, Phase III, Annual Review
Programme Value £ (full life): £15m		Review date: June 2025
Programme Code: 300949	AMP start date: 1/5/2023	AMP end date: 31/3/2030

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A+	A+
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300949 Documents (fcdo.gov.uk)
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The TaxDev III Programme, jointly delivered by the Institute for Fiscal Studies and ODI Global, aims to strengthen the capacity of Tax Policy Units (TPUs) in the Finance Ministries of low- and middle-income countries to design and advocate for more equitable, evidence-based, effective tax policy. The programme will run until 2030 and – if successful – will support partner countries to maintain economic stability and reduce dependence on international aid.

Summary narrative for the overall score

This 2025 Annual Review process – which included discussions with all 6 partner countries - found that the programme is operating well in a challenging context. Partner countries have struggled to significantly increase revenues in recent years but there is evidence of improved capability and increasing traction with policymakers in several settings. The overall score of A+ reflects the fact that the programme is meeting all of its Output targets and exceeding them in some areas.

Major lessons and recommendations for the year ahead

There are 3 main reflections and 2 main recommendations for 2025/26 stemming from this Review:

Three reflections:

There is a mismatch between TaxDev III’s time and incentives for capacity building and the complexity of the challenge at hand. Building the expertise and experience of Tax Policy Units (TPUs) is – unsurprisingly – very challenging. Sustainable capacity building depends on multiple factors, from pay and human resource policies through to organisation culture and ways of working, so even the best classroom or on-the-job training may not be enough. Discussions held with TPUs for this review revealed strong demand for hands-on support on tax policy analysis, this demand for research is a positive signal about TPUs’ motivation to build, retain, and use analytical skills in their teams, though it also means TaxDev Advisors have limited time left for capacity building after meeting the demand for analysis.

TaxDev only provides a small part of the solution to increasing tax-to-GDP ratios in partner countries. This is most starkly illustrated in Ethiopia where TaxDev have provided sound, in-demand support to the TPU over several years but there has been a steady fall in the Tax-to-GDP ratio. TaxDev is not a silver bullet for tackling Public Financial Management (PFM) challenges and was not designed to be one. FCDO Teams in Post should engage with TaxDev advisors and ensure that TaxDev’s support is integrated into a wider approach to supporting partner governments (possibly including other channels of support from the UK, but also from partners like the World Bank and IMF).

TaxDev III is a good example of the UK ‘sticking at’ a complex, important problem and delivering results over a long period of time. UK ODA cuts and re-prioritisation exercises in recent years have reduced the predictability of UK support. TaxDev III is an example of a patient, dedicated programme which has delivered results through persistent support. Across the interviews with TPUs the Review Team met several staff who reflected that TaxDev’s persistence was paying off; gradual gains on tax expenditure reporting are a good example of this.
And two recommendations:

Sustainable capacity building remains the area where TaxDev has most room for improvement, the Team should consider what they could do differently in 2025/26. Several previous Annual Reviews have challenged the TaxDev team to deepen work on capacity building. There is still more to do. Most TPU interviewees weren’t aware of the TaxDev end date in 2030; in 2025/26 the TaxDev team should reflect on what they can do differently – beyond classroom and on the job training – to plan for a sustainable transition at the end of the programme. Kenya and Nigeria, in particular, present an opportunity to take a new approach to capacity development.

FCDO Teams should consider how TaxDev can complement wider work on PFM. Improvements in tax policy will only be effective in supporting revenue increases, poverty reduction and stability if complemented by strong PFM in other areas. This is most strikingly illustrated in Ethiopia where the Tax-to-GDP ratio has consistently fallen since the start of the TaxDev programme because of macroeconomic challenges. FCDO Posts should consider how TaxDev support fits with the overall Development Partner support package, the extent to which TaxDev is playing a critical role, and what the FCDO team can do to make TaxDev an effective part of a portfolio approach to UK support.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The TaxDev III Theory of Change

The Theory of Change for TaxDev III is summarised below:

Impact	Governments, particularly partner governments, develop and implement evidence-based tax policies which help them to achieve their revenue, poverty reduction, and sustainable growth objectives.
Outcomes	Increased and sustained capacity within partner governments to design, conduct, interpret, and use applied policy analysis, and increased demand amongst decision makers, both in partner countries and elsewhere, for appropriate tools, methods, and evidence to inform the tax policymaking process.
Outputs	Objective 1 is to support and sustain the increased use of evidence in the tax policymaking process in six partner countries. / Objective 2 is to generate high-quality research, analysis, and commentary on tax and development through partnerships with policymakers and researchers. / Objective 3 is to support the wider uptake of tax research and resources and strengthen local and international tax policy networks and learning.
Assumptions	- Increased access to high-quality analytical evidence will be used to improve policy in tax and expenditure. / - Policymakers want to improve the effectiveness of tax policy.
Inputs	- Microsimulation modelling and training on in-house modelling and analysis use. / - Data capture, verification, cleansing work to improve modelling and analysis. / - Policy costing analysis and capacity building in (mainly) Finance Ministries and Revenue Authorities. / - Working with senior policymakers to incorporate findings into public policy. / - Research workshops and dissemination at international tax research conferences and regional seminars. / - Lesson-learning exercises and guidance materials to share with wider audiences.

Since the programme was first established in 2016, a lot has been learned about this Theory of Change (ToC). A detailed summary of lessons learned was provided in the Phase II Programme Closure Review. TaxDev has seen many examples where this ToC has worked and some where the programme has struggled. Three examples of this ToC in action (or not) in 2025 are listed below:

In Uganda, TPU officials reflected that consistent TaxDev support over several years has helped them move towards specialisation (4 specialist roles were recently hired) and improve their use of data. Tax policy changes announced in April 2025 to excise taxation of beer were informed by TaxDev-supported TPU analysis.

In Ethiopia, strong technical TaxDev support has led to increased use of evidence in the policy making process but has not led to the desired impact of increased revenue and poverty reduction. Factors beyond the control of TaxDev, including, the Government’s broader macro-economic policy, have (at least until recently) undermined the TaxDev ToC in this setting.

In Zambia, GIZ Zambia’s Good Financial Governance have used the TaxDev Tax Policy Costing Manual and the Tax Policy Appraisal Manual to guide their support for a tax policy analysis framework, illustrating that the ToC of using research/evidence to spread policy change can work.
On balance, there is evidence that the ToC is valid, though – as with most policy change - complex to achieve in practice.

Progress towards expected outcomes and impact, and actions for 2026

In 2025, most of the TaxDev partner Governments are struggling to achieve their revenue, poverty reduction, and sustainable growth objectives. Since the TaxDev programme moved into its third phase, three of the four partner governments have seen their tax-to-GDP ratio fall in at least one year (Figure 1). These countries’ macroeconomic performance is clearly beyond the control of the TaxDev programme, which – given its scale – can only expect to make a modest contribution to a very complex challenge. TaxDev cannot change all tax policy at once - it can advise on new initiatives but not the stock - and it can’t singlehandedly change the macro economy or change the tax administration system through which tax policy is applied. Nonetheless, it is striking that progress towards the high-level objective set for the TaxDev programme has been slow.
[note] See the IMF’s April 2025 Sub-Saharan Africa Economic Outlook “Recovery Interrupted” for more detail.

There is a case that TaxDev has helped Tax Policy Units soften the impact of shocks, and the IMF forecasts that all TaxDev III partner countries will increase their tax-to-GDP ratios significantly in the coming years. At this 2025 Annual Review mark, however, the jury remains out on whether the intended impact of TaxDev III will be achieved in full.

Figure 1: Not Smooth Sailing on tax-to-GDP
Source: IMF reporting between Sept 2024-Jan 2025

Progress on delivering the intended outcomes of the TaxDev III’s programme has been relatively strong, as Table 1 shows.

There is strong evidence that TaxDev support is in demand and highly valued by policy makers, and that this has led to a more evidence-based tax policy making process as envisaged in the Theory of Change. There is evidence across all four core countries – Ethiopia, Ghana, Uganda and Rwanda – of strong analysis by TaxDev advisors translating into policy; analysis of VAT reforms in Ethiopia, excise reforms in Uganda, and tourism taxation in Rwanda all stand out as good examples in 2024/25.

As in previous reviews, sustainably building capacity within TPUs remains challenging. In Ethiopia, where there are just two staff working on Tax Policy, staff interviewed for this Annual Review reflected that they don’t have the time or IT resources to engage in significant capacity development with the TaxDev Team. In Uganda, where TaxDev advisors have run several training sessions with staff, TPU officials reflected that building expertise and experience in a department is a complex, long-term process which requires more than classroom training.

The recommendations for the TaxDev and FCDO Teams set out in section A are intended to address the potential weaknesses in the TaxDev Theory of Change.

Continuation of TaxDev III

Based on the findings of this review, there is a strong case for TaxDev III continuing its work in 2026. The external context is challenging but there is good evidence of success at both Output and Outcome level. In 2025, with cuts to ODA budgets by the UK and many other traditional development partners, the case for experienced programmes like TaxDev continuing to support work to increase domestic revenues is very strong.
Table 1: Progress against Outcome Indicators
Outcome indicator	Target	Progress 1st May 2024-30th April 2025
Number of requests from senior civil servants and ministers in TaxDev partner countries for evidence using TaxDev- supported tools, models or analyses	6	Achieved. There is evidence of strong demand for TaxDev support in all of the TaxDev III core countries: / In Ethiopia, interviews showed clear evidence of a trusting, demand-led relationship with the Director of Tax Policy which has led to research on Ethiopia’s falling Tax-to-GDP ratio and VAT system changes. / In Ghana, TaxDev support was requested to support officials with analysing a range of proposals during and after the elections in December 2024. / In Rwanda, TaxDev responded to a request from the State Minister for analysis of a new Tourism Tax. / In Uganda, the Team have responded to demand for analysis of potential VAT and excise tax changes. / The Team have also had an initial request for support in Nigeria to review tax bills as the Programme establishes in Abuja. The logical framework target of 6 requests from senior policymakers was comfortably met.
Number of national tax policy decisions which have been informed by analyses and evidence generated by TaxDev	5	Achieved. In several cases where TaxDev analytical support was requested, it was possible to see impact on policy in during 24/25. E.g.: / In Ethiopia, TaxDev input directly shaped new VAT Directives to rationalise exemptions which was enacted in 2024. / In Rwanda, TaxDev advice supported the introduction of a tourism levy and increase in the tax on gambling revenue, amongst other changes. / In Uganda, consistent support by TaxDev on excise taxation translated into increases in the duty levied on beer and wine. / Unsurprisingly, TaxDev advice didn’t translate into policy in every instance, however. / On balance, the logical framework target for this indicator is comfortably met.
Number of core tax policy functions that TaxDev has introduced or improved, now delivered with limited input from/independently of TaxDev staff	4	Achieved. Evidence of TaxDev impact on this indicator is modest: / Progress on embedding tax expenditure reporting within Tax Policy Units continued. Uganda published its latest Tax Expenditure report in April 2025. Rwanda also published its 7th such report in May 2025. Both are now being delivered with limited input from TaxDev. / There is evidence that in-house cleaning and structuring of data has improved in Rwanda. Following TaxDev’s support in this area, TPD partners now are leading on the cleaning and structuring of data for motor vehicle policy analysis and have expanded the analysis to examine hybrid and electric vehicles. / The challenges to sustainably building capacity have been well documented, including in the 2024 Annual Review. Turnover of staff, limited staff capacity, and limited resources all make progress slow. A recommendation of this report – as with previous Reviews – is to re-double efforts on capacity building.
4 & 5. Collaboration with local researchers & TaxDev influence beyond partner countries.	0	Exceeded. TaxDev III is not expected to make progress on Outcome Indicators 4 & 5 – relating to local research collaboration and influence beyond core countries – until 2026. / In March 2025, however, GIZ Zambia’s Good Financial Governance team highlighted that TaxDev resources – specifically the Tax Policy Costing Manual and the Tax Policy Appraisal Manual – have guided their support for a tax policy analysis framework in Zambia.

## C. DETAILED OUTPUT SCORING

Output Title	Taxpayer micro-level data is made available to support improved modelling and analyses of national tax policies
Output number:		1	Output Score:	A
Impact weighting:		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone	Progress
Number of countries in which available taxpayer administrative micro-data has been mapped (new countries).	0	N/a
Number of countries in which agreed mechanisms are in place for the sharing of taxpayer micro-data between the Ministry of Finance & Revenue Authority, and where necessary from an operational perspective, IFS and ODI.	0	Achieved. / In Uganda, TaxDev signed a Memorandum of Partnership with MoFPED to establish the responsibilities of both parties, including on the sharing, governance and use of data, which should ensure and facilitate effective taxpayer and other administrative data access and use for tax policy analysis.
Number of tax policy areas for which administrative datasets have been cleaned and structured in a way that is accessible to TPU analysts.	3	Achieved. / In Ghana, TaxDev reviewed and documented Integrated Customs Management System micro data which covers daily releases of import data from 2022 and 2023 which feed into the Customs Model. TaxDev has also processed data on monthly petroleum import volumes (2010-2023) for use in forecasting. / In Rwanda, TaxDev cleaned beer sales excise data (2022-23) to extract information on beer volumes. / In Uganda, TaxDev created a VAT summary database, based on the administrative data at the Uganda Revenue Authority (URA) research lab, and shared with Tax Policy Department (TPD) staff.
Number of countries in which a structured plan is being implemented to ensure continued data access, maintenance, and use to support sustainability and the delivery of core tax policy functions.	1	Achieved. / In Rwanda, TaxDev has supported MINECOFIN and RRA to improve data sharing and management processes. Shifts in the management approach at RRA have made the data handling processes more structured and efficient.

Output 1 Summary

Use of data is consistently highlighted as a strength of TaxDev. Interviewees in Ethiopia, for example, were clear that the quality of their advice to policymakers is only as good as the quality of their data and TaxDev’s work on data has been very valuable to them. During the review period, TaxDev teams have comfortably achieved all the milestones on data availability.

Uganda and Rwanda stand out as the countries making greatest progress this year on data management. In Uganda, TaxDev has built on an existing partnership between UNU-WIDER and URA, who have established a data lab. In Rwanda, TPD and RRA have clarified the process for data requests and developed a system of shared folders and focal persons which appears to be working well.

In Ghana, there is early work to learn from the positive examples in Rwanda and Uganda. TaxDev are using a new Sustainability Checklist to ensure that required data inputs and processing skills can be sustained over time, and FCDO Ghana recently participated in a discussion with the Commissioner General about data requirements for policy analysis. In Ethiopia, TaxDev has looked carefully at methodologies for estimating GDP, TPU officials in Addis reflected on useful discussions with TaxDev Advisors about the advantages and disadvantages of different GDP methodologies.

A score of A is comfortably achieved. Strong evidence of polices on data being sustainably embedded into TPD structures in 2026, and mapping in the two new partner countries, would see this elevated to an A+.

Changes to this Output

During the programme year, the target for Output 1.1. was revised downwards from data mapping in 2 countries to data mapping in 0 countries. This was to reflect the fact that factors beyond the control of TaxDev had delayed the programmes rollout in Kenya and Nigeria.

Recommendations

Neither of the recommendations from the previous Annual Review have been completed. These were:

TaxDev should review its data protection policies and consider whether there is a need to develop special data protocols for staff embedded in Ministries.

TaxDev should finalise their note on Data for Tax Policy Analysis, publish it, and use it as a platform to build more systematic resources in partner countries, and as a public good for analysts in other countries.
A priority in 2025/26 should therefore be to follow up on these recommendations. Recognising the success and complementarity of the UNU-WIDER – URA partnership in Uganda, TaxDev might also consider whether this is something which could be replicated in other countries with support from TaxDev Advisors.

Output Title	Microsimulation models, policy costings tools and applied analytical projects are developed in collaboration with analysts, and generate rigorous, relevant policy analyses
Output number:		2	Output Score:	A+
Impact weighting:		35%	Weighting revised since last AR?	No

Indicator(s)		Milestone	Progress
Number of countries in which available taxpayer administrative micro-data has been mapped (new countries).		4	Achieved. / Annual workplans have been agreed or are being finalised in Ethiopia (March ’25), Ghana (July ’24), Rwanda (Aug ’24) and Uganda (April/May ’25).
Number of countries in which TAXDEV has developed at least one model or tool for analysing national tax policies using taxpayer or survey micro-data (new countries only)		0	N/a
Number of models or tools developed which can be used to respond to requests from senior policymakers and to support the delivery of core tax policy functions		2	Achieved. / In Ethiopia, TaxDev have developed a template for the Annual Revenue Performance report which will allow TPD to take over this reporting. The TaxDev team also developed models to estimate the relationship between Ethiopia’s tax-to-GDP ratio and used an IMF model to estimate Ethiopia’s ‘VAT Gap’, though both of these models are complex and were developed to complete a report on Ethiopia’s tax-to-GDP ratio rather than regular use by the TPD Team. / In Ghana, TaxDev developed a model to forecast petroleum volumes and inform static costings of petroleum rate changes. / In Rwanda, TaxDev updated the beer excise model and used it to analyse pricing impacts of policy changes.
Number of costings, appraisals, reports or policy briefs drafted based on the results of TAXDEV analyses and presented in policy fora		10	Exceeded. / In Ethiopia, the centrepiece of TaxDev-TPD collaboration has been a detailed report on Ethiopia’s falling tax-to-GDP ratio. TaxDev have prepared policy notes on at least 6 other topics, including analysis of VAT changes and analysis of proposals intended to incentivise start-ups. TaxDev has also provided feedback on issues such as presumptive taxation and income tax reform proposals. / In Ghana, TaxDev provided analysis of various pre- and post-election tax proposals, with 14 different measures costed in total. TaxDev also worked with the Tax Policy Team to draft a Medium-Term Revenue Strategy (MTRS) de-brief report (reflecting on the MTRS drafting process) and a series of summary notes drawing together joint work over the last 3-4 years. / In Rwanda, TaxDev collaborated with TPD on a tourism tax appraisal, an assessment of investment promotion incentives, tax expenditure reporting, and policy briefs on both financial services and gambling taxation. / In Uganda, TaxDev have produced 5 policy briefs, a paper on Uganda’s tax-to-GDP ratio, and supported tax expenditure reporting. / In Nigeria, TaxDev completed their scoping report and provided some initial analysis of tax bills and tax expenditure reporting.
Number of national tax policy proposals by policymakers which have been analysed and informed by models, tools, or (distributional) analyses supported by TAXDEV		8	Exceeded. / This Output links closely to output 2.4. Analytical work in Ethiopia informed 3 new VAT directives/regulations. In Ghana, 5 measures costed by TaxDev were included in the March 2025 budget. In Rwanda, proposals on VAT changes, a tourism levy, an increased gambling tax, reduced incentives for hybrid vehicles, and an updated ‘stay of application’ policy position for EAC discussions, were al informed by TaxDev analysis. In Uganda, TaxDev analysis informed 7 national tax proposals, mostly on excise taxation.
Number of internal or external events organised with TPU partners to raise awareness of TPU work and to disseminate policy findings		3	Exceeded. / In Ethiopia, TaxDev supported dissemination events for the TPD’s Tax-to-GDP study and an internal workshop to present initial findings of policy projects on VAT and tax incentives. / TaxDev hosted a delegation of tax policy and administration officials from Ghana to London in September 2024 and held workshops in November to discuss costing of manifesto proposals. / In Rwanda, TaxDev supported the kick-off workshop for tax expenditure reporting work by the TPD (with a blog on the lessons learned available here). / In Uganda, TaxDev hosted workshops on data analysis for revenue forecasting, the harmonisation of excise duties and revenue mobilisation strategy implementation.
Number of countries in which TAXDEV has contributed to significant reform agenda or medium-term strategic planning processes, such as DRMSs or MTRSs		2	Achieved. / In Ghana, TaxDev’s support has enabled a review of the VAT system which has fed into the MTRS and informed discussions with the IMF. / In Rwanda, TaxDev support informed new tax measures announced in February 2025 and the continued work on tax expenditure reporting. / In Uganda, TaxDev presented an analysis of progress against the Government’s Domestic Resource Mobilisation Strategy.

Output 2 Summary

Microsimulation modelling, proposal costing, and policy advice is the Output where TaxDev teams have consistently delivered strongest results. In addition to ‘routine’ work with Tax Policy Units to cost and advise on specific proposals, such as analysis of VAT and excise duty changes in Ethiopia and Uganda, the TaxDev team has also delivered several larger analytical pieces to provide an evidence base for broader policy decisions. The VAT system analysis in Ghana, Tax-to-GDP paper in Ethiopia, and tax incentives analysis in Rwanda are good examples of this. In addition to the volume of work produced in this area by TaxDev, the efforts to improve transparency, through blogs, workshops, and publication of documents, are what elevate the score for this output to A+.
TaxDev’s work on producing evidence to inform policy has not all been smooth sailing; in some instances reform options analysed have not proceeded for a variety of reasons. In 2026, as recommended in Section A, it may be that there is scope to improve collaboration between TaxDev teams and FCDO Posts to ensure that policy messages from TaxDev and TPUs are increasingly communicated at a political as well as technical level.

Changes to this Output

During the programme year, the targets for Outputs 2.1 and 2.2. were revised downwards to reflect the fact that factors beyond the control of TaxDev had delayed the programmes rollout in Kenya and Nigeria. For Output 2.1, Milestone 2 (April 2025) was changed from 6 to 4 while Milestone 3 (April 2026) was left unchanged at 6. For Output 2.2., Milestone 2 was changed from 2 to 0 while Milestone 3 was increased from 0 to 2.
During the programme year, in response to feedback from FCDO, the target for Output 2.7 was increased from 1 to 2, for this year and all future years of the programme.

Recommendations

There are no new or old recommendations to follow up for this output. The TaxDev Team are judged to be performing well and learning as they progress.

Output Title	Government analysts build the skills and systems to manage independent quantitative analyses of national tax policies
Output number:		3	Output Score:	A
Impact weighting:		25%	Weighting revised since last AR?	No

Indicator(s)		Milestone	Progress
Number of countries with a completed baseline and endline assessment, and documented lessons learned		0	N/a
Number of countries with a structured skills development plan and monitoring framework in place		0	N/a
Number of key tax policy analysis skills/tools that government tax policy analysts are trained in across the programme to support the delivery of core functions. These should be in line with identified needs assessments and/or skills development plans.		2	Achieved. / In Ethiopia, TaxDev ran small-group trainings on VAT Gap modelling, and on the preparation of revenue performance and tax expenditure reports. All trainings were internal and linked to ongoing policy work. / In Ghana, TaxDev ran one-day trainings on distributional analysis and policy appraisal/costing for TPU and GRA staff. Tax also delivered a one-week training on customs, petroleum forecasting, VAT Gap modelling and GHATAX models. / Trainings in Rwanda focused on Excel/R (3 staff) and ongoing training linked to tax expenditure reporting. / In Uganda, TaxDev delivered a training on data analysis for policymaking which focused on using URA tax return data (12 staff). TaxDev also delivered a week-long workshop on tax expenditure reporting (20 staff).
Number of tax policy analysis skills/tools for which a structured plan is being implemented to ensure sustainable uptake and maintenance. This could be through, for example, the production of induction and handover materials, manuals, guides, training resources		3	Achieved. / In Rwanda, TaxDev staff collaborated with TPD on a Capacity Development Plan (building on work from 2022) and developed training materials/notes to help embed tax expenditure reporting. / In Uganda, TaxDev has produced a set of tax expenditure estimation manuals for each of the relevant tax heads to accompany the set of Excel models developed for estimating foregone revenue under tax expenditures.
Number of instances across the programme of TPU staff sharing skills and knowledge acquired through the work with TAXDEV with their colleagues and/or regional peers. Examples could be through co-production, coaching, the delivery of training or workshops, and should be validated during the AR process.		2	Exceeded. / Ethiopia’s Tax Policy Director presented on the challenges and opportunities for business taxation in Ethiopia at a World Bank conference side event ‘The Business of Taxing Businesses in East Africa’ – September 2024. / Ghana’s then Principal Economics Officer presented on practical experience of using data and statistics to inform tax policymaking at a UNU-WIDER/UNDESA/TaxDev event ‘Data and Statistics for Development-focused Public Finance’. Revenue Policy Division colleagues also made significant contributions to TaxDev training workshops in September and December. / One of Uganda’s Tax Policy Economists presented at a World Bank conference side event on East Africa business taxation, and a TED Talk about establishing a TPD in Mozambique. TPD Officials shared skills developed with TaxDev support on several other occasions: in training new staff on tax expenditure reporting, showcasing the excise duty database to other Departments, and showcasing their VAT modelling.
Number of tools, training manuals, and guides developed and published on the TAXDEV website and disseminated beyond partner countries.		1	Achieved. / French Translation of the Tax Policy Costing Manual - Introduction à l’estimation du coût d’une politique fiscale: Un manuel et des exemples pratiques published.

Output 3 Summary
Building capacity of Tax Policy Units through the TaxDev programme is challenging; some staff leave, others are stretched in their day-to-day work, and basic barriers like IT equipment and data availability can make training difficult. Despite these challenges, there are a range of good examples of TaxDev capacity building in 2025. Tax expenditure reporting in Uganda and Rwanda continues to be a strong example of Tax Policy Units gradually learning skills and taking on new, complex responsibilities.
The scope for capacity building varies significantly across TaxDev partner countries. In Ethiopia, there are effectively just two full-time staff working on tax policy (See Box 1 for Case Study). In Uganda, there are over 30 staff. In Rwanda, structural changes to the Tax Policy Unit, including the transition of 3 interns to Officers, the hiring of a new senior expert, and plans to expand support from expert consultants, increase the scope for capacity building.
[note] Alongside a team of 10 working on tax exemptions and incentives.
As recommended in the 2024 Annual Review and in Section A of this review, with the end of TaxDev (2030) on the horizon it is important that the TaxDev Team put increasing focus on the challenge of capacity building – including the structural changes that many require in some instances – to ensure that progress isn’t lost.
Changes to this Output

There have been no changes to this Output this year and none are planned.
Recommendations
The TaxDev team have responded to one recommendation from last year’s Annual Review relevant to this Output, and are working on a second:
To improve the way TaxDev captures lessons learned, a new Skills Development Working Group has been set up. The team hold cross-country monthly meetings to share updates and ideas.

To improve the sustainability of the TaxDev model and identify how partner government’s might be able to transition to less intensive support over time (rather than a sudden stop in 2030), the TaxDev team have been developing a note on sustainability which will be shared with FCDO after this review.
As recommended in Section A, there is more to do to strengthen TaxDev’s work on capacity development. In particular, interviews for this 2025 Annual Review suggested that there is an opportunity for TaxDev support to move beyond classroom/on-the-job training to support TPUs to think more strategically about capacity development. The Business Case for TaxDev III noted that: “Increased attention will be paid to distinguishing between analysis that TPU analysts should conduct themselves and work that can be contracted out; in the latter case, TaxDev III will focus on supporting TPUs to better commission projects, and to interpret, critique and present report findings to internal and external audiences”. This type of support, to help TPU’s think more strategically about the transition away from TaxDev in 2030 could be very valuable.

Box 1: Skills, Interest and Energy: A Case Study on the Challenge of Capacity Building.
Uganda’s Tax Policy Department (TPD) has been a long-time TaxDev partner. During interviews for this 2025 Annual Review, TPD staff had several very thoughtful reflections on the ‘capacity development’ objectives of TaxDev: / Building expertise and experience in TPD requires skills, interest, and energy, not just classroom teaching. In a government system where salaries are low, this combination can be hard to come by. TPD officials reflected that building for the long term requires careful thought about a range of topics from pay structures to formal training, not all of which TaxDev can impact directly. / On-the-job training is still very valuable with the right mindset. On the job training works best where there is mutual respect between TaxDev Advisors and TPD staff – getting the right combination of individuals matters. In the TPD, some individuals have made much better use of TaxDev Advisors than others. / In-person support is worth a lot. TPD appreciate specialist training, but the fly-in fly-out nature of some support makes it difficult to embed learning. Officials consistently reflected that the in-person nature of TaxDev support really matters.

Output Title	High quality, theoretical and empirical evidence on tax and social insurance policies is generated in collaboration with government and academic partners, and is effectively disseminated to target relevant audience
Output number:		4	Output Score:	A+
Impact weighting:		20%	Weighting revised since last AR?	No

Indicator(s)		Milestone	Progress
Number of funding calls complete		1	Achieved.
Number of reports or working papers published on the TAXDEV website		4	Exceeded. / 8 reports/papers listed in Annex A.
Number of papers submitted to peer-reviewed academic journals		2	Exceeded. / 6 papers listed in Annex A.
Number of blogs, policy briefs or digital media published on the TAXDEV website and externally		6	Exceeded. / 14 outputs listed in Annex A.
Number of invitations to present at or participate in relevant research and policy conferences (e.g. ATRN, ATAF, ICTD, IGC, Spring Conferences), or to engage with international, regional, or local tax debates/dialogue		12	Exceeded. / Over 20 invitations listed in Annex A.
(A) % increase in number of users visiting the TAXDEV website, (B) % increase in followers on LinkedIn, (C) % increase in newsletter, recipients.		A) 10% / B) 20% / C) 10%	Exceeded. / 1st May 2025 – 30th April 2025: 8,403 users = 46% increase in user numbers. / 1st May 2024 – 30th April 2025 – 1044 new followers = 135% increase / Two newsletters completed during this period.
Number of local and international research seminars organised by TAXDEV to facilitate engagement with networks of tax policy experts and researchers		2	Exceeded. / 7 seminars listed in Annex A.

Output 4 Summary
Research capability is a clear strength of TaxDev. The team has made good progress on producing both practical policy briefs and high quality academic publications; researchers have published papers on a range of topics including: the role taxation in reducing inequality in low- and middle income countries (Journal of Economic Perspectives); the effect of digitisation of transactions on tax compliance (American Economic Journal: Economic Policy); and the impact of enlisting consumers for tax enforcement (National Tax Journal, forthcoming). In November 2024, TaxDev launched the first call for proposals for a new research fund and has had 5 proposals for projects across 9 countries.
Following the return of previous Research Director – Dr Anne Brockmeyer – to the World Bank, TaxDev appointed Professor François Gerard as Research Director in September 2024. TaxDev has recruited new research assistants, IFS has continued to host a Post-Doctoral Scholar who specialises in tax havens and evasion - Jakob Brounstein - as well of a number of academic visitors during the review period including Barbara Ama Zelu, Edward Abrokwah (Ministry of Finance Ghana), Laura Contreras-Portelas and Karen Codazzi.

Many of the events organised by TaxDev in 2025 involved close collaboration with partners. In August 2024, TaxDev researchers presented 7 papers and organised a special session on the taxation of wealth in low- and middle-income countries at the International Institute of Public Finance's (IIPF) 80th Annual Congress on 'International Tax Sheltering and Inequality'. In September, TaxDev co-organised the World Bank Public Finance Conference in Washington and supported a side event on Business Taxes in East Africa. In November, TaxDev researchers presented 3 papers and contributed to sessions at the 9th Zurich Conference on Public Finance. Contributions to these events, along with in-country collaboration with partners such as UNU-WIDER and ICTD, put TaxDev at the forefront of academic thinking on tax policy.

Changes to this Output
Following the 2024 Annual Review, the target for Output 4.5 was increased from 6 to 12 for this year and all future years. It was comfortably achieved.

Recommendations
Amongst the recommendations of the 2024 Annual Review were that TaxDev should (a) consider increasing its ambition on output targets, (b) disseminate lessons learned more widely, and (c) consider carefully how to deploy its limited resources. Actions under this Output show a good response to those recommendations: the target for engagement in research fora was increased, targets for sharing research were exceeded, and the TaxDev team made a conscious effort to increase the profile and visibility of the programme’s research which is a key strength of the programme.
## D: VALUE FOR MONEY

Key cost drivers and Value for Money of the TaxDev III Programme

The value for money of the TaxDev programme, based on detailed reporting, is judged to be strong. Below is a summary of our assessment of TaxDev’s performance against the 4 E’s:

Economy. Salaries, travel, and research dissemination costs are the main costs on the TaxDev programme. Important cost drivers, therefore, are the market conditions for tax policy expertise and the extent to which the TaxDev team decide to pay for international travel for their work. In 2025, staff costs have remained within the agreed budget. TaxDev have identified areas for collaboration with partners to ensure that costs are shared where possible, for example in relation to the delivery of the Annual Public Finance Conference with the World Bank and the 9th Zurich Public Finance Conference. Interviews with partner governments highlighted that the TaxDev team are sparing in deciding when it offers value for money to pay for international travel.

Efficiency. The efficiency of TaxDev programme is driven by the extent to which the programme can maximise the use of their experts’ expertise. In 2025, the TaxDev team continued to demonstrate that they are sharing tools, templates, and expert time across countries to deliver efficiently. For example, methodologies for estimating tax-to-GDP were shared between Ethiopia and Uganda, and expertise from the 4 ‘core countries’ was used in 2025 to provide initial inputs into the new Nigeria project. In London, a new Senior Project Manager, funded jointly by IFS/ODI Global and supporting both organisations, is identifying opportunities for increased efficiencies on program delivery.

Effectiveness. The effectiveness of TaxDev III depends on the extent to which TaxDev Advisors’ support and expertise leads to a sustainable increase in the use of evidence and research in tax policymaking. The interviews conducted for this review found strong evidence that TaxDev’s support is leading to increased use of data and evidence in the tax policy process; the results under Output 4 illustrate strong demand for TaxDev’s research. The outstanding question for the TaxDev Team – as discussed in Section B – is whether they can do even more to increase the sustainability of their impact through smarter capacity building. In 2025, to address this issue, TaxDev has implemented a new Sustainability Checklist tool to help inform decisions around providing support to TPUs, introduced a new Skills Development Working Group to develop a range of standardised training materials, and collaborated closely with the IMF/World Bank on their ongoing engagements in TaxDev Countries.

Equity. TaxDev has an opportunity to improve the equity of tax policies by supporting TPUs to consider equity in the policy design process There is some evidence of this in TaxDev’s work in 2025 – for example research in Uganda into the progressivity (or not, as the case may be) of VAT exemptions – but this is an area where TaxDev can improve in 2026.
Based on this assessment, the TaxDev III programme continues to represent good value for money to UK taxpayers and should continue. As discussed in Section B – FCDO Posts can improve the VfM of TaxDev III by considering it as part of a portfolio approach to supporting PFM processes in partner countries.

E: RISK

Overview of risk management

Table 2, below, outlines key risks to the programme in 2025, TaxDev III’s mitigation strategy, and FCDO’s judgement of the residual risk. The overall risk rating of the programme is minor on the basis that the programme represents very low reputational and fiduciary risk. As the Table below outlines, however, 2025/26 could be a relatively difficult year for policy & delivery risk given continued expansion to new countries and instability in Rwanda.

Table 2: Key Risks
Risk Description	Mitigation	Residual Risk
Expansion to Kenya and Nigeria is poorly executed or delayed. Setting up new partnerships is difficult and time consuming. There is a risk that TaxDev resources become too stretched and/or that the expansion into Kenya/Nigeria ends up offering poor value for money. Both Kenya and Nigeria have seen recent protests related to proposed tax changes and cost of living pressures.	TaxDev have recruited a new Senior Project Manager, Project Manager, Country Economist, two Senior Technical Advisors, and two Research Assistants. Updated country planning & reporting procedures have been introduced to streamline work. TaxDev teams are closely monitoring the protest situation/willingness to engage in reform in both countries.	Moderate. Set up in Kenya and Nigeria is still at a very early stage with considerable uncertainty. Something to watch closely.
Political and security situation in Rwanda. The UK has suspended most direct bilateral financial aid to Rwanda. Rwanda has severed diplomatic ties with Belgium.	TaxDev and FCDO Kigali are in regular contact.	Moderate. A fast-evolving situation which is hard to predict.
Challenging fiscal situation in partner countries. As discussed in detail in section B & Box 1, fiscal challenges can undermine countries efforts to raise Tax-to-GDP with TaxDev support (as seen in Ethiopia).	This can best be mitigated by FCDO Country Offices engaging with TaxDev and treating it as part of a wider portfolio of support on PFM.	Moderate.
Reductions in ODA budgets. The UK has announced significant ODA cuts. USAID has been abolished. This creates significant uncertainty for partner governments and for TaxDev.	Regular communication with FCDO and Partner Governments.	Moderate.
TaxDev is ineffective in building capacity for the long-term. Staff in partner institutions are not always able to effectively engage in skills development and contribute to policy outputs due to lack of time, resources, as a result of staff turnover, or because the activities are not of sufficiently high priority. There is a risk that TaxDev ‘fills a gap’ in analytical capacity but doesn’t build capacity for the longer term.	Careful planning of TaxDev activities to ensure that TPUs are delivering core activities, and that TaxDev’s support is built around this everyday work of the units, helps ensure that work is sustainable. TaxDev III will also focus on the strengthening of tax policy expertise and analysis outside of TPUs through – for example – collaboration with local researchers.	Moderate. Recommendations from several Annual Reviews have focused on the need to continually strengthen TaxDev’s capacity building work.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summary

FCDO is the sole funder of the TaxDev III programme. During this reporting period, Nigeria and Kenya were selected as the two additional countries. Nigeria: A Country Economist has started working based in Abuja, embedded within the Technical Service Department in the Ministry of Finance. A Senior Technical Adviser for Nigeria has been recruited and is working remotely but will make periodic visits to Abuja to ensure close collaboration. Kenya: In June 2025 a part-time Senior Technical Adviser was appointed and the process of recruiting a Country Economist was underway.

Finance

The approved budget in the TaxDev III Business Case is £15,000,000. For FY 2024-2025, total spend was £1,702,110, of which Country Programmes was £1,287,653 and the Research component £414,457.

ODI Global and IFS are paid quarterly in arrears based on actual expenditures. Forecasting quarterly accruals can be difficult as both partners must wait until staff timesheets are submitted and reviewed, and their books for the period can’t be closed until they have received all receipts and invoices. With the arrival of the Senior Project Manager covering both IFS and ODI Global, the finance reporting has greatly improved to meet deadlines. FCDO has regular discussions / communication with the partners to keep the forecast updated as it changes frequently. Payment requests are normally received 6-8 weeks after the end of the quarter. There are currently no concerns around financial performance. Clear and accurate financial reports are submitted quarterly with the payment requests. IFS/ODI Global financial systems are robust and provide confidence that FCDO funds are allocated and spent as per agreed work plans. At the time of writing the Annual Audited Statements for IFS are up to date.

Reporting

FCDO has regular meetings with the TaxDev programme team and the Steering Committee meets twice a year. Detailed minutes are recorded of programme team meetings (attended by PFTD regional advisers and TaxDev in-country teams) which obviates the need for partners to produce an annual report for TaxDev. Detailed documents with updates and progress are also produced for the Steering Committee.

FCDO continues to maintain an effective and well-established partnership with IFS and ODI Global, who continue to be strong implementing partners and are responsive to ad hoc requests for information. IFS/ODI Global work closely with other development partners and country offices, keeping them informed of their activities and workplans. They have also built good relationships with officials in partner governments, as confirmed by feedback from FCDO Country Offices.

Risks

The delivery chain risk map was updated by TaxDev at the start of Phase III, and the risk register is a standard item at the programme team meetings, along with safeguarding and counter-fraud and anti-bribery. There have been no reported cases of concern (see previous section for risks).

Assets
There are a few assets which continue to be used from Phase II (6 laptops and a projector). TaxDev keep the Asset Register up to date.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Throughout 2024/25, the TaxDev programme was managed by a Senior Responsible Owner and Programme Manager in the UK and monitored by FCDO Regional Advisors based in Kigali and Accra.

This Annual Review was led by an FCDO Economic Advisor from one of the core countries supported by TaxDev. The Advisor was familiar with the programme but not involved in day-to-day management of TaxDev. The Annual Review involved interviews with Tax Policy Units in Ethiopia, Ghana, and Uganda.

Evidence

A large amount of evidence was produced by the TaxDev III programme this year, with most of it documented in Section C (Output 4) and Annex A.

Learning

The TaxDev III Teams have internal learning mechanisms, such as a cross-country monthly meeting for country teams to compare activities. Evidence of this cross-country learning was seen in practice; for example, work on Ethiopia’s Tax-to-GDP ratio informing subsequent work in Uganda. The TaxDev website published several blogs demonstrating lessons learned from TaxDev activities, such as the development of tax expenditure reporting mechanisms.

Date of last narrative financial report	1 May 2025	Date of last audited annual statement	31 December 2024

Annex A – Research Deliverables and Outputs

Output 4.2 Number of reports or working papers published on the TAXDEV website
Date	Authors	Title
08/2024	Anne Brockmeyer / Francisco Garfias / Juan Carlos Suárez Serrato	The Fiscal Contract up Close: Experimental Evidence from Mexico City
9/10/2024	Abdul Malik Iddrisu / Martin Miklos / David Phillips / Daniel Nuer / Edward Abrokwah / Benjamin Kamal Chackson / Manzi Abdulai / Nana Ama Kwakyewaah Asumah / Tom Blanchard	Survey of the Ghanaian Tax System
23/10/2024	Vedanth Nair / Ross Warwick	African Tax Administration Forum (ATAF) 2024 Environmental Tax Handbook / Chapter 2: The African Context / Chapter 7:Reforms to African Motoring Taxation
12/11/2024	François Gerard / Joana Naritomi / Joana Silva	Cash Transfers and the Local Economy: Evidence from Brazil
12/11/2024	Kyle McNabb / Ronald Davies / Miroslav Palanský	IGC Working Paper You can't tax what you can't see: Using fixed cargo scanners to combat tax evasion
18/11/2024	Antonella Bancalari / Juan Pablo Rud	Resource windfalls, public expenditures and local economies
11/02/2025	Ross Warwick / Abdul Malik Iddrisu / Vedanth Nair / David Phillips / Yani Tyskerud / Edward Abrokwah / Daniel Nuer / Seth Akuffo Anoff	A review of Ghana’s value-added tax (VAT) system
03/2025	Pierre Bachas / Anne Brockmeyer / Roel Dom / Camille Semelet	Effective Tax Rates, Firm Size and the Global Minimum Tax

Output 4.3 Number of papers submitted to peer-reviewed journals
Date	Authors	Title
Winter 2024	Pierre Bachas / Anders Jensen / Lucie Gadenne	Tax equity in low- and middle-income countries / Accepted and published at Journal of Economic Perspectives
02/2025	Anne Brockmeyer / Magaly Sáenz Somarriba	Electronic Payment Technology and Tax Compliance: Evidence from Uruguay's Financial Inclusion Reform / Accepted and published at American Economic Journal: Economic Policy. / Already included as submitted in Project Completion Review in June 2023. Now accepted and published.
TBC	Anne Brockmeyer / Alejandro Estefan / Karina Ramirez / Juan Carlos Suárez Serrato	Taxing property in developing countries: Theory and evidence from Mexico / Revise & Resubmit, American Economic Journal: Applied Economics
Forthcoming	Joana Naritomi / Tsogsag Nyamdavaa / Stephanie Campbell	Enlisting Consumers in Tax Enforcement: A Policy Review / Forthcoming, National Tax Journal
Forthcoming	Pierre Bachas / Anne Brockmeyer / Pablo Garriga / Camille Semelet	The Impact of COVID-19 on Formal Firms: Lessons from Administrative Tax Data / Forthcoming, Journal of Development Economics
Forthcoming	Abdul Malik Iddrisu	On the relationship between corruption perception and tax morale: Does natural resource abundance matter?” / Forthcoming, Comparative Economic Studies

Output 4.4 Blogs, policy briefs and digital media published on TAXDEV website and externally
Date	Authors	Title
21/05/2024	Romal Sanjeeda / Bálint Ván / Harshil Parekh	Rwanda publishes its sixth tax expenditure report
17/06/2024	Kyle McNabb / Laura Abramovsky / Tom Hart	The problem with tax potential estimates – key considerations to develop sustainable tax systems
10/07/2024	Laura Abramovsky / Hazel Granger	Look beyond the tampon tax: alternative solutions to close gender gaps
29/08/2024	Kyle McNabb	Ugandan Ministry of Finance, Planning and Economic Development publishes tax expenditure report for 2022/23
02/10/2024	Israel Bikorimana / Harshil Parekh / Romal Sanjeeda	How Rwanda embedded tax expenditure reporting: 7 key lessons for practitioners
09/10/2024	Abdul Malik Iddrisu / Martin Miklos / David Phillips / Dan Nuer / Edward Abrokwah / Benjamin Kamal Chackson / Manzi Abdulai / Nana Ama Kwakyewaah Asumah / Tom Blanchard	Survey of the Ghanaian Tax System
14/10/2024	Edris Seid / Ben Waltmann / Richard Hughes	Ethiopia publishes its first National Medium-Term Revenue Strategy
23/10/2024	Hazel Granger / David Phillips / Kyle McNabb	Reform or Replace? Three country perspectives on the use of tax incentives for structural transformation
16/01/2025	World Bank, IFS, ODI Global	6th World Bank IFS ODI Public Finance Conference Driving Progress: Public Finance and Structural Transformation / Conference Proceedings
04/02/2025	Antonella Bancalari / Juan Pablo Rud	How Peru transformed natural resource wealth into local economic development / Article for VoxDev
11/02/2024	David Phillips	Ghana publishes major new VAT report
24/02/2025	TaxDev	TaxDev collaborating with Government of Ghana on VAT, customs, and distributional analysis / 3 videos with RPD colleagues sharing information about our collaborative work.
31/03/2025	Joana Naritomi / Maria Trobat I Castelltort	Enlisting Consumers in Tax Enforcement: A Policy Review
17/04/2025	Alexandra Readhead / Agustin Redonda / Christian von Haldenwang / Giovanni Occhiali / Hazel Granger	FfD4 Countdown: A Watered-Down Proposal on Tax Expenditures Risks Undermining Countries’ Domestic Revenue Mobilization / Article for Council on Economic Policies (CEP) blog.

Output 4.5 Number of invitations to present or participate in relevant research and policy conferences
Date	Event/conference	Presentation(s)
03/05/2024	Sefaz-SP Tax Gap Seminar - online	Martin Miklos presented '"Methodologies and implementations of the Tax Gap".
08/05/2024	CEP-ATI ATI Follow-up Technical Meeting on Tax Expenditures (Asia) - Nepal	Ben Waltmann presented "Indirect Tax Expenditure Reporting".
17/05/2024	Wealth-related taxes in low- and middle-income countries - online	Laura Abramovsky presented "Wealth-related taxes in low- and middle-income countries" at an online meeting of officials from the BMZ and GIZ.
21/05/2024	Rwanda Economist Working Group - Kigali	Balint Van and Harshil Parekh were invited to present on the findings of latest tax expenditure report and interpreting it for policy purposes.
05/06/2024	FCDO Community of Practice - online	Balint Van and Harshil Parekh presented at the FCDO Community of Practice on Rwanda-TaxDev experience with tax expenditures reporting, focusing on the process, sustainability and capacity building strategy.
20/06/2024	Community of Practice on research and policy in Gender and Tax (CoPGT) - online	Laura Abramovsky presented on gender inequalities in income, paid and unpaid work and its interaction with fiscal policy at the first official general meeting of the Community of Practice on research and policy in Gender and Tax
25/06/2024	Oxford Conference on Business Taxation - Oxford	Jakob Brounstein presented his paper “The three body problem: Ecuador’s tax on tax haven ownership”
21/08/2024	International Institute for Public Finance (IIPF) Annual Conference 2024 - Prague	Jakob Brounstein presented his co-authored paper "Tax noncompliance penalties: Optimality, evidence" in the session "Optimal Taxation: Enforcement Frictions".
21/08/2024	International Institute for Public Finance (IIPF) Annual Conference 2024 - Prague	Vedanth Nair presented his co-authored paper "Why Are The Rich More Sensitive To Tax Rates? Evidence From Mexico City" at a session on "Taxing Wealthy Individuals".
22/08/2024	International Institute for Public Finance (IIPF) Annual Conference 2024 - Prague	Kyle McNabb presented his co-authored paper "Personal Income Tax Reforms and Income Inequality in African Countries" at a session on Cross-Country Analysis of Inequality.
23/08/2024	International Institute for Public Finance (IIPF) Annual Conference 2024 - Prague	Kyle McNabb presented his co-authored paper "The Dynamics of Formal Employment During and After the Covid-19 Pandemic in Uganda" at a session on Public Finance During the Pandemic.
10/09/2024	Community of Practice on Gender and Tax (CoPGT) presentation - online	Laura Abramovsky presented “Gendered fiscal incidence analysis and tax-benefit microsimulation models: Overview, opportunities, and caveats”.
03/09/2024	GIZ Expert Panel: How to Tax the Super Rich - online	Hazel Granger joined an expert panel to discuss how to tax the super-rich hosted by Dr Günther Taube, GIZ’s Head of Sector Programme Good Financial Governance, and attended by over 50 GIZ advisers. Hazel’s insights covered the role of domestic tax policy, especially in lower income countries in taxing the rich for domestic revenue mobilisation and tackling inequality. Also contributing to the discussion was TaxDev Senior Research Associate, Laura Abramovsky.
24/09/2024	DaTax Lab Launch – Washington DC	As part of the World Bank's 2024 Tax Data Analytics Week, the TaxDev team contributed to discussions at the launch of the DaTax Initiative, a cutting-edge tax data laboratory that uses tax microdata -such as tax records and firm-level filings- to address critical global policy challenges.
26/09/2024	6th World Bank/IFS/ODI Public Finance Conference: Driving Progress: Public Finance and Structural Transformation - Washington DC	François Gerard presented "Mitigating the consequences of job-loss in low-income countries: Experimental evidence from Ethiopia" as part of a session on the public finances of pensions and social protection.
22/10/2024	Workshop in honor of David Card - Barcelona	François Gerard presented "Mitigating the consequences of job-loss in low-income countries: Experimental evidence from Ethiopia"
23/10/2024	KOF Swiss Economic Institute at ETH Zurich Seminar - Zurich	François Gerard was invited to present on "Formal Employment Dynamics and Economic Development"
06/11/2024	Oxford CSAE Lunchtime Seminar - Oxford	François Gerard was invited to present on "Formal Employment Dynamics and Economic Development"
30/10/2024	VATT Institute for Economic Research - Helsinki	Jakob Brounstein presented his paper “The three body problem: Ecuador’s tax on tax haven ownership"
19/11/2024	Oxford CSAE Research Workshop - Oxford	Jakob Brounstein presented his paper “The three body problem: Ecuador’s tax on tax haven ownership”
03/12/2024	Enhancing Fiscal Policy Coherence: Data and Statistical Frameworks and Institutional Collaborations – New York	As part of the Second Session of the Preparatory Committee for the Fourth International Conference, Hazel Granger was invited to speak at a UNDP side event examining how data and statistics can strengthen public finance’s development impact.
03/12/2024	University of Barcelona presentation - Barcelona	Jakob Brounstein presented “The three body problem: Ecuador’s tax on tax haven ownership”
06/12/2024	University of Toronto presentation - Toronto	Jakob Brounstein presented “The three body problem: Ecuador’s tax on tax haven ownership”
16/12/2024	9th Zurich Conference on Public Finance in Developing Countries - Zurich	Vedanth Nair presented "Are the Rich more Sensitive to Taxes? Evidence from Mexico City"
17/12/2024	9th Zurich Conference on Public Finance in Developing Countries presentation - Zurich	Jakob Brounstein presented his paper “The three body problem: Ecuador’s tax on tax haven ownership”
4/01/2025	American Economic Association's (AEA) Annual Meeting 2025 – San Francisco	François Gerard presented "Access to Justice and Social Protection" at a paper session on Social Protection in Low and Middle Income Countries.
23/01/2025	Skatteforsk - Centre for Tax Research seminar - Ås	Jakob Brounstein presented titled "The three body problem: Ecuador's tax on tax haven shareholdership"
30/01/2025	2025 Dialogue on Public Finance and the SDGs – New York	Hazel Granger was invited to present at the "Plenary Session: Public Finance for Climate, Nature, Governance and Crisis Contexts"
31/01/2025	Université of Aix-Marseille seminar – Marseille	François Gerard presented "Mitigating the consequences of job-loss in low-income countries: Experimental evidence from Ethiopia"
03/02/2025	Oxford University Centre for Business Taxation - Oxford	Jakob Brounstein was invited to present his paper titled "The three body problem: Ecuador's tax on tax haven ownership"
10/02/2025 12/02/2025	Wilton Park: Simplification and Digitisation of Tax Systems for the Commonwealth – West Sussex	Yani Tyskerud was invited to (i) facilitate a panel on rate rationalisation and rate structures, and (ii) participate in a panel providing reflections from academics and researchers about tax simplification efforts.

Output 4.7 Number of local and international research seminars organised by TaxDev to facilitate engagement with networks of tax policy experts and researchers
Date	Location	Event/conference	Attendees/ additional information
23/08/2024	Prague, Czechia	International Institute of Public Finance's (IIPF) 80th Annual Congress	At IIPF 2024 TaxDev held a Special Session titled ‘The taxation of wealth in low- and middle-income countries (L&MICs): What does the evidence tell us, and what are the gaps?’
25/09/2024	Washington DC and online	Pre-Conference Side Events: The Business of Taxing Businesses in East Africa	The event brought researchers and policymakers together for comprehensive and practical discussion about the promises and pitfalls of business taxation in Low- and Middle-Income Countries, particularly in East Africa.
26/09/2024- / 27/09/2024	Washington DC and online	6th World Bank/IFS/ODI Public Finance Conference | Driving Progress: Public Finance and Structural Transformation	The 2024 Public Finance Conference brought together leading researchers and policymakers to discuss how public finance policies in low- and middle-income countries needed to adapt to structural changes driven by economic growth, including tax, fiscal, and labour market policies, as well as the design of pension systems. Key topics included growth-oriented tax policies, industrial policy, addressing informality, and promoting formalisation. / The conference proceedings are here.
19/11/2024	Johannesburg	CABRI/ODI Global International Conference on Public Finance in the Digital Era - Johannesburg	At the International Conference on Public Finance in the Digital Era, TaxDev held an event titled ‘Strengthening Policy Analysis and Research Through Tax Data Labs: Insights from South Africa and Uganda’
03/12/2024	New York and online	United Nations Second Preparatory Committee of the Financing for Development Conference	TaxDev co-organised a side event at the Second Session of the Preparatory Committee for the Fourth International Conference on Financing for Development titled ‘Leveraging Personal Income Taxation for Sustainable Development’ to bring together academic and policy experts to discuss innovative personal income taxation (PIT) reforms are essential for financing sustainable development and achieving the Sustainable Development Goals.
16/12/2024 -17/12/2024	Zurich	9th Zurich Conference on Public Finance in Developing Countries	The 9th Zurich Conference on Public Finance in Developing Countries brought together leading economists working on public economics in low- and middle-income countries.
31/01/2025	New York	2025 Dialogue on Public Finance and the SDGS - Plenary Session	At the UNDP’s 2025 Dialogue on Public Finance and the SDGs TaxDev co-organised, with UNU-WIDER and UNDESA, a side event titled ‘Data and Statistics for Development-focused Public Finance’.