## Annual Review Template

Title: Integrated Programme for Strengthening Security and Justice– Phase 2 (IP-SSJ 2) / Shortened to: Security and Justice Programme (SJP) in May 2023
Programme Value £ (full life): up to £35m		Review date: March 2025
Programme Code: #300955	AMP start date: 12 April 2022	AMP end date: 31 Dec 2027

Summary of Programme Performance
Year	22-23	23/24	24/25
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Security and Justice Programme (SJP), originally called the Integrated Programme for Strengthening Security and Justice phase 2 (IPSSJ2), is FCDO Nepal’s flagship initiative to deliver on Country Plan Campaign Goal Outcome 2.4: developing more representative and accountable security and justice institutions that respect human rights, tackle gender-based violence (GBV), and address exclusionary practices that fuel grievances. With a £35 million commitment until 2028, the Business Case also set an aim to supports the peaceful devolution of policing in Nepal’s transition to federalism, and prevention and response to GBV in four provinces (Madhesh, Lumbini, Karnali and Sudurpaschim), alongside federal level engagement.

SJP builds on over two decades of UK engagement with Nepal Police and lessons from IPSSJ Phase 1, which reached over 4.6 million people and significantly contributed to improving Nepal’s rule of law scores. The programme now takes a more integrated approach – linking police reform, governance and GBV prevention – while aligning with the UK’s global commitments under the International Strategy on women and Girls and the 2023 International Development White Paper.

SJP is implemented for FCDO in Nepal through two major partners – UNOPS and People in Need (PIN). UNOPS lead the work on police reform, professionalism and performance management, inclusion, retention and promotion of women police officers in the workforce and infrastructure improvements through designing and delivering Women, Children and Senior Citizens Service Centres (WCSCs). PIN supports the community-based and social norms component, focusing on shifting harmful attitudes and behaviours that enable GBV through Gender Transformative Social Norms (GTSN) pilots as well as platforms like the Girls Inclusive Education Networks (GIENs).

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This review: A team comprised of an independent consultant with peace and security expertise and an Education Adviser from British Embassy Kathmandu (BEK) undertook this third Annual Review (AR) in March 2025. The review period is April 2024 to April 2025. The review draws on interviews with the Nepal police (NP), government stakeholders at federal, provincial and local (including palika, ward, and tole) levels, delivery and downstream partners, other development partners, and a small number of community beneficiaries, as well as a review of progress reports and deliverables. The AR reviewed the first full year of implementation of the multi-year programme, following the launching phase in 2023. Under the guidance of the SJP senior responsible officer (SRO), the review team focused on the integration and internal coherence of the programme components, the quality of the theories of action (ToA) developed as part of SJP’s integrated adaptive results framework (ARF), and recommendations for continued integration of SJP’s delivery, adaptation, and learning.

Key findings: Between April 2024-25, SJP placed commendable effort on designing an adaptive programme, intentionally creating the structures and building the programmatic culture needed to effectively grapple with complexity, understand behaviour change, and learn and adapt through its delivery. The process of developing an ARF served two interlinking objectives – 1) to integrate the two programme components on police reform and harmful social norms; and 2) to articulate theories of action that more realistically represented the ambition of the programme and the realities of working on complex issues within Nepal. This process of integration proved challenging, however, for a number of reasons:
1. The ARF was developed following the submission of two separate proposals UNOPS and PIN for their respective multi-year agreement (the latter in a mini-competition amongst five INGOs for an accountable grant). This was, prior to the creation of the new intermediary outcomes (IO). Both proposals contained their own separate, and more traditional theories of change (ToC), based on their understanding of the distinct problem sets facing police reform and social/gender norms.
2. The process of integration and the development of the ARF had to bring together two partners with very different networks, operating models, visions for delivery, and understanding of adaptive approaches. These differences resulted in uneven buy-in to the process.
3. Ultimately, the process also happened alongside continued delivery, resulting in some opportunities being missed by one or both partners for better integration, alignment, and sequencing of activities.
Despite these challenges, the integration/ARF process has arrived at a more unified understanding what SJP is doing and why, and has resulted in better coordination across partners. The year ahead will be the ultimate test of progressing from coordination to collaboration (joint planning and implementation)to deliver complementary and cohesive outputs and contributions to IOs.

SJP enjoys strong relationships with NP at Headquarters (HQ) and at provincial and district levels. However, activation and proper functioning of the governance arrangements remains a challenge, though this does not appear to be unique to SJP and was echoed by other DPs working with the same designated line ministries. Despite BEK senior leadership engagement to push for the activation of SJP’s National Steering Committee (NSC) chaired by the Secretary of Ministry of Women, Children and Senior Citizens (MoWCSC), it has yet to convene. This is largely due to the multiple transfers of key officials in one or both lead line ministries (MoWCSC and Ministry of Home Affairs – MoHA). The risk of continued delays and avoidance among key parts of the GoN apparatus is high. The BEK team, in collaboration with delivery partners, is actively tracking this risk and seeking to address it. The monitoring, evaluation, and learning (MEL) framework designed to deliver on SJP’s adaptive approach creates a platform for analysing such risks and making tough decisions.

While there has been a mixed achievement of output targets, with some areas of slight underperformance as described in greater detail in Section C, the overall score of “A” reflects: 1) the output weightings as per the table below for this stage of the programme; 2) SJP’s commendable investments in establishing adaptive structures that will better enable understanding of, and contribution to, meaningful change in the longer term; and 3) the review team’s confidence in these structures to address challenges and areas of underperformance, and learn (reasonably quickly) from its successes and failures. Based on the Good Practice Note for Adaptive Annual Reviews, the score takes into consideration the four key areas of focus for adaptive programmes:

Delivery	Output Score Weighting / 1 B 10% / 2 A 30% / 3 A 20% / 4 B 20% / 5 A 10% / 6 B 10% / As described in Section C, Outputs 2, 3 and 5 met expectations, with slight under-delivery for Outputs 1, 4, and 6. Some of this under-delivery reflects the nascent nature of the ARF, which was only just finalised during the field trip for this AR. Time is still needed for SJP to arrive at milestones that reflect the pace of delivery across two very different partners, the proper sequencing and layering of interventions, and changes within the socio-political context.
Actionable Learning	Through the development of the ARF and associated MEL framework, SJP has an established platform for generating evidence and reflecting on learning. This review highlights some recommendations to strengthen this platform as it becomes fully operational in 2025.
Contribution to Meaningful Change	As highlighted in Section B, it is too early in implementation to see concrete evidence of linkages between output delivery and SJP’s intermediary outcomes. SJP has the systems in place to actively reflect on these linkages and measure behaviour change of key actors. The next year of the programme will need to test if these systems are functional and provide the evidence and insights needed for adaptation and contribution analysis.
Fitness for Purpose	Based on the above three areas, SJP remains fit for purpose. Its political astuteness and BEK’s strong engagement in tracking strategic threats and opportunities gives sufficient confidence that the programme can respond to a dynamic and evolving context. If the MEL framework can be operationalised to drive forward decision-making and delivery, SJP will remain relevant in a context where police behaviour and the existence of harmful social norms play critical roles in Nepal’s ability to respond to and prevent GBV.

Major lessons and recommendations for the year ahead [1/2 page]

Lesson 1: Integration and internal coherence / Integration of the two programme components was a key focus of the period under review, following on from the recommendation of the previous AR. Investing resources in this process of integration, primarily via the development of an integrated theory of action (ToA) and associated results framework, was the right decision. Complex programmes like SJP need to be intentionally adaptive, and SJP has made significant progress over the review period in developing ToA and sub-ToAs that provide narrative to how programme components contribute to the four IOs. This process has helped SJP transition from two separate components to a more cohesive understanding of what SJP is doing, and why. Integration is still very nascent, however; a reflection of the long process of arriving at ARF, notably a delay in PIN’s appetite to evolve its original proposal. / Significant appreciation of this process was expressed by SJP partners, but how the ARF will practically drive strategic decision-making and delivery remains a work in progress. It will require continued investment in ensuring that the culture of adaptation, the focus on behaviour change, and the drive towards effectively integrated results is well understood across the full delivery chain, from Kathmandu to field levels – the downstream partners need additional guidance around the adaptive requirements of this programme. It is now urgent to consider the practicalities of ensuring that the ARF and MEL frameworks are able to effectively drive programme delivery and decision-making, as opposed to being limited to monitoring and evaluation purposes. The process now underway to convene six- monthly Pause and Reflect sessions should help this.
Recommendation 1.1: Ensure that there is a clear approach to operationalising the ARF as a driving force of delivery and decision-making. This includes a practical and cohesive approach (across the SJP triangle – BEK, PIN and UNOPS) to identifying if an intervention is not working, a clear timeline for making decisions to adapt or stop the intervention, and a process for if and how changes to the ARF can be made in support of adaptation. For example, if a rubric milestone is not met, what happens next, in what timeline, with what evidence and justifications? This approach also needs to cascade to downstream partners. The numbering of the MEL framework output and rubric also needs to be checked and clarified to avoid risks of confusion and duplication in reporting.
Responsible: SJP triangle – SRO and PRO alongside delivery partner leads	Target date: Q1 2025
Recommendation 1.2: Continue to invest in the culture of integration and adaptation across the SJP triangle. This will include continuous capacity building across the delivery chain to understand how behaviour change happens, and how the MEL framework can be used to shape design and delivery of interventions, as well as measure and test the effectiveness of those interventions. BEK should consider if sufficient capacities exist across the delivery partners, or if additional resources are needed to ensure an even and robust approach to adaptive management.
Responsible: SRO	Target date: Q1 2025

Lesson 2: Streamlining and refining strategic focus / While the process of integration has supported critical decision-making on what is and is not in scope within SJP, additional opportunities for streamlining remain. The process of integration that occurred over the period under review has also seen some missed opportunities to be better aligned. The current ODA environment reinforces the importances of streamlining, and presents an opportunity to engage critically in defining a more narrow and refined focus of SJP. Decisions on streamlining, alignment of approaches, and narrowing of strategic focus should consider: / Better aligning areas of operation and targeted participants: for example, how school selection by PIN is informed by WCSC proximity, and how SARA and GTSN participants could be expected to integrate. / Deeper integration of CDEL and RDEL support: with a particular focus on integrating PIN’s ‘soft-side’ (RDEL) support with the UNOPS infra (CDEL) and RDEL. / Clearer articulation of locale- and institution-specific GBV-related problems: PIN currently takes a wide-net somewhat untargeted approach to its engagement with coordination bodies and at-risk women and girls communities. This approach could lead to inefficiencies if it does not quickly refine/narrow target at-risk groups and develop tailored engagement strategies, based on assessment of the potential scope to reduce GBV. This could perhaps be done in closer coordination with the concerned WCSCs.
Recommendation 2:1: The work planning process for 25/26 (with revised ODA numbers) should be seen as a forcing point for SJP partners to identify clear areas of alignment and focus, to address some of the missed opportunities from the previous year. For example: 1) PIN should be encouraged to include close proximity to WCSCs as a selection criterion in identifying target schools for GIEN activity and target communities for GTSN, to better bridge work under Outputs 5 and 6; 2) UNOPS should be encouraged to consider how to engage on harmful gender norms within the police in the delivery of Outputs 1 and 2; 3) both partners should be intentional in aligning, where possible, soft-side support to the CDEL investments, specifically the WCSC.
Responsible: SJP delivery partners	Target date: Q1 2025
Recommendation 2.2: Equally, the workplan should demonstrate critical attention to how interventions will sequence and layer onto each other, leaning into learning from IPSSJ that layered interventions yield greater impact in the longer run. This may require pausing of certain activities, to allow for an approach that builds on interventions as opposed to running in parallel. One priority should be for PIN to reassess its ward and school selection criteria to better align with WCSC locations and maximise layered impact. For example, could complaint response mechanisms (CRMs) in schools be better linked into WCSC functions and outreach to help ensure they are trusted and effective for GBV-related concerns? Attention to sequencing could result in changes to the rubric and milestones, which should also be reflected in updates to the ARF.
Responsible: SJP delivery partners	Target date: Q1 2025
Recommendation 2.3: PIN should develop a more problem-driven approach to its engagement with CBOs and GBV coordination structures. Within each local government unit, it should use research, including from its own launching phase, to articulate the key at-risk groups per locality, and justify why coordination structures were selected in relation to these specific at-risk groups. In some localities, this may require pivoting away from the GIEN approach to other structures or mechanisms that are better placed to address specific risks. It will also be important for partners to understand public financial management rules and procedures so as to engage effectively to influence allocations by LGs for response (e.g. the GBV elimination fund) and prevention (other discretionary funds) and spread these impacts through the local government system.
Responsible: PIN with guidance from PRO	Target date: Q1 2025

Lesson 3: External coherence / SJP has placed strong emphasis on building external coherence, and touchpoints and leveraging points have been identified across the BEK portfolio and other DPs. The programme has mapped similar programmes operating in the same provinces as SJP and has organised meetings both at federal and local levels to learn more about other BEK portfolio and other DP programmes operating in similar locations and/or with similar stakeholders. The programme now needs to move to implementation in practice, again focused on operationalising those touch and leverage points. Creating complementarity and finding ways to fill critical gaps that SJP is not able to address becomes even more important as the programme enters a year of likely reductions to ODA spend within Nepal. / The programme could further strengthen its linkages to other development partners that are implementing initiatives tackling gender norms, GBV prevention and work on inclusive education through GIENs, including those funded by the EU (UNICEF, UNFPA, etc.) , VSO, Save the Children etc. Equally, additional linkages to livelihoods programming (in support of GBV prevention), demand-side accountability programming (in support of mobilising public demand for service delivery), and access-to-justice programming (linking security to justice responses to GBV) could enhance coherence and complementarity. Though it is noted that these initiatives outside SJP may not have incentives to link up with the programme. / Additionally, how SJP thinks about coherence now needs to reflect the significant gaps left in the wake of USAID’s abrupt closure, and the decreasing investment globally in foreign development assistance. Coherence with GoN planning and budget processes is also critical. Aligning the sequence of SJP’s interventions to local government budget planning and NP’s work planning processes is essential for strengthening the sustainability of efforts and catalysing wider systems change.
Recommendation 3.1: Delivery partners should update coherence maps to include identification of any additional programming on gender norms, livelihoods, demand-side accountability, and access-to-justice operating in similar locations to SJP. The strength of linkages to these complementary thematic areas should also be considered within SJP’s ToC/ToA assumptions, as well as its risk register, to inform reflection on SJP’s ability to link, or not, with others working on critical gaps within wider reform efforts and support to GBV survivors.
Responsible: SJP delivery partners	Target date: Q2 2025
Recommendation 3.2: A rapid assessment on the impact of USAID’s closure on the programme should be conducted, where possible in conjunction with other relevant BEK teams (e.g. in health and education). This assessment should inform SJP’s decision-making for fiscal year 2025, in terms of where it can reallocate resources to fill, however modestly, resulting gaps, or where the gaps will result in major risks to the delivery of SJP’s IOs and outcomes.
Responsible: SJP delivery partners	Target date: Q1 2025
Recommendation 3.3: SJP should also consider how it uses its evidence and learning to influence other DP’s approaches to engaging on issues of GBV and police reform. Learning products can be developed specifically to reinforce the importance of coherence and shared outcomes, and help to align DPs to specific policy influencing goals or programmatic approaches. A learning agenda or influencing strategy could support the development of these products and approaches to engaging other programmes.
Responsible: SJP triangle	Target date: Q2 2025
Recommendation 3.4: UNOPS should focus maximum effort on lobbying for the integration of key priorities into the NP annual plan, especially given the very recent appointment of a new IGP and the imminent Nepali government planning process for its FY82/83. These priorities should be agreed on between UNOPS and BEK.
Responsible: UNOPS	Target date: Q1 2025

Lesson 4: Incentivising behaviour change / SJP’s design, and its newly integrated ToA is informed by a wholistic understanding of behaviour change (the COM-B model). To ensure that this ToA translates to delivery, investment in cascading this understanding of how change happens across the full delivery chain is critical. Equally, greater attention will need to be drawn to how to incentivise, or motivate, behaviour change. The M of the COM-B model is notoriously difficult to programme for, but without it, change will never be institutionalised. Change agents can play a critical role in this process – identifying who has leverage or influence within the systems under reform, and working with and through them, can result in more sustainable enablement of these systems going forward. Change agents can range from influential and reform-minded police personnel (e.g. in WCSCs), to journalists who can mobilise public pressure, to local leaders and/or CBOs who are already pushing back against harmful social norms. While SJP partners demonstrate an understanding of who these change agents could be, this review did not see a structured approach to their engagement.
Recommendation 4.1: Delivery partners should reflect critically on what capability (C), opportunity (O), and motivation (M) gaps exist within the key actors they are targeting, and how interventions will address these gaps, during the work planning phase for 2025. For example, can role models from coaching programmes be deployed to incentivise uptake of Women in Policing changes? Can adolescent participation in GIENs be better institutionalised through leadership training and student sub-committees? Conducting simple COM-B change frame exercises can be a helpful process as part of the workplan development.
Responsible: SJP delivery partners	Target date: Q1 2025
Recommendation 4.2: Informed by systems-thinking, delivery partners should increase their focus on engaging change agents, understanding who has influence with which target audiences, and how SJP can support these change agents to further incentivise more effective responses to and prevention of GBV. Change agents can be individuals or influential groups.
Responsible: SJP delivery partners	Target date: Q1 2025

Lesson 5: Evidence-to-influence chain / Linked to the above lesson, SJP’s approach to piloting change at local levels can be enhanced by a more structured evidence-to-influence chain. UNOPS is piloting approaches to problem-driven policing via SARA committees at ward level. It is also piloting data-driven approaches to response via the use of a GIS mapping tool. PIN is demonstrating how school complaint response mechanisms can better respond to and prevent GBV within schools. These pilots are focused on change at a local level – within wards, within APOs, within schools. For these pilots to have a catalysing effect, SJP now needs to consider how to evidence change at these local levels and use this evidence to influence the institutionalisation of those changes within wider systems. Arming change agents with meaningful evidence that speaks to the interests and incentives of decision-makers can support their continued efforts to catalyse reform.
Recommendation 5.1: Delivery partners should be resourced and incentivised to expand MEL structures in support of this evidence-to-influence chain. Defining how MEL can also support the external-facing interests of the programme, via a learning or influencing strategy, is an important evolution in SJP’s journey towards behaviour change.
Responsible: SJP triangle	Target date: Q2 2025
Recommendation 5.2: UNOPS should its training inputs against existing NP training to avoid duplication and improve efficiency. For sustainability of impact, the focus must be on influencing (and demonstrating) the curricula of the police organisation.
Responsible: UNOPS	Target date: Q2 2025

Lesson 6: Monitoring, Evaluation and Learning / Significant time and resources have been spent on MEL this past year, which was the right decision. It has resulted in much greater understanding within the programme team of the ‘why’ of delivery and is slowly shifting ways of working, but more time is needed. On the one hand, the current MEL framework needs to be allowed to go forward and test out its ability to measure critical change and drive adaptation, allowing it to also flex and adapt as it learns what is and is not working. On the other hand, opportunities exist to simplify the structure. Because the MEL framework evolved out of two programme proposals and agreements and was trying to bring along partners that were at different stages in mindset and approach, the resulting ARF is complicated and dense. It can be simplified and better aligned. For example, 11 rubric scores exist in the MEL framework, which then translate (somewhat awkwardly) to six outputs in the (newer) ARF. The outcome mapping also contains duplications across key actors, as opportunities for better integration across UNOPS and PIN’s approaches exist. Finally, this review saw opportunities to merge certain outputs within the ARF where overlap has been noted.
Recommendation 6.1: Allow the MEL framework (rubric and outcome mapping) to trial its approaches over the coming quarter, with an openness to adapting the framework and ARF if there are inconsistencies or opportunities for simplification identified. In this regard, SJP should consider: / Full matching ARF output numbering to the numbering of the rubric scores, to avoid further confusion or complication. / Reviewing milestone scores and timelines to adjust ambition where needed and align with annual review cycles and align data collection and reporting mechanisms to report on all indicators within the ARF. / Reflecting on the possibility of merging ARF outputs where overlap exists. This review noted particular overlap across Outputs 3, 4, 5 and 6. Such a reflection should also prompt a revision of rubric scores to also merge and reduce, where relevant. (See also 1.1. above). / Creating a programme learning agenda to guide evidence generation and influence other development partners and GoN
Responsible: SRO, with support from delivery partner MEL teams	Target date: Q2 2025
Recommendation 6.2: Urgently decide on an approach to a survey baseline, to add to the rubric baselines already collected, and ensure that critical data is not missed in support of understanding how change happens. The baseline should inform SJP’s understanding of community and police perceptions, experiences of service-delivery by survivors, and the costs / cost-effectiveness of response mechanisms. This baseline data should also reflect SJP’s understanding of the type of evidence that will influence decision-makers, in relation to the evidence-to-influence chain referenced above.
Responsible: SRO	Target date: Q2 2025
Recommendation 6.3: Develop MEL approaches that better measure the value of CDEL support – in particular the Koshi training centre and the WCSCs under construction. Understanding if and how this infrastructure support, especially if delivered with wrap-around RDEL support, contributes to behaviour change is a critical learning question for SJP.
Responsible: Delivery partner MEL teams	Target date: Q2 2025
Recommendation 6.4:
UNOPS should Develop a results approach for the Koshi Police Training Centre to understand its impact on female police recruitment and training.
Target date: UNOPS by end of Q4 (PTC opening)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Following recommendations from the 2024 annual review, SJP underwent a comprehensive process to provide narrative linkages between its high-level and ambitious outcome and impact statements, and the realities of working on police reform and social norms within the complex political and social realities of Nepal. This process led to an overhaul of the programme’s ToA, resulting in four IO that outline key behavioural shifts needed to contribute to SJP’s overall outcomes and impact. The four IOs are:
- IO1, Women in Policing: Nepal Police achieves a better balance of men and women in its recruitment and promotions
- IO2, Police Professionalism: Nepal Police strengthens its leadership, HR systems, and community informed practices to ensure professional policing standards
- IO3, Communities with Agency: Communities have agency to tackle the perpetration and acceptance of safety concerns including GBV in their communities
- IO4, Collaborative & Responsive Duty Bearers: Drawing on data and evidence, mandated authorities are collaborating effectively on community safety concerns, including GBV prevention and responses
The four IOs map onto the original theory of change annexed to the approved Business Case for IPSSJ2, which stated:
If police is more representative and accountable and better overseen, it will be more responsive to the needs of communities and if the police and local justice mechanisms have better capacity to address public safety problems and better take into account the specific needs and vulnerabilities of women and girls and if men, women, boys and girls have the knowledge, skills and attitudes to prevent and respond to GBV and there is increased capacity of and pressure from wider society to take action to address GBV then there will be increased prevention of GBV and wider public safety problems and there will be increased responsiveness of security and justice providers which will result in increased trust in the state and greater stability.

IO 1 and 2 seek to improve the diversity and professionalism of the police in order to improve responses to safety concerns, specifically of women, girls, and marginalised communities. IO 3 and 4 seek to strengthen community agency and wider society coordination structures, including of duty-bearers, to respond to and prevent GBV. Each IO has a sub-ToA, that breaks down into separate outputs and assumptions linked to the achievement of the behavioural shifts saught by each IO.

While the ToA still links clearly to the original ToC of the approved business case, it provides a much more nuanced narrative of the step changes between inputs, outputs, and outcomes, with a needed emphasis on the behavioural shifts that SJP specifically will contribute to. As such, it represents how the programme has learned from and adapted to recommendations from previous reviews and the challenges faced by its preceding phase, IPSSJ. A noted gap between the previous ToC and the current ToA is the latter’s lack of specific focus on judicial actors, which the programme deliberately decided to move away from in order to allow for streamlining of resources and because significant anecdotal evidence suggests that local government judicial committees are rarely approached in GBV and wider security cases. In addition, the revised IO4 places less emphasis on public pressure to take action on GBV, arguably resulting in a less clear focus across the programme on accountability. It is recommended that SJP provides greater clarity on how communities, within the effort to enhance their agency, will be supported to hold duty-bearers to account, including through the mobilisation of public pressure, within IO3 and 4.

Contribution to meaningful change: describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

SJP’s data collection to assess behaviour change, using outcome mapping, will only be finalised after the deadline for this review, so it is difficult to fully analyse SJP’s contribution to meaningful change at this time. It has also been only 8-10 months since the PIN and UNOPS implementation teams have been in place following the signing of multi-year agreements with BEK in May 2024. The MEL framework has also only recently been finalised, making it very early within the programme lifecycle to assess this change. Therefore, this review considers more specifically the programme’s ability to measure contribution to meaningful change, and to adapt in response to challenges, obstacles, and learning, as well as anecdotal indications of positive shifts in behaviour.

On measuring contribution to meaningful change: SJP have a clear plan in place to measure this, as defined by the outcome mapping framework. Data collection appears robust and allows for triangulation across multiple data sources. The programme team will convene bi-annually to discuss behaviour shifts, via the outcome mapping framework, during pause and reflect sessions. The review team attended an initial such session, which gave confidence that the programme is sufficiently considering how SJP interventions will contribute to change, what challenges they will confront, and how they can and should adapt. As mentioned in the recommendations above, a plan to operationalise how to make adaptation decisions will further strengthen this process.

On indications of positive shifts in behaviour: this review noted several indications of positive behaviour shift among key actors, at least partially linked to sustained engagement by the UK and other DPs in the spaces of police reform and GBV. The NP in particular demonstrated strong willingness to engage with SJP in improving professionalism among police ranks, with select leadership indicating existing initiatives for improvements that represent windows of opportunity for the programme to engage. The programme’s approach to engaging at mid to upper-mid levels within the police is justified, as these individuals are likely to rise within the senior leadership ranks over the tenure of SJP. Equally, community champions indicated a strong desire to amplify their voices in challenging harmful social norms, though the road to societal shifts will be long and patience and tempered ambition is required.

Fitness for purpose: justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above analysis of outcome and output achievement, theory of change and value for money (VfM) analysis, there is sufficient evidence that SJP is fit for purpose. The review team saw strong indication of the importance of addressing harmful social norms in improving the response and prevention of GBV, justifying the tandem approach to engaging police, local duty-bearers, and communities in strengthening service delivery and help-seeking behaviours. The continued integration of the dual components of police reform and addressing harmful social norms, driven by a cohesive understanding of the joint adaptive results framework, will further reinforce the fitness of this programme. There are indications, however, that the efforts of PIN need to be more closely tied to problem-solving change processes that can be sustained beyond the lifetime of the project.

Important to the question of fitness will be SJP’s monitoring and analysis of the political environment, tracking the impact of the Police Act Amendment and changes to NP leadership. The SJP triangle demonstrates aptitude for understanding this political landscape, and its potential impacts on the programme. This approach to thinking and working politically will support SJP’s adaptations and streamlining, which will be especially important in light of the recently announced reductions to ODA.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	NP develops and implement evidence-based, gender-inclusive strategies, programs, and public engagement initiatives to enhance the recruitment, retention, and professional advancement of women within Nepal Police.
Output number:		1	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
1.1 Progress on Development and Implementation of Gender-Inclusive Recruitment, Retention, and Promotion Policies within Nepal Police	Level 2 (Commitment & Planning): Formal commitment from NP leadership to initiate the development of gender-inclusive, evidence-based HR policies.	Moderately did not meet expectation / Level 1 (Initial engagement) achieved. Progress has been made in terms of generating initial buy-in and in-principle commitment from NP leadership. But formal signing of CoP partnership has not yet happened.
1.2 Progress on Development and Implementation of Gender-Inclusive Leadership and Professional Development Programs within Nepal Police	Level 2 (Needs assessment): Identification of specific professional development needs for women within NP, including training, mentoring, and career development opportunities.	Moderately did not meet expectation / Level 1 (Leadership engagement) achieved. NP leadership demonstrate commitment to further explore and take collaborative action for improving the status of women in Nepal Police, though challenges in this commitment are evident. Not yet resulted in a decision to establish a platform for women officers.
1.3 Progress and Quality of Gender-Inclusive Public Outreach Initiatives Across SJP Project Areas	Level 4: Indications of increased female applications into NP intakes in at least 50% SJP supported Palikas	Moderately did not meet expectation / Level 3 achieved. Outreach events were held and suitable female candidates have been enrolled in the coaching programme. Indication of increased applications will not be evident until June, following coaching programme.
1.4 Number of women participants in community events* regarding Women Police recruitment	70 (35 from Karnali and Lumbini province, 35 from Madhesh province)	Substantially exceeded expectation / 465 total. 118 participated in awareness events on NP recruitment process; 62 participated in coaching classes for WiP recruitment; 285 participated in the pre-screening for recruitment coaching.
% of women applicants supported in SJP project areas* who pass the exam	At least 45% out of 70 eligible women pass the exam	Too early to judge: Women are still undergoing coaching curriculum, and figures related to passing the exam will not be available until June.
1.6 Progress on strengthening gender-inclusive police training infrastructure through the construction of a new training centre in Koshi Province	Continued progress along the different stages of construction	Met expectation. / Construction continues along the agreed upon timeframe.

Delivery
Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

UNOPS leads the delivery of this output, linked to IO 1 on supporting the NP to achieve a better balance of men and women in its recruitment and promotions. It has approached the delivery of this output from two lenses – one in terms of strengthening gender-inclusive leadership and retention via engagement with NP HQ’s programmes and policies; the second in terms of demonstrating how to run recruitment drives specific to female candidates. While a high level of activities and interventions have taken place in support of Output 1, the overall score for this output reflects slower than anticipated progress along rubric scores, in part due to the non-convening of the NSC, as well as a slight misalignment of timelines between the AR and the finalisation of certain interventions, such as the coaching sessions for female candidates. This score should prompt a review of the ARF, to ensure alignment of timelines for the 2025 AR, and that rubric scores are flexible to contextual challenges, such as the continuously delayed convening of the NSC.

Over the review period, SJP has secured support from the UK’s College of Policing (CoP) to enter into a multi-year partnership with the NP for mutual sharing of knowledge and experience (which also supports delivery of output 2). While engagement between CoP and NP has commenced and the MoHA Minister has stated his support, the formalisation of the partnership depends on the convening of SJP’s NSC, which has yet to meet since the launch of SJP. This poses a risk to the delivery of a key element of this output, and should prompt a recalibration of how rubric progression is analysed and delivery is adapted if formal signature of the partnership is not achieved. While awaiting signature of the partnership, UNOPS has still managed to organise engagements between CoP and NP in the development of NP’s new Masters in Policing Sciences course, and has helped to enrol one female Deputy Superintendent of Police (DSP) in CoP’s Executive Leaders Programme (ELP).

UNOPS also organised a National Women in Policing (WIP) workshop attended by police officers from NP Headquarters and all seven provinces. Recommendations from this workshop were compiled by UNOPS to help drive forward future initiatives with NP, though challenges remain in securing full buy-in of NP. In addition, UNOPS has led outreach events to raise awareness on the recruitment process of NP for girls/ women, leading to pre-screening events, the procurement of coaching programmes, and candidate preparation for the NP recruitment process. Commendable effort has been made by UNOPS to ensure participation from marginalised communities, including via door-to-door engagement with families of young women eligible for participation. There seems to be opportunity to harness the transformation of the capabilities of these young women to communicate their stories and create role models to drive further progress.

In addition, progress on the construction of the training centre remains largely on-target. How this facility will contribute to the achievement of this output in particular, however, is less clear. Even before construction is complete, UNOPS should consider how it will measure use of the facility, and trainings delivered in support of female retention and advancement, to better understand the CDEL contribution to this output and IO 1 overall.

The UNOPS MEL framework provides reasonable confidence that contextual challenges are being tracked and adaptations to approaches will be made to navigate potential obstacles, but this should be a clear focus of the next year of programming.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under BC. This output links to the previous output 1 of the BC.

Learning
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The 2024 AR recommended a greater focus on measuring the ‘improvements’ delivered under output 1, which has been addressed. SJP-wide efforts to focus on behaviour change have led both to different approaches to output measurement, as well as a delivery approach that looks beyond capacity building. To continue to strengthen this focus on behaviour change, UNOPS should place even further effort on the “M” of the COM-B framework. This requires analysing the interests and incentives of key decision-makers within the NP, and designing and testing approaches to pulling on levers that could motivate mindset shifts within senior leadership. One lever currently being pulled is police-to-police partnerships, facilitating engagement between NP and senior international police expertise (such as the UK’s CoP). Additional levers could also be considered and tested: 1) the identification of change champions within the police that could be supported to advocate from ‘within;’ and 2) the mobilisation of public pressure for reform, identifying influencers within the public sphere and working with them to advocate for reform related to the diversification of the NP, including media and influential business leaders.

SJP continues to demonstrate political astuteness in its analysis of the ever-evolving political context across Nepal, and more specifically within NP, acknowledging the recommendation from the 2024 AR on tracking strategic threats and opportunities. This tracking will be especially important in 2025, as SJP anticipates at least two major shifts in NP leadership and the signing of the Police Act Amendment that could pose risks to the programme’s approaches and objectives. On the latter, UNOPS have committed to translating and analysing the amendment, which will help SJP identify emerging risks and plan mitigation measures accordingly. An additional risk also relates to NP’s commitment to the WIP recruitment platform. UNOPS has procured an external coaching vendor, though one senior officer in NP indicated that he was not interested in the NP participating in or supporting such a structure going forward. Redoubled efforts need to be made to secure this commitment or shift course, with an understanding of the resources required for its sustainability within a police service that continues to be underfunded. Attention to how role models coming out of this coaching programme could be used to further incentivise uptake of the platform could also impact on the VfM calculation.

High turnover /transfer rate continues to plague the sustainability of all training and capacity development in Nepal Police (including the efforts of SJP). In addition, engagement with police during this AR raised questions on duplication of training programmes across what is offered by UNOPS and what is already part of NP’s training curriculum, if NP proves resistant to evolving, or even dropping, its more ‘old-school’ content (e,g, on community policing). RPDD at HQ raised the need to map UNOPS training and its curriculum to avoid this duplication in the future, which should be undertaken in the first quarter of 2025. Additional approaches to knowledge retention and management should also be explored by the UNOPS team in the development of SJP’s training programmes for this coming year. Identification of police champions at mid-senior level, who can be capacitated to continue on-the-job training and reform even after transfer (and even outside of SJP target provinces), could help to mitigate this risk.

Entrenched gender norms and deeply embedded attitudes about seniority, both within the police and across the wider Nepali context (especially within some marginalised communities) continue to create barriers to the diversification of the NP. This justifies SJP’s overall focus on reducing harmful gender norms, but raises the question as to why the outputs related specifically to strengthening the NP (outputs 1 and 2 under IOs 1 and 2) do not currently include an explicit focus on addressing the institutional gender norms that affect female recruitment and more sensitive responses to GBV. UNOPS engaged with family members in the recruitment drives as a starting point, though more sustained attention to addressing these barriers within families and participating communities is merited and presents opportunities for further integration with PIN’s component of SJP.

Finally, as indicated above, the indicator milestones should be reviewed to 1) ensure appropriate ambition; and 2) align data collection with the annual review cycle. Due to the lengthy efforts of UNOPS and PIN to bring all staff members on their SJP teams on board, the ARF was only finalised shortly priort to the review trip, meaning that some indicators do not yet have sufficiently aligned data collection mechanisms and some milestones might have been over or under ambitious. While this did affect the scoring of this output, the MEL structure recently established by SJP gives strong confidence that these issues will be addressed in due time.

Finally, attention will also be needed early in the upcoming quarter to developing a specific results approach in relation to the Koshi Police Training Centre to understand its impact on the recruitment and in-service training of female police.

Output Title	Nepal Police strengthens strategic leadership, enhance HR management capacities, improve women and children’s service centres, establish community engagement and accountability mechanisms, and improve systems for setting and inspecting professional policing standards
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
2.1 Progress on Development and Implementation of Departmental Strategies Aligned with Professional Standards in Nepal Police	Level 2 (Strategy commitment): Formal commitment received from NP leadership to support strategy alignment with professional standards; preliminary plans drafted for departmental strategic alignment.	Moderately did not meet expectation / Progress has been made in terms of generating initial buy-in and in-principle commitment from NP leadership. But formal signing of CoP partnership has not yet happened.
2.2 Progress on Development and Implementation of Evidence-Based HR Policies, Strategies, and Systems in Nepal Police	Level 1 (Engagement & prioritization): Engagement sessions conducted with HRD, RPDD, and NPA leadership to determine HR policy priorities and reach agreement on areas for evidence-based revision and curriculum development.	Met expectation. / Level 1 attained
2.3 Progress on the enhancement of Community Engagement and Accountability Mechanisms within Nepal Police	Level 1 (SARA in pilot areas): SARA approach implemented with CPP personnel in pilot districts; and an agreement on revising the CPP curricula	Met expectation. / Level 1 attained
2.4 Progress on Development and Implementation of Revised Inspection Standards within Nepal Police	Level 1 (Agreement & review): Initial meetings held with NP leadership and key stakeholders; agreement reached on the need for revised inspection standards and preliminary review conducted.	Met expectation. / Level 1 attained
2.5 Progress on strengthening services to women and girls through the construction of new WCSCs	Progress on construction	Met expectation.

Delivery
Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

UNOPS has largely met expectations in the delivery of this output. Much of the focus for 2024 has been on securing NP commitments to professionalisation through 1) partnerships and engagements between international police expertise and the NP and 2) informal meetings between UNOPS and NP (namely RPDD, HRDD and NPA) to discuss opportunities and align priorities. For example, the partnership between UK’s CoP and the NP will also benefit work under this output. Draft Terms of Reference (ToR) have also been developed to guide support from His Majesty’s Inspectorate of Constabulary and Fire & Rescue Services (HMICFRS) in helping NP to establish a new national inspection regime for NP and develop the capabilities needed to institutionalise it. Resources permitting, this support is due to start in Q1 of FY25-26.

UNOPS have also tried to build on work conducted during IPSSJ1, which saw the development of a Performance Management System (PMS), by hosting an overview session with relevant directorates within NP. Police display very little appetite for integration of this system in its entirety; however, anecdotally this review heard of select police leadership taking individual measures to improve performance metrics at District and Area Police Offices (DPO and APO) levels. Such initiatives from within the police present an opening for SJP to support improvements to performance management in more targeted ways, rather than pushing for the integration of a full system that has little buy-in.

Contrary to more limited committed from NP in relation to the PMS, senior leadership demonstrates high levels of interest and engagement in the SARA model of problem-solving in policing. Leaders in charge of DPO and APOs and representatives from NP HQ directorates took part in a one-day training session organised by UNOPS on the strategic elements of SARA problem solving to strengthen CPP. Across each of three priority provinces, district in-charge officers have also participated in introductory sessions: a major step forward. Some confusion among police was noted during meetings held for this review, however, on if SARA replaced or duplicated the CPP structure. Such confusion highlights the need to continue to reinforce the behaviour change (better problem-solving and community engagement) that the SARA model seeks to instil, as opposed to focusing attention more specifically on the adoption of the tool or approach itself. NP have indicated that they will incorporate SARA into the CPP curriculum, though this echoes previous unfulfilled commitments on similar tools and models and is a risk that the programme needs to continue to monitor via its rubric score.

Additional trainings have also sought to support investigative capacities within NP, particularly in response to GBV crimes. Police interviewed for this review noted great appreciation for these practical trainings and the knowledge gained by participating officers. These included Crime Scene First Responder (CSFR) training, Gender Responsive Investigations and Counselling Skills, and an initial assessment of investigation-related police units, which will lead to a 16-day Automated Fingerprint Identification System (AFIS) training programme. On the latter, RPDD highlighted NP’s lack of capacity to absorb the costs for the AFIS within the coming few fiscal years given reducing resources to the NP, signalling that the clear formal communications on this issue have not been fully absorbed by relevant authorities. A failure of GoN to upgrade the system is a risk to critical crime investigation capability as well as to sustainability of this higher cost technology. Such risks should continue to be tracked by SJP. In addition to the expertise already provided for the assessment of fit-for-purpose options, UNOPS could also consider advocacy skills development for NP leadership, to support them to lobby federal government for the integration of needed resources for specific technology identified as essential to strengthening NP’s response to GBV.

UNOPS is also making sufficient progress on the construction of WCSCs and female barracks in twelve municipalities, and is encouraging female labour in construction sites through safe lodging and stipends.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under the BC. This output links to the previous output 1 of the BC. Output 2 of the BC, on the strengthening of justice actors, has been dropped by the programme due to an assessment that working with both security and justice actors would stretch resources too-thinly, and acknowledged the challenging nature of working on strengthening the justice system in Nepal. While this decision feels appropriate given limited resources, the lack of clear linkages between strengthening security actors’ ability to respond to GBV cases, and the justice sector’s ability to process those cases, presents a risk for the programme.

Learning
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from AR 2024 overlap between Output 1 and 2; as such, the analysis of recommendations and learning outlined in the Output 1 section above are also relevant to this output.

Additionally, progress and challenges highlighted under this output emphasise the importance of behaviour change as the barometer of success, as opposed to a narrower focus on the adoption or integration of specific tools and approaches. A prime example is the PMS that UNOPS developed under the previous IPSSJ. Historically, efforts have focused on the integration of the full PMS (across all ranks and positions) into police policy, which continues to face significant resistance from within the NP. Shifting focus to the behaviour change that the PMS was ultimately supposed to engender – more accountable police – creates opportunities to engage with the police in more targeted ways that support this need for accountability without pushing for a system that is unlikely to integrate in its entirety. This same learning will also help to identify opportunities for SJP to lean into NP’s existing systems, identifying where improvements within these systems, even at small scale, can help push forward positive behaviour changes in the shorter-term.

As noted under Output 1, approaches to incentivising behaviour change should be tested and analysed, to help justify future investment in the same approaches, or a redirection of approach. In particular, SJP should continuously reflect on if and how police-to-police partnerships between NP and external expertise is able to unlock change. Equally, UNOPS should consider if and how international expertise can also engage with a wider remit of GoN stakeholders to make the case for sufficient resources to support NP’s uptake of training and hardware/software. A key learning focus for SJP should be about how to incentivise change within key stakeholder groups, including senior leadership within the NP.

UNOPS is actively considering learning from the previous IPSSJ1, on the need to wrap soft-side services around CDEL investments. However, the current ARF does not allow for sufficient measure of if and how layered interventions of infrastructure, capacity development, and community engagement are impacting responses to GBV specific to the areas serviced by the WCSC. It is recommended that SJP considers how this specific question – the combined, localised impact of CDEL and RDEL investment – will be measured going forward.

Output Title	Communities’ agency to tackle safety concerns strengthened
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number (and percentage) of SJP-supported Palikas where multi-stakeholder collaboration is at or above the 'Level 3 - Joint Planning and Action' for addressing community safety and GBV concerns	0 - but all 7 Phase 1 Palikas should move to Level 2 (Initial Engagement)	Met expectation. / In the seven (7) Phase 1 sites, Level 2 has been achieved. Scan and analysis events have taken place in the seven phase 1 sites, and groups have agreed to meet regularly in these sites.
3.2 Number (and percentage) of SJP-supported Palikas where community groups are at Level 3 (Intention to change) wherein Individuals and groups express motivation to shift harmful norms	0 - but all 7 Phase 1 Palikas should move to Level 2 (Critical Reflection)	Moderately did not meet expectation / In the seven Phase 1 sites, Level 1 (Initial engagement) has been achieved. GTSN toolkits have been rolled out in: / - 14 CBOs/CSOs in Madhesh / - 19 CBOs/CSOs in Karnali / - 18 CBOs/CSOs in Lumbini / 30 safe spaces have been identified in Madhesh for critical reflection on harmful norms and GBV. / Community groups enrolled in GT-SN Toolkit process are still at the stage of identifying social norms (both positive and harmful), but critical reflection has not yet fully started. / Consultative assessment has been initiated but there is no strong evidence yet that groups are engaging in deeper reflection.

Delivery

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Under Output 3, SJP works to empower communities to prevent and respond to GBV by fostering critical reflection on harmful social norms and strengthening local safety mechanisms. The key interventions include: 1) Rolling out the Gender Transformative Social Norms (GT-SN) Toolkit through community-based organizations (CBOs) and civil society organizations (CSOs). 2) Creating safe spaces for community discussions on harmful norms, with 30 spaces identified in Madhesh and similar efforts ongoing in Lumbini and Karnali. 3) Training facilitators and community members on engaging in critical reflection and shifting attitudes on GBV. 5) Engaging men and boys through partnerships with organizations like Hami Daju Vai to challenge harmful masculinity norms. 6)) Building multi-stakeholder collaboration at local levels to integrate community-driven GBV prevention into broader safety and governance mechanisms. 5) Integrating the SARA (scanning, analysis, response, assessment) model into community-police engagements on security concerns.

The programme has made progress toward building community agency, particularly in establishing foundational structures and mobilizing key stakeholders. Indicator 3.1 met expectations, as the UNOPS-led component brought together informal groups of community representatives for SARA events in each of the Phase 1 locations. These groups have agreed to meet quarterly, and are also engaged in data collection and providing inputs to identify, prioritise, address, and evaluate the community safety concerns. UNOPS has also trained these community groups, alongside police participants, in the community GIS tool.

Indicator 3.2 moderately did not meet expectations, as critical reflection (Level 2) has not been fully achieved across all seven sites and it is not clear yet whether key change agents are involved in the processes funded by SJP. GT-SN toolkit activities have been launched in 51 CBOs/CSOs, and critical reflection spaces are in place. Additionally, the programme has noted some early signs of attitudinal shifts in some communities, however the evidence on these attitudinal shifts remains preliminary. While community groups are actively engaged on the basis of their institutional identity (e.g. as an early learning centre) or marginalised status (e.g. a newly formed LGBTQ+ group), discussions remain at the initial assessment stage, with norm identification but limited sustained reflection and less clarity of what systems change will be achievable. Given the complexity of shifting deep-seated social norms, this is an expected challenge, and the programme can build on momentum toward achieving its next milestone.

As such, while some aspects of the target have not yet been fully realised, the progress made and the systems in place justify an overall score of A (Met Expectation). Moving forward, continued facilitator support and structured follow-ups will be crucial to deepening engagement and ensuring progression in the next review period. Further, it will be important to differentiate among beneficiaries of the GT-SN classes, as during the field visits it was noted that many participants were ready for more advanced discussions as they had been enrolled in other grassroots work on women’s rights etc. As noted above, the identification and engagement of change agents will be vital for impact and sustainability, as will a closer tie-in with UNOPS-supported processes.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under BC. This output links to the previous output 3 of the BC.

Over the past year, PIN has expanded its approach to strengthening community agency by incorporating a structured rollout of the GT-SN Toolkit, engaging a wider range of CBOs and CSOs across the target provinces. Specific changes include 1) the scaling of GT-SN activities: moving from initial pilot engagement to rolling out GT-SN in 51 CBOs/CSOs. 2) establishing safe spaces for reflection. 3) a stronger focus on engaging men and boys, through a new technical partnership with HamiDajuVai. 4) regular reflection sessions with facilitators and coordination meetings with local governments and CSOs to strengthened local ownership and ensured alignment with existing governance structures.

Learning

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Continuing to reflect on the integration of this output is critical for the coming year, as PIN and UNOPS activities have largely operated in parallel under Output 3. Not all activities require full integration, however, as long as cohesive understanding of the joint results can practically drive forward the two components. Consideration should be given to whether and how CBOs participating in PIN’s GT-SN work can be integrated into UNOPS’ SARA events and sessions, to ensure that the security concerns of these diversity groups and/or marginalised communities’ security can be part of those reflections. It was also noted during the field visits that participants in GT-SN classes possess varied levels of prior exposure to gender-related initiatives; while some are new to these concepts and forums, others indicated experience and readiness for more advanced content or training. The diversity in participation necessitates a tailored approach to facilitation and training, but also to identify early on those of them who are ready for peer-to-peer mentoring or cascading these learnings at the community level. Some participants already demonstrated the ability to act as community leaders. Hence, there needs to be a mechanism within the GT-SN framework to continuously identity, mentor, and support emerging agents of change. PIN’s provincial partners need to be alert to their potential.

The previous AR recommended exploring whether Output 3 (community agency) and Output 4 (stakeholder coordination) could be combined to streamline programme coordination and reinforce coherence with the broader SJP. The ARF has encouraged greater coordination of PIN-led and UNOPS-led components, which was evident during field visits conducted for this review, though collaboration is still nascent particularly where PIN’s activities are in different wards to the one where the police DPO is located and thus the place prioritised for UNOPS SARA CPP support. While the new Outputs 3 and 4 remain separate, both PIN and UNOPS are contributing to both, which will strengthen coherence across programme components. However, given the overlap in activities supporting both Outputs 3 and 4, this recommendation remains relevant and should be considered as part of the ARF simplification.

Another concern flagged in the previous AR was that many local governments (LGs) struggle to effectively allocate Niwaran Kosh funds (GBV Elimination Fund), leading to a risk that they are diverted to unrelated agendas. On this, PIN has recently engaged local stakeholders in all three provinces to strengthen awareness and capacity on fund utilisation. Coordination with LGs has increased, with specific Gender Equality Coordination Committees (GECCs) established in Lumbini and Madhesh. A multi-stakeholder service mapping workshop was conducted to ensure local actors are better informed about GBV services and funding mechanisms. In Lumbini, PIN held meetings with provincial leadership (Chief Minister, Ministers, and Secretaries) to align Niwaran Kosh funding priorities with Gender Equality Policy 2080.

In particular for the work on social norms, this AR makes the following recommendations for this output:

- Ensure adaptive programming that identities and invests in community-level agents of change – for example those individuals or groups showing readiness to influence others, in both schools and GTSN classes.
- Differentiated facilitation in GTSN classes (or participating thought leaders) based on the level of readiness shown by the participants, and more rapid progression to advanced phases of the curriculum where appropriate. While targeted sub-granting for community led actions is one way to do this, PIN could also consider structured mentorship models, peer-to-peer learning in GTSN classes etc.
- Identify overlapping actors and create a joint action cycle where GTSN reflections can feed into GIEN-led school or LG plans. For example. Community findings on harmful norms could be used to tailor the GIEN related training materials on GBV related norms, this could also be used to feed into the school improvement planning via GIENs
- Implement structured follow-up coaching for facilitators to ensure that they can deepen discussions in GT-SN classes that go beyond norm identification.
- Identify participants who have previously been exposed to such classes and are ready for the next phase (critical reflection), explore the possibility of identifying peer leaders within the classes who can accelerate collective reflection on harmful social norms.
- Enhance monitoring tools to systematically capture early attitudinal changes and readiness to move towards phase 2 of the GT-SN classes.
- Develop a simplified guidance note for LGs on fund utilisation through the Niwaran Kosh, tailored to their capacity.

Output Title	Strengthened community safety mechanisms to address safety concerns including GBV
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number (and percentage) of SJP-supported LGs where CPP committees are at or above the “Level 3 - Regular Activity and Training” in community policing partnership functionality.	0 - but all 7 Phase 1 Palikas should move to Level 2 (initial structure)	Moderately did not meet expectation / In the seven Phase 1 sites, Level 1 (Basic awareness) has been achieved. / Early-stage awareness of community safety mechanisms has begun, but not all CPPs are active in Phase 1 sites.
4.2 Number (and percentage) of SJP-supported LGs where communities are at or above the “Level 3 - Capacity Development and Knowledge Building"	0 - but all 7 Phase 1 Palikas should move to Level 3 (Capacity Development and Knowledge Building)	Moderately did not meet expectation / In the seven Phase 1 sites, Level 2 (Initial Structure) has been achieved. Community groups and facilitators have been oriented on the GT-SN Toolkit, objectives, and processes. Safe spaces for GBV discussions have been identified. Schools received technical support to establish or strengthen GIEN. While schools have received technical support to establish or strengthen GIENs, the engagements remained at Level 2.
4.3 Number of women and girls directly benefitting from SJP efforts to strengthen their agency to address safety concerns, including GBV.	200	Substantially exceeded expectation / 1446 total women and girls benefitted. 687 received services from psychosocial workers; 750 women and girls participated in the different SARA events; 9 women and girls participated in GIS mapping training.

Delivery
Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Under Output 4, SJP works to strengthen community safety mechanisms and enhance local government capacity to address GBV and wider safety concerns. Key activities include reactivating and training Community Policing Partnership (CPP) committees, integrating GBV prevention into multi-stakeholder platforms, and supporting local governments in service mapping and response coordination. Additionally, the programme seeks to operationalise GIENs in schools and municipalities to enhance community-driven GBV prevention efforts. However, based on field observations, the emphasis so far has been on structure and following a step-by-step sequential process rather than catalysing meaningful change in social norms.

Over the past year, multi-stakeholder service mapping workshops have been conducted, and schools have been supported in strengthening GIEN mechanisms. However, full institutionalisation of coordination mechanisms remains incomplete, with LGs still at the initial awareness and structural setup phase.

Given the mixed progress, the output is rated B (Moderately Did Not Meet Expectation). While significant achievements were made in direct beneficiary reach, structural progress on LG coordination, capacity-building, and multi-stakeholder engagement remains behind schedule. The slow transition from Level 1 (Basic Awareness) to Level 2 (Initial Structure) in CPP committees and multi-stakeholder GBV coordination platforms suggests that additional technical support and institutional alignment are needed to meet programmatic expectations, and as suggested for other outputs, should also prompt a review of milestones in the ARF to ensure that they are realistic.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under BC. This output links to the previous output 4 of the BC.

Over the past year, Output 4 has seen a stronger emphasis on institutional engagement, particularly through multi-stakeholder coordination efforts at the municipal and provincial levels. The expansion of GIENs in local governments and schools has introduced structured mechanisms for at least preliminary or initial youth engagement in GBV prevention and response issues. Additionally, service mapping on GBV prevention and response was initiated in Madhesh and Karnali, aiming to improve local referral pathways for survivors.

The programme has shifted toward a more phased approach for LG capacity-building, recognising that deeper structural change takes time. The GBV situation analysis, initially planned across all target provinces, has faced delays in Karnali due to limited applications and is still in the contracting process in Madhesh. These gaps indicate the need for more intensive technical support to local governments to ensure that community safety mechanisms transition from planning to full functionality. Moving forward, additional training, follow-up mentoring, and stronger alignment with local governance frameworks will be key to achieving the expected programmatic milestones in the next review cycle.

Learning

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The previous Annual Review recommended:
1. Exploring the integration of Output 3 and Output 4 or at least improving alignment between their respective logframes and theories of change.
2. Strengthening linkages between GBV service providers (Judicial Committees, police, One-Stop Crisis Management Centres (OCMCs), Women and Children Service Centres (WCSCs), and referral mechanisms).
3. Ensuring the selection of palikas for multi-year interventions is based on existing infrastructure investments, particularly UK- and ADB-funded WCSCs, and complementary BEK programs.
Over the past year, coordination between PIN and UNOPS has improved, with joint planning sessions and the ARF facilitating stronger alignment; however, full integration has yet to be achieved. Progress has been made in strengthening GBV referral mechanisms, with service mapping initiated in Madhesh and Karnali and multi-stakeholder engagement increasing, though systematic coordination between Judicial Committees, police, OCMC, and WCSC remains incomplete. Additionally, PIN has aligned multi-year palika selection with existing UK and ADB-funded WCSCs, ensuring investments are in the same LG area. However, more attention is needed to where and why tole and/or ward selection diverges within the programme. Further refinement is needed in formalising selection criteria (please see relevant recommendation under Output 5 below) and integrating these efforts with BEK’s broader programming.

In addition, the complaint response mechanism (CRM) setup through GIENs remain limited in monitoring, activating and strengthening trust in accountability systems for GBV related concerns and cases. There is a risk that GIEN activities remain confined to project activities and remain ineffective in addressing key bottlenecks like strengthening school level CRMs and referral pathways to LG level GIENs. These networks at school level appear to be primarily led by adult actors-often teachers, school nurses etc.-who may themselves hold or reinforce harmful norms. This can constraint capacity building of the young adolescents and come in the way of transformative dialogue around GBV.
Equally, GIEN and GTSN efforts are currently operating in parallel silos despite working in similar thematic areas and geographic spaces.

This AR makes the following recommendations for this output:

- As further highlighted below for Output 5, take a problem-driven approach to identifying the right coordination bodies within each locality, and engaging with them in tailored ways to addressing key risks.
- Where GIENs are identified as the key mechanism to work with, move beyond procedural formations of GIENs to a more dynamic positioning that challenge harmful norms, raise awareness on SRGBV and use of CRM, integrate feedback loops to increase trust and responsiveness and act as an accountability mechanism for local level planning and response on GBV.
- Support school level GIENs to engage in the 7-step planning process and GoN-mandated School Improvement Plans (SIPs) to ensure that GBV prevention are reflected in institutional priorities and resourcing and sustain beyond the project activities of this programme.
- Institutionalise more adolescent participation through student sub-committees, leadership training so students can be identified as agents of change.
- Integrate learnings from GIENs into GTSN change pathways so that critical reflections at community level can inform school action and vice versa. Joint planning and cascading of social norms messages could improve coherence and diffusion.
- Enhance local government capacity by developing simplified operational guidelines on Niwaran Kosh utilization and GBV coordination addressing the real factors that prevent either the allocation and/or utilisation of the fund (e.g the worry of key officials about politicised corruption allegations). It should also be explored how the funds could be directed at prevention rather than individual case response.
- Pilot joint PIN-UNOPS intervention sites to integrate community-based norm change with policing reforms for more cohesive impact, focused specifically on GBV risks/hotspots reported by police (e.g. in private boarding schools or online).
- Strengthen GBV referral mechanisms by formalising coordination between Judicial Committees, police, OCMC, and WCSCs to improve survivor support.

Output Title	Local stakeholders are coordinated and skilled to plan and initiate preventive actions on Community Safety including GBV
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number (and percentage) of SJP-supported Palikas where multi-stakeholder collaboration is at or above the 'Level 3 - Joint Planning and Action' for addressing community safety and GBV concerns.	Level 2 (Commitment to Collaboration) in all 7 Phase 1 Palikas.	Met expectation / In the seven Phase 1 sites, collaboration commitments have been seen from relevant LG leaders/representatives. Scan and analysis sessions held, GIS tool introduced. Regular communication channels for sharing GBV data less clearly evident.
5.2 Number (and percentage) of SJP-supported Palikas where multi-stakeholder collaboration is at or above the 'Level 3 - Capacity Building' for addressing community safety and GBV concerns	Level 2 (Formalization) in all 7 Phase 1 Palikas.	Met expectation / In the seven Phase 1 sites, multi-stakeholder coordination mechanisms have been formalized, following mapping of GBV stakeholders for coordination.

Delivery
Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Similar to Outputs 3 and 4, work under this output has proceeded in two parts – the first as it relates to how local stakeholders from the community, the police, and the local government (including palika, ward, and tole levels) are collaborating under the SARA model to respond to GBV; the second as it relates to how local government and schools, through GBV coordination mechanism and government mandated GIEN committees, collaborate in response and prevention mechanism for GBV. The score of A for this output represents the reviewers’ understanding of the status of the rubric score progressions, though it should be noted that it was not fully clear from the MEL framework how exactly progress for this output should be assessed. Further clarifying what is meant by ‘regular communication channels’ or ‘formalised committees’ would help future ARs assess progress. Equally, PIN’s reporting can be strengthened by more clearly linking its delivery narrative to its rubric score assessments. For example, PIN’s annual report narrative notes that multistakeholder collaboration mechanisms have been formalised within 8 municipalities, while at the same time noting that it was only at Level 1 within the rubric score.

On the first component, SARA events (as discussed under Output 3) have generated initial interest among the ward and tole leaders, community stakeholders, and police that this review engaged with. Community stakeholders and ward and tole leaders in particular expressed their appreciation for the SARA process during engagements for this review. Key challenges to this continued collaboration include: 1) workload overstretch within NP, which was mentioned by a number of police engaged for this review; 2) LG incentives to allocate resources to the response initiatives identified via the SARA process. Additional attention needs to be drawn to the linkages between SARA committees operating at ward level, and leadership at palika level, in support of incentivising the latter’s engagement and commitment to sustaining this process. UNOPS is exploring how to support provincial and local governments to unlock use of the GBV elimination fund as one way of addressing this resourcing constraint.

On the second component, PIN conducted a mapping exercise to identify the existing GBV coordination mechanisms that formally exist to guide decisions on where to focus resources and attention within targeted LGs, demonstrating attention to VfM, though the practical operation and impact of these bodies is less clear. On the back of that analysis, PIN has provided technical support to municipalities to form or reactive committees to serve as coordination mechanisms for GBV prevention and response. PIN has also supported the activation of 15 school-level GIEN within targeted schools across its seven targeted LGs, and LG-level GIEN within the seven LGs, as well as Complaint Response Mechanisms (CRM) within two schools. In four LGs, PIN has provided technical support for the development of GBV elimination fund guidelines.

While a significant amount of effort to identify and engage these coordination structures was evident, the review team felt less confident that a problem-driven approach guided this identification. For example, police and community members engaged by this review raised the risk of GBV of private school children, who did not appear engaged by the GIEN structure. A clearer articulation of why GIEN is critical for the response and prevention of GBV within the confines of SJP is needed, particularly given its policing component, and how these mechanisms will (eventually) support the improved help-seeking behaviour of at-risk children and those charged with their care. Equally, this component currently appears more mechanistic, focused on operationalising committees. Within Nepali context, these committees do appear critical to laying foundations for improved collaboration and response. However, PIN will need to quickly move from this foundational level into engagements that more clearly link to the desired behaviour changes of the key stakeholders. Such changes should also prompt a review of rubric scoring system and ensure that they are reflective of approaches in support of behaviour change.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under the BC. This output links to the previous output 4 and 5 of the BC. This output also overlaps significantly with output 6, both of which feed into IO 4. SJP should consider combining these two outputs to avoid repetition and over-complication of the ARF.

Learning
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Notwithstanding the challenges and limitations recognised in the attainment of rubric progress under this output, SJP also needs to urgently address how it will effectively integrate these two seemingly distinct components for multi-stakeholder collaboration where safety risks overlap and the time for convergence is right (given excessive assertions of authority by male policemen might be counter-productive). This integration needs to go beyond the overlap in ‘process’ participation of stakeholders across the two components. Using the MEL framework as the driving force for integration and internal coherence, SJP needs to put in place a plan for how initiatives under output 5 and 6 are working in collaboration to build towards IO 4, layering initiatives to multiply effects. The results of this integration may take time to see – meaning that parallel initiatives may continue into this coming year in the name of foundation building, but clear articulation of how those separate initiatives build into joint results (as articulated by the outcome mapping) is needed. Work to integrate the outcome mapping framework will support this output integration as well; that framework still includes separate UNOPS and PIN actor groups, which risks reinforcing siloed and parallel components.
As noted above, this review raises questions about whether PIN’s approach to multi-stakeholder coordination is sufficiently problem-driven. The decision to target GIEN in particular appeared to be at least partially driven by PIN’s previous interventions and programmes, rather than a clearly articulated stance on how and why GIEN engagement is critical for GBV prevention (how a GIEN can help identify and drive positive change) and the linkages to police analysis and/or responses to GBV. Within Q1, PIN should re-evaluate its approach to be more guided by a locale-specific diagnosis of problems and targeted at-risk groups.
Sequencing interventions to align to GoN processes is also important to consider in the implementation of Output 5. For example, UNOPS should ensure that its SARA events cycle aligns well to the LG’s annual budget development cycle, to allow response initiatives identified under the ‘R’ phase to be integrated into LG budgets.
The 2024 AR noted the need to ensure that PIN’s target locations should be chosen based on where there are already existing or new ADB- and UK-funded WCSC buildings at APOs. Although UNOPS and PIN are working in the same palikas, this review did not understand PIN’s selection of targeted schools given the ward locations of existing or to-be-constructed WCSC locations within, resulting in missed opportunities to ‘layer’ investments in the same area and connect SARA and GTSN/GIEN stakeholders better together. Given the proportion of CDEL investment comparative to SJP’s overall budget, SJP should quickly address this gap by ensuring that any additional schools chosen for GIEN support under SJP link to areas of constructed (or under construction) WCSCs. An alternative adaptation might be towards non-GIEN mechanisms or gaps from which GBV reporting and risks are found to most arise.

The previous review also noted that additional thought was needed on how stakeholders beyond the federal police HQ will be brought into accountability efforts, linked to the previous output 4. The SARA model offers opportunity for more community involvement in assessing police responses. However, this output, as well as output 6 below, could benefit from a more specific articulation of how communities can be supported to hold duty-bearers to account. An alternative adaptation might be towards non-GIEN mechanisms or gaps from which GBV reporting and risks are found to most arise, e..g. private boarding schools where a WCSC has identified significant problems.

Output Title	Multi-stakeholder groups use evidence to collaboratively design, implement, and improve Community Safety initiatives including GBV prevention and responses
Output number:	6	Output Score:	B
Impact weighting (%):	10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number (and percentage) of SJP-supported Palikas where NP's data-driven mechanisms for community safety and GBV reporting are at or above 'Level 3 - Regular Reporting and Data Collection	0 - Level 2 (Initial recording) in all 7 Phase 1 Palikas.	Moderately did not meet expectation / In the seven Phase 1 sites, Level 1 (Initial Engagement and Awareness) has been achieved, with initial introduction of the GIS-mapping tool and early-stage data collection about the safety concerns, but standardised approaches to recording safety concerns not yet attained
6.2 Number (and percentage) of SJP-supported Palikas where engagement of multi-stakeholders for GBV situation analysis is at or above 'Level 3 - Data Validation and Collaborative Consultation’	0 - Level 2 (Participatory Data Generation & Tool Development) in all 7 Phase 1 Palikas.	Moderately did not meet expectation / Level 1 (regular engagement) was achieved in the Phase 1 sites, with engagements appearing very initial and foundational. ToR for co-design of situation analysis tools finalised and process started in Lumbini, but other provinces delayed. Integration of GIS tool also delayed.
6.3 Number of people engaged in collaborative processes to improve community safety, including GBV prevention and response through the SJP	500	Substantially exceeded expectation / 2224 total. 772 people received services from psychosocial workers; 1440 people participated in the different SARA events; 12 people participated in GIS mapping training.

Delivery
Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Work under this output largely reflects what has been described under Output 5, reinforcing considerations for merging these two outputs in the ARF. As such, work under Output 6 also followed a dual track – the first focused on using evidence to engender collaboration through SARA events, the second via GIEN and GBV coordination mechanisms within LGs. While integration remains nascent in relation to this output as well, it is worth noting that UNOPS and PIN explored ways to collaboratively address issues and engage stakeholders during the period under review.

In addition to the activities described under Output 5, UNOPS also introduced the Community Geographic Information System Tool (C-GIST) to SARA event participants, which will allow community and police representatives to input data on relevant security issues to better visualise and analyse security concerns. UNOPS provided laptops to all seven LGs, as well as to NP and SARA Social Mobilisers (SMs), to facilitate C-GIST-based data collection. UNOPS also supported eight psychosocial workers (PSWs) to provide counselling and referral services to survivors in police stations at each of the seven SJP Phase 1 sites. Challenges of sustainability for the GIS tool and the PSWs were noted during the review, as both investments are currently fully project-supported. PIN has also contracted an expert to support the GBV multi-stakeholder situation analysis process, which has kicked off in Lumbini.

For both components, evidence of transitioning from Level 1 to Level 2 along the rubric framework is limited, resulting in a score of B for this output. This is partially due to delays in the co-development of a GIS tool that PIN will procure. The contract for the development of this tool has just been finalised, which will seek to integrate data gathered by the current UNOPS C-GIST tool, as well as map the available GBV response resources, prevalent harmful practices related to GBV, and types of GBV. To ensure that this output progresses, urgency should be placed on the rapid design and deployment of this tool, as well as migrating data from the UNOPS-specific tool, as orienting stakeholders in its use will also take time and could lead to further delays in 25/26.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Please refer to the discussion of changes to the ToC in section B for further details on the changes to IOs and associated outputs, transitioning from the previous five outputs under the BC. This output links to the previous output 4 and 5 of the BC.

Learning
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Learning and recommendations highlighted under Output 5 are also relevant to Output 6. In addition, the sustainability of PSW needs to be urgently considered as SJP looks to integrate this service into WCSCs. Their added value is evident from their engagements and satisfaction ratings with survivors, but a plan for their contractual transition from UNOPS to NP or other GoN departments needs to be articulated during this fiscal year.

Concerns related to the sustainability of the GIS tool were also noted by the review team, including challenges of digital literacy among potential data entry users, and the availability of mobility data for police and community input. However, the importance of such a tool lies first in its ability to reorient police and community dialogue around data-driven problem identification – the behaviour change. The tool can therefore be used to demonstrate this positive behaviour, making sustainability less of a concern about the tool. However, SJP must also feel confident that it can effectively steward this demonstration to wider uptake of such a tool by NP or government stakeholders for the sustainability of the behaviour change.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The Business Case stated that a comprehensive VFM framework would be developed in the inception phase, based on the 5E framework - economy, efficiency, effectiveness and equity (including gender equality and, disability), and overall cost-effectiveness. The recently finalised ARF now includes a single, programme-wide VFM framework, aligning to the recommendation to do so from the 2023 AR. As the ARF and associated VFM framework were only just finalised, evidence in relation to assessing VFM along this framework has not yet been collected. This review provides the following reflections per the 5E framework:

Economy SJP demonstrates decision-making based on best economy, for example in the co-location of UNOPS staff in PIN’s field office in Karnali. However, some considerations should be made to continue to improve the economy of SJP. The WCSC building under construction that was visited by the review team was notably large, and included a terrace space without clear usage in support of GBV response (although the site engineer explained that the additional building height is necessary for the water supply system). It is evidently challenging to calibrate to a best-estimate of future use where the served population is substantial (150,000-200,000) but harmful norms impede so many from contacting the police in incidences of GBV. Equally, UNOPS’ approach to delivery, especially as it relates to the SARA model, relies heavily on flying staff from Kathmandu to the field. This seems necessary in the initial phase to open the door, introduce the methodology and develop senior officer interest. Considerations should, however, be made to understand if and how this delivery model can be adjusted to achieve better economy, including training of trainers models and any additions to the field-level expertise of the SARA mobiliser (usually a young woman from a traditionally marginalised group). The UNOPS office specific to SJP in Bishalnagar has been well-justified for its VFM given the easy access it facilitates to NP and from/to BEK, though the assumptions therein should continue to be tested to ensure that this separate office continues to reflect better VFM than co-location with the UNOPS Kathmandu office in Patan.

Efficiency SJP has seen a reasonable conversion of inputs to outputs, though progress along rubric scores has been slower than anticipated in some outputs, as described in Section C. Inputs over this period of review have been largely focused on relationship building, early engagement, foundation building, and construction initiation. Time is needed to understand how these early inputs translate into GoN commitments, improved capacities, and strengthened coordination mechanisms, though anecdotal evidence from this review confirms that SJP’s activities are having some traction. The structure of the pause and reflect session attended by the review team gives confidence that SJP will be able to understand where adaptations are needed, though as highlighted in Section A, a clear process for decision making should be articulated. Close attention will also be needed to PIN’s balance of staff costs and travel allowances on the one hand relative to activity costs, on the other.

Effectiveness Additional time is needed to understand if and how SJP’s outputs are having the intended effect, especially as it relates to behaviour change. SJP’s ARF gives reasonable confidence that these effects can be effectively measured and analysed, supporting the programme’s ability to make adaptations where needed and redirect resources in support of better VfM. Some potential in-depth reflections and thus potential shifts are recommended at the top of this review.

Equity This review saw indications of marginalised communities, including women, children, and PWD, actively targeted and integrated into programme interventions. PIN’s selection of CBOs for participation in the GTSN reflected a strong commitment to centering voices of diverse and/or marginalised communities. UNOPS has demonstrated intentionality in reaching marginalised communities in their WIP recruitment efforts and SARA mobilisers in the priority wards. It has also made specific accommodations to encourage female laborers at their construction sites, though social barriers, notably in Madhesh areas, continue to prohibit a more equitable distribution of male to female local workers. In Janakpur, the contractor brought female workers from the western Terai.

Early indications also show that data collected in support of the MEL framework is being disaggregated by sex and caste.

Cost-effectiveness It is challenging to offer a meaningful assessment of SJP’s impact to date on BEK’s overarching Campaign Goals, given the nascent alignment of the programme around the new ARF. As stated throughout this review, SJP’s focus on generating the right evidence and its commitment to learning and adapting will strengthen its cost-effectiveness and overall contributions to the Campaign Goals. Systems and structures are now in place to allow for this evidence and learning, supporting contributions to meaningful change. The priority for this coming year should be to operationalise those systems and inculcate a culture of learning and adaptation across the delivery team.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of outcome and output attainment, theory of change, and VfM analysis, there is sufficient evidence for the programme to continue.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The risks and mitigations in the risk register are reviewed and updated regularly by the SJP BEK team, as well as by both implementing partners. After the September 2023 risk review and regular periodic review, two gross risks within SJP were escalated in the office . While they are currently above BEK’s standard risk appetite, they are signed off by the Development Director,

1. Partners’ safeguarding policies have inadequate compliance processes or are unable to ensure compliance with sub partners (their own due diligence)
2. Partners supported by the programme are alleged or prove to be involved in safeguarding incidents.

These risks were articulated and escalated because of the inherent nature of police powers, with an risk of individual police personnel behaving over-coercively or abusively to members of the public because they hold those powers de jure. SJP also remains somewhat distant from how NP ensures its own personnel are informed of safeguarding policies, procedures, and whistle-blower protections in contexts where female officers are usually heavily outnumbered by male colleagues where they work and live (in barracks). As a result, SJP is unusual in the BEK portfolio.

Strong mitigations processes are in place and will be maintained throughout the implementation, and BEK does raise with NP concerns about incidents where HR violations have been alleged. However, even if mitigations make an incident unlikely (the lowest possible) rating, the programme cannot remove the possibility altogether. Residual impact would remain inherently severe, given the nature of the programme objectives and the power of security personnel over citizens, notably the most vulnerable.

The following are key risks which could cause strategic damage to or failure of the programme:

- As with all public sector reform efforts in Nepal, SJP continues to be challenged by the politicisation of appointment and priorities, and the excessive role of the Federal line ministry, particularly the Minister of Home Affairs, in operational matters. The police organisation itself also remains highly centralised, with minimal changes since the new federal constitution in 2015. Conversely, rapid devolution without institutions to clarify divisions of labour and to minimise political influence may undermine the professionalism of the police more than is the case already, particularly if the politicisation of appointments, promotions and certain investigations is also devolved to provinces.
- The high frequency of police transfer remains a major hurdle to effective and efficient processes of change. The recent change of the Chief of Police (IGP) and an anticipated change in its leadership again within 2025, accompanied almost simultaneously by additional rotations of senior positions, will further impact the program as it requires time and effort in establishing relationship with new leadership within NP. There is little SJP can do about this other than try to engage as many top officers, including the next ‘batch’ in-waiting to underpin continuity, as has been the case to date.
- Difference in mandates, priorities, and bureaucratic hurdles among different government line agencies, particularly between the Ministry of Home Affairs (MoHA) and the Ministry of Women, Children and Senior Citizens (MoWCSC) and among federal, provincial and local governments, has limit SJP’s effective coordination with the GoN apparatus. Delays in the convening and decisions making of SJP’s formally agreed governance committees risk impacting programmatic delivery; for example, the signing of the formal partnership agreement between NP and the UK’s College of Policing risks indefinite delays. Likewise linking initiatives across line ministries and decentralised units of government remains challenging in practice due to continued silos in government, requiring significant time and effort on coordination and coherence.
- One of the major risks for SJP in the current context is the recent announcement of ODA budget cuts, which could significantly affect the overall programme delivery, buy-in from the Nepal Police and reputation of UK support at all levels in Nepal. The potential impacts of the budget cut include: 1) losing credibility among key stakeholders and government officials; 2) possible scaling down of key interventions, or early programme closure in extreme conditions, may limit the SJP’s long-term impact and sustainability. Such a budget cut could further challenge the collaboration with key government line agencies - MoHA and MoWCSCs – and with provincial and local governments, given the much more limited scope for any Financial Aid, as specified in the MoU between FCDO and GoN.

The SJP team is monitoring these risks closely, ensuring proper mitigation measures in place to avoid – to the extent possible - and minimise the impact of these potential risk. SJP prioritises building strong relationships with senior future NP leaders as well as outgoing top officials within the police. The pioneering partnership with UK’s College of policing, which includes advising on a new Master of Police Science in Nepal and mentoring support to the National Police Academy, has been specifically effective in enhancing SJP’s relationship with NP. The team also holds regular meetings with both MoHA and MoWCSC officials, and organises high level exchanges between the UK Ambassador and counterparts within these line ministries to push for the convening of the NSC, recognition of the IGP of Nepal as a standing member of the NSC, and the signature of the formal agreement between NP and UK CoP and also.

BEK is conducting scenario planning exercises both internally and with implementing partners to explore innovative ways to maximise the SJP’s impact despite possible significant reductions in resources. BEK will also engage in discussions with government line agencies to communicate the potential scenarios and resource constraints.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

SJP began with a launching phase through UN Office for Project Services (UNOPS) from December 2022 to, upon amendment, April 2024. After completion of this phase, UNOPS and People In Need (PIN) were brought onboard as Tier 1 partners to implement the multi-year SJP at federal, provincial, and local levels. In nearly all LGs, UNOPS is administering and overseeing capital investments in the construction of new WCSCs for local police units, and additional police infrastructure, such as accommodation for female personnel and a training centre in Koshi Province.

UNOPS

FCDO signed a MoU with UNOPS on May 2024 for a multi-year project of up to £16,374,748 in two segments, spanning from May 2024 to 31 December 2027 in total. Spend thus far amounts to £6,900,000. UNOPS’ original forecast was £6.1M, which was later adjusted to £6.9M following a GoN strong request for infrastructure development of WCSCs and female barracks, complementing BEK’s own CDEL priorities for this year. UNOPS brought forward some infrastructure works (£1,316,272) that were planned for Segment two and adjusted timelines to allow sufficient time for construction and the Defect Notification Period (DNP). This has changed the composition of CDEL and RDEL forecast in segment 1 originally envisaged as lasting to March 2026: CDEL increased from £2.9m to £5.27m and RDEL reduced from £3.2m to £1.62m.

Phase 1 infrastructure work started in mid-2024 and involved six locations for construction in six out of seven LGs. Phase 2 started in late 2024 and involved a further six locations. As a result of surplus funds arising from the gap between contract package estimates and actual awarded contracts (after competitive bidding), a further four locations have been added to be contracted by the end of March 2025. All locations are in the priority provinces for BEK’s portfolio: Karnali, Lumbini and Madhesh.

The overall delivery and financial management of UNOPS has been satisfactory during this reviewing period. UNOPS delivered on recommendations made in the previous AR in investing in its strategic leadership capacity. It recruited a qualified Programme Manager, and brought in additional MEL support to lead efforts to integrate components and create an adaptive framework. The Programme Manager and relevant project team members work closely with BEK’s SJP team, and are responsive to feedback and suggestion provided by BEK on forecasts, revised workplans, reports, compliance and planning for increasing CDEL spend. UNOPS has been maintaining a delivery chain risk mapping which captures fund flows, risks, and mitigation measures. It is also maintaining FCDO funded assets for the police component as per FCDO guidance.

UNOPs has been submitting detailed and high-quality monthly and quarterly progress reports in a timely manner. It is also leading and managing regular joint field visit for the SJP team in coordination with PIN, NP, Provincial Governments, LGs and communities.

PIN

In May 2024, an Accountable Grant Agreement was signed with People in Need (PIN) for up to £8m covering the period until December 2027. FCDO provides quarterly up-front grants to PIN on the basis of forecast and workplan submission, after reviewing quarterly progress reports. During this review period, PIN has spent £814,998 out of £1,608,196 originally forecasted, with a variance of approximately 50%. This is beyond FCDO’s variance limit, and has resulted from 1) underspend in allocated capital fund as PIN took over multiple vehicles from a previous BEK programme as opposed to procuring a new one; 2) sub-grant partners agreements shifting to year two after originally anticipated within year one; 3) a late start to multi-stakeholder engagements (started only from December 2024), GTSN, and the selection of CBOs; and 4) PIN and its partners taking on more work in-house, such as the stakeholder mapping and social norms change assessment, partially contributing to higher staff costs proportional to activity expenses. It should be noted that the balance of staff costs to activity expenses is concerning from a VfM perspective, and requires additional justification from PIN as they prepare workplans and associated budgets for this fiscal year.

PIN leadership initially resisted BEK’s efforts to integrate the two components and align results under the ARF, preferring to retain its original approach and ToC as submitted at proposal stage. This initial resistance resulted in uneven uptake of the adaptive approach and commitment to the COM-B model. To address this lag, the PIN team need to ensure that appropriate resources and skills are in place in order to fully grasp the ARF and cascade understanding from PIN leadership in Kathmandu, to its field staff, and to its downstream partners. Given PIN’s long delivery chain, equipping each link of that chain with this knowledge and capacity to deliver an adaptive, behaviour-led programme, is critical to PIN’s success. The review team did note efforts being made by PIN to enhance integration following the development of the AR, through proactive coordination with UNOPS and other DPs working in overlapping locations. However, its selection of wards and schools in several LGs is hard to follow.

There are also areas of improvement to enhance PIN’s efficiency and collaboration with BEK’s SJP team. PIN should strengthen its financial management and overall forecasting approach, ensuring proactive and timely communication (notably of justifications) with BEK about changes in forecasts and potential challenges to spend. PIN is advised to conduct more thorough reviews of its forecasts and financial reports before submitting to BEK to avoid any discrepancies and errors, as well as to meet FCDO variance limitation. It also needs to look closely at the proportions of expenditure on staff costs relative to activity costs and how these correspond to the VfM framework now established.

PIN provides FCDO with monthly updates as well as quarterly, six monthly, and annual progress reports as per the agreed timeline. On occasion, PIN has requested to extend these deadlines over this review period, which can have knock-on effects on approval processes and timely delivery. To minimise delays, PIN is encouraged to strengthen its reporting process, including via its downstream partners and commit consistently to agreed reporting timelines. PIN has been managing assets as per FCDO guidance assets and regularly sharing an updated inventory list.

PIN is registered with a general agreement under the Social Welfare Council (SWC), which is valid until September 2025. It is in the renewal process, while a SWC project agreement remains pending, despite the application having been submitted by PIN several months ago. If the renewal process takes more time this will create risks to PIN’s ability to implement SJP activities and within agreed timeframes. LGs, even those with whom an MoU has been reached by PIN, may decline to engage,

BEK Performance

The BEK SJP team hosts monthly and quarterly joint meetings with UNOPS and PIN to track progress and discuss risks. The BEK SJP team also conducted induction meetings for UNOPS and PIN to familiarise the partners with FCDO compliance and expectation. Additionally, the BEK team has joined regular joint field visits with UNOPS and PIN to implement and monitor activities as well as build working relationship internally and externally.

Governance

There is mandatory arrangement of the National Steering Committee to review SJP progress once a year with coordination from UNOPS as the implementing partner. However, the NSC has yet to meet due to a lack of clarity in the steering committee structure and the frequent transfers of key officials. The BEK team is in frequent contact with the Ministry of Home Affairs and MOWCSW to try to address this confusion and activate the NSC.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

As noted throughout this review, a significant portion of BEK and delivery partner attention over fiscal year 2024 was focused on the development of an integrated approach to results and adaptation. The MEL framework includes rubric scores for capturing output-level performance, and an outcome mapping across key actors for capturing intermediate outcome-level progress. This framework has been wrapped into a wider adaptive results framework, which also includes indicators for measuring impact and outcome level progress. While comprehensive, and providing a needed basis for internal programme coherence and integrated strategic direction, the ARF is also very detailed and can result in confusion and some duplication of M&E efforts. For example, the ARF has six outputs, linked to four IOs. The rubric, as part of the programme-specific MEL framework, has 11 scores linked to the same four IOs, that feed into the six ARF outputs but with different numbering systems. Consistency across output and indicator numbering will help to avoid confusion in reporting and scoring for future AR. In scoring the six outputs as part of this AR, repetition of activities and indicators capturing similar data were noted across outputs 3, 4, 5, and 6.

The MEL team across UNOPS and PIN are collaborating in data collection and analysis, particularly via the hosting of bi-annual Pause and Reflect sessions. The review team was able to participate in an initial such session in March, which provided the reviewers with high confidence that mechanisms are in place for structured and consistent evaluation of progress.

The BEK programme team remain closely engaged with SJP and have conducted multiple field visits to programme sites and activities in support of monitoring progress and deepening relationships with stakeholders. These include joint visits to all three provinces, including sites, at least three or four times each over the review period

This third Annual Review has been undertaken by a team comprised of an independent consultant with peace and security expertise and an Education Adviser from BEK. The review period is April 2024 to April 2025. The review draws on interviews with NP, government stakeholders at federal, provincial and local (palika, ward, and tole) levels, delivery and downstream partners, other partners, and a small number of community beneficiaries, as well as a review of progress reports and deliverables. Updated rubric and outcome mapping analysis from partners is due after this AR is completed.

Evidence

As the ARF was only finalised while the annual review was underway, SJP is at the initial stages of data collection and evidence generation for the outcome mapping. This evidence will be analysed during the April pause and reflect session, to provide robust indication of progress across the four IOs. Evidence generated for rubric scores is discussed in section C, per output, above. Quantitative data is being disaggregated by age, sex, caste, and disability.

Learning

Again, given the nascent stage of the ARF and the programme’s approach to adaptive management, no notable learning activities or events took place during this review period. The main lessons from the year are highlighted in earlier sections of this report. As noted in the previous AR and in the key lessons noted in section A of this AR, it would be worthwhile developing a programme learning agenda. This agenda could further focus evidence generation on key questions relevant to: 1) informing BEK portfolio and wider FCDO; 2) shaping other Nepal-based development partners’ approaches to similar or complementary issues; 3) influencing GoN and NP uptake of evidence and learning from SJP.

Date of last narrative financial report	UNOPS – March 2025	Date of last audited annual statement	Due in July 2025
Date of last narrative financial report	PIN – January 2025	Date of last audited annual statement	Due in September 2025