## Democratic Resilience Platform - Annual Review

Title: Democratic Resilience Platform
Programme Value £ (full life): £16.375million		Review date: 20 March 2025
Programme Code: [AMP ID#] / 300956	AMP start date: / 20/12/2022	AMP end date: / 31/03/2026

Summary of Programme Performance
Year	2023	2024
Overall Output Score	A+	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	D0003178.odt (live.com) and D0003569.odt (live.com)
DevTracker Link to results framework:	tbc

A. SUMMARY AND OVERVIEW

Description of programme
The Democratic Resilience Platform (Platform) programme was approved in July 2022 as a Directorate wide tool to provide a more cohesive and effective offer to help Posts and partners on democratic governance. The overarching aims of the Platform are to:

- Help UK Posts, partners and practitioners to support democracy in a wide range of contexts;
- Help formulate a new, joined-up approach across the Network to address democratic decline; and,
- Offer greater coordination among related policy areas.

Since the original business case and launch of the programme in late 2022, there were several developments that affected the original objectives and ambition of the Platform programme. These included overall budget reduction to meet costs arising from the Ukraine and Afghanistan crises along with the creation of FCDO (merging DFID/FCO), which led to a period of uncertainty and changes in overall scope and scale of the programme since the Concept Note was approved.
Key interventions under the Platform currently include: (i) the Centre of Expertise (CoE) launched in April 2023 to equip Posts to deliver more effectively across Open Societies objectives and to respond to democratic crises and openings through agile, call-down Technical Assistance (insourced roles/Westminster Foundation for Democracy - WfD); (ii) UNESCO’s Global Media Defence Fund (GMDF) – a Ministerial commitment of £3million over 5 years to support the creation of a safer global environment for journalists (iii) Open Government Partnership Programme - to promote open and accountable use of emerging digital technologies; (iv) Thinking & Working Politically (TWP) in partnership with University of Birmingham; and (v) the recently launched Public Interest Media and Healthy Information Environments (PIMHIE). The Platform has also supported a limited number of one-off interventions and agreements (Summit for Democracy conferences, Foreign Agent Law research and supporting journalists in Gaza through the UNESCO crisis response mechanism), to respond to new and emerging priorities by providing a consolidated funding source.

In 2023, the Platform was extended for 2 years (up to March 2026) and secured additional resources of £11.4million to allow current programming to continue and to consolidate separate projects (such as media freedom) onto one thematic platform. The total Platform programme budget now stands at £16.375million over the period 2002/23 to 2025/26.

Summary supporting narrative for the overall score in this review
The findings and overall score for this review are based on a revised Theory of Change and Results Framework, reflecting more accurately the changes and refocus of resources initially envisaged for the Platform. This programme has therefore been given an overall score of A: on course to achieve desired outcomes. Key interventions such as the Centre for Expertise and Open Government Partnership have continued to demonstrate strong progress against expected outputs and the overall management of the Platform continues to strengthen through the guidance of a dedicated ‘Delivery & Corporate Excellence’ lead to bolster overall programme performance and compliance and general project management. Quarterly Strategy & Programme Board meetings (the ‘steering committee’ envisaged in the original business case design) have now become a routine part of the programming year and encourage dialogue between policy and programming objectives and inform decision-making.

Major lessons and recommendations for the year ahead

1. The performance area of Actionable Learning was added to platform level results framework in response to the recommendations of AR2024. This needs to be developed further in the forthcoming year. The Platform Steering Committee should devote time to investigating and documenting the benefits of the Platform model. Good coordination and knowledge sharing across the different interventions is a key component of making the Platform a success.
2. Project teams should discuss the revised Theory of Change (ToC) and overarching results framework with implementing partners through formal consultation and/or as opportunities arise to make improvements to their own MEL processes/systems (e.g. as programmes are being evaluated or extended etc). Any additional new areas of major focus should be viewed and assessed through the lens of the revised Platform ToC and where relevant, incorporated into a new or existing nested component ToC,

1. FY 2025/26 is the last year of programming for the Platform. In the context of an evolving geo-political climate and a new spending period, a decision will need to be made in 2025, on the future of the Platform, in order to provide clear and timely direction to partners.
2. More work is required on the collection and disaggregation of data on protected characteristics to ensure Platform interventions ‘do no harm’

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

In response to a key recommendation of the 2023/24 annual review and the significant change in scope and scale of the Platform since inception, in mid-2024 support was commissioned through EQUaLs[1] to update the original business case Theory of Change (ToC) based on the revised programme.
[1] The Evaluation Quality Assurance and Learning service, which provides independent technical advice to FCDO
The refreshed theory of change was the basis of an updated platform level results framework around which this Annual Review is organised. A diagram summarising the DRP Theory of Change is overleaf.
The new ToC now refines the underlying high-level outcomes and better captures the full collective contribution of policy, programming and international and internal engagement that takes place.
The ToC also uses the COM-B model (Capability, Opportunity and Motivation), to more clearly capture behaviour change in complex settings. The Platform therefore strives to improve capabilities, and to identify and support opportunities to use these and incentivize motivation to bring about long-term changes in behaviour and/or systems (internally and externally).  This is expected to contribute to enhanced democratic institutions, processes and systems, environment and empower people to further engage.
In addition to the overarching ToC, a set of three nested ToC have also been developed to zoom in on different pathways for change. The three nested theories relate to:
- Upskilling/Harmonising/Use of Evidence/Learning by Post
- Open government and digital democracy
- Media freedom

The most important use for the ToC should be as a lens to make decisions around existing and future interventions to ensure they align with current policy and strategy. This is important as we head into the final year of programming and options for future engagement are being considered.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Three platform-level outcomes, shown in the table below, were identified through the process of refreshing the theory of change. These will be measured in future years by using an outcome map[2] – where the programme team will identify the behaviour changes they would expect, like or love to see. It was not feasible to establish and measure these progress markers for this Annual Review.
[2] https://www.intrac.org/app/uploads/2024/12/Outcome-Mapping.pdf

Section C of this Annual Review scores the contribution to component level outcomes (which are more short-term and sit below these platform level outcomes) as A (on course, with supporting evidence), which suggests progress to the platform level outcomes is on track.

For information, the revised Platform level Outcome statements are:
Outcome Statement	Example Indicators
A. Supported Posts, external implementing partners and/or practitioners deliver better across DG/OS and digital democracy objectives and respond to democratic crises and openings, in line with a coherent, coordinated UK policy position	A1. Evidence of behaviour changes and improved outcomes at Post as measured by progress markers in the Outcome Map
B. Continued/Increased visible UK commitment and promotion of open government/society and digital democracy values and norms, preventing further backsliding and supporting liberal democracy / OGP 1 year anniversary	B1 Evidence of UK Government Commitment to democratic governance as measured by progress markers in the Outcome Map / B2 Evidence of behaviour changes and improved outcomes for external partners, as measured by progress markers in the Outcome Map
C. Enhanced democratic institutions, processes, systems and environments [in supported/priority countries], in which democracy can thrive, whereby people are empowered to exercise and enjoy their democratic rights, both on and offline	C1 Number of democratising countries in Sub Saharan Africa / C2 Number of democratising countries in Middle East and North Africa / [Source VDem]

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis and results of Platform interventions, it is recommended that the programme continues, with the recommendations identified in this review undertaken over the next 12months. Positive results have been noted across all interventions and lessons from early interventions have also been learnt. The Platform concept is offering linkages and improved coordination across different policy areas and strengthening the precision of what we are trying to achieve. It is also demonstrating better overall coordination within our portfolio and with Posts to ensure resources and activities are more focused on outcomes. Strengthening of programme management skills across the department has also improved compliance including: improved due diligence and accurate financial management and responding quickly to strategic opportunities that arise throughout the year.

## C. DETAILED OUTPUT SCORING

In the spirit of the previous year’s recommendations to develop a revised Theory of Change and overarching results framework, this Annual Review is structured according to a revised results framework which considers the ‘performance areas’ of Actionable Learning, and Contribution to Change alongside the traditional areas of Delivery of Outputs. The weighting for Output 4 was reduced to 0% and redistributed across other the remaining output areas as there is no activity to report against in this review period.

Output Title	Platform-level actionable learning
Output number:		1	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Learning Questions	Milestone(s) for this review	Progress
Behaviour Change Questions
Q1. FCDO staff supported by the programme have the opportunity and motivation to translate knowledge and skills into programmes and non-programme interventions?	Narrative-based assessment	On track - reliable, planned evidence generated by the CoE and MFC projects indicates that the technical products and advice on democratic governance/Media freedom issues are providing Posts with greater understanding and application of knowledge to support their objectives at Post. This continues to improve as we build on the CoE offer.
Platform Model Questions
Q2. Platform model contributes to platform outcomes over and above having discrete programmes within a portfolio	Narrative-based assessment	On track. In discussion with project teams, there is strong support for the platform model vs separate programmes. The Platform offers greater coordination, resource flexibility and an opportunity to find synergies to help support and demonstrate what we are trying to achieve.
Q3. Platform model provides more strategic value beyond what Post could have delivered directly.	Narrative-based assessment	In progress - Given this is a new output that was developed late in FY24/25, there is no reliable, systematic learning about the Platform model but work is being undertaken to improve this in the coming year.

Briefly describe the output’s activities and provide supporting narrative for the score.

The three learning questions above have been prioritised, through the theory of change refresh, to be addressed at Platform level. The scoring of this performance area is based on both (a) the extent to which the Platform has generated reliable learning in a systematic way and (b) whether the learning has been applied to guide platform level (or wider) decision making. This Performance Area has scored B. The relevant projects within the platform programme have generated planned, reliable evidence especially in relation to Q1. However, there was limited planned learning in relation to learning questions about the merits of the Platform Model.

On behavioural change (Q1), the programme theory is that the combination of increased capability, together with opportunity and motivation will translate into FCDO staff behaviour change. Both CoE and MFC have collected reliable evidence to test this. Evidence from CoE and MFC activities show positive progress in this area. CoE support is frequently requested in the development of the thinking and approach in Governance Business Cases, Post portfolio reviews and Post strategies (e.g. election strategies).The majority (88%) of CoE beneficiary questionnaire respondents strongly agreed or agreed that the CoE technical products provided them with a greater understanding of the democratic governance issues on the which they had requested support. Beneficiary feedback further supports that services have led to a greater ability to translate improved democratic governance knowledge into the beneficiary Post programmes and non-programmatic interventions.

Through our active membership of the Media Freedom Coalition (MFC) executive group, as well as the reputation we have built up in this space, we have been instrumental in a number of important interventions such as issuing statements on the guilty verdicts against former newspaper editors -much of which was been driven by staff at Post, who now know that an MFC statement can have a positive impact. FCDO staff are also actively able to put countries in need of legislative advice on media freedom in contact with the High-Level Panel.

On the Platform Model – (Q2) –evidence from implementing teams suggests that having a Platform approach with regular oversight and exchange across projects helps support progress towards Platform outcomes. In particular, the Platform model has:

provided the capacity to meet the unique needs of many different and changing contexts and priorities with interventions covering a range of related policy areas and countries, allowing us to tailor our support where impact and need is greatest.
- Enabled teams to have an agile approach to take action on new, strategic opportunities such as the recent contribution to the UN to support journalists in Gaza. Having this flex in the Platform to reallocate money within projects allows us to respond to strategic opportunities in a quick and timely way and supports the continued/increased visible UK commitment and promotion of open governance.
- Begun to support learning and adaptation when teams and Posts identify the most effective ways to intervene.
- provided the space to test new and innovative approaches that may emerge (alone or in partnership with others). This has included scoping studies to assess the level of demand in different Posts and the nature of support required to inform the development and launch of products such as the Women’s Political Empowerment toolkit.
When considering the strategic value of the Platform model, the programme theory is that the Platform offers advantages over and above operating a portfolio of separate programmes. To date, there has not been planned learning on these questions however, the experience of the CoE project supports the Business Case (Appraisal Case) premise that the Centrally Managed Programme model has greater strategic value and vfm than a model where Posts source democratic governance technical advice bilaterally. The CoE brings technical expertise rapidly to Posts, enhancing ability to respond to windows of democratic governance opportunities. The CoE model allows greater access to different sorts of technical expertise than likely a Post would have access to operating in isolation. The CoE model is also beginning to allow best practice learning across Posts regionally or in similar contexts and sharing of best buys, what does and doesn’t work.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The performance area of ‘Actionable Learning’ was added to the Platform level results framework in response to the recommendations of AR2024 therefore there are no changes or planned changes as a result of this review. Project teams report overall satisfaction against this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The major recommendations from the previous annual review relating to the Platform wide model and approach, focused on revising the Theory of Change (Toc), and development of a new overarching Results Framework (RF), following an adaptive approach. The revised ToC and RF have been realised. The main recommendation going forwards under this output is for the Platform Steering Committee to devote time to investigating and documenting the benefits of the Platform model. Good coordination and knowledge sharing across the different interventions is a key component of making the Platform a success.

Output Title	Platform contribution to Component Outcome Changes.
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Basket Indicator(s)	Success Criteria	Brief Summary of Progress
1.Number and high level overview of cases how staff supported at Post by the Platform have applied knowledge and evidence to democratic governance programming and policy decisions. (CoE)	Evidence of application of ‘what works’ knowledge: / Staff can narrate how products and service contributed to decision making / Decision making is consistent with evidence on “what works”.	Focus groups and beneficiary questionnaires and internal feedback indicates that CoE technical support has enhanced beneficiary Posts’ thinking on governance issues, which then contributes to Post future programme and portfolio design. CoE support (through learning in this way) has also contributed to Posts’ strategies and responses to country events, and, when shared, strengthened Posts’ ability to convene international partners.
3A.1 Number and description of cases where country-level reformers (government and civil society) have used OGP products and services and where open government values are increasingly embedded in domestic policy-making. (OGP)	Evidence of open government values: From OGP RF: / 1. At least three Tier 1 countries demonstrate advancement in addressing digital governance policy gaps. / 2. At least three Tier 2 countries demonstrate stronger domestic coalitions of government and civil society actors forming a consolidated advocacy agenda.	Overall, OGP has met this indicator. / 1. Four of five Tier 1 countries co-created digital governance-related commitments in 2023, such as combating mis/disinformation and developing strong online civic space. / 2. Three of five Tier 2 countries have demonstrated strengthening domestic coalitions:
3A.2 Number and description of cases where UK policy positions on issues related to open government and media freedom are reflected in international forums and norms.	Evidence of policy positions reflected in relevant international forum and norms.	UK funding of the MFC Secretariat and as one of the leading contributors to the Global Media Defence Fund (GMDF), we are able to provide international leadership on this issue such as through OECD, OSCE, UN and through briefing of UK delegations to Parliamentary Assembly for debates.
3B.1 Number and description of country-level cases where media protection and journalists’ access to legal advice is enhanced (UNESCO (GMDF/CRM)	Policies and strategies promote the defence of journalists / National action plans are put into practice / Progress would not have happened (or not have happened as quickly) without support from GMDF/CRM	Progress continues. Since June 2024, GMDF conducted 324 instances of legal assistance to journalists and created 2 new legal units to help defend journalists. / At a state level, in 2024 the High Level Panel of Legal Experts on Media Freedom engaged bilaterally to provide advice and recommendations on issues pertaining to media freedom, including on the implementation of the Panel’s recommendations in their four Advisory Enforcement Reports. As part of this, the High-Level Panel provided advice on draft legislation regarding the safety of journalists to one Member State of the Media Freedom Coalition, and to one non-member State of the Coalition regarding the repeal of certain laws.
3B.3 Number and description of cases where Media Partners have adopted or adapted their business, management and production practices. (PIMHIE)	Content is increasingly high quality, inclusive and public interest.	As the global media development project ‘Public Interest Media and Healthy Information Environments (PIMHIE) has not been in implementation during the majority of this year, we cannot say we have yet supported any outlets to adopt or adapt their business, management and production practices.

Briefly describe the output’s activities and provide supporting narrative for the score.
In reviewing this performance area we are interested in evidence in changes in behaviour that are within the direct influence – but not control – of the Platform. These are the first steps in the pathway to change (which are labelled in the refreshed theory of change as Component Level Outcomes).

The performance area is scored using criteria based on the availability and strength of evidence, and on the suggested trajectory. Based on this review, the Performance Area is assessed as A: on course to achieve desired outcomes. With the exception of the Public Interest Media & Healthy Information Environments project, which is at the early stages of implementation, all the projects are able to cite examples of their contribution to outcome changes. However, there is opportunity to strengthen the evidence of why these changes are important, and how the projects have contributed. This is reflected in the recommendations below.

Upskilling/Harmonising/Use of Evidence/Learning pathway
Whilst it can be challenging to trace the onward contribution of all CoE products and services, the FCDO CoE (and WfD) team sought to better understand how CoE products and services were being used at Post, to what (programming and strategic decisions) they were contributing, and if there was any impact in part attributable to CoE engagement. Learning and its application can have a subjective element that is difficult to baseline and to assess with available MEL methods however, evidence from focus groups, questionnaires, internal feedback showed that CoE technical support had enhanced beneficiary Posts’ thinking on governance issues, which then contributed to future programme and portfolio design. CoE support (through learning in this way) also contributed to Posts’ strategies and responses to country events, and, when shared, strengthened Posts’ ability to convene international partners.

Open Government and Digital Democracy pathway
Following a recent project level review, the OGP is showing good progress against indicators. Four of five Tier 1 countries have co-created digital governance-related commitments in 2023, such as combating mis/disinformation and developing strong online civic space. In addition, Three of five Tier 2 countries have also demonstrated strengthening domestic coalitions. More broadly, across OGP, there is an upward trajectory in the number of digital governance commitments featuring in national action plans (NAPs) up from 20% of NAPs announced in 2022 to 24% of NAPs in 2023. This has been achieved through instruments including OGP’s co-creation process, support and sub-grants to CSOs, and the organisation of Global South-led regional meetings and workshops. A review and description of the use of OGP products and services is provided under Output 5.

UK policy positions
UK funding of the MFC Secretariat and as one of the leading contributors to the Global Media Defence Fund (GMDF), has meant we are able to provide international leadership on an important policy area. Examples include: development of media principles, incorporated at the OECD in May 2024; supporting the mandate of the OSCE Representative on Freedom of the Media, and UN Special Rapporteur on Freedom of Expression, highlighting Media Freedom in statements; and briefing UK Delegation to the Parliamentary Assembly for debates. We have also contributed to negotiations on other international products such as the Global Digital Compact, OECD Resolution on Information Integrity.

Media Freedom pathway
Linked to indicators 3A1, 3B1 and 3B3 - The Global Media Defence Fund (GMDF) and the High-Level Panel continues to support journalists and states in accessing legal assistance. This includes supporting journalists directly, as well as actions that facilitate easier access to legal resources. Whilst we have yet to substantively support media organisations to adapt and improve their output due to delays in PIMHIE by six months, we anticipate we should be able to demonstrate significant support to organisations next reporting year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As a new/revised output for this reporting year, there are no changes reported during the past year. Looking ahead, the indicators and evidence base will need to be refined and incorporated into project team planning.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In the next reporting period, the CoE team will investigate how to better assess indicator 1 and therein understand the impact of the programme with more precision. We recommend introducing a mechanism in the post-enquiry questionnaire to measure posts’ ability to ‘better engage on democratic governance’.  This may involve the addition of two reflective questions where the responder describes to what extent they feel more able to engage on democratic governance issues and to provide examples. The CoE team will continue with its use of focus groups.

The CoE will also update the questionnaire to include the following direct question: “Has the project informed policy, strategy or programming?” This will allow us to better capture incidents where CoE support has directly influenced programme or strategy. Taken together, these new questions will give deeper insight into the COM-B model of change emphasised in the refreshed Platform ToC and Results Framework.

The Open Government Partnership project completed its first year of operation in September 2024. There remains strong appetite from all stakeholders to continue focusing on the implementation of global commitments such as those emerging from the UN Global Digital Compact. During the review period, the project has been an excellent platform for building effective synergies with other critical issues on democratic governance—such as combatting mis- and disinformation, promoting civic space, inclusion and public participation, enabling transparency, and supporting media freedom. The project will aim to continue building on this, as open government requires a multifaceted approach. OGP is also well placed to work with partner governments and civil society to protect and strengthen democratic governance globally.

Linked to indicators 3A1, 3B1 and 3B3 – We will continue to engage in international organisations such as the OECD, OSCE and the Council of Europe to advocate for media freedom and advance UK policy positions. Building on the previous media development programme PRIMED, we will ensure our media development support goes to both individual media outlets as well as support to the wider information eco-system.

Output Title	Skills, harmonisation and use of evidence: products and services for staff at Post and other practitioners are designed, delivered and improved.
Output number:		3	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Indicator(s)	Milestone(s) for this review	Brief Summary of Progress
3.1 Extent to which Centre of Expertise has delivered agreed outputs / 3.1aNumber of technical assignments delivered for Posts by the Centre of Expertise when compared to 2023/24	All expected output milestones in the Centre of Expertise (CoE) results framework are met.	Overall, WfD exceeded output milestones. / The majority (82%) of feedback questionnaires relating to enquiries completed in the reporting period rated the service received as excellent or good against a milestone of 65%. / The majority (88%) of respondents agreed that CoE products met their goal of providing them with a greater understanding of the issues on which they had requested support. / The CoE produced five networkwide products in the reporting period against a target of four (for the full financial year) / The CoE completed 27 (WfD) assignments in the reporting period compared to 20 in the previous (full year) period.
3.2 Extent to which Thinking and Working Politically Community has delivered agreed products and services / And # increase in number of newsletter subscribers when compared to 23/24	All agreed milestones are met	Overall, the TWP CoP Secretariat exceeded output milestones. / By the end of January 2025, there were 1506 subscribers (+223 since end FY23/24) and ahead of schedule to meet the FY2024/25 target of 1500. This is a long running indicator, and the reach of the newsletter has grown significantly since the baseline of 370 subscribers was set at the end of FY 2019/20. / Similarly, the target of an average opening rate (“click through”) for the newsletter was exceeded. By the end of January, the open rate was 42.5 per cent (and increase of +4.5 per cent since FY23/24 year-end). / On other milestones: / The target to deliver three events/webinars was met. And the related target of 120 registration per event was significantly exceeded with an average of 200 registrations. / There were 14 publications in the reporting period (nine papers, three book reviews, two blog/thought pieces) against the target of three papers for the full year. / Three requests for direct strategic support to the FCDO were requested and delivered in additional to inputs to smaller pieces.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focuses primarily on the ‘Internally-focused’ Platform-funded policy and programming aimed at upskilling and capacity development of staff at Post (and to a lesser extent external implementers/ practitioners), harmonisation of policies, approaches, tools and guidance and promoting use of evidence and learning

Centre of Expertise (CoE)
The Democratic Governance CoE has seen a high level of demand from Posts since its launch in 2023. Over half of-ODA eligible Posts have been supported to date, and it is on track to meet its ambition to become an authoritative source of expertise across governance issues and to strengthen systems and knowledge-sharing between the centre and Posts. On average, it receives about seven requests for assistance a month. To date, the CoE has taken on 117 enquiries and received requests from all FCDO geographical directorates.

The use of insourced roles has amplified and deepened the CoE’s offer to Posts. In-house technical experts understand the specific requirements of FCDO Posts and can build their trust.  In particular, the CoE team has found that in-house experts are able to talk to Posts on more sensitive issues to understand how to support them best and to tailor that support more effectively than we could do with only outsourced experts. In-house experts are also able to maintain a longer and more impactful relationship with Posts.

Thinking and Working Politically (TWP)
Testimonials and respondents to a piloted feedback survey suggest that TWP CoP has contributed to achievement of its outcome (Outcome: TWP lens becomes more thoroughly socialised among individuals and organisations and helps inform ways of thinking and working) over the reporting period. TWP CoP members have continued to receive regular requests to provide expertise, guidance and advice from several key international organisations including DFAT, Global Affairs Canada, OECD DAC, SDA, USAID and UNDP, thus increasing the socialisation of the TWP.

TWP CoP members have also supported the application of a TWP framing and lens in FCDO analytical tools, guidance and processes. This includes the CoE’s Democracy Diagnostic Tool, contributions to the refresh of the Stabilisation Guide, content for the AIP course (mentioned above) and wider engagements with OCSM, and with FCDO implementing partners. The increase in reach of the TWP CoP Newsletter, growth in LinkedIn followers and level of activity on the TWP CoP website further demonstrate the CoP’s support to further embed TWP ways of working.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

CoE - Recently, the FCDO team, working with its partner, WfD, has reviewed the CoE results framework to refresh indicators not proving to be as meaningful as intended at design. Partly, this is because operating procedures have evolved and enquiries going to WfD are first pre-scoped and triaged by FCDO. The refresh is also intended (as mentioned under Outputs 2) to introduce a mechanism to better assess the extent to which beneficiaries feel better able to engage on governance issues because of support and into to what Post outcomes (programming and non-programming) that CoE products have fed. Ultimately, we want to better understand the impact, usage and longevity of Posts’ interaction with the CoE.

TWP - The TWP programme has sought to more thoroughly socialise and embed a TWP lens among individuals and organisations.  In FY25, the TWP CoP Secretariat will consider focusing programme objectives in the light of a changing and rapidly evolving geo-political environment that includes dramatic changes in US foreign policy and commitments to international development, as well as the Prime Minister’s February 2025 announcement to reduce ODA to 0.3% GNI.  Focusing the programme’s efforts towards maintaining the community through leaner years and supporting the community to use a TWP lens to augment outcomes in sectors continuing to receive funding (albeit likely reduced) may be one pathway forwards.  Work that continues to explore the use of TWP principles and sharpen skills in diplomacy and advocacy will also likely have increased prominence in the years ahead.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The 2024 Annual Review recommended that the CoE expand its available experts (in numbers and across specific thematic areas) and deepen its offer on learning. It has responded well to this recommendation with a current complement of 5 Senior Governance advisors. WfD have also successfully expanded their technical expertise on which CoE requests may call. They onboarded 73 new experts in the reporting period. To further expand the subject areas on which they can offer expertise, WfD also issued a tender for organisations with technical expertise across three Lots (Rule of Law and Justice, Political Economy Analysis, and Media Freedom and Development), to apply to partner them through Framework Agreements. The procurement process is ongoing.

During 2024, the CoE developed two training courses. The first of these is a broad course on Inclusive and Accountable Politics (IAP) that will be hosted in FCDO Learning, and available to all political officers and other staff at induction or any time in their careers plus external partners. The course will launch in Quarter 1, FY 26. The second of these involves joining forces with Human Rights Department to deliver regional training workshops on Human Rights, Gender, Equalities and Democratic Governance. The pilot course took place in Bangkok in January 2025.

Key actions for next year are to: (1) roll out the newly developed Democratic Diagnostic and Women’s Political Empowerment tools across the FCDO network, supporting Posts to analyse barriers and identify opportunities in these areas; and (2), focus on and proactively reach out to Posts in countries that directly support the Foreign Secretary’s priorities.

As the CoE enters its third year, partners will consider the accuracy and relevance of its name – democratic governance – given the offer in practice has proven more expansive. A name that better captures the entirety of the CoE’s thematic coverage would be clearer to Posts and would reduce risk that the offer is interpreted too narrowly.

Output Title	Flexible, responsive Platform funding for one off, emerging and/or other strategic initiatives
Output number:		4	Output Score:	N/A -too early to judge
Impact weighting (%):		0%*	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Indicator(s)	Milestone(s) for this review	Brief Summary of Progress
Extent to which flexibly funded products and services are delivered according to budget, timescale and quality.	Flexible Fund recipients deliver products and services in line with funding agreements.	In Progress - A second Wilton Park event on democracy - ‘Democratic Governance: Shaping Future International Cooperation and Partnerships’ - (to follow the Feb 24 event) is due to be held 18-21 March in Nairobi.

Briefly describe the output’s activities and provide supporting narrative for the score.

One intervention has been earmarked for support in this reporting period under the flexible fund element of the Platform. Westminster for Foundation (WfD), working with Wilton Park, and the support mechanism organisations (IDEA, OGP, OECD and CoD) are leading the planning for a second international conference ‘Democracy Governance: Shaping Future International Cooperation and Partnerships’. This conference is a follow up to the successful event held in February 2024 and therefore falls outside of this review period. Given the constantly evolving geo-political context, modest outcomes are expected, such as maintaining momentum and providing a platform for discussions on international cooperation and architecture, with possible new plans and proposals post-S4D. Approximately 50 government and civil society participants drawn from wide range of countries with focus on global majority.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

*This event takes place between 18-21 March in Nairobi and is a follow up to the successful event held in February 2024. It therefore falls outside of this review period but within FY24/25 and the weighting of this output has been redistributed across the remaining outputs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

This is a new intervention from the flexible funding element of the Platform. No previous or new recommendations to report for this period.

Output Title	Open Government and Digital Democracy: products and services targeted at country-level partners are delivered as planned.
Output number:		5	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Indicator(s)	Milestone(s) for this review	Brief Summary of Progress
5.1 Extent to which Open Government Partnership has delivered agreed products and services. / 5.1a# of reformers from government and civil society benefitting from OGP support products and services	1. Reformers from government and civil society in 8–10 countries participate and benefit from: / a. Technical support on digital governance by connecting reformers to strategic partners. / b. Cross-country learning and exchange; / c. Grants to CSOs to enable active participation in policymaking. / d. Actively identifying and connecting relevant actors on digital governance to each other.	All agreed milestones for this review period met. / 1. Support was provided to all 10 target countries / a. Technical support provided to 7 countries (Kenya, Dominican Republic, Indonesia, Armenia, Colombia, the Philippines, Ukraine). / b. Cross-country learning and exchange provided to all 10 countries via in-person and online exchanges. / c. Grants to CSOs provided in 4 countries (Kenya, Ghana, Nigeria, Zambia). / d. Connecting actors – all 10 countries.
5.2 Extent to which policy leadership products and services are delivered by Democratic Governance Department	2. Use of key learning resources on digital governance, including the Open Gov Guide and public notes, tracked annually for unique views and downloads.	All agreed milestones for this review period met. / 2. Annual tracking (January–December 2024): / a. Open Gov Guide: 7,120 landing-page views and 252 views for its Disinformation chapter. / b. Horizons blog posts on digital governance: 6 released, with 2,025 views, 581 reads and a 36% read ratio. / c. OGP blog posts making digital governance recommendations: 4 released, with 3,851 views and 48 PDF downloads.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has been scored A: on course to achieve desired outcome. OGP has been able to drive domestic momentum on digital governance-related commitments across the grant’s 10 focus countries. This has been achieved with the provision of technical support in seven countries by: providing advice to governments and civil society for the co-creation of National Action Plan commitments, producing research, and identifying opportunities to advance digital governance. It has supported cross-country learning and exchange to, and brokered connections between and beyond, all 10 countries—achieved by organising regional stakeholder conferences, issue-specific workshops and brokering bilateral meetings with third countries and organisations including the EU. Sub-grants have also been provided to CSOs in four countries to support the co-creation of digital governance commitments, raise awareness of digital governance-related issues, fund research and draft digital policy frameworks in-country.

OGP has expanded its diverse set of knowledge resources, which benefit stakeholders in civil society, governments and partners. This includes an OGP ‘Open Gov Guide’ chapter with case studies, blog articles and blog posts focused on issues including: digital threats during elections, AI and state capacity, harmful content online, and how OGP’s model can help to deliver the UN Global Digital Compact. These have all together attracted several thousand unique views.

Of the five Tier 1 focus countries, four have shown tangible evidence of developing digital governance commitments; three of five Tier 2 countries, meanwhile, have made steps towards integrating digital governance into future commitments. Beyond the principal framework of National Action Plans, five countries have developed or are developing standalone digital governance commitments under OGP’s ‘Open Gov Challenge’. Internationally, countries were supported to input into the UN Agreement on Artificial Intelligence and the UN Global Digital Compact last year, while all 10 also participated in a three-day OGP workshop to develop strategies for implementing or progressing digital governance commitments. Although progress has been slow in the Philippines and Ukraine, groundwork has been laid in preparation for future development.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No new or planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The project is on track to achieve tangible results and thus develop good case studies with regard to promoting transparency and open government through the accountable use of digital technologies with partner countries. Going ahead, Tier 1 and 2 countries should continue to be prioritised, working closely with FCDO country offices to ensure that we are all working to the same objectives.

OGP can be used to leverage UK efforts to strengthen and implement international standards by shaping those standards and frameworks around governance and we should continue to make use of this opportunity. OGP can also use its position in building global norms and reforms to support democracy. Uptake of norms by OGP members, such as Beneficiary Ownership Transparency (in 33 members), digital governance or open contracting, reaches a critical mass whereby pressure is then brought on other countries to follow suit.

Output Title	Media freedom: products and services targeted at governments, institutions, media partners, and others are delivered as planned.
Output number:		6	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	n/a New/Refined output following ToC refresh

Indicator(s)	Milestone(s) for this review	Brief Summary of Progress
6.1 Extent to which the UNESCO Global Media Defence Fund delivers agreed outputs and journalists’ work supported through initiatives funded through Global Media Defence Fund	All expected output milestones in the GMDF results framework are met.	The Global Media Defence Fund (GMDF) continues to support journalists in need, particularly seeking legal support, but has also expanded to thematic calls for proposals including on climate. Since June 2024 up to February 2025 the Fund has supported: / 484 journalists, including 268 women journalists (around 57%) / 120 lawyers, including 78 women lawyers (around 65%) / 19 media organisations / 39 NGOs.
6.2 Extent to which Media Freedom Coalition Secretariat services have been delivered	N/A – no milestones.	The MFC is continuing its mission to expand with 51 member states. It continues to deliver support and activities ranging from high-level events at UNGA to commemorate the 5th anniversary of the MFC, launched the “Why Media Freedom Matters” report which features over 100 pieces of evidence on the links between media freedom and democracy, health, peace and security, the economy and the environment and actively engaged with Embassy networks and produced statements to support media freedom objectives.
6.3 Extent to which BBC Media Action products and service Via PIMHIE have been delivered / AND/OR / # organisations benefitting from training and technical assistance	N/A	PIMHIE incurred a substantial delay as a result of a protracted negotiation with BBC Media Action. The programme is now operational, but is only starting to implement substantively in March 2025. Research and project design are being conducted across the six selected countries to inform the detailed country plans and theories of change. The results framework will be developed based on the insights and research activities done during this phase.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has scored an A - on course to achieve desired outcome. Positive progress has been seen across our media freedom interventions and launch of the new media development project (PIMHIE) which will build on the success of the previous project (Promoting Independent Media for Effective Development). We also responded to an opportunity to support journalists in Gaza through a one-off contribution to the UNESCO Special Fund for Gaza.

This year marked the final year of the UK’s £3m commitment to GMDF over five years. In the past, the GMDF launched calls on the 3 main line of actions (legal defence, investigative journalism for crimes against journalists, strategic litigation). In 2024, the Fund launched its first thematic call for the safety of environmental journalists, which received 100 proposals. The fund also continued its support for the High-Level Panel and the Consultative Network.

Support to the media freedom coalition (MFC) secretariat this year, has seen significant progress. The secretariat convened the 5th anniversary event at high level week in New York, attended by an FCDO Minister. A local coordinator in the Philippines is now in position (November 2024); this will enable outreach to create more Embassy networks in the region and encourage more MFC members/engagement in the region. There were a significant amount of statements between Oct-Dec 2024. Through the secretariat’s work in establishing the MFC as a policy tool, we are now seeing Posts pro-actively proposing action through the MFC.

For the new media development programme, ‘Public Interest Media and Healthy Information Ecosystems’ (PIMHIE), the major factor impacting delivery this year has been the delayed start to the programme. We did not formally kick off the programme until the beginning of October, which was more than six months on from the anticipated start date. Within those constraints however, we have made reasonable progress, including determining the countries we wish to work in – Sierra Leone, Ethiopia, Bangladesh, Zambia, Peru and Indonesia. Detailed country business plans and a results framework are being developed in time for the next reporting period.

With Ministerial agreement, in December 2024 we also supported UNESCO’s Special Fund for Gaza, which is providing journalists within Gaza support to continue reporting. The Fund is separate from the Global media Defence Fund, but is being delivered by the same division, alongside UNESCO’s office in Ramallah. The Special Fund reports on results on an annual basis and will be captured in the next reporting period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The major change in the last year has been the beginning of the new media development programme, PIMHIE. Next financial year will see the programme move into implementation phase. We have joint funded an evaluation of the MFC, with the report expected to be published in April 2025. Similarly, we have supported an evaluation of the Global Media Defence Fund (GMDF). We expect there may be changes in objectives and approach as a result of these reviews. In the coming year, the GMDF will be launching another thematic call for partnerships focusing specifically on women journalists and will seek to enhance the visibility around it by providing a platform for the voices of GMDF.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
PIMHIE has been conceived and designed to recognise the lessons learned from the previous media development programme PRIMED (Protecting Independent Media for Effective Development). This includes investment in the wider information ecosystem beyond media outlets, and a slimmed down team ensuring more funding went into country. Going forwards, we would like to ensure greater linkages between development and political objectives in country, which formed a consideration in what countries we chose to implement PIMHIE in. Furthermore, we also want to ensure the programme is coherent with the platforms wider objectives, including the CoE.

For the Media Freedom Coalition Secretariat, we will ensure there is an agreed revised logframe in place for next financial year. The evaluation will provide a reflection point on how the MFC should evolve, although the secretariat have continued to demonstrate an ability to learn. This includes the paper produced on statements and how we can ensure they can deliver the greatest impact.

## D: VALUE FOR MONEY

Key cost drivers and VfM performance
The most significant cost drivers under the Platform are around expert consultant time (CoE, TWP), staffing and associated costs (PIMHIE, MFCS, OGP) and the appointment of insourced roles to support the CoE. Other cost drivers across the Platform range from contributions to multi-donor trust funds (UNESCO) and support to conferences, where VfM can be achieved in terms of the costs ratio against the audience reached (Wilton Park II).

At intervention level, there a good demonstration of VfM being an integral part of planning and delivery including:
The Centre of Expertise’s use of both in-house and out-sourced expertise provides a cost-effective way of supporting the wide range of requests from Posts.  In sourced roles are also more beneficial to FCDO over the longer term as staff gain vital experience that can be taken forward in future roles (cost-effectiveness).
- TWP’s lean structure and its underlying approach of fostering peer learning and building networks helps to achieve intended outcomes economically. Further economy is driven through VfM reviews of activity budgets before sub-contracts are agreed to ensure dispersed funds are being used effectively.
- OGP has taken an economy-of-scale approach to providing technical assistance to partners by organising group workshops, reducing costs and creating a network for supporting peers, thereby maximising the benefits of the partnership. Efficiency and effectiveness, meanwhile, have been achieved via the public goods strategy that OGP adopts for its products, which are used by over 70 governments and 100 civil society organisations in the partnership.
- Similarly, the Wilton Park II event brings together approximately 50 government and civil society participants to strengthen international cooperation and dialogue on democracy issues.
- PIMHIE prioritises economy by using existing resources and office spaces. Efficiency is achieved by sourcing locally and engaging bespoke expertise on a targeted basis. Effectiveness is maintained through adaptive strategies, rigorous Monitoring & Evaluation processes, and local stakeholder engagement. Equity is a core principle, ensuring inclusive and gender-sensitive approaches so all community segments benefit equitably.
- Under the GMDF, resource allocation is based on competitive calls for partnerships where selection is made against pre-set criteria whose goal is to ensure that resources are used optimally to achieve desired outcomes and thereby ensure a contribution to GMDF Outputs.
- The MFC Embassy networks, support the Secretariat in maximising resource impact and efficiencies through coordinated actions such as local statements, joint lobbying, events, and development assistance. Global statements direct international attention towards media freedom and journalist protection, achieving notable coverage without requiring extensive additional funding.
Please assess VfM performance compared to the original VfM proposition in your project business case
With the recently revised Platform Theory of Change (ToC) and results framework, we have an opportunity in the year ahead to properly test the VfM assumptions outlined in the original business case. For example: “Ease of achieving synergy between the programme outputs” or “Improved policy coherence and coordination of CMPs” have now been captured under ‘Platform level – Actionable learning’ with specific indicators to report against. There is growing evidence, as listed above, that interventions are supporting the original VfM assumptions but these will need to be tested further going forwards.

Assessment of whether the programme continues to represent value for money
The Platform itself provides an efficient and flexible means of delivery and continues to represent VfM as evidenced above. Bringing partners together under a single platform makes it easier to manage than administering independent grants or contracts, requiring fewer staff and less administration while also creating more opportunities to find synergies and share learning. The delivery model also provides more flexible funding which has been used to manage risk, increase VfM and enhance impact. Throughout the reporting year, the Programme Board has assessed project level performance and impact and reallocated funds from lower than anticipated spending components to higher performing ones or ad-hoc strategic opportunities in order to achieve greater VfM and impact (e.g. UNESCO Gaza, Wilton Park II).

E: RISK

Overview of risk management
Risk management is reviewed with project leads on a quarterly basis through the Strategy and Programme Board meetings and through individual meetings with the project lead and Platform lead. Each project/intervention has undertaken a due diligence assessment (where required) and a risk register in place and applying do-no-harm principles. Project teams review DDAs and risk registers together with partners on a quarterly/annual basis to ensure proportionate assurance is provided and adapting to any changes in context or partner performance. The changing global political and economic environment means that many of the risks identified at intervention level continue to focus on resourcing and engagement risks such as attracting and retaining high-quality technical staff and maintaining strong engagement with Posts.

The overall risk for the Platform continues to be assessed as moderate with no risk escalations in the reporting year. The Platform faces risk both outside and within its control. The geographical spread of programming includes countries where the political situation may change rapidly, offering both opportunities and challenges for delivery. Within the platform itself, one of the main challenges is the complexity of the platform’s portfolio and its multiple modes of delivery which has the potential to weaken its strategic impact if not resourced sufficiently with the right FCDO staff capacity. The risk of safeguarding issues through the Platform continues to be low given the nature of delivery however, safeguarding is integrated into the design and delivery of each intervention, including a focus on social, sexual and environmental abuse-prevention.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Platform has spent approximately £9.7million against an available budget of £16.4million over the period 2022/23 to February 2025. Spend in 24/25 has been slightly under budget due to delays in implementation of PIMHIE but additional requests for spend such as: (i) £200,000 in September 2024 to deliver on additional activities for OGP; (ii) £250,000 contribution to UNESCO support for journalists in Gaza; and (iii) approximately £150,000 towards the Summit for Democracy (Wilton park II) event, have helped to offset some of this underspend.

At the project level, all partners and service providers continue to provide robust and accurate financial reports throughout the duration of the project lifetime. A significant number of the Platform interventions are delivered through accountable grant agreements (CoE, OGP, TWP, PIMHIE, MFCS) and as part of our due diligence process, governance and reporting arrangements are carefully examined in advance of any agreement, to ensure that the Partner meets expected levels of compliance.  As standard, all accountable grant agreements include a break clause at the mid-term point to provide flexibility to review the Platform and make changes that improve performance.  Such breaks allow the Programme Board to assess whether funding should continue if there are any concerns. Most partners are paid quarterly in arrears upon receipt of the supporting documentation (request for payment, breakdown of previous quarter spending, updated financial year forecast, and narrative report).  The quarterly narrative reports explain to what extent the partner has achieved objectives over the previous quarter.  Taking this approach has enabled project teams and the Programme Board to closely monitor progress and have control over the financial arrangements. For example, where funding has been agreed as an MoU (e.g. UNESCO GDMF), closer attention was paid to financial requests to ensure any payment was not made in advance of need.

After a significant delay, PIMHIE the new media freedom project went live in October 2024. As a special condition of the accountable grant agreement, payments are made in advance on a monthly basis. Fortnightly meetings with the partner have also been established to discuss progress in the inception phase and modelling of financial spend as the project begins to ramp up delivery.

G: MONITORING, EVIDENCE AND LEARNING

The Platform business case originally envisaged an independent MEL module with dedicated advisory support to realise this ambition.  Due to budget reductions and uncertainties around continued funding, this had to be scaled back. With a revised Theory of Change and results framework agreed in late 2024, the Platform is now following an adaptive programming approach to capture overall contributions to the outcomes - combining delivery, actionable learning, contribution to meaningful change and fitness for purpose. In the development of this and the nested Theories of Change, the programme board and project teams now have the tools to begin to identify more clearly what success looks like and the monitoring needed to inform decision making. Drawing this out will be a key activity for project teams and the Programme Board in the year ahead.

At intervention level, various monitoring and evaluation activities have been conducted during this review period to inform programming decisions. This has included: field visits; reviews and engagement with stakeholders; gathering of beneficiary feedback such as the CoE focus groups to assess performance and demand for products; and sharing of case studies to support learning. All projects (excluding PIMHIE and ad-hoc funding such as Wilton Park II) also report regular (quarterly) engagement with partners to review activities and trailing of new outcome level indicators to gain a deeper understanding of project impact and responding to new and emerging needs. As PIMHIE has primarily been in inception phase, there has been little to formally learn during implementation from evidence.

Where additional monitoring and data collection could be strengthened across the Platform, is in the disaggregation of data to support our Public Sector Equality Duty requirements, as this is not systematically collected at present.

Date of last narrative financial report	All Jan/Feb 2025 - with the exception of WPII, where no spend has incurred	Date of last audited annual statement	CoE: Summer 2024 / TWP: February 2025. / OGP: August 2024 / PIMHIE: Summer 2024 / Annual reports / GMDF:31st December 2023 / MFCS: Summer 2024 / Annual Report