ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	Democratic Resilience Platform
Country or region targeted	Non-specific
Type of cost extension (if applicable)	N/A
Original project budget	£4.975m
Original project start and end dates	20 Dec 2022 to 31 March 2024
Current Project budget	£16.375m
Cost extension value (if applicable)	£12m
New project end date (if applicable)	31 March 2028
Business Case Quest Document No.	Platform Business Case on devtracker

INFORMATION
What is the project’s purpose?
The purpose is to provide significant support to reverse democratic declines and shape and influence the international system.
What is the objective of the cost extension or other changes?
The objective is to continue the purpose of the project for another two years and improve predictability for partners (and thus cost effectiveness of the project) while we develop a new Business Case which will expand the project purpose. / The original project was designed as a five-year programme but was curtailed to one year at approval in 2022 due to uncertainty caused by the then ODA pause. In 2023, the programme was extended for 2 years (up to March 2026) and secured additional resources of £11.4 million to allow current programming to continue and to consolidate separate projects (such as media freedom) onto one thematic platform. The total Platform programme budget now stands at £16.375million over the period 2002/23 to 2025/26. We are now seeking an additional £12m over two years (2026/27 to 2028/29). This will enable us to strike the right balance between predictability for partners and flexibility for FCDO, given new developments since the government was elected in 2024, such as the decision to cut UK ODA to 0.3% of GNI, conclusion of the multi-year Spending Review and corresponding changes to FCDO priorities. / This extension will give us time to further streamline FCDO’s portfolio and implement the decisions of Ministers to consolidate separate projects covering the current thematic scope of Democratic Governance, Civil Society and Civic Space and Human Rights Departments onto one platform with a broader thematic coverage and purpose. It will, in the meantime, also enable us to start immediately to shift how we deliver the government’s priorities on systems, rights and governance, implementing the direction set by Ministers on FCDO's development delivery model. / This investment both directly delivers on priority national security outcomes on UK democratic resilience and is recognised as critical to enabling our international priorities and delivery model. Investment will support FCDO to make shifts (a) from service delivery to systems strengthening, (b) away from central programmes and (c) towards a wider set of levers, particularly expertise, but also sanctions, convening, influencing (including through secondments), multilateral reform and alliances. / Finally, on advice from Commercial colleagues, this addendum will allow us to house the Election Observation Mission framework agreement, which facilitates the UK sending both short-term and long-term election observers. It will allow posts to channel their budgets to a supplier who recruits, trains and deploys observers to specific elections. As there is no central funding attached to this, there is no funding required and no cost implications. The agreement is currently being renegotiated by the Elections Policy team as it is due to expire later this year.
What is the additional and total support the UK will provide?
Continued support to the renamed Politics, Governance and Rights Centre of Expertise (CoE) (up to £4.5m additional support per year making a total of £15.3m support). / £1.5m per year additional funding to deliver outcomes through a shift from central programmes to a modern policy toolkit, including: responsible exit from CMP’s, to interventions that ensure key sectors (media freedom; democracy) identify sustainable financing models; convening and influencing (including through secondments) priority bilateral and multilateral partners and alliances (reforming democracy alliances; driving outcomes through specialist multilaterals, such as the OGP; driving effectiveness of key multilaterals by embedding systems approaches): bringing total support to £13 million [£3m + £10m previous CMP spend] / With the costed extension, total support through the Platform would be: £28 million covering the period 2022/23 to 2027/28.
What are the expected results?
CoE: / At least 100 units of bespoke technical advice, analysis and programmatic support on governance issues, including politics and institutions, delivered to posts and partners, including in-country deployment of technical assistance; / Bespoke evidence and learning derived from CoE post-specific enquiries synthesised to support learning and production of at least six global public goods; and / At least six thematic policy guides and tools; / All independently quality-assured to demonstrate they augment understanding; together leading to; / Supported posts and partners are in a stronger position to engage and act on governance issues in-country. / Democratic Governance Partnership Fund / UK takes leadership of at least one key multilateral, driving reform, effectiveness and outcomes; / Two key democratic governance sectors start to identify and shift towards sustainable financing models; / One new evidence-based sanctions regime designed and instigated / Shifts in approach (systems focus) and effectiveness (in sub sectors, like democratic development) of key bilateral and multilateral partners / Global community starts to coalesce around a new governance and democracy agendas and develops mechanisms to deliver
What is the approach to implementation?
The approach to implementation will largely continue as before. Specifically for the components mentioned above: / CoE: This will be delivered through a mixture of UK-based in-sourced experts and delivery specialists and external experts sourced mainly through the Westminster Foundation for Democracy (WFD). Further details can be found in the original Business Case under the Management Case (and subsequent BC Addendums). We will augment the CoE’s in-sourced role provision in tandem with overall expansion. We will also expand the diversity of external providers including through new peer-to-peer arrangements with UK institutions and through South-South partnerships. / Democratic Governance Partnership Fund: This extension will enable us to start to shift how we implement UK systems, rights and governance priorities, particularly a shift away from centrally managed programmes, towards alternative tools and levers including: / Leading the transition from service delivery through developing and testing sustainable financing models within the media sector / Targeted support to key coalitions in the democratic governance and media ecosystems, including the Open Government Partnership, Freedom Online Coalition and the Media Freedom Coalition, enabling the UK to play a prominent role in reshaping coalitions as the funding landscape evolves. / A small strategic opportunities fund to support flexible and adaptive programming (e.g. secondments to key multilaterals, support to Posts on election observation and research) to respond to new and emerging priorities, evidence and learning, and global events. / Due regard to Gender Equality / Gender Equality – and specifically women’s political participation and leadership (WPPL) are central to the objectives of the Platform. WPPL will continue to be a priority theme, and gender equality and inclusion objectives will continue to be mainstreamed throughout analysis, research, and other thematic initiatives. / Terrorism Act / Partners will be subject to due diligence assessments and must demonstrate full compliance with UK legislation, including on anti-bribery and on the financing of terrorist activities.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
N/A. Since the original business case was approved, new evidence relevant to activities planned under this extension has been produced, e.g, about the most cost effective approaches to procurement, and we have adapted the project’s implementation and theory of change to respond, but none of it is ‘key’ in the sense of suggesting changes in overall approach. We will continue to keep this under review. / This project will itself produce new evidence through ongoing monitoring and learning work; and the presence of a MEL Adviser as part of the CoE integrated WFD/FCDO team will ensure we adapt the project’s approach and activities in response to emerging evidence.