## Annual Review Template

Title: Effective Governance for Economic Development in Central Asia
Programme Value £ (full life): £25 mln		Review date: July 2025
Programme Code: 300961	AMP start date: / 12 August 2020	AMP end date: / 31 March 2027

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/59933417.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004804.xlsx

 A. SUMMARY AND OVERVIEW

Description of programme

The Effective Governance for Economic Development (EGED) is a multi-year baseline ODA programme funded by the UK Foreign, Commonwealth and Development Office (FCDO). It aims to improve the effectiveness, transparency and accountability of economic policies through encouraging data and evidence uptake by government officials, civil society organisations (CSOs) and media in Kyrgyzstan, Tajikistan, Uzbekistan and (since March 2023) Kazakhstan. Initially designed for five years – 2020/2025, the programme was extended at no cost to March 2027.

The programme comprises two pillars. Pillar 1 implemented by the World Bank aims to support effective, evidence-informed design and delivery of economic policies. This includes supporting the governments to generate better data and evidence, using this data for policy design and implementation of up to 15 economic reforms, improving coordination within governments on policy implementation, and developing better engagement with citizens. Pillar 2 implemented by the Agency for Technical Cooperation and Development (ACTED) in Tajikistan and Development Policy Institute (DPI) in Kyrgyzstan and Uzbekistan, aims to empower civil society actors in target countries to actively demand transparent and effective economic policy. This pillar helps to develop civil society capacity to produce, analyse, and use robust data for advocacy, engage in and facilitate cross-sector public-private dialogue on economic policy issues, and develop the capacity of the media to deliver data-driven analytical reporting on economic policy.

Owing to reductions in the UK ODA in 2020/2021, the FCDO programme team could not launch some activities originally included in the Business Case, such as cross-country learning and peer-to-peer exchange. Responding to additional climate funding in late 2023, the programme had mobilised a Special Climate Window focsuing on design and improvements in climate-smart policies across the region. In 2024/2025, the EGED delivered a portfolio of 10 policy engagements across four countries, responding to demand from both host governments and FCDO Posts in Central Asia.

Summary supporting narrative for the overall score in this review

The review team scored the programme as an A. There is good progress against most output level indicators. The programme is delivering against the outcomes too. The review team assessed that the programme continues to demonstrate strong value for money, turning relatively modest UK spend into lasting policy and institutional changes benefiting the recipient countries. It has remained flexible and agile, responding to the needs and opportunities.

In Kyrgyzstan the portfolio deepened (sub-national development) and expanded (business licensing/permits); a highlight is the successful delivery through the civil society implementing partner despite the Foreign Agent Law and tight civic space. In Tajikistan both pillars performed well underpinned by continued improvements in delivery of the Targeted Social Assistance (TSA) and institutionalisation of civil society engagement in development policies. In Uzbekistan the programme also deepened (PFM and SOE reforms) and expanded (WTO accession); two highlights are the re-launching of the transparency work and a small disability pilot. In Kazakhstan, the programme footprint remained limited.

Major lessons and recommendations for the year ahead

EGED remains relevant delivering on the Growth, Stability and Development objectives set by the Foreign Secretary. Its flexible approach allowed upscaling or deepening where demand was/is high. In the remaining time, EGED should remain agile and prioritise: (i) achieving the planned outcomes, (ii) UK/Central Asia peer-to-peer engagement, and (iii) visibility of the UK support in the region.

Over the past four years the programme has helped generate many results at output and outcome levels. The emphasis of the past year on impact assessments and implication for people wellbeing has been useful to enhance the visibility of the UK contribution to growth, prosperity and stability in the region and merits of evidence-based reforms. The focus on results should continue in the remainder of the programme.
The value of good analytics for policy design, review, and/or adjustment is hard to overestimate. The backbone of the EGED approach – data/evidence for policy action proved to be an effective instrument to convince policymakers (the governments) and the public of the need to change. Conscious the FCDO often wants to see quick results, the path from analytics to policy action cannot be quick a priori, yet the outcomes are lasting and systemic.
Civil society and media advocacy for policy change or its effective delivery has become hard to deliver in Kyrgyzstan (due to FAL) and remained challenging in Tajikistan and Uzbekistan. Success depends on multiple factors including government buy-in, sound political economy analysis of the intervention, and strong policy expertise of CSOs. Guidance from FCDO is critical to navigating risks.
Small pilots (through ICNL and SABR) albeit brought extra management burden onto the FCDO team, demonstrated good Value for Money – slightly more than £300k had built resilience of dozens civic activists in Kyrgyzstan/Tajikistan, helped continue monitor the civic space in Uzbekistan, and create income opportunities for hundreds of women with disability (or having family member/s with a disability). The FCDO team used these pilots well to respond to the needs and bridge the gap not covered through other instruments.

Recommendations at the programme level for the year ahead:
No	Recommendation	Owner	Deadline
1.	Given the March 2027 end date, consider adding policy interventions that respond to the UK Embassies’ priorities in Growth, Development, and Security, e.g. mining (in EITI member states), business/investment regulatory environment, civic space and media.	FCDO	October 2025
2.	Complete the work streams that delivered the targets, assess what EGED interventions meant for local economy and/or people wellbeing. Decide whether a formal assessment toward the programme end or targeted in-depth reviews of its components will be carried out.	FCDO	December 2025
3.	Consider continuing small, targeted pilots to close the policy or programme gaps in EGED countries in line with CBP goals, where other funding instruments are not available or insufficient.	FCDO	By October 2025 latest
4.	Continue enhancing the visibility of EGED among government, civil society, and development partners. Develop and implement the EGED Communications Plan. Use online (e.g. social media) and offline (bilateral meetings, public events) to communicate about the EGED contribution and results to the line ministries and wider public.	FCDO	Throughout the year
5.	Design and start implementing the sustainability strategy post-EGED for the transparency/accountability model used in the programme.	FCDO	March 2025
6.	Given the governance trends in the past 3 years, future FCDO governance programming in the region should place emphasis on improving regulatory environment, transparency, and accountability of public policy.	FCDO	Subject to the new programme design timeline
[note] See Section B for Kazakhstan, Kyrgyzstan, Tajikistan, and Uzbekistan scores on select Worldwide Governance Indicators (regulatory quality, government effectiveness, and voice and accountability) from 2021 onwards.

Progress against the recommendations made in the last AR are as follows:

No	Recommendation & Progress	Owner	Achieved
1.	Consider expanding the portfolio in Kyrgyzstan, Tajikistan and Uzbekistan by adding or deepening engagements around regulatory environment, structural reforms (e.g. PFM, revenue mobilisation), and/or pro-growth policies. For Pillar 1, any new policy area should link to a World Bank DPO, ongoing policy reform project, and/or prior action/s. Make sure such expansion is properly resourced – both funding and human resource (economist). / Progress: The following work streams were added or expanded: equity assessment of fiscal policies in Kyrgyzstan, Tajikistan, and Uzbekistan; support to WTO accession and sub-national PFM in Uzbekistan; and streamlining business permit/licensing policy in Kyrgyzstan. FCDO team had also started exploring support to transparency in mining in Kazakhstan, Kyrgyzstan, and Tajikistan.	FCDO	YES
2.	Prioritise impact assessment in areas where engagement has been ongoing for more than two years. Ensure FCDO collects and reflects on the lessons learned systematically. This can be done through case studies, MEL, or external support. Make sure impact assessments embed a GESI lens. / Progress: Three assessments were launched – to explore change in hiring process following the new Labour code in Uzbekistan (2023), to understand if revised targeted social assistance in Tajikistan helped households to graduate poverty, and what GEDSI relevant change (output/outcome and impact level) the EGED programme has had.	FCDO	YES
3.	Building on lessons learned in Kyrgyzstan and Tajikistan, consider working at different levels – both national and sub-national. Policy changes done in capitals is felt on the ground. There might be better traction at sub-national level, which should be capitalised on. / Progress: Sub-national development work in Kyrgyzstan was delivered exclusively outside the capital – in 7 target districts. In Tajikistan, up to 50% of the programme spend was delivered in the provinces.	FCDO	YES
4.	Continue enhancing the visibility of EGED and UK contribution to development in Central Asia. Given heightened disinformation risks, communicate about the programme objectives and results more frequently using both online and offline tools. Launch the programme website asap. / Progress: EGED website (eged-ca.org) launched; EGED country factsheets updated and disseminated at programme events; EGED programme and UK International Development logos are used in all public comms and events.	FCDO	YES
5.	Make sure adherence to FCDO programme management compliance standards is upheld and accountability is improved. Risk management by World Bank and ACTED to be proactive and timely escalated to FCDO. Evidence of progress is to be shared with FCDO. / Progress: ACTED tracked and discussed risks with the FCDO team through bi-weekly calls and quarterly risk matrix update. World Bank team handling of risk per FCDO standards remained without change.	World Bank and ACTED	YES, PARTIALLY
6.	Explore opportunities to extend the lessons learned in social protection and sub-national development work streams across the EGED geography. / Progress: EGED supported an exchange between the Kyrgyz Union of Self-Governments and Uzbek Mahalla Association on sub-national governance and development. Both entities signed an MoU and continue contacts beyond our support.	FCDO	YES
7.	With 32% of the approved budget remaining as of July 2024 and several workstreams unlikely to be completed by the EGED end date of October 2025, FCDO should consider a No-Cost Extension for up to 2 years. / Progress: No-cost extension approved at the Development Director level until 31 March 2027.	FCDO	YES

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The EGED theory of change is as follows:
IF EGED deploys technical expertise in response to requests from governments of Kyrgyzstan, Tajikistan, and Uzbekistan to support the design/revision of select economic or social policies,
IF we help generate new and streamline existing data and evidence into design/revision of economic or social policies
AND IF we support civil society’s involvement in select economic or social policies to improve the effectiveness of those policies making them more transparent and inclusive
THEN, the governments feel capable to design more effective policies and feel pressured by civil society for delivery of such policies AND civil society is able to constructively challenge governments on policy outcomes
THEN economic policy is delivered transparently, making sure the outcomes make positive difference for the target populations
THAT IN TURN, will help countries to maintain stable and open economies allowing inclusive growth.
The ToC remains valid, as the EGED recipient countries continue facing government capacity, effectiveness, and transparency challenges in turning ambitious goals of sustained and inclusive growth into reality. The governance gaps are in part caused by a lack of high-quality data, limited analytical capacity, an underdeveloped body of rigorous evidence, and low responsiveness and accountability of government institutions to citizens for policy outcomes. As a result, evidence-based policymaking has been limited, hindering the effective selection, design, and implementation of initiatives – even those addressing urgent national development priorities. Moreover, these limitations restrict citizens’ ability to engage in informed public discourse and reduce policymakers’ capacity to fully assess and internalize the social and economic impacts of their decisions.

The EGED delivery partners operationalise the ToC by: i) providing technical assistance on country-selected priority policy issue areas, ii) closing data and knowledge gaps with analytics in each country, and iii) building capacity of CSOs and journalists to use data/evidence to monitor and report on policy delivery, and engaging governments on the policy outcomes. Through these activities, EGED proactively uses data and evidence to improve the quality of economic governance in Central Asia, with the end goal of promoting inclusive growth in the programme countries.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

EGED programme is on track to contribute to the expected outcomes with multiple examples of progression from analytical outputs to policy outcomes and building trust between government and civil society. EGED has also responded to government demands on new policy areas in Uzbekistan and Kyrgyzstan.

In Kyrgyzstan, EGED’s support for sub-national development contributed to the formulation of Socio-Economic Development Plans (SEDPs), which were formally integrated into the State Programme for the Comprehensive Socio-Economic Development of the Regions (2025–2030), approved in March 2025. In the field, SEDPs helped plan local economy drivers that translated into higher growth in two pilot districts (At-Bashu and Nookat). The EGED programme has also responded to the government's demand for new policy areas such as business licensing reforms. The engagement with the Ministry of Economy and Commerce Press Service offered an alternative way to encourage the government’s transparency around economic policy delivery.

In Tajikistan, reforms of the Targeted Social Assistance (TSA) supported through EGED have positioned TSA as a potential delivery mechanism for the Rogun Benefit Sharing Programme, following adjustments to benefit levels and targeting mechanisms. At least 11 policy changes related to EGED reform issues were influenced, scrutinised and/or monitored by civil society and media, of which 8 were adopted during the review period.

In Uzbekistan, the 2024 PEFA assessment informed the 2025-2030 Public Financial Management (PFM) Strategy and its KPIs, which were adopted in April 2025. Legislative reviews under the SOE reform stream are guiding the development of the 2026–2030 national SOE Privatisation Strategy. EGED’s analytical work has influenced large-scale World Bank operations, including prior actions in Development Policy Operations (DPO) and the design of regional investment programmess such as the IGNITE Trade Multi-Phase Approach. The EGED programme has also responded to the government's demand for new policy areas such as WTO accession.

Impact is measured by the World Bank Worldwide Governance Indicators on regulatory quality (RQ), government effectiveness (GE) and voice and accountability (VA). The scale runs from -2.5 (worst possible score) to 2.5 (best possible score). The baseline was set in 2020 – the data for 2024 has not yet been published. Given the time needed for reforms to take full effect, it is not possible to assess the attribution of EGED’s intervention to the impact at this stage. Data up to 2023 shows marginal improvements in Voice and Accountability (except in Kyrgyzstan) and in Regulatory Quality only in Kazakhstan and Uzbekistan. There is a relative stagnation on Government Effectiveness across four countries, with slight deterioration in Uzbekistan compared to 2022.

Regulatory Quality Estimate	Government Effectiveness Estimate	Voice and Accountability Estimate

Source: World Governance Indicators; Notes; Data for 2024 not yet available

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue and complete the link from policy change to impact, seeking to ensure governments and civil society systematically use data to inform policy change. Progress has been steady across multiple areas, moving from analysis to policy adoption and, in some cases, implementation. Further support is needed to finalize reforms initiated in 2025, advance reforms by supporting the drafting of secondary legislation and developing capacity within government to use toolkits for policy simulations in new areas such as fiscal incidence analysis (initiated in FY 2025-26). Despite the challenges of restricted civic space in Kyrgyzstan, Tajikistan, and Uzbekistan, EGED’s contribution helped build trust between civil society and government, and fostered engagement between the two centred on policy outcomes.

EGED remains the biggest FCDO bilateral multi-year economic governance intervention in Central Asia, which supports growth and poverty reduction through economic reform, and accountability through civil society advocacy. It continues to deliver in line with Country Business Plans and recipient countries’ strategic development objectives, including SDGs.

## C. DETAILED OUTPUT SCORING
Output Title	Kyrgyz government supported to use data and evidence more effectively on selected policies (World Bank)
Output number:		1	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes-Down

Indicator(s)	Milestone(s) for this review	Progress
1.2 Improved regional development (service delivery): / Improved capacity of LSG staff to use Sanarip Aymak facilitates public service delivery at municipal level	100% of 235 LSGs have passport of LSG in Sanarip Aymak by June 2025. At least 50% increase in the number of certificates (national IDs, birth and death certificates, residency registrations) issued by LSGs that improved capacity in using Sanarip Aymak.	PARTIALLY MET. Due to the development of new SEDP Module, Passport of LSG is being revised. Passport is filled once a year (the data will be available in July 2025). 78% increase in the number of documents issued by LSGs.
1.3 Improved regional development planning: / Data from Sanaryp Aymak systematically used for regional socio-economic planning	100% of newly formed LSGs have developed and approved Socio-Economic Development Programmes using new Methodologies. Dashboard to track regional development is launched.	PARTIALLY MET. As of June 2025, about 70% of newly formed LSGs had approved SEDPs. TOR for the SEDP module and Dashboard was officially approved by GoKR, to be developed by Dec 25.
1.4 Improved monetary policy: / Use of inflation forecasting data, data on remittances and improved DSGE model in setting monetary policy direction	Monetary policy is based on new data sets on inflation expectations, remittances and the updated Dynamic Stochastic General Equilibrium (DSGE) model (Dec- 2025)	MET. National Bank of the Kyrgyz Republic uses DSGE model forecasting quarterly to inform decision for the policy rate.
1.5 Improved administration of SME licences and permits: / Sectoral assessment of licences and permits used to improve regulatory environment for SMEs	(i) Inception note (March 2025) / (ii) Identification of maturity assessment of business licenses as mechanism of identifying reforms / (iii) Selection of two pilot sectors for business license reforms / (iv) Review of status of business licenses and requirements in Kyrgyz Republic	(i) MET. (ii) MET. Ministry of Justice and Ministry of Economy and Commerce (MoEC) sent individual letters to the World Bank requesting maturity assessment (April 2025) (iii) MET. MoEC confirmed interest in piloting business license reforms in tourism and food processing (April 2025) (iv) MET. Initial assessment completed in May 2025 and later updated in technical mission in country on the week of June 9-13, 2025.
1.6 More equitable fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Kyrgyzstan fiscal policy	Fiscal incidence analyses preliminary findings are presented and discussed with the Ministry of Economy and Commerce (MoEC)	MET. The concept of the CEQ analysis was presented to the First Deputy Minister of MoEC in April 2025 and preliminary findings in June 2025.
1.7 EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Kyrgyz Republic (Gender Assessment, Poverty Map; Listening to the Citizens of Kyrgyzstan; E-Commerce Diagnostics)	At least 2 Listening roundtables (from July 2024 to July 2025) held; L2KGZ open-access electronic dashboard launched; Sub-National Poverty Assessment developed and published. At least 5 new verified instances of EGED-funded analytical products (L2KGZ, Sub-National Poverty Assessment) used by the GoKR to inform decisions/policies.	MET. See details below.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 was on track to deliver set milestones. To support the SEDPs development by local self-government bodies (LSGs) and district-level specialists, a nationwide series of practical trainings was conducted from April to December 2024, achieving full (100%) coverage – 2,769 officials were trained, including 2,052 LSG staff and 706 representatives from local state administrations and district agencies (47.5% women). The MoEC prepared a FAQ Book (https://mineconom.gov.kg/ru/post/11008) for LSGs on drafting SEDPs. Based on a new planning mechanism (SEDPs), the State Programme for the Comprehensive Socio-Economic Development of the Regions of the Kyrgyz Republic for 2025-2030 was approved in March 2025 (https://mineconom.gov.kg/ru/post/10865). Additionally, the work began on developing the SEDP Module in the Sanarip Aymak system and the Dashboard with expected delivery by December 2025. Output 1 was delivered alongside Output 7 demonstrating strong complementarity and coordination between Pillar 1 and 2 work streams. The WB relied on the deep expertise of the Development Policy Institute (DPI), EGED Pillar 2 delivery partner in: (i) mobilising civil society for the SEDP trainings; (ii) mainstreaming inclusion at village level; (iii) learning from previous capacity building activities with LSGs.

Two L2KGZ roundtables were conducted in October 2024 (Life in Kyrgyzstan conference) and April 2025 (EGED Roundtable). L2KGZ open-access microdata has been published and L2KGZ Dashboard launched. Sub-National Poverty Assessment was completed, the report was published and disseminated at the ‘Life in Kyrgyzstan’ conference and L2KGZ roundtable in 2025. L2KGZ was used by the GoKR to inform decisions around inflation forecasting, energy tariff reform, administrative territorial reform, and water tariff reform; the Subb-National Poverty Assessment informed the 2025-2030 State Programme for the Comprehensive Socio-Economic Development of the Regions.
[note] 240 data downloads as of 20 June 2025.

EGED responded to the GoKR requests (through the WB) to reduce bureaucracy and undertake fiscal incidence analysis. For the former, the programme is helping assess the Regulatory and Institutional framework and map licensing and inspections requirements in tourism and food production. For the latter, the CEQ (Certainty Equivalent) analysis was performed to assess whether the fiscal policy reduces the poverty and inequality; the preliminary findings were presented to the MoEC in June 2025. The results of the analysis were included in the upcoming Public Finance Review of the Kyrgyz Republic.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two new areas were added in 24/25 - review of the business licensing and permits in tourism and food production, and poverty and equity analysis of the fiscal policy. Both additions were in line with the EGED programme objectives (business environment and pro-poor public revenue policy), GoKR priorities and WB country programme in Kyrgyzstan.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations:

	Recommendations & Progress	Owner	Achieved
1.	Going forward, the programme should focus on completing capacity building activities for socio-economic development planning and integrating data systems to automate the use of data in the development of local development plans. FCDO should reflect this in the design of any future phase. / Progress: Capacity building activities were completed; automation of data use for local development plans is in progress, expected to end by December 2025.	FCDO / World Bank	IN PROGRESS
2.	The use of data products to inform government policy decisions needs to be tracked and verified. Government interest in data products does not guarantee their being used when drafting policy. / Progress: World Bank is tracking the uptake of data products produced through EGED where possible. Limitations persist – a WB verification of data products uptake among government officials may be perceived as interference.	World Bank	YES
3.	Should resources permit, consider adding a business regulatory environment or structural reform policy focus to the programme / Progress: Two new areas added – business licensing and fiscal policy review.	FCDO	YES

Lessons learned this year:

The Kyrgyz economy going through once in a generation boom means that the resulting growth of regions will come from multiple factors including the rationalising of resource allocation through the SEDP methodology. For the duration of the EGED programme, it might be difficult to judge its impact on local economic growth, however, it can be more accurately judged in how it enables the provision of key public services using high quality evidence.

Reducing bureaucracy will require time to yield a substantive output but there is a high-level commitment to these reforms at the GoKR. Any proposed rationalisation of the regulations should consider the likely outcome including positive and negative (unanticipated) consequences beyond the creation of a ‘level-playing field’. The sources of a lack of level playing field are not purely regulatory but also related to the political economy.

Since the WB through EGED has already invested in the development of regional and local economic planning methods and policies, it should also be conscious how the reducing bureaucracy may impact or enable LSGs to bring necessary entrepreneurship into local food production and tourism sectors.

Recommendations for the year ahead:

	Recommendation	Owner	Deadline
1.	Understand the whole set of government responses to promoting sub-national economic development especially how grants and direct transfers are made to LSGs and small towns. Encourage the use of SEDP across all GoKR sub-national development work.	World Bank	Throughout the year
2.	Monitor SEDP adoption and its impact in the provision of priority public services and the extent to which inclusion is mainstreamed.	World Bank, FCDO	Dec 2025 and June 2026
3.	Identify/assess the potential impact of rationalising the business licensing regulations on local economic growth.	World Bank, FCDO	Sept 2025
4.	Anticipating the new governance programme, prioritise intervention/s that will improve business enabling environment.	FCDO	During the design of new programme

Output Title	Tajik government supported to use data and evidence more effectively on selected policies (World Bank)
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes - Down

Indicator(s)	Milestone(s) for this review	Progress
2.2 Updated Targeted Social Assistance policy (TSA): / Data/evidence used by Ministry of Health and Social Protection (MoHSP) to improve TSA policy design and implementation	Core Diagnostic Assessment (CODI) of Social Protection in Tajikistan published by June 2025. Evidence of the intended impact of the modernised TSA formula (targeting) and benefit structure (amounts) on reducing recipient household poverty collected and partly presented to the public.	PARTIALLY MET. / CODI report dissemination event was held jointly by WB, UNICEF and Government of Tajikistan in June 2025, preceded by the validation with all stakeholders. / Impact assessment of TSA reform was delayed due to slow late receiving of the Social Registry data from the MoHSP.
2.3 Updated welfare measurements (poverty and middle class): / Quality of citizens welfare monitoring data used and capacity of using the data to generate quantitative evidence in policy making in Tajikistan improves	The updated poverty measurement methodology fully approved by the Government of Tajikistan. Poverty data (re)calculated using new measurement methodology. Middle-class measurement methodology fully approved by the Government of Tajikistan. Middle class calculated using new methodology.	MET. Both methodologies were approved by the GoT Council for Middle-Class expansion in Sept 2024 and Feb 2025 respectively. The poverty and middle-class concepts were also presented and discussed at the regional consultations with CSOs in Dushanbe and in Khatlon.
2.4 More equitable fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Tajikistan fiscal policy	Fiscal incidence analysis is planned for FY 25/26.	N/A
2.5 EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Tajikistan (Gender Assessment, Poverty Map; Listening to Tajikistan; E-Commerce Diagnostics)	At least 2 L2TAJ Roundtables (from Juy 2024 to July 2025); L2TAJ open-access electronic dashboard launched; Poverty and Equity Assessment completed, presented, and published. At least 5 new verified instances of EGED-funded analytical products used by the Government of Tajikistan to inform decisions/policies.	MET. Two L2T roundtables were held (Nov 2024, June 2025). The Poverty and Equity Assessment report dissemination planned for September 2025. See more details in the text below.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 was largely on track with a couple of delays caused by slow response from partner line ministries. Several deliverables were finalised during the past year: (i) the poverty and middle-class measurement methodologies, (ii) the Core Diagnostic Assessment of the social protection in Tajikistan, (iii) Poverty and Equity Assessment. While the practical use of the poverty and middle-class measurements seems clear, the policy implication of the latter analytical products remains less clear – needs to be tracked next FY.
[note] E.g., the GoT had noted that the middle-class measurement will guide a potential government programme to support expansion of middle class in Tajikistan.

The past year demonstrated enhanced accessibility of the Listening to Tajikistan (L2T) to the public – through launching its interactive Dashboard and marking the 10-year anniversary, and use of its findings by the research community. L2T data was used by the Institute of Economics and Demography - a government think-tank, for publications on: (i) Dushanbe as a smart and safe city (part of the first Local Voluntary Review of the city of Dushanbe), (ii) ‘Current state and prospects of demographic development of the Republic of Tajikistan’ report, publication is expected in July 2025, (iii) setting objectives and prospects for the development of Tajikistan’s employment system; (iv) combination of national and regional aspects of ensuring food security; (v) economic wellbeing in Tajikistan: status and perspectives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A new area was added in FY 24/25 - poverty and equity analysis of the fiscal policy. This addition was in line with the EGED programme objectives (pro-poor public revenue policy), GoT priorities and WB country programme in Tajikistan.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations:

	Recommendations & Progress	Owner	Achieved
1.	Prioritise the impact assessment of the Targeted Social Assistance reform. By January 2025, the revised TSA benefits will have been active for 18 months. Given the higher benefit amounts and budget allocations, it is crucial to assess the impact of TSA on poverty. WB in consultation with the FCDO team to produce an impact story. / Progress: TSA impact assessment was postponed to FY 25/26 due to delays in receiving the registry data from the relevant line ministry (MoHSP) to draw the sample from.	World Bank	DELAYED
2.	Make GESI results of the TSA, poverty and middle-class measurement work more pronounced. All three engagements suggest strong focus on equity. Yet the impact on women, people with disability and other vulnerable groups needs to be brought to surface. A separate note summarising GESI results to be developed. / Progress: FCDO commissioned GEDSI review of EGED, findings to be presented in Sept 2025. WB plans to conduct TSA impact assessment delayed (see above).	World Bank and FCDO	IN PROGRESS
3.	Work to sustain demand for L2T in the Government and among research institutions, civil society and development community. / Progress: The Institute of Economics and Demography - a government think-tank has been increasingly using L2T data in its analytical work. Demand for L2T from other government institutions remained nascent.	World Bank	PARTIALLY
4.	Consider adding an economic or structural reform policy to the portfolio. EGED portfolio in Tajikistan has been predominantly poverty driven. FCDO team needs to decide if there is scope to bring in an additional policy engagement addressing the constraints to economic growth. / Progress: Poverty and equity review of fiscal policy was added. WB team declined adding other areas proposed by FCDO.	FCDO	YES

Recommendations for the year ahead:

	Recommendation	Owner	Deadline
1.	Track and report to FCDO the policy uptake of evidence and recommendations generated through the CODI and Poverty and Equity Assessment.	World Bank	Dec 2025 and June 2026
2.	Develop a poverty reduction impact story that EGED Pillar 1 contributed to in Tajikistan.	World Bank and FCDO	January 2026
3.	Consider adding a new policy engagement to support SOEs or PFM reform. Make sure any such addition complements the structural reforms taken through the IFIs in the country.	FCDO	October 2025

Output Title	Uzbek government supported to use data and evidence more effectively on selected policies (World Bank)
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes - Down

Indicator(s)	Milestone(s) for this review	Progress
3.2 Labour Code: / Data/evidence used to improve the design and implementation of Uzbekistan's new labour code	Evidence of the intended impact of the modernised Labour Code on improved employment opportunities for women collected and presented to the public.	MET. Phone survey conducted based on a randomly selected sub-sample of 100 medium and 100 large firms from the World Bank Enterprise Survey master sample. The findings presented during the L2CU roundtable in June 2025.
3.3 Climate-smart policies: / Data/evidence use by relevant government ministries improves the design and implementation of the climate-smart policies (decarbonisation, air quality, climate adaptation and resilience)	N/A
3.4 Public Procurement: / Quality of design and implementation of e-complaints handling module on procurement	N/A
3.5 SOE reform: / iSOEF report used by the Government of Uzbekistan and other partners to inform SOE reform	Assessment report of the 2021-2025 SOE reform strategy implementation. A policy note on reform opportunities to enhance competition and create a level playing field between SOEs and the private sector.	MET. See detail below.
3.6 WTO accession: / CGE modelling used by the Government of Uzbekistan to inform adjustment in sectoral policies to comply with WTO standards	Distributional impact analysis using the CGE-GIDD framework that offers a structured approach to understanding and mitigating trade reform effects in Uzbekistan: drafted the summary of literature review for trade liberalisation reforms and methodology brief for the CGE-GIDD.	MET. Completed the summary of literature review for trade liberalisation reforms and methodology brief for the CGE-GIDD (Computable General Equilibrium – Global Income Distribution Dynamics) framework and shared with the WTO Chief Negotiator’s Office.
3.7 Public Finance Management: New evidence generated on the public finance management informs the Government of Uzbekistan strengthen PFM outcomes, including at sub-national level	PEFA 2024 launched & publicly available. Recommendations and KPIs included in 2025-2030 PFM Strategy. Completed the sub-national PEFA assessment in at least two districts and developed note on the Program for Accelerated Integrated Development (PIAD)'s district level rapid PFM performance benchmarking.	MET. (1) The 2024 PEFA Report launched and made publicly available in October 2024. (2) The PFM Strategy and KPIs included were submitted in November 2024 approved on April 8, 2025, through the Cabinet of Ministers Resolution #210. (3) Completed the sub-national PEFA assessment in a low (Syrdarya) and higher (Fergana) fiscal capacity setting and developed an advisory note on PIAD titled “Resourcing Sub-National Government for Results”.
3.8 More equitable fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Uzbekistan fiscal policy	Baseline fiscal incidence analysis for Uzbekistan and the results presented to the government counterparts	MET. Completed baseline fiscal incidence analysis for Uzbekistan. Results of the analysis has been made part of upcoming Public Finance Review of Uzbekistan.
3.9 EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Uzbekistan (Gender Assessment, Poverty Map; Listening to Tajikistan; E-Commerce Diagnostics)	At least 2 L2CU roundtables (from July 2024 to June 2025). L2CU open-access electronic dashboard launched. At least 5 new verified instances of EGED-funded analytical products used by the Government of Uzbekistan to inform decisions/policies.	MET. See the detail below.
3.10 Monitoring of GoUZ policy delivery: The Delivery Unit is supported to use data/evidence to track progress on select reform priorities set/requested by the President of Uzbekistan	A workshop on Data Analytics and AI in the public sector held. A prediction model for public investment needs using the school data designed, submitted to DU.	MET. (1) Workshop on Data Analytics and AI in the Public Sector held in April 2025. / (2) Nine ML models for school, pre-school and hospital investment planning in Samarkand region, and three reports describing the logic flows for models’ creation developed and shared with the DU team.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 scored A, meeting the target results. Two instances of analytics informing policy were recorded – a new 5-year PFM Reform Strategy and public investment guided by geospatial monitoring of access to public services. The addition of two new areas (WTO accession and equity review of fiscal policy) expanded the programme’s contribution to address key economic governance challenges.

SOE reform: State-owned enterprises (SOE) reform remained a GoUZ priority (especially in the view of Uzbekistan’s accession to WTO). Despite legal and institutional changes, the SOEs share in GDP is still high - 32%. In FY 24/25, the WB (i) finalized a Stocktaking Report on the 2021–25 SOE Strategy Implementation (submitted to the State Assets Management Agency (UzSAMA) in June 2025) and 2) reviewed and provided comments for the 2026–30 SOE Reform Strategy, including two capacity building workshops for Uzbekistan State Assets Management Agency (UzSAMA) and Joint Stock Company UzAssets in May 2025. The 2026-2030 SOE Strategy is being prepared by UzSAMA with an estimated deadline of December 2025.

WTO Accession: Accession to WTO is another key priority for GoUZ. Multiple regulatory and legislation changes have been enacted already to meet the WTO membership requirements; more to come, e.g. on safeguard measures, anti-dumping and countervailing duties, technical regulation, and intellectual property rights. FCDO supports Uzbekistan’s WTO accession through the World Bank, which initiated a CGE-GIDD-based analysis to assess the impact of trade liberalisation on household welfare. As of July 2025, the WB team drafted the summary of literature review for trade liberalisation reforms and methodology brief for the CGE-GIDD analysis and submitted it to the WTO Chief Negotiator’s Team. Work is on track to finalise the CGE analysis evaluating the impact of reforms in August 2025, GIDD analysis – in October 2025, and final paper on CGE–GIDD framework – in January 2026.

PFM reform: The pace of reform remained stable, demonstrating the MoEF commitment and readiness to avoid rushed decisions. The PEFA assessment – second for Uzbekistan, was launched in autumn 2024. This was paralleled by the World Bank team work on designing suggested KPIs for 2025-2030 PFM Reform Strategy, which were submitted to the MoED in November 2024. The new 5-year PFM Strategy signed off in April 2025 took in most of the suggested KPIs. Following the FCDO decision to expand PFM to sub-national level, the WB managed to assess two pilot regions (Syrdarya and Ferghana) to inform the advice (to MoEF) on result-oriented resourcing of local governments.
Monitoring of GoUZ policy delivery: The evidence demonstrated the milestones set were met, while the GoUZ demand for technical assistance remained high and the engagement led to changes in policy over the last 6 months. The Delivery Unit (DU) launched a prototype dashboard to track progress on reform priorities within the E-Government navigation portal. Support on the machine learning models to analyse geospatial inequality in public services led to designing and launching a geoportal platform, which has already influenced government investment decisions, e.g. the GoUZ WASH programme allocated approx. $75mln annually for WASH facilities in schools across country.
EGED analytical products: Two L2CU roundtables were held on February and June 2025, In December 2024, the L2CU microdata (for 2018 to latest) and questionnaire were published on the WB Microdata Library to provide wider access to the data for research and analysis. In addition, the World Bank developed a new interactive L2CU dashboard to showcase monthly trends of key indicators, which is publicly available on Uzbekistan’s L2CU website. EGED-funded analytics were used in/for: (i) monitoring briefs on public perceptions of the 2024 and 2025 energy tariff reforms, (ii) Behavioural Science Insights for the Energy Tariff Reform for enhancing effectiveness of communication campaign, (iii) citizens’ perspectives on the implementation of the Labor Code, (iv) understanding the middle-class and economic mobility, and (v) citizens’ views on the government fiscal policies.
[note] The briefs are used to report to the President Administration, Ministry of Economy and Finance, and National Agency for Social Protection.
[note] Shared with the Ministry of Energy, Ministry of Economy and Finance, and NASP.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The SOE reform work stream deliverables were updated (Indicator 3.5) to align with the timeline for the new SOE Strategy 2026-2030. The PFM work (Indicator 3.6) deepened to the sub-national level. Two new interventions were added – technical assistance to the GoUZ on WTO accession and equity analysis of the fiscal policy. The WTO Accession work stream (Output 3.6) evolved from the original roadmap due to the fluidity of demands from the WTO Chief Negotiator’s Team.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress against last year’s recommendations:
	Recommendation & Progress	Owner	Achieved
1	There is a need to review the milestones for 2025 to reflect updated workplans and priorities across all areas covered above. / Progress: Milestones were reviewed, targets determined for FY 24/25, priorities updated in Sept/Oct 2024.	FCDO / World Bank	YES
2	Maintain focus on EGED branding and ensure government officials are aware of EGED-supported outputs, especially ahead of Annual Review meetings. / Progress: EGED and UK International Development branding were used in public events in the presence of FCDO officials. In bilateral conversations/discussions with the GoUZ partners, the WB team failed to highlight the UK FCDO contribution.	World Bank	PARTIALLY
3	Explore options to ensure EGED reforms on SOE are backed by a political economy analysis; this includes through engaging more extensively with the political section at the UK Embassy. / Progress: WB team update the 2021 inception note though not the political economy analysis (PEA) section. FCDO had discussed vested interests behind SOEs with the colleagues internally.	FCDO / World Bank	PARTIALLY
4	FCDO should assess what more could potentially be achieved through the Delivery Unit to inform future programming decisions. / Progress: FY 24/25 deliverables were determined in a series of consultations with the WB and DU.	FCDO	YES
5	Identify champion/s in the Uzbek Government to work through and align support to the government priorities where needed. / Progress: FCDO team held several meetings with GoUZ officials (both senior and department heads) which helped form a better understanding of champions behind reforms in EGED-supported areas.	FCDO	YES

Lessons learned this year:
The peer-to-peer format with the UK counterparts seems underutilised. Several GoUZ partners kept flagging their interest in learning from UK experience in respective areas, e.g. data governance, privatisation of state assets, fiscal decentralisation. FCDO team may wish to consider supporting the peer-to-peer format in the remainder of the programme.

EGED still has low visibility among partner government officials who do not fully comprehend the FCDO contribution (through the EGED programme) behind the World Bank technical assistance. It is crucial for FCDO team to (i) build/maintain relations with the mid-management level in the partner line ministries who feed the information up the chain, (ii) hold FCDO-led EGED event albeit small they will be, and (iii) implement programme communication plan.

While sharing and communication between the WB and FCDO teams have improved, the pattern is not uniform across the WB teams delivering the EGED programme in Uzbekistan. The FCDO team often struggles to receive regular sufficient detail on the implementation, risk management, and status of deliverables for some work streams, e.g. WTO accession. The post-factum approach in sharing with FCDO practiced by some of the WB teams must change.

Recommendations for the year ahead:
	Recommendation	Owner	Deadline
1.	While small additions/expansion of the current programme portfolio may be reasonable (FCDO to decide in each case), the focus in FY 25/26 should be on achieving policy change and quantifying the impact of these changes.	World Bank, FCDO	Throughout the year
2.	Assess what more could be achieved through the Delivery Unit in Uzbekistan or wider region and to inform future programming decisions, keeping in mind the clarity of deliverables and impact.	FCDO	Sept/Oct 2025
3.	Ensure monthly communication with FCDO across all WB teams delivering EGED, proactive sharing about progress and any challenges/risks arising.	World Bank	Continuous
4.	Continue enhancing visibility of EGED to ensure government and other stakeholders are aware of EGED-supported outputs (e.g., through FCDO-led events, bilat meetings with senior and mid-management of GoUZ partner ministries, joining WB/GoUZ meetings, active external comms).	FCDO	Throughout the year
[note] 2024 Annual Review had noted the request for assistance from the Delivery Unit evolved over the years, expanding in scope from the original ask. This had stretched the hired expert’s capacity and blurred the understanding of the impact.

Output Title	Kazakh government's Statistics Office supported to enhance evidence based policy development in Central Asia (World Bank)
Output number:		4	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes - Up

Indicator(s)	Milestone(s) for this review	Progress
4.2 Data literacy: Public sector capacity for data analysis and use of evidence in policymaking improved	2025 AR to review progress of 2024 milestones	NOT MET. The programme targets were achieved in Kazakhstan but not Tajikistan, Uzbekistan and Kyrgyz Republic. The programme is still ongoing and accepting participants from three countries.
4.3 Statistics capacity: Sector-specific and leadership capacity of Bureau of National Statistics practitioners improved	Indicator reviewed in 2024 AR	N/A
4.4 EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Kazakhstan (L2Kaz)	Indicator reviewed in 2024 AR	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Most targets of Output 4 were delivered in FY 23/24 and reviewed in 2024 programme Annual Review. The EGED programme in Kazakhstan received support from collaborating government institutions and fostered productive inter-institutional partnerships (between UK ONS and Kazakh Bureau of National Statistics (BNS)). The only underperforming work stream was the data literacy programme, which is reviewed in FY 24/25. An online data literacy training course for Central Asian public officials, general population and civil society has been developed in collaboration with the BNS. It is available on an e-learning hub - Data Literacy Hub, accessible in multiple languages, including English, Russian, Kazakh, Kyrgyz, Tajik, and Uzbek. The data literacy e-learning course has been officially launched in 2024, yet the number of public officials in Kyrgyzstan, Tajikistan, and Uzbekistan completing the training remains below the target. The World Bank team continues advertising the course, expecting to reach the target of at least 30 public officials from each country (except Kazakhstan) to complete the training by December 2025. The World Bank will draft and publish a policy note on the data literacy training results.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes made to this Output. The data literacy training for public officials in the Kyrgyz Republic, Tajikistan and Uzbekistan was the only pending deliverable in FY 24/25.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations:

	Recommendation & Progress	Owner	Achieved
1.	Programme deliverables in Kazakhstan can be expanded considering strong buy-in and better capacity. / Progress: FCDO agreed with the World Bank team to extend fiscal incidence analysis to Kazakhstan in FY 25/26.	FCDO	PARTIALLY
2.	Success of collaboration between UK and Kazakh Statistics Offices could be replicated in other EGED countries. This can be done by providing trainings, mentorship support, leadership programme and access to online courses. / Progress: FCDO facilitated a visit of UK ONS to Kyrgyzstan, Tajikistan and Turkmenistan in April 2025. Collaboration plan and a follow-up workshop are due in Sept 2025.	FCDO	YES

Lessons learned this year:

The institutional partnership between UK ONS and BNS continued without any funding from the programme, demonstrating the value of peer-to-peer collaboration when based on mutual interest.

Lack of progress on the uptake of the data literacy training across non-Kazakhstan public officials may have various reasons spanning from genuine lack of interest to the training content to poor targeting and advertisement. FCDO team needs to better understand the reasons behind low uptake and draw lessons shall similar regional training courses be offered until the programme end.

 Recommendations for the year ahead:

	Recommendation	Owner	Deadline
1.	Expand the programme footprint in Kazakhstan – recommended areas include equity review of public revenue policy and transparency/accountability for select economic reforms (e.g. mining, taxation, energy transition, government procurement).	FCDO	Sept 2024

Output Title	Governments and private sector in Kyrgyzstan, Tajikistan, and Uzbekistan supported to increase revenues through e-commerce (World Bank E-GATE)
Output number:		6	Output Score:			A+
Impact weighting (%):		20%	Weighting revised since last AR?			Yes - Down

Indicator(s)				Milestone(s) for this review	Progress
6.2 Horticulture Export to Global Markets through E-commerce channels: export volumes increase				N/A (activity dropped in 2024)	N/A
6.3 Onboarding SMEs to global B2B e-platforms: sales volumes increase				For every dollar of EGED E-GATE programme funding spent (100%) and events (50%), facilitate more than 1.5 USD of e-commerce sales in two years' projection for firms that have onboarded for at least 6 months	EXCEEDED. / The E-GATE program generated over $23 million in exports, delivering a return of more than 23 times the initial FCDO investment of less than $1 million.
6.4 Promotional events to attract global resources to Central Asia e-commerce markets: number of events held				Targets delivered & reviewed in 2024	N/A
6.5 Demand-driven regulatory support to the governments: number of advisory knowledge products delivered				Targets delivered in 2024.	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 6 sought to help reduce poverty by opening new opportunities and broadening market access for Central Asian producers and smaller business entities. Shortly after its launch, the World Bank team re-branded the e-commerce workstream into E-GATE – Elevating Global Access through E-commerce in Central Asia. Output 6.3 in FY 24/25 exceeded the expectations and scored A+.

The E-GATE programme supported 83 SMEs from Kyrgyzstan, Tajikistan, and Uzbekistan to start global sales through the global B2B e-commerce platform Alibaba.com. Over $23 million in export contracts were secured across the participating SMEs from the three countries. This represents a 23-fold return on investment where less than $1M of the FCDO spend leveraged over $23M in confirmed exports and pipeline. The project helped Central Asia SMEs access new markets across Europe, Africa, and the Americas. SMEs reported a mindset shifts, having realised that the global markets were within reach.
[note] SMEs from Kyrgyzstan were successful – companies faced difficulties in securing contracts for several reasons – delays in sample dispatch, issues with quality certificates of products, etc.

The E-GATE engaged women-led firms and firms located in rural areas. It also supported job creation (about 20% of firms hired new personnel for e-commerce roles, predominantly offered to youth and women). The project triggered legislative changes in three countries with varying, yet positive, impact on business environment and regulatory framework: (i) in Kyrgyzstan the first E-Commerce Consumer Protection Law was passed; (ii) in Uzbekistan, E-GATE recommendations on dispute resolution were incorporated into the Cabinet of Ministers Resolution #885 on e-commerce development; (iii) in Tajikistan, E-GATE recommended the government to reform the postal licensing regulations – a major bottleneck for B2C delivery.

Both, FCDO and World Bank approached the project as a scalable pilot. The pilot proved successful – the World Bank is working on scaling it up through IGNITE Trade MPA, now in preparation. The digital regulators from three countries publicly endorsed new E-Bridge vision – E-GATE off-spring to facilitate regional digital trade.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following 2024 AR, activities under output indicators 6.2 (Horticulture Export to Global Markets through E-commerce channels) and 6.5 (Demand-driven regulatory support to the governments) were discontinued, agreed by the FCDO and World Bank.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations:
	Recommendation & Progress	Owner	Achieved
1.	Following the first evaluation in 2024, evaluate the alignment of chosen firms to the original objectives of the project. / Progress: E-GATE shared the profiles of the chosen firms, which confirmed the alignment with the original objectives.	FCDO/ WB	YES
2.	Review the programme management arrangement for E-GATE to address gaps in reporting of plans, spending and risks. / Progress: WB team made effort to enhance communication with FCDO through regular result-sharing and engagement updates.	FCDO/ WB	YES
3.	Agree clear workplan on regulatory reform following the assessment due in August 2024.	FCDO/ WB	NO / (activity discontinued)

Lessons learned this year:
The fittest firms benefited most from the access to the global market that the project had facilitated for them. Many participating firms expected the registration on Alibaba.com would bring quick and substantial wins (new purchase contracts) without much investment – both human and resource from the firms. Insufficient experience in cross-border trade procedures, managing an online shop, production and human capacity constraints were the starting point for about 90% of chosen firms. Of 83 firms only 20% managed to succeed – these are the firms fittest to the compete for consumers globally.

Sector targeting matters: B2B contracts favoured high-volume or standardised goods; niche or bulky items (e.g., soap, heavy manufacturing) fared worse.

Policy and infrastructure development must align to allow e-commerce to generate multi-billion profits (as, for example, in the UK). Customs, payments, logistics, and technical regulations are major barriers still needing reform.

Job creation is hard to verify in the short term, especially since firms opt for outsourcing rather than hire in-house staff due to the lack of qualified/experienced experts in the labour market and for cost efficiency.

Recommendations for the year ahead:

E-GATE project was completed and closed, thus not applicable.

Output Title	Regional economic development improved as a result of a CSO-participatory, gender-inclusive approach and increased coordination among Local Self-Governments, Ministries and CSOs
Output number:		7		Output Score:		A+
Impact weighting (%):		15%		Weighting revised since last AR?		Yes - Up

Indicator(s)			Milestone(s) for this review		Progress
7.1 Regional development (1): Percentage of development activities listed in the Socio-Economic Development Plans (SEDPs) implemented through the Coordination Councils			At least 10% of development activities approved in new SEDPs (At-Bashy and Nookat, and 5 new districts) have been implemented, funded by the state and other alternative sources, covering a range of economic sectors.		EXCEEDED. Per local state administrations, average implementation rate across 7 target districts was 27%: / - Aitmatov (new) 43%, / - At-Bashinsky (old) 31%, / - Bazar-Korgonsky 12%, / - Dzhety-Oguzsky (new) 7%, / - Kadamdzhaisky (new) 5%, / - Keminsky (new) 12%, / - Nookatsky (old) 77%.
7.2 Regional development (2): Number of new districts where Co-ordinational Council is operating with SEDP being developed			1) 5 new Coordination Councils established in 5 more pilot districts with SEDP developed. / 2) At least 500 local civil society and business representatives took part in SEDPs co-creation process (based on new methodologies) on municipal and district level.		MET. All 5 new pilot districts have Coordination Councils and approved their SEDPs. / EXCEEDED. 576 civil society representatives (26% of the total number of participants), including 44% women). FAQ Book prepared to assist LSGs in the development of their SEDPs.
7.3 Regional development (3): Local economy growth and improved public services (factual and/or projected) in target districts as a result of multistakeholder engagement around SEDP design and delivery			At least two verified cases of local economy growth (revenue in sector, new jobs, rising local resident income, inward investment) as a result of new SEDPs implementation. Analytical forecast for new target districts based on administrative and statistical data. At least five stories of change in local residents' wellbeing.		MET. 2 verified cases of local economic growth in 2 "old" pilot locations and 15 industry forecasts in 7 "new" pilot locations.
7.4 Regional development (4): Impactful exchanges in the field of LSG reform between Central Asian peers			Senior management visit of Uzbekistan Mahalla Association to the Kyrgyz Republic. MoU signed betwwek Uzbek and Kyrgyz LSG authorities.		MET. MoU signed, an action plan was developed, which is already being implemented.

Briefly describe the output’s activities and provide supporting narrative for the score.

In FY 24/25, Output 7 was fully delivered by Kyrgyzstan-based NGO – Development Policy Institute (DPI). DPI has done a commendable job of training and mentoring pilot districts the SEDP methodology and helping to scale its adoption across the country. DPI utilised strong partnership with Ministry of Economy and Commerce (MoEC), Central Asian Local Governments Academy (CA-LGA), and Kyrgyz Union of Local Self Governments (U-LSG) to deliver the work.

The most robust part of the intervention in FY 24/25 has been the strong partnership of local government capacity building centres. DPI offers a strong expertise in developing tools and piloting them, which CA-LGA can scale at pace. The U-LSG brought in political weight and expertise – all three entities worked credibly with the MoEC.

The documentation of local economy growth (revenue in sector, new jobs, rising local resident income, inward investment), recorded in two pilot districts (At-Bashy and Nookat) thanks to new SEDPs implementation are interesting examples of how the programme is beginning to show impact. Yet, it would be also useful to show (through testimonies) how local officials and Coordination Councils are using the SEDP to improve their planning process in public service provision along with local economic growth.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The only major change is, as above, Output 7 was delivered entirely by DPI in FY 24/25 following the ACTED phase-out from the programme in Kyrgyzstan.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations:

	Recommendation & Progress	Owner	Achieved
1.	Consider contracting DPI directly to scale up support to LSGs and CSOs in implementing the new SEDP system / Progress: FCDO had contracted DPI directly as of 1 September 2024 after phasing out ACTED.	FCDO	YES
2.	Monitor sustainability of recent improvements in SEDP system and plan for evaluation / case study in 2-3 years’ time. / Progress: World Bank and DPI kept track of SEDP roll-out and use by local and village authorities. PCR will evaluate the impact on local planning and growth.	FCDO, World Bank	YES
	Consider offering additional support to CSO partners to build their resilience amid the foreign agent law enforcement. Look at opportunities to bring in experienced INGOs or individual experts to train CSOs on how to legally respond to the new law and adapt policy advocacy. / Progress: FCDO had contracted ICNL for short-term assignment in Kyrgyzstan, Tajikistan, and Uzbekistan to deliver resilience capacity building to at-risk NGOs.	FCDO	YES

Lessons learned this year:

Removing the intermediary – ACTED, helped build coherent and robust intervention that delivered agreed results, eased the burden on FCDO to manage the intervention, and substantially improved the visibility of UK and EGED as contributors to sub-national development.

The collaboration among DPI, CA-LGA, U-LSG, and MoEC created a structured public-civil society-political partnership, through which different capacity building initiatives for local economic development can and should be managed in the future. These partnerships does present an avenue to test and trial interventions dedicated to local economic growth beyond SEDP, e.g. modules for SME promotion and encouraging inward investment, rolling out agriculture extension services, or business support services.

 Recommendations for the year ahead:

	Recommendation	Owner	Deadline
1.	DPI to set a cut-off point to build capacity on SEDP, leaving the scale-up to CA-LGA and MoEC. DPI to advise what other capacity building initiatives to pilot	DPI	Sept 2025
2.	DPI to deepen sub-national development work in the pilot locations by helping LSGs raise/increase inward domestic investment to boost local economy.	DPI, FCDO	Aug 2025
3.	Seek a coordinated development partner effort to strengthen CA-LGA through international and regional exposure. CA-LGA to raise revenue (either through LSGs, or national government) from the services they provide to local officials, away from reliance on donor support.	CA-LGA, DPI	Throughout the year
4.	DPI to identify policy space in sub-national economic development, fiscal decentralisation, and business regulation, where the partnership with the WB could maximise influence and bring policy change.	DPI, FCDO	Oct 2025

Output Title	CSOs' involvement and monitoring of TSA implementation and taxation regime led to increased effectiveness of TSA and improved taxation for CSOs sustainability and productive employment of PWDs
Output number:		8	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, Up

Indicator(s)	Milestone(s) for this review	Progress
8.1 Financial sustainability of CSOs: Increase in business funding channelled to CSOs (targeted for SEPP II)	1) At least 5 CSOs (graduates of SEPPIII) attract at least 10% of their annual income from private sector. / 2) Up to 5 CSOs (graduates of SEPPIII) receive loans from microcredit organisations/banks (interest rate covered by EGED grant) for best business ideas. 3) At least 80% of social enterprises that received financial support from EGED project, continued their operations post-investment among graduates of SEPP I and SEPP II trainings.	EXCEEDED. 10 CSOs from the SEPPIII cohort reported that on average 78% of their annual income came from the private sector sources. / MET. 15 CSOs submitted applications for blended finance; 5 CSOs selected for subsidised loans (EGED covering the interest rate). / MET. 100% of supported CSOs from SEPPI and SEPPII remain operational and continue reinvesting in their social enterprises.
8.2 Financial sustainability of CSOs: / Improved conditions for financial sustainability (FS) for CSOs as a result of new tax regulations in the Tax Code.	1) At least 5 new tax regulations for social enterprises (SE) development proposed and at least 3 adopted by the Tax Committee. / 2) At least 4 new SE-specific indicators were introduced and approved by MoEDT for the MTDP 2026-2030 as a result of advocacy campaigns and policy dialogue events based on expert analysis. 3) Impact of EGED's Research on the Economic Benefits of Social Entrepreneurship in leading to the Adoption of SE Legislation	MET. Three tax reliefs endorsed by the Tax Committee. / PARTIALLY MET. 4 new indicators (inclusion and innovation) included in the draft MTDP 2026-2030, not approved at the time of this review. / MET. EGED-funded research coupled with stakeholder consultations and CSO accelerated the adoption of the Social Entrepreneurship Law.
8.3 Effectiveness of dialogue platforms / % of targeted dialogue platforms that became more inclusive demonstrating increased participation from all stakeholders measured through PIP index	PIP index of the target dialogue platforms scored 80 out of 100	MET. 14 NDC IWGs assessed through PIP scoring 84.23 out of 100.
8.4 Targeted Social Assistance (TSA): Civil society engagement in TSA programme implementation is formalised through government policy for next three years	1) The State TSA Program (2024-2028) is formally adopted by the GoT, including provisions for CSOs to take part in implementation and monitoring. 2) MoHSP integrates TSA monitoring in its social order process	NOT MET. The adoption of the State TSA Programme 2024-2028 is pending. However, some key policy changes are secured to institutionalize civil society engagement. / NOT MET. Advocacy efforts are still underway to integrate TSA monitoring into State Social Order.
8.5 Targeted Social Assistance (TSA): The number of TSA in-need recipients in DRS is increased as a result of CSOs efforts based on the official statistics from the ASP	Minimum 10,000 direct beneficiaries (through 6 supported small grants) in the Sughd region and GBAO have increased knowledge of the TSA mechanism as a result of an outreach campaign, leading to minimum 30% increase of recipients in the target regions	EXCEEDED. The outreach campaigns in Sughd and GBAO reached over 11,000 people. Per the SASP, approved TSA applications in target districts increased by 31% in 2025 compared to 2024, with overall 40% rise in total applications.
8.6 Targeted Social Assistance (TSA): Decrease in volume of TSA informal payments to local authorities in the target districts of DRS following the improved transparency of TSA mechanism and better oversight of CSOs	1) 30% drop in informal payments as monitored by CSOs in the target districts of Sughd Region (3 districts) as a results of the TSA awareness raising activities and anti-corruption training sessions. 2) MoHSP has formally integrated the Anti-Corruption module into the curriculum of its Capacity Building Institute for Social Protection Specialists.	MET. The Anti-corruption ARCs and trainings in three districts of Sughd region led to a 47.5% decrease in reported informal payments related to TSA services. / MET. EGED’s anti-corruption training module was integrated into the curriculum of the Institute for Social Protection Specialists.
8.7 Number of new evidence-based indicators for social protection and employment adopted by the National Development Council	1) At least five new evidence-based indicators for Productive Employment and Middle Class will be developed and adopted by the National Development Council in the MTDP 2026–2030, based on recommendations from the research on productive employment and Middle Class. / 2) At least 5 new evidence-based indicators for social protection will be developed and adopted by the National Development Council in the MTDP 2026-30, aligning with the TSA State Program for 2028 and the State Social Protection Strategy for 2040.	PARTIALLY MET. 5 result indicators designed on employment and middle-class. The indicators were included in the draft MTDP 2026-2030, which is pending formal adoption by the GoT in Sept 2025. / PARTIALLY MET. Five additional indicators covering TSA reach, digital beneficiary registers, certified social workforce capacity, public information campaigns, and grievance redress mechanism proposed for the MTDP 2026-2030; adoption by the NDC expected in late 2025.
8.8 Number of Persons with Disabilities (PWD) provided with job placement support and securing employment	1) At least 6000 direct beneficiaries reached as the result of information campaigns on jobs and training opportunities for vulnerable people in target districts / 2) Up to 1,000 vulnerable individuals, including PWDs, women, and youth (among TSA recipients), received employment opportunities in the target districts.	NOT MET (in progress). / At the time of the review (i) 6 CSOs selected to conduct ARCs in Khatlon, Sughd, GBAO, and DRS, (ii) Adult Learning Centers and SASP agreed to offer access to relevant data. / NOT MET (in progress). / The employment outcomes of the ARCs will be assessed in Sept 2025, after ARCs.

Briefly describe the output’s activities and provide supporting narrative for the score.
In FY 24/25, Output 8 focused on strengthening the engagement in of civil society in the government Targeted Social Assistance (TSA) and wider social protection policy, productive employment, and financial sustainability of CSOs (emphasis on tax exemptions and social entrepreneurship). Output 8 scored B, reflecting progress achieved in some but not all targets. The programme highlights include the reduction of informal payments in TSA, lobbying new KPIs around inclusion, employment, and social protection in the GoT’s Mid-Term Development Plan 2026-2030, and the GoT adoption of the Social Entrepreneurship Law. The output delivered well amid limited civic space and regulatory pressure on CSOs.

CSO financial sustainability (indicators 8.1, 8.2)
This work was delivered through (i) SEPP (Social Entrepreneurship Pre-Acceleration Programme) training and alternative financing to CSOs, (ii) policy advocacy for tax reliefs. Ten CSO graduates of SEPP III cohort demonstrated income diversification and financial resilience; 5 CSOs were awarded subsidy grant (to cover bank loan interest rate) for the best social entrepreneurship ideas and business plan. All CSOs that received subsidy grants after SEPP I and SEPP II are operational. Challenges remain in scaling business models beyond initial support, with some CSOs still reliant on short-term consultancies and grants.
[note] These CSOs reported an average of 78% of their income came from private sector sources.

The policy advocacy resulted in three amendments to the Tax Code: (i) income tax exemption for organizations with at least 50% PwDs employees, and property tax exemption for similar organizations using real estate for core functions, (ii) simplified tax regime eligibility for SEs meeting the PwD employment and payroll thresholds, (iii) Social Entrepreneurship Law.
[note] Delivered through numerous policy advocacy events, research dissemination, and multi-stakeholder consultations within the Tax Coordination Council, NDC IWGs and among CSOs.

Lobbying development KPIs and improving CSO policy engagement (indicators 8.3, 8.7)
In 2022, the EGED programme helped design and launch the Platform Participation Index (PPI) index - a localised evidence-based mechanism to measure inclusiveness, transparency, and responsiveness in public-private dialogue platforms. In FY 24/25, PIP assessed 14 NDC IWGs – average score 84.23 out of 100 – a jump from 40 in 2022. PIP index helped civil society improve engagement in 4 national public-private dialogue platforms.

Through small-scale research, monitoring of MTDP 2021-2025 delivery, and public discussions with the line ministries responsible for employment, social protection, and economic development, nine new KPIs (result indicators) were lobbied by local CSOs and experts to the MTDP 2026-2030. These KPIs cover inclusion, productive employment, social entrepreneurship, social protection and innovation. The programme contributed to the design of the Human Capital Development section of the MTDP 2026-2030. At the time of this review, KPIs were added to the draft text of the MTDP, pending MoEDT and NDC Secretariat endorsement.

Targeted Social Assistance and PWD employment (indicators 8.4 through 8.9)
The formal adoption of the TSA State Programme for 2024-2028 remains pending. TSA monitoring had not yet been integrated in the State Social Order mechanism. However, the changes introduced through government decrees and ministry (MoHSP) orders demonstrate that EGED helped drive meaningful governance change in the TSA programme – promoted transparency of the TSA mechanism and institutionalised CSO participation in social protection policy delivery.
[note] (1) GoT decree #488 (30 Aug 2024) institutionalized CSO engagement in TSA awareness campaigns and monitoring; created dedicated TSA staff roles within every jamoat; mandated the recruitment of over 400 local TSA officers, all required to possess anti-corruption knowledge. (2) Law of the Republic of Tajikistan #2102 (13 Nov 2024) amended the Law on TSA to establish digital notification systems for applicants – especially benefiting rural residents, and recognized employment reintegration of TSA beneficiaries as a core principle. (3) MoHSP Order #67 set eligibility criteria for local social protection workers, making anti-corruption knowledge a formal requirement.

The TSA awareness raising campaigns expanded its reach in underserved regions of Sughd and GBAO, covering entire country since 2021. The activities included community seminars, door-to door outreach, distribution of printed materials, and media coverage. The ARC improved community residents’ knowledge of TSA entitlement, eligibility criteria, and application process. Increased numbers of approved and total TSA applications and decreasing bribery demonstrated the effectiveness of ARC and suggest growing public trust in and demand for TSA.

To reduce corruption in the TSA, the EGED intervention addressed supply (citizen readiness to bribe) and demand (government officials ask for bribes). In Sughd, ARCs helped reduce corruption in the TSA process – the number of self-reported instances of bribery almost halved. The tailored anti-corruption training delivered to 200+ newly hired TSA specialists, including from remote areas of Tajikistan has been integrated into the curriculum of the Institute for Capacity Building of Social Protection Specialists.

In FY 24/25, FCDO team decided to expand inclusion lens and launched an intervention to improve access to employment and training for vulnerable people, including PwDs, women and youth and TSA recipients. 6000 people are set to be reached out, with employment opportunities facilitated for at least 1000 individuals.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two work streams were added in FY 24/25: facilitation of employment for vulnerable groups and support to designing new KPIs for MTDP 2026-2030.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

	Recommendation & Progress	Owner	Achieved
1.	Monitor whether the five recommendations made by civil society are accepted in the final State TSA Programme and Action Plan - and if the increase in TSA applications is sustained. If so, draft a case study/ ‘success story’ for dissemination in FCDO and more widely. / Progress: Recommendations were included in the draft TSA Programme and Action Plan. The case study has not been finalised by the time of this review.	FCDO/ ACTED	PARTIALLY
2.	Consider offering additional support to CSOs to build their resilience to the increased restrictions on their activities. Look at opportunities to bring in experienced INGOs or individual experts to train CSOs on how to legally respond to the increasingly difficult context. / Progress: FCDO had contracted ICNL for a short-term assignment in Kyrgyzstan, Tajikistan, and Uzbekistan to deliver resilience capacity building to at-risk NGOs	FCDO	YES

Lessons Learned this year:
CSOs can be drivers of policy reform when entry points and political economy is navigated correctly. The successful CSO advocacy for the tax reliefs and SE Law showed the spaces CSOs need to be in and a model that can be replicated to influence economic policy beyond social protection.

The blended finance, access to loan, and business mentoring (SEPP) triggered a mentality change among the CSOs – many realised they could be credible social entrepreneurs capable of scaling impact, not just service providers. Yet, further business mentorship and peer learning are needed to sustain this change among EGED SEPP graduates.

EGEDs advisory inputs into strategic development policy frameworks like the MTDP show that the adoption of evidence-based KPIs require patient and longer-term relationship with the government, and ability to navigate shifting political priorities.

The remarkable drop of informal payments in the TSA was only possible due to a layered approach, combining ARCs, institutional reforms, and mandatory anti-corruption trainings. This highlights that complementing the top-down and bottom-up approaches SMART-ly in a governance programme is highly likely to generate intended result.

 Recommendations for the year ahead:

	Recommendation	Owner	Deadline
1.	Institutionalise and handover successful CSO led pilots (ARCs, PIP index, TPMs, SEPP model, anti-corruption training module). This includes handover of ARC design and training materials to MoHSP, transferring PIP index methodology to the NDC Secretariat, transferring anti-corruption module to the Institute for Social Protection.	FCDO, ACTED	October, 2025
2.	Deepen financial sustainability pathways for CSOs through facilitating peer learning. Support the creation of the SE SEPP alumni club to support, share and transfer revenue models. Advocate for blended finance special products in banks.	FCDO, ACTED, / ROST	October, 2025
3.	Present the Pillar II cases at the EGED Conference, Donor Coordination Council and/or its Governance Working Group. Draft an externally facing brief summarising EGED Pillar II contributions, lesson learnt, and results to be disseminated within FCDO, donor community, and local CSOs.	FCDO	October, 2025
4.	Monitor the impact of Pillar II institutional reforms post-ACTED. Develop a simple Results Monitoring Framework to track the institutional reforms beyond ACTED’s phase out.	FCDO	Throughout 2025-2026

## D: VALUE FOR MONEY

Key cost drivers and performance
The key cost drivers under Pillar 1 remained unchanged: World Bank staff costs, consultancy costs (individuals and firms) and travel. Under Pillar 2, the cost drivers were staff time (core and support), downstream partners’ staff costs, consultancies, service delivery, travel and purchase of low-value assets. Both pillars incur costs for events. Overall performance has been good with clear evidence of effective spend, reaching the set objectives and making real-world change.

VfM performance compared to the original VfM proposition in the business case
All three lead implementing partners used VfM metrics in FY 24/25 - ACTED and DPI did particularly well on tracking the VfM performance based on indicators. The latter was encouraged through the Value for Money refresh work the Ecorys delivered in FY 23/24.

Economy
All three lead delivery partners tried to keep the costs of the inputs low and tracked the spend. Examples include: (i) WB external consultancies fees are capped to a mid-point of the grade above which a director’s waiver is required, (ii) travel expenses of the WB staff missions were kept low – less than a tenth of the actual costs due to charging multiple budgets, (Iii) the cost per interview for Listening to surveys ranged between USD 5.60 and 8.70 per interviewee, compared to USD 14.50 in Mongolia and USD 33 in East Asia, (iv) the cost per one Listening roundtable was kept low – around $300 per event, as these events were routinely held in the WB offices in Kazakhstan, Kyrgyzstan and Tajikistan, (v) 21% was saved on the purchase of catering services during outreach meetings (DPI), (vi) £2.17 per beneficiary was spent during the TSA awareness raising campaigns (Tajikistan) that reached 11,000 potential TSA recipients.
[note] Higher rates were offered to less than 1% of consultants on the EGED consultants’ roster.

Efficiency
There was also good evidence of efficient spend of EGED resources. Examples are: (i) WB staff time charging a fraction of its time to EGED due to engagement in the wider WB country programmes, (ii) number of training and conference participants exceeding the plan by 37% on average for the same cost (DPI), (iii) cost sharing of sub-national development events by the Swiss and U-LSG (DPI).

Effectiveness
There were several examples of the EGED spend reaching its intended objectives, including but not limited to the following: (i) two big analytical pieces (worth less than $300K) having informed the PFM and SOE reform (being drafted) strategies in Uzbekistan that can save and raise USD millions for the budget, (ii) impressive gains through the e-commerce intervention, where under $1mln investment generated $23mln in export contracts (23-fold return), (iii) substantial enhancement of capability of local authorities in designing local development plans from 27% to 86%, (iv) spending £873.50 per CSO for capacity-building, mentorship, and private sector networking triggering an average of £3,700 in private investment per CSO, (v) £29,723 worth intervention brought corruption in the TSA down by 47%.

Equity
In FY 24/25, more than 75% and 55% of the WB EGED programme budget in Kyrgyzstan and Tajikistan was spent on sub-national socio-economic development, social protection and poverty reduction which have an explicit poverty and inclusion focus. The introduction of the fiscal incidence analysis across the EGED countries brought additional equity lens in the discussion of fiscal policy. The SEDPs inclusivity review done by DPI revealed significant differences between the programme target and non-target locations, favoring the former – demonstrating the EGED’s impact. The target municipalities have significantly more measures in SEDPs that respond to the needs of vulnerable groups: improving economic conditions, expanding service provision, improving access to infrastructure, and increasing participation of vulnerable groups in development and decision-making.

Source: DPI self-assessment report, June 2025.

Assessment of whether the programme continues to represent value for money
EGED continues to represent good value for money, bringing about positive change for relatively modest resources invested to date. Additionality of the World Bank support maximises the impact. Complementarity of intervention through the programme’s Pillar 2 demonstrated cautious success amid a challenging operational environment for civil society. EGED continued to respond well to Post Country Business Plans.

E: RISK

Overall Risk Statement
EGED remained within risk appetite this year. The overall programme risk rating continues to be Major, driven by persistent challenges in the civic space, delivery, and safeguarding. Most risks are assessed as moderate, and mitigation measures have been largely effective. No incidents disrupting the programme delivery or damaging the UK reputation were recorded in FY 24/25. Challenges in engaging with government stakeholders (Uzbekistan) and implementing partner risk management practices continue to require close monitoring. Consistency across delivery partners in updating risk registers quarterly is expected.
[note] Safeguarding/security risks for journalists producing content which cover or may be perceived to cover politically sensitive issues.

Main Risks and Risk Management
The space for civil society policy advocacy remained restricted in EGED recipient countries with Kyrgyzstan on a downward trend. The FAL enacted in Kyrgyzstan in 2024 constrained working with and through civil society. This limited the EGED Pillar 2 economic journalism to working through the line ministry (MoEC). In Tajikistan, the approach for civil society engagement in economic policy taken forward through EGED proved to be an optimal choice – working on politically less sensitive policy issues, using scenario-based risk assessments. In Uzbekistan, civic space remains limited FCDO continue to monitor the situation; additional support to strengthen CSO resilience is welcome via the programme or EECAD Resilience Programme (ERP).

The USAID dismantling exposed local CSO extreme donor dependency and lack of credible financial resilience. EGED Pillar 2 lead implementers (ACTED and DPI) and their partners in the field were affected to varying degree by the cuts. Both, ACTED and DPI continue to operate thanks to the diverse funding flows and agile strategies in place. To mitigate the impact of drying up donor funding on smaller CSO partners in the field, the EGED continued training CSOs in launching social enterprise and using blended finance. Furthermore, the US President statements on the destructive nature of USAID foreign aid made it harder to work with regional authorities. DPI and FCDO managed the risk through targeted external communication showcasing the value of the local governance reform and EGED contribution to Kyrgyzstan economic development.
[note] DPI was the Tier 1 implementing agency for the USAID Local Governance project.

Delays in delivery were noted across three countries due to slipping timelines of the government partners or their slow responsiveness, e.g. around 2025-2030 PFM Strategy approval in Uzbekistan, the 2025-2030 State Programme on Regional Development in Kyrgyzstan, and TSA impact assessment in Tajikistan. EGED implementing partners mitigated these delays by reallocating resources to other work streams and strategic patience with government counterparts (e.g., through seeking FCDO no-cost extension approval to finalise outputs).

Visibility of EGED and UK International Development among key government stakeholders remained blurred in Tajikistan and Uzbekistan. In Kyrgyzstan, DPI dedicated use of programme branding at the public events/products and in communication with the government beneficiaries helped make clear the EGED’s unique contribution. FCDO should promote EGED among key audiences using different channels, particularly toward the programme end, when policy change start delivering tangible outcomes.

Fiduciary risks were mitigated by strong financial controls and zero tolerance to corruption and fraud. The World Bank and ACTED reported on concerns and remedial measures to FCDO where fraud risk went beyond appetite. No safeguarding incidents were reported. Gender, disability, and environmental risks remained low. While all EGED implementing partners managed risks, not all followed the FCDO programme standard of updating risk registers quarterly and applying political economy analysis. A refresh of DDAs for the World Bank and ACTED is recommended.

Update on Partnership Principles (delete this section if n/a)

The UK has Strategic Partnership and Cooperation Agreements with Kazakhstan and Uzbekistan but not yet Kyrgyzstan and Tajikistan. The partnership agreements with Kazakhstan and Uzbekistan record commitments of both countries to respect for democracy, principles of international law and human rights as defined in the United Nations Charter, the Helsinki Final Act and the Charter of Paris for a New Europe, as well as the principles of market economy. British Embassies Astana and Tashkent monitor government performance against these principles. UK does not provide ODA directly to the Governments of Kazakstan, Kyrgyzstan, Tajikistan or Uzbekistan - neither through budget support, nor direct financing of governments or government programmes. Some of the UK-funded bilateral development programmes provide technical assistance to the governments through the International Financial Institutions (e.g. the World Bank Group) and third parties subject to financial controls. The EGED programme is consistent with this approach.
[note] See Partnership and Cooperation Agreement between UK and Uzbekistan - CP 1226 and CP 1365 – Strategic Partnership and Cooperation Agreement between the United Kingdom of Great Britain and Northern Ireland and the Republic of Kazakhstan.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery
During the past year, the programme delivery continued through three lead implementing partners – the World Bank, ACTED and DPI. The World Bank continued delivering Pillar 1 across the region; ACTED implemented Pillar 2 in Tajikistan; the DPI took over the delivery of Pillar 2 in Kyrgyzstan and partly, Uzbekistan. Two smaller direct grant agreements were managed by FCDO team with ICNL and NGO ‘SABR’ (Uzbekistan).
[note] FCDO phased out ACTED in Kyrgyzstan (August 2024) and Uzbekistan (January 2024).

The World Bank delivers through the Umbrella Facility for Poverty and Equity Multi-Donor Trust Fund (MDTF) Administrative Arrangement signed with FCDO in October 2021. Prior to this, a 12-month Externally Financed Output (EFO) was signed in February 2021 to launch the programme and deliver initial agreed outputs.

Until 2024, Pillar 2 was delivered by ACTED through the Accountable Grant Agreement signed with the FCDO on 1 July 2021. ACTED was phased out in Uzbekistan in January 2024 following the 2023 Annual Review recommendation. In August 2024, ACTED was phased out in Kyrgyzstan following the 2024 Annual Review and an independent Value for Money assessment (performed by Ecorys), which recommended the change of the delivery partner for Pillar 2 in the country. DPI took over the implementation as of September 2024.

FCDO maintains overall management arrangement to facilitate the delivery and relationships with all the partners. SRO and Programme Managers in Astana, Bishkek, Dushanbe, and Tashkent hold regular progress and result review meetings with all partners in respective countries. The management of a complex, multi-partner, and multi-team programme like EGED cannot use one-size-fits-all approach as the partnership modality differs for the EGED delivery partners. The relationship between the World Bank teams and FCDO varied across countries and teams within the World Bank. While open and constructive communication with the Poverty and Equity team continued, reporting and accountability by some teams (e.g., those leading the WTO accession and Kazakhstan output) was not as effective as they could be.

FCDO/ACTED relations in Tajikistan continued to be open and constructive – yet, ACTED could do more to share whether and how EGED model or its elements were used by ACTED in grant proposals to other donor organisations. ACTED shall follow the FCDO visibility and recognition disclaimer at any time the programme elements including its model are used to attract donor funding. FCDO/DPI relations were honest and solution-oriented, particularly around discussing the challenges of delivering data-driven economic journalism in Uzbekistan.

Financial and commercial performance
The programme spend is monitored by the SRO and PRO (Regional Programme Manager) for each implementer through quarterly (ACTED, DPI, ICNL, NGO SABR) and annual (World Bank) reporting, including regular meetings on the spend forecast.

Payments to the World Bank Trust Fund are made annually in line with the Administrative Agreement and payment schedule. Each new tranche is paid once more than 80% of the previous tranche has been utilised and/or committed. FCDO has access to the World Bank Trust Fund Development Partner Centre, which offers updates on financial flows and spend. FCDO also receives annual MDTF financial reports showing the utilisation of the UK and other donors’ contribution. The next audited statement is expected in September 2025.

ACTED is paid quarterly and in arrears upon receipt of quarterly progress report. Funding provided to ACTED is received by its headquarters (HQ), which is responsible for administering the funds and distributing them to the field offices monthly. ICNL followed the same approach of payment in arrears. DPI and NGO ‘SABR’ received first tranches as advance due to low cashflow needed to kick start delivery of their outputs. Financial reports are submitted to FCDO quarterly. An external audit report for ACTED is expected in September 2025. The audit reports for other partners are expected by end 2025. Each partner uses its procurement procedures, validated through the FCDO Due Diligence process. In FY 24/25, FCDO conducted a spot check of ACTED in November 2024.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
FCDO team continued using several instruments – oral and written, to monitor the delivery progress across the implementing partners. Some tools were uniform with all implementing partners (e.g. regular progress conversations), others used more with the NGO implementers than the World Bank (e.g. quarterly narrative and financial reports). FCDO programme managers (PMs) held either bi-weekly or monthly progress check-ins with all delivery partners. They attended all programme-funded events in country. PMs also joined SRO quarterly result reviews with partners. SRO held regular leadership call/meetings with the World Bank, ACTED, and DPI, and occasionally with the management of select downstream partners.

ACTED and DPI submitted quarterly narrative and financial reports to FCDO. In addition, DPI shared monthly briefs, while ACTED – the Annual Progress Report for April 24 to March 25). Both partners submit the self-assessment before the Annual Review. The World Bank submits the self-assessment prior to the Annual Review.

In FY/24/25, the FCDO team commissioned GEDSI review of EGED programme to generate a holistic account of the programme input to gender equality and inclusion. The GEDSI review is carried out by Ecorys – the EECAD Monitoring, Evaluation, and Learning framework contractor, from April to July 2025. Besides, the FCDO team agreed two output-level evaluations with the World Bank: one to assess the poverty reduction implication of the reformed Targeted Social Assistance programme (Tajikistan), another – to explore the impact of the new Labour Code (Uzbekistan) on medium and large size firms.

The FCDO team is looking forward to conduct: (i) evaluation of Pillar 2 in Tajikistan in the autumn 2025, and (ii) a programme evaluation in the autumn 2026 before the programme ends.

Learning
Lessons learned from the delivery and thematic work streams were captured in various ways. ACTED and DPI integrated the lessons learnt in quarterly and final/annual progress reports. The World Bank recorded learning in the self-assessment report shared before this annual review. All implementing partners followed internal policy and practice of collecting and recording learning.

Date of last narrative financial report	World Bank – June 2025 / ACTED – May 2025 / DPI – June 2025	Date of last audited annual statement	World Bank – September 2024 / ACTED – September 2024

Annex 1

List of acronyms

Acronym	Meaning
ACTED	Agency for Technical Cooperation and Development
AMP	Aid Management Platform
AR	Annual Review
ARC	Awareness-Raising Campaign
BNS	Kazakhstan Bureau of National Statistics
CA-LGA	Central Asian Local Governments Academy
CEQ	Certainty Equivalent Analysis
CGE-GIDD	Computable General Equilibrium – Global Income Distribution Dynamics
CODI	Core Diagnostic Assessment
CSO	Civil Society Organisation
DPI	Development Policy Institute (Kyrgyz Republic)
DRS	Districts of Republican Subordination (Tajikistan)
DU	Delivery Unit (Uzbekistan)
EECAD	Eastern Europe and Central Asia Directorate
E-GATE	Elevating Global Access through E-commerce in Central Asia
EGED	Effective Governance for Economic Development
ERP	EECAD Resilience Programme
FAL	Foreign Agent Law
FCDO	Foreign, Commonwealth and Development Office
FY	Fiscal Year
GBAO	Gorno-Badakhshan Autonomous Oblast (Tajikistan)
GEDSI	Gender Equality, Disability, and Social Inclusion
GoKR	Government of the Kyrgyz Republic
GoT	Government of Tajikistan
GoUz	Government of Uzbekistan
ICNL	International Center for Not-for-Profit Law
IFI	International Financial Institution
INGO	International Non-Governmental Organization
L2CU	Listening to the Citizen of Uzbekistan
L2Kaz	Listening to Kazakhstan
L2KGZ	Listening to the Kyrgyz Republic
L2T	Listening to Tajikistan
LSG	Local Self-Government
MoEC	Ministry of Economy and Commerce (Kyrgyzstan)
MoEDT	Ministry of Economic Development and Trade (Tajikistan)
MoHSP	Ministry of Health and Social Protection (Tajikistan)
MoU	Memorandum of Understanding
MTDP	Medium-Term Development Programme
NDC	National Development Council (Tajikistan)
NGO	Non-Governmental Organization
NSC	National Statistics Committee
ODA	Official Development Assistance
PEA	Political Economy Analysis
PEFA	Public Expenditure and Financial Accountability
PFM	Public Finance Management
PIAD	Programme for Integrated Accelerated Development
PRO	Programme Responsible Owner
PWD	People with Disabilities
SDGs	Sustainable Development Goals
SE	Social Entrepreneurship
SEDP	Socio-Economic Development Plan
SEPP	Social Entrepreneurship Pre-Acceleration Programme
SMEs	Small and Medium-sized Enterprises
SOE	State-Owned Enterprises
SRO	Senior Responsible Owner
ToC	Theory of Change
TOR	Terms of Reference
TSA	Targeted Social Assistance
U-LSG	Kyrgyz Union of Local Self Governments
UzSAMA	State Assets Management Agency (Uzbekistan)
WB	World Bank
WTO	World Trade Organization