## LogFrame
|  |  |  | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
PROJECT TITLE | Effective Governance for Economic Development in Central Asia
IMPACT | Impact Indicator 1 |  | Baseline (2020) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2026)
More stable, open and transparent economies with resilient growth in Kyrgyzstan, Tajikistan and Uzbekistan | World Governance Indicators: Regulatory quality estimate TJK/UZB/KGZ | Planned | TJK: -1.1; UZB -.95; KGZ: -.54 | at least 0.1 improvement from the baseline | at least 0.1 improvement from previous milestone | at least 0.1 improvement from previous milestone | at least 0.1 improvement from previous milestone | TJK: -.60; UZB -.30; KGZ: -.20
Achieved
Source
| Impact Indicator 2 |  | Baseline (2020) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2026)
| World Governance Indicators: Government effectiveness estimate TJK/UZB/KGZ | Planned | TJK: -.80; UZB -.60; KGZ: -.60 | at least 0.1 improvement from the baseline | at least 0.1 improvement from previous milestone | at least 0.1 improvement from previous milestone | at least 0.1 improvement from previous milestone | TJK: -.30; UZB -.10; KGZ: -.20
Achieved
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (2026)
| World Governance Indicators: Voice and accountability estimate | Planned | TJK: -1.78; UZB: -1.54; KGZ: -.59 |  | at least 0.2 improvement from the baseline |  | at least 0.2 improvement from previous milestone | TJK: -1.3; UZB: -1.0; KGZ: -.30
Achieved
Source
Reported in the Worldwide Governance Indicators statistics database. Estimate gives the country's score on the aggregate indicator, in units of a standard normal distribution, i.e. ranging from -2.5 to 2.5. These indicators lack direct attribution to project activities.
OUTCOME | Outcome Indicator 1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
More effective, accountable and transparent delivery of economic policies in Kyrgyzstan, Tajikistan and Uzbekistan | Economic policy effectiveness (WB): Number of economic and/or social policies (within EGED policy portfolio) that delivered better outcomes for citizens through increased use of data and evidence by governments in Kyrgyzstan, Tajikistan, and Uzbekistan (broken down by country) | Planned | 0 | n/a | 3 case studies (one each for TJK/UZB/KGZ) - Labour Code (UZB), Regional Dev (KGZ) and TSA (TJK) | 3 more policies (one each for TJK/UZB/KGZ) - Total 6 policies across KGZ/TJK/UZB | 3 more policies across KGZ/TJK/UZB - Total 10 policies across KGZ/TJK/UZB | 3 more policies across KGZ/TJK/UZB - Total 12 policies across KGZ/TJK/UZB
Achieved
Source
Methodology for this indicator to be agreed in September 2022. Data for case studies will be based on WB survey amongst policymakers as well evaluative data collected by external consultant
| Outcome Indicator 2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Governance effectiveness (WB): Number of cases (within EGED policy portfolio) demonstrating that systematised use of data and evidence simplified, fastened or otherwise improved the delivery of a policy by the governments in Kazakhstan, Kyrgyzstan, Tajikistan, and Uzbekistan (broken down by country) | Planned | 0 | n/a | 4 case studies (one each for TJK/UZB/KGZ) - Labour Code (UZB), Public Procurement (UZB), Regional Dev (KGZ) and TSA (TJK) | 4 more cases across TJK/UZB/KGZ - Total 8 cases across KGZ/TJK/UZB | 2 more cases - Total 10 cases across KAZ/KGZ/TJK/UZB | 2 more cases - Total 12 cases across KAZ/KGZ/TJK/UZB
Achieved
Source
Methodology for this indicator to be locked in September 2022. Data for case studies will be based on WB survey amongst policymakers as well evaluative data collected by external consultants
| Outcome Indicator 3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Policy advocacy of civil society and media based on data/evidence (Pillar 2): # and quality of policy changes un/related to EGED reform issues influenced by civil society and media in Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan through institutionalised channels | Planned |  | Milestones and methodology to be agreed following 2022 AR |  | Draft methodology designed. [Provisionally: 3 cases (at least one each for KGZ/TJK/UZB)] | 2 more cases - Total 5 cases across KGZ/TJK/UZB | 2 more cases - Total 7 cases across KAZ/KGZ/TJK/UZB
Achieved
Source
Methodology for this indicator to be agreed in September 2022
| Outcome Indicator 4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Reputation of and trust in civil society to support policy processes (Pillar 2): Perception change of citizens and government officials in communities where EGED worked believing that civil society can or does contribute positively to improve public policies in Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan | Planned |  | Milestones to be agreed following 2022 AR |  | Draft methodology to track perception change designed | N/A | Perceptions of civil society and media in communities where EGED worked improved
Achieved
Source
Methodology for this indicator to be agreed in September 2022
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
100%
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Kyrgyz central and local governments supported to use data and evidence to improve delivery of select policies (World Bank + DPI) | Quality of World Bank delivery of support for evidence use by the Kyrgyz Government: a) # of detailed inception notes and work plans developed; b) % of planned activities per work stream delivered on schedule; c) demonstrated capability of WB to adapt plans and deliverables building on lessons learnt and changes in context | Planned | n/a | a) 2; b) 90%; c) adaptation planning embedded in work plans | a) 1; b) 90%; c) adaptation planning embedded in work plans | a) 1; b) 90%; c) amendments made to inception notes and activity work plans | a) 4 (total); b) 90%; c) adaptation planning embedded in work plans | N/A
|  | Achieved |  | a) MET. Two inception notes are delivered (Monetary Policy and Regional Development and M&E). Additionally, HSE report Assessment of data needs for the evidence-driven economic reform, governance, and policy making was completed; b) MET c) MET: plans and activities were adapted to meet changes in context and political and economic environment | a) Met. Inception note for E-Commerce. Annual Work Plans are developed for all components; b) Met; c) MET: plans and activities were adapted to meet changes in context and political and economic environment
Source
| Output Indicator 1.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Sub-national development (service delivery): Improved capacity of LSG staff to use Sanarip Aymak facilitates public service delivery at municipal level | Baseline Data showed that [16%] of LSGs have passport of LSG completed in Sanarip Aymak | 10% annual improvement over the baseline value | At least 50% of LSGs have passport of LSG in Sanarip Aymak | At least 80% of LSGs have passport of LSG in Sanarip Aymak | At least 90% of LSGs have passport of LSG in Sanarip Aymak by June 2024. At least 20% increase in the number of certificates (national eIDs, birth and death certificates, residency registrations) issued by LSGs that improved capacity in using Sanarip Aymak. | 100% of 235 LSGs have passport of LSG in Sanarip Aymak by June 2025. At least 50% increase in the number of certificates (national eIDs, birth and death certificates, residency registrations) issued by LSGs that improved capacity in using Sanarip Aymak. | 100% of 235 LSGs have passport of LSG in Sanarip Aymak by June 2026. 100% increase (from 2024 baseline) in the number of certificates (national eIDs, birth and death certificates, residency registrations) issued by LSGs.
|  | Achieved |  | Partially Met 1. Inception note on Regional Development and M&E is developed; 2. HSE report Assessment of data needs for the evidence-driven economic reform, governance, and policy making was completed; 3. Roundtable on Data for Regional Development was held in May 2022; 4. ToRs for consultant for regional development planning based on data for LSGs and Capacity building are under discussion with counterparts; 5. Survey on inclusiveness of Sanarip Aymak will be conducted by ACTED in July-August, with survey results ready in September | Met. As of November 2022, 79.7% of LSGs have passport of LSG in Sanarip Aymak. Additional LSGs added in following months, full assessment scheduled for November 2023. | The target has not been achieved due to delays in approving the new Administrative Territorial Reform (ATR) Law. | PARTIALLY MET. Due to the development of new SEDP Module, Passport of LSG is being revised. Passport is filled once a year (the data will be available in July 2025). 78% increase in the number of documents issued by LSGs.
Source
| Output Indicator 1.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Sub-national development (planning): Data from Sanaryp Aymak systematically used for regional socio-economic planning | Planned | Regional-level socio-economic planning conceptualized and developed | Regional-level socio-economic planning pilotted and adjusted | Draft methodologies for socio-economic development programs of LSGs and district level bodies based on data from Sanarip Aymak prepared and pilotted at least in two rayons | At least 4 Socio-Economic Development Programmes (using new methodologies) prepared and approved + 5 new SEDPs prepared based on new SEDP methodology using Sanarip Aymak data by June 2024. | 100% of newly formed LSGs have developed and approved Socio-Economic Development Programmes using new Methodologies. Dashboard to track regional development is launched. | 100% of newly formed LSGs have developed and approved Socio-Economic Development Programmes using new Methodologies. Dashboard to track regional development is launched.
|  | Achieved |  | Partially Met 1. Consultant is preparing the terms of reference for the development of the national monitoring system and its dashboard, that will be hosted on the Presidential Administration’s website; 2 Consultations with counterparts on capacity building for regional development are in place; 3. Consultations with counterparts on inter-budgetary relations for regional development are in place | MET. Draft methodologies for socio-economic development programs of LSGs and district level bodies based on data from Sanarip Aymak prepared. Detailed plan of the piloting new methodologies in 2 rayons and 4 LSGs was developed in: At-Bashy Rayon; At-Bashy aiyl aimak; Ak-Muz aiyl aimak; Nookat Rayon; Nookat city; Kok-Zhar aiyl aimak. Piloting is scheduled for May/June 2023 | 26 SEDPs were prepared (using new methodology) and approved. | PARTIALLY MET. As of June 2025, about 70% of newly formed LSGs had approved SEDPs. TOR for the SEDP module and Dashboard was officially approved by GoKR, to be developed by Dec 25
Source
| Output Indicator 1.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Sub-national development (from planning to results): Evidence of new local development planning process leading to economic growth (factual and/or projected) in target districts | Planned | Budgetary provision to local communities remains too low to meet their needs, but channels for communication between local communities and national-level decision makers are unclear. NEW: Insufficient SME Engagement in developing tourism infrastructure |  |  | Tourism marketing strategy and other development activities implemented in At Bashy and Nookat districts within the implementation of 2 pilot programs (as per SEDP) focusing on the development of regional sustainable tourism, in coordination between Local Self Governments (LSGs), local and central tourism SMEs, Department of Tourism, CSOs. | At least two verified cases of local economy growth (revenue in sector, new jobs, rising local resident income, inward investment) as a result of new SEDPs implementation. Analytical forecast for new target districts based on administrative and statistical data. At least five stories of change in local residents' wellbeing. | Investment profiles approved for all 7 EGED pilot districts. % growth is priority sectors (factual as of June 2026), X amount of investment (as of June 2026), # of new jobs, # of new SMEs in 7 EGED pilot districts
|  | Achieved |  |  |  | New indicator added after 2023 Annual Review | MET. 2 verified cases of local economic growth in 2 "old" pilot locations and 15 industry forecasts in 7 "new" pilot locations | Indicator moved to Output 1
Source
| Output Indicator 1.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Sub-national development (peer exchanges and learning): Impactful exchanges in the field of LSG reform between Central Asian peers and with the UK | Planned |  |  |  | Working-level exchange visit of the Uzbek LSG officials and experts to Kyrgyzstan. | Senior management visit of Uzbekistan Mahalla Association to the Kyrgyz Republic. MoU signed between Uzbek and Kyrgyz LSG authorities. | (1) Central Asian LSG forum establishes a regional cooperation platform. (2) Kyrgyz LSG visit Kazakhstan, MoU signed between Kyrgyz and Kazakh LSG
|  | Achieved |  |  |  |  | MET. MoU signed, an action plan was developed
Source
| Output Indicator 1.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Improved monetary policy: Use of inflation forecasting data, data on remittances and improved DSGE model in setting monetary policy direction | Planned | Value at macroeconomic level (quantitative or qualitative) | Existing DSGE Model revised | At least 10 policymakers from NBKR, MoEC, MoF, President's Administration trained in developing a dynamic stochastic general equilibrium model for the Kyrgyz Republic (DSGE) | NBKR develops at least 3 actual shock scenarios with DSGE model using real data and presents findings to the NBKR board. At least 5 verified instances of shock scenarios used to inform NBKR decisions in monetary policy. | Monetary policy is based on new data sets on inflation expectatios, remittances and the updated DSGE model (Dec- 2025) | N/A
|  | Achieved |  | MET 1. Inception note is developed, describing DSGE model concept; 2. ToR for international consultant is developed and agreed with NBKR; 3. Three consultations with potential consultant firm OG Research were conducted; 4. Proposal from OG Research was received and discussed with NBKR; 5. ToR is updated and dates for TA is agreed with NBKR, MoEC; 6. Questions on Inflation Expectation are received from NBKR and embedded into L2KGZ survey | MET. Two weeks trainings were conducted in November 2022. 13 participants from the NBKR, MoEC, MoF, President's Administration. The second round of trainings is ongoing in April 2023. Prior to that, three online sessions was conducted to participants on DSGE modelling. | 8 shock scenarios using DSGE model were prepared, of which 4 presented to NBKR board. | MET. National Bank of the Kyrgyz Republic uses DSGE model forecasting quarterly to inform decision for the policy rate | Delivery ended in FY 2025/26
Source
| Output Indicator 1.7 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Improved administration of SME licences and permits: Sectoral assessment of licences and permits used to improve regulatory environment for SMEs | Planned | n/a | n/a | n/a |  | (i) Inception note (March 2025) (ii) Identification of maturity assessment of business licenses as mechanism of identifying reforms (iii) Selection of two pilot sectors for business license reforms (iv) Review of status of business licenses and requirements in KR | (i) Business licensing reviewed in five additional sectors (ii) e-Permit platform concept designed and endorsed by GoKR (iii) procurement of supplier to build e-Permit launched (iii) Impact assessment of improved licensing/permit regime shared with FCDO
|  | Achieved |  |  |  |  | MET
Source
| Output Indicator 1.8 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Improved business/investment regulations and investor protection mechanisms | Planned | n/a | n/a | n/a | n/a | At least 3 laws amended by Jogorku Kenesh in response to private sector asks. | (1) IDRC concept endorsed by GoKR, changes to domestic legislation made, IDRC premises identified and agreed upon with GoKR. (2) At least 3 laws amended by Jogorku Kenesh in response to private sector asks.
|  | Achieved |  |  |  |  | MET
Source
| Output Indicator 1.9 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Kyrgyzstan fiscal policy | Planned | n/a | n/a | n/a | n/a | Fiscal incidence analysis preliminary findings are presented and discussed with the Ministry of Economy and Commerce (MoEC) | Fiscal incidence analysis is completed, findings are presented to the GOKR, report is shared with GOKR and FCDO, government officials trained in CEQ methodology
|  | Achieved |  |  |  |  | MET
Source
| Output Indicator 1.10 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Kyrgyz Republic (Gender Assessment, Poverty Map; Listening to the Citizens of Kyrgyzstan; E-Commerce Diagnostics) | Planned | Survey launched | 2 Listening Roundtables | 2 Listening Roundtables, Gender Assessment, e-commerce assessment | 2 L2KGZ Roundtables convened (from September 2023 to June 2024). L2KGZ open-access electronic dashboard launched. Country Gender Assessment report published. Poverty Map showing poverty rate at rayon level published. At least 5 verified instances of EGED-funded analytical products (L2CK, Gender Assessment, Poverty Map, E-commerce Diagnostics) used by the GoKR to inform decisions/policies. | At least 2 Listening roundtables (from Juy 2024 to July 2025) held; L2KGZ open-access electronic dashboard launched; Sub-National Poverty Assessment developed and published. At least 5 new verified instances of EGED-funded analytical products (L2KGZ, Sub-National Poverty Assessment) used by the GoKR to inform decisions/policies. | At least 2 Listening roundtables (from July 2025 to June 2026) held; L2KGZ open-access electronic is used. At least 5 new verified instances of EGED-funded analytical products (L2KGZ, Sub-National Poverty Assessment, etc.) used by the GoKR to inform decisions/policies.
|  | Achieved |  | MET 1. L2KGZ survey launched in December 2021; 2. First roundtable on L2KGZ was held in March 2022; 3. Second roundtable - June 2022; 4. Gender Assessment report launched in February 2022; 5. First roundtable on GA was held in March 2022; 6. Second roundtable - May 2022 | MET. October 6, 2022 L2KGZ Presentation to Government officials/President's Administration. November 29, 2022 L2KGZ Presentation to AUCA students. December 2022 and February 28, 2023 L2KGZ Presentation to the Ambassadors. March 23, 2023 Gender Assessment roundtable with high senior officials participation. Completed draft e-commerce assessment and readiness index. | L2KGZ roundtables were held in October 2023 and June 2024. Country Gender Assessment report published. 5 instances of use of EGED-funded analytics presented (2 instances were pending verification). | MET
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Tajik government supported to use data and evidence to improve delivery of select policies (World Bank + DPI) | Quality of World Bank delivery of support for evidence use by the Tajik Government: a) # of detailed inception notes and work plans developed; b) % of planned activities per work stream delivered on schedule; c) demonstrated capability of WB to adapt plans and deliverables building on lessons learnt and changes in context | Planned | n/a | a) 2; b) 90%; c) adaptation planning embedded in work plans | a) 2; b) 90%; c) adaptation planning embedded in work plans | a) 1; b) 90%; c) amendments made to inception notes and activity work plans | a) 4 (total); b) 90%; c) adaptation planning embedded in work plans | N/A
|  | Achieved |  | Partially Met a) Not Met: Both inception notes are significantly delayed and not finalized. Draft inception note on TSA shared, but is not finalized. In-ception note on Poverty Measure-ments not shared b) Partially Met: Progress on work-streams but overall delays in finalizing inception notes and work-plans. c) Met: Plans and activities are constantly reviewed and adapted | a) Met. Inception note for E- Commerce. Annual Work Plans are developed for all components; b) Met. c) Met. Plans and activities were adapted to meet changes in context and political and economic environment as well as to the demand of the clients
Source
| Output Indicator 2.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Updated Targeted Social Assistance policy (TSA): Data/evidence used by MoHSP to improve TSA policy design and implementation | Planned | Basic targeting formula (2009 Vintage); coverage of 30% of the bottom 40. No proactive outreach to encourage uptake, streamlining/digitizing application procedures | Targeting mechanism with HBS data conducted, Core Diagnostic Assessment conducted | Policy note on benefit design adopted in the TSA legal acts. Two technical capacity building seminars conducted with government counterparts. | Core Diagnostic Assessment (CODI) of Social Protection in Tajikistan completed and published by June 2024. Evidence generation of the intended impact of the modernised TSA formula (targeting) and benefit structure (amounts) on reducing recipient household poverty commenced. | Core Diagnostic Assessment (CODI) of Social Protection in Tajikistan published by June 2025. Evidence of the intended impact of the modernised TSA formula (targeting) and benefit structure (amounts) on reducing recipient household poverty collected and partly presented to the public. | Impact of the modernised TSA formula (targeting) and benefit structure (amounts) on reducing recipient household poverty assessed.
|  | Achieved |  | Met a) Met: Targeting assessment completed and formula, which di-rects more resources to the poorest households developed. b) Met: Core diagnostic of simulated welfare impacts completed. | Met. Inception note developed and delivered. Met. TSA modernization officially adopted through a government decree including EGED recommendations on the benefit design. Met. 5 seminars and/or bilateral technical discussions conducted with the Ministry of Finance (MoF) and MoHSP technical and leadership teams in the lead up to official publication of legal acts. Met. A roundtable TSA discussion carried out during Poverty Council meeting. Multi-mode uptake campaign designed | PARTIALLY MET. CODI of Social Protection in Tajikistan has been completed, preliminary results presented to key stakeholders in February 2024 (not published). Evidence generation of the impact of the modernized TSA has been pushed to 2025. | PARTIALLY MET. CODI report dissemination event was held jointly by WB, UNICEF and Government of Tajikistan in June 2025, preceded by the validation with all stakeholders. Impact assessment of TSA reform was delayed due to slow late receiving of the Social Registry data from the MoHSP.
Source
| Output Indicator 2.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Updated welfare measurements (poverty and middle class): Quality of citizens welfare monitoring data used and capacity of using the data to generate quantitative evidence in policy making in Tajikistan improves | Planned |  | HBS methodology improved and piloted; re-launch of the Poverty Council | New poverty measurement methodology endorsed by the Poverty Council; Terms of References of the Poverty Council updated and endorsed by the Poverty Council with additional data-analytics and poverty reduction strategy responsibilities; Implementation of the amended ToR through the initiation of the Tajikistan Poverty Assessment report together with the Poverty Council. | Updated poverty measurement methodology adopted with either legal act or published at the Government of Tajikistan official website. Middle class definition and measurement methodology approved by the Poverty Council. Draft core diagnostics module (Part 1) of Poverty Assessment produced. | The updated poverty measurement methodology fully approved by the Government of Tajikistan. Poverty data (re)calculated using new measurement methodology. Middle-class measurement methodology fully approved by the Government of Tajikistan. Middle class calculated using new methodology. | N/A
|  | Achieved |  | Partially met: a) Partially met: TOR on improving HBS developed but no evidence of new methodology being piloted. b) Met: Poverty Council re-launched in May. | Met. A modern poverty measurement survey was officially launched in 2022, with support from the EGED programme, and an updated poverty line developed with WB technical assistance. The poverty measurement is currently undergoing approval process by the Ministry of Justice. The formal approval is expected shortly. Met. The February 2023 Poverty Council discussed the updated ToR for the Council which was approved by MoEDT on 24 February 2023. Met. The ToR was amended, and many of the ToR‘s points (e.g., expansion of responsibilities of the Poverty Council etc.) are being already implemented. | The poverty measurement methodology has been updated and pre-approved at the technical level by the Poverty Council. The middle-class measurement methodology not approved by the Poverty Council by the time of Annual Review. | MET. Both methodologies were approved by the GoT Council for Middle-Class expansion in Sept 2024 and Feb 2025 respectively. The poverty and middle-class concepts were also presented and discussed at the regional consultations with CSOs in Dushanbe and in Khatlon | Delivery ended in FY 2024/25
Source
| Output Indicator 2.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Sub-national development: # of beneficiaries in EGED pilot jamoats who have improved their wellbeing | Planned |  | N/A | N/A | N/A | N/A | 120 beneficiaries
|  | Achieved | [5 empty] | New indicator
Source
| Output Indicator 2.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Tajikistan fiscal policy | Planned | N/A | N/A | N/A | N/A | N/A. Fiscal incidence analysis to launch in 2025/26 reporting cycle | Fiscal incidence analysis is completed, findings are presented to the GoTaj, report is shared with GoTaj and FCDO, government officials trained in CEQ methodology
Achieved
Source
| Output Indicator 2.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Improved administration of SME licencing/permits and inspection system: Assessment of licencing/permits and inspection system used to improve regulatory environment for SMEs | Planned | N/A | N/A | N/A | N/A | N/A | (i) Inception note (October 2025) (ii) Maturity assessment of business licensing and inspection system completed - report presented by June 2026 (iii) Policy note analysing the relationship between size of companies and licensing/inspections regime completed and shared with GoT and FCDO
Achieved
Source
| Output Indicator 2.7 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Public Finance Management: New evidence generated on the public finance management informs the Government of Tajikistan PFM reform, including at sub-national level | Planned | N/A | N/A | N/A | N/A | N/A | PEFA Climate, Gender, and Sub-National launched; data collected by June 2026.
Achieved
Source
| Output Indicator 2.8 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Tajikistan (Gender Assessment, Poverty Map; Listening to Tajikistan; E-Commerce Diagnostics) | Planned | Survey launched | 2 L2T Roundtables | 2 L2T Roundtables conducted; Gender Assessment published; | 2 Listening to Tajikistan Roundtables convened (from September 2023 to June 2024). L2T open-access electronic dashboard launched. Poverty Map showing poverty rate at rayon level published. At least 5 verified instances of EGED-funded analytical products (L2T, Gender Assessment, E-commerce Diagnostics) used by the Government of Tajikistan to inform decisions/policies. | At least 2 L2TAJ Roundtables (from Juy 2024 to July 2025); L2TAJ open-access electronic dashboard launched; Poverty and Equity Assessment completed, presented, and published. At least 5 new verified instances of EGED-funded analytical products used by the Government of Tajikistan to inform decisions/policies. | At least 2 L2TAJ Roundtables from July 2025 to June 2026; L2TAJ open-access electronic dashboard is actively used; Poverty and Equity Assessment completed, presented, and published. At least 5 new verified instances of EGED-funded analytical products used by the Government of Tajikistan to inform decisions/policies.
|  | Achieved |  | Exceeded: Three Roundtables completed: November 2021; March 2022; June 2022 | 6 Listening to Tajikistan roundtables conducted and consultations/implementation of recommendations from the Country Gender Assessment were completed. |  | MET. Two L2T roundtables were held (Nov 2024, June 2025). The Poverty and Equity Assessment report dissemination planned for September 2025.
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Uzbek government supported to use data and evidence to improve delivery of select policies (World Bank) | Quality of World Bank delivery of support for evidence use by the Uzbek Government: a) # of detailed inception notes and work plans developed; b) % of planned activities per work stream delivered on schedule; c) demonstrated capability of WB to adapt plans and deliverables building on lessons learnt and changes in context | Planned |  | a) 6; b) 90%; c) adaptation planning embedded in work plans | a) 1; b) 90%; c) adaptation planning embedded in work plans | a) 1; b) 90%; c) amendments made to inception notes and activity work plans | a) 8; b) 90%; c) adaptation planning embedded in work plans | N/A
|  | Achieved |  | a) Met. 6 inception notes and work plans are completed and cleared with the GoU. The team is preapring a new AWP for 2023. b) Met c) Met | Met. All inception notes and work plans have been approved and confirmed with the client. Operations are conducted in compliance with the AWPs. | Met | Target not subject to AR
| Output Indicator 3.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Labour Code: Data/evidence used to improve the design and implementation of Uzbekistan's new labour code | Planned | Current Labor Code is obsolete; Expert review report of the Labor Code completed | Modern labor code adopted and in force (Apr 2022); | Modern labor code and full M&E system active | Evidence of firms' awareness and adoption of the modernised Labour Code collected and presented to the public. | Evidence of the intended impact of the modernised Labour Code on improved employment opportunities for women collected and presented to the public. | Report evaluating Uzbekistan’s Labour Code in relation to international standards and ILO conventions submitted. Set of indicators in the Unified National Labour System for monitoring of the updated Labour Code submitted.
|  | Achieved |  | Met. Modern labor code is adopted and in force. The team has conducted a conference - launching event on the labor code. | Met. Modern labor code was adopted in December 2022 and is in force since 30 of April 2023. Launch of the labor code conference was conducted on the 16th of December 2022. Basic M&E in place, and recruitment of the company that will improve measurement/M&E system is currently being finalized. Improved version of M&E system will become active by December 2023. | A roundtable to increase firm's awareness of the adoption of new labor code was organized and delivered with the Ministry of Employment and Poverty Reduction (MEPR) in Karshi city in August 2023. | MET. Phone survey conducted based on a randomly selected sub-sample of 100 medium and 100 large firms from the World Bank Enterprise Survey master sample. The findings presented during the L2CU roundtable in June 2025.
Source
| Output Indicator 3.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Climate-smart policies: Data/evidence use by relevant government ministries improves the design and implementation of the climate-smart policies (decarbonisation, air quality, climate adaptation and resilience) | Planned | Inception note | 3 trainings conducted; seminar series completed; institutional and sectoral assessment | Adoption of the long-term strategy for green growth; adopted fully-assessed climate friendly policy reform | Draft LTS presented to the Government. Adaptation and Vulnerability Assessment report delivered to MEF and MEECC, serves as an input to UZB CCDR. Policy note on estimating additional economic benefits from improving resilience of landscapes submitted to MEF and MEECC. Report feeding into National Adaptation Strategy. Action Plan on AQM improvement in UZB submitted to MEF and MEECC, aimed at improving national regulations on AQM. | N/A: workstream deprioritised | N/A
|  | Achieved |  | Met. Trainings and 12 seminar series are comepleted. Insitutional and sectoral assessments are completed. | Met. A long-term strategy for green growth is adopted. | Draft LTS presented to GoUZ. Adaptation and Vulnerability Assessment report delivered. Action Plan on AQM improvement submitted to MinEcology and MEF. | NA | N/A
Source
| Output Indicator 3.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Public Procurement: Quality of design and implementation of e-complaints handling module on procurement | Planned | No contract management system and no digital complaint-handing module in e-procurement system | E-procurement complaints module developed and successfully piloted (June 2022) | Fully operational complaint handling module in e-pocurement system and Full adoption of contract management system module (Jun 2023) | Successful response of complaints within prescribed norm. Open publication of metadata and issue resolution. Ongoing user satisfaction survey. Comprehensive review of PP legal framework completed, recommendations delivered to MEF, incl. on regulating application of sustainable public procurement. At least two Green PP trainings delivered. | N/A: workstream deprioritised | N/A
|  | Achieved |  | Met. E-procurement complaints module has been developed and successfully piloted with the MoF. The team has also prepared and finalised a Public procurement strategy for Uzbekistan. | Met. Operational complaint handing module in the e- procurement system has been developed and commissioned by the client (MEF). National PP strategy has been completed and approved by the client. Due to the administrative reforms and the change of the counterpart the development of the contract management system module shall be reconfirmed with new client. | Complaints Handling Module fully operational. The planned user satisfaction survey not completed. Review of PP legal framework completed, recommendations delivered to MEF. Training on sustainable PP delivered. | N/A | N/A
Source
| Output Indicator 3.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| SOE reform: iSOEF report used by the Government of Uzbekistan and other partners to inform SOE reform | Planned | Data sources scattered, limited quality, not published. | Integrated SOE framework assessment completed according to standard; uptake pathway in SOE reform process clarified | Open publication of SOE and firms database. Governance reform adopted | iSOEF report published with analysis of the SOE firm database. At least 3 legislation changes to support SOE reform adopted by GoUZ as a result of iSOEF and new evidence (Law on Privatisation of State Property, competition guidelines, etc.) | Assessment report of the 2021-2025 SOE reform strategy implementation. A policy note on reform opportunities to enhance competition and create a level playing field between SOEs and the private sector. | A final policy note on reform opportunities to enhance competition and create a level playing field between SOEs and the private sector.
|  | Achieved |  | Met. All deliverables including SOE framework assessment envisaged for the 2022 are completed under the SOE issue area. | Met. Governance reforms: Law on privatization, law on competition, law on insolvency. SOE information harmonized and included in global database. iSOEF report, which analyses the SOE database, on track (internal WB review and approval process was completed but , publication pending on the GOV). | The iSOEF report launched, report made public. Privatization Law enacted in early 2024. Secondary legislation on competition (guidelines on leniency and competition in initial markets) not attributable to EGED. | MET. Draft Stocktaking Report on the 2021–25 SOE Strategy Implementation submitted to UzSAMA. Comments for the draft 2026–30 SOE Reform Strategy provided to UzSAMA.
Source
| Output Indicator 3.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| WTO accession impact mitigation: CGE modelling used by the Government of Uzbekistan to inform adjustment in sectoral policies to comply with WTO standards | Planned | Limited expertise, weak institutions, and a shortage of neutral advice on WTO accession. | N/A | N/A | N/A | Draft paper on the Computable General Equilibrium (CGE) model. | CGE-GIDD analysis completed, report presented to the GoUZ and FCDO by June 2026
|  | Achieved |  |  |  |  | MET. Completed the summary of literature review for trade liberalisation reforms and methodology brief for the CGE-GIDD (Computable General Equilibrium – Global Income Distribution Dynamics) framework and shared with the WTO Chief Negotiator’s Office.
Source
| Output Indicator 3.7 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Public Finance Management: New evidence generated on the public finance management informs the Government of Uzbekistan strengthen PFM outcomes, including at sub-national level | Planned | PEFA 2019 and 2020-2024 PFM Strategy | N/A | N/A | Draft PEFA Assessment submitted to PEFA Secretariat by June 2024. | PEFA 2024 launched & publicly available. Recommendations and KPIs included in 2025-2030 PFM Strategy. Sub-national PEFA assessment completed in at least two districts. | Workshop on decentralization conducted
|  | Achieved |  |  |  | Initial results of PEFA and assessment of the climate PFM were delivered to MEF and PEFA Secretariat in June 2024 | MET. (1) The 2024 PEFA Report launched and made publicly available in October 2024. (2) The PFM Strategy and KPIs included were submitted in November 2024 approved on April 8, 2025, through the Cabinet of Ministers Resolution #210. (3) Completed the sub-national PEFA assessment in a low (Syrdarya) and higher (Fergana) fiscal capacity setting and developed an advisory note on PIAD titled “Resourcing Sub-National Government for Results”.
Source
| Output Indicator 3.8 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Fiscal policy: New evidence generated through EGED programme (baseline fiscal incidence and targeted distributional impact analyses) enhances the equity of the Government of Uzbekistan fiscal policy | Planned | N/A | N/A | N/A | N/A | Baseline fiscal incidence analysis for Uzbekistan and the results presented to the government counterparts | Fiscal incidence analysis is completed, findings are presented to the GoUZ, report is shared with GoUZ and FCDO, government officials trained in CEQ methodology
|  | Achieved |  |  |  |  | MET. Completed baseline fiscal incidence analysis for Uzbekistan which included evaluation of distributional impact of major direct and indirect taxes and transfers (including health and education). Based on the outcome of the analysis, multiple consultations with the government counterparts were held in February 2025 to discuss possible policy reform scenarios. Results of the analysis has been made part of upcoming Public Finance Review of Uzbekistan.
Source
| Output Indicator 3.9 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| # of women with disabilities (or having a family member with disability) from poor households who gain income source through skills, grants, and microloans | Planned | 0 | N/A | N/A | N/A | 480 women and youth with disabilities from low-income families trained. 350 people starting their own enterprises. 50 people accessing employment. | 336 women and youth with disabilities from low-income families trained. 140 people starting their own enterprises. 30 people accessing employment
|  | Achieved |  |  |  |  | Target not subject to AR 2024/25 | Cumulative targets for 2024/25 and 2025/26 subject to separate review
Source
| Output Indicator 3.10 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Uzbekistan (Gender Assessment, Poverty Map; Listening to Tajikistan; E-Commerce Diagnostics) | Planned | Survey launched | 2 Listening Roundtables | 2 Listening Roundtables, Gender Assessment, mahalla index | 2 Listening to Citizens of Uzbekistan Roundtables convened (from September 2023 to June 2024). L2CU open-access electronic dashboard launched. Country Gender assessment report published. At least 5 verified instances of EGED-funded analytical products (L2CU, Gender Assessment, E-commerce Diagnostics) used by the Government of Uzbekistan to inform decisions/policies. | At least 2 L2CU roundtables (from July 2024 to July 2025). L2CU open-access electronic dashboard launched. At least 5 new verified instances of EGED-funded analytical products used by the Government of Uzbekistan to inform decisions/policies. | At least 2 L2CU roundtables (from July 2025 to June 2026). L2CU open-access electronic dashboard is actively used. At least 5 new verified instances of EGED-funded analytical products used by the Government of Uzbekistan to inform decisions/policies (incl analytical products from the Climate Window).
|  | Achieved |  | Met. 4 Listening round tables have been conducted. | Met. 3 L2CU events were conducted. The L2CU anniversary conference has been conducted on the 27th of January 2023, which included mahalla survey/Index findings. Country gender assessment workshop was conducted on the 13.04.2023, on track for delivery in Q2 2023. | 2 L2CU roundtables (February and June 2024) and the Country Gender Assessment (CGA) report launch event (March 2024). L2CU dashboard not launched. | MET: Two L2CU roundtables held in February and June 2025, In December 2024, the L2CU microdata (for 2018 to latest) and questionnaire were published on the WB Microdata Library. World Bank developed a new interactive L2CU dashboard, publicly available on Uzbekistan’s L2CU website. EGED-funded analytics were used in/for: (i) monitoring briefs on public perceptions of the 2024 & 2025 energy tariff reforms, (ii) Behavioural Science Insights for the Energy Tariff Reform for enhancing effectiveness of communication campaign5, (iii) citizens’ perspectives on the implementation of the Labor Code, (iv) understanding the middle-class and economic mobility, and (v) citizens’ views on the government fiscal policies
Source
| Output Indicator 3.11 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Centre of Government monitoring of policy delivery: Delivery Unit uses data/evidence to track progress and/or guide select reform priorities set by the President of Uzbekistan | Planned | No tracking of progress on the reform priorities using data-based instruments/tools | N/A | N/A | Progress tracking dashboard is designed and launched among the Government of Uzbekistan. | A workshop on Data Analytics and AI in the public sector held. A prediction model for public investment needs using the school data designed, submitted to DU. | N/A
|  | Achieved |  |  |  | A prototype tracking dashboard designed but not completed or launched. | MET. (1) Workshop on Data Analytics and AI in the Public Sector held in April 2025. (2) Nine ML models for school, pre-school and hospital investment planning in Samarkand region, and three reports describing the logic flows for models’ creation developed and shared with the DU team.
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Kazakh government supported to enhance the use of evidence to improve delivery of select policies (World Bank) | Quality of World Bank delivery of support for evidence use by the Kazakh Government: a) # of detailed inception notes and work plans developed; b) % of planned activities per work stream delivered on schedule; c) demonstrated capability of WB to adapt plans and deliverables building on lessons learnt and changes in context | Planned |  | N/A | N/A | a) 1; b) 90%; c) amendments made to inception note/s and activity work plans | N/A | N/A
|  | Achieved |  |  | N/A
| Output Indicator 4.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Data literacy: Public sector capacity for data analysis and use of evidence in policymaking improved | Planned | No data literacy program exists | N/A | Launch of the pilot data literacy portal, initial training module | At least 120 public sector officials in Kyrgyzstan, Tajikistan, and Uzbekistan improve their data literacy by taking BNS/WB Data Literacy course. | 2025 AR to review progress of 2024 milestones | N/A
|  | Achieved |  |  |  | The data literacy hub ready with local languages (Russian, Kazakh, Kyrgyz, Uzbek, Tajik and English). Around 40 Kazakh officials completed the data literacy course. | NOT MET. The programme targets were achieved in Kazakhstan but not Tajikistan, Uzbekistan and Kyrgyz Republic.
Source
| Output Indicator 4.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Statistics capacity: Sector-specific and leadership capacity of Bureau of National Statistics practitioners improved | Planned | No program | N/A | N/A | At least 40 BNS officials improve knowledge of statistics modernizsation, new methodology for agricultural census, scanner data and tourism. | N/A | N/A
|  | Achieved |  | N/A | N/A | Met target | Indicator reviewed in 2024 AR
Source
| Output Indicator 4.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED analytical products: # of reports/assessments based on new data developed, published, and used by the Government of Kazakhstan (L2Kaz) | Planned | L2Kaz Survey launched | N/A | 2 Listening Roundtables | 2 L2Kaz roundtables convened (from September 2023 to June 2024). L2Kaz open-access electronic dashboard launched (data updated monthly). At least 5 verified instances of L2Kaz used by the Government of Kazakhstan to inform decisions/policies. | N/A | N/A
|  | Achieved |  |  | Not met | Met target | Indicator reviewed in 2024 AR
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
200000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Governments of Kazakhstan, Kyrgyzstan, Tajikistan, and Uzbekistan supported to use data and evidence to design and/or improve climate-smart policies and approaches (World Bank) | Implementation of the long-term carbon neutrality/decarbonisation policies in Kazakhstan and Uzbekistan supported | Planned |  | N/A | N/A | A comprehensive LEDS roadmap for KAZ is developed by June 2024 outlining sector-specific policies and measures for achieving carbon neutrality by 2060. Report on green and carbon financing options and opportunities in UZB developed by June 2024. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Government of Kyrgyzstan supported to update the Green Economy Strategy for 2024-2028 |  |  | N/A | N/A | A Policy Note on conceptual framework of the Green Growth KYR established. A multi-stakeholder workshop conducted by June 2024 to explore the policy trade-offs identified in the Policy Note on Green Growth for KYR. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Government of Tajikistan supported to implement the 2023 Disaster Risk Finance (DRF) Strategy | Planned |  | N/A | N/A | A PFM assessment of options for establishing a dedicated disaster reserve fund in TAJ has been conducted and a note with the options shared with GoT. At least 2 knowledge sharing (seminar/workshop) events held (disaggregated by stakeholders, type of activity) about the assessment. At least 10 dissemination materials published (disaggregated by type and social media platform) communicating the results of the assessment. | N/A | N/A
|  | Achieved |  |  |  | Target partially met in 2024 AR
Source
| Output Indicator 5.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Forecasts of medium and long-term climate change impacts at macro level in the Kyrgyz Republic and Tajikistan are generated | Planned |  | N/A | N/A | A macro-fiscal model for the period up to 2060 for KYR for the BAU (business as usual) scenario has been calibrated. A macro-structural country-level modelling framework designed for TAJ to stimulate a range of climate and policy scenarios. A Climate-informed macro-model for TAJ contributed to WB CCDR report for TAJ. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Tools to assess household vulnerability to climate variability and long-term distributional impacts developed and used in climate adjustment scenarios for KAZ, KYR, TAJ, and UZB | Planned |  | N/A | N/A | A standardized household datasets for estimating household climate vulnerability functions in targeted CARs created. A technical note developed on the climate variability vulnerability functions for target CARs. An accessible and operational interactive online tool established for estimating climate variability vulnerability functions under different climate adaptation scenarios. The designed micro-simulation model for estimating the distributional impact of climate change adjustment scenarios for Tajikistan inputted to the CCDRs. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Challenges and opportunities for Tajikistan to mobilize climate finance reviewed | Planned |  | N/A | N/A | Detailed PowerPoint Presentation and aide memoire summarizing the review findings for TAJ CCDR around the challenges and opportunities for TAJ to mobilize climate finance | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.7 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Institutional set-up in Kyrgyzstan and Tajikistan to achieve climate change adaptation and mitigation assessed through Climate Change Institutional Assessments | Planned |  | N/A | N/A | Benchmarking of climate change institutional capabilities for KYR and TAJ formulated by June 2024. Country notes for KYR and TAJ generated based on the CCIA results by June 2024. Recommendations on prioritisation and sequencing of climate change institutional improvement submitted to Governments of Kyrgyzstan and Tajikistan. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.8 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Climate Public Expenditure Financial Accoutability (PEFA) Assessment in Uzbekistan carried out | Planned |  | N/A | N/A | Draft Climate PEFA for UZB submitted to PEFA Secretariat for review by June 2024 | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
| Output Indicator 5.9 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Public attitudes and perceptions towards climate change, climate policies and subsidy reform explored in KAZ, KYR, TAJ, and UZB | Planned |  | N/A | N/A | Survey of households across four CAR countries completed. Regional Diagnostic Report developed and published. | Survey of households across four CAR countries completed. Regional Diagnostic Report developed and published. | N/A
|  | Achieved |  |  |  | Target not achieved in 2024 AR | Target partially met. Survey completed, final draft report not published.
Source
| Output Indicator 5.10 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Modelling of costs and distributional impacts of green transition policies in KAZ, KYR, TAJ, and UZB carried out | Planned |  | N/A | N/A | Poverty and Social Impact Analysis (PSIA) developed on green growth/green transition policies for further use in DPO (World Bank Development Policy Operation). Technical note measuring poverty and distributional impacts of green transition policies on jobs across the four CAR countries developed and published. | N/A
|  | Achieved |  |  |  | Target not achieved in 2024 AR
Source
| Output Indicator 5.11 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Climate change recommendations of Uzbekistan land reform code assessed | Planned |  | N/A | N/A | A report on land management issues and the scope to scale up climate smart agriculture solutions developed for UZB by June 2024. Policy options for enhancing the regulatory framework governing land tenure security for climate smart agriculture provided by June 2024. At least 2 workshops conducted to promote ownership of the reform agenda in the key sectoral ministries incl. UZB Ministry of Agriculture. | N/A | N/A
|  | Achieved |  |  |  |  | Indicator reviewed in 2024 AR
Source
INPUTS (£) | FCDO (£) 1,900,000 |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Governments and private sector in Kyrgyzstan, Tajikistan, and Uzbekistan supported to increase revenues through e-commerce (World Bank E-GATE) | Quality of World Bank delivery of support for the governments and private sector in KYR/TAJ/UZB: a) delivery of a high quality inception note and a work plan; b) % of planned activities per work stream delivered on schedule; c) demonstrated capability of WB to adapt plans and deliverables building on lessons learnt and changes in context | Planned | n/a | n/a | n/a | a) 1; b) 90%; c) amendments made to inception note/s and activity work plans | N/A | N/A
|  | Achieved |  |  |  | Indicator was depriioritised in 2024 AR | Targets delivered in 2024
| Output Indicator 6.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Horticulture Export to Global Markets through E-commerce channels: export volumes increase | Planned | n/a | n/a | n/a | For every dollar of EGED E-GATE programme funding spent (100% of expenditure) and events (50% of expenditure), facilitate more than 1 USD of export | For every dollar of EGED E-GATE programme funding spent on this activity (100% of expenditure) and events (50% of expenditure), facilitate more than 1.5 USD of export | N/A
|  | Achieved |  |  |  | Horticulture exports through ecommerce channels did not progress as expected. | N/A
| Output Indicator 6.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Onboarding SMEs to global B2B e-platforms: sales volumes increase | Planned | n/a | n/a | n/a | At least 150 firms from Kyrgyzstan, Tajikistan, and Uzbekistan (upto 50 from each country) are onboarded to the global B2B e-marketplace | For every dollar of EGED E-GATE programme funding spent (100%) and events (50%), facilitate more than 1.5 USD of e-commerce sales in two years' projection for firms that have onboarded for at least 6 months | N/A
|  | Achieved |  |  |  | 83 (out of 150 originally planned) firms were onboarded by June 30. | The E-GATE program generated over $23 million in exports, delivering a return of more than 23 times the initial FCDO investment of less than $1 million.
| Output Indicator 6.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Promotional events to attract global resources to Central Asia e-commerce markets: number of events held | Planned | n/a | n/a | n/a | At least 1 promotional events per country in Tajikistan, Uzbekistan, Kyrgyzstan | N/A | N/A
|  | Achieved |  |  |  | Delivered in all three countries. Uzbekistan: “First Marketplace Conference”, Tashkent, 30/09/23. Kyrgyzstan: “E-commerce Expo”, Bishkek, 22/10/23. Tajikistan: “Dushanbe E-commerce Forum”, 01/03/24. | Targets delivered & reviewed in 2024
| Output Indicator 6.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Demand-driven regulatory support to the governments: number of advisory knowledge products delivered | Planned | n/a | n/a | n/a | Deliver at least 1 advisory product per country in Tajikistan, Uzbekistan, Kyrgyzstan, demanded by the government on regulating or monitoring e-commerce | N/A | N/A
|  | Achieved |  |  |  | E-commerce measurement methodology offered to the governments of the Kyrgyz Republic, Tajikistan, and Uzbekistan | Targets delivered in 2024.
INPUTS (£) | FCDO (£) 750,000 |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (100%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 7 | Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Regional economic development improved as a result of a CSO-participatory, gender-inclusive approach and increased coordination among Local Self-Governments, Ministries and CSOs (DPI) | Quality of ACTED delivery of support for civil society: a) # of high quality inception notes and work plans developed; b) % of planned activities per work stream delivered to a high standard; c) demonstrated capability of ACTED to adapt plans and deliverables building on lessons learnt and changes in context | Planned | n/a | a) Program Design 1 high quality inception report finalised and operationalised b) Delivery 2 high-quality issue-based work plans including PEA approved and operationalised c) Adaptation Project adapted based on Civil Society Consultations conducted in 5 regions | a) Program Design At least 1 high-quality relevant issue plans operationalised in close coordination with WB; 1 additional policy issue selected and analysed b) Delivery 90% of planned activities for FY22-23 implemented to a high standard c) Adaptation Demonstrated ongoing PEA for issues with ongoing activities; Civil Society Consultations are held to ensure CSOs inputs in the issue-based work adaptation and capitalization | N/A | N/A | N/A
|  | Achieved |  |  |  | Indicator deleted after the logframe review following the 2023 Annual Review
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Capacity of CS & Media to use data for accountability a) # and % of targeted CS representatives and media who report using more data and evidence in their work; b) # of high-quality data and evidence-based reports, articles published by civil society and media on topics around selected policy issue areas | Planned |  | a) Data incubator Downstream partner selected and contracted to implement the data incubator; 2 data desks trained b) Access to data 1 Online Open Data Portal launched; c) Analytical materials 5 data-based analytical products on economic policy published with project support | a) Data incubator Data incubator first round of trainings completed / 50% of targeted CS representatives and media report using more data and evidence in their work; b) Access to data # of site visits and # of new data entries to the Open Data Portal (ODP) c) Analytical materials At least 10 high quality reports/articles/materials published by civil society and media on topics around selected policy issue areas | N/A | N/A | N/A
|  | Achieved |  |  |  | Indicator deleted after the logframe review following the 2023 Annual Review
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Financial sustainability of CS and media % of targeted CSOs that have increased ability to implement financially sustainable business strategies (measured through their GOCA scores and results of social entrepreneurship incubation) | Planned |  | 1) Organisational capacity GOCA Modules adapted, prepared and translated 2) Social enterprise Social entrepreneurship feasibility study completed and approved, and incubation programme designed with PEAK (and approved); First pilot training successfully conducted | 1) Organisational capacity GOCA baseline conducted and tailored training plan designed for at least 5 key CSOs working proactively in policy issue areas 2) Social enterprise At least 20 start-up social enterprises supported through the pilot program At least 3 social enterprises show promising business plans and access private financing Second round of SE incubator launched with direct link to policy issue areas | N/A | N/A | N/A
|  | Achieved |  |  |  | Indicator deleted after the logframe review following the 2023 Annual Review
Source
| Output Indicator 7.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Regional development (1): Percentage of development activities listed in the Socio-Eonomic Development Plans (SEDPs) implemented through the Coordination Councils | Planned | No clear vision or methodology for citizen accountability in regional development under the new administrative- territorial reform. NEW: 6 SEDPs approved in 2 Coordination Councils with 0 development activities implemented. | Work plan presented and endorsed by key stakeholders (inc. Ministry of Economy, NSC); MoU signed with key counterpart(s) Target pilot districts selected; agreements signed with 2 district-level governments | Draft methodology for inclusive and people-centred regional development planning is prepared in partnership with the WB and presented to key ministries New accountability mechanisms (coordination councils) established and pilot-tested in at least 2 regions | 2 Coordination councils are operating (covering 2 target districts and 4 municipalities) with CSOs, local Kenesh and at least 30% women membership. 6 SEDPs (covering 2 target districts and 4 municipalities) are implemented in the two districts and four municipalities through the Coordination Councils. 10% of activities approved in 6 SEDPs (2 at district level & 4 at municipal level) have been implemented, funded by the state and other alternative sources, covering a range of economic sectors. | At least 10% of development activities approved in new SEDPs (At-Bashy and Nookat, and 5 new districts) have been implemented, funded by the state and other alternative sources, covering a range of economic sectors. | N/A
|  | Achieved |  |  |  | Indicator refined after 2023 Annual Review | EXCEEDED. Average implementation rate across 7 target districts was 27% | Target irrelevant - focus changed to promoting raising investment into sub-national level
Source
| Output Indicator 7.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Regional development (2): Number of new districts where Coordinational Council is operating with SEDP being developed | Planned | Budgetary provision to local communities remains too low to meet their needs, but channels for communication between local communities and national-level decision makers are unclear. NEW: 0 new districts where SEDPs are adopted. |  | At least 60% of key civil society and media activists in the target regions have improved skills on data-driven monitoring and advocacy; At least 4 local activists’ advocacy campaigns supported in target regions 4 national coalitions supported to strengthen their connections with regional civil society and representation of regional development issues; At least 10 data-driven articles/reports/materials on issues of local importance are published, and at least 50% are raised for discussion in national-level platforms Emerging transparency/ accountability issues in regional development are raised and discussed at the national level by civil society Key barriers to the development of regional media identified and discussed with decision makers | 2 Coordination Councils (in addition to the 2 existing CCs) established in 2 new districts with SEDPs being developed, as a result of advocacy and awareness raising activities in which 35 districts increase their knowledge on the work of Coordination Councils. | 1) 5 new Coordination Councils established in 5 more pilot districts with SEDP developed. 2) At least 500 local civil society and business representatives took part in SEDPs co-creation process (based on new methodologies) on municipal and district level. | N/A
|  | Achieved |  |  |  | Indicator refined after 2023 Annual Review | MET on (1) and EXCEEDED on (2) | Target irrelevant - SEDP training completed in 2024/25
Source
| Output Indicator 7.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Regional development (3): Local economy growth and improved public services (factual and/or projected) in target districts as a result of multistakeholder engagement around SEDP design and delivery | Planned | Budgetary provision to local communities remains too low to meet their needs, but channels for communication between local communities and national-level decision makers are unclear. NEW: Insufficient SME Engagement in developing tourism infrastructure |  |  | Tourism marketing strategy and other development activities implemented in At Bashy and Nookat districts within the implementation of 2 pilot programs (as per SEDP) focusing on the development of regional sustainable tourism, in coordination between Local Self Governments (LSGs), local and central tourism SMEs, Department of Tourism, CSOs. | At least two verified cases of local economy growth (revenue in sector, new jobs, rising local resident income, inward investment) as a result of new SEDPs implementation. Analytical forecast for new target districts based on administrative and statistical data. At least five stories of change in local residents' wellbeing. | Economic growth is demonstrated in relevant sectors in all 7 pilot districts of the EGED Programme
|  | Achieved |  |  |  | New indicator added after 2023 Annual Review | MET. 2 verified cases of local economic growth in 2 "old" pilot locations and 15 industry forecasts in 7 "new" pilot locations | Indicator integrated in Output 1
Source
| Output Indicator 7.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Regional development (4): Impactful exchanges in the field of LSG reform between Central Asian peers | Planned |  |  |  | Working-level exchange visit of the Uzbek LSG officials and experts to Kyrgyzstan. | Senior management visit of Uzbekistan Mahalla Association to the Kyrgyz Republic. MoU signed between Uzbek and Kyrgyz LSG authorities. | (1) Central Asian LSG forum establishes a regional cooperation platform. (2) Kyrgyz LSG visit Kazakhstan, MoU signed between Kyrgyz and Kazakh LSG
|  | Achieved |  |  |  |  | MET. MoU signed, an action plan was developed | Indicator integrated in Output 1
Source
| Output Indicator 7.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Increase in women who have obtained legal permission, tenure, or rights to use leased land through the mechanism in 4 districts | Planned | In 2023, a total of 190 women in the four districts of Nookat, At Bashy, Kochkor, and Naryn obtained legal permission, tenure, or rights to use leased land out of a total of 2,731 issued permits. | N/A | N/A | The Land Allocation Mechanism improved through adoption of new, gender-focused procedures on allocation of land by the District Administration within the Land Allocation Mechanisms in Nookat, Naryn, At Bashy and Kochkor. # number of women who have obtained legal permission, tenure, or rights to use leased land in Nookat, Naryn, At Bashi, and Kochkor through the LAM mechanism increased by 20%. | N/A | N/A
|  | Achieved |  |  |  | Target added after 2023 Annual Review | Indicator deleted following 2024 AR
Source
| Output Indicator 7.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Improved State Loans Mechanism delivered to the Parliament and Ministery Advisory Council | Planned | Lack of effective State Loans Mechanism as evidenced by case-study research | N/A | N/A | Case-study research produced on the effectiveness of the State Loans Mechanism, delivered and discussed at the Parliament and a Ministry Advisory Council. | N/A | N/A
|  | Achieved |  |  |  | Target added after 2023 Annual Review | Indicator deleted following 2024 AR
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 8 | Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
CSOs' involvement and monitoring of TSA implementation and taxation | Quality of ACTED delivery of support for civil society: a) # of high quality inception notes and work plans developed; b) % of planned activities per work stream delivered to a high standard; c) demonstrated capability of ACTED to adapt plans and deliverables building on lessons learnt and changes in context | Planned |  | a) Program Design 1 high quality inception report finalised and operationalised; 2 high-quality issue-based work plans including PEA approved and operationalised b) Delivery N/A c) Adaptation Project adapted based on Civil Society Consultations conducted in 5 regions | a) Program Design At least 1 additional high-quality relevant issue plans and analysis prepared b) Delivery 90% of planned activities for FY22-23 implemented to a high standard c) Adaptation Demonstrated ongoing PEA for issues with ongoing activities; Civil Society Consultations are held for each policy issue to ensure CSOs inputs in the issue-based work adaptation and capitalization | N/A | N/A | N/A
|  | Achieved |  |  |  | Indicator deleted after the logframe review following the 2023 Annual Review
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Capacity of civil society and media to use data for accountability: # and % of targeted CS representatives and media who report using more data and evidence in their work; b) # of high quality data and evidence-based reports, articles published by civil society and media on topics around selected policy issue areas | Planned | Weak skills to use data among both civil society and media Very limited access to machine-readable open data CS and media rarely publish high-quality reports, articles and materials based on data | a) Data Incubator Downstream partner selected and contracted to implement the data incubator; 2 data desks trained b) Access to data 1 Online Open Access Database launched; c) Analytical materials 5 data-based analytical products on economic policy published with project support | a) Data Incubator Data incubator first round of trainings completed, 40% of participants (10 CSOs and 10 media specialists) demonstrate improved use of data in their work b) Access to data # of site visits and # of new data entries to the Open Data Portal (ODP). Open Data Portal is used actively by Data Incubator participants c) Analytical materials At least 10 high quality reports/articles/materials around selected issues published with project support Press clubs facilitate policy dialogue with journalists based on data and evidence | N/A | N/A
|  | Achieved |  |  |  | Indicator deleted after the logframe review following the 2023 Annual Review
Source
| Output Indicator 8.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Financial sustainability of CSOs: Increase in business funding channeled to CSOs (targeted for SEPP II) | Planned | Lack of financial resources, weak organisational management increasingly threaten civil society and media sustainability. Very limited awareness and skills for social entreprise. NEW: The baseline annual income for SEPP II participants in 2023 had 0% contribution from business. | 1) Organisational capacity GOCA Modules adapted, prepared and translated 2) Social enterprise Social entrepreneurship feasibility study completed and approved, and incubation programme designed with PEAK (and approved); First pilot training successfully conducted | 1) Organisational capacity GOCA baseline conducted and tailored training plan designed for at least 6 key CSOs working proactively in policy issue areas 2) Social enterprise At least 20 start-up social enterprises supported through the pilot program At least 3 social enterprises show promising business plans and access private financing Second round of SE incubator launched with direct link to policy issue areas | Contributions from businesses increased by at least 10 % to the annual income of CSOs (among at least 15 SEPP participants) as a result of series of training for CSOs, dialogue between businesses and CSOs, and through a multistakeholder forum and policy dialogue events. | 1) At least 5 CSOs (graduates of SEPPIII) attract at least 10% of their annual income from private sector. 2) Up to 5 CSOs (graduates of SEPPIII) receive loans from microcredit organizations/banks (interest rate covered by EGED grant) for best business ideas. 3) At least 80% of social enterprises that received financial support from EGED project, continued their operations post-investment among graduates of SEPP I and SEPP II trainings. | N/A
|  | Achieved |  |  |  | Indicator refined after 2023 Annual Review | (1) EXCEEDED. (2) MET. (3) MET | Delivery ended in FY 2025/26
Source
| Output Indicator 8.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Effectiveness of dialogue platforms % of targeted dialogue platforms that became more inclusive demonstrating increased participation from all stakeholders measured through PIP index | Planned | Dialogue platforms are invited spaces that do not represent diverse interests Weak civil society representation in major policy dialogue platforms | 1) PIP implementation Expert selected and contracted to deliver the PIP index 2) Stronger inclusive platforms 2 NDC Working Groups Selected to participate in platform strengthening programme | 1) PIP implementation PIP methodology finalised and test-piloted; At least 10 CSOs trained in using the PIP methodology PIP index report published on 14 IWGs (including in Tax Advisory Council, Poverty Council) Strategy for PIP Implementation is proposed to IWG 2) Stronger inclusive platforms A new, inclusive IWG Regulation and COP which specifies CSOs participation is developed and adopted by NDS Secretariat Roadmap on CSO engagement in IWG is developed and presented to the NDS Secretariat 20 civil society members (including those from working groups) trained on M&E of the NDS; CSOs are supported to analyse NDS indicators progress implementation | N/A | PIP index of the target dialogue platforms scored 80 out of 100 | N/A
|  | Achieved |  |  |  | Indicator suspended following the 2023 Annual Review | MET. 14 NDC IWGs assessed through PIP scoring 84.23 out of 100. | Delivery ended in FY 2025/26
Source
| Output Indicator 8.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Financial sustainability of CSOs: Improved conditions for financial sustainability (FS) for CSOs as a result of new tax regulations in the Tax Code. | Planned | Tax procedures remain too complicated and non-transparent for taxpayers. The system remains difficult to monitor from both inside and outside. NEW: The current taxation regime lacks provisions for tax relief for CSOs, which hinders their ability to operate social enterprises effectively. | PEA conducted in in Tax Code to identify challenges in the policy issue; Tax Reform work plan presented and endorsed to key stakeholders inc. Tax Committee.; Activities agreed and coordinated with the World Bank and Tax Committee | 1) Access to information Round Table is held to consult with CSOs on the Manual development; Manual on simplified information on new Tax Code is developed for CSOs and endorsed by TC and agreed with WB; 4 awareness campaigns by Civil Society promoting accessible information on new tax code in coordination with Tax Committee; 10 workshops conducted for on changes in the Tax Code reaching 1,500 active CSOs and Business Associations 2)Public-private dialogue Active participation of civil society in Tax Code Coordination Council; Members of key dialogue platforms received Policy dialogue training; New CSOs and Business Associations joined Tax Coordination Council; PIP Index is tested in the Tax Coordination Council 3) Policy advocacy Policy Dialogue is held towards identifying policy gap and discussion are held to address them; Study on CSR and Tax Breaks conducted, and results discussed with key stakeholders | At least 2 new tax regulations in the tax regime including additions to charity stream/tax break in the tax regime for SE, VAT redemption, or introduction of social tax on improving sustainability for CSOs proposed to the Tax Committee as a result of advocacy compaings and policy dialogue events based on experts analysis. | 1) At least 5 new tax regulations for social enterprises development proposed and at least 3 adopted by the Tax Committee. 2) At least 4 new SE-specific indicators were introduced and approved by MoEDT for the MTDP 2026-2030 as a result of advocacy campaigns and policy dialogue events based on expert analysis. 3) Impact of EGED's Research on the Economic Benefits of Social Entrepreneurship in leading to the Adoption of SE Legislation | N/A
|  | Achieved |  |  |  | Indicator refined after 2023 Annual Review | (1) MET. (2) PARTIALLY MET. (3) MET | Delivery ended in FY 2025/26
Source
| Output Indicator 8.4 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Targeted Social Assistance (TSA): Civil society engagement in TSA programme implementation is formalised through government policy for next three years | Planned | Lengthy and unclear process for selection of potential recipients of TSA Lack of awareness and limited/or no involvement of civil society in the process of TSA implementation NEW: There is no new TSA State program based on the new reforms on TSA as of the baseline. | PEA conducted on TSA to identify challenges in the policy issue TSA work plan presented and endorsed to key stakeholders including ASP. Activities agreed and coordinated with the World Bank and ASP | 1) Coalition building Coalition around TSA is established has a developed MOU and work plan to monitor the implementation of TSA; At least 6 TPM conducted by CSOs to collect and verify data on TSA; 2) Community engagement At least 20 CSOs in target districts trained and supported to implement campaigns among vulnerable communities; 6 Data-driven advocacy campaigns supported; Awareness raising in Campaigns on TSA through media products reached at least 10000 citizens 3) Policy advocacy Results of the activities are presented through a multi-stakeholder roundtable event; Relevant platform members trained on effectiv Policy dialogue; 3 new CS representatives are included and active in Social Protection IWG | An inclusive State Program on TSA State (2024-2026) is developed and adopted by the Government of Tajikistan (GoT) by the Working Group (WG) under the Ministry of Health and Social Protection (MHSP). A new State TSA Program (2024-2026) stipulates a designated role for CSOs in implementation and monitoring of TSA. | 1) The State TSA Program (2024-2028) is formally adopted by the GoT, including provisions for CSOs to take part in implementation and monitoring. 2) MoHSP integrates TSA monitoring in its social order process | N/A
|  | Achieved |  |  |  | Indicator refined after 2023 Annual Review | NOT MET | Delivery ended in FY 2025/26
Source
| Output Indicator 8.5 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Targeted Social Assistance (TSA): The number of TSA in-need recipients in DRS is increased as a result of CSOs efforts based on the official statistics from the ASP | Planned | Based on the official statistics from the Agency of Social Protection for Q1 2023, a total of 3,693 TSA recipients were recorded in the six target districts (Gissar, Vahdat, 2 projects in Rudaki, Lahsh, Varzob) | N/A | N/A | Minimum 10,000 direct beneficiaries ( through 5-6 supported small grants) in the DRS have increased knowledge of the TSA mechanism as a result of an outreach campaign, leading to minimum 20% increase of recipients in the target regions | Minimum 10,000 direct beneficiaries ( through 6 supported small grants) in the Sughd region and GBAO have increased knowledge of the TSA mechanism as a result of an outreach campaign, leading to minimum 30% increase of recipients in the target regions | N/A
|  | Achieved |  |  |  | New indicator added after 2023 Annual Review | EXCEEDED | Delivery ended in FY 2025/26
Source
| Output Indicator 8.6 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Targeted Social Assistance (TSA): Decrease in volume of TSA informal payments to local authorities in the target districts of DRS following the improved transparency of TSA mechanism and better oversight of CSOs | Planned | The baseline data shows that % of those who approached the TSA made informal payments. | N/A | N/A | 10% drop in informal payments as monitored by CSOs through Third Party Monitoring (TPM) in the districts of DRS as a results of the TSA awarness raisning activities | 1) 30% drop in informal payments as monitored by CSOs in the target districts of Sughd Region (3 districs) as a results of the TSA awarness raising activities and anti-corrupion training sessions. 2) MoHSP has formally integrated the Anti-Corruption module into the curriculum of its Capacity Building Institute for Social Protection Specialists. | N/A
|  | Achieved |  |  |  | New indicator added after 2023 Annual Review | MET. | Delivery ended in FY 2025/26
Source
| Output Indicator 8.7 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Number of new evidence-based indicators for social protection and employment adopted by the National Development Council | Planned | 1) PE Research findings will be used Baseline 2) MDTP indicators analysis with regards to SP and PE. | N/A | N/A | N/A | 1) At least five new evidence-based indicators for Productive Employment and Middle Class will be developed and adopted by the National Development Council in the MTDP 2026–2030, based on recommendations from the research on productive employment and Middle Class. 2) At least 5 new evidence-based indicators for social protection will be developed and adopted by the National Development Council in the MTDP 2026-30, aligning with the TSA State Program for 2028 and the State Social Protection Strategy for 2040. | N/A
|  | Achieved |  |  |  | New indicator added after 2024 AR | PARTIALLY MET | Delivery ended in FY 2025/26
Source
| Output Indicator 8.8 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Number of Persons with Disabilities (PWD) provided with job placement support and securing employment | Planned | % PWD currenly employed in SE based on statictics on employment rate in specific district | N/A | N/A | N/A | 1) At least 6000 direct beneficaries reached as the result of infromation campaigns on jobs and tranining opoortunities for vulnurable people in target districts 2) Up to 1,000 vulnerable individuals, including PWDs, women, and youth (among TSA recipients), received employment opportunities in the target districts. | N/A
|  | Achieved |  |  |  | New indicator added after 2024 AR | NOT MET | Delivery ended in FY 2025/26
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 9 | Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Uzbek civil society & media supported to promote accountability on selected policies using data and evidence (DPI) | Quality of ACTED delivery a) # of high-quality inception notes and work plans developed; b) % of planned activities per work stream delivered to a high standard; c) demonstrated capability of ACTED to adapt plans and deliverables building on lessons learnt and changes in context | Planned |  | 1) Program Design 1 high quality inception report finalised and operationalised; 2 high-quality issue-based work plans including PEA approved and operationalised 2) Delivery 3) Adaptation Project adapted based on Civil Society Consultations conducted in 5 regions | a) Program Design At least 2 additional high-quality relevant issue plan prepared including PEA b) Delivery 90% of planned activities for FY22-23 implemented to a high standard c) Adaptation Project adapted based on Consultations with Civil Society and Government on the policy issues | a) Program Design At least 1 additional high-quality relevant issue plan prepared including PEA, and operationalised b) Delivery 90% of planned activities for FY23-24 implemented to a high standard c) Adaptation Project adapted based on Consultations with Civil Society and Government on the policy issues; 1 mid-term review of the change pathways conducted | N/A | N/A
|  | Achieved |  |  |  | Indicator obsolete due to IP phaseout
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Capacity of CS & Media to use data for accountability a) # and % of targeted CS representatives and media who report using more data and evidence in their work; b) # of high-quality data and evidence-based reports, articles published by civil society and media on topics around selected policy issue areas | Planned |  | a) Data Incubator Downstream partner selected and contracted to implement the data incubator b) Access to data 1 Online Open Access Database launched; c) Analytical materials Downstream partner selected to support data-driven journalism | 1) Data Incubator First round of data incubator completed; 50% of participants demonstrate improved use of data for policy monitoring & analysis 2) Access to data # of site visits and # of new data entries to the Open Data Portal (ODP). Open Data Portal is used actively by Data Incubator participants 3) Analytical materials At least 10 high quality reports/ articles/ materials/ policy papers are published based on data | a) Data Incubator Second round of data incubator completed; 60% of participants demonstrate improved use of data for policy monitoring & analysis b) Access to data % increase in site visits and # of new data entries to the Open Data Portal (ODP) c) Analytical materials At least 10 high quality reports/articles/materials published based on data | 40 posts published reaching 1 mln contacts. 30 journalists trained in economic data journalism with 19 receiving mentorship. 6 media projects developed and deliver. | At least 30 media products and an audience reach of 1,500,000 contact reached. 20 journalists trained in economic data journalism. 5 media projects developed. 5 media products created with parliament with 50,000 contacts.
|  | Achieved |  |  |  | Indicator refined to focus only on media products | Target not subject to AR 2024/25 | Target moved to Output 10
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Financial sustainability of CS and media % of targeted CSOs that have increased ability to implement financially sustainable business strategies (measured through their GOCA scores and results of social entrepreneurship incubation) | Planned |  | 1) Organisational capacity Organizational Capacity Training Modules adapted, prepared and translated 2) Social enterprise Social entrepreneurship feasibility study completed | 1) Organisational capacity GOCA baseline conducted and tailored training plan designed for at least 5 targeted CSOs working on policy issues 2) Social enterprise At least 10 organisations working in policy issue areas trained on social entrepreneurship | 1) Organisational capacity At least 6 targeted key CSOs show improvements in their key identified organizational capacity weaknesses (measured through GOCA scores) 2) Social enterprise At least 2 social enterprise start-ups working in policy issue areas supported with start-up grants | N/A | N/A
|  | Achieved |  |  |  | Indicator obsolete due to IP phaseout
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED Policy Issue: Labour code Accountability of effective implementation of the new Labour Code and protection of Labour Rights in Uzbekistan, particularly for women and PWDs 1) Capacity of independant NGOs, professional associations and media to ensure independent monitoring, oversight & accountability 2) Government holds meaningful dialogue and takes into account civil society voices in the implementation of labour policies and legal documents 3) Quality of Labour Code implementation | Planned | Lack of independent monitoring of the implementation of labour legislation, weak advocacy among independent civil society & media on labour rights Limited consideration by government agencies of Labour issues raised by civil society Labour Code is not fully implemented and little awareness among the general population | 1)Independent monitoring Concept for Uzbek Civic Alliance for Labour Rights developed with inputs of key stakeholders Launch of coalition and signature of agreement commenced Open data portal used by civil society to access data and prepare evidence-based materials on labour relations 2) Dialogue for Effective Labour Code Work plan presented and endorsed by key stakeholders (inc. MELR) | 1)Independent monitoring Civic Alliance established and trained; annual report on labour situation analysis published. Monitoring tools and guidelines accessible and applied by CSOs. 3 monitoring projects on labour rights and labour legislation conducted and presented to government.3 initiatives to increase public awareness of labour rights. Multi-stakeholder collaboration established. 2) Dialogue for Effective Labour Code Labour Code has been published, government starts to prepare implementation arrangements. Government supports Alliance and engages proactively and constructively in policy discussion with the coalition. At least 2 policy dialogue activities presenting recommendations conducted jointly with state, CSOs and business representatives. Multi-stakeholder platform discusses gaps in Labour Code | 1)Independent monitoring Civic Alliance prepares annual reports on activities conducted, including recommendations on identified gaps in monitoring and implementation of Labour Code; Multi-stakeholder working group prepares annual reports with actionable recommendations. Civic Alliance members can are sustain their activities independently 2) Dialogue for Effective Labour Code Regular two-way communication between government and Alliance. At least 2 multi-stakeholder dialogue activities conducted jointly with state, CSOs and business representatives. TPM evidence used in discussion by government of changes to implementation of Labour Code. Alliance develops partnerships with international coalitions and hosts an international event. Government responds to at least 1-2 recommendations developed by Alliance. | N/A | N/A
|  | Achieved |  |  |  | Indicator obsolete due to IP phaseout
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| EGED Policy Issue: Green Growth (Decarbonization) Capacity of civil society and media to engage in dialogue, advocacy and monitoring of decarbonization reforms, and mitigate social risks | Planned | Ambitious targets for decarbonization, but GoU lacks realistic strategy for implementation and mitigation of poverty & social risks. Absence of meaningful civil society engagement in the reform process; energy policy remains particularly sensitive area |  | Policy Dialogue Group is formed and offered with Intensive capacity building program. 8 data-driven reports and articles published on decarbonization. 3 evidence-based policy recommendations put forward by civil society are discussed with the MEDPR. CS proposes social & poverty mitigation measures to MEDPR. | GoU integrates at least 2 policy recommendations from civil society in the LT. 3 high-quality policy analyses of the LTS are published and discussed. Independent decarbonization monitoring plan in place. | N/A | N/A
|  | Achieved |  |  |  | Indicator obsolete due to IP phaseout
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Policy Issue: Public procurement EGED Policy Issue: Public Procurement 1) Capacity of independent NGOs, professional associations and media to ensure active engagement in, oversight and accountability of effective and transparent public procurement 2) Improved mechanism for accountability, transparency and monitoring for efficient procurement | Planned | Civil society (inc. media) rarely engages with public procurement issues, due to lack of capacity, data and mechanisms for engagement Inefficient procurement processes limit the quality of public goods and services, due to limited mechanisms in place for accountability, transparency and monitoring | N/A | 1) Civil society monitoring procurement Procurement monitoring group formed, and members are trained to use e-tools for monitoring and investigation. 4 investigative research projects are conducted and published to raise awareness about procurement issues and ongoing reforms 2) Dialogue for efficient, transparent procurement Scoping Study conducted to demonstrate gaps and opportunities for PP mechanism accountability at the Central Asia level, and results discussed with Government and civil society and presented at the EGED conference and discussed with the relevant stakeholders. Recommendations on enhancing the BI tool are developed based on community discussion and BI use. 2 Policy Dialogues organized to promote open contracting reforms to discuss identified problems and proposed solutions with stakeholders | 1) Civil society monitoring procurement # of monitoring projects or investigations published in the media that resulted in change in the procurement procedures. At least 20 complaints resolved through the complaint mechanism system 2) Dialogue for efficient, transparent procurement. CS using open contracting data to develop actionable recommendations to improve procurement outcomes of at least 6 tender decisions. At least 4 policy dialogue events lead to follow up on the research and proposed reforms and fixes. | N/A | N/A
|  | Achieved |  |  |  | Indicator obsolete due to IP phaseout
Source
| Output Indicator |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| # of women with disabilities (or having a family member with disability) from poor households who gain income source through skills, grants, and microloans | Planned | 0 | N/A | N/A | N/A | 480 women and youth with disabilities from low-income families trained. 350 people starting their own enterprises. 50 people accessing employment. | 336 women and youth with disabilities from low-income families trained. 140 people starting their own enterprises. 30 people accessing employment
|  | Achieved |  |  |  |  | Target not subject to AR 2024/25 | Cumulative targets for 2024/25 and 2025/26 subject to separate review
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 10 | Output Indicator 10.1 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026 | Assumptions
Enhanced public awareness of economic policies/reforms, their implementation and delivered results | # of data and evidence-based media products that uncover governments' social and/or economic policy delivery | Planned | 0 | XXX | XXX | XXX | At least 100 media products (50 in Tajikistan, 40 in Uzbekistan, 10 in Kyrgyzstan) | 320 media products (100 in Kazakhstan, 110 in Kyrgyzstan, 110 in Uzbekistan)
|  | Achieved |  |  |  |  | MET.
Source
| Output Indicator 10.2 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| Number of contacts covered by the media products and campaign | Planned | 0 | N/A | N/A | N/A | 2,000,000 views | 6,500,000 contacts (Kazakhstan: 2,000,000; Kyrgyzstan: 1,400,000; Uzbekistan: 3,100,000)
|  | Achieved |  |  |  |  | Indicator refined, target added in FY 2024/25
Source
| Output Indicator 10.3 |  | Baseline | Annual Review 2022 | Annual Review 2023 | Annual Review 2024 | Annual Review 2025 | Annual Review 2026
| # of local budgets and PPP projects that have undergone public monitoring (Uzbekistan) | Planned | 0 | N/A | N/A | N/A | N/A | 11 (6 local budgets and 5 PPP projects)
|  | Achieved | [5 empty] | Indicator added in FY 2025/26
Source
Note on B61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from FY 2025/26.
Note on I152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Laura Kadirkulova what did you mean by the second sentence here? Is WB supposed to deliver this? If not, pls drop this. Reply: @Jafar Usmanov yes, WB will submit it by end of May.
Note on B187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from FY 2024/25.
Note on A321: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator redundant as of FY 2025/26.
Note on A322: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Output and indicators refined after 2023 Annual Review and in discussion with ACTED
Note on B322: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B327: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B332: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B347: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B352: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B357: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B362: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024
Note on A371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator redundant as of FY 2025/26.
Note on A372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Output and indicators refined after 2023 Annual Review and in discussion with ACTED
Note on B372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B377: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B387: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live in 2021-2023, not applicable in 2024.
Note on B402: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B407: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B412: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on B417: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator live from 2024.
Note on A426: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator redundant as of FY 2025/26.
Note on B457: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicator integrated to Output 3.