## Annual Review

Title: Nepal in Business (NIB)
Programme Value £ (full life): £36.2 million		Review date: 01/04/2026
Programme Code: 300965	AMP start date: 25/07/2023	AMP end date: 31/03/2031

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	D0004649.odt (live.com)
DevTracker Link to results framework:	D0007448.xlsx

## A. SUMMARY AND OVERVIEW
Description of the programme
Nepal in Business (NIB) is a flagship private sector development programme of the British Embassy Kathmandu (BEK) launched in July 2024. The UK Government-funded programme aims to unlock economic prosperity in Nepal by fostering the growth of small and medium-sized enterprises (SMEs), creating new jobs, and driving private sector-led economic growth. NIB has four priority sectors for investments and targeted interventions: agro-processing, tourism, light manufacturing, information and communications technology (ICT). Renewable energy was adapted to be a cross-cutting theme rather than standalone sector. These sectors are identified to have high export potential, with strategic products & services that can be catered to niche international markets.
The programme has three components with two delivery partners, as detailed below. This is the second Annual Review (AR) of the programme, and the first since the BSF and BERF components moved from inception to implementation. The NIB – Catalytic Finance component commenced its inception phase during the AR period but has not yet entered implementation.
NIB – Growth Advisors oversee the following two components, which are being implemented by DAI Global UK.
1. Business Support Facility (BSF): Providing technical assistance and grants to SMEs to enhance their productivity, competitiveness, and potential for job creation.
2. Business Environment Reform Facility (BERF): Engaging with stakeholders to advance reforms in business regulations, reduce barriers to trade, support sector initiatives driving market development and improve the overall enabling environment for SMEs in Nepal.
NIB – Catalytic Finance (previously SME Financing Facility) aims to catalyse investments into the SME ecosystem. The financing gap for SMEs in Nepal is £710 million and is faced by 83% of SMEs. NIB – Catalytic Fund managed by FMO will de-risk investments into Nepali SMEs through a blended finance facility – leveraging grant to mobilise additional capital from Development Finance Institutions (DFIs), Banks & Financial Institutions (BFIs), and Private Equity & Venture Capital (PEVC) Funds into the SME ecosystem.
The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a portfolio and partnership in transition, with recommendations and lessons learned focused on an new Expertise and Investment based partnership.
About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
The British Embassy Kathmandu (BEK) is committed to FCDO’s four shifts: from donor to investor, to systems change, to providing expertise, and to supporting local solutions. In Nepal, this means moving to an Investment & Expertise Partnership. BEK will design a revised portfolio which leverages investment and expertise across the full range of UK and partner instruments. Our ODA bilateral budget to Nepal will be ~£39m over three years. BEK will close all existing programmes, including the Nepal in Business programme in 2027, ahead of moving to a new portfolio instrument.
Summary supporting narrative for the overall score in this review
This Annual Review supports an overall score of A, recognising strong progress across the Business Support Facility (BSF) and Business Environment Reform Facility (BERF) components during their first full year of implementation. The Catalytic Finance (CF) component remains in an early stage of delivery but the inception phase has laid solid foundations for future results.
A pragmatic approach was taken to scoring the CF component given its early stage of delivery and with many log frame indicators not yet meaningfully assessable. Output 3 (CF) has been introduced this reporting year, as there is an assessable indication, but in line with FCDO guidance the output weightings have been adjusted to reflect the availability and credibility of performance data. Outputs 1 (BSF) and 2 (BERF) are each weighted at 40%, reduced from 50% last reporting year. Output 3 (CF) has been introduced at 20% with one target for one output indicator, while Output 4 (CF) cannot yet be assessed in this review period.
BSF performance has been strong. Focused sector strategies aligned with Government of Nepal priorities, developed in the inception phase, have been operationalised effectively. Targeted TA and grants are supporting firms to adopt new practices, strengthen governance, and build investment readiness. Finally, early job creation and inclusion outcomes exceed annual milestones for this stage in delivery, although future targets must be rebased to reflect that no further cohorts will receive support.
BERF delivery has similarly met or exceeded expectations, with priority reforms either adopted or progressing well in both wellness tourism and ICT sectors. Across both components, the supplier has demonstrated high responsiveness to FCDO direction, including adjustments arising from budget reductions, geographic reprioritisation, and the shift away from financial assistance to government, while maintaining delivery momentum.
The supplier was meant to design a strategy to support to renewable energy sector at the end of year 1 (FY 25/26). However, following the programme re-design and a need for robust prioritisation considering resource and time constraints, this is being addressed in a crosscutting way. For example, the ESG audits required of BSF partners can highlight important changes on energy and processing efficiencies that reduce climate and environmental impact whilst delivering competitive advantages through cost savings and reliability of key inputs. This has particularly been the case for light manufacturing, agro-processing and tourism.
Finally, the CF component has successfully completed inception, established governance and delivery systems and built an initial pipeline. It will begin contributing to outcomes in subsequent periods.
Performance has been achieved despite a disrupted operating context marked by political instability, market shocks and programme reconfigurations. Considering this reconfiguration, it is not possible to robustly assess likely programme performance against end‑of‑programme output and outcome targets, which need to be recalibrated to reflect the revised budget envelope and delivery timeframe. Nonetheless, evidence from this review demonstrates strong early implementation performance, effective adaptation to changing constraints, and credible progress are delivering results within the updated programme scope.
Programme performance not captured by outputs
There are potential synergies between the BSF and BERF components that are core to the programme value proposition. BSF partnerships with high‑potential firms in priority sectors are deliberately aligned with BERF market systems approach, ensuring that firm‑level actions can inform the prioritisation and design of sector‑level reforms. Additionally, BERF should enhance the commercial viability and sustainability of BSF‑supported firms by improving enabling conditions beyond the life of individual grants. This complementarity led to the strengthening of ‘sector initiatives’ within the programme modality, which are sector level actions led by industry associations in close collaboration with government bodies, aiming to improve competitiveness across a whole subsector, rather than just for BSF-supported firms. They sit within BERF, but act as a bridge between firm level evidence (from BSF) and system-level reform.

Major lessons and recommendations for the year ahead
Lesson 1: Lessons from BSF on SME investment-readiness can help make CF more effective
Barriers to SME investment exist on both the demand and supply-side of finance. Lessons from BSF demonstrate that firm-level interventions are needed to strengthen investment-readiness, particularly around governance, financial management, ESG and market positioning. This must be reflected in the NIB-CF approach to be shared with FMO and their downstream funds partners and incorporated in their model.
Lesson 2: BSF and BERF learning can be helpful for Government of Nepal’s SME support programme.
BSF/BERF have evidence and learning on supporting SMEs to grow and create job through risk sharing and technical assistance. These learnings can be helpful to support the Government of Nepal’s Nepal Enterprise Facility which will support startups and SMEs through policy support, financial instruments and funding access, networking and entrepreneurship promotion programmes.
Key insight: SMEs can be supported to invest in new products and services through risk mitigation instruments such as co-financing and returnable grants. Investments in companies is catalysed by building capacity in the sector through access to expertise and markets.
Lesson 3: BERF impact depends as much on institutional counterparts as on reform design
BERF performance demonstrates that successful policy reform is likewise strengthened by certain success factors, including government buy-in, capable and engaged business support organisations (BSOs), alignment between proposed sector reforms and key stakeholder interests, and private‑sector champions. In ICT, strong enthusiasm and prioritisation by the government, coupled with an effective BSO in NAS-IT, enabled rapid progress. In wellness tourism, BERF was able to add significant value through sustained convening and ecosystem‑building of a previously fractured and diffuse institutional and stakeholder landscape. Latent government buy-in was present but this was honed through the credible, evidence-based BERF intervention.
Key insight: BEK’s Investment & Expertise Partnership (EIP) model should concentrate reform efforts in sectors prioritised by the Government of Nepal. BEK can play a key role in convening BSOs and MDB’s to jointly lobby for reform. Targeted technical assistance can help garner support from a delivery focused government. BSOs could be made central to the NIB exit and legacy strategy and should be further leveraged in the final phase of delivery. BEK should continue to engage BSOs as part of BEK’s EIP.
Recommendations
Recommendation	Detail (what will be done / evidence of delivery)	Owner / Deadline

1. Tighten BSF monitoring around firm‑specific value propositions	For each remaining BSF partnership, explicitly define the intended value proposition (e.g. innovation testing, market expansion, demonstration effects) and track delivery against it. Output: establish clear dissemination channels where demonstration effects are intended, such as through BSOs or to donor partners.	NIB‑GA; Q2–Q3 2026
2. Strengthen oversight of BSF delivery under compressed timelines	Step up delivery management in 2026 by: (i) reviewing progress for BSF partnerships against revised timelines; and (ii) identifying bottlenecks to implementation. Evidence: quarterly progress reviews shared with FCDO with prioritised focus.	NIB‑GA, FCDO; ongoing through 2026
3. Distil BERF success factors through targeted MEL learning	Produce a short comparative learning note analysing why BERF gained traction in ICT and wellness tourism particularly and more so than in other sectors, focusing on stakeholder readiness, champions, and reform sequencing. Potential output: MEL learning brief feeding into future reform programming or shared with development partners.	NIB‑GA MEL, BEK; Q3 2026
4. Focus BERF effort on sectors with highest reform traction	Concentrate BERF engagement on wellness tourism and ICT, where government buy‑in and private‑sector champions are strongest. Potentially focus resources where BERF additionality is greatest (e.g. wellness tourism). Evidence: revised sector prioritisation and workplans.	NIB‑GA / BEK; immediate
5. Support emergence of a wellness tourism coordination mechanism (e.g. BSO)	Continue convening in wellness tourism with the explicit objective of enabling a credible, private‑sector‑led coordination body (formal or informal). Align discussions with MAP stakeholders to strengthen the Nepal‑specific value proposition (e.g. ‘wellness ecosystem). Evidence: agreed roadmap or terms of reference led by private actors.	NIB‑GA handing over to BEK; Q4 2026
6. Proactively capture and share NIB knowledge with development partners	Package and share BSF/BERF insights including through Recommendations 3 and 5 with key partners (WB, ADB etc.), ensuring NIB analysis informs country diagnostics and sector strategies. Maintain close engagement with BII to identify potential pipeline relevance. Evidence: briefings delivered; references in partner processes.	BEK, FCDO; ongoing
7. Sharpen the problem statement and additionality logic for CF	Drawing on evidence from BSF firms, IIN, FMO and other programmes. Each CF transaction must articulate the specific market failure addressed and pathway to additionality. This should be shared with and interrogated by BEK/FCDO private sector advisors. Evidence: transaction‑level additionality statements cleared by BEK/FCDO.	FMO, BEK, FCDO; immediate and ongoing
8. Establish complementarity between CF, the BEK EIP portfolio and like-minded development partners.	Support CF with policy reform and financial sector deepening activities from BEK’s Enterprise and Investment Partnership portfolio. Convene development partners (WB, ADB, SDC) to jointly lobby for/ support improvement in access to finance for SMEs. Evidence: read-out from development partner meeting and committed TA support.	BEK, FCDO
9. Establish a structured dialogue on PE/VC exits and pipeline quality	Convene key stakeholders potentially including NAS‑IT, relevant BSOs, FMO, BII and selected investors to discuss binding constraints to PE/VC exits and pipeline development. Use findings to inform CF and TA design. Evidence: convening outputs and agreed follow‑up actions.	BEK, FMO; Q4 2026 – Q3 2027 (ahead of PE/VC transaction)
10. Plan and manage an orderly programme close‑out and handover	Develop and implement a close‑out plan capturing knowledge transfer, ownership of learning products, and institutional handover (notably to BEK) to mitigate risks from accelerated exit. Evidence: agreed close‑out plan and named custodians for key outputs.	NIB‑GA, BEK, FCDO; Q3 and Q4 2026/27 FY.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
For this annual review two Theory of Change (ToC) are relevant: the ToC in the business case, and that of Nepal in Business Growth Advisors (NIB-GA) which is nested within the business case ToC.

The business case for Nepal in Business aims to support "inclusive economic growth, creating jobs and improving productivity and competitiveness of firms and fostering competition" by stimulating the private sector, particularly SMEs. The interventions aim to address three cross sectoral constraints to business growth (weak policy environment, low firm capabilities and poor access to finance) and indirectly address anti-competitive behaviours. Additionally, TOC assumes that another key constraint related to poor energy and connectivity infrastructure will be addressed through other BEK programs, especially Local Infrastructure Support Programme (LISP) and Green Growth Nepal (GGN).
Over the course of this reporting period, the programme’s understanding of its Theory of Change has evolved, informed by the transition from inception into active implementation and by the experience of operating in a constrained and changing delivery context.
The NIB- Growth Advisors program has tentatively been proven well-placed to address barriers regarding firm capabilities and weak policy environments, albeit in early stages. NIB Catalytic Finance is designed to target barriers to access to finance by addressing supply-side constraints, alongside the demand-side intervention by NIB-GA components. No significant changes have been made to the ToC during the inception period, concluding December 2025. Whilst the underlying assumptions and causal logic remain valid, an emerging consideration relates to the level of deployable capital, which may influence the scale and pace of demonstration effects. Increasingly, success will depend on whether NIB CF can articulate and address specific barriers in the supply of finance to SMEs by crafting and implementing innovative solutions that the market will then adopt. Without this, a key constraint to SME growth will remain unaddressed by NIB.

A nested ToC (above) has been further developed by NIB-GA. This Growth Advisors ToC is largely an unbundling of the business case ToC, so the impacts and outcome targets are consistent, and the outputs and activities are described in greater detail. For the Business Support Facility, the intended outputs include, strengthening trade/investment linkages and improving capabilities via provisioning of specialised Business Development Services for SMEs. Similarly, the intended outputs for Business Enabling Reform include improving capabilities of policy actors to be provided through technical assistance on targeted issues, and promotion of public-private dialogue and advocacy.
While the core causal logic remains valid, implementation experience has sharpened the programme’s understanding of where it has most leverage. As described in the 2025 Annual Report by NIB-GA, the refined ToC places greater emphasis on the joint operation of firm‑level support and ecosystem‑level reform, recognises BSOs as critical intermediaries for sustained sectoral change, and explicitly incorporates lessons relating to funding uncertainty, political cycles, and operational disruption. Conversely, constraints that fall outside the programme’s realistic sphere of influence, such as large‑scale infrastructure provision and entrenched anti‑competitive behaviour, are no longer foregrounded within the ToC as described in this year’s Annual Report by NIB‑GA.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Outcome	Indicators	Outcome cumulative target for 2022/23		Achievement 2022/23 against cumulative target
Increase number of productive jobs	Number of additional new productive jobs created (Full Time Equivalent; cumulative)	60		66
	% of all direct new productive jobs created for women (cumulative average)	20%		45%
	% of all direct new productive jobs created for disadvantaged groups (cumulative average)	10%		33%
	Number of SMEs with increased value of additional input purchases from Nepali producers, at least 10% above the firm-level baseline (cumulative)	4		4
Improved competitiveness and productivity of firms	Number of SMEs with improved productivity at least 20% above the firm-level counterfactual (cumulative)	N/A		N/A
	Number of SMEs with increased turnover (domestic and export), at least 20% above the firm-level counterfactual (cumulative)	4		5
Improved conditions for doing business in target sectors	Number of Business Environment reforms adopted by the government to enhance productivity or competitiveness of targeted sectors (cumulative)	2		2
	Number of Business Environment reforms implemented by the government to enhance productivity or competitiveness of targeted sectors (cumulative)	0		1
	Number of sectoral initiatives taken up by government agencies, associations, or private sector actors to enhance business enabling environment for sector competitiveness through FA and/or TA (cumulative)	1		1

In its first year of implementation, the programme performed strongly against the agreed Year 1 milestones, demonstrating early effectiveness in job creation, inclusion, firm performance, and policy engagement. These results provide credible evidence that the programme design is sound and that NIB-GA is capable of translating support into tangible outcomes. However, while the programme is on track against original Year 1 expectations, it is not on track to deliver the scale of future results implied by the original logframe targets. With its early closure in March 2027 due to reduced ODA allocation, NIB will not deliver its original expected end of programme results.
Performance to date indicates that the programme has generated early additionality in job creation, which marginally exceeded expectations, and especially for inclusion outcomes for women and disadvantaged groups that have far surpassed targets. SMEs supported through grant and technical assistance have already demonstrated turnover growth, and initial business environment reforms have been adopted and, in one case, implemented. These results suggest that causal pathways from firm‑level support and policy engagement to outcomes remain valid.
However, the budget reduction and early closure of the Business Support Facility (BSF) and Business Environment Reform Facility (BERF) materially alter the programme’s delivery model. The original theory of change and numeric targets assumed a pipeline of up to 40 supported firms, underpinning projected increases in jobs, productivity, SME performance, and reform momentum in outer years. Under the revised funding envelope and delivery timescales, the number of supported BSF grantees is now capped at 12 and BERF engagement will conclude earlier than planned with the number of targeted sectors narrowing. As a result, while quality and depth of support remain high, the programme will not be able to deliver the scale of incremental results anticipated for the majority of indicators.
Against this backdrop, the programme can be assessed as performing well but increasingly misaligned with its original targets. The programme team should work with NIB-GA to allow for meaningful evaluation as these components conclude by applying the similar assumptions to the reduced scale of BSF/BERF activity. The impact of the programme can be high by sharpening prioritisation towards the highest‑impact firms and reforms. In parallel, emphasis will increasingly shift to the Catalytic Finance component, which is now operationally ready and offers the best opportunity to deliver scale and systemic impact within remaining resources.
Pending formal adjustment of targets, overall programme trajectory should be considered moderately on track, subject to successful re‑baselining and disciplined prioritisation for the remaining delivery period.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Based on the achievements above, the programme is well- positioned to meet recalibrated outcomes in line with the change in operating context. The outcome can be reduced proportionate to the budget for the next fiscal year to ensure the programme is positioned to deliver and exit responsibly with key lessons from BSF/BERF components channelled into the NIB-CF and work on policy reforms (e.g. Wellness Tourism) to be incorporated into BEK’s new Expertise & Investment Partnership (albeit through a different delivery modality). The budget for NIB-GA is reduced from £2.1 million in FY26/27 to 1.6 million. The programme will also cap their grant and TA support to SMEs at 12. This has significant implications on outputs and outcomes of the programme which will be reflected in the revised logframe targets (in line with guidance on early closure from FCDO HQ).

## C. DETAILED OUTPUT SCORING

Output Title	Improved capabilities and practices of SMEs in target sectors - Business Support Facility (BSF)
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of SMEs supported by BSF to enhance productivity and competitiveness (cumulative)	10	12 / Outputs moderately exceeded expectation
1.2 Volume of additional private finance mobilised as a result of NIB support (£; cumulative)	£180,000	£190,327 / Outputs met expectation
1.3 Number of new B2B partnerships between SMEs and domestic & international businesses to enhance productivity and competitiveness (cumulative)	4	4 / Outputs met expectation
1.4 Number of SMEs adopting new or improved practices or innovations to enhance productivity and competitiveness (cumulative)	4	4 / Outputs met expectation
1.5 Number of firms with developed action plans for adopting new or improved Environmental, Social, and Governance (ESG) practices (cumulative)	2	6 / Outputs substantially exceeded expectation
1.6 Number of BSF learning products produced and disseminated to target audience (cumulative)	2	2 / Outputs met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
This output relates to the activities and results of the Business Support Facility (BSF) component of the programme. Core activities included technical assistance, grant support, and market linkage activities to a cohort of SMEs in priority sectors to strengthen productivity, competitiveness, and investment readiness. Activities included: firm‑level diagnostics and co‑created growth plans; support to adopt new or improved business practices, technologies, and operating models; facilitation of domestic and international business-to-business (B2B) partnerships to unlock new markets and commercial opportunities; and targeted assistance to mobilise additional private investment alongside NIB grants. The BSF also prioritised governance and sustainability by conducting ESG assessments and supporting SMEs to develop actionable ESG improvement plans, alongside delivery of energy and process efficiency support, delivering climate benefits and investment readiness.
The output has scored A+, moderately exceeding expectations in its first year of full implementation. Reporting is based on the achievements made in the individual projects of the 12 BSF partners. Summarised details on engagement with these partners are available in the NIB GA Annual Report 2025.
All indicators met expectations, with two indicators delivering results exceeding logframe targets. Firstly, NIB-GA expanded the planned pipeline from 10 to 12 SMEs supported in the year in response to uncertainty around future funding and the likelihood that a second BSF cohort would not be launched. Whilst this was in response to revised FCDO expectations rather than straightforward overperformance, the ability of NIB-GA to adaptively respond to changing contexts and successfully identify further BSF SMEs constitutes a moderate exceeding of expectations.
More notably, the delivery of ESG action plans significantly exceeded the milestone of two, with a total of six achieved therefore also exceeding the target for next year. This reflects the substantial benefits achieved for SMEs through the technical assistance provided by NIB-GA, strengthening governance policies and internal procedures. This has in turn improved investment readiness and ability to engage with international markets, positioning them to access additional financing beyond the grant.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The budget envelope revision means that the programme will not open a new BSF cohort beyond the current 12, and delivery will instead focus on completing the current pipeline. Programme timelines have also shortened, requiring early partnership closures in some cases. In response, NIB-GA have front-loaded delivery where possible with activities fast tracked, which might in turn affect the time profile of targets and results.
Therefore, ongoing and end-of-programme targets no longer hold for these output indicators and a meaningful assessment cannot be made regarding whether delivery is on track. In the year ahead, NIB-GA will propose revised targets to FCDO that reflect the reduced budget envelope.

Progress on recommendations from the previous AR
Recommendation	Progress
Focus on designing innovative cross-sector partnerships.	There is emerging evidence that NIB-GA are stimulating cross-sector collaboration within the BSF cohort. NIB-GA cited three partnerships in their Annual Report: i) Herveda Botanicals expansion to wellness products and Ph Balance spa, ii) NTC’s venture into wellness tourism building upon their tea tourism experience; iii) FinPos mini design that enables affordability of payment devices by micro enterprises targeting tourist destinations. / Further commercial opportunities are being explored, including: i) Herveda and Buddha Maya Garden regarding supply of white-label wellness products for the hotel; ii) Nepal Tea Collective and Hokke Hotel exploring establishing a tea bar at one of the hotel sites. / Recommendation: assess whether the proposed expansions and new target markets materialise for the identified partnerships.
Provide TA to potential pipelines for DFIs	The BSF has delivered targeted TA to strengthen investment readiness, including governance, financial management and ESG support including energy audits, all critical for DFI investment. Tranquillity, Nepal Tea Collective and Citytech undertook structured assessments with follow‑on actions identified. While this indicates progress towards stronger pipelines, continued focus will be needed to translate TA into clearly investable DFI opportunities. / Recommendation: consider potential synergies between above-mentioned assessments, lessons and identified actions with the TA for the FI and PE/VC investments by FMO as part of the CF component.
Develop a working relationship with NIB-CF and BII	Working‑level engagement with NIB‑CF and BII has progressed, including alignment following NIB‑CF’s inception and BII participation in SME pitch‑focused mentoring. These interactions provide a constructive foundation, though deeper and more systematic collaboration remains a key area for further development.
Maintain a strong focus on enterprise development through BSF grants	Grants supported productivity, ESG improvements, and operational strengthening, including tailored energy audits and procurement of sector‑specific technical expertise in carpet and paper manufacturing subsectors. Four more international experts are in the pipeline. Their guidance will help partners position themselves in international markets and unlock access to key distributors and buyers. Five companies received tailored TA on energy assessment and efficiency increment.

Lessons learned this year and recommendations for the year ahead
With the BSF partnerships now well advanced and delivery taking place under a compressed timeline to December 2026, this reporting period has generated early but useful evidence on partnership formation, investment readiness support, and delivery feasibility. While many outcomes remain at an early stage, the coming year represents a critical window both for implementation and for focused learning and maximise potential impact. The lessons and recommendations below prioritise areas where strengthened oversight, clarification of pathways, or deliberate learning could most improve programme performance in the remaining implementation period and support onward priorities for British Embassy Kathmandu.

Box 1: Creating a Nepal Wellness Ecosystem – aligning firm‑level support and sector reform in two priority sectors for systemic impact
The potential to build a wellness ecosystem highlights how different NIB programme components can worked together in a mutually reinforcing way. A Nepal ‘wellness ecosystem’ could underpin and bolster two NIB priority sectors of tourism services and medicinal and aromatic plants (MAPs), drawing on a Nepal‑specific value proposition and offering a credible pathway toward higher‑value market positioning by creating and honing a global image of Nepal as a wellness leader.
BSF contribution: firm‑level experimentation and market signalling. NIB is supporting a small number of leading private‑sector firms across wellness tourism services and MAP‑based products in early innovation (products, services, processes) and business‑model development. This builds and tests the commercial viability of wellness‑linked offerings grounded in Nepal’s natural and cultural assets, generating market signals that wellness is investable. The integration of MAP‑related inputs to this would be particularly salient, as it strengthens the unique Nepal offering and links upstream producers to downstream demand without requiring immediate export‑led growth.
BERF contribution: market coordination and policy traction. BERF engagement has built a nascent wellness tourism landscape through sustained stakeholder convening, working with private sector, business organisations and government counterparts to define the wellness tourism space and craft a policy agenda.
Individually, BSF and BERF would be expected to deliver incremental gains at this stage. Together, they can create reinforcing forms of momentum:
- BSF supports credible private‑sector actors willing to test risk, creating demonstration effects.
- BERF provides a channel through which this activity can influence government thinking and future policy choices.
- The MAP–wellness linkage anchors the sector in a non‑replicable asset base unique to Nepal, increasing the potential for international attention, investment and export-led growth.

Output-level recommendation: revise down output indicators to reflect that the total number of SMEs supported will be capped at 12 due to the absence of follow‑on cohorts, with targets recalculated by applying the previously agreed assumptions to the reduced cohort size.
Thematic lessons and recommendations:
Cross‑sector partnerships and market development:
As above, there is early evidence of cross‑sector exploration within the BSF cohort, particularly between agribusiness, wellness tourism and enabling services. This suggests potential interest and experimentation, but example partnerships remain at an early stage.
Recommendation for the year ahead: assess whether anticipated commercial expansions and new target markets materialise for these firms, and what measurable changes in demand, revenues or market access result.
Learning opportunity: set as a deliberate learning priority, including requesting analysis by the NIB-GA MEL function on outcomes and constraints, potentially through a learning product. Given cross-cutting potential of ICT to act as an enabler across sectors, this could be a complimentary focus.
Investment readiness and relevance to DFI pipelines
The BSF has continued to emphasise investment readiness through targeted TA focusing on governance, financial management, ESG and energy audits. Reporting indicates progress at firm level; however, supported firms remain relatively small and early‑stage compared to typical DFI investment thresholds, which might constitute a challenge in the programme directly supporting DFI pipelines. Last year’s Annual Review also recommended that firm selection should more strongly emphasise investment readiness further, particularly looking at companies through the lens of DFIs and commercial investors.
Recommendation for the year ahead: clarify the intended investor pathways for BSF firms identified during firm selection; monitor whether and how investment‑readiness TA leads to concrete changes in firms’ ability to engage investors including local banks, PEVCs and DFIs; and explore how the resulting findings could inform or align with the Catalytic Finance component, given DFI involvement.
Learning opportunity: as above, this could be set as a learning priority, requesting outputs from NIB-GA MEL function. Findings could inform the NIB-CF component. Characteristics of BSF cohort should be compared to typical DFI pipelines in Nepal to ensure findings are relevant.

Delivery management under compressed timelines
Monitoring indicates that several partnerships are behind original implementation plans, largely because delivery timelines have been shortened with partnerships closing by December 2026. ESG assessments and action plans have been completed for multiple firms, but reporting to date focuses largely on diagnostics rather than progressing to implementation. Therefore, 2026 is a critical implementation year for the BSF partnerships.
Recommendation for the year ahead: NIB-GA should step up oversight of delivery against revised timescales, by reviewing progress and achievements to date, identifying key bottlenecks, and evaluating remaining activities required to achieve the agreed objectives – outcomes to be shared with FCDO. FCDO should consider complementing partner reporting with periodic FCDO monitoring, where feasible.
Adaptive programming and flexibility
NIB is a programme delivering through private sector partnerships, with SMEs exposed to volatile market dynamics and exogenous shocks, as well-evidenced in the past year of delivery. Therefore, adjustments to activities and timelines have been required to maximise impact and feasibility of targets.
Recommendation for the year ahead: consider how similar programmes could use greater use of outcome- rather than output-level budgeting, agreeing flexibility for amending outputs within an agreed outcome-level budget envelope.
Overall, the recommendations above focus on ensuring that BSF delivery in its final year is realistic, well‑prioritised, and tightly aligned with intended outcome pathways, while also generating actionable learning for the wider BEK programming.

Output Title	Improved business environment in target sectors - Business Environment Reform Facility (BERF)
Output number:		2	Output Score:	A
Impact weighting (%):		[40%]	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of stakeholder communiques identifying and prioritising significant and tractable business environment issues in target sectors (cumulative)	4	4 / Outputs met expectation
2.2 Number of Business Environment reform papers submitted for adoption by stakeholders (cumulative)	4	4 / Outputs met expectation
2.4 Number of BERF learning products produced and disseminated to target audience (cumulative)	1	1 / Outputs met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
This output relates to the Business Environment Reform Facility (BERF), which aims to improve conditions for doing business in priority sectors through targeted sectoral reforms, structured public–private dialogue, and support to business support organisations (BSOs) and relevant government ministries. During the reporting period, BERF focused on advancing reforms and sector-level initiatives in the four priority sectors of agro‑processing, tourism, ICT and light manufacturing.
Core activities included: convening stakeholders to agree priority reform issues and produce formal communiques; drafting and submitting business environment reform papers for adoption by government and sector stakeholders; facilitating sectoral initiatives led by BSOs and government counterparts to pilot and socialise reforms; and delivering targeted technical assistance to government ministries and associations following the removal of direct financial assistance.
Performance met expectations across all assessed indicators in a challenging political and operating context, including election‑related disruptions and government reshuffles. The output score of ‘A’ reflects sound prioritisation, consistent delivery against milestones, and credible early reform traction in selected sectors. Four stakeholder communiques were produced, and four reform papers were submitted for adoption, including the National Wellness Tourism Strategy, the IT Decade Strategic Framework, and the Medicinal and Aromatic Plants (MAPs) Strategic Action Plan. Notably, one reform has already progressed beyond adoption into initial implementation, with the formation of the National Wellness Tourism Promotion Subcommittee following the submission of the policy brief. One BERF learning product was also produced and disseminated during the year. Output Indicator 2.3 is not assessed following the pivot to technical assistance rather than financial aid to government ministries following change in FCDO priorities and delivery mechanism.
BERF is on track to meet its end-of-programme outputs targets, with no significant underperformance, though election-period delays and key government officials shuffle required careful sequencing and slight rescheduling of consultations in some sectors.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the past year, BERF made a deliberate strategic adjustment in how sectoral reforms were prioritised. Following completion of PEAs and consultation with stakeholders, the programme decided not to pursue the proposed wool value‑chain reform in light manufacturing, due to limited feasibility, weaker stakeholder buy‑in, and lower alignment with BERF’s scope. This decision reflects appropriate adaptive management and did not affect delivery against agreed logframe indicators.
More significantly, in response to the reduced budget envelope and the need to maximise value for money, BERF will narrow its sectoral focus in its final year. Delivery will concentrate primarily on tourism (particularly wellness tourism) and ICT, where strong government demand, capable BSOs, and demonstrated reform momentum are already evident. Engagement in other sectors will be wound down or limited to light‑touch knowledge transfer. In addition, following the discontinuation of financial aid to government, BERF has fully shifted to a technical‑assistance‑led model, including support to policy drafting, validation, and reform implementation planning.
Progress on recommendations from the previous AR
Recommendation	Progress
Maintain a clear line of sight on the impact of the BERF support to line ministries and stakeholders. Attribution of programme activities must be clear at the outset of partnerships.	BERF has strengthened its engagement model so that each reform or sectoral initiative has a clearly identified champion ministry and/or BSO responsible for guidance, endorsement and ownership. Engagement with line ministries has become regular and structured, providing greater clarity on BERF’s contribution. This is most evident in wellness tourism, where uptake by the Ministry of Culture, Tourism and Civil Aviation, the Hotel Association of Nepal, and private‑sector stakeholders has reinforced attribution and government ownership.
Focus on a few key challenges to increase VfM of the programme by identifying critical bottlenecks in policy, regulation and business environment in priority sectors, rather than spread the programme’s resources too thin across multiple work areas.	This recommendation has directly informed BERF’s delivery approach. PEAs were used systematically to prioritise reform areas, and in the second half of the year BERF concentrated efforts on tourism and ICT, where traction was highest and reforms could move quickly. Other reform areas progressed more lightly, such as agro-processing where less intensive engagement is required or were exited following feasibility assessments.

Lessons learned this year
With BERF now moving beyond reform identification into adoption and early implementation in selected sectors, this year has generated valuable lessons on what enables effective business‑environment reform.
A key lesson is the importance of strong ownership by ministries and BSOs. Reforms in wellness tourism and ICT progressed most rapidly where there was an aligned and capable sector champion, providing sector oversight and credible convening. Ministry buy-in is required for institutional leadership and credibility that BERF activities could lead to reform.
A second lesson is that concentration delivers greater impact than dispersion. Attempting to advance reforms simultaneously across many sectors risks fragmentation and diluted outcomes. Identifying the presence of the previously mentioned success factors – political buy-in and effective BSOs – should inform a prioritisation of scarce resources to deliver greatest impact and value for money.
A third lesson is that business environment programmes can add value through different intervention modes depending on sector context. In areas such as wellness tourism, where political ownership and momentum were initially weaker and the institutional landscape fragmented, BERF added value by convening stakeholders and shaping a shared reform agenda. Here, BERF is playing a more additional and catalytic role. In contrast, in ICT, where reform momentum and government leadership were already established through the IT Decade, the BERF contribution was more targeted, supporting alignment, technical structuring and acceleration. Potentially, where reform momentum is already strong, BERF should identify priority sub‑sectors or innovations that are not naturally surfacing through existing processes to achieve a similarly catalytic effect
Finally, coordination with other development partners amplifies impact as NIB activities decline. Collaboration with the World Bank, ADB and other partners, particularly around wellness tourism and ICT, has increased the likelihood that BERF‑supported reforms will have a sustaining impact.
Recommendations for the year ahead
1. Maintain a tight focus on wellness tourism and ICT, the sectors showing the greatest traction for BERF-led reform agendas
  1. Wellness tourism: consider scope to champion the development of a dedicated wellness tourism BSO, convening the most engaged and capable actors from the currently fragmented ecosystem of BSOs. Experiences from ICT, where NAS‑IT has demonstrated the role that an ambitious and well‑organised BSO can play in driving sectoral reform, suggest this could be a potentially catalytic next step
  2. ICT: identifying priority sub‑sectors or innovations in sector practices that are not naturally surfacing through existing reform processes so that BERF efforts can have the greatest catalytic impact, e.g. viewing IT as an enabler to other sectors within Nepal
2. Continue to embed BSOs and government champions at the centre of reform delivery, including exploring options to formalise coordination mechanisms in wellness tourism to reduce fragmentation.
3. Request the NIB-GA MEL function to analyse pathways for how reforms progressed differently across sectors (e.g. ICT versus wellness tourism), producing a concise learning product to inform future FCDO private‑sector and reform programming in Nepal and comparable contexts
4. Strengthen donor coordination, particularly with the World Bank and ADB, to ensure BERF outputs inform larger system‑level interventions and ongoing levers in the Nepal development landscape
5. Update Output Indicator 2.3, to reflect the change in support to government ministries through technical assistance.

Output Title	NIB CF provides catalytic capital (through RDC products) to FIs (banks and VC/PE fund managers) to mitigate the risks associated with offering tailored debt and equity products that address the financing needs of SMEs
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
3.4 Number of de-risking catalytic capital investments in Oppscan stage. "Oppscan" is the first stage of the formal due diligence process.	2	2 / Outputs met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
This output relates to the Catalytic Finance (CF) component of NIB, implemented by FMO, which aims to mobilise private capital through de‑risking mechanisms and technical assistance supporting investment, firm growth and job creation in priority sectors. The CF component entered its inception phase during the reporting period.
Activities focused on establishing the foundations required for effective deployment rather than implementing activities tracked in the logframe, with the exception of Output Indicator 3.4, which tracks pipeline origination and due diligence on potential investments. FMO is currently exploring investment opportunities in two areas- banks and financial institutions and funds. Three potential investees have been chosen in each category with due diligence planned in May. FMO is working closely with BII exploring co-investment in the funds space.
Key achieved milestones, as set out in the FMO Annual Report, included:
- Establishment of programme governance and advisory structures;
- Development of an indicative pipeline aligned with priority sectors and investor interest;
- Initiation of transaction‑level coordination with selected financial intermediaries; and
- Preparation of technical assistance, MEL and risk‑management frameworks to support future delivery.
These steps are necessary precursors to delivering programme results relating to the mobilisation of finance and job creation. Therefore, alongside the sole non-zero target being met, the output score of ‘A’ reflects generally strong performance against agreed milestones for an inception year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no substantive changes to the CF output objectives or indicators during the reporting period. The component is moving from design to inception, with delivery sequencing prioritising pipeline development, investor engagement and internal systems ahead of capital mobilisation. This sequencing reflects the late start of the component relative to other programme outputs, due to the delay in singing the Memorandum of Understanding with FMO because of change in ODA budget and strategy. Additionally, the need to establish credibility with investors and financial intermediaries before deploying instruments took time.
Progress on recommendations from the previous AR
There were no CF‑specific recommendations in the previous Annual Review, as the component was not yet operational at that stage.
Lessons learned this year
A key lesson from the inception phase is the importance of investing early in governance, pipeline quality and delivery systems for catalytic finance interventions. The experience to date reinforces that mobilisation outcomes cannot be accelerated without upfront investment in structuring, risk management and credible engagement with investors and intermediaries.
A second lesson is the need for close coordination between the CF component and other NIB outputs, particularly BSF and BERF, to ensure pipeline relevance and coherence across the programme. Early interaction suggests potential complementarities, but these will need to be operationalised as delivery moves from planning to execution.
Recommendations for the year ahead
1. Share lessons from BSF and BERF in SME investment-readiness with CF. Barriers to SME investment exist on both the demand and supply-side of finance. Lessons from BSF and BERF demonstrate that firm-level interventions are needed to strengthen investment-readiness, particularly around governance, financial management, ESG and market positioning. This must be reflected in the NIB-CF approach, ideally utilising lessons learned and distilled by NIB-GA, to be shared with FMO.
2. Ensuring catalytic finance delivers additionality and market change. Given the small number of transactions FMO will make under the CF component, there must be a clear and credible articulation of additionality and pathways to impact to maximise likelihood of shifting market behaviour. FMO should articulate the specific constraints each transaction is intended to address and pathways for change, sharing these with BEK for no objection. BEK could consult the FCDO private sector cadre and/or BII in country.
## D: VALUE FOR MONEY
Key cost drivers and performance
The main cost drivers during this reporting period have been through the NIB-GA. This mainly includes technical assistance and advisory inputs to SMEs and government counterparts, grants disbursed to SMEs through BSF, and the cost of convening and consultation under BERF. For BSF and BERF components, expenditure broadly aligns with the business case model, with approximately 45% allocated to grants, 49% to delivery staff and fees, and 6% to expenses. This reflects a human resource intensive cost structure alongside the grant provision.
BERF activity has been relatively resource-intensive in this period, reflecting the nature of policy reform including consultation, technical drafting, stakeholder engagement and validation. These are also harder to quantify in terms of outputs. By contrast, BSF expenditure reflects a mix of upfront costs in terms of pipeline development, due diligence and structuring of partnerships, with ongoing support via grant disbursement and TA delivery. The adjustments to programme timeframes, with planned wind-down from December 2026, means a lot of these costs were frontloaded. During the reporting period, NIB-GA committed £921,355 in grants to 10 partnerships. £750,000 were disbursed into SWEEP accounts ear-marked for the partnership giving the private sector confidence to invest and only triggering disbursement when performance milestones are met.
A key cost-offsetting factors baked into programme design is the match funding contributions from the partner SMEs ensuring direct private capital mobilisation. So far, NIB-GA has spent £209,578 and mobilised £190,327 from partners. We expect private capital mobilisation to rise to £1,401,355 by December 2026 which maintains the business case expectations of a one-to-one mobilisation ratio. Milestone based payments ensure costs are reasonable for delivery.
Assessment of whether the programme continues to represent value for money
The below assessment primarily considers the NIB-GA programme components where delivery is underway, whilst the early stage of the NIB-CF component precludes detailed analysis. In the next annual review, VfM for NIB-CF can be considered.
A. Economy – “Are we buying inputs well?”
Inputs appear broadly proportionate and controlled. Programme management costs are reported at between 9 to 12% of total spend, consistent with business case expectations, with the majority of funding directed to frontline delivery including technical assistance, grants, and sector reform activity. The programme’s cost-sharing model has further improved economy, with increasing levels of private-sector co-investment reducing the funding burden on FCDO while sharing growth-related risk with SMEs.
The programme has taken a number of practical steps to manage input costs, most notably through close collaboration with APO, whereby NIB-GA secured $5,000 of financing contribution for the wellness tourism workshop, enabling delivery of an additional sectoral initiative.
However, there are limitations in the current evidence base. Systematic benchmarking of unit costs as committed to in the business case is not yet well developed. This could include management fees, cost per firm supported, cost per advisory input and cost per reform process. Given the wind-down of components, it is not recommended as proportionate to seek this information now given that on balance, inputs appear to be procured and utilised at reasonable cost, with no immediate VfM concerns.
B. Efficiency – “Are we turning inputs into outputs well?”
Efficiency in converting inputs into outputs appears strong overall, particularly given the programme’s early stage and the disruption caused by budget reductions and compressed timelines. Output delivery under both BSF and BERF has either met or exceeded expectations for the period. Notable examples including the expansion of the BSF cohort from 10 to 12 firms, suggesting effective use of pipeline and delivery capacity.
There is also clear evidence of adaptive management, improving efficiency over the course of implementation. For example, improving internal processes to reduce delays and transactions costs regarding grant disbursements to partners. In response to budgetary changes to the programme, and incorporating lessons learned, NIB-GA narrowed resources behind a smaller number of high priority sectors ensuring the greatest value from our inputs is achieved.
Overall, the programme demonstrates good operational efficiency, with evidence that learning and iteration are improving over time.
C. Effectiveness – “Are outputs leading to outcomes and impact?”
There are early indications that outputs are translating into intended outcomes at both firm and sector levels, as set out in the programme theory of change. A key programme outcome is productive job creation, where results have slightly exceeded expectations – 66 jobs delivered against a target of 60 – despite a disrupted year of delivery. There has also been strong overperformance on inclusion metrics within the disaggregated data for direct job creation. Supported SMEs also show early signs of improved performance including increased turnover and input sourcing from Nepali producers. Finally, through an increased focus, technical assistance has supported core business functions and investment readiness, including governance, ESG practices and financial management.
Taken together, these activities constitute a business support package that has been piloted across several SMEs, with lessons learnt potentially able to shape future programming of BEK and development partners to deliver further impact despite the early closure of the programme.
Through the BERF component, there are also initial signs of market-level impacts. Policy reforms have progressed from identification through to adoption, with one reform entering implementation earlier than expected at this stage of delivery. Learning has shaped delivery, with the NIB-GA team recognising the value of sectoral initiatives and strengthened efforts in wellness tourism and ICT sectors to increase impact.
However, whilst initial indications are positive, they remain early and not yet fully evidenced. Regarding BSF, this is particularly in relation to sustained firm growth, investment mobilisation and longer-term job creation. In addition, evidence on additionality is mixed. Some investments made by firms appear clearly contingent on grant support, whilst others may have proceeded without programme funding, albeit more slowly or at smaller scale. For BERF, there are risks around sustained momentum particularly in the more nascent sector of wellness tourism. The shortened delivery timeline also reduces the likelihood that outputs will fully translate into higher-level outcomes and impact within the programme period.

D. Equity – “Who benefits, and are we checking for harm?”
Across the 4 E framework, performance on equity and inclusion has been the strongest to date, based mainly on disaggregated data regarding direct job creation. Key results include that 45% of jobs created have been for women, against a 20% target. 33% of jobs have been for disadvantaged groups compared to a 10% target. Finally, approximately one third of the SMEs supported are women-owned. These results suggest that the NIB-GA approach, such as sectors targeted, SME selection criteria, the integration of ESG processes and strengthened governance at the firm level has translated into more inclusive outcomes. This should be a focus of any learnings distilled and shared from this programme.
Programme design shifts will create some uncertainty in the final year of delivery, particularly the focus on ICT and wellness tourism instead of agro-processing and light manufacturing, which may have indirect impacts depending on the inclusivity of job creation in those industries. However, performance has been sufficiently strong to date to reassure that it is a key outcome of the programme.
Conclusion
Overall, VfM performance is broadly on track at this stage of delivery, with cost drivers, delivery profile, adaptive programming and early results aligning well with expectations. For the next year of delivery, the key priority is to maximise and sustain emerging outcomes from existing investments and ensure that early gains are embedded in the wider development landscape to support longer-term impact.

E: RISK

The overall risk for NIB programme remains “Major”. The programme team and the partner regularly review, discuss and update the programme risks. The following picture provides a summary of the current NIB programme risk register.

As shown above, the NIB risk register has seven categories of risks and there are fourteen active risks in total.

The main risks identified, and the mitigation plans are as follows.

Financial & Fiduciary:

There is a risk of misuse of funds or corruption involving suppliers, supply chains, or other downstream funding mechanisms. This risk could arise if funds are not used for their intended purposes, due to mismanagement, or if staff are pressured to engage in corrupt practices. The potential impacts include financial losses, delivery disruptions, reduced ability to achieve programme objectives, and erosion of trust.

To mitigate this risk, DAI will implement embedded counter-fraud measures through robust eligibility criteria and strong due diligence of SMEs, partners, and all fund-receiving organisations or institutions. All partners will be fully vetted and assessed prior to contracting. Fund disbursements to grantees and partners will be made conditional upon the achievement of agreed contractual milestones.

A Delivery Chain Map will be regularly updated to present the full flow of funds and identify all recipients, enabling effective tracking and review. Regular spot-check visits will be conducted by team members, due diligence assessments will be periodically updated, and partners and beneficiaries will be required to submit regular technical and financial reports.

DAI will ensure that clear ethical and behavioural clauses are included in all contracts, in line with DAI’s Code of Business Conduct, the UK Anti-Bribery Act, and relevant FCDO policies. Regular capacity-building activities, including ethics training, will be undertaken to ensure that DAI staff and subcontractors understand and comply with DAI’s and FCDO’s ethical standards. Clear escalation procedures will be established to address any emerging issues in a timely and effective manner.

DAI will also apply strict conflict of interest (COI) protocols for all team members, partners, and project associates, including the establishment of a COI register. Any potential or perceived COI, along with mitigation actions, will be recorded in NIB’s Potential COI Register. All staff involved in procurement processes will complete an annual COI declaration to ensure transparent identification and management of conflicts.

Financial mismanagement by failing to achieve robust management of grant funding to SMEs, caused by a lack of awareness and measures in place to ensure accurate financial management. This could lead to a failure to meet programme objectives (particularly VfM) and contractual requirements surrounding financial transparency.

To mitigate this, DAI to put robust cost controls, in line with the contract, agreed forecast and budget. Test transfers will be carried out to confirm recipient bank account and speed of transfers. Financial reports, forecasts, invoices are accurate and submitted on time. VfM is maximised across inputs, outputs, and outcomes as per our VfM framework; agreed regular VfM reporting accurately demonstrates results & good management. Ensure up-to-date and accurate financial reporting of use of the Business Support Facility (BSF) grants and technical assistance pool, which will also be regularly reviewed for spend discrepancies, cash flow and accuracy of forecasts. Ongoing monitoring and accurate reporting of the use of financial assistance provided to the Ministry of Industries, Commerce and Supplies (MoICS) at the federal and subnational levels. Ongoing monitoring of burn rate against allocated budget and the transfer of funds.

Strategy & Context:

There is a risk of insufficient political will for substantive reform or failure to secure project buy-in from national and sub-national (provincial and local) partner institutions. This risk may be driven by limited resources or skills, political instability, or external shocks. The impact could be reduced achievement of programme outcomes, particularly for the Business Environment Reform Facility (BERF) component.

To mitigate this risk, DAI’s team includes an experienced Government Partnerships Lead who will engage closely with government entities to ensure they are informed of programme activities and that these activities align with, or do not contradict, government strategic and political objectives. An iterative co-creation approach will be applied to address the specific needs of each target geography. This approach will be informed by regular stakeholder analysis and engagement, ensuring sustained buy-in and enabling adaptation of interventions to remain responsive to local priorities and interests.

Civil unrest and protests caused by the political environment impacting business operations, transport, and/or local security, thereby hampering programme delivery.

To mitigate this risk, ongoing assessment of the political environment guides decisions on NIB operations. Flexibility of programme design allows for pivot of activity if needed.

Safeguarding:

Breaches of the Code of Business Conduct and Ethics, including bullying, conflicts of interest, corruption, fraud, and sexual or gender-based harassment, represent a key safeguarding risk. These risks may stem from limited awareness or inadequate enforcement mechanisms among implementing partners.

DAI will mitigate these risks by providing security awareness training that includes coverage of sexual and gender-based violence and personal security measures. A harassment reporting mechanism will be established, and staff will be trained in its appropriate use. DAI to ensure adherence to the Code of Business Conduct and Ethics through formal systems and processes.

All staff undergo introductory briefing on DAI’s Code of Business Conduct and Ethics and are required to sign it as part of their contract. All staff undergo mandatory annual training in ethics and safeguarding. DAI’s Speak Up Line includes provision for reporting concern about bullying, misconduct, conflicts of interest, and other ethical concerns. Discrimination-related issues and sexual harassment cases are addressed through rapid escalation by DAI’s Head of Diversity, Equity, Engagement and Inclusion, while bullying and management-related issues will be managed by the Project Human Resources function.

Public Service Delivery & Operations:

There is a risk that the programme fails to increase the social and economic participation of women and other disadvantaged groups (WODG) due to weak recruitment of appropriate companies. This risk may arise from political interference, cultural barriers, or limited willingness among SMEs to actively promote inclusion. The impact could be the reinforced economic and social exclusion for women and disadvantaged groups.

To mitigate this risk, NIB-GA/DAI will conduct periodic audits of processes and procedures to ensure continued compliance with required standards. The programme includes specific KPIs related to WODG participation to monitor and promote inclusive outcomes. Company selection criteria will place emphasis on WODG-owned or WODG-managed businesses. Conflict and Gender Equality and Social Inclusion (GESI) analyses will guide programme implementation to avoid reinforcing exclusion, and investment and implementation strategies for both components will be carefully designed to promote inclusion.

Policy & Programme Delivery:

There is a risk of failing to secure suitable local partners or experts due to limitations in commitment, capacity, or capability. This may result from logistical or institutional weaknesses that prevent partners from adequately supporting NIB’s requirements. The impact could include delays or failure to deliver planned activities and outputs.

To mitigate this risk, the NIB-GA team will proactively identify and engage experts and partners with the appropriate skills and capacity to deliver programme objectives. This will include leveraging extensive national and international networks, using both online and offline channels to ensure broad reach and access to qualified partners.

FCDO budget cuts could erode trust in the long-term, either uncertainty for partners who have already signed BSF agreement or scepticism for potential firms. This could lead to sub-optimal outcomes, especially if firms are not adequately invested into NiB partnership.

To mitigate this risk, NiB will keep clear communication with all potential partners to ensure that they are aware of FCDO commitment.

Programme supports unproductive firms which do not offer genuine potential to create jobs and drive growth.

To mitigate this risk, investments will be guided both by a sector/sub sector prioritization strategy and robust screening process to ensure firms that offer the maximum potential to support programme ambitions receive support. The MEL team will review performance of each partnership and inform the programme exit strategy and timely withdrawal from low performing partnerships - using an adaptive approach.

Reputational:

The programme faces criticisms around market distortion and/ or capture of grants by the privileged class.

Democratising access to capital will be embedded into programme's operational processes and selection criteria. Knowledge products and knowledge dissemination sessions during implementation will focus on clear rationale for interventions (interventions to focus on creating a catalytic effect in the ecosystem rather than distorting the market negatively). Deal sourcing process, including for grants, will be robust and will include an independent selection committee.

Update on Partnership Principles:

Not applicable, as no financial aid was allocated during the reporting year.

https://fcogovuk.sharepoint.com/teams/prof/_layouts/15/Doc.aspx?OR=teams&action=edit&sourcedoc={7D463CDF-8B96-4F5F-BB76-CE3F767971A7}
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The Nepal in Business (NIB) programme was approved in 2023 with a total budget of £36.2 million. The programme has four major components:

1. Business Support Facility (BSF)
2. Business Environment Reform Facility (BERF)
3. SME Finance Facility (SMEFF)
4. Monitoring and Learning

To ensure better value for money and to maximise complementarity and cohesion between programme components, the Business Support Facility (BSF) and Business Environment Reform Facility (BERF) were combined into a single contract. DAI Global UK was selected through a competitive bidding process to implement these components, collectively known as NIB – Growth Advisors. Similarly, FMO was selected through a mini‑competition to implement the SMEFF component, renamed to NIB – Catalytic Finance, which was launched in July 2025. The inception phase of Catalytic Finance was completed in December 2025, and the project is currently at an early stage of the implementation phase.

The table below provides a breakdown of expenditure by programme component.

Components	Spent (GBP) / as of March 2026
NIB – Growth Advisors	£1,657,021
NIB – Catalytic Finance	£12,000,000
MEL Component	£80,795
Insourced Role	£29,311
Total	£13,767,127

NIB – Growth Advisors commenced in July 2024, with the inception phase completed on 14 January 2025. Implementation began in mid‑January 2025. The period from mid‑January to March 2025 was covered in the previous Annual Review, while this report assesses commercial and financial performance from April 2025 to March 2026 which is year 1 of the implementation phase of the project.

The implementing partner, DAI Global UK, is managing the programme effectively. All quarterly and annual reports have been submitted in a timely manner. NIB Ga shared their FY 2024/25 audit report in April 2026. NIB GA is advised to share the ToRs with BEK before they advertise for the procurement of audit firms.

The FCDO team assessed the performance of supplier against all KPI criteria biannually. The scores demonstrate that good performance - supplier delivering efficiently and effectively meeting responsibilities and requirements with little improvement needed.
The BEK programme team conducted a financial and asset spot check of the NIB‑GA project in January 2026. The review observed that project has strong internal control systems in place and utilises an online financial transaction system through which expenditure records were verified. The project has generally maintained an up‑to‑date asset inventory. However, a few gaps were identified, including missing asset values and serial numbers for some IT equipment.

In addition, the review noted areas for improvement in the procurement of services. Some lapses related to transparency and fairness in the procurement process were identified; avoid last‑minute changes to quantities, participant numbers, or scope. If such changes are unavoidable, robust justification and prior approval should be obtained before proceeding. It was also noted that procedural compliances were not fully maintained during tight timelines.

Detailed findings and recommendations from the spot check have been formally shared with the project team for follow‑up and improvement.

The table below provides a breakdown of the actual spend against the forecast for the reporting period.

Budget Category	Forecast 2025/26	Actual spend 2025/26	Variance	%
Programme Staff Cost / (including NPAC and Profit)	£803,136.88	£813,771.68	£10,634.80	1.32%
Expenses	£97,954.55	£93,249.38	£4,705.17	4.80%
Grants	£750,000.00	£750,000.00	£0	0.0%
Total	£1,651,091.43	£1,657,021.06	£5,929.63	0.35%

The total forecast for this reporting period (July 2025 to March 2026) was £1,651,091.43, against which actual expenditure amounted to £1,657,021.06. Overall forecasting for this fiscal year is within the acceptable 5% variance.

There was a slight overspend under the Programme Staff Cost category, mainly due to the inclusion of an additional 2.5 months of KPIs from the previous financial year to align with the reporting cycle. Similarly, the planned second EOI call, originally budgeted at £12,000, was replaced by two additional ESG plans at £8,712.60 each, resulting in an increase of £4,932.

There was an underspend of 4.8% in the expenses category. This variance arose primarily from savings on office rent due to exchange rate fluctuations, as the rent contract is fixed in Nepali Rupees. Additionally, there was an overall underspend of 6.69% on the travel budget line, mainly resulting from cost-effective advance flight bookings made to avoid price increases.

Summary of Grants: The total grant amount disbursed this year is £750,000, which is held in the bank’s SWEEP account. However, the total utilisation of grant funds is only £220,650 against a target of £436,005, amounting to 50.60% of the target. The key reasons for these delays are outlined below.
- Procurement delays & changes
  - Equipment procurement was delayed due to re-evaluation of machinery and specifications.
  - Some machinery (e.g., offset printer) reconsidered as it added limited value.
  - New machinery lines have now been finalised, increasing overall spending %.
  - Additional delays due to vendor LC issues for imported machines (~GBP 40K).
- Operational & project adjustments
  - Strategic shift: reduced focus on Lumbini collection centre, increased focus on Champi facility.
  - New facility location finalised ahead of timeline; procurement now being fast-tracked.
- External challenges
  - Inability to attend international trade fairs due to geopolitical tensions and event cancellations (e.g., Seamless Dubai).
  - International travel restrictions delayed marketing and equipment-related activities.
Overall, while external factors and procurement challenges caused delays, key decisions have been made, implementation is progressing.
Date of last narrative financial report	22 April 2026	Date of last audited annual statement	9 April 2026

NIB – Catalytic Finance commenced in July 2025 and is implemented by FMO. The inception report was successfully submitted in December 2025, and the programme entered the early stage of implementation from January 2026 onwards. Programme management systems are fully established, with core governance and delivery processes in place. Recruitment of a Nepal‑based local consultant is currently underway to strengthen local market insight and support pipeline development.

During the year, a total of GBP 12 million was transferred to FMO, comprising GBP 8 million under the first tranche in November 2025 and GBP 4 million under the second tranche in February 2026. These payments were critical to support FMO in building pipeline of investments. Budget fluctuations have raised questions on FCDO’s ability to honour multi- year contracts. Any risk of spend has been assured by disbursement requests for each investment pipeline.

Date of last narrative financial report	31 March 2026	Date of last audited annual statement	Not due yet

Under the MEL component, total annual expenditure amounted to GBP 80,795. The majority of the cost relates to the contract with PwC that conducted due diligence assessment of FMO before formalising partnership. The remaining expenditure relates to two small contracts procured under this component for the Department for Business and Trade (DBT):

- Market Research for Scoping Business Opportunities for UK Businesses in the Refurbishment of Hydropower Plants in Nepal (GBP 17,990); and
- Market Research for Scoping Business Opportunities for UK Businesses in the Health & Life Sciences Sector of Nepal (GBP 17,948).

Date of last narrative financial report	n/a	Date of last audited annual statement	n/a

G: MONITORING, EVIDENCE AND LEARNING

During the inception phase, a slightly revised programme Theory of Change (ToC) was developed based on the programme Terms of Reference, alongside the key strategy documents. The ToC is the foundation of the MEL system and illustrates the high-level impact objectives of NIB and the programme logic. Furthermore, the ToC guided the development of the NIB Monitoring Evaluation and Learning (MEL) framework to ensure accountability and transparency of programme activities, as well as support the team for evidence-based decision making to enhance sustainability by integrating learning and adaptive management.
Based on the ToC and MEL framework, a monitoring evaluation and learning system was developed to support continuous evidence-based decision making across all programme level – from firm level engagement to overall strategy. The MEL system provides required information to meet the OECD, DAC and FCDO evaluation criteria such as effectiveness, efficiency, impact, relevance, appropriateness, and sustainability as well as incorporating DCED Standard for Measuring Results in Funds Management. The system integrates field visits, quarterly partnership firm reviews, component level reviews and bi-annual programme reviews which provides a structured mechanism for assessing progress and collecting feedback.
Results framework (including logframe indicators) was finalised for both BSF and BERF components - which provides a structure tool for planning, monitoring and evaluation activities as well as supports in defining programme activities, indicators and means of verification. Based on all these technical documents, a MEL system was developed which will be utilised to assess programme performance and progress, thereby ensuring that NIB delivers measurable and impactful results. The MEL system is built around two key objectives: providing results for accountability and improving results through continuous learning and adaptation. The MEL system emphasises robust data collection, analysis, and use of reporting systems to generate credible evidence of NIB’s achievements, enabling the programme to optimise resource allocation and maximise its impact.
The programme has institutionalised learning as a core pillar of its MEL system. NIB team has developed a Knowledge Management Manual that uses a structured approach informed by realist evaluation to understand what works, for whom, and in what context. Learning questions are embedded within each component’s results chain and will be reviewed during formal adaptive management process, including quarterly reviews, bi-annual strategic reviews, and stakeholder workshops.
In its final year of delivery, MEL should focus on disseminating learnings to key stakeholders including the Government of Nepal and MDBs. For example, the initial key lesson identified is that a proactive stakeholder engagement is required to maintain momentum on programme activities.
Counterfactual – What could have happened during the year
N/A, since the programme is in its initial stage of implementation and is currently identifying potential partners to deliver programme objectives. Counterfactual analysis is a key pillar in the approved MEL system of NIB for future years of implementation.