Programme Completion Review

Title: Zimbabwe Humanitarian and Resilience Programme (ZHARP) 2019-24
Final Programme Spend £ (full life): £54,875,954	Review Date:	June 2025
Programme Code: 300972	Start Date: 28/06/2019	End Date: 31/03/2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024	2025
Programme Score	A	A+	A+	A	A	A
Residual Risk Exposure Rating	Major	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/54009338.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.fcdo.gov.uk/iati_documents/56678402.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The primary aim of the ZHARP programme was to meet the urgent, immediate needs of the most vulnerable in Zimbabwe. The programme delivered cash and, until March 2021, in-kind support in rural areas to critically food insecure people, focusing on improving dietary diversity and reducing negative coping strategies such as skipping meals or reducing food portion sizes. During its peak years, the programme provided food assistance to 413,726 people in rural areas (FY 2019/2020) and cash transfers to 110,114 people in urban areas (FY 2020/2021).

The ZHARP programme was implemented by the World Food Programme (WFP) with several national and international non-governmental organisations delivering the activities on the ground. It was initially planned as a 3-year programme but was extended to run for almost a further three years (with a £7m increase beyond the initial business case value), with the aim of layering different approaches onto the cash transfers to explore the nexus between repeated humanitarian inputs and more long-lasting resilience outcomes, as well as integrate gender equality more fully into humanitarian work.

ZHARP played a vital role in supporting vulnerable Zimbabwean households, helping to mitigate the effects of persistent economic and climatic challenges. The programme led to notable improvements in food consumption patterns across both rural and urban areas where assistance was provided. Zimbabwe’s ongoing macroeconomic difficulties—intensified by the COVID-19 pandemic and the 2024 El Niño-induced drought—underscored the continued relevance of ZHARP throughout its implementation. By delivering life-saving assistance, the programme effectively addressed critical levels of food insecurity among affected populations.

The programme showed impressive cross-sectoral working and innovation in terms of gender, which was not anticipated at the business case design stage. In its final years, the programme only operated in the urban domain of Chiredzi, where cash-based transfers were layered with a gender-based violence (GBV) prevention and response model called Toose (meaning ‘together’). This Toose model had been developed and financed under the separate FCDO-funded Stopping Abuse and Female Exploitation (SAFE) programme which ran from 2019-2025. To a lesser degree, the cash transfers were also layered with WFP’s separate urban resilience building programme. This leveraging of other initiatives and funding was notable in the context of Official Development Assistance (ODA) cuts and had other positive spillover effects, for example, in embedding GBV prevention approaches within WFP. WFP has now internalised Toose into its delivery model, and has included the model as part of its proposals for future funding. The economic empowerment component of the Toose model also provided an important exit approach for the programme given cash assistance in Chiredzi has now ended.

Over its lifespan, the programme scaled back its business case ambitions of system strengthening and building resilience as an eventual exit to humanitarian funding, due to both UK budget cuts and ongoing contextual challenges. At the end of the programme, humanitarian needs appear to remain high, with no sustained reductions in the official humanitarian caseloads despite Zimbabwe being a relatively stable country. There are also continued challenges of siloed working between the humanitarian and social protection sectors which weakens efforts to move the country toward more predictable and efficient safety nets for the vulnerable. In the context of low bilateral ODA, the UK should carefully assess how it engages in the humanitarian sector in Zimbabwe going forward. It may be beneficial for the UK to play a greater role in supporting vulnerability assessments and evidence generation to ensure the effective and strategic use of multilateral humanitarian funding.

Major lessons learned, evidence generated and recommendations

- A repetitive loop of humanitarian appeals in Zimbabwe underlines the lack of credible data and alarm systems on food insecurity. Zimbabwe's food insecurity is cyclical and predictable, and the country is broadly stable. Official caseloads are routinely high and may not always be useful in identifying the most vulnerable communities. Ongoing humanitarian assistance as delivered by ZHARP may not be the best use of a smaller pot of ODA, and the UK should be seeing its role increasingly in supporting early warning systems, preparedness and nuanced data to identify genuine emergency needs.
- There continues to be little linkage between the humanitarian and social protection sectors in Zimbabwe. This is an area that the UK should advocate for UN Reform. For example, WFP’s database of 7m people has not been recognised as a starting point for the World Bank / UNICEF social registry in Zimbabwe. The British Embassy should continue to argue for pragmatic linkages between these sectors, and should encourage social protection actors to understand the GoZ’s food assistance as part of wider efforts on social protection.
- Layering a GBV prevention and response programme onto humanitarian or resilience programming presents a valuable and replicable model. In a low-ODA world, stand-alone GBV programming is unlikely to be common. Layering GBV prevention and response onto other economic empowerment initiatives will enable efficiencies in funding, and will allow both the gender and economic dimensions to be more impactful. Evidence from SAFE highlighted the strong linkages between economic insecurity and intimate partner violence (IPV), whilst there are also risks of economic upliftment aggravating violence if underlying gender norms are not addressed. ZHARP provided a useful model of how support for economic security can be more effective and equitable whilst also reducing safeguarding risks when carefully combined with a strong GBV prevention and response component.

How this report was conducted

This report was drafted by the Social Development Adviser who also led on the programme completion report for the SAFE programme, and was thus able to bring together lessons from the two programmes. Given the length and changes in the programme over its lifespan, the annual reviews and reports were an important source of information. The Human Development and Inclusion Team at the British Embassy in Harare also conducted a review of the El Nino Drought Response in 2024 which considered the state of affairs for the humanitarian sector more generally. The findings of this review have also been drawn on in this report.

Actions following approval of this report

This report will be published and will inform planning on the overall portfolio of the British Embassy Harare, which is undergoing significant change due to upcoming ODA cuts. Ongoing inputs into the social protection sector will also be informed by the recommendations from this report.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£49,000,000	£56,100,000
Timeframe	3 years (1 Nov 2019 – 31 Dec 2022)	Almost 6 years (28 June 2019 – 31 March 2025)
Outcomes	Outcome indicator: Food-insecure people in targeted rural districts and urban domains are enabled to meet their basic food and nutrition requirements in the face of severe climatic, economic and other shocks and stresses in ways that increasingly aim to reduce their need for such future assistance.	The outcome statement was adjusted inn 2020 to the focus on immediate needs of most vulnerable people, reducing the original ambition to find “ways that increasingly aim to reduce their need for such future assistance”.

Overall assessment of programme outcomes, sustainability and VfM

The original programme’s business case had several goals. The first primary aim was to deliver assistance to the most food-insecure Zimbabweans, with an initial target of providing 20% of lean season assistance. This focus was justified through evidence by FEWS NET, which suggested that by the lean season in March 2020, Zimbabwe would have been the fourth country after Yemen, DRC and South Sudan in terms of need of emergency food assistance – i.e. it was projected to have the fourth highest number of people in IPC Phases 3 and above. In August 2019, the UN issued a Humanitarian Appeal seeking $468 million and targeting 3.7 million of the most vulnerable people in Zimbabwe and the ZHARP business case directly responded to this appeal.

The business case set out two other secondary aims for the programme:
1. To address the structural causes of vulnerability through piloting approaches to resilience building of vulnerable populations. However, over the course of the programme, the plans for urban resilience work were adjusted, given the significant change in the context requiring a stronger focus on meeting immediate needs of a larger population impacted by COVID-19. Subsequent annual reviews argued that the ongoing high numbers of people with immediate and increased needs meant that “it is no longer realistic nor appropriate to assume that urban resilience-building activities can replace short-term humanitarian support.”
2. To develop a comprehensive national disaster and climate risk financing framework. This activity was stopped, given the focus on the Covid-19 pandemic at the time. There was also recognition of the risk of this activity being run by the international community, instead of being owned by the Government.

Whilst the primary aim of the business case was maintained (although the scale was reduced), the secondary aims were largely removed. In a business case addendum in July 2021, a sharpened focus on meeting the needs of the most vulnerable was approved, rather than on strengthening national systems and starting to address longer-term resilience of rural households. A second business case addendum was approved in August 2022, which focused on better integrating the programme with GoZ’s social protection instruments to support an eventual exit from humanitarian aid, and to support a layering of cash assistance with prevention of GBV through a partnership with the FCDO-funded Stopping Abuse and Female Exploitation (SAFE) programme.
Overall, evidence suggests that the programme did successfully deliver on its primary objective of supporting food-insecure Zimbabwean (see Outcome Indicators in section below). The provision of assistance did cushion households against the severely negative influence of the macro-economic conditions, and food consumption patterns improved across all supported areas, both rural and urban. Also, the coping strategy index significantly improved in urban areas. The ongoing macroeconomic challenges in Zimbabwe, which were exacerbated by the impact of COVID-19 and the 2024 El Nino drought, maintained the relevance of the programme throughout its lifespan as it provided life-saving support to people with critical levels of food insecurity.

That said, the 2024 El Nino-induced drought led to a context remarkably similar to the backdrop on which the ZHARP business case was developed. The 2024 ZIMLAC determined that 7.6 million people (50 per cent of the total population) in the country faced food insecurity as a result of the drought, and the GoZ and the UN both launched flash appeals to fund the crisis. This demonstrates that food insecurity remains a cyclical issue in Zimbabwe with an overall upward linear trend which points to increasing percentages of food insecure populations (see chart below which sets out the percentage of the rural population estimated to be food insecure as determined by the ZIMLAC).
[note] ZIMLAC is the Zimbabwe Livelihood Assessment Committee which is regulated by the Government of Zimbabwe, and determines humanitarian needs for communities. ZIMLAC was formerly named the Zimbabwe Vulnerability Assessment Committee (ZIMVAC).

This observation on the persistence of humanitarian needs in Zimbabwe also informs conclusions on the overall VFM of the programme. Traditional humanitarian assistance is delivered annually at high cost, and however efficiently it is delivered (with cash being more efficient than in-kind assistance), it does not often build lasting resilience on its own. A better approach may be to support the social protection system to provide predictable safety nets, but there has been limited success in integrating the humanitarian and social protection systems in Zimbabwe. Some of this is to do with the political context which prioritises food assistance, and the provision of which has sometimes been seen as partisan. There is also a need for ongoing UN reform to better join up its humanitarian and social protection work.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

Impact Statement: Food security in targeted urban domains in Zimbabwe is maintained or improved in the face of shocks and stresses with improved coping strategies.
- Impact Indicator 1: Livelihood Coping Strategies (compared to control populations). The livelihood-based coping strategy is an indicator that measures the extent of livelihood coping mechanisms that households utilise in response to a lack of food or money to purchase food over a 30-day period. Livelihood-based coping mechanisms affect the longer-term coping capacity of households, and these include the sale of productive assets, withdrawing children from school, and engaging in illegal activities. The indicator classifies households into four categories: stress, crisis, emergency coping strategies, and those that never implemented any of the coping strategies. Under ZHARP, the prevalence of households applying the most severe coping strategies, crisis and emergency coping strategies, notably declined. At the baseline of urban cash transfers, 38.6% of urban households used stress coping strategies (July 2022), only 8.3% did at midline (February 2023). These figures increased over 2024 with the drought and 9.2% used stress coping mechanisms in September 2024. However, this is still below the milestone of 16%.
- Impact Indicator 2: Food Insecurity Experience Scale (FIES; compared to control populations) [SDG2 indicator]. The targets of this indicator were met in FYs 22/23 and 23/24 but this indicator was removed in FY 24/25 given this data was dropped in national assessments such as ZIMLAC. The chart below shows the trends in food insecurity in urban areas, which increased from 30% in 2019 to 42% in 2020, before declining to 29% in 2023 and rising again to 35% in 2024 (Figure 1). Overall, the number of people facing high levels of acute and chronic food insecurity in Zimbabwe has remained relatively high in recent years.

Figure 1: Urban food insecurity trends (2019 – 2024) [Source: ZIMLAC 2024]
Outcome Statement: Food-insecure people in targeted rural districts and urban domains are enabled to meet their basic food and nutrition requirements in the face of severe climatic, economic and other shocks and stresses in ways that increasingly aim to reduce their need for such future assistance. The outcome statement was adjusted in 2020 to the focus on immediate needs of most vulnerable people, reducing the original ambition to find “ways that increasingly aim to reduce their need for such future assistance”.
Outcome Indicator 1: The Food Consumption Score (FCS) is a proxy indicator used to measure household caloric intake and overall diet quality. It is calculated by recording the frequency of consumption of specific food groups and applying weights based on their nutritional value. Based on predefined thresholds, households are classified into three categories: poor, borderline, or acceptable food consumption levels. There was an overall improvement in household food consumption patterns. The proportion of households with acceptable FCS increased from 42.1% at baseline (when households were not receiving assistance) to 94.9% in March 2024, settling at 90% at endline.
- Outcome indicator 1.2: The Negative Coping Strategy Index (CSI) measures the extent to which households adopt coping strategies over a seven-day recall period when faced with food shortages or limited financial resources for food. A higher rCSI indicates more frequent and/or severe coping mechanisms. Under ZHARP, there was a declining level of food insecurity stresses within the household from 17.4 (out of 56) for urban households at baseline, to 5.3 at endline. This exceeded the milestone of 8.3, and showed that there was a declining proportion of households resorting to strategies such as relying on cheaper or less preferred foods, borrowing, reducing the number of meals that are usually consumed by the households per day, limiting portion sizes, and restricting adult consumption for young children. The programme’s assistance was important in driving this change, although it must be noted that this data is self-reported and there was no comparison group.
- Outcome Indicator 3: The Food Expenditure Share measures the proportion of each household’s available budget spent on food. In general, the higher the expenses are on food in relation to other consumed items and services, the more economically vulnerable the household. In general, over the course of ZHARP, there was an improvement in Food Expenditure Share. The proportion of households spending 65% or more of their expenditure on food decreased from 50.5% (baseline) to 33% (endline), indicating reduced economic vulnerability. However, this indicator was closed in FY 24/25 given its removal from WFP’s corporate framework.
- Outcome Indicator 4: The Minimum Dietary Diversity Women indicator measures the proportion of women and girls aged 15–49 who consumed at least five out of ten defined food groups in the previous day or night. It serves as a proxy for micronutrient adequacy, a key dimension of diet quality. The proportion of women meeting this minimum dietary diversity increased from 23.3% at baseline to 65.5% at endline. The indicator was however closed in FY 24/25 given the reduction in the scale of the programme. It must be noted that whilst the targets for this indicator were consistently met in the urban areas, targets were not met in rural areas in the early years of the programme given the effects of the Covid-19 pandemic.

## C: Detailed Output Assessment

Output Number and Title	Effective delivery of cash-based transfers to the most food insecure and vulnerable individuals in targeted urban domains
Output Score	A
Impact weighting (%)	50%		Impact weighting revised since last AR?	No

Output Indicator		Final Result	Narrative and Final PCR score
% Transfers completed by monthly distribution cycle		The target for this output was 95% in its final year, which was met with a 98% completion rate.	A: This target was met and in most years 100% transfers were completed by the monthly distribution cycle.
Number of men, women, boys, and girls receiving cash-based transfers/ commodity vouchers		The final year target of 11,000 people receiving cash based transfers in Chiredzi was met. In the February 2025 disbursement cycle, 10,998 cash-based transfers were distributed (6879 females and 4119 males, 458 people with disability).	A: For all financial years this target was consistently met. The overall number of beneficiaries reduced as the programme progressed with a peak of 132,114 people provided with cash transfers in FY20/21, down to 11,000 people in 24/25.
% of total contribution directly transferred to people assisted		This output was removed from FY 22/23 given the addition of the SAFE programme to the scope of work.	A+: When this output was included, it consistently passed the target of 70% indicating good value for money.
Previous Output 1: Effective delivery of food assistance to the most food insecure and vulnerable rural households.
Previous Output Indicator 1.1: Average # of women, men, boys and girls receiving food/cash-based transfers/commodity vouchers (and % of the planned)		This output was closed at the end of FY 20/21 given the termination of food assistance to rural areas. / Previous targets: / FY 19/20: 270,00 / FY 20/21: 167,578	A+: For the two years of inclusion, this output indicator consistently exceeded its targets. In FY19/20 413,726 people were supported in the lean season, and in FY 20/21, 259,249 people were supported.
Previous Output Indicator 1.2: % of the daily kcal requirements of the people assisted enabled by the monthly in kind distribution		This output was closed at the end of FY 20/21 given the termination of food assistance to rural areas.	A: For the two years of inclusion, this indicator met it target of 62.5%.
Previous Output Indicator 1.3: Proportion of food assistance decision-making entity committee members who are women (Rural)		This output was closed at the end of FY 21/22 given the termination of food assistance to rural areas.	A+: For the two years of inclusion, this indicator exceeded its target of 50%. In FY 19/20, 62% of the committee were women, and in FY 21/22, 65.6% were women.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This Output focuses on the delivery of cash-based transfers in urban areas, and previously food assistance in rural areas. Across the lifespan of this indicator, targets have almost always been met in terms of beneficiaries reached and the equity and cost-transfer ratio around this. A peak of 132,114 people provided with cash transfers in FY20/21, down to 11,000 people in FY24/25, given reducing ODA budgets as well as changing priorities for the British Embassy in Harare. Large numbers were also supported with food assistance during the early years of the programme based on the appeals around urgent food security needs– for example, 413,726 people were supported in the lean season of FY19/20, and in FY 20/21, 259,249 people were supported.

In its final years, the programme focused on assistance to the urban population in Chiredzi. Livelihoods in the district are highly vulnerable to climatic shocks, including frequent droughts and flooding, especially as Chiredzi is prone to cyclones. Flooding in urban wards 4, 5, and 6 regularly disrupts livelihood activities during the rainy season, contributing to Chiredzi’s status as one of the most frequently food-insecure urban districts. In addition to localised shocks, national macroeconomic factors such as inflation and currency volatility further undermine household food security. Data confirms that food insecurity was a significant challenge in Chiredzi over the programme years, rising from 26% in 2019 to 45% in 2023, and then slightly improving to 35% in 2024.

WFP employed a multi-tiered targeting strategy in Chiredzi to ensure that assistance reached the most vulnerable and food-insecure populations. Following the identification of food insecurity "hotspots" in collaboration with local authorities and partners, geographical targeting was conducted using key food insecurity indicators. Each hotspot then underwent a door-to-door baseline data collection exercise, gathering information on household size, income, disability and disease burden, shelter, and food insecurity. This data was entered into WFP’s beneficiary management system and analysed using a syntax developed by WFP’s research team.

WFP also worked to ensure that its support went to the most vulnerable through several retargeting exercises over the lifespan of the programme (including in April-June 2021 and March-April 2024). For example, in 2021, this retargeting resulted in maintaining 58% of the caseload, while 42% was replaced with new, more vulnerable households. Whilst the risk of politicisation of food assistance remained throughout the programme, the agreement that WFP supported entire geographical units allowed for better planning and ensuring distribution to those with real need.

In Chiredzi, the modality of assistance also changed flexibly in response to contextual and economic conditions as well as beneficiary feedback. Food insecure households were initially provided with food vouchers for redemption at specified retailers until December 2022, after which they were provided with physical US Dollar cash through the Mukuru money transfer agent. Beneficiary feedback and market analysis by WFP indicated vouchers were more problematic and less effective value for money than direct cash transfers, so the switch was made. Families were then provided with US$13 per actual household member, (a rate set to be in accordance with the National Food Security cluster guidelines) per month. Beneficiary feedback in the period following the change indicated it was well received, and beneficiaries appreciated the flexibility actual cash gave them.
[note] UN Food Security Cluster and UN Humanitarian Country Team 2023. Family sizes were not averaged and there was no cap on the maximum number of family members per household.

One challenge experienced was due to the high rates of beneficiary mobility in Chiredzi, which resulted in some households failing to redeem entitlements within the set period. Due to its proximity to South Africa and limited livelihood options in Chiredzi, beneficiaries often travelled to nearby areas in search of opportunities. This highlights the importance of extensive sensitization of beneficiaries regarding disbursement dates.

Lessons learned through this output, and recommendations for future programming

Despite the programme meeting the targets under this Output, the broader challenges facing the humanitarian sector in Zimbabwe remain pertinent. There is no real sustainability to humanitarian assistance in Zimbabwe, and it is not clear that cash transfers alone built any longer term resilience amongst the urban population. Caseloads of food-insecure people remain high and predictably linked to droughts given the prominence of rain-fed agriculture. As the context globally shifts to a low-aid world, more accurate alarm systems and credible identification of the most vulnerable is required to focus limited humanitarian resources in Zimbabwe. Alongside this, greater linkage of the humanitarian and social protection sectors is required to enhance efficiency of funds and build longer term predictable systems to support the most vulnerable.

The challenges with humanitarian spend in Zimbabwe were recognised across annual reviews, and extensions to the programme were approved in the context of the innovative partnership with the SAFE programme which provided opportunities to generate evidence on GBV prevention and explore linkages between the provision of humanitarian assistance and resilience-building activities delivered in parallel with gender transformation models. The SAFE partnership was also part of the exit strategy of the ZHARP programme, as it further provided economic empowerment opportunities through helping households develop income generating activities.

Output Number and Title		Mitigate protection risks through the provision of community-based support and response mechanisms
Output Score		A+
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Final Result		Narrative and Final PCR Score
Proportion of targeted people receiving assistance without safety challenges	The proportion of households reporting no safety issues increased from 90% at baseline to 98% in March 2024 and 98.6% at endline.		A+: This Indicator consistently exceeded the 90% target and met the target when it was increased to 100% in FY 23/24.
% of priority 1 complaints and issues raised by people that are responded to by WFP	At endline, 100% of complaints and issues were responded to by WFP.		A+: This Indicator consistently exceeded the 90% target and met the target when it was increased to 100% in FY 23/24. Across all programme years, every priority complaint was responded to (100%).
Previous Indicators under this Output
Proportion of households where women, or both women and men make decisions on the use of food/cash/ vouchers (rural & urban)	This Output was closed after FY 22/23 given the data was no longer being collected by WFP and this indicator was difficult to standardise.		A+: Across the four FYs where this indicator was included, targets were consistently met. At least 95% of households reported women-led or joint-couple decisions on resource use, in both rural and urban areas.
The PSEA Coordinator technically ensures that PSEA is incorporated throughout all facets of the HRP and that a dedicated inter-agency PSEA project is included to fundraise resources to support collective PSEA initiatives in 2021	This Output was only included in FY 20/21. FCDO funding for PSEAH position at the Resident Coordinator’s office (RCO) ended in May 2021.		A: This indicator was met as each sector in the Humanitarian Response Plan (HRP) had a reference to PSEA as well as the overview chapter; and one dedicated project was included and funding was available from Ireland, starting 1 April 2021 for one year (300,000 €).
The coordination of the humanitarian response is enhanced through improved information products (funding overviews, accountability on received resources, Humanitarian Needs Overview – HNO 2021)	This Output was only included in FY 20/21. FCDO funding for humanitarian coordination positions at RCO ended in December 2020.		A: HNO was finalised and a chapter on Zimbabwe included in the global Humanitarian Needs Overview for 2021; HRP was finalised, but GoZ refused to launch officially after lockdown ended in March 2021; Funding Tracking was available until December 2020 and resumed in May 2021 although clear funding tracking has not been maintained in the sector.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output considers accountability to affected populations (AAP), including issues of do-no harm and community feedback. Overall, this output scored an A+, given WFP’s strong mechanisms to support AAP, including a national tollfree hotline, a helpdesk and suggestion box in the community and a sensitisation campaign around the feedback mechanisms. The programme consistently met the targets around safety and responding to complaints under this Output area. WFP is also an active member of the “Group of Friends on AAP” and hosted a field visit to Chiredzi in 2024 to share best practices. WFP analysis showed that the proportion of households who were informed about programme modalities such as selection criteria and entitlements remained high at 96.9% in March 2024 and 94% by project closure.

Regular training on safeguarding to all implementing partners was also conducted. Most recently, a PSEA training was conducted in Chiredzi in July 2024, targeting staff from WFP, Plan International, Musasa, financial service providers, and relevant government line ministries, including the Ministry of Women’s Affairs, Community, and Small and Medium Enterprises, the Department of Social Development, and the District Development Coordinator’s Office. The training focused on humanitarian principles and protection from sexual exploitation and abuse. PSEA banners, written in the country’s three main languages—Shona, Ndebele, and English—were also prominently displayed at redemption centres. An additional layer of activities was introduced to enhance protection among assisted households through the layering of the SAFE programme. This initiative aimed to reduce intimate partner violence, gender-based violence, and other forms of abuse. It also funded important GBV response services in Chiredzi including a one-stop centre and a shelter.

In 2020, this programme also funded several roles in the UN Resident Coordinator’s Office. The first was a role around Preventing Sexual Exploitation and Abuse (PSEA), as well as two OCHA positions to support humanitarian coordination. Progress by these roles was seen to be adequate at the time although there was some challenge due to their work on a Humanitarian Response Plan (HRP) which the GoZ never launched. Since then, there has not been a UN endorsed HRP, with Zimbabwe now following the GoZ’s Lean Season Response plan, and so there appears to have been limited sustainability to this work.

This programme promoted the active participation of women in managing household resources, especially in rural areas where gender norms often discourage women taking part in decision-making. The proportion of households where men and women make decisions jointly over the use of cash assistance remained high at over 95% of households. However, it is not clear how accurate this self-reported data is, as the independent endline study of the SAFE programme found that women’s input into decision making and genuine agency may have reduced over the programme lifespan, including in Chiredzi, when using several international measures.

Lessons learned through this output, and recommendations for future programming
There needs to be clear organisational commitment to genuinely protecting beneficiaries and mitigating safeguarding risks, and this requires dedicated budget to ensure appropriate and accessible feedback mechanisms. Layering a GBV prevention and response programme plays an important role in meaningful reduction in safeguarding risk and presents an efficient and impactful model for replication.

Output Number and Title		Effective delivery of Toose (TISALS + Toose Curriculum) in targeted urban domains
Output Score		A
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Final Result		Narrative and Final PCR Score
Number of men and women participating in TISALS	This was a new output for the final programme year.		A: The target of at least 227 people participating in the Toose Internal Savings and Loans Groups (TISALS) was met through 16 women groups (involving 224 women, with an average group size of 14) and 2 men groups (comprising 26 men, one group of 14 and one group of 12).
Number of individuals participating in Toose	This was a new output for the final programme year.		A: The target of 454 people participating in the social empowerment Toose course was largely met. 435 people (218 female and 217 male) graduated from the programme which meant that they attended at least 6 of the 9 Toose sessions.
Number of persons accessing GBV information through GCBCs	This was a new output for the final programme year.		A+: The target of 600 people was exceeded and 814 people accessed GBV information through the GCBCs.
Number of persons who received GBV response services	This was a new output for the final programme year.		A+: The target of 300 people was exceeded and 741 people received GBV response services (mobile one-stop centre +static one-stop centre + shelters)
Previous Indicators under this Output
A previous Output in the 2023 AR included “Development and effective delivery of a VAWG prevention model, combining social empowerment with household economic strengthening measures, underpinned by robust evidence and learning” together with indicators from the SAFE programme. However, the Annual Review noted that these indicators would not have been included in the weighting to avoid double counting, as they were captured in the SAFE logframe.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

During the final year of the programme, WFP took over direct implementation of the fourth cohort of SAFE beneficiaries, and the layered programme was offered to individuals receiving the cash-based transfer in Chiredzi, with further engagement of other households through community diffusion. WFP managed local implementing partner, Plan International, to deliver the economic empowerment and social empowerment activities. Musasa continued to provide response services together with support to Gender Community-based Clubs (GCBC) to enhance their knowledge and skills to effectively support to the GBV survivors at local level and referral for protection services.

In this forth cohort, 18 Independent Savings and Loans (ISAL) groups were formed. Each group completed 6 sessions of ISAL training and 5 modules of Selection Planning and Management (SPM training) regarding income generating activities (IGAs). Following this, a seed strengthening fund of USD200 was distributed to all 18 groups. The seed funding bolstered the ISAL groups' portfolios, enabling members to take out loans to support their IGAs. In December 2024, 10 ISAL groups had share outs ranging from US $1,046 to US $2,360 savings (excluding the seed fund) being shared out, with members receiving amounts ranging from US $68 to US $340 depending on one’s savings. In January 2025, the remaining 8 ISAL groups had share outs, with the lowest being $2,172 and the greatest being $4,408. No one reported using the loans to buy food or pay for other household needs, which speaks to the importance of the complementary cash-based transfer which allowed households to use ISAL loans on IGAs. The main IGAs which ISAL participants engaged in were baking, hairdressing, horticulture, informal and petty trade, livestock, and retail.

From September 2024, the social empowerment curriculum (Toose) was rolled out to the 18 ISAL group members and their partners. This curriculum covered topics around conflict resolution, power and intimate partner violence. Review and feedback meetings between implementing partners followed each session. Following the completion of the Toose curriculum in January 2025, 435 participants (218 female and 217 male) who attended at least 6 of the 9 Toose sessions graduated from the programme.

The response component was also a key aspect of the programme. Current global evidence suggests that implementing programming on GBV will increase demand for response services, due to both increased awareness of what violence looks like, and backlash. In order to ensure that programmes are ethical, GBV response services should always be provided alongside prevention programmes. Musasa led the provision of response services including a one-stop centre and shelter in Chiredzi. Musasa also engaged 20 members (14 men and 6 women) from the community to be part of the gender community-based clubs (GCBCs). During the fourth cohort, the GCBCs successfully engaged with 814 people, providing them with valuable information and support. A total of 741 survivors sought various psychosocial support services (counselling, accompaniment, transport services, shelter, medical and legal) from July 2024 to February 2025. Of the 741 survivors who accessed Musasa’s support services, the most common forms of violence that were reported were emotional violence (32%), physical violence (31%), economic violence (19%), and sexual violence (18%). The referrals for services were coming from the GCBCS, Victim Friendly Unit, Courts, and the Ministry of Health.

Lessons learned through this output, and recommendations for future programming
The embedding of a GBV prevention and response programme within food delivery agency, WFP, remains an important achievement, and can serve as a model for similar layered programming beyond the pilot areas, and feasibly beyond Zimbabwe. WFP fully engaged with all aspects of the Toose implementation and proactively distributed lessons about it across WFP offices. There is evidence of sustainable commitment to the GBV programming within WFP, and WFP recently submitted several funding proposals for both resilience and humanitarian programmes with a Toose component.

Evidence from the SAFE programme, including the endline study, highlighted economic insecurity as a significant factor in GBV and intimate partner violence (IPV). Women in households where food security improved or remained stable were less likely to report IPV, whereas those experiencing greater food insecurity at endline reported increased IPV across all measures. While SAFE’s economic activity, ISALs, did not fully mitigate economic shocks, an association was found between women taking multiple loans and reduced severity of IPV - suggesting that access to financial resources may contribute to lowering stress-related triggers of violence. These findings reinforce the importance of integrating economic empowerment initiatives into GBV prevention programming.

The SAFE studies also suggest that layering the programme onto the cash-based transfers was successful in mitigating economic stress. The cash-based transfers in Chiredzi allowed households to use vouchers or cash for food, strengthening their ability to direct money into ISAL savings that could then be converted into loans and income generating activities (IGAs). The layered approach, integrating cash assistance into the Toose initiative, ensured that both food insecurity and underlying drivers of gender-based violence were addressed simultaneously.

Output Number and Title		Contribute to the development of the Toose Manual
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Final Result		Narrative
Implement the adapted Toose package received by SAFE Communities in May 2024	This was a new output for the final programme year.		A: The full Toose Social Empowerment Curriculum was implemented. All 9 Toose sessions were delivered between Sept 2024 – January 2025.
WFP adapted package, drafted and submitted in January 2025 by SAFE Communities (M&E framework, training materials, and Toose curriculum), has undergone thorough WFP review following its reception	This was a new output for the final programme year.		A: WFP and SAFE-C worked closely together to review and agree a package of materials. The WFP package in the end did not differ significantly from the broader Toose package. The full package included the following documents: / Toose Implementation Guide / Toose Economic Empowerment Facilitators Guide / Toose Social Empowerment Facilitators Guide / Toose Response Guide / Toose Community Diffusion Guide / Toose Fidelity Brief / Toose Implementation Videos (9 in total)
Previous Output 4: Building capacity of local stakeholders and strengthening integration with the Government of Zimbabwe’s national social protection policies
Previous Output 4.1: Number of workshops and trainings organized with government stakeholders for capacity building and policy alignment on social protection	This output was closed in FY 23/24. The targets in previous years were: / FY20/21: 1 / FY 21/22: 1 / FY 22/23: 1		A: This indicator was consistently met with meetings held each year. In 22/23, a training of social protection was delivered and harmonised manuals were prepared. However, these results must be nuanced against the continued lack of GoZ commitment to the core social protection instruments and the fact that this manual has not appeared to make a significant impact.
Previous Output 4.2: Improved coordination between development partners and the Government of Zimbabwe (GoZ) on food security and social protection in urban areas through a joint workplan and quarterly coordination meetings	This output was closed in FY 23/24. No formal targets were set but the logframe asked for qualitative evidence of improved coordination in FY 20/21; 21/22 and 22/23.		A: This indicator was consistently met with meetings held each year. In 22/23, a social protection roadmap was drafted. However, these results must be nuanced against the ongoing challenges of integration between the humanitarian and social protection sectors.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

In the final year of the programme, SAFE partners jointly defined what a Toose manual adapted to WFP would be comprised of, and agreed upon timelines for the delivery, review and finalization of a WFP adapted Toose package. WFP Zimbabwe formed an internal reference group to review the Toose package and provide strategic guidance.
There were some collaboration and coordination challenges between WFP and SAFE-C on the package of materials, complicated by staff movement and turnover, and some confusion in agreeing the roles of different stakeholders in this process. However, this was rectified in the final months of the programme, and a package of materials was carefully reviewed by WFP. There were some delays in the timeline to producing the materials, which condensed review time, but the final materials package is comprehensive, professional and clear. WFP has strongly absorbed the Toose approach and has included it in proposals for future humanitarian and resilience funding.

A previous Output 4 focused on enhancing linkages between the humanitarian and social protection sector. The indicators were largely met but remained somewhat superficial (focused on meetings and workshops). It is not clear at the end of the programme whether there is any real integration of humanitarian and social protection. The failure of the World Bank to consider WFP’s humanitarian database as a starting point for the social registry provide one example. Similarly, the GoZ’s capability and commitment to providing significant food distribution over the El-Nino drought has also not been recognised as part of the wider efforts on social protection. Even within UN coordination structures, there is limited collaboration, with WFP irregularly attending the social protection coordination meetings that are chaired by UNICEF.

Lessons learned through this output, and recommendations for future programming
Careful programme management is required to ensure that timelines are met. There were some missed opportunities such as a final programme event which did not include presentation of the full package of materials. A further lesson is around relationship management between different implementing partners – the FCDO may add value in taking a more proactive approach to ensure strong working relationships and progress on joint tasks.

D: Value for Money

 VfM performance compared to the original VfM proposition in the business case

The programme demonstrated VfM against several indicators:

Economy - Cost efficiency gains were achieved through several initiatives:
- The shift from vouchers to USD cash reduced vendor price inflation and increased purchasing power. With the vouchers, beneficiaries had a limited 3-day window to redeem, and vendors tended to inflate prices during the voucher redemption periods. Cash increased competition and encouraged fairer pricing.
- The use of Mukuru as a financial service provider offered competitive pricing and wide accessibility. Mukuru offered lower transaction costs compared to other providers and had multiple redemption points in Chiredzi.
- The consolidation of delivery partners (e.g., Plan International delivering both CBT and SAFE) reduced overhead costs in terms of delivering both aspects of the programme in its final year.
- The CTR (Cost Transfer Ratio) was overall adequate. For example, in 2021: 72.8% of funds directly transferred to beneficiaries. However, the CTR was inconsistently tracked over the programme’s lifespan, and enhanced monitoring of CTR is important for future humanitarian programming.

Efficiency – The programme demonstrated efficiency through transfer completion, targeting improvements and digital innovations:
- Over 2023–2024, 100% of monthly transfers completed on time. For five out of six of the programme years, over 95% of transfers were completed on time.
- Reprofiling exercises in 2021 and 2024 improved inclusion/exclusion accuracy, through a retargeted caseload of the most vulnerable.
- Digital innovations including use of Mukuru enabled better tracking, reconciliation, and reduced fraud risk.

Effectiveness – The programme demonstrated effectiveness in the significant improvements of outcome indicators from baseline:
- The transfer amount of 13 USD per person per month was calculated to cover approximately 60% of an adult’s basic food needs, and this did result in improvements in the Food Consumption Score (FCS) from baseline, as well as a drop in the Coping Strategy Index (CSI) which indicates less frequent and/or severe negative coping mechanisms.
- The integration with the SAFE programme (Toose model) showed reductions in severe intimate partner violence (IPV) and the mean number of IPV acts since baseline. Over 800 CBT beneficiaries accessed GBV services in 2023–2024. The cash-based transfers provided a financial cushion enabling beneficiaries to engage in gender empowerment and income-generating activities.

Equity – ZHARP prioritised assistance for highly vulnerable households based on specific inclusion criteria, such as those headed by children, elderly caregivers of orphans, widows/widowers, households with one or more disabled or chronically ill members, and pregnant or lactating mothers.
- The retargeting exercises ensured those most in need received assistance. For example, the final retargeting in March and April 2024 resulted in revised caseloads for all retargeted domains.
- Specific attention was given to increasing the numbers of persons with disability who received support. This was achieved and disability inclusion increased from 1.3% (2021) to 5.1% following the first retargeting, and then to 4.2% following the second retargeting exercise.

Overall, the programme demonstrated VfM against its objectives by delivering timely, targeted cash assistance which improved food security outcomes. Its value for money was enhanced through leveraging partnerships with the SAFE GBV prevention programme and with WFP’s ongoing urban resilience programme, which enhanced impact at lower costs. This layered approach of combining humanitarian cash with gender empowerment and resilience generated significant learning and offers a replicable model for future interventions both by the WFP and other development partners.

However, as previously discussed, humanitarian spend does not present the best value for money, and social protection instruments are better value for money in relatively stable countries like Zimbabwe. Humanitarian delivery mechanisms are by nature expensive, suffer from short term fluctuations so do not necessarily build lasting system resilience, and do little to prevent the following year facing the same risk. In a low-ODA context, the bar for humanitarian intervention needs to be even higher in terms of credible analysis of emergency needs, and ongoing efforts in Zimbabwe to integrate humanitarian support into predictable safety nets is required.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

During its first year, the programme was classified as a major risk. This reflected the challenging external environment (particularly Covid and the currency volatility), as well as reputational risks linked to fiduciary and potential politicisation of food aid. This was in the context of the significant disbursement of £25m during the first year of the programme.
For subsequent programme years, the programme risk was classified as Moderate overall. Strategy and context risks continued to be present, and in the final year of the programme, was particularly related to the 2024 El Nino drought. Political interference in beneficiary targeting remained a risk but was largely mitigated through the multi-tiered targeting approach which included several household profiling exercises, as well as consultations with community and local stakeholders to ensure broader ownership.
Safeguarding risks remained pertinent throughout the programme lifespan given the vulnerability of beneficiaries. Mitigation mechanisms included a PSEA focal point in the Country office, training of staff, and then strong, appropriate and accessible community feedback and complaints mechanisms. The programme also funded a PSEA position in the UN Resident Coordinator’s Office at the beginning of the progamme. That said, it remained concerning that there were no safeguarding reports during the lifespan of the programme, which is a red flag that mechanisms may not have been working as they should.
Operational risks were also experienced through staff turnover on both implementing partner and within the FCDO. Whilst strong handovers and short-term temporary support was engaged during the course of the programme, changes inevitably led to some challenges and delays. Another risk related to potential changes in national directives governing cash provision to beneficiaries. In July 2024, the government issued a directive prohibiting cash assistance in rural areas, but this did not affect the ongoing deliver of cash in urban Chiredzi. Delivery risks also included fluctuations in commodity prices which had the potential to erode the value of assistance and reduce beneficiaries’ purchasing power. Commodity prices and purchasing power were monitored on a regular basis, and assistance was provided in USD.
In the final year of the programme when WFP implemented SAFE, the joint SAFE risk register was also updated regularly. This included risks around consortium coordination and alignment between SAFE and ZHARP funds.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Financial management was conducted adequately during the course of the programme. A total of £54,875,954 was disbursed during the lifespan of the programme, with the peak in its first two years. Thereafter, annual spend dropped below £5m per year (see chart below). This meant that the contribution of ZHARP to the British Embassy portfolio declined over its lifespan, from 22% of the total FCDO Zimbabwe budget in FY 21/22, to 8% in FY 24/25. There were no FCDO programme funded assets.

There was a good working relationship between FCDO and WFP, with fairly regular conversations at both the programme and strategic level. The WFP team also joined the monthly programme working group meeting for the SAFE programme, which was important to ensure join-up across the different streams of work between the two programmes.
During the final year of the programme, WFP opted to implement the Toose approach in Chiredzi. The benefit of this was that the local implementing partner, Plan International, was already familiar with the methodology and was also implementing the cash transfers. This allowed efficiencies in programme delivery through making use of one implementing partner for both components of the programme, and also enabled effective delivery of the layered model.
The reporting requirements on WFP were low, and the reports that were received did not provide significant detail on financial spend. Reports were also sometimes delayed, and there were lower assurances around funding spend compared to other partners which have contractual requirements to the FCDO.
Programme-level approach to monitoring and evaluation

Monitoring
Regular field visits took place over the lifespan of the programme. During this extension year, WFP made use of the existing SAFE monitoring framework to track implementation of the SAFE programme, although some adaptations were required given WFP’s existing delivery model. The ZHARP delivery methodology of cash-based transfers via Mukuru provided a strong basis for monitoring of the numbers reached, as it allowed real-time reconciliation which improved financial transparency. WFP’s post distribution monitoring, conducted every two months, used internationally recognised indicators of dietary diversity and reductions in use of negative coping strategies. GoZ’s data in the form of the annual ZIMLAC reports were also used.

However, more generally, there is a lack of credible data around food insecurity in Zimbabwe (for example, GoZ does not adopt the IPC measure), which means that political agendas and established narratives dominate. Official caseloads are routinely high and seemingly unrelated to data on ground reality.  There is a need for stronger evidence around humanitarian appeals, based on defensible evidence and clearer identification of vulnerability and suffering.

Learning
The programme did not undertake a formal evaluation given it was primarily a humanitarian programme, and so made use of post-distribution monitoring data. However, the ZHARP collaboration with SAFE gave rise to significant learning about the interrelation of cash support and GBV prevention which would not normally be generated by a more standard CBT programme. This has been of great importance and value to FCDO, WFP, SAFE and also external stakeholders. Broadly, the learning found that the SAFE approach had positive impacts in multiple areas. There were significant improvements in the wellbeing of family units, with participants reporting better communication, joint decision-making in households and more gender equitable attitudes at endline. The learning also highlighted how food insecurity was a key driver of GBV, for example, the endline study found that IPV only increased in households that experienced increased food insecurity, highlighting the importance of addressing both. The endline study also found that there are limits to the impact on GBV that one intervention can have, as fully transforming underlying gender norms takes significant time, economics, social and cultural changes. Further detail on the learning from the SAFE programme can be found in the SAFE PCR on Devtracker.

Date of last narrative financial report		Date of last audited annual statement