## Annual Review Template

Title: Humanitarian Assistance and Resilience Building in Somalia (HARBS)
Programme Value £ (full life): £300 million		Review date: 07/08/2025
Programme Code: 300978	AMP start date: 07/08/2022	AMP end date: 31/07/2028

Summary of Programme Performance
Year	2022/23	2023/24	2024/25
Overall Output Score	A+	A	A+
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003443.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006814.xlsx

## Scoring your programme
## The Annual Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.
Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of overall programme
The UK through the Humanitarian Assistance and Resilience Building in Somalia (HARBS) Programme is providing effective life-saving humanitarian assistance and improved crisis preparedness, whilst building the resilience of the most vulnerable in Somalia to recurrent shocks. In terms of overall impact, the programme is estimated to assist at least 7 million people through a combination of resilience, durable solutions, and emergency humanitarian support. More specifically HARBS will programmatically seek to deliver against four broad outcomes:
  1. Deliver effective and timely emergency humanitarian assistance and protection services.
  2. Reduce vulnerability of displaced communities though durable solutions programming.
  3. Support vulnerable rural communities to cope with shocks and stresses.
  4. Improve the efficiency and effectiveness of humanitarian response architecture.

The HARBS programme is a critical vehicle for delivering on the Foreign Secretary’s Climate and Nature and Development priorities. Furthermore, the programme delivers on FCDO’s more specific humanitarian and resilience priorities, including increased investment in prevention, anticipatory action and increased resilience to predictable shocks. With a strong focus across objectives on state-led disaster response through innovated disaster risk finance and insurance, and a shift from international intervention to locally led provision of humanitarian and resilience-building initiatives.

Description of the HARBS Programme in FY 24-25
This was the first year that we saw the full implementation of both the humanitarian and resilience pillars of HARBS as envisaged. All resilience and multi-year humanitarian partnerships were out of their design and inception phases. Taking a steer from the FY 23-24 HARBS annual review, the intention at the outset of FY 24-25 was to focus on priority partnerships:

Humanitarian
Gaashaan Consortium: Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia, implemented by a consortium of partners led by Save the Children International (SCI).
Shock responsive social safety nets: implemented through our partnerships with WFP and World Bank.
Humanitarian Enablers: ongoing support for security analysis focused on NGOs through the International NGO Safety Office (INSO), and support for humanitarian coordination positions through our Standby Roster arrangements (SBP).
Resilience
BRCIS: Supporting the resilience and adaptation of rural communities, implemented by the Building Resilient Communities in Somalia (BRCiS III) consortium. Led by the Norwegian Refugee Council (NRC).
Danwadaag (DWD): Reducing Vulnerabilities of Displaced Communities through Durable Solutions Programming in Somalia, implemented by the ‘DANWADAAG’ consortium, led by International Organisation for Migration (IOM).
Restore: Restoring the riverine eco-systems for climate adaptation (RESTORE) programme, implemented by the Food and Agriculture Organisation (FAO).
However, externally Somalia experienced enduring impacts of El Nino flooding, increased conflict and insecurity, recurring disease outbreaks and in the final 6 months of the year below average rainfall and worsening dry conditions – all of which increased displacement and humanitarian need, over and beyond what we saw in FY23-24. Internally, the British Embassy Mogadishu (BEM) was managing cross-office underspends and additional global underspends, coupled with welcome additional support for our resilience partnerships through a short-term allocation from the central FCDO Resilience and Adaptation Fund (RAF). The HARBS programme was well positioned to absorb this funding in response to the worsening humanitarian situation. Therefore, the breadth and scale of HARBS partnerships expanded during 24-25, with large scale support for annualised appeal based humanitarian partners (ICRC, IOM, OCHA and the Somalia Humanitarian Pooled Fund (SHF)), alongside top ups to our existing prioritised partnerships and an activation of the HARBS’ internal risk facility (IRF) to support lifesaving health, nutrition, water and protection response work.

HARBS delivered almost £65m through 12 country level bilateral agreements and 2 centrally managed programmes (CMPs). We continued to protect and prioritise resilience investments with 38% of HARBS funding going to the resilience pillar, 14% to building and delivering through the social protection system with shock-responsive humanitarian cash, 2% on the HARBS MEL partnership and the remainder on humanitarian response work. As a result, the total number of people reached with a combination of humanitarian and resilience interventions in FY 24-25 is 1,461,083
Humanitarian Assistance and Resilience Building in Somalia (HARBS) Programme (April 2024 – March 2025)
Humanitarian Assistance
IRF (Emergency response fund) – CAAFIMAD+
Multi-Year Humanitarian Partnerships
-Gaashaan Consortium
-Shock responsive social Protection (WFP + WB)
- Humanitarian Enablers (INSO + SBP)
Annual Appeal Humanitarian Partnerships
-ICRC
- OCHA/Somalia Humanitarian Pooled Fund
- IOM Emergency Assistance
Resilience
Rural Livelihoods – Building Resilient Communities in Somalia (BRCiS) – NRC and consortium
Urban Durable Solutions – Danwaadag IOM and consortium
Natural Water Resource Management – FAO
.

Summary supporting narrative for the overall score in this review
This HARBS annual review has scored as an A+ meaning outputs moderately exceeded expectation. This year the HARBS programme is being assessed against a new comprehensive multi-year results framework. There was no change to impact and outcomes, nor any material change to the programme. However, following the establishment of all multi-year humanitarian and resilience partnerships, and the completion of their respective inception periods BEM has been able to work with the HARBS MEL partner, to develop the comprehensive output level results framework and set out how we will measure achievements under intended outcomes and impact. Improving the overall accountability and quality of the programme.

As set out in the table below, 4 out of the 7 outputs scored an A+, including 3 of those with the highest weighting: resilience strengthened by access to and delivery of basic services improved (20%); improved livelihoods, food security and ecosystems (20%); and humanitarian support delivered (25%). The HARBS programme has been assessed as on track to contribute to intended outcomes and impact in accordance with the current context in Somalia and likely trajectory.

Output	Score	Weighting
Output 1: Strengthened community capacity for crisis response	A+	10%
Output 2: Number of people supported to adapt to effects of climate change	A	10%
Output 3: Improved access to and delivery of humanitarian Basic Services	A	20%
Output 4: Improved livelihoods, food security and ecosystems	A+	20%
Output 5: Provision of emergency assistance to vulnerable individuals	A+	25%
Output 6: Improved use of evidence in humanitarian assistance and resilience building	A	5%
Output 7: Strengthened Government Capacity for crisis response	A+	10%

Contextual relevance of the HARBS programme:
The humanitarian context deteriorated during the reporting period. Conflict and insecurity increased, becoming the primary driver of displacement in Somalia. Over the course of the 2024, the country pivoted from severe flooding to failed Deyr rains. The constant cycle of unpredictable rainy seasons, alongside a consistent flooding threat (due to Somalia’s vulnerability to highlands rainfall in Ethiopia and ecosystem degradation) sustained high levels of food insecurity, malnutrition and weak livelihoods.

In early 2025, the removal of USAID as a bilateral donor and near complete removal of USAID funding in Somalia has had devastating humanitarian and resilience consequences which continue to unfold. Over 189 health facilities have closed; broader basic services have contracted with schools closing and the WASH sector has collapsed. Critical humanitarian coordination, assessment and information management systems are also impacted, making it very hard to monitor the true scale of the impact.

Finally, ongoing political fragmentation across the Federal Government of Somalia and Federal Member States is fuelling inter-clan violence and partly enabling an Al-Shabaab resurgence which was already impacting Middle and Lower Shabelle in the final months of this reporting period. This is a trend that is likely to continue as Somalia enters an election cycle with subnational and Federal elections expected over the next 12 months.

Partner programme performance:
Against this context the HARBS programme, partners and instruments have demonstrated agility, relevance and impact. The IRF has supported one of the most effective humanitarian response consortiums (Caafimaad+) to deliver humanitarian assistance to almost 1 million Somalis. Resilience partners draw on strong community partnerships to sustain access and continue to build resilient systems – community, ecosystem, livelihoods, government planning and response – as well as activate crisis modifiers to address urgent needs in targeted areas. As much as possible, HARBS supports early warning, anticipatory and early action – whether through the government social safety net programme, BRCIS crisis modifier, or through flood mitigation infrastructure that has benefitted over 200,000 people. HARBS has sought to prevent and mitigate and not just respond to crisis.

The resilience partnerships under HARBS rely on a range of approaches to protect access and delivery capability in the face of the inevitable climatic, conflict and political shocks that are to some extent predictable in Somalia and will continue through 2025 and 2026. Community engagement and partnership is crucial to designing and delivering programmes under HARBS, but particularly under the resilience pillar. Sustainable and conflict sensitive management of natural resources are also a crucial common objective and approach, communities are motivated by these resources, their effective management is intrinsically linked to conflict management and mitigating the constant cycle of too much or too little water.

The HARBS portfolio and partners also adopted a nuanced approach to both local and government partnerships for resilience building and crisis response. Local partnerships are not equated with Somali NGOs only – community structures, self-help groups, community health workers – are all integral to the delivery of both humanitarian and resilience work. Some government systems, institutions and personnel are both present, effective, and sustained regardless of the outcomes of political cycles and elite bargains. With that in mind, the HARBS programme and partners have trained local government frontline workers in both urban and rural settings to deliver services and in doing so build more sustainable capabilities in government institutions and staff. In urban settings in particular, HARBS partners support government planning and coordination services, including early warning and response mechanisms. Linked to that, but at a national level the HARBS programme has seen significant progress in policy and institutions to deliver shock responsive capabilities of the national social safety net programme. Hundreds of thousands of Somalis have benefitted from anticipatory action and early response to climatic risks and shocks as a result of this effort.

HARBS partners have delivered as per their programme and financial plans with successful utilisation of the highest annual budget for the programme and delivering an A+ score against the broader results framework. However, it is important to note the specific challenges under the RESTORE programme. The termination of the USAID Transform project – the US contribution to the broader Jowhar Off stream Infrastructure Rehabilitation Programme (JOSP) – followed by Al Shabaab’s continued territorial advances in Middle Shabelle pose an existential threat to the intended outcomes of this project. The FAO led, predominantly UN consortium, is struggling to redefine itself to a set of new achievable shorter-term objectives that still simultaneously chart a course towards more transformative ecosystem restoration, climate change adaption, disaster management, food security and agriculture production objectives.

BEM and FCDO Performance:
Partner risk and challenges sections set out the consequences of annualised and regularly fluctuating UK ODA allocations. This is particularly true for our multi-year resilience work. This was further complicated by the unique CDEL challenges the UK passed on to HARBS partners in the reporting period. High pressure expenditure monitoring, particularly of more complex infrastructure work, did not enable adaptive and responsive programming. However, BEM did all it could to ensure protected budgets for more complex resilience work. As well as provide earlier commitment to those same partners, carrying risk with more flexible and low risk annual appeal partnerships. Donor collaboration and co-financing is at the heart of all HARBS flagship multi-year humanitarian partnerships and resilience work:

- Caafimaad+: HARBS is co-financing the consortium together with ECHO. Together, we are working with the consortium to deliver on the humanitarian system reset through this programme. This includes co-financing the humanitarian access initiative which brings in technical support from Institute of Development Studies (IDS) to support community engagement methodologies for improved accountability, partnerships and access. We are working with Caafimaad+ to support health and nutrition facility digitalisation efforts, to enable improved referral capabilities (crucial during largescale crises). We are also working together to improve mortality surveillance and analysis, which remains a gap in the Somali context.
- Danwadaag and BRCIS: both consortiums have become multi-donor consortiums drawing on funding from the likes of World Bank, EU, SIDA and Danida. Often both sharing best practice that is then integrated into wider programmes (BRCIS adopting the Danwadaag Derisnimo approach and Danwadaag adopting BRCIS EWEA systems). Both consortiums now have Donor Steering committees that formalise donor collaboration on durable solutions and resilience policy work as well as programming efforts.
- State led disaster response, including shock responsive social safety nets: HARBS is working closely with the World Bank to jointly manage partnerships with WFP and the Somali government. This is a large and complex policy and programme area, BEM and the World Bank need to work together to pool political influence and development resources to move the policies, systems and programmes in the right direction and at the same time, building on the momentum, attention is now turning to how we can better incorporate the opportunities that come with the disaster risk finance instruments that Somalia have access to.
- RESTORE/JOSP: USAID’s withdrawal from the JOSP consortium was a setback. However, the UK continues to work with the UN Somalia Joint Fund, who still invest in the wider JOSP programme. Increasingly, we are collaborating with the EU who are interested in investing future resilience resources (from 2026).
- Gulf partnerships: BEM continues to work together with HARBS partners to establish and then expand on co-financing and policy partnerships with gulf partners. There is a prospect of a third partnership between UK-BRCIS-QFFD, with $6m of support – and for the first time it will be multi-year. Following a second partnership between the UK-KSrelief-UN, focussed on WFP and UNICEF, BEM is pursuing a more technical MEL partnership before seeking additional funding. A new Kuwait has also been achieved in the next FY with $2million co-financing for Somalia.
We continue to try and respond to the IAID recommendations to support partners with horizon scanning, particularly where we may have added value on political trajectory, security scenarios, or specialised knowledge including through UK government partners such as the Met Office.

As BEM seeks to adopt the portfolio programme approach, HARBS is already leading the way in demonstrating how to deploy a suite of flexible partnerships and instruments to ensure that a programme can respond and adapt to a highly dynamic context. Crucially, HARBS demonstrates this ability but not just through its shorter-term emergency response initiatives, but under the resilience pillar as well which is the UK’s main vehicle for delivering bilateral International Climate Finance in Somalia (a top Foreign Secretary priority). Adaptability and the portfolio approach can still be used in pursuit of complex multi-year development objectives.

Lastly, the Humanitarian, Health, Education and Resilience team (HHEART) responsible for delivering the HARBS programme continue to deliver a mutually reinforcing policy and influencing agenda alongside the programme. These influencing efforts are already well aligned to FCDO’s new humanitarian policy priorities and the larger global humanitarian reset agenda. BEM’s humanitarian and resilience work ensures system level change, that affects how other donor funds and programmes work. There are four critical policy workstreams:

1. Humanitarian reform – HHEART consistently represents BEM at the Humanitarian Country Team and Humanitarian Donor Group level, to promote a more localised, prioritised and thus cost-effective humanitarian system. Community engagement partnership and accountability is also central to this. Our influencing efforts are aligned with the global reset agenda and BEM is co-leading a new dedicated coordination group focussed precisely on what the reset means for the Somalia humanitarian system. Its partly due to UK drive and leadership that Somalia is likely to be selected as a pilot country to demonstrate globally, what the ERC, IASC and donors want from the humanitarian reset. This wider reset work, is building on two key working groups focused on aid diversion (which was co-chaired by BEM) and the other, on UN and AU transition (which BEM was a member of).
2. Durable Solutions for IDPs– BEM co leads both donor working groups for Durable Solutions, with the Danwadaag programme supporting programme coordination policy development related to the Federal Government’s target to provide solutions to over 1 million displaced people.
3. State led disaster response and international pre-agreed finance – BEM co leads the donor working group on Social Protection, with a focus on shock-response. Linked to this BEM is working closely with the World Bank as the key international partner to ensure that the Somali state does more to respond to recurrent shocks and humanitarian need through its sovereign access to disaster risk finance and insurance. Specifically, this is about connecting the disaster response systems in Somalia to financing initiatives such as Global Shield, ARC and Start Replica are all active in Somalia.
4. Climate Resilience and Adaptation – HARBS is the UK’s main vehicle for bilateral ICF programming in Somalia. BEM and HARBS programme innovation is helping to define what community led, nature-based approaches to climate adaptation and resilience can look like in fragile and conflict settings such as Somalia. This complements our higher-level climate and climate finance policy work, generating proven and impactful ‘supply’ ideas to ensure that climate financing to fragile and conflict-affected contexts such as Somalia is successful.
Managing reductions and Prioritisation
As BEM adjusts to FCDO’s new development approach and significant ODA reductions, the HARBS programme will need to change and contract. ODA budgets for the UK Spending Review period had not yet been confirmed, but bilateral Posts have been commissioned to mode 30-70% cuts in budget. The HHEART team already have a strategy for streamlining the HARBS programme that will reinforce those elements that align with BEM’s vision for portfolio programmes, and the FCDO’s new paradigm for development (i.e. a shift from direct service delivery to supporting self-delivery; from grant giving to exchanging expertise; from international intervention to local provision; and from significant contributor to international organizations to engaged reformer). In particular, HARBS will preserve the instruments that support BEM’s capability to pivot to new and unforeseen humanitarian need; enable adaptive programming to give multi-year resilience partners the ability to adjust to contextual realities; and finally, allow BEM to absorb additional funding when required to address rapidly escalating needs. Across all of this, we will continue to cultivate partnerships.
Going forward, the humanitarian pillar within HARBS will have fewer partners. HARBS will focus on the most agile partnerships that will be best placed to deliver priority interventions - namely multipurpose cash, health, nutrition, WASH, protection – in priority high humanitarian need locations, including areas under non-state armed group control. These partnerships will more closely align with emerging priorities under the humanitarian reset, particularly increased support for locally led and more inclusive humanitarian response.

As per the latest strategic direction from FCDO “within humanitarian and other fragile contexts, we want to apply our learning on prevention, anticipatory action, resilience and financial innovation.” Evidence and learning from BEM humanitarian investment in Somalia over the past decade has highlighted the importance of adopting a multi-year resilience focused approach to addressing humanitarian needs and the underlying drivers of those needs. Therefore, we will continue to invest in resilience with a particular focus on climate adaptation and ecosystem restoration – which implicitly will support prevention of and anticipatory action to climate shocks, including famine. However, we will be unable to sustain the current number of resilience partnerships, which will also have to reduce.

Finally, the lessons and recommendations set out below will be central to HARBS partnerships and how we pursue our intended humanitarian and resilience outcomes. Crucially, the learnings and recommendations from the value for money section, will be more important than ever.

Major lessons and recommendations for the year ahead
HARBS MEL partner HHELMS facilitated an annual learning event with all HARBS partners in May 2025, reflecting on the reporting period covered by this Annual Review and looking ahead into FY 25-26. The points below represent the consolidated lessons and recommendations from that workshop, and the annual reviews from partners:

Local partnerships are essential to humanitarian and resilience work in Somalia:
This has been a recurrent theme in HARBS annual reviews and is well cited in research and evaluations of humanitarian and development work in Somalia. However, the learning and delivery experience from FY24-25 continues to reinforce this. BEM have commissioned a learning review focussed on community engagement and partnership, which will consolidate learning and best practice from HARBS partners that should then be embedded in the new streamlined programme portfolio. This will focus on three key issues within this broader theme:

  1. Community engagement – access, priorities and capabilities
It feels redundant to state that we should engage with and understand Somali communities. However, it’s still not built into all projects. This has to be every project’s starting point, it needs to be unstructured and not be based only on partners’ interests and capabilities/sectors, but on first understanding community capabilities, load bearing capacity, and what their priorities and interest are from the partner and project. This engagement should also be used to ensure predictable access and design delivery modalities (more below).

  1. Local and sustainable partnerships – working through local actors and systems
Wherever possible, safe and responsible to do so HARBS should be working with and through local partners and systems. Local partners should not be limited to Somali NGOs, it can mean community structures, local authorities and frontline workers, and private sector. Systems should be understood based on the community engagement and could point to functioning systems of humanitarian assistance and essential services, that could range from clan to government and projects HARBS should be open to working through such structures where feasible.

  1. Community accountability
Moving forward the HARBS programme needs to assess whether it is effectively delivering on all the points above. Are we engaging communities? Do HARBS and community priorities and intended outcomes, match? Are we doing enough to work with and through local partners? HARBS MEL framework needs to do more to answer those questions.

Institutionalisation through Government – not politically impossible
Government is a complex and layered term in Somalia, and the HARBS programme should remain agile and capable of identifying which government institutions, systems and personnel are effective and can be invested in. Such investments can improve longer term government capacities for disaster response and sustainably address community needs and resilience.

HARB’s programme partners are currently working across very different levels of Federal, Member States and City level authorities. This work is expanded on in detail under output 6. The range of partnerships demonstrates that different approaches are required, depending on the sector, personnel, systems and issue that we are trying to influence. All partners are working with relevant Federal Ministries, as this is necessary for core ‘license to operate’. We have more advanced and dedicated investment in federal authorities and systems through the World Bank and WFP shock responsive social safety net work. BEM capacity building and policy investments that target SODMA and MOLSA, are translating into system level resilience. The success is partly down to functionality and independence of the social safety net programme and universal social registry which deliver tangible benefits from Somali’s across the country.

It’s a much more complicated partnership with the Ministries of Agriculture and Water, under the RESTORE/JOSP programme. Our investment and partnership efforts are focussed on the governance of water across districts and member states – a high value natural resource, thus a very politicised issue. Our government partnership work has to be complemented by local community level partnerships, that guarantee community and district authority led systems and capabilities to manage water and associated infrastructure in the absence of national level systems and policies. These aren’t mutually exclusive, nor do they undermine each other, we just need to work at different levels as the federal level investments take more time.

Building on our ways of working and learning under RESTORE, our Danwadaag partnership demonstrates the distinct way of working when it comes to cities and towns. Mayors and municipalities have smaller, more discreet mandates. Plus, their proximity to their constituency means that they are held to account more effectively. As a consequence, Danwadaag’s investment in legislation, policy and systems has resulted in much more concrete impacts for IDP security of land tenure, or access to basic services. This has then been complemented by simultaneous work with communities and local institutions that work in partnership with municipal authorities on planning, service delivery and protection of the most vulnerable.

There are further examples under output 6, but the broader learning demonstrates the need for bespoke strategies for different objectives, sectors and geographies that draw on a blend of formal government partnerships and bottom up community abd local partnerships and approaches to achieve system level change and resilience.

Lastly, the HARBS programme should always manage risks with such partnerships and consider thresholds for disengaging from such partnerships. This will mean working at different levels of government, acknowledging that the Office of the Prime Minister is very different to district level community health workers and agriculture extension workers, and that not all systems are equally ‘captured’.

Managing short-term life-threatening crises, but avoiding short-termism
The cost efficiencies and logic of tackling drivers of humanitarian crisis, and improving capabilities and resilience are well understood. The contextual challenges in Somalia and other fragile and conflict-affected contexts, and the overwhelming frequency and scale of humanitarian crises make it difficult to deliver on what is well understood. HARBS as an instrument, and through its partnerships, is already demonstrating its capacity to respond to communities demands for longer term resilient solutions, rather than resource-transfer based short term humanitarian assistance. Whilst preserving flexibility to respond to very real and immediate life-threatening situations – flooding, disease outbreak, drought/famine risks, and forced displacement. This needs to be protected in the new HARBS programme, avoiding either over-focussing on a prioritised ‘lifesaving only’ approach to managing declining resources, or equally a ‘let’s just tackle root causes’ approach – both will fail when they come into contact with the Somali context and community demands.

Area-based approaches – coordinating and delivering integrated assistance
HARBS resilience partners have demonstrated that area-based approaches to targeting, design and delivery can have more transformative impacts. Danwadaag use the Derisnimo approach within cities and towns, BRCIS have used natural resource and ecosystems to delineate and target interventions and RESTORE is focussed on large-scale reservoir infrastructure within a watershed as the determining factor in defining an area. All these approaches avoid using administrative boundaries and instead are driven by how Somali’s structure life, services and decisions. These approaches also better reflect community relations (including conflict dynamics), resource sharing and other common assets. Understanding and addressing these contextual factors are critical to ensuring the success of development programmes in fragile and conflict affected contexts such as Somalia.

Area based approaches enable improved coordination across partners and programmes, in pursuit of common goals acknowledging that our efforts are often mutually dependent. In a period defined by declining global ODA resources, area based programming also provide a platform for multiple-donors to invest in a range of priorities, but in a mutually reinforcing way achieving maximum benefits for a specific geography/area.

Similarly, on the humanitarian side OCHA-led local sub-national coordination structures have been established in response to the failure of more traditional cluster-based coordination mechanisms. They are still in their infancy but are demonstrating some of the opportunities for improved understanding of local community humanitarian needs and bespoke response, even in harder to access locations. Ensuring a connectivity and a division of labour with more development focus area-based coordination structures and programming would take this to the next level (being realistic in what is possible in an ODA constrained context).

UK should continue to be a convenor and mobilise non-traditional partners
As set out above, HARBS programmes with BEM support are coordinating with and leveraging additional finance from a range of traditional and non-traditional donors. This is a critical value add of UK diplomatic support alongside technical programming. This has to be a central feature of ongoing HARBS work.

Beyond GEDSI mainstreaming in design and policy, start measuring impact and success
The equity sub-section of value for money (section D) highlights the findings of the HARBS MEL partner GEDSI review. HARBS and its partners have acted on the recommendations from the two previous annual reviews to ensure that GEDSI integration is essential to success and impact in Somalia. However, it’s still difficult to measure whether policies and approaches are translating to success. Moving forward HARBS will need to do more to embed this analysis in its M&E frameworks.

Reflecting all of the above in a new reduced and prioritised Humanitarian, Climate and Resilience Portfolio Programme
As FCDO transitions to a reduced ODA budget, BEM will adopt a new portfolio programme approach. HARBS will need to be amended to align with the portfolio approach, and a reduced level of financing over the final 3 years of the programme. All the lessons and recommendations above will be reflected in the new portfolio programme with a particular focus on fewer partnerships that focus down on more transformative areas-based approaches. Reduced ODA levels and service delivery capabilities will require increased investment in government and local level partnerships to ensure sustainability.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The theory of change (ToC) for HARBS states that IF communities have reduced vulnerabilities and increased coping capacity through multi-year livelihoods and climate resilience, and durable solutions, programming, AND humanitarian crises are addressed in an effective and timely manner through flexible risk financing, AND this package of support is effective, evidence-based, and innovative while influencing positive change in the wider humanitarian sector, THEN severe humanitarian outcomes in Somalia will be reduced.

As set out in Section A, this year the HARBS programme is being assessed against a new comprehensive multi-year results framework. There was no change to impact and outcomes, nor any material change to programme. However, following the establishment of all multi-year humanitarian and resilience partnerships, and the completion of their respective inception periods BEM has been able to work with the HARBS MEL partner, to develop the comprehensive output level results framework and set out how we will measure achievements under intended outcomes and impact. Improving the overall accountability and quality of the programme. The updated outputs and associated indicators are set out in section C.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The HARBS programme is on track to deliver on its intended outcomes. As assessed in last year’s HARBS annual review, we are even likely to exceed our intended outcomes in relation to humanitarian response and social protection systems specifically. FY 25/26 represents the mid-year for many of our multi-year resilience partnerships, and we will be able to provide a comprehensive update on our outcome indicators in the next annual review as many partners carryout their mid-line assessments. However, we still have significant evidence of contribution to our outcomes.

To demonstrate, our core humaniatrian response partnership with Caafimaad achieved all its outcomes in its targeted locations, including keeping the proportion of deaths from all causes during the response period under 1%. Similarly, case fatality rates for malaria, pneumonia and diarrhoea among children aged under 5 also remained under 5%. The WFP and WB partnerships made significant measurable progress toward strengthening the country’s shock-responsive social protection systems, beyond just delivering timely cash assistance through a predictable system (which it has also done for 110,000 Somalis). The programme has laid foundational elements for long-term sustainability through structured institutional support. Capacity-building initiatives—including federal and state-level agreements, policy development, and the deployment of technical assistance—are actively enhancing the ability of Somali institutions to manage shock-responsive safety nets. These systems are vital for Somalia to access global climate financing instruments such as the Global Shield Against Climate Risk. Furthermore, the program’s approach aligns with the principles of the humanitarian-development-peace (HDP) nexus, contributing not only to immediate relief but also to long-term governance and resilience outcomes. The evolving coordination between MoLSA and SODMA is an encouraging sign of emerging government leadership, although continued support is necessary to strengthen sub-national implementation capacity.

The HARBS resilience portfolio has pushed on since last year’s inception year and even though all partners had to reduce their year 3 budgets versus plans, they have exceeded intended outputs and demonstrated actual and likely progress towards intended outcomes.

To demonstrate, BRCIS has initiated annual progress monitoring surveys which are primarily qualitative in nature. Key highlights of BRCiS’ outcome progress from this survey include:
- Women’s empowerment gains: Over 85% of SHG female members reported increased psychosocial and economic empowerment since joining the groups.
- High adoption of sustainable practices: 86% of food producers reported using at least one sustainable farming or livestock practice, surpassing the Year 2 target of 50%.
More inclusive leadership: Community members described greater trust in local leadership structures and noted clearer roles and stronger engagement from women and minority representatives. The progress monitoring survey also yielded several practical recommendations about changes to indicators and reflections on the TOC that will be used in the upcoming re-design workshop, including:

Similarly, the Danwadaag II programme is on track to contribute to the expected outcomes and impact. Strengthening government capacity has been a key focus, with coordination structures like the DSTWG, led by state and local leadership, and supported by national government representatives such as Ministry of Planning, Investment, and Economic Development (MoPIED) and Jubaland Commission for Refugees and IDPs (JUCRI). Targeted technical, material, and financial support has been provided following a comprehensive assessment of existing capacity gaps. The Derisnimo neighbourhood coordination approach has shown promising progress, demonstrating its value in informing contextualized targeting and potential for further scalability. The project also generated several evidence-based products and approaches to enhance influence on durable solutions programming and decision-making at national and regional levels. These products have guided local and national shifts, with validation and endorsement from officials, setting the stage for targeted programming, data analysis, and impact assessments. In addition, the programme strategically leveraged investments across the EU-Xaldoon and USAID projects, complementing them with FCDO-HARBS funds for cross-cutting initiatives such as CAPs, government capacity building, urban plans, and DSP assessments. This approach ensured the optimal utilization of resources, effective layering and sequencing of activities, and enhanced the sustainability and impact of interventions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the achievements and progress this FY and over the duration of the HARBS programme, the programme should continue. However, the upcoming announcements and clarification of BEM’s ODA budget for the next three years, alongside the finalisation of BEM’s new country business plan, will necessitate a revision to the HARBS programme and partnerships. The provisional strategy for managing this change is set out in Section A and will ensure that the programmes intended impact and outcomes match the resourcing that is available, as well as aligns with the BEM country strategy.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Strengthened Community Capacity for Crisis response
Output number:		1	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Partner	Planned	Achieved	Score
# individuals better able to prevent GBV and protect women, girls and boys from serious violations in their communities	Caafimaad + / Gaashaan	1520M +3440F= 4960	2650M+3489F=6139	A++
# of compiled area-level action plans developed and shared to align with state development frameworks	BRCIS	37	37	A
% of Community Resilience Committees (CRCs) with women in leadership positions	BRCIS	70%	100%	A+
Number of Consolidated Community Action Plans (CAPs) prepared/implemented for district level management of flood and drought risk in Jowhar and Balcad district.	RESTORE	15	15	A
Total value (in GBP) of anticipatory actions financed directly through community structures, disaggregated by source of contribution (BRCiS small grants fund or community contribution)	BRCIS	0	0	NA – nothing planned till 25-26

Briefly describe the output’s activities and provide supporting narrative for the score.

This output areas brings together the achievements of HARBS multi-year humanitarian and resilience partners (Caafimaad +, Gaashan, BRICS and RESTORE) in relation to strengthening community capacity to respond and be more resilient to crisis. Overall, this output area has scored an A (meaning outputs met expectations).

BRICS: Community led anticipatory action under BRCIS (indicator 5), was not planned to begin until FY 25/26. BRCIS finalized consolidation of 55 community action plans (CAPs) that were not completed in the first year for community climate resilient action and disaster preparedness and aggregated all 172 CAPs into 37 area-level action plans (AAPs), ensuring that community priorities remained locally driven and context specific. These bottom-up and locally led planning tools owned by communities reflected enhanced participation of different community groups including marginalized groups and aligned with gender equity objectives. To strengthen community and institutional ownership of AAPs, BRCIS facilitated state-level validation workshops with active participation from Community resilience committees (CRCs), local government representatives from regional and district authorities, relevant state level line ministries, and project implementing partners (members and downstream partners). The validation workshop was led by the state level Ministry of Planning, Investment, and Economic Development (MoPIED), these workshops ensured alignment of CAPs and AAPs priority activities with broader state development frameworks in the targeted communities and districts.

100% of CRCs’ leadership include women, since the CRC’s formation in FY 23/24. Output 1’s focus shifted to engagement on matters of Gender Equality and Social Inclusion (GESI) and general improvement of community leadership capacity. BRCiS CRCs, which had been previously established in YR1, actively participated in 60 GESI trainings. These sessions reached a total of 1,774 CRC Members, (1114 Male, 660 Female), thereby reinforcing women’s leadership and inclusion in community decision-making processes.

Gaashaan established community structures in the first year of the programme, year 2 has focused on strong community engagement, knowledge, behaviour change and empowerment with the objective of Social Behaviour Change against harmful gender-based abuses. Consortium partners, in close collaboration with local community-based structures, (GBV/CP response and Prevention committees) organised a series of impactful awareness campaigns and community dialogue sessions in the project locations aimed at sensitising community members on fostering positive attitudes toward survivors of Gender-Based Violence (GBV), Unaccompanied and Separated Children (UASC), and Children Associated with Armed Forces and Groups (CAAFG). These community engagement sessions focused on educating communities about the risks of child abuse and GBV and their effects on children, while empowering participants with knowledge on how to recognise and report such cases.

Furthermore, a total of 3,489 (946M, 1,643W,254B and 646G) individuals were reached by Gaashaan partners through community awareness sessions focused on their rights, entitlements, Prevention of Sexual Exploitation and Abuse (PSEA), and Feedback and Response Mechanisms (FRM). These sessions aimed to equip community members with essential knowledge on available support channels and mechanisms for reporting concerns. These sessions were designed to be inclusive, with a focus on both adults and children, but the project took care to ensure that the content was tailored appropriately to each group’s specific needs. For adults, sessions focused on rights, entitlements, PSEA, and the Community Feedback and Response Mechanism (CFRM) channels, while sessions for children (where applicable) were centred around basic safety awareness and age-appropriate methods for reporting concerns. Information about the CFRM) channels was actively disseminated, including hotlines and through Information Education and Communication (IEC) materials, ensuring participants understood how to access services and report issues related to exploitation, abuse, and other grievances.

Under the RESTORE programme, the communities and villages along the Shabelle River, particularly around the reservoir of the project area, are highly subject to flooding, causing displacement and affecting large areas of farmland. The climate challenges are exacerbated by the absence of policies on land-use and disaster risk management at the national level. At local levels, communities lack the financial, technical and informational resources needed to build their resilience to climate change as well as the knowledge of how to prepare for extreme weather impacts. To address this challenge and provide long term sustainability, the Consortium was tasked to roll out Community-Based Disaster Risk Management (CBDRM) approaches, early warning system and anticipatory actions in the target communities. The main tasks were to develop key approaches, structures, and mechanisms, as well as conducting disaster risk reduction (DRR) assessments and planning within the framework of CBDRM in Jowhar district with the eventual goal of realizing Community Action and Adaptation Plans (CAAPs).

At the community level, participatory rural appraisal assessment processes and appreciative enquiry protocols (through community meetings, focus group discussions, community critical informant discussions and joint transect walks) were conducted to engage with different socio-economic groups. Ultimately, 15 DRR community action plans (CAPs) were developed along with early warning systems as well as anticipatory action protocols.

Following a conflict analysis to evaluate community access in 15 villages, pilot Gender and Climate Vulnerability Assessments were conducted in all the RESTORE programme villages, followed by respective CAAPs, engaging 1,056 participants (604 male and 452 female) to establish their own community adaptation framework. IDPs are often more exposed to flooding, conflict and drought, worsened by continuous environmental degradation, canal breakages and tempering of river embarkments, and negative livelihood coping strategies that are a detriment to the environment. CAAPs focused on wider humanitarian needs, as drought-flood-conflict affected IDPs prioritized: green infrastructure to mitigate flood risk; resuscitation of water harvesting infrastructure to resume normal agricultural activities; the provision of health services and infrastructure support in flood-proof shelter designs; economic strengthening; livelihood diversification; and social safety nets.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

It’s increasingly clear that community engagement and partnerships, are critical to ensuring effective delivery of humanitarian and resilience objectives in the Somali context. Reduced levels of international ODA and increasing political uncertainty and insecurity, means that this output will be more critical in the coming 1-2 years, and we will be carrying out a learning review compiling best practices and lessons learned over the next 3 months.

Mobilizing and leveraging community Influencers around tackling GBV: Engaging trusted community figures—such as religious leaders, mentors, teachers, and GBV champions—has been instrumental in fostering local ownership of gender-based violence (GBV) and child protection (CP) interventions in humanitarian crisis. By enhancing their understanding of GBV/CP issues, these influencers have played a vital role in promoting the rights of women and children and shifting harmful community attitudes. A notable example includes mosque Imams in certain areas who have begun incorporating GBV awareness messages into their Friday (Jumu’ah) sermons. This represents a significant step in leveraging religious platforms to challenge harmful norms and advocate for social justice. The active participation and endorsement of these influential figures have strengthened community engagement and collaborative efforts in GBV prevention and response.

BRCIS’ progress monitoring survey highlighted (1) strong representation of women and minority groups in decision-making structures: Across all assessed community leadership bodies (CRCs, WMCs, EMGs, and EWEA institutions), the proportion of women (40%) and members of minority groups (52%) exceeded the Year 2 targets of 25%. However, representation of persons with disabilities remains low (6%), indicating uneven inclusivity progress across groups or potentially suggesting that participation in committees may not be the preferred pathway of engagement for these groups. (2) Widespread familiarity and active engagement with CAPs and AAPs among community leaders: Nearly all sampled decision-makers (95–100%) self-reported being familiar with their respective action plans and regularly monitoring their implementation. Qualitative data from FGDs largely supported this, showing that leaders can articulate priorities and track progress. (3) Community confidence in local leadership is improving. Focus group participants across districts noted greater responsiveness from CRCs and related structures, including regular feedback loops and clearer accountability mechanisms. While these perceptions varied somewhat by gender and location, they consistently reflected improved trust in local governance. This indicates progress toward community-led structures that are not only inclusive but also seen as effective and legitimate.

Output Title	Number of people supported to adapt to effects of climate change
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Partners	Planned	Achieved	Score
Number of people supported to better adapt to climate change (ICF KPI 1)	WFP Shock Response / RESTORE / BRCIS / Danwadaag	423,294	442,562	A

Briefly describe the output’s activities and provide supporting narrative for the score.

This output area maps on to the UK’s International Climate Finance (ICF) Key Performance Indicator 1 on climate change adaptation, specifically the number of people supported to better adapt to climate change. This output area brings together four resilience partners and overall has scored A+ (exceeding expectations).

The additional HARBS top-up from the central FCDO Resilience Adaptation Fund (100% ICF funding) which allocated £1.7m, not only enabled the partners to expand activities but also exchange with other contexts on learning.

WFP’s shock responsive safety net cash assistance – this is the first year that shock-responsive cash assistance has been eligible, as this was the first time it was delivered through an established system in accordance with a pre-agreed universal vulnerability targeting system, which accounts for climatic shocks. 110,532 individuals benefitted from this cash assistance.

RESTORE’s Flood mitigation infrastructure – 27 river embankment breakages were repaired (4,047 metres repaired, protecting over 44,503 hectares of farmland and approximately 34,861 homes in Beledweyne and Jowhar) thus protecting 209,166 individuals from flood risks.

BRCIS’ nature-based ecosystem restoration and climate resilient water supply and agriculture practices – as described in more detail under outputs 3 and 4, BRCIS has fully integrated climate adaptation and resilience into its approaches to improving water management at community level, ecosystem restoration work, and food security and livelihoods programming. 120,001 people have benefitted from BRCIS’ climate adaptation work.

Danwadaag made a contribution to ICF KPI this FY, supporting sustainable food production and climate adaptation and resilience for 2721 individuals catalysed by the RAF additional financing. Danwadaag plan to expand their adaptation and resilience efforts in FY25/26.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This year was the first year we reported on ICF KPI 1 following the dissemination of the newly developed HARBS ICF methodology note. This enacted previous recommendations to be more disciplined and ambitious, when measuring which activities constituted supporting adaptation to climate change. In particular, this has removed over reporting on humanitarian activities which are responding to climatic shocks but not supporting individuals to adapt.

More broadly, the resilience partners are expanding their climate adaptation and resilience work in line with BEM’s climate strategy, supporting the restoration of foundational ecosystems, adopting environmentally friendly and sustainable nature-based solutions to infrastructure work, and adopting livelihood strategies and practices that support climate adaptation and resilience.

Output Title	Improved access to and delivery of humanitarian Basic Services
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Partner	Planned	Achieved	Score
# of unaccompanied and separated children who have received alternative care support and family tracing and reunification services (disaggregated by age, sex and disability)	Gaashaan / Caafimaad +	Total - 779 100 (Gaashaan) / 679 (Caafimaad)	Total - 1034 / Gaashaan - 160 (91G, 69B) / Caafimaad - 874	A+
Number of people benefiting from improved access to more sustainable water supply and infrastructure	Danwadaag / BRCIS	14,800 (DWD) 41 structures (BRCIS)	Total- 124,306 / 8,856 (DWD) / 63 structures/115,450 (BRCIS)	B
# of people receiving emergency WASH Assistance and sanitation services (hygiene kits, latrines, water trucking)	BRCIS	214,246	230,545	A+
# of individuals in DAC communities supported to secure land tenure	Danwadaag	28,000	42,333 / (15,021M; 27,312F)	A++
# of individuals reached through incremental housing solutions (improved incremental shelters and shelter expansion through owner-driven approaches)	Danwadaag	2400	1200	B

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers services delivered by HARBS humanitarian and resilience partnerships to improve access to and delivery of humanitarian basic services in Protection, WASH, Housing Land and Property and Shelter. Overall, the output scores A (meeting expectations).

Child Protection Services in humanitarian contexts: The HARBS programme has provided a range of critical protection services this FY, through both the Gaashaan and Caafimaad + partnerships. GBV services are covered under Output 5. On specialised child protection services in humanitarian contexts, Gaashaan supported a total of 160 (91G, 69B) unaccompanied and separated children (UASC) between the ages of 1-15 years were through foster care families. These children were provided with different support based on their specific needs, including psychosocial support and essential materials such as food, clothing, and hygiene kits, in collaboration with local authorities and community protection committees to facilitate efficient and safe family tracing. Caafimaad + provided similar support in humanitarian contexts for an additional 679 children.

Sustainable water supply and infrastructure: In the second year of project implementation, BRCIS significantly advanced the establishment and capacity strengthening of community-based Water management committees (WMCs) and Natural Resource Management (NRM) structures across targeted intervention areas. As a result, 101 functional committees were successfully established and operationalized, comprising a total of 704 members (415 men and 289 women). These committees are playing a pivotal role in promoting sustainable resource use, ensuring inclusive participation in decision-making, and supporting locally led restoration and adaptation initiatives.
A total of 18,197 community members (9,507 Male and 8,690 Female) participated in awareness-raising sessions on ecosystem restoration and integrated water resource management, aimed at strengthening community knowledge on sustainable environmental practices. These sessions were designed to strengthen community understanding of sustainable environmental practices and build local ownership of restoration efforts. Additionally, 4,459 community members (2,646 Male and 1,813 Female) actively participated in restoration initiatives through a structured cash-for-work programme. The participants received training on the Resilience Design approach and were mobilized in priority activities such as riverbank stabilization, restoration of rangeland, irrigation canal rehabilitation, and recharge of water points which all align with resilience priorities outlined in the climate adaptation guidance from the workstream as well as the World Agroforestry (ICRAF) baseline recommendations.

The rehabilitation and construction of climate resilient water infrastructure was prioritised by BRCIS this FY, based on Community CAPs and AAPs, addressing both FCDO capital development (CDEL) expectations and community resilience priorities. The early implementation of water systems created a strategic foundation for layering ecosystem restoration efforts, enhancing the impact of integrated interventions. A total of 63 climate-resilient water points such as boreholes, berkads, shallow wells, and rainwater harvesting systems were rehabilitated or constructed across all BRCiS project locations, significantly improving water access for domestic, productive, and environmental uses. BRCiS communities face acute water insecurity, affecting both human consumption, livestock and food production due to increasing climate variability and prolonged droughts, During the reporting period BRCiS hugely invested in water intervention to build resilience and enable communities to absorb climate shocks, sustain livelihoods, and improve food and water security.

Moving away from building or restoring infrastructure, Danwadaag have used the public-private partnership model for the water supply system in Bardhere has been successfully established, benefiting 8,856 individuals (2,657 male, 6,199 female, 442 PLWD). This initiative has enhanced access to clean and safe water while promoting sustainable corporate-community relationships that align with the long-term development goals for DACs.

Land Tenure: Significant strides were made in supporting tenure security across all project locations during the year under review through the Danwadaag project, focusing on communities at risk of eviction who previously relied on informal, oral agreements. Working closely with government authorities, eviction task forces, landowners, and IDP leadership structures, NRC, Peace Hub Foundation (PHF) and Juba Foundation facilitated lease agreements that legally protected displaced communities and enhanced their access to services and long-term housing stability.

In BRA districts (Kahda, Dayniile, Garasbaaley), NRC secured five-year lease agreements for 26,883 individuals (8,961 male, 17,922 female) across 20[1] IDP settlements. PHF contributed by facilitating 30 land documentation and lease agreements for IDPs from Garasbaley resettled in Dayniile, and 4 additional agreements, totalling 1,541 households (9,246 individuals). In Baidoa[2], 3,114 individuals (1,038 male, 2,076 female) received communal tenure security agreements, with 100 households supported by cash assistance for documentation costs. In Xudur, NRC facilitated five-year lease agreements for 125 individuals (58 male, 67 female) across various IDP settlements. In Kismayo, NRC worked with local authorities and partners to secure five-year tenure agreements for 2,394 individuals (1,015 male,1,343 female). In Dollow's Kaxareey settlement, NRC protected 126 individuals (39 male, 87 female) from eviction through negotiations, securing extended notice and finalized lease agreements. In Baardheere, 481 individuals (213 male,268 female) received a 20-year written agreement to reside on Bulsho, government-owned land provided by the Bardhere municipality. A comprehensive land status investigation was conducted, resolving disputes and ensuring long-term stability for the community.
[1] Ciyow Kooyoow, Buulo Adan, Biyo Guur, Buulo Suldán, Waryaroy, Daris Uroone, Janaay, Banyaale, Ducale, Goobyaal, Cunadheer, Gumar, Fargaduudo, Wardi, Sucdi, Cirdeey, Durdur, Qoyslayaal, Rakaale, Talowanaag, Buulo Siidow, Sharaf, Iskaashi, Koris, Hayaan, Wabishabeele, Maslah, Daqare, Daxale, Rabituun, Xaqiiqasoomane, Dumaaye, Fatxul-iimaan, Qaacdheere, Bilan, Axmed Gurey, Dhagaxtuur, Soomane, and Rabituug
[2] Koobabo, Qasabileer, Buulo timbow, Dubugaas, Banbusul aliyow keerow Banbaare, Wadajir 4, Deg gomar, Bay, Abaq halul 2, BurBakar, Humbawaley and Macaney

Sustainable Shelter: During the year under review, 200 out of 580 targeted IDP participants were reached through an owner-driven construction model, delivering transitional hybrid shelters in Baidoa. Innovated pilot to test durable solutions. Each shelter included a family latrine and individual title deed, ensuring secure housing and land ownership. Beneficiaries received two days of pre-construction training on shelter typologies, Bill of Quantities (BoQs), and designs. Additionally, twelve solar streetlights were installed in key locations, improving safety and promoting sustainable energy use. The project prioritized Age, Gender, and Diversity Inclusion (AGDI), focusing on vulnerable groups such as women, children, the elderly, Persons with Disabilities (PWDs), and marginalized communities. Women were actively involved in decision-making, and a community-based selection process, supported by the Complaints Feedback Mechanism (CFM), ensuring accountability.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The HARBS programme continued to reinforce lessons learned in the FY 23/24 Annual Review and specifically on reinforcing the Gaashaan and Caafimaad+ consortiums in delivery of protection services. This year, both consortiums have provided a framework which can be adapted to mainstream protection in the wider humanitarian architecture and in the year ahead, BEM will ensure that lessons learned are integrated as part of the Humanitarian reset agenda.

In addition, use of community structures remained central to improving delivery of services. All partnerships under this output utilised community structures including in the delivery of specialised humanitarian interventions (Caafimaad + and Gaashaan) and sustainable WASH and Shelter infrastructure (BRCIS and Danwadaag). This year BEM will take forward the use of community structures and community engagement as the pinnacle in which to improve service delivery and accountability.
Output Title	Improved livelihoods, food security and ecosystems
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Partner	Planned	Achieved	Score
# of food producer groups trained on agroecological practices	BRCIS	Total - 1441 / 1,441 (30% female and 3% disabled people) 0 (not originally planned for this FY)	Total – 2,136 / 1,819 (938 Male and 881 Female) and a total of 113 disabled people (61 male and 52 female) are / Included. 317 / Bardhere:120 farmers (66 M; 54 F) / Baidoa: 98 farmers (46 M;52 F) / Xudur: 99 farmers (48 M; 51 F)	A++
# of people benefiting from kitchen gardens support package (seeds, linkages, training) through market-based approaches		0	0	(see justification below)
# of people newly engaged in saving groups supported by the project, disaggregated by gender	BRCIS	3,568 people (80% Female and 5% disabled people) engaging in 194 Saving Groups	4,624 individuals (634 Male and 3,990 Female), including a total of 84 people with disabilities (28 male and 56 female) engaging in 223 SHGs	A++
# Individuals access business development support (including members of cooperatives, producer groups and SMEs	BRCIS / Danwadaag	Total - 924 / 100 - BRCIS / 254 – DWD core / 570 – DWD RAF	Total - 971 / 90 (30 male and 60 female) - BRCIS / 311 – DWD Core / 570 – DWD RAF	A
Percentage change in crop yield at household level		0	0	B – Restore project activities delayed
# of hectares of degraded communal land covered by rehabilitation and conservation measures.	RESTORE	528ha	830.68 ha	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focused on core activities by the resilience partners BRCIS, Danwadaag and RESTORE and achievements across food security, livelihoods and ecosystems were additionally supported by the Resilience and Adaptation Fund (RAF). Overall, and due to RAF complementarity, outputs scored A+ (meaning outputs exceeded expectations).

Food security and Livelihoods: BRCIS did not deliver the kitchen garden activities this FY, focussing core project resources on more impactful and cost effective climate smart agro-practices and drawing on additional central resources from RAF, focused on permagardens instead. In the Galkacyo, Wajid, Hudur, Bardhere, Beelet-Hawo, Afgoye, Wanlawayne, and Jariban districts, BRCIS Members IRC, ACF and KAALO established agricultural cooperatives. These producer groups received tailored agro-ecology practices training. The cooperatives not only enhanced agricultural skills and production but also fostered local ownership, women’s empowerment, and improved governance, aligning with best practices. In total, BRCiS Members and downstream partners supported 41 new farmer cooperatives, encompassing 1,819 smallholder farmers (938 men and 881 women).

In Dhusamareb, NRC supported 150 households (68 Male, 82 Female) in establishing backyard permagardens. Participants included individuals with disabilities (1 man, 2 women) and 15 people from minority groups (5 men, 10 women). Households were trained in bed preparation, double digging, soil enrichment using local materials, mulching, and the use of greywater. In Galkacyo, KAALO engaged 50 participants (12 men, 38 women). These initiatives were aimed at enhancing food security, nutrition, and sustainable agriculture through resilience-focused designs.

Self Help Groups: During the reporting period, the Share Trust, in coordination with BRCiS Members and partners, led a preparatory webinar on 16 June, followed by a comprehensive three-day self-help group (SHG) workshop in early July 2024. These workshops addressed key distinctions between SHGs and other group models (e.g. NGO-established VSLAs and indigenous Ayuutos) and aligned with the guidance and methodologies outlined in the BRCiS SHG that aimed to foster consistent implementation of harmonized SHGs practices across consortia members. As a result, a total of 218 SHGs were established or reactivated across target locations, engaging 4,364 members (562 Male, 3,802 Female). The group members are saving with individual monthly contributions ranging from USD 1 to 5, and collective savings totals per group ranging from USD 200-600.

Success of the Self Help Groups has been due to mentoring and provision of technical back stopping and this community of practice is able to share the learnings and challenges on a group WhatsApp group for real-time support and on a monthly basis is able to review learnings and document any lessons, more so support in the cross learnings and exchange of hands field experiences and exposure for the benefit of the wider team.

Under Danwadaag, a total of 311 beneficiaries received business start-up kits, entrepreneurship training, and individual cash grants, promoting economic self-reliance, particularly among women, by providing essential resources to launch and sustain small businesses. Furthermore, using RAF, Danwadaag implemented a pilot project focused on strengthening livelihood diversification, food security, and climate resilience among marginalized and displaced communities across Baidoa, Bardhere, Berdale, and Xudur. Led by Danwadaag partners CWW, GREDO, and IOM, the pilot targeted a total of 570 individuals: 240 individuals from 12 women-led SHGs and 330 marginalized individuals outside of group structures. Assuming an average household size of six, the support provided is estimated to have benefited approximately 3,420 people.

Under the RAF pilot project, participants were grouped into similar livelihood categories to receive tailored training aligned with their specific adaptation strategies e.g. on climate change adaptation, business development and climate smart agriculture , and followed by cash or in-kind support. All participants also received support in developing business plans to help them identify their strengths, assess potential risks and challenges, and take appropriate actions to improve or diversify their income. As a result, each of the 12 SHG received between GBP 11,000 and GBP 13,000 in cash support, following the submission of business plans. To ensure transparency and accountability, financial support was paid into each SHG’s centrally managed pooled fund, which required having a bank account. SHGs supported under the pilot have already begun reinvesting profits from their initial businesses into new income-generating activities. For example, some groups have used earnings to purchase water tanks, enabling them to store and resell water to additional customers – demonstrating both entrepreneurial growth and potential for sustainable business expansion.

Among the 330 individual beneficiaries:110 female-headed households received GBP 300 cash transfers to invest in improved stock management, solar-powered cooling systems, and access to water; Another 110 farmers were supported through linkages with three local agro-dealers who supplied quality seeds, tools, and extension services free of charge, and to help offset financial pressure during the lean season, each farmer further received $30 (approx. £ 22) monthly cash transfers for three months. An additional 110 individuals received GBP 300 each to support activities like community tree nurseries, communal kitchen gardens, and fodder production.

Lastly, a total of 317 farmers from Baidoa and Bardhere received targeted training on climate-smart agriculture techniques, quality seed distribution, and a USD 30 monthly allowance to cover basic household needs.

Ecosystems: Throughout the second year, BRCIS Members and downstream Partners placed strategic emphasis on finalizing area action plans (AAPs) and co-designing ecosystem restoration initiatives in alignment with community-identified priorities. USAID’s Resilience Design (RD) guidance was used to support the context specific design of ecosystem restoration activities for implementation. This framework aims to harmonize the quality and effectiveness of interventions across all BRCIS sites. It serves as a key foundation for scaling up efforts in the next phase, ensuring consistency, sustainability, and community-led solutions in land restoration and resource management. A total of 18,197 community members (9,507 Male and 8,690 Female) participated in awareness-raising sessions on ecosystem restoration and integrated water resource management, aimed at strengthening community knowledge on sustainable environmental practices. Additionally, 4,459 community members (2,646 Male and 1,813 Female) actively participated in restoration initiatives through a structured cash-for-work programme. The participants received training on the Resilience Design approach and were mobilized in priority activities such as riverbank stabilization, restoration of rangeland, irrigation canal rehabilitation, and recharge of water points which all align with resilience priorities outlined in the climate adaptation guidance from the workstream as well as the ICRAF baseline recommendations.

BRCIS has been working with 33 communities on regenerative rangeland management, such as rotational grazing, ecosystem restoration, and the sustainable use of natural resources. BRCIS introduced practical methods for soil health, allowing vegetation recovery, and improving biodiversity. A key outcome was the development and adoption of community by-laws to govern natural resource usage. While initially one overarching by-law framework was conceived, the discussions led to each village creating its own tailored regulations. As a result of these discussions, each community agreed on several by-laws governing the use of their natural resources, including grazing land, pastures, and water resources the by-laws developed were formally translated, typed, and distributed to the communities. The project team will make quarterly follow up with the CRCs to document if they have been instances where they applied the by-laws and how this went, the CRCs will be tasked to these by-laws with known clan-elders and the local authorities to get their buy-in and support, hence ease their implementation. The extensive availability of degraded rangeland mapped by the ICRAF baseline report created a valuable opportunity to expand restoration efforts. This was effectively utilized through active community participation, with local communities contributing significant to labour, which enabled the rehabilitation of an additional 302.59 hectares beyond the original plan of 528 hectares.

Additionally, BRCiS Members focused on the construction and management of 13 fodder storage and production facilities across 7 districts: Hudur, Afgoye, Bardere, Jariban, Kismayo, Baidoa, and Beletweyne. These interventions aimed to reduce post-harvest fodder losses and ensure availability for lactating animals during dry seasons for drought-affected communities to enhance nutrition, food security and income generation for the affected communities. Could

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- Planned kitchen gardens and crop yield activities were not implemented by BRCIS and RESTORE respectively . This year both consortiums will analyse cause and effect and set out an implementation plan for these activities.
- The Resilience and Adaptation Fund (RAF) proved effective as a complementary fund to core resilience activities. This year FCDO will explore another bid and to support activities under this output.

Output Title	Provision of emergency assistance to vulnerable individuals
Output number:		5	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Partners	Planned	Achieved	Score
Number of people assisted by SHF attributable to UK funding	SHF	N/A – SHF does not set an annual target.	SHF – 102,120 people (8.5% of total people the fund reached in 2024, as per the UK contribution)	A
# of people in detention who received who benefitted from improved living conditions and access to water		4,182	4,889	A+
Total number of people directly assisted, through IRF/Crisis Modifier funding	Caafimaad + / BRCIS / RESTORE	N/A – BEM and partners don’t set targets for IRF and Crisis Modifiers. Its context dependent	Total – 964,446 / Caafimaad + = 941,616 / BRCIS = 10830 / Restore = 12,000	A
Total number of people who receive multi-purpose cash assistance (MPCA) across all partners	BRCIS / WFP	BRCIS – N/A (cash through crisis modifier, thus no target) / WFP SRSP – 105,696 (pre-agreed finance so does have a target) / WFP Emergency – 61,212	Total - 37,253 or 223,518 individuals (multiplying by 6) / 1805 HH/ 10,830 – BRCIS CM / 18422HH/110,532 - WFP SRSP cash / 61,212 - WFP relief cash (completed in September 2025)	A
Total number of people who receive cash-based food assistance		0	0
Total number of people who receive assistance through shock responsive social protection	WFP	WFP SRSP – 105,696 (pre-agreed finance so does have a target)	18422HH/110,532 - WFP SRSP cash	A (not to be double counted with above MPCA results)
Total number of people who receive GBV assistance across all partners	Gaashaan / Caafimaad+	94,802	128,852	A+
Total number of people who receive emergency health assistance across all partners	Caafimaad +	244,276	318,502	A++
Total number of activations of crisis modifiers and IRF	Caafimaad+ / RESTORE / BRCIS	N/A – BEM and partners don’t set targets for IRF and Crisis Modifiers. Its context dependent	4 total IRF – 2 x Caafimaad CM – 1 x RESTORE: 1 x BRCIS	A

Briefly describe the output’s activities and provide supporting narrative for the score.

This output captures the provision of HARBS emergency assistance through a number of contingency funding mechanisms built within the programme. This includes contributions through pooled funds, the HARBS Internal Risk Facility and specific projects Crisis Modifiers. This year the programmes activated all the contingency mechanisms given the shift from flooding to drought. Overall, the output scored A+ (meaning outputs exceeded expectations).

Multi-sector humanitarian response: The Somalia Humanitarian Fund (SHF) allocated US$33 million to 58 humanitarian partners to implement 83 multi-sector projects across the country. Throughout the year, whether in responding to drought, floods or mitigating the impact of displacement – the SHF remained steadfast in prioritising life-saving humanitarian assistance. With a focus on underserved and hard-to-reach areas, it played a critical role in ensuring flexible and timely funding to respond to immediate needs. Notably, the Fund piloted an Anticipatory Action allocation of $3 million to mitigate the impact of flooding on vulnerable communities in three remote districts. The SHF continued to aim for maximum efficiency by prioritising direct implementation, with 100 per cent of allocations channelled exclusively to nongovernmental organisations (NGOs). A distinct niche for the fund is its strong commitment to localisation. In 2024, the SHF reached a major milestone, with direct funding to local and national NGOs rising to 78 per cent, exceeding the 70 percent target. This accomplishment aligns with the Fund’s overarching objective of supporting partners best positioned to deliver timely, efficient and accountable interventions at local levels. The UK provided $4.4m (8.5%) to the fund in 2024 – and for the purposes of this review we have attributed 102,000 individuals to the results framework.
Humanitarian assistance to people in detention: International Committee of Red Cross (ICRC) provides a unique and critical role in the Somalia humanitarian response providing multi-sector support and protection. The HARBS log frame captures only one indicator that summarises their critical work in places of detention, something only ICRC can do. However, they have a huge response footprint across the entire country with a focus on the hardest to reach locations and conflict affected populations. More broadly, ICRC has assisted 327,230 people with supplementary food and cash assistance in response to conflict, drought and displacement induced needs. Working in partnership with the Somali Red Crescent Society, ICRC provides lifesaving medical assistance to wounded and sick Somali’s. People obtained basic curative and preventive health care at 24 Somali Red Crescent Society clinics that regularly received comprehensive support – supplies, financial assistance and staff training – from the ICRC. During outbreaks of violence and floods in the latter part of the year, five mobile clinics were assigned to the communities most affected. Over 74,700 women obtained antenatal/postnatal consultations at all the clinics mentioned above. Many of them gave birth with the help of ICRC-trained health staff. When necessary, they were referred to other health facilities for further care. More than 246,000 children were immunized against polio, measles and/or other diseases at the clinics mentioned above. ICRC’s 2024 budget was £65m, UK contributed £15m unearmarked (23%) to the appeal and were the largest bilateral donor.

 IRF and Crisis Modifier:
The HARBS IRF was activated two times this year following El Nino flooding experienced during the Seasonal rainfall in the last quarter of 2023 and a second time to respond to incidences of conflict and disease outbreaks. In both cases funding allocations were made to Caafimaad+. In addition, RESTORE and BRCIS both activated crisis modifiers in response to flooding.

IRF Activation: Caafimaad + Partnership : This FY the IRF was activated and used to deliver a £2.7m response through the Caafimaad plus consortium for multi-sector response (health, nutrition, WASH and protection. The activation was divided into two 6-month phases, the first of which was responding to ongoing needs from El Nino flooding (end of 2023/early 2024), which was exacerbated by worsening insecurity and localized conflict, as well as disease outbreaks. The second phase, continued to respond to ongoing conflict, displacement and disease outbreak related needs and the impacts of a below average Gu and Deyr rains in 2024.

A total of 941,616 (570,393 female & 371,303 male) unique beneficiaries received services from Caafimaad+ emergency interventions. The program reached 318,502 beneficiaries with outpatient consultations, child health, and reproductive health services. The outcome indicator tracked for the health sector was case fatality rates (CFR) for malaria, pneumonia, and diarrhoea which remained below 1% in all cases. 14,189 children under 5 years (U5) with severe acute malnutrition (SAM) were admitted at the OTP, while 1,991 children U5 with medically complicated SAM were admitted to stabilization centres. The cure rates for children U5 in the supported facilities during the reporting period stood at 97.4% for OTP, and 95.1% for stabilization centres at health facilities, above the targeted minimum of 95%. A total of 91,638 beneficiaries were reached with water and sanitation support services.

We continue to see demonstrated success in Caafimaad’s integration of specialized protection services. Of the people reached by frontline responders 4,221 women and girls have benefitted from specialized GBV and protection services; 7877 children benefitting from PSS at child friendly spaces (CFS); while 874 children at risk of separation were provided with case management services.

In addition, Caafimaad + continued to respond to disease outbreaks at the occur, responding to 189,540 people across Afgoye and Kismayo districts (cholera), and Wanlaweyn district (characterised by water shortage and poor quality).

Crisis Modifier Activation: Two of our partners activated their crisis modifiers for multi-sector humanitarian response:

BRCiS activated the crisis modifier in Q3 of this FY in order to respond to riverine flooding in Beledweyne along the Shabelle River, through Save the Children; and to provide anticipatory and early response to drought needs, as well as conflict related needs, in Mudug region through IRC and KAALO. These CM activities reached a total of 1,805 individuals and were informed by localized early warning indicators and risk assessments, aligning with the Early Warning Early Action (EWEA) framework. While CM funds for Year 2 remained limited at approximately £400,000, the Consortium prioritized anticipatory and responsive actions that addressed emerging shocks such as localized flooding, inter-clan tensions, and climate-related livelihood disruptions. The interventions included cash assistance, distribution of emergency supplies, support to livelihoods through livestock vaccination and fodder provision, and temporary water access solutions.

The RESTORE project also activated their crisis modifier when communities in the project areas in Jowhar and Balcad district were adversely affected by the disastrous El-Niño floods in the area. The CM action aimed to assist 5,400 households across 12 impacted villages by rehabilitating shallow wells and irrigation canals through a Cash-for-Work modality. However, 4,614 households (85% of the target) were ultimately reached, comprising 2,337 female participants and 2,277 male participants. The remaining target households failed to pass the biometric verification requirements and were thus dropped from the intervention. This intervention and the work contributed to the rehabilitation of 39 irrigation canals measuring a total of 80,840 m, with the potential to serve 50,000 ha of farmland with a supply of irrigation water. Moreover, 24 shallow wells were rehabilitated (desilting, cleaning, chlorination and deepening), restoring access to clean water for 12,000 individuals. To further improve rehabilitated asset management, the action trained 60 water management committee members (40 male; 20 female), who actively provided appropriate hygiene and sanitation behaviour change communication to prevent the risk of WASH-related diseases during the flooding in April-May 2024. The trained individuals reached out to 12,000 people in 12 villages and through the intervention, USD 388,536 was disbursed to beneficiaries through mobile money transfers. Each beneficiary received a USD 84 single cash payment.
Shock responsive social safety net assistance:
WFP is the main cash partner under the HARBS programme. This FY, WFP has made significant progress on both the policy architecture and broader shock responsive social safety net system, as well as in delivering multipurpose cash assistance through that architecture. With funding from FCDO, WFP successfully provided in Year 2 cash transfers to 18,422 households (110,532 individuals) in districts prioritized by the Somalia Disaster Management Agency (SoDMA) for shock response, in close coordination with Ministry of Labour and Social Affairs (MoLSA). Each household received a one-time transfer value of US$360 to cushion the effects of acute shocks. A comprehensive and targeted communication outreach, using radio broadcast and SMS to -ensure that the key recipients were well-informed about the intervention. All communication steps, including public messaging, were jointly approved by SODMA and MoLSA, ensuring alignment and transparency.

Furthermore, Year 2 implementation demonstrated that it is possible to activate a shock-response mechanism with an exceptionally tight timeline - just 6 weeks from design to disbursement. This rapid deployment was made possible by 3 key enablers:

1. A pre-existing, credible Unified Single Registry and beneficiary database under the national safety nets
2. High level political will and operational commitment from MoLSA and SODMA
3. WFP’s technical leadership and convening role, facilitating timely coordination and logistical execution

Muilti purpose Cash assistance:
Through UK support, WFP, BRCIS, Gashaan provided emergency cash assistance, and this was done through different modalities.

- WFP provided multi-purpose cash assistance (MPCA) for 61,212 individuals. This emergency cash assistance was in fact completed in September 2025.
- Under the BRCIS crisis modifier, 1,805 households were reached through multipurpose cash transfers and in response to different needs and different crisis. For example, one-month MPCA assistance was given to flooding and conflict affected individuals, whereas for individual affected drought, received 3 or 4 months of MPCA assistance.
- The Gaashaan protection programme provided 613 GBV survivors with emergency cash assistance as part of broader case management services.

GBV in Emergency: The total number of people reached with GBV assistance is 128,852. This overachievement is mainly delivered across Caafimaad + and Gaashaan that each demonstrated capabilities of expanding their specialized protection capabilities as part of its multi-sector offer including services and response to GBV survivors. Assistance delivered include women and girls receiving case management support, clinical support for health complications associated with GBV, distributions of hygiene and dignity commodities and psychological first aid, access to safe houses, psychosocial support services and referrals.

GBV and CP caseworkers provided support to survivors in line with the Inter-Agency Standing Committee (IASC) Case Management Guidelines. As part of case management, partners ensured safe referrals according to the needs and wishes of the survivor, including referrals to health services, safe houses, and legal and police protection.

Interventions were also supported by dedicated hotlines in Banadir, Hirshabelle, Jubaland, Southwest and Galmudug regions. The hotlines provided confidential support to survivors of gender-based violence (GBV) seeking assistance.

Dignity kits were distributed to women and adolescent girls with the support of the existing community-based structures in the target locations. These kits contained basic items to support female hygiene and to help protect the health and safety of women facing displacement and other challenges due to recurrent conflict in the region.

Emergency Healthcare: Caafimaad + reached 318,502 beneficiaries with outpatient consultations, child health, and reproductive health services. The package of health care services included outpatient consultations and referrals for severe cases, and included treatment for malaria, pneumonia, diarrhoea. In addition, the reach beneficiaries included 13,214 children receiving their measles vaccination before their first birthday and 37,432 pregnant women who attended ante natal care clinics and received support from skilled birth attendants.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The last Annual Review reported results through a bespoke log frame focused on our humanitarian response, the recommendation made was to establish a new multi-year HARBS log frame, after establishment of all HARBS multiyear humanitarian and resilience portfolio , and for this ensure that all results across humanitarian response and resilience are captured in a single framework. This action was finalised with the MEL partner in December last year, and the programme now has a multi-year Log frame which has been used for this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Integrate Early Warning and Response Systems (EWER) into GBV and CP - Somalia recurrent climate shocks such as flash floods, drought and conflict not only had impacted the food security of communities but has also increased the risk of GBV/CP to women and girls. To ensure the communities are able to respond and prevent the different protection concerns women and girls face in onset of the crisis, GAASHAAN will prioritize the integration of GBV/CP messaging and Protection triggers into early warning monitoring during the community awareness in coordination and collaboration with GBV/CP committees.

Caafimaad primary lessons learned include the utilization of the specialised tools for assessing monitoring and analysis nutrition and mortality data. Implementation proved very useful in achieving the objectives of the nutrition sector. There was also increased utilization of opportunities offered through the integrated approach to sensitize and create awareness on protection (GBV and CP) among the communities, as well as referral of cases. Ongoing mentorship of trained workers resulted in notable changes in reach in awareness and case identification.

WFP - the successful early response to the anticipated drought, where selected Baxnaano households received a one-time cash transfer of $360, was made possible due to two critical factors. First, the existence of the Baxnaano and the USR databases allowed for rapid identification and targeting of beneficiaries, highlighting the importance of having robust, pre-established systems in place for effective shock response. Second, the implementation was strongly supported by coordinated leadership from MoLSA, SODMA and WFP, enabling a unified and timely response. Building on these experiences from Year II, a key recommendation is to establish a formal tripartite agreement between MoLSA, SODMA, and WFP well in advance of any future crisis. Such an agreement should clearly define the roles, responsibilities, and protocols required for establishing the triggers, coordinating and activating social protection responses during shocks, and in future expand this agreement to include Ministry of Finance and make links with Disaster Risk Financing instruments.
Output Title	Improved use of evidence in humanitarian assistance and resilience building
Output number:		6	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Partner	Planned	Achieved	Score
# of evidence-based advocacy materials such as policy briefs, fact sheets, and reports created and disseminated by Gaashaan		0	0	N/A (Activities for this indicator were dropped for this year with BEM approval)
# of products that support improved risk knowledge for climate hazard prediction and planning to inform climate change adaptation and resilience building, produced by RESTORE	RESTORE	25	22	B
Better Lives and HARBS partners find HHELMS' outputs useful or very useful	HHELMS	75% (or 6/8)	75% for this indicator. (6/8 HARBS partners responded, with all 6-reporting useful or very useful outputs)	A
# of research, learning and data products/reports or briefs generated by the Danwadaag programme	Danwadaag	8	8	A
# of learning documents, toolkits, best practices published or disseminated internally and externally by BRCIS	BRCIS	2	3	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

This output supports the generation and use of high-quality evidence across the main HARBS resilience partners and the HARBS Monitoring , Evaluation and Learning Facility, HHELMS. This year, focus was on operationally relevant learning across BRCIS, RESTORE , Gaashaan, Danwadaag and performance of HHELMS. To note only Gaashaan output indicator 1 above was not delivered. Overall, the output scores A (meaning outputs met expectation).

Gaashaan: This year Gaashaan pivoted away from producing research and advocacy documents, to a focus on establishing capacity building plans as the partnership was still in its early start phase. This was a strategic move to ensure that the needed capacity is in place to deliver against the set output indicators and milestones.

RESTORE: The RESTORE consortium has a strong focus on using scientific evidence to inform early warning, response and watershed management. The consortium developed a flood model for the Shabelle river based on the Digital Elevation Model methodology. The model will continue to be improved through 2025. The downscaling of climate model for Shabelle was completed with a focus on impacts of hydrology in Middle Shabelle. FAO’s SWALIM team conducted a comprehensive analysis of climate data, employing advanced methodologies and leveraging cutting-edge technology to generate accurate and timely early warning products for the targeted project area, as well as other regions across the country. Throughout the ongoing Gu rain season, SWALIM has consistently delivered vital information to stakeholders, including one seasonal Somalia rainfall outlook and eight detailed rainfall forecast bulletins. Moreover, a total of 60,284 early warning SMS messages have been efficiently disseminated to vulnerable communities through SWALIM’s innovative Digniin system, complemented by 11 informative radio public service announcements aimed at alerting communities about the imminent threat of floods (note the SMS were not included under the indicator reporting to not distort reporting, which focusses on evidence products).

HHELMS: HHELMS supports MEL functions across the HARBS programme, partners and components. This year a key focus was to determine HHELMS' outputs utilisation and usefulness. HHELMS conducted a partner feedback survey. The survey was sent out to 1 Better Lives partner and 8 HARBS partners, with the received data disaggregated by respondent. For HARBS, 6 of the 8 partners provided feedback on the usefulness of outputs and the extent to which recommendations were implemented. All 6 provided feedback that the HHELMS outputs were useful or very useful, which meets the planned output of 75% useful or very useful feedback. 100% of HARBS partners that responded to the survey found the HHELMS outputs were useful or very useful.

Danwadaag: Danwadaag has had a similar focus on evidence and learning products. During the reporting period, IMPACT Initiatives/REACH and IOM developed and implemented the Durable Solutions Readiness Assessment (DSRA), leveraging data from the Detailed Site Assessment (DSA) and contextual analysis. The DSRA is designed to assess the demographic characteristics and displacement-related vulnerabilities of IDP households, as well as the key factors influencing their progress toward durable solutions, benchmarked against IASC criteria and compared to host community populations at the neighbourhood level. The first round of DSRA (DSRA I) was conducted between February and April 2024, with 8,880 household surveys completed across 84 selected IDP sites and host communities. Key findings from six locations (Baidoa, Galdogob, Galkacyo, Garbahaarey, Kadha and Kismayo) were disseminated in February 2025.

The Durable Solutions Landscape Assessment (DSLA) report was also produced during this period, evaluating the coherence and compliance of Somalia's solutions-relevant policies, laws, and plans, as well as the use of data to measure progress towards durable solutions and validation workshop held with representing the federal member state governments, UN agencies, and NGOs.

The IOM DTM Data for Solutions (D4S) team launched several key initiatives in 2024 to strengthen evidence-based programming. From April to June, the Durable Solutions Progress (DSP) Survey was conducted across eight HARBS cities, collecting representative data from IDPs and host communities with support from Displacement Tracking Matrix (DTM) and Danwadaag partners. This exercise, covering approximately 60 per cent of Somalia’s IDP caseload, was undertaken in coordination with the Ministry of Planning, Investment, and Economic Development (MoPIED) and other stakeholders. The findings were published on MoPIED’s website in November 2024 and validated during a workshop in December with local authorities and partners, including MoPIED.
The DTM-D4S team also led the rollout of the first round of the Solutions Projections Framework, developed in partnership with GIST. This report estimates future displacement flows into urban centres under various intervention scenarios, providing forward-looking insights aligned with Danwadaag’s territorial strategy. The analysis focuses on the long-term effects of investments in smaller towns like Xudur and Berdale, amidst rapid urbanisation in major hubs such as Baidoa and Mogadishu. FGD findings were compiled in a separate report to inform area-based planning across HARBS locations.

Additionally, the Local (Re)Integration Assessment (LORA), a tool established to measure durable solutions by comparing household data between displaced and host communities, was adapted to enable data collection at the neighbourhood/Derisnimo level, enhancing relevance for localised durable solutions planning. This adaptation resulted in the development of the DSP Survey as a nationally recognised tool. Adopted by the National Centre for Rural Development and Durable Solutions (NCRDS), the survey now serves as a baseline for the National Solutions Pathways Action Plan.

BRCIS: This year, BRCiS produced and disseminated three key learning products to enhance evidence-based programming and stakeholder engagement. These learning publications covering gatekeeping dynamics in Somalia, ecosystem health assessments findings in BRCiS locations, and BRCiS III implementation lessons were shared through BRCiS’ website and in-person workshops conducted in Nairobi and Mogadishu. Below is a summary of each:
- Gatekeeping in Somalia Learning Brief this study examines the role of gatekeepers in controlling aid access for displaced populations. It identifies two dominant models: an organized IDP business model in urban centres (e.g., Mogadishu, Baidoa) and a clan-based system in rural areas. The brief provides actionable recommendations to mitigate exploitation and improve accountability in humanitarian interventions.
- Ecosystem Baseline Assessment This assessment evaluates land health across 37 BRCiS project sites using field data, remote sensing, and machine learning. It analyses soil quality, vegetation, climate trends, and socio-economic indicators to guide restoration efforts. The findings offer a benchmark for tracking ecosystem recovery and informing adaptive management.
- BRCiS III Lessons Learned and Best Practices An external review by GIST synthesized 18 months of project data to highlight successes, challenges, and recommendations ahead of the midline evaluation. Key themes include community engagement strategies, operational hurdles, and priorities for the remaining project period.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The HARBS programme continues to employ the use of HHELMS and has so far been successful in generating learning and evidence for utility. Moving forward, This review recommends new learning, in the context of the HARBS portfolio needing to be reshaped/downsized), to continue to invest in evidence and learning, critical for high impact investments (important with less ODA) and also unique UK USP going back to the year one independent review of UK’s drought response, on FCDO continuing to create, value and act on evidence.

Output Title	Strengthened government capacity for crisis response
Output number:		7	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Partners	Planned	Achieved	Score
# of functional government-led coordination mechanics supported by the programme that effectively lead and coordinate durable solutions programming and develop relevant strategies and policies	Danwadaag	4	4	A
# of government institutions supported with material and technical support in Housing Land and Property (HLP)	Danwadaag	5	11	A++
# of government frontline workers trained on service provision in humanitarian contexts	BRCIS / Caafimaad + / RESTORE/ / FSNAU	Total - 4486 35 – BRCIS / 4431 – C+ / 20 – FSNAU/RESTORE	Total - 6299 / 37 (BRCIS extension workers) / 6242 CHW trained on ICCM+ / 20 (FSNAU government and local university staff trained on and participating in IPC seasonal analysis	A++
Number of capacity strengthening activities undertaken to support government line ministry (MOLSA & SODMA) for shock responsive social safety nets	WFP	One meeting per quarter	2 federal coordination meetings, 7 meetings with MoLSA and SODMA	A+

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focused on strengthening government capacity and effective coordination for crisis response by harnessing expertise across HARBS programme humanitarian and resilience components. Overall, this output scored A+ (meaning outputs exceeded expectations) and noted progress especially on training of government workers and strengthening coordination on shock response.

Capacity building and support for urban authorities for IDP durable solutions: Danwadaag continues to focus on development and sustainability options for IDPs linked to more effective and well-established urban authorities. Three municipal govt? Durable Solutions Working Groups (DSWGs) were successfully established in Banadir Regional Administration (BRA), Jubaland, and Southwest State (SWS), alongside the formation of a dedicated Durable Solutions Unit (DSU) in BRA to strengthen government-led coordination. The coordination platform remained active throughout the reporting period, with approximately 12 joint coordination meetings convened. This was made possible through strategic cost savings and co-funding synergies between the UK HARBS and EU Xaldoon projects. These additional sessions responded to emerging government priorities and evolving programmatic needs, enhancing government engagement and alignment.

Danwadaag also provided specialised HLP support to government authorities. In SWS, the Ministry of Public Works was supported with the printing of booklets of Urban land law and posters conveying HLP rights promotion messages in Baidoa. In Jubaland, four government institutions - Jubaland Commission for Refugees and IDPs (JUCRI), the District Commission office for social affairs, the Ministry of Justice, and the Land Commission Authority received office materials including equipment and furniture in Kismayo and Dollow. In BRA, four government institutions including district authorities in Dayniile, Garasbaaleey, Kaxda and the office of durable solutions for BRA received material support for providing HLP service to the communities. Salary support through capacity injection to was provided to two BRA-DSU officials (1 male, 1 female) that is the Director of Durable Solutions and the Head of Operations. Additionally, two staff from the Office of the Prime Minister (1 male,1 female) received support to develop and facilitate the National Transformation Plan (NTP) 2025–2029.

Training government frontline service providers: BRCIS utilised the RAF funding from centre to train government extension workers as lead agents of regenerative resilience, equipping them to deliver follow-on trainings and providing them with on-the-job mentoring (as part of the local community of practice approach). In Dhusamareb, 27 extension workers (26 male, 1 female) from the Galmudug line ministries of Agriculture, Environment, Livestock, and Water & Energy, along with local authorities and community representatives, participated in hands-on training in Resilience Design principles, permagarden establishment, and ecosystem restoration techniques. The sessions combined classroom instruction with practical fieldwork, including Resilience in Design theory, site assessments, and use of A-frame tools to initiate contour-based land design. Participants then implemented soil and water conservation techniques such as half-moons, bioswales, and rock check dams.

In Baidoa, BRCiS did not need to carry out a new training as there was an existing cohort of 10 extension workers (6 male, 4 female) who were previously trained under a project funded by another donor, These extension workers were therefore immediately available to support the rollout of restoration activities under RAF Activity 2.1, while continuing to receive mentorship from BRCiS, forming a local community of practice.

The temporarily appointed RAF Project Manager developed two qualitative case studies in Baidoa and Dhusamareb to examine the early outcomes, implementation dynamics, and sustainability prospects of these public extension schemes. The studies focused on understanding how Resilient Design? training and demonstration sites were received, applied, and adapted in the two distinct regions:
- Extension workers and communities responded positively to Resilient Design approaches, with many participants highlighting the relevance of the techniques to local climate and land degradation challenges. In both sites, extension workers reported applying their new skills beyond the project period, indicating strong potential for replication and ownership.
- Hands-on training combined with staff presence in the field was highly effective, creating visible shifts in participant motivation and practical understanding. However, uneven baseline skills and occasional overconfidence in replication efforts revealed the need for ongoing mentoring, technical oversight, and support systems.
- Institutional fragility—particularly the lack of salaries and logistical support for government staff—limits scalability, but the case studies also showed that strategic facilitation, targeted incentives, and partnerships with credible local actors can help overcome these constraints and build pathways to long-term resilience.

Caafimaad + Community Health Workers trained implementing Integrated Community Case Management (ICCM) plus nutrition (ICCM+) identified and referred 6,242 children U5 with uncomplicated Severe Acute Malnutrition (SAM), for treatment. These communities are typically located very far from the facilities and also tend to have security-related access challenges for the mobile outreach teams.

Under the Food Security and Nutrition Analysis Unit (FSNAU) component of the RESTORE project, a total of 338 government and local university staff (284 male and 54 female) benefited from various capacity development support during the reporting period:
- 75 through training on IPC and food security (58 male and 17 female)
- 141 through training participation in seasonal assessments (127 male and 14 female), and
- 122 through participation in IPC analyses (99 male and 23 female).
In addition, as part of the continued implementation of the recommendations from the 2023 Independent Somalia IPC Review (funded by the UK), an IPC Technical Working Group (TWG) was formally established in February 2025 including Government representation.

Government capabilities to deliver shock responsive social protection: WFP’s capacity strengthening efforts have supported three interconnected components aimed at: a) the development of an Adaptive Social Protection strategy and policy dialogue; b) operational engagement through partnership agreements with government agencies; and c) providing hands-on technical training for MoLSA and SODMA on community early warning, early action, Disaster Risk Management (DRM) plans, and coordination at the FMS level.

This strategic injection of capacity building has resulted in a breakthrough, particularly in fostering collaboration between the FGS SODMA and MoLSA. A key achievement has been the signing of a joint memorandum of understanding between these two agencies, formalizing their roles in activating shock response social protection within the project. This agreement clarified the respective responsibilities of each agency in times of crisis and significantly strengthened the collaboration between them. Furthermore, the technical expertise of SODMA in monitoring and triggering climatic shocks was highlighted, while MoLSA’s role as the custodian of cash transfers through Baxnaano was also reinforced. These achievements lay a strong foundation for future systems strengthening within the agencies and establish clear lines of coordination for shock response.

In addition, the HARBS programme provided £1.5 million to the World Bank through the multi-partner fund, and this provided advisory and analytics to MoLSA to strengthen delivery systems for the Baxnaano programme and establish building blocks for a future Social Protection programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first year that we are using this new multi-year HARBS log frame which was finalised with the MEL partner in December last year. So, no changes as part of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

To advance the development and implementation of a shock-responsive social protection framework, WFP introduced three interconnected capacity-building initiatives: a) support for policy and strategy development; b) establishment of federal and state-level operational agreements with government entities; and c) deployment of a technical firm to deliver hands-on capacity strengthening for both federal and member state MoLSAs and SODMA. This technical support focused on reinforcing the link between disaster risk reduction (DRR) and social protection in the design of responsive safety nets. The next step is for these arrangements to extend beyond the UK funded WFP project to wider shock responsive system. This initiative has been timely in providing a catalytic opportunity for Somalia to bid for other opportunities, such as the Global Shield Against Climate Risk financing.

Furthermore, the Global Sheild’s Country Capacity Assessment process is a key step in the strategy/ policy development will lay the foundation for the Government of Somali to bid for climate financing opportunities. Key lessons learnt from this work are (a) Building sustainable government capacity in shock responsive social protection requires sustained, intensive engagement, shifting focus from short-term operational support to long-term strategic systems development, institutional strengthening and service delivery. Capacity building efforts must go beyond training to include institutional support, mentorship and embedded technical assistance that enables government to lead and implement effectively; (b) the integration of SP systems into Disaster Risk Reduction (DRR) design has proven essential for increasing the shock responsiveness of safety nets. The linkage not only strengthens the relevance of SP frameworks in fragile and climate-affected contexts like Somalia but also positions the country to access global climate financing; (c) MoLSA and SODMA coordination at the federal level has demonstrated emerging government leadership and ownership. However, implementation capacity and coordination mechanism at the sub-national level remains uneven. For the systems to be truly inclusive and effective, sub-national structures require targeted investment in both technical and leadership capacities through structured collaboration frameworks.

Looking ahead, a key recommendation is to strengthen both technical capacity and joint leadership at the sub-national level to ensure that these systems are effective and inclusive across all levels of government. Similarly, WFP has established formal agreements at national/state which is helping lay a foundation among key stakeholders to clarify roles and expectations, promoting accountability. Support from FCDO has helped lay the essential foundation which will enable FGS and FMS to continue building DRR and SRSP efforts for the country.

Lastly this review notes that there are inherent risks and challenges associated with “capacity building” through delivery – what are the sustainable and system level shifts in an organisations governance and delivery capabilities? Or is it simply transactional? In the year ahead, the HARBS programme team should challenge all partners on their approaches, and ensure that this is informed by political economy, local dynamics, and an assessment of local commitment to deliver. With reduce ODA, working with and ensuring responsibility of local communities, public sector workers and govt is even more critical

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
This year saw significant increases in the overall value for money of the HARBS portfolio. Driven largely by the fact that resilience partners were fully operational and out of inception phase. This meant that we saw the cost effectiveness that comes with large scale investment in resilient action, as partners such as BRCIS and RESTORE invested in prevention and mitigation in advance of foreseeable shocks – specifically water harvesting interventions in advance of forecasted below average rainfall, and improved flood defences in advance of forecasted flooding. HARBS also continues to support more sustainable delivery models and systems – ecosystems, nature-based solutions, government response systems – which bring sustainability and cost effectiveness. Lastly, as mentioned in Section A, donor collaboration is at the heart of HARBS major programmes, ensuring maximum return on investment in an era of declining ODA.

Economy and efficiency: Throughout programme implementation, implementing partner operating costs have remained proportionate. Various measures were put in place by partners to ensure costs were fair, these included:
- Within the RESTORE project, operational and administrative costs were shared with other projects, therefore enhancing VfM by achieving economies of scale.
- In the Danwadaag consortium, private-public partnership options were explored, resulting in a 30% private sector contribution to a water access intervention.
- Both Danwadaag and RESTORE used local suppliers, where possible, to procure goods to support humanitarian response, ensuring that procurement was conducted transparently to drive down costs.
- The Caafimaad+ consortium ensured that human resources were fairly compensated using the Ministry of Health approved EPHS 2009 and EPHS 2020 guidance, ensuring that whichever fee was highest was the one used to motivate and retain staff.
- INSO’s services were used to support NGO safety, which proved better value for money compared to using individual private providers who charge higher fees for reduced service compared to INSO.
- Using existing national infrastructure, e.g. beneficiary databases, to identify households eligible for Social Protection Support provided by WFP. This enabled cash transfer values to be increased due to the savings made from these efficiencies.

Some partners highlighted BEM generated challenges. The BRCiS consortium, for example, highlighted how FCDO practices of encouraging implementing partners to deliver spend in short timelines meant that partners were incentivized to deliver more costly CDEL investments. This meant that some partners were delivering interventions that were knowingly more expensive to the FCDO than was necessary were these constraints not in place.

Effectiveness and efficiency: the overall performance of the HARBS programmes and its partners, proves that the resources are translating to successful outputs and outcomes. Key partners including Caafimaad, Danwadaag and BRCIS have seen significant overachievements as they have deployed efficiency measures to increase reach and achievements. This includes communities replicating interventions at their own initiative and cost such as water harvesting techniques or land restoration practices under BRCIS; or pooling multiple donor resources for efficiencies and increased achievements as in Danwadaag. The SHF prides itself as having the highest proportion of funds going directly to local partners, this is a key reason that the fund is having such success at delivering priority interventions in some of the hardest to reach locations in Somalia. The partnership model is both cost effective and delivering on strategic priorities. As set out in the HARBS business case, key partnerships are establishing robust frameworks for analysing VFM throughout and comprehensively come the end of the programme, as demanded in the HARBS business case design and as per UK ODA rules. BRCIS and Gaashaan are analysing cost drivers by output and assessing that against achievements to identify best practices and inefficiencies. Danwadaag is building on best practice from phase 1, and planning on conducting return on investment studies against key workstreams to assess what has proven to be best value for money.

Strong use of evidence to adapt programming, supported by strong community, government and implementing partner engagement enabled the programme to spend well, though unstable funding meant some investments in Y1 were not capitalised on. In a volatile and changing environment, it was critical that partners responded quickly to crises and adapted their approaches to respond to the external environment. Some partners were able to capitalise on existing resources and consortia structures to rapidly respond to crises, for example, through Caafimaad+’s use of existing consortium office structures, which enabled them to focus on pre-positioning health and nutrition supplies ahead of a crisis. The use of the crisis modifier also enabled HARBS to support rapid response.

Partners also sought to work with government and other implementing partners to ensure that inputs were not duplicative to achieve the same / similar outputs. Key examples of strong collaboration include:
- Danwadaag, BRCiS and SomREP consortia producing a joint EWEA strategy designed to reduce the risk of duplication and better coordinate early warning systems.
- WFP’s work alongside the World Bank under the Social Protection Support project to support a coordinated approach to social protection based on shared data and needs analysis frameworks. This has enabled social protection systems to be more interoperable.
- Danwadaag’s engagement with line ministries and local authorities to ensure IDPs were integrated into existing public services, sector plans and social protection systems following identification of potential duplication of work.

Many partners saw good returns on their output indicators, with BRCiS overachieving on their key resilience activities; GAASHAAN showing evidence of meeting their outcomes around strengthened capacity of GBV and child protection actors, as well as empowering communities and community-based protection structures. INSO received 96% overall beneficiary satisfaction for their delivery, showing strong returns for FCDO investment.

During their annual reviews, some partners shared efficiency challenges when using FCDO funds: BRCiS highlighted the impact of reduced budgets on their ability to maximise the gains of Year 1 investment in Year 2, as some activities had to be de-prioritised. Whilst greater value for money could have been achieved in Year 1 had these activities not been conducted, BEM oversaw strong prioritisation of activities with partners impacted by funding reductions, ensuring that long-term resilience partnerships were protected despite reduced funding.

Equity: the previous HARBS annual review set out the importance of integrated GEDSI into design, targeting and delivery. It’s integral to the conceptualisation of humanitarian and resilience impact and success in Somalia- did it have the intended impact specifically for women, youth, persons with disability and marginalised groups (clans in particular). throughout the HARBS programme, partners evidenced strong focus on marginalised groups, with interventions being targeted to these groups and data disaggregated in reporting.

Evidence across the programme shows that most, if not all, programmes utilised GEDSI analysis, or similar methods, to ensure participation by all genders, particularly women, in their interventions and to make sure they were supported by humanitarian interventions. Examples include:
- Danwadaag’s creation of a consortium-wide GESI strategy, which support protection considerations being embedded into EWEA systems
- WFP systems de-duplicated data to allow them to reach a wider geographic area with their shock-responsive social protection
- BRCiS used GEDSI analysis to enable active women’s participation and awareness of issues that impact them (e.g. sexual exploitation and abuse, gender roles etc.).
Furthermore, some delivery partners have acknowledged where they can be even more ambitious with their inclusion of diverse groups, e.g. INSO reaching 36% local NGOs, with further work planned to increase this reach through capacity building of local NGOs.

Responding to a recommendation from last year’s annual review, HHEART commissioned the HARBS MEL partner to do a desk review of GEDSI mainstreaming across HARBS and in doing so assessing the extent to which equity considerations are successfully addressed. There are many examples of positive initiatives across the programme, such as: HARBS programme policy on improved indirect cost recovery for local partners; shock responsive safety net cash assistance and Caafimaad health, nutrition and protection work all predominantly or wholly target women and children; BRCIS and Danwadaag explicitly target and measure outputs and outcomes for minority groups. However, it also highlights key areas for ongoing improvement:
Localisation features prominently in programme design, though implementation depth is unclear: Most partners describe partnerships with national NGOs, with some setting quantitative targets or outlining capacity support. The extent to which these partnerships influence delivery, leadership, or decision-making needs to be measured more deliberately as part of HARBS partner performance.
Disaggregation commitments are common, but limited in scope and consistency: Many projects plan to disaggregate data by sex, age, aFSDFDSnd disability. Though we are making good progress on gender and age, disability and minority clan remain absent from too much of what we measure.
Engagement with minority-led organisations is limited across the portfolio: Only a small fraction of SHF funding is documented as reaching minority-focused organisations, and few IPs provide detail on direct collaboration, or tailored support. These gaps will require deeper exploration during fieldwork
References to transformative GEDSI approaches are present but not well operationalised: Some IPs (e.g. BRCiS, WFP) describe gender-responsive strategies and inclusive MEL. However, most programmes stop at general commitments, with few outlining indicators, resources, or systems to track deeper shifts in inclusion or power dynamics.

Assessment of whether the programme continues to represent value for money
In a similar vein to the assessment of whether the programme should continue, HARBS represents value for money. However, the upcoming ODA reductions and strategy changes value for money will be central to decision-making on a consolidated approach – cost effectiveness and equity in particular. . This will be central to the HARBS streamlining and amendment process which was described in sections A and B.

E: RISK [½ to 1 page]

HARBS continues to operate within the BEM risk appetite with an overall risk rating of Major.

The multi-year humanitarian and resilience partnerships began implementation of the projects based on lessons from the El-Nino response the previous year and post inception learnings and recommendations. FCDO begun the financial year with a reduced budget allocation that required IPs to prioritise programming in different locations whilst managing compounding contextual and operational risks which remain in Somalia. To manage risks, the programme team has maintained a robust risk management approach (with bi-monthly risk conversations) to ensure that the HARBS programme is implemented within the portfolio risk appetite and escalate where risk is outside the risk appetites. The programme team held quarterly risk discussions, highlighting trends and strengthened mitigating actions appropriately.

Strategy and contextual risks continued, with 2024 recording a significant increase in inter-clan conflicts in Hirshabelle resulting in increased humanitarian needs and displacement. Political tensions between FGS and FMS required continuous engagement amongst partners to mitigate programme delivery impacts. Climate risks such as below average Deyr rainy seasons resulted in some areas experiencing moderate drought conditions and increased needs. UK supported early action through FAO, CAAFIMAAD and ICRC. Mitigations are set out in our risk register, including system wide initiatives as we seek to ensure that the humanitarian community increases its capability to deliver in AS controlled areas – beyond just partner specific contingency planning.

Fraud, Corruption and Safeguarding remains under-reported with only 7 suspicions of fraud reported. UN partners continued to provide periodic updates on aid diversion allegations monitored and investigated through internal systems and processes. Talk to Loop handled various types of feedback including requests for assistance, information, and concerns. Importantly, during the quarter, 174 sensitive protection-related (GBV, child protection, MHPSS) and SEAH cases and 38 complaints related to aid diversion, fraud, and corruption. These reports mainly highlighted concerns that humanitarian aid did not reach those most in need, but instead unfairly benefited certain groups, individuals with personal connections, or those in positions of power. Complainants often raised issues of favouritism in aid distribution, misallocation of resources, and a lack of transparency in the selection process. Whilst there was no evidence that UK funding was implicated, the programme team continues to engage with partners on the issue of gatekeepers and aid diversion during quarterly programme review meetings whilst reiterating UK Zero tolerance to fraud and corruption. The HARBS programme team will assess partner compliance and assurance efforts through its TPM activities.

The programme team conducted refreshed due diligence assessments (DDA) for NRC, IOM, OCHA, FAO and WFP. Some of the recommendations from the assessments included close monitoring of staffing gaps to ensure programme delivery is well resourced including implementing short term measures to cover gaps, continuous improvement of financial management systems to improve transparency and VfM and strengthening complaints and feedback mechanisms within organisations to better respond to SEAH as reporting remains low across all HARBS partnerships. The programme team will follow-up on DDA recommendations with lead agencies periodically.

Finally, there are significant risks associated with wider ODA reductions and BEM specific ODA reductions. As the HARBS programme adjusts to this new reality, HHEART will work with wider BEM and HARBS partners to identify the most critical risks and do all that is possible to manage and mitigate these.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Programme Management

This review period marked the second year of implementation for the multi-year partnerships with BRCiS, Danwadaag, RESTORE, GAASHAAN and HHELMS. The programme team conducted post inception workshops with partners to review lessons learnt and recommendations for the next phase of programming. This included agreeing workplans, milestones and budgets to ensure alignment and delivery of project outcomes and outputs. Progress updates against all projects were provided in accordance with agreed timelines through narrative and financial reports and ad hoc discussions were held to discuss and agree specific issues on a case-by-case basis.

Performance of partnerships
Through years of collaboration, BEM has established a strong working relationship with our partners, built on trust, understanding and mutual benefit. Partners continue to be engaged and responsive to BEM ensuring the programme is agile, adaptable and responsive. However, as described above partners have shared concerns around the continuing uncertainty and realism around UK ODA financing, with deadlines for capital spend, for example, that potential undermine programme impact. Coordination with humanitarian partners and other donors through the Humanitarian Country Team (HCT) and the Humanitarian Donor Group (HDG) continues to strengthen advocacy efforts, and drive reforms with the humanitarian system to promote efficiency and effectiveness.
The UK continues to seek opportunities to secure strategic partnerships with other donors. The programme team secured additional multi-year funding from QFFD for the BRCiS programme; negotiations are underway for a planned start date in 2025. The USAID co-funding arrangement for the BRCIS FARMS project (01 Dec 2024- 31 August 2027) was paused in January 2025 following the USAID Stop Work Orders and eventually terminated in March 2025 resulting in a refund of USD 2,975281 to the donor.
We continue to enjoy high performing partnerships under our AG agreements with BRCIS, INSO and Gaashaan who all demonstrate transparency and adaptability. The MOU with Danwadaag does well to exhibit similar traits despite the different level of accountability provided for by the terms of the MOU. However, we continue to face challenges under the complex and ambitious MOU with the Restore consortium. The most notable challenges are (1) unwillingness to include BEM in the core governance structures of the consortium; (2) unwillingness to share risks with BEM; (3) consortium partners operating in organisation and sector siloes. BEM will conduct a series of partner engagement sessions at senior and consortium leadership levels in order to make concrete demands on how we want the programme to change.
Contract Performance
The monitoring and evaluation component - Humanitarian, Health Evaluation, Learning and Monitoring in Somalia (HHELMS) team led by Oxford Policy Management Ltd is in its second year of implementation. Delivery of outputs during the year under review have remained good - all reporting have been submitted on time and of good quality and supplementary documentary requests provided in a timely manner.

The HHELMS and BEM teams meets every two weeks which allows for continuous adaptation in response. The two teams meet every quarter to review progress against deliverables. There are other ad hoc meetings depending on the programme needs, which HHELMS team have fully engaged in during the year. HHELMS team have maintained a responsive, open, transparent, and solutions focussed approach to technical delivery, management and administration.

HHELMS engagement with the HARBS implementing partners has been through their focal points who have strengthened the relationships, visibility and participation in partner meetings, and have increasingly direct engagement beyond the quarterly review meetings, especially under BRCiS, Gaashaan, and Danwadaag partnerships.

HHELMS team has been proactive in flagging risks and raising potential issues to BEM, and have worked closely with programme team to mitigate, address, and adapt deliverables as need be changing timelines and circumstances for all stakeholders.

Over the next reporting period, across partners, one area that will require a close focus is spending against forecast due to the constantly changing context and reducing budgets for HARBS partnerships. The BEM Team is working to finalise a contract amendment for personnel changes for implementation phase.

Financial Performance
The initial budget allocation for the financial year was £38million a significant reduction from the previous year allocation. This required ruthless prioritisation at the start of the year by implementing partners to ensure the programme responds to those most in need of humanitarian assistance and resilience support. Additional funding was made available in year bringing the total HARBS allocation to £64million allocated as follows:

Humanitarian	Forecast £	Actual Spend £	Percentage Allocation
World Food Programme - Shock Response	8,240,272	8,240,272.00	13%
GAASHAN (Save the Children)	2,665,800	2,594,984.88	4%
ICRC	15,000,000	15,000,000.00	23%
INSO	435,219	435,219.00	1%
SHF	3,500,000	3,500,000.00	5%
OCHA	500,000	500,000.00	1%
IOM emergency response	3,000,000	3,000,000.00	5%
WFP Emergency response	3,300,000	3,300,000.00	5%
Resilience
RESTORE (FAO)	8,542,689	8,542,689.00	13%
BRCiS (NRC)	8,849,973	9,247,650.34	14%
Danwadaag (IOM)	5,015,151	5,039,773.53	8%
World Bank for Shock Responsive Safety Nets	750,000	750,000.00	1%
MEL
HHELMS	1,438,106	1,532,536.45	2%
HSOT/Stand By Partners	290,000	344,888.24	1%
IRF
Caafimaad Plus (AAH)	2,700,000	2,608,015.67	4%
TOTAL	64,227,210	64,636,029.11	100%

*FY 2024/25 ICF spend £15.5million

The programme team maintained a high-level of oversight, carefully reviewing partner budgets to ensure transparency, accuracy and accountability in financial forecasting and expenditures. There was continuous effort in correct classification of budgets across ICF, RDEL and CDEL categories and in line with the designed HARBS ICF methodology note (an action from the last Somalia office-wide internal audit).

Funding to partners was disbursed in accordance with the agreements and in line with the Programme Operating Framework (PRoF) rules. Where funds were disbursed in advance, proper justification was provided to ensure it was not in advance of need. Partners submitted financial reports and statements as agreed, these were reviewed by the programme team to ensure spend against agreed budgets. There will be further scrutiny on the RESTORE financial report before the next tranche payment to ensure payment is not in advance of need and aligns with workplan and forecasts.

Audited reports were submitted in September 2024, all of which received unqualified opinions. Some of the key findings across the reports relate to weaknesses in management, procurement and payment processes, incomplete personnel files, budget overruns without prior approvals and non-compliance with reporting timelines. The programme team continue to monitor progress against recommendations and actions outlined in the report. Partners have commissioned audits for the period Apr 2024-Mar 2025 which will be finalised and submitted by September 2025.

Implementing partners maintain up-to-date asset registers for all programme funded assets and these are updated and shared quarterly. Asset spot-checks will be weaved into subsequent TPM activities conducted for the next implementation period..

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
The Humanitarian Resilience and Human Development, Monitoring, Evaluation and Learning (HHELMS) component provides monitoring, evaluation, and learning (MEL) functions across the HARBS programme and is led by Oxford Policy Management with consortium partners Consilient, Laasfort, New Access International and Social Development Direct. HHELMS commenced its inception period in August 2023, which concluded in February 2024 and is now in full implementation until 2028. There are four key workstreams delivered by HHELMS:
1. Programme-wide and implementing partner monitoring
2. Operational learning
3. Evaluation and evidence generation
4. Cross-cutting data management, analysis and communication
Key monitoring activities for this year included:
- Third Party Monitoring activities (conducted across WFP KSrelief (cash), BRCiS, Danwadaag, Gaashan and RESTORE (FAO-led).
- VfM programme framework development and commencement of support to partners on how to report into the framework, though further work on this has been paused due to capacity challenges in BEM.
- Partner-level MEL Systems Review, which analysed how partners’ indicators were embedded within the HARBS Theory of Change (ToC).
- Finalisation of the overall HARBS programme results framework.

In addition to HHELMS MEL provision, delivery partners have their own MEL arrangements which are used to feed into the programme-level MEL. HARBS partners invested in numerous assessments, strategies and other bespoke evidence pieces which have effectively guided planning of activities and helped refine project strategies and delivery approaches. In terms of evaluation, baseline evaluation has been carried out for GAASHAAN protection project. This evaluation used a Realist Evaluation perspective, which has considered equity as part of its approach to formulate evaluation questions in line with PrOF Rule 9.

Evidence

HHELMS recently conducted an evidence review analysing the areas of evidence addressed and those with gaps across a range of thematic areas (see Figure below). This review noted that there were some areas where multiple implementing partners were delivering interventions and producing evidence on the same thematic area.

Recommendations and next steps therefore focus on validating and expanding evidence inputs with implementing partners; tracking the finalisation and dissemination of planned deliverables and any changes to evidence needs; and supporting implementing partner dialogues to synthesise learning in priority areas. Whilst evidence tended to be good, HHELMS noted that it was often filtered through leaders. Therefore, to ensure representation of marginalised groups, direct outreach is needed in future for inclusive learning.

A priority for the next year will be using HHELMS engagement with partners, and the learning workstream (particularly learning events) to bring partners together to share the work they are doing within projects on evidence generation to ensure it is shared across the portfolio – and wider.

In addition to partner commissioned evidence work, HHELMS via the Evidence Window established this year a partnership with Ground Truth Solutions to generate evidence on understanding the path to inclusive aid and resilience. This is a key component of our forward-looking policy engagement on the Somalia humanitarian Reset

A priority for 2025, will be to determine early what other strategic research the UK can commission to support policy objectives. Pipeline ideas being scoped is support to the DRSRG/RC/HC with a review on the Humanitarian Reset and wider Post-Delivery Aid Diversion reforms, and support to further work on mortality modelling which will be critical to understanding the impact of aid reductions on the humanitarian context in Somalia.

 Summary of evidence coverage for HARBS, conducted by HHELMS MEL partner

Learning

HHELMS has collated quarterly and annual review contributions for implementing partners, with a learning event held in Q1 Fy24/25. Quarterly review meetings were initially introduced to engage with implementing partners, though time constraints in these meetings led HHELMS to establish standalone meetings with partners to ensure learning was addressed. Whilst contextual learning products for HARBS were delayed due to internal BEM budget delays, HHELMS did produce a start bespoke data platform in February 2025 to showcase Somali health and humanitarian data.[3] Communications products were also produced by HHELMS to raise awareness of the HARBS programme, with work ongoing to create a project summary for RESTORE. A priority for 2025 will be finalising the set up of the data platform to ensure utility for the HARBS team in analysing and understanding the programme portfolio. The BEM team will need to proactive in using this new tool to realise it’s full utility.
[3] HHELMS MEL data platform available at: https://hhelms.net

During their annual review meeting with BEM, HHELMS highlighted a number of key lessons from the implementation of HARBS from across partners:
- Shifting aid landscape: Major ODA reduction threatens operational capacity in Somalia, with implications for GDP, food security, and programme sustainability
- Community Engagement: Deep investment in relationship-building has reduced elite capture in BRCiS areas; however, inclusive participation remains challenged by structural barriers, time poverty, and unclear power dynamics.
- Danwadaag’s Neighbourhood-Based Model: Danwadaag offers a strong model for localised resilience, combining neighbourhood-level targeting (Derisnimo), anticipatory action systems, and active use of consortium evidence. Their work to link diaspora support with community grants and shift toward livelihoods and PPEs shows how evidence-driven transitions can be anchored in local systems.
- Evidence Use and Local Voice: Community priorities call for support to long-term resilience, not handouts; inclusion, transparency, and acknowledgment of existing capacities are critical.
- Feedback Systems: Tools like Talk to Loop are proving vital for trust-building and surfacing protection concerns, especially in high-risk or remote contexts.
- Private Sector and Diaspora: Emerging conversations emphasise mobilising diaspora finance and co-investment models to bridge the humanitarian-development divide.
- Operational Shifts: IPs are actively rethinking exit strategies, activity prioritisation, and community-owned programming (e.g., small funds, CHW-led surveillance, harmonised engagement models).

Accountability to Affected Populations
A pilot with Talk to Loop was implemented through the Gashaan and BRCiS consortium to provide communities with complementary safe and real-time pathways to share feedback, report fraud and abuse anonymously, ensuring independence and addressing fears of retribution and other barriers to community feedback. Loop saw a rise in engagement from people living with disabilities highlighting significant challenges in accessing humanitarian assistance across livelihoods, healthcare, food security and shelter emphasizing the need for engaging with Organisations for People with Disabilities (OPD) to amplify voices and make aid more accessible, relevant and inclusive.

Beneficiary verification contributed to strong accountability to affected populations. In the RESTORE project, the Hormuud database and community-level registration helped prevent collusion, ensuring transparent aid distribution.

Annual Review approach
This Annual Review has been prepared primarily by the HARBS programme team, with input from an external FCDO colleague from the Resilience & Adaptation Fund team. The HHELMS team supported with the collation of programme-wide results against the HARBS logframe and also produced a summary paper on learning from across programme MEL outputs (TPMs, learning events, GEDSI review and results collation). Annual reports and presentations from implementing partners provided a significant amount of input into this review, as well as AR meetings conducted with OCHA/SHF and ICRC on their 2024 operations.

Date of last narrative financial report	BRCiS – May 2025 / Danwadaag – June 2025 / Restore – May 2025 / Gaashaan – May 2025 / WFP – May 2025 / INSO- Apr 2025 / Caafimad – May 2025 / HHELMS – Apr 2025 / ICRC – June 2025	Date of last audited annual statement	Caafimad – May 2025 / BRCiS – Sept 2024 / Danwadaag – Sept 2024 / Restore – Due 2025 / Gaashaan – Sept 2024 / INSO- Sept 2024 / WFP – Due 2025 / HHELMS – Dec 2024 / ICRC – Due 2025