## Annual Review Template

Title: International Economic Partnership Programme
Programme Value £ (full life): £4m		Review date: July 2025
Programme Code: AMP ID # 300985	AMP start date: 04/08/21	AMP end date: 30/06/27

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	B	B	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-300985 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004843.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

South Africa has an influential role on the global stage. A member of the G20, with the Presidency in 2025, it is a core member of the BRICS grouping, vocal at the WTO, and a regional hub for finance and trade, South Africa is able to shape the global policy debate and represent the views of Africa and wider developing countries in a number of key policy fora.

Alongside this, South Africa has faced increasing domestic economic pressures. Stagnating per capita incomes for over a decade, increasing levels of public debt, and crumbling infrastructure have increased pressure on the government to deliver reforms that will improve the growth outlook and address the some of the world’s highest levels of unemployment and inequality.

This programme supports reform and collaboration on international and domestic economic policy through research, technical assistance, and policy formulation. It partners with key institutions including the National Treasury (NT), the Presidency, Department for International Relations and Cooperation (DIRCO), Department of Trade, Industry and Competition (DTIC) and the South African Reserve Bank (SARB).

The programme currently consists of two projects:
Project 1: Phase II of the Southern Africa – Towards inclusive Economic Development (SA-TIED) programme (up to £1m), started May 2022 and implemented by the United Nations University World Institute for Development Economics Research (UNU-WIDER). The project funds policy research, dialogue and debate on economic policy issues in South Africa to bridge the gap between research and policymaking. In the long-run, this will support evidence-based economic reform. The project is co-funded by National Treasury and the EU and has the following workstreams:
Enterprise development for job creation and growth;
1. Public revenue mobilisation for inclusive development;
2. Structural transformation, labour markets, and inequality dynamics;
3. Macro-fiscal analysis and policy modelling;
4. Food, energy, and water in a context of climate change;
5. Reform implementation; and
6. Data for evidence-based policy making.

Project 2: The International Economic Partnership (IEP) (up to £2.8m), started in July 2023 and is delivered by a consortium led by DNA Economics, supported by Economic Research Southern Africa (ERSA) and ODI. This project will strengthen the UK-South African partnership on economic policy by providing demand-led, flexible technical assistance to support South Africa’s urgent domestic economic reforms and strengthen SA’s ability to lead policy change within the Rules Based International System (RBIS).

Summary supporting narrative for the overall score in this review

Over the last year, the programme has continued to deliver high quality, policy-relevant, research for key UK stakeholders within the Government of South Africa (GoSA). It has helped to support the development of evidence-based policies in key areas of domestic economic reform, most notably in relation to Operation Vulindlela (President Ramaphosa’s reform agenda overseen by the Presidency and National Treasury). The work of the programme, particularly IEP, has also delivered high quality inputs to South Africa’s G20 Presidency, often at very short notice, which has strengthened the programme’s global influence and delivered strongly on the original business case.
SA-TIED has effectively navigated significant uncertainties and strained capacity within the National Treasury, continuing to deliver high quality and policy-relevant outputs, especially through the direct commissioning channel, for example on fiscal policy. The Secure Data Centre continues to be an exemplar – which was highlighted at UNGA – and is highly valued by both National Treasury and South Africa’s wider academic and policy community. The shift of the Secure Data Centre to report directly to the Director General have enabled its work to more directly support high profile national initiatives, and whilst the move out of the old National Treasury building has been disruptive, the team is settling in well to its new location.
The IEP has continued to expand, with high levels of demand accelerating programme delivery significantly. This demand, combined with the programme’s flexibility and extensive global and local network, has allowed IEP to support critical GoSA priorities on both the domestic and international stage, often at very short notice. This demand-led approach carries risks of mission-creep and spreading the programme too thinly, but these risks have generally been managed. The expansion of the programme also placed significant pressure on the existing team in the first nine months of the year, leading to some shortcomings in processes and procedures which were not fit for purpose at this new scale. The recent recruitment of a dedicated deputy team leader has led to significant improvements in programme management.
The advent of South Africa’s G20 Presidency has led to increased relevance of IEP on the international front. Inputs to work on the Finance Track, especially around the Cost of Capital, Illicit Financial Flows, and Tax, have been highly valued by GoSA and have informed G20 Communiqués and the recent Compromiso de Seville at the Financing for Development conference. It has also placed significant strain on both GoSA and British High Commission (BHC) staff, which has led to challenges in arranging high-level governance meetings of the Steering Committee. Despite this, the relationships which IEP has helped to build have enabled regular contact between the IEP team, BHC, and key GoSA stakeholders in different fora which have ensured the programme remains aligned with GoSA priorities and FCDO programme compliance.

Major lessons and recommendations for the year ahead

The additional workload generated by the G20 has caused some delays in implementing the recommendations of the previous annual review. Therefore there is some overlap between the recommendations of this review and the previous one.

Key overarching lessons include:

The demand-led nature of this work is its greatest strength but also contributes to a heavy reliance on GoSA “Champions” who are committed to driving forward the work. Both projects benefit from strong Champions, especially SA-TIED due to its structure where each workstream has a GoSA Policy Lead. However, if these people leave (as happened with the lead on the International Financial Architecture Working Group) and are replaced by less committed individuals, the work can stall. In instances like this, it is important that the programme pivots quickly and/or takes quick decisions to cancel workstreams which lack a Champion.

Both projects garnered some media attention, with outputs informing articles and Op-Eds. However, both could benefit from a stronger and more deliberate communications strategy for engaging and shaping public debate. This would allow for wider dissemination of the ideas generated by the research, including to relevant stakeholders not directly engaged by the programmes. This strategy must be mindful of the need to maintain GoSA confidence and not share sensitive information.

The programme is highly effective at supporting the Government of South Africa in delivering evidence-based policy making. As this programme reaches its conclusion, any future business case to design further support should ensure best practice from this programme is effectively captured.

Specific recommendations include:

1. SA TIED:
  1. The programme has grown substantially which presents some challenges for governance. Before the next phase of the programme, a governance review should be undertaken to ensure that the roles of the Steering Committee and Advisory Board remain fit for purpose.

  1. As GoSA take on an increasing role in funding SA-TIED, UNU-WIDER should ensure a clear breakdown of responsibilities of governance in the design of phase III.

  1. High churn of research advisors can mean that there is a constant need for training. Developing re-usable training materials will improve efficiency.
2. IEP:
  1. Whilst the failure to hold a Steering Committee meeting this year is understandable given the pressures created by the G20, holding one in the next quarter of the programme cycle should be a high priority to ensure continued alignment with GoSA and to surface opportunities for the programme to deliver influential work.

  1. The process of selecting workstreams, and identifying Champions, also needs to be deliberate. Flexibility is a positive but can lead to mission creep and the BHC and DNA Economics team must be mindful of the need to maintain a coherent programme of work. As demand for the programme grows, potentially outstripping budgets, this will be important for helping the team to prioritise, including saying no to certain requests which do not align or a deliver sufficient impact to warrant flexibility.

  1. Where IEP work is delivered by non-consortium partners, e.g. the work on Rail Reform, it is more difficult for the DNA Economics team to ensure its quality and timeliness which presents additional risks. These risks must be owned and managed by the BHC and therefore this delivery channel should be used only for very high impact activities.

  1. Gender has been a significant focus of the programme but has fallen short of expectations. The recent changes implemented to allow the GESI expert to engage earlier in the process ought to lead to some improvements. However, there remains a lack of demand for this work in some areas of GoSA, especially macro-fiscal. Thoroughly addressing this is likely beyond the scope and capacity of this programme so GESI resources ought to be pragmatically targeted where they can have the most impact, for example with the Planning Commissioners.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (ToC) remains unchanged from the original business case: support to the government of South Africa (GoSA) on economic policy will strengthen reform efforts to tackle domestic growth challenges and deliver a more effective rules based international system that better reflects the interests of developing countries.

UK-SA International Economic Partnership Theory of Change

Whilst the programme had a more significant focus on the domestic agenda than the international in the initial phase, in 2024/25, the balance has swung back towards the original focus of the Business Case (shaping the RBIS) due to South Africa’s G20 Presidency. The IEP has provided several important pieces of work to inform the G20 Presidency, including supporting the engagement of Professor Michael Jacobs who had previously engaged with the Brazilian G20 Presidency, and contributing significantly to a position paper on the Cost of Capital. Given that many key GoSA stakeholders for both IEP and SA-TIED were closely involved in the G20 Presidency, the relationships built through the domestic work helped the programme to pivot quickly and respond to GoSA priorities at short notice.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Whilst the impacts of policy change will take time to emerge, the programme is performing well against its outcome-level indicators, meeting or exceeding both milestones this year. This indicates that the programme is positively influencing policy-making on both the domestic and international stages within South Africa.

Outcome-1	Outcome Indicator 1.1	Baseline August 2022		Milestone August 2023	Milestone August 2024	Milestone August 2025	Target: August 2026
Evidence-based approach to economic policy making, with domestic and international policy informed by IEP activity	Policy discussions informed by research and debate generated by IEP (cumulative)	0	Planned	-	4	9	10
			Achieved	-	4	9
		Source
		Formal reporting from implementing partners
	Outcome Indicator 1.2	Baseline August 2022		Milestone August 2023	Milestone August 2024	Milestone August 2025	Target: August 2026
	Examples of South Africa using IEP-led research in its approach to international policy debates (cumulative)	0	Planned	0	4	6	8
			Achieved	0	1	8
		Source
		Formal reporting from implementing partners

The programme continues to have a direct input to the key policy issues domestically within South Africa, most notably Operation Vulindlela (OV), where both the SA-TIED and IEP projects have been active.

The IEP project was able to build on previous funding for an evaluation report titled “Operation Vulindlela (OV) – Phase 1: High-level Impact Assessment of OV’s Impact on GDP Growth” to provide targeted TA to support OV Phase II. This supported the stakeholder engagements with the various departments and experts in the field, and officials currently involved in managing these areas. These workshops refined the Theories of Change developed for local government and spatial inequality focus areas and agreed on the proposed interventions. This supported the outcome of enhanced economic reforms in the programme’s own theory of change.

SA-TIED also support OV, but less directly than in previous years where the team had participated in the Operation Vulindela Conference. Building on that engagement, the academic lead for SA-TIED Workstream 6, Professor Ian Goldman, held a workshop for Operation Vulindlela personnel on Theory of Change in October 2024. The work of workstream four, on macro-fiscal analysis and policy modelling, has also supported work on OV Phase II.

On the international stage, the programme has outperformed. The IEP project in particular has contributed towards successes under South Africa’s G20 Presidency. Some of this work was well-choreographed and forward-thinking, such as a background paper was developed to inform the South African Presidency’s alignment and prioritisation against the agenda set by Brazil’s G20 Presidency. However, some of the most valuable technical assistance to support DIRCO and NT on the G20 was delivered at short notice due to the programme’s flexibility. The assistance to draft the Cost of Capital issue paper was particularly valuable, coupled with the technical assistance to the Presidential Climate Commission to support the G20 Climate, Environment and Sustainability Working Group.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme continues to deliver high-quality, timely, and valuable outputs that directly contribute to evidence-based policy-making in South Africa and inform South Africa’s international engagement. As discussed below, both aspects of the programme offer strong value for money on their direct outputs, as well as a number of secondary benefits to the UK Government, most notably strengthened relationships with key stakeholders.

SA-TIED has exceptional levels of GoSA buy-in, including significant direct funding, which ensures that its outputs directly contribute to policy making in priority areas, including macro-fiscal modelling and Operation Vulindlela. The funding from the UK allows SA TIED to do more than it otherwise would, whilst strengthening UK-SA ties on economic issues.

IEP has a strong team and excellent domestic and international networks which have allowed the programme to respond rapidly to GoSA priorities. This has built the confidence of key GoSA stakeholders and has positioned the programme well to continue shaping policies that will improve the economic outcomes for South Africa and its people.

## C. DETAILED OUTPUT SCORING

Based on recommendations from the previous annual review, a new logframe was drawn up to capture activity from both the SA-TIED and IEP elements of the programme. For this reason, some outputs have changed compared to the previous annual review to capture activity across the programme. The reporting cycles for SA-TIED and IEP remain misaligned which has increased the demand on partners to input into the logframe.

Output Title	High quality policy-orientated evidence on economic issues produced, utilised and shared.
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of products developed for policymakers. (cumulative)	150 (SA-TIED) + 45 (IEP)	99 (SA-TIED) + 70 (IEP)
Qualitative discussions with policy makers to identify examples of policy debate informed by IEP	6 (IEP)	9 (IEP)
Number of data extractions made available in the Secure Data Center at the National Treasury for researchers and policy analysts	33 (SA-TIED)	46 (SA-TIED)

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall the programme has continued to deliver both high quantity and quality of policy-oriented evidence on economic issues which are relevant to both South Africa’s domestic and international priorities.

IEP
The IEP has had an excellent year in which it has delivered above all targets for this indicator. The programme has become highly relevant for key stakeholders, especially within the Presidency. Working with the Presidency has increased the profile and relevance of IEP, especially around OV where IEP and the DNA Economics team is well positioned to work with both the Presidency and National Treasury. Other work with the Presidency, for example on the Rail Reforms, was delivered by Crossrail and BCRRE and aimed to support the rail sector's capacity and capability recovery post-COVID as a matter of urgency, while assisting in the implementation of the emerging longer-term rail masterplan for rail in South Africa.

SA-TIED
For SA-TIED, the work of the Secure Data Centre continues to outperform, despite challenges related to moving buildings. Data extractions were 40% above the target, and a large portion of these directly informed policy making. The number of products developed for policy makers, which includes research papers, was 34% below the target. There were a variety of reasons for the slower than anticipated publication of papers. Two examples were strategic delays to maximise impact, which did not delay use of the research by policy makers, and unanticipated delays due to revisions of papers which did not meet expectations around quality – as SA-TIED looks to broaden its network to different Universities and early career researchers this is to be expected but comes with additional resource requirements for the team which must be considered.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Targets were revised in line with the accelerated IEP spend.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There has been good progress against the previous recommendations, with outputs clearly of use to policy makers, with a good mix of longer research papers alongside shorter policy papers for senior readers. Dialogue with GoSA stakeholders has been somewhat informal (ie no IEP Steering Committee) but the programme has navigated this well to retain relevance, e.g. through high-level dinners.

Looking forward, there remains a fine balance to be struck between flexibility and mission creep. Thus far, the preference for flexibility has allowed IEP to respond to GoSA priorities very effectively. However, where IEP work is delivered by non-consortium partners, e.g. the work on Rail Reform, it is more difficult for the DNA Economics team to ensure its quality and timeliness which presents additional risks. These risks must be owned and managed by the BHC and therefore this delivery channel should be used only for very high impact activities.

Output Title	An active dialogue among UK, SA and other stakeholders to inform economic policy generation and prepare for RBIS discussions
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of formal engagements (roundtable events, study group meetings, webinars) delivered on relevant policy topics.	22 (SA-TIED) + 11 (IEP)	27 (SA-TIED) + 21 (IEP)

Briefly describe the output’s activities and provide supporting narrative for the score.

Both components, especially IEP, substantially over-performed their targets this year.

IEP
This year, IEP pivoted to hosting hybrid events, which combine in-person and virtual participation, as opposed to exclusively in-person or online formats. Hybrid events offer several benefits: they help contain costs associated with travel, venue hire, and accommodation, while simultaneously enabling broader participation from both local and international experts and networking for those in person. Exclusively in-person events were reserved for events that require focused and immersive experiences for all the participants, such as some of the Gender and Informal sector workshops. This allowed IEP to reach an audience of 488 people, including almost 200 participants from GoSA.

The events covered diverse, policy-relevant topics including social protection (SRD grants), fiscal modelling, digital trade, G20 priorities, infrastructure investment, gender mainstreaming, and informal sector development. Content was generally well-received, with participants consistently rating insights from presenters highly (typically 4+ out of 5). The gender mainstreaming and informal entrepreneurship workshops were particularly effective at shifting participant perspectives, with 68% of attendees reporting evolved understanding.

SA-TIED
In addition to workshops relating to individual workstreams, which had strong engagement, SA-TIED’s research seminar series was reinstated in 2024, providing a platform for engaging policymakers, researchers, and stakeholders in discussions on pressing socio-economic and fiscal policy issues. These sessions drew diverse participation from government institutions, academia, the private sector, and civil society, with attendance averaging between 80 and 120 participants per seminar.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Targets were revised in line with the accelerated IEP spend.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation around consistent and effective branding was reflected in the use of the ERSA website to host the research papers and to ensure these were presented in a consistent way, with DNA Economics providing consistent formatting of research produced. The website is available here.

One reflection from this review is the extent to which the IEP could or should look to engage in and shape public debate, which is often a critical aspect of policymaking and implementation. The main audience of the programme is and should remain policymakers, but the team should consider a more deliberate approach to public facing comms, whilst recognising that it may be unhelpful to publicly brand work as UK-funded.

Output Title	Provision of technical assistance to SA policy makers to improve engagement with economic policy debate
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
SA-TIED Papers co-authored with GoSA officials, % of total	19%	24%
Number of IEP technical assistance interventions to provide expert input into SA policy-making (IEP, cumulative)	5	6
Number of individuals engaged with capacity building initiatives / (SA TIED)	54	183
Papers co-authored by a South African female, % of total / (SA-TIED)	33	51.5

Briefly describe the output’s activities and provide supporting narrative for the score.

Both components of the programme have performed above expectations this year.

IEP
IEP Technical Assistance has focused on high priority areas, such as Operation Vulindela and the G20 Presidency. Other important workstreams included TA to update the Fiscal Rule report, and to convene stakeholder engagement sessions and develop the necessary inputs for the long-term fiscal model for the Budget Office.

SA-TIED
Technical Assistance from SA-TIED complemented the work of IEP. A significant focus of the SA-TIED TA was on macro-fiscal analysis and policy modelling. In a policy space like the National Treasury, where evidence-based decision-making is crucial, the continued efforts of developing dynamic stochastic general equilibrium (DSGE) and Computable General Equilibrium (CGE) modelling capacity is a top priority. DSGE models are essential tools for macroeconomic policy analysis, enabling policymakers to examine the dynamic effects of economic shocks, assess policy interventions, and understand the interplay between key economic variables over time. These models provide a rigorous foundation for designing policies that are both forward-looking and aligned with the broader economic framework.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two new output level indicators were added to better capture SA-TIED’s focus on working with female South African researchers, and IEP’s Technical Assistance.

However, some of the IEP work to mainstream gender is not adequately captured in this logframe. Given that the gender work has been a challenge for the IEP component of the programme, it is important to explore ways to capture this aspect of the programme in the logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The recommendation to build closer links with other activity within the BHC has continued well. A particularly strong example is the Spatial Economic Activity Data: South Africa (SEAD-SA) work which relies heavily on the Secure Data Centre.

Further revisions to the logframe may be considered to capture GESI aspects of the IEP programme and some additional SA-TIED work to build economic research capacity within South Africa.
## D: VALUE FOR MONEY

Key cost drivers and performance

The majority of project costs are in the provision of technical assistance, primarily through expertise and research provided to the government of South Africa to inform domestic and international economic policy. The VfM assessment remains similar to the previous annual review, which found that the programme offers strong value for money.

Economy – Both components of the programme continue to explore ways to reduce costs, for example through greater use of hybrid events and GoSA locations for events.

Efficiency – The policy focused work of the IEP is closer to economic consulting than the more research focused work of SA-TIED. However, both are highly efficient, making use of strong networks amongst global and local academia to deliver high quality outputs for low cost. The IEP component of the programme had a good year, allocating 62% of working days to technical experts, above the 50% benchmark.

The ratio of overhead and management costs to output costs has been below those agreed in the initial contract for IEP, delivered by DNA Economics. Programme leadership, management, support and administration costs were agreed at 18.4% in the original proposal, but for the year under review have come to a total of 12% of total costs.

Effectiveness – Previous sections of this Annual Review cover and confirm that IEP is an effective programme which is delivering high quality and relevant inputs to high priority areas of policymaking in South Africa. The focus on engaging senior decision makerxs within the Government of South Africa who lead on key areas of economic policy making in both domestic and international policy allow the programme to ensure technical assistance is well targeted and focussed on the most pressing policy debates where evidence is most needed.

Equity – Both projects within the programme have diversity-related targets to improve equity outcomes of the project. SA-TIED has
.

	Target	2024	2025	2026
Economy / Percent of costs which are not programme costs	18.4%	9%	12%
Efficiency / Share of work days allocated to technical experts	50%	65%	62%
Effectiveness / Share of survey respondents agree that IEP has informed policy making	60%	No data	82% (domestic policy) / 45% (international policy)
Equity / Share of activities with early GESI input	75%	22.2%	23.2%

Assessment of whether the programme continues to represent value for money

Overall the project represents strong value for money given the relatively low cost of providing technical expertise and the large impact of tackling key economic policy challenges. The close work with government helps maximise the impact on policy development.

Beyond the direct impact of support to policy makers, the close work with officials has helped ensure the work of other parts of the High Commission are closely aligned with government priorities, providing a platform to engage with key stakeholders on other development and policy priorities.

E: RISK

Overview of risk management
Risks to project delivery, as identified through the project risk register, have generally fallen over the past year. Risks remain within the risk appetite as set out in the FCDO’s risk appetite statement. Regular conversations with project implementers, monthly in the case of SA-TIED and bi-weekly in the case of IEP, allow for a close monitoring of existing and emerging risks. Significant risk changes throughout the year are listed below.

Programme-wide
A key risk to the programme identified for the previous year was GoSA engagement with the IEP project as it moved to delivery, and potential changes in policy direction following South Africa’s general election. This risk has not materialised and indeed the IEP project has strengthened engagement with different parts of GoSA, most significantly NT and the Presidency, but also DITC, SARB, and National Planning Commission.

For the remainder of 2025, the lack of GoSA bandwidth arising from the G20 Presidency remains a both a risk and an opportunity for the programme where work funded by IEP can plug gaps.

SA TIED
The risk of low GoSA engagement with SA-TIED is very limited given the role of NT in funding and designing the programme. The structure of SA-TIED embeds GoSA engagement very effectively.

Instead, the main risk for SA-TIED has stemmed from the failure of NT to secure a new building following their move out of Madiba Street. This has seen staff work from home and posed a significant risk to the Secure Data Centre. Fortunately, a new secure home for the Secure Data Centre has been found which (alongside strengthened processes) effectively guard against risks of data breaches. This location also allows for the installation of a new server which will allow the Lab to incorporate additional data-sets and to expand access to more researchers.

IEP
The risk of limited engagement from key stakeholders in GoSA is a little higher for the IEP component. To date this risk has not materialised, due to the excellent networks and engagement of the programme director – and increasingly BHC staff – alongside strong demand from GoSA. However, the programme relies heavily on a small number of critical personnel so remains vulnerable to personnel changes on either the GoSA or programme side.

The main risk for IEP this year was limited bandwidth within the DNA Economics team to effectively manage the programme as it scaled up. In the first nine months of the year this led to excessive pressure on the programme director, reducing her capacity to deliver to her strengths. The recruitment of a dedicated Deputy Team Leader has led to significant improvements, as reported by all interviewees for this review.

Internal
A lack of project management support to the project within the BHC was flagged as a risk at the last Annual Review. This risk grew and increasingly materialised over the first part of the year, for example through the delayed revisions to the logframe. The recruitment of a programme manager (confirmed at the end of the review period) ought to reduce this risk going forward.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Project implementers have performed well, delivering agreed outputs on time and within budget. Reporting has been timely and informative, supplemented with informal updates reflecting close working between implementors and the FCDO, with regular catch-ups between project officers and implementing partners.

SA-TIED has spent £481,000 within the year, an uplift of the original budget as a result of agreed discussions between the BHC and UNU-WIDER to support greater public engagement and the delivery of an upgraded Econ3x3 platform.

IEP spend has also been higher for the year that initially forecast, with spend of £1,070,538. This represents a 45% uplift in the budget from previous targets. This decision was taken between the BHC and the implementing partner, reflecting strong uptake from GoSA on the technical assistance provided, and activity levels continue to be higher than that originally envisaged.

This acceleration in funding deployment will necessitate a reduction in the length of the programme from five to four years. Going forward a new business case should be developed to set out how the BHC will continue to support GoSA on high priority evidence-based policy making, with a focus on areas which are binding constraints to inclusive and green growth. The models of engagement developed by both SA-TIED and IEP are effective and should form the starting point for any such programme, whilst noting some of the risks to the model highlighted earlier including heavy reliance on a small number of excellent people. Consideration should be given to whether BHC is best placed to support GoSA on its international agenda or whether there are other more appropriate centrally managed programmes.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation
The BHC continues to hold regular conversations with programme beneficiaries within the GoSA to ensure the programme aligns with their priorities and to understand how the programme is informing policy debate. Whilst the G20 Presidency has constrained bandwidth for regular engagements this year, the demand for IEP support on critical issues demonstrates the ongoing usefulness of the programme for GoSA. Its flexibility and responsiveness and particularly helpful, as well as the close alignment with their priorities.

This Annual Review has been conducted by an external reviewer as recommended previously. Whilst challenges have been identified in this review, one of the most impressive aspects of the programme is that they have largely been addressed in year – for example, the SA TIED team finding a new secure location for the Secure Data Centre or DNA Economics’ decision to recruit a Deputy Team Leader to address programme management issues. This speaks to both the strong engagement from the BHC and the proactive and solutions-focused programme partners.

The reporting cycles of both IEP and SA-TIED remain misaligned. In future programmes this should be addressed.

Evidence
Evidence based policy making is the core of both SA-TIED and the IEP. Whilst it is too early to fully evaluate the impact of the policy changes informed by their work, it is clear that the programmes both contribute to and benefit from a strong culture of evidence with GoSA, especially within the National Treasury. The work of the Secure Data Centre under SA-TIED is a particularly strong example of how the quality of evidence generated by the programme and how it links to policy development.

Learning
The programmes have a strong learning culture, especially SA-TIED through its capacity development work. The role of Research Analysts is a strong point of the programme, building capacity both within the National Treasury and the wider community. Efforts to make these trainings more efficient would be valuable.

IEP also takes steps to ensure timely learning, including through the use of Post Event Surveys. These typically showed that the work was well received, especially the quality of insights from participants which rated consistently above 4 out of 5. However, the engagement rates for the surveys was a little on the low side (17-44%). This can partially be explained by limited GoSA bandwidth, but strengthening the mechanism for feedback on events would also be valuable.

Date of last narrative financial report	July 2025	Date of last audited annual statement	July 2025