## Annual Review Template

Title: Bangladesh Climate and Environment Programme (BCEP)
Programme Value £ (full life): £120 million		Review date: 12 Mar 2026
Programme Code: [AMP ID#] 300991	AMP start date: 31 Jan 2022	AMP end date: 31 Jan 2030

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	B	A	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300991/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300991/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Bangladesh Climate and Environment Programme (BCEP) aims to strengthen climate resilience and accelerate emissions reduction in line with the UK–Bangladesh Climate Partnership. The programme supports Bangladesh, which remains acutely vulnerable to climate-related hazards, by working on locally led adaptation efforts that incorporate nature‑based solutions and show strong potential to strengthen community resilience and addresses technical and policy barriers to deploying renewable energy technologies can accelerate green growth. BCEP contributes to the Government of Bangladesh’s National Adaptation Plan (NAP) and Nationally Determined Contributions (NDC), as well as to the UK’s commitment to provide £11.6bn in international climate finance (ICF) between 2021/22 and 2025/26. The programme supports progress towards SDG 7 (Affordable and Clean Energy), SDG 11 (Sustainable Cities and Communities) and SDG 13 (Climate Action). BCEP also remains an integral part of the UK’s climate diplomacy in Bangladesh, strengthening partnerships with key government counterparts on locally led adaptation, environmental governance and the energy transition.

This Annual Review covers the period 1 April 2025 to 31 March 2026 - a year of transition shaped by reduced UK ODA, a refreshed UK development approach, and delivery under an Interim Government. Throughout the year, the programme continued delivery primarily through its two largest and most established components: NABAPALLAB, implemented by a CARE‑led NGO consortium, and the partnership with the Global Centre on Adaptation (GCA). Two newer components launched in 2024 also progressed—the Eco‑Leaders youth programme delivered by The Earth and a renewable energy technical assistance project delivered by WEglobal. In addition, two small projects were initiated: a hydro‑met partnership to strengthen Bangladesh’s flood‑forecasting capacity, implemented by RIMES with support from the UK Met Office, and a climate‑finance scoping study for the Economic Relations Division, implemented by DAI with NAICOM.

During the review period, the programme underwent significant adjustments to its delivery model and overall resourcing as a result of ODA reductions and the refreshed UK development approach. This included decisions to:
- not extend funding for the GCA component after FY 2025/26;
- close the SOAS research project before it moved beyond inception;
- terminate the WEglobal contract; and
- pause selected NABAPALLAB activities, reducing the overall scale and budget of the component.
These changes required the programme to refocus resources, adopt a revised delivery plan, and set new results targets that reflect the tighter budget environment. Consequently, the findings of this Annual Review capture a programme in transition—maintaining delivery in priority areas while adapting to a materially altered funding and operating context.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
Summary supporting narrative for the overall score in this review

The programme has maintained strong overall performance during a year of transition, with the main components continuing to deliver outputs at A and progress against outcomes despite reduced ODA and re‑scoping of delivery. It remains on track, with solid results from core partners and a tighter, more focused portfolio following the closure of weaker or lower‑performing elements. These management decisions have strengthened programme coherence and ensured resources remain concentrated on areas delivering the greatest impact, justifying the overall score.

Major lessons and recommendations for the year ahead

- Business Case addendum is required to reflect recent changes, including the closure of components and increasing emphasis on climate finance and technical partnerships.
- Revise the Theory of Change in Spring 2026 to reflect the streamlined programme structure, updated assumptions and the adjusted delivery model. Review assessing the programme’s impact indicators to ensure that these are measurable and have clear milestone targets.
- Strengthen measurement of adaptation impacts on women, youth and marginalised groups by, where feasible, requiring partners to report disaggregated data and embed proportionate Gender, Equality and Social Inclusion considerations within monitoring and evaluation systems.
- Strengthen the Value for Money framework, addressing gaps carried over from the previous Annual Review and internal audit.
- Encourage delivery partners to provide structured feedback on policy and regulatory barriers that could unlock progress beyond project‑level work.
- Explore opportunities to connect BCEP’s gender‑inclusive adaptation work with GoB gender–climate priorities where there is a natural fit and partner capacity allows (e.g., selectively sharing lessons from community‑level adaptation to inform relevant NAP or Climate & Gender Action Plan discussions).
- Capture lessons from closed components during the ToC updates, to prevent repetition of delivery risks in future programming.
- Strengthen political‑economy analysis and demand validation before launching major technical assistance to ensure durable government buy‑in.
- Ensure safeguarding and risk‑management processes are fully aligned across all partners from the outset.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change for BCEP was developed as part of the programme’s design process in 2022. The overarching intended impact set out in the ToC is to deliver a more climate resilient, less carbon-intensive, and cleaner Bangladesh, and this was initially supported by 8 outcomes. In practice, delays and changes in ODA budget finalisation meant that only one component was fully operational by the time of the first Annual Review, and it was recommended that the ToC should be revised to reflect a more targeted focus. This revision maintained the original impact statement and reduced the outcomes to: Vulnerable communities and ecosystems better able to cope with current climate impacts in the short and longer term; Greater investment, knowledge and leadership for climate action in Bangladesh; and Technologies and policies are in place and tested that support expansion of renewable energy.

These changes at the outcome level were made in September 2023 and the revised ToC determined that the impact statement could still be achieved through revised outputs under these outcomes. This continues to be the case, and the ToC remains valid for this AR’s reporting period. However, an in-depth review of the ToC will be completed in 2026 to reflect new programming changes and test the underpinning intervention logic.

At the output level, several adjustments have been made over the last year to reflect changes in the programme’s components, for example adding ICF output indicators (output 2.4 and 2.5), enhanced flood forecasting through shortened systems, skills and knowledge sharing for RIMES (output 5.1, 5.2, 5.3), strengthen government to better access and utilise climate finance and the removal of the component delivered by SOAS.

The programme is continuing to adapt to changes in context, particularly in response to reductions in funding and key shifts in the UK’s approach to development. The ToC will be revised in Spring 2026 to ensure that any changes in delivery and programme focus are still underpinned by robust logic, and that the assumptions underpinning these have been tested. As part of this process, the programme team should review the logframe to reflect any changes. This should also involve assessing the programme’s impact indicators to ensure that these are measurable and have clear milestone targets.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

BCEP remains on track to deliver its impact and outcomes. CARE, the largest BCEP partner, has achieved two outcome milestones for the review period, as evidenced by its annual outcome assessment. GCA, the other major partner, has met all three outcome targets as evidenced in the independent Impact Evaluation submitted in March 2026. The smaller partners, including two newly mobilised ones, have also successfully met their output targets and further strengthened progress toward BCEP outcomes. The discontinued work on climate research and renewable energy has had minimal effect on the overall achievement of outcomes as both projects were in inception phase.

The programme uses an integrated approach combining locally led adaptation, nature-based solutions and renewable energy to support people’s ability to cope with climate and nature shocks and stresses (such as flooding, cyclone and salinity). CARE’s annual assessment indicates that the programme is on track to deliver its expected outcomes: (i) 270,972 climate vulnerable people have improved their climate resilience, and (ii) 22,288 people have gained improved access to clean energy and diversified their livelihoods, reducing pressure on local ecosystems.

Bangladesh Water Development Board (BWDB) has virtually inaugurated its upgraded Flood Forecasting Operational Centre, developed following a UK study visit hosted by the UK Met Office and strengthened through technical support from our ongoing Hydro‑met collaboration.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Based on the analysis of outcome and output achievement, theory of change and VfM, there is evidence that the programme should be continued as it makes a significant contribution towards the FCDO Climate and Nature priority forming part of the Country Business Plan for BHC Dhaka.

## C. DETAILED OUTPUT SCORING

Output Title	Support ecosystem-based adaptation in communities living adjacent to ecologically critical areas (Sundarbans and Hakaluki Haor) - CARE
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of people supported to better adapt to the effects of climate change	314,810	358,982 / Moderately exceeded expectations. Strengthened climate‑resilient livelihoods through climate‑smart agriculture, resilient WASH and renewable energy, and expanded LLA across 28 Union Parishads and 5 companies.
1.2 Area under sustainable management practices (ha)	5,468	5,940 / Met expectations. Scaled nature‑based solutions through community forestation, natural regeneration, canal re‑excavation and sanctuary protection.
1.3 Number of community groups and GoB Agencies engaged in protection and restoration activities in the Sundarbans and Hakaluki	84	90 / Met expectations. Broader engagement in restoration activities, with stronger community influence in ECA committees and approval processes.
1.4 Number of households supported with climate resilient houses and other infrastructures (Adaptive).	12,705	13,276 / Met expectations. Also Improved access to resilient housing and public infrastructure, supported by training 140 carpenters and masons.
1.5 Number of households received relevant/ tailored climate information services	70,725	79,102 / Moderately exceeded expectations. Households received tailored climate information through regional forums and hydromet collaboration, helping them adjust livelihoods such as crop calendars.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output aims to increase the climate resilience of vulnerable communities and support the protection and restoration of two Ecologically Critical Areas (ECAs). The programme has taken a locally led adaptation approach and nature-based solutions to maximise benefits for people and ecosystems. Prior to implementation, the programme undertook 5 sectoral studies (Renewable Energy, WASH, Mud Crab, Climate and Weather Information, and Inclusion) to: (i) refresh technical intervention design, (ii) identify relevant government and private sector stakeholders, and (iii) develop an implementation strategy.

Overall the output has met expectation, making strong progress promoting climate resilient and nature-positive livelihoods and renewable energy, engaging community groups, GoB agencies and private sector companies, advancing LLA across 28 Union Parishads, supporting climate resilient houses and infrastructure and WASH, providing information on climate services, and having a high improvement in the area under sustainable management practices - a total of 162,613 saplings were planted to restore and protect mangroves, and 21 km of canals were re-excavated to store fresh water for aquaculture and crop production and in dry season. The programme’s monitoring, evaluation and knowledge partner C3ER (Centre for Climate Change and Environmental Research) completed its annual survey using a robust design and sample to assess progress. During a joint visit in May 2025, BHC’s Internal Audit Department and the BHC Climate Team observed that the programme was already delivering positive results, protecting highly climate‑vulnerable communities and mangrove ecosystems while supporting improved livelihoods.
The output has adopted a phased implementation approach. This has enabled adjustments in scale in line with ODA allocations and allowed the technical design and delivery model to be refined through adaptive management. Under this approach, implementation began in the southwest in April 2024 and expanded to the northeast in September 2025, at a reduced scale and in collaboration with the Ministry of Environment, Forest and Climate Change (MoEFCC) and local administration. Going forward the output is shifting from service delivery to a knowledge‑driven policy partnership and systems‑strengthening approach that enhances scale, cost‑effectiveness, and sustainability. It is reprioritising activities to focus only on interventions that are scalable, locally led, aligned with the political economy and government priorities, and commercially viable for private‑sector engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The programme has delayed its implementation in the northeast Hakaluki Haor ecosystem and reduced its scale to align with revised ODA allocations. Consequently, milestone targets for all output indicators have been adjusted.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The programme has taken concrete steps to address all recommendations from the last Annual Review. It has finalised the stakeholder engagement and policy advocacy strategy, informed by the political economy analysis, and developed a comprehensive climate and weather information dissemination mechanism and service delivery network as outlined in the technical proposal.

Lessons:
LLA approach has enhanced communities’ engagement with local government, and this collaboration has helped embed LLA activities within government’s annual development plan and budgets at union level, strengthened engagement with UNOs, LGIs and technical departments to accelerate site approvals and institutional integration. There was mixed experience of CARE increasing engagement with technical government departments and strengthening GoB buy in for future transition plans.

Recommendations:
- The programme is transitioning from service delivery to a knowledge‑based partnership focused on policy influence and technical assistance to ensure scale, cost‑effectiveness, and sustainability. The CARE Consortium needs to finalise the transition strategy and begin implementation by April 2026.
- The CARE Consortium needs to align the Theory of Change, results framework, and VfM strategy with the transition approach and revise these documents by July 2026.

Output Title	Influence the design of investments to take greater account of climate risk and adaptation - GCA
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of infrastructure resilience advisory packages developed or launched with support from GCA	6 CRAs completed & / 1 Urban Masterclass delivered	Met expectations: Completed CRAs for 6 secondary towns and delivered an 1 urban resilience masterclass, alongside national workshops on nature‑based solutions. Organised a National Dissemination Workshop and a three‑day workshop on Enhancing Coastal Resilience.
2.2 Number of Concept Notes and Funding Proposals (FPs) submitted to GCF, Adaptation Fund or other climate investment fund supported by GCA	2 CNs and 1 FP support provided	Met expectation: GCA delivered support for 2 Concept Notes and1 Funding Proposal, including an US$ 80m GCF CN for PKSF now cleared for submission, a Funding Proposal on climate‑resilient coastal forestry for IDCOL, and a CN on solar‑powered irrigation for drought‑prone areas.
2.3 Number of Locally Led People's Climate Adaptation Plans completed	3 PCAPs completed	Met expectation: Completed 3 People’s Climate Adaptation Plans (PCAPS) for Feni, Mirsharai and Laksam. Follow‑up is underway with IFIs and local government to progress priority solutions, and demonstration activities from the PCAPs reached 17,036 indirect beneficiaries across coastal and delta areas.
2.4 Number of people supported to better adapt to the effects of climate change as a result of International Climate Finance / ICF KPI 1	90 individuals	Moderately exceeded expectation: 100 individuals supported. The direct beneficiaries included central and local-level officials from the Local Government Division (LGD) engaged in climate‑resilient planning, budgeting, and mainstreaming, as well as academic institutions.
2.5 Number of individuals and organisations informed by International Climate Finance technical assistance / ICF TA KPI 2	25 organisations	Met expectation: 25 organisations informed by ICF TA. GCA supported climate‑risk mainstreaming across key IFIs (World Bank, ADB, AIIB, AFD) and government bodies including LGD and BPATC, through technical engagement and workshops.

Briefly describe the output’s activities and provide supporting narrative for the score.
GCA delivers this output by strengthening locally led adaptation, promoting nature‑based solutions and improving access to adaptation finance through advisory support to IFIs and government. Over the year, it provided technical inputs to major infrastructure and urban projects, supported climate‑finance proposals, and advanced PCAPs. Its work focused on systemic influence-embedding climate‑risk management in national and local planning while demonstrating practical community‑level solutions. These improved resilience planning and institutional capability across multiple levels of government.

Overall, the output has met expectation: four indicators met expectations and one indicator moderately exceeded targets across advisory work, capacity‑building and ICF reporting. Delivery strengthened climate‑risk integration, supported access to sizeable adaptation finance, and advanced LLA approaches, though stronger emphasis is now needed on ensuring analytical tools and guidance are fully embedded in downstream investment decisions. Progress could also be enhanced by ensuring all downstream partners adopt safeguarding and risk‑management plans from the outset to minimise delivery risks. Engagement with IFIs remains positive, but more deliberate efforts would build institutional capacity in a sustainable rather than input driven manner. At the project’s outset, it was envisaged that this support would help establish a longer-term, internally sustained delivery route within IFIs themselves, reducing the need for continuing donor funded assistance; this remains a key consideration for the future direction of support.

While delivery continued to meet expectations, some operational and administrative processes were occasionally slower than anticipated. The organisation is not formally registered in Bangladesh, which presents ongoing delivery and administrative risks. The project will conclude in March 2026, in line with budget allocations and timelines set out in the Accountable Grant Agreement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output 2.4 and 2.5 on ICF KPIs have been added in the logframe in September 2025. The changes were added to better capture the ICF results as BCEP is a 100% ICF programme. These changes also address the recommendations of Internal Audit Report, May 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Since the last AR i) GCA continues to strengthen relationships with key ministries/agencies, including the Ministry of Finance, while keeping the MoEFCC closely informed of project activities. ii) GCA’s M&E strengthened by gathering evidence on how support to IFIs/ government translates into real-world impact and systemic changes and accordingly results indicators refined in September 2025. iii) GCA’s work remains firmly focused on systemic influencing e.g. any community-level engagement aimed to strengthen LLA approaches also facilitate linkages with relevant IFI projects.

Lessons:
i) Changes in the national political landscape can have significant knock-on effects on scaling up adaptation efforts. A contingency plan is therefore essential, though its effectiveness often depends on external factors beyond the control of partners. ii) Measuring climate adaptation benefits from large infrastructure projects remains difficult without a clear counterfactual and tangible benefits accruing outside the project period. iii) The long-term in-depth engagement with large-scale MDB investment projects provides an excellent platform for systemic and large-scale impact though it requires a significant upfront investment in time and resources to yield result.

Recommendations:
Support partners with best practice learning on operational issues.
Output Title	Support to address technical and policy challenges and gaps to encourage greater deployment of renewable energy - WEglobal
Output number:		3	Output Score:	C
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Provide TA to SREDA to enhance their knowledge, skills and capacity on selected renewable energy sectors	TAPP approved by the government	Substantially did not meet expectation TAPP not approved by the government
3.2 Number of individuals and organisations informed by ICF technical assistance on renewable energy	Number of individuals and organisations informed by ICF technical assistance on renewable energy	Substantially did not meet expectation N/A as TAPP not approved

Briefly describe the output’s activities and provide supporting narrative for the score.
This output aimed to address technical challenges and gaps so as to encourage greater deployment of renewable energy, through providing TA to the Sustainable and Renewable Energy Development Authority (SREDA). This output did not meet expectations during the review period. Although WEglobal implementation commenced in November 2024, the project was unable to achieve its primary Year 1 deliverable: obtaining GoB approval of the Technical Assistance Project Proposal (TAPP). TAPP approval is a mandatory regulatory requirement for any technical assistance programme in Bangladesh that exceeds a certain financial threshold, and the contract set a 12‑month timeline for securing government approval. By December 2025, 14 months into the contract, this milestone had not been achieved.

Alongside shifting government priorities and staffing changes in the Power Division and SREDA, which contributed to prolonged discussions on the TAPP. The project also encountered several internal operational challenges during inception. This included delays in submitting a complete TAPP package, gaps in budget information requiring multiple rounds of revisions, and some coordination difficulties between the lead contractor and the lead local subcontractor. These issues collectively slowed progress and contributed to uncertainty about how best to respond to government demand while remaining aligned with the contracted scope of work. The delays also created implications for the project’s forward spend profile, which became increasingly difficult to accommodate within the tighter ODA allocations and resourcing constraints expected in future years. In this context, a decision was taken to end the contract without default of the supplier, in line with the provisions of the agreement.

Changes to this output during the past year:
N/A.

Progress on previous AR recommendations, lessons learned, and recommendations:
Last year’s AR emphasised the importance of close coordination with SREDA and early government engagement to navigate the TAPP process. The delivery partner maintained regular communication with SREDA senior management; however, this was insufficient to secure timely TAPP approval.

Lessons learned:
- Political transitions can rapidly reshape the feasibility and demand for technical assistance, even where early groundwork is strong. Programmes dependent on government approval processes (e.g. TAPP) must account for political‑economy risks, shifting institutional leadership, and potential disruption. Future support will need continuous demand validation, early political mapping, and flexible design to remain viable through institutional change.
- Supplier‑subcontractor relationships are critical delivery risks that must be assessed and monitored throughout the inception phase.

Recommendations for the year ahead:
- Any future energy sector TA should adopt a modular, flexible design, allowing adjustments to scope as government priorities evolve.
- FCDO should review its supplier management approach to ensure stronger oversight of key personnel stability and subcontractor relations during inception phases.
Output Title	Youth trained and empowered to lead on climate action - The Earth
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Capacity building of youth for active engagement / in climate and environment issues and inputs to policy initiatives	100 youth trained on climate and environment management.	Met expectation: 99 youth trained on climate and environment management.

Briefly describe the output’s activities and provide supporting narrative for the score.
The Earth expanded delivery of the Eco‑Leaders youth training programme, equipping young people across Bangladesh with the knowledge, skills, and networks to lead climate action during its second year of implementation. During this period, four 3‑day Eco‑Leaders training programmes were delivered, each structured as two days of interactive learning and one day of facilitated networking, supported by a diverse group of experts from academia, government, civil society, media, the private sector and development partners. The programme maintained strong gender balance and reached youth from across Bangladesh, ensuring equitable access and broad regional representation.

Overall, the output has met expectations, and the Earth remains on track to contribute meaningfully to end‑of‑programme outcomes by strengthening youth capacity, confidence and visibility in national climate dialogue. Despite being a relatively small organisation and undergoing internal transitions, including changes in leadership, the Earth maintained delivery momentum and demonstrated strong commitment to youth engagement. The Eco‑Leaders initiative has begun to foster an emerging cohort of motivated young climate leaders, providing them with opportunities to test early ideas for community-based climate and environmental projects. The small‑grant support mechanism further enabled participants to pilot innovative solutions, helping them build confidence, leadership skills and practical experience essential for sustained engagement in climate action. The programme will continue this output by delivering new Eco-Leaders cohorts, strengthening training and small‑grant support, and establishing an alumni platform. The Earth will enhance follow‑up mentoring and ensure strong inclusion and links between youth-led ideas and national climate priorities

Changes during the past year and planned adjustments:
There were no formal changes to indicators or milestones during the year. However, internal organisational transitions, and political landscape of the country required minor adjustments to delivery timelines. Over the next year, the programme will refine its engagement approach, strengthen its network of technical experts, and set clear milestone targets for subsequent Eco‑Leaders cohorts.

Progress on recommendations, lessons learned and future recommendations:
Progress against previous recommendations has continued, with the Earth strengthening its training curriculum and establishing a national platform for youth engagement.

Key lessons:
Importance of early risk planning when working with smaller organisations undergoing internal transition, the value of diverse expert input in youth capacity‑building, and the need to maintain strong gender balance and inclusion to ensure equitable leadership opportunities.
Recommendations for the year ahead:
- The Earth should reinforce its organisational capacity, particularly in programme management, monitoring and stakeholder coordination and deepen collaboration with government and technical agencies so that youth-led ideas can connect more meaningfully to national climate and renewable energy priorities.
- To sustain momentum beyond the training cycle, the Earth should operationalise a structured alumni engagement strategy that keeps all participants connected and supported. This will help ensure youth remain empowered, engaged and connected throughout their climate leadership journey.

Output Title	Enhanced flood forecasting supported through shortened systems, skills and knowledge sharing – RIMES
Output number:		5	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Additional meteorological forecast datasets integrated into BWDB/BMD's modelling environment to produce multi-model flash flood guidance.	At least 2 meteorological data sets integrated and evidence of improved decision-making process through additional analytics and visualisation in the FFWC-Decision support system.	Met expectation. 3 meteorological data sets-dataset from BMD-WRF and UKMO (both deterministic and ensemble) were integrated in the Flood Forecasting and Warning Centre (FFWC) decision support system. Improved forecasting capacity by enhancing data quality and analytics at the FFWC. It integrated UK Met Office datasets into the FFWC data support system.
5.2 BWDB/BMD staff trained and applying advanced forecasting tools.	20 Staff trained with more than 70% participants reporting improved capacity in the post training survey.	Moderately exceeded expectation. 26 Staff trained with more than 80% participants reporting improved capacity in the post training survey.
5.3 Climate Application Forums (CAF) organised	Forums conducted (1 National + 1 Regional) with at least 25 organisations participating and 70% participants reporting improved forecast interpretation	Moderately exceeded expectation. / 2 Forums conducted (1 National + 1 Regional) and 64 organisations participated in these forums. 85% participants reporting improved forecast interpretation at national level and 71% participants reporting improved forecast interpretation. Established a national‑to‑local knowledge‑exchange mechanism for climate and weather information by strengthening the national Climate Application Forum (CAF).

Briefly describe the output’s activities and provide supporting narrative for the score.
Enhanced collaboration between the UK Met Office, the Bangladesh Water Development Board (BWDB), and the Bangladesh Meteorological Department (BMD) is significantly strengthening Bangladesh’s hydrological and meteorological forecasting systems. This partnership has moved from technical cooperation to full system integration, including the incorporation of UK Met Office and BMD WRF datasets into BWDB’s Flood Forecasting and Warning Centre (FFWC) operations—an important step in improving forecast accuracy, lead times, and evidence‑based decision making.

The programme provided capacity‑building support to BWDB and BMD officials, including a technical and policy exposure visit to the UK on advanced technologies, modern policy frameworks, and operational best practices. This support directly contributed to BWDB’s virtual inauguration of its upgraded flood‑forecasting operations centre, marking a significant improvement in national forecasting capability The programme also trained frontline technical staff from BWDB and BMD on advanced flood and weather forecasting systems, including impact‑based forecasting and nowcasting. This has strengthened their regional operations - for example, enabling the digitalisation of the forecasting system in southeast Bangladesh.

This output moderately exceeded expectation making substantial progress with strong government buy‑in and commitment from Bangladesh. It is a strong example of applying UK expertise and diplomatic engagement to deliver effective technical assistance and system strengthening. This collaboration was discussed in a meeting between the Honourable Adviser for the Government of Bangladesh Ministry of Environment, Forest and Climate Change and Ministry of Water Resources, and the UK Special Representative for Climate, in March 2025. It was subsequently presented in the UK Parliament as a good example of the UK’s development model and later formalised with the Government of Bangladesh. The collaboration also aligns with wider UK regional support through CARA and the Met Office’s WISER Asia Pacific programme, ensuring consistent technical standards across Bangladesh’s hydromet systems. BWDB and RIMES are jointly reviewing the interventions to consolidate learning and conduct a needs assessment, identifying priorities for further development and partnership beyond the current year, subject to budget and resource availability.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Lessons:
- A demand‑led and top‑down approach from the GoB was a key success factor for this technical assistance programme. It helped secure strong government buy‑in and commitment, leading to quick wins in hydro‑met forecasting systems that are also sustainable.
- UK expertise, combined with effective diplomatic engagement from both governments, helped elevate this technical collaboration and deliver high-performing results at pace.
Recommendations
- Sustain and expand UK-Bangladesh data‑sharing technical assistance, which is exceptional value for money. Build on the strong government demand and MoU to deepen UK technical cooperation, ensuring continued system integration, targeted capacity building, and application of advanced forecasting tools (nowcasting and impact‑based forecasting).
- Establish a national-to-local knowledge exchange mechanism for climate and weather information by strengthening the national Climate Application Forum (CAF) with BWDB and BMD, and by collaborating with development programmes (e.g., NABAPALLAB) and humanitarian actors (e.g., START Network, NGOs, and media).
## D: VALUE FOR MONEY

Key cost drivers and performance

The different components of this programme are at varying stages of implementation, the programme’s key cost drivers to date are associated with the more advanced components, adaptation and resilience led by GCA and CARE. Payments of £8,342,639 to CARE International UK represented around 76% of total costs in this reporting year. Their main costs included programme delivery, field office set up, staffing and equipment. Payments of £1,876,448 to GCA represented 17% of total costs in this reporting year. Their main costs related to programme delivery and staffing. The other three partners: the Earth, WEglobal, DAI, RIMES received payment of £710,649 representing the remaining 7% spend.

All partners have managed spend effectively and kept key costs within expectations. As the programme continues, key cost drivers will continue to be closely monitored.

VfM performance compared to the original VfM proposition in the business case

Economy: The GCA takes steps to reduce the operating cost in Dhaka, such as using office space within GoB’s Department of Environment; and using centrally managed services (e.g., HR, finance, procurement) provided by GCA HQ. CARE made some savings from implementation through reducing senior management staffing costs and sharing field-office set up with the partners and used it for programmatic purposes. However, the delayed mobilisation of projects accrued the benefits later than planned, disrupting planned timeline and milestones, causing losses in economic benefits forgone and missed opportunities.

Efficiency: The GCA and CARE are on track to achieve their milestone targets in the logframe, indicating that they are ‘spending well’ in terms of converting inputs to outputs. CARE’s consortium partners have long experience of working in Bangladesh particularly the local partners deliver programme on the ground with excellent understanding of local context.

Effectiveness: The GCA’s work with other large organisations, including the World Bank and Asian Development Bank, provides an opportunity to increase effectiveness and reach by influencing larger investments. CARE contributes to effectiveness by targeting the improved resilience of climate vulnerable people in the ecologically critical areas and conservation of biodiversity.

Equity: BCEP continues to advance equity through partners’ inclusive approaches, CARE’s targeting of women, adolescent girls, people with disabilities and minority groups where more than 60% of CARE beneficiaries have historically been women. The Earth enhances youth participation through its Eco‑Leaders programme under BCEP. The programme can take proportionate steps to strengthen the visibility of gender‑related results by progressively summarising, where feasible, women’s emerging benefits across resilience, services, livelihoods and leadership. Evidence from upcoming evaluations and improved monitoring systems will help build a stronger and more reliable gender results base over time.
Assessment of whether the programme continues to represent value for money

Cost-effectiveness: The programme continues to progress towards impact and represents value for money. Over the last year the programme has closed projects that were not contributing towards a high impact such as the support to address technical and policy challenges and gaps to encourage greater deployment of renewable energy. The programme is more narrowly focused than in the original Business Case, and remaining programme components will need to continue demonstrating evidence of positive VfM practice through reduced operational cost, well spent fund, greater reach and inclusive strategy but further analysis on impact is needed as the programme develops further. VfM strategies and frameworks will need to be developed to show cost effectiveness demonstrate VfM across the 5Es, CARE is developing a VfM Strategy framework for 2026/27.

E: RISK

Overview of risk management
The overall risk of the BCEP programme is rated as ‘moderate’ as all risks fall within BHC’s risk appetite. The programme risk register sets out mitigation measures and trigger points for escalation. This risk register is updated every quarter, in consultation with the partners and information gathered during field visits. BCEP partners maintain separate risk registers and report on risks in Quarterly Progress Reports.

A summary of main risks is set out below:
Policy and Programme Delivery Risks. Continued budget constraints will make it challenging to achieve all planned BCEP results within the remaining years. Mitigation measures include building internal skills around adaptive and flexible programming and early engagement with partners. BHC also strengthened its partnership with the interim government for uninterrupted programme delivery. Partners developed contingency plans for any anticipated instability around the National Election held in February 2026.

Safeguarding Risks. Instances of programme participants, particularly women and girls facing sexual exploitation, abuse or harassment by downstream partners or other stakeholders were identified primarily within the CARE project. This reflects its direct, service‑delivery model and close contact with beneficiaries. Other partners were assessed as lower‑risk due to the nature of their projects and more limited direct engagement with programme participants. e.g. GCA largely develops knowledge products, however evaluation finding suggests downstream partners safeguarding and risk management procedures could have been better aligned from the outset. In line with the internal audit recommendation May 2025 to improve on beneficiaries safeguarding reporting awareness, GCA and CARE have adopted enhanced reporting training through field workers. This is mitigated by partners having effective safeguarding policies in place, an assessment via Due Diligence Assessments (DDAs) and close monitoring. CARE has developed a safeguarding strategy in consultation with BHC.

Financial and Fiduciary Risks. The risk of BHC funds being misused due to fraud or corruption applies across all BCEP partners. Mitigation measures remain robust and aligned with the BHC’s zero‑tolerance approach to fraud. These include active fraud registers maintained by each partner, regular monitoring visits, and assessments of partners’ financial capacity through DDAs. Recommendations from DDAs are followed up on a quarterly basis. During the review period, seven fraud cases were reported by CARE. All have now been closed except for one ongoing case. Closed cases were either not proven or resulted in no financial loss to BHC.

Reputational Risks. Repeated ODA budget cuts may lead to loss of credibility with partners including the GoB, affecting the BHC’s bilateral relationship with the government. CARE received funding for the Northeast expansion in September 2025 against originally planned in April 2025 and had to follow a phased approach in programme area coverage. Mitigation measures include effective communication with the partners to help them adjust their workplans.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery: GCA and CARE are the largest BCEP partners and their delivery against workplan is on-track. Due to the budget constraints in FY 2025/26, CARE had to go through some revisions to the workplan such as a phased programme roll out. Overall, CARE adapted well and met the annual targets. GCA is in its final year of implementation and also met the delivery targets. Of the smaller partners, the Earth in its second year of implementation met targets while DAI Global UK Limited and RIMES had a one-off delivery target which they met successfully.

Commercial Performance: One MoU was signed with RIMES in September 2025 and one contract was signed with DAI Global UK Limited in August 2025. Both agreements ended in March 2026. The AG with SOAS University of London on collaborative climate research was discontinued since April 2025 following the inception phase. The contract with WEglobal for a Technical Assistance on Renewable Energy to SREDA was also terminated in March 2026 following a one-year inception phase.

Financial Performance: BCEP is a 100% ICF programme. Despite challenges partners utilised as planned over the review period except the two partners facing discontinuity. In line with the Accountable Grant, BHC disburses quarterly advance payments to GCA, CARE, the Earth, RIMES and arrears to WEglobal, a commercial supplier. GCA utilised £1,876,448 and CARE utilised £8,342,639 as planned over the review period. The remaining parters (WEglobal, the Earth, DAI and RIMES) utilised £710,649 as per the plan. Another £200,000 was channelled through BCEP from a Centrally Managed Programme to support a health TA project integrating climate adaptation into health systems, implemented by UNFPA. A thorough review is done before each payment is made to ensure the payment is not in advance of need. Asset spot checks were carried out for CARE BD in November 2025, GCA in January 2026, and the Earth and RIMES in February 2026, and no issues were identified.

In line with the signed Accountable Grants, CARE and the Earth submitted their Annual Financial Audit Reports for the period 01 April 2024 to 31 March 2025 in September 2025. GCA’s audit report was submitted in February 2026. The audit reports demonstrate satisfactory financial management practices by BCEP partners except GCA. GCA received a qualified opinion in the audit report for not obtaining a registration in Bangladesh resulting in major financial and reputational risks.

G: MONITORING, EVIDENCE AND LEARNING

The overall logframe for BCEP is used to monitor progress against outputs and outcomes on an annual basis. The output targets are revised in consultation with the partners and Results Adviser to enable capturing of the most realistic targets and bring more relevance to the achievement of programme objectives. The last logframe revision was carried out in September 2025 and resulted in several changes. To better assess overall programme progress and results, GCA added two ICF output indicators and two outcome indicators in the logframe. Some targets linked to CARE’s work on the Northeast intervention were also revised due to delays in BHC’s approval.

To supplement the partners’ own monitoring processes and to validate results, two field visits were undertaken for BCEP during the review period. One field visit was carried out in May 2025 to see the adaptation work in Mongla and Bagerhat district. Another field visit was carried out in December 2025 with the Development Director to see early inception phase adaptation work in Ecologically Critical Areas of Northeast Haor.

In line with BHC’s Inclusive Data Charter commitments, the programme has encouraged partners to disaggregate beneficiary data by key characteristics, noting the difficulty of doing so retrospectively. While partners are making progress, further improvement is needed. A 2025 internal review also urged BCEP to expand sex‑disaggregated data beyond female‑headed households and to report sex‑disaggregated results. Because women and girls face disproportionate climate risks, BCEP has prioritised inclusive interventions with strong potential for gender‑transformative impact. Additional work and upcoming evaluations will help assess outcomes for these groups.

An independent Impact Evaluation of GCA programme was submitted in March 2026 to assess the impact and sustainability of GCA’s work, and the programme team engaged closely with the evaluation provider to feed into this process. CARE has also planned a mid-term evaluation for September 2026. Both the evaluations will inform programme adaptation by providing an assessment of what has worked well and where there have been challenges in delivery. They will also capture partner efforts against Gender, Equality and Social Inclusion (GESI) issues.

BCEP partners have used learning and reflection to guide adaptation efforts. GCA strengthened field‑level capacity through LGED, supporting effective integration of adaptation measures, and its NbS compendium reflects diverse ecological regions to encourage wider uptake. GCA’s Climate Risk Assessments also advance NAP goals for a climate‑resilient economy. CARE’s learning processes shaped the transition strategy and prioritised key adaptation activities. Opportunities remain to better link BCEP’s policy influence with GoB gender–climate frameworks.

Date of last narrative financial report	CARE – 15 Feb 2026 / GCA – 17 Feb 2026 / The Earth – 15 Feb 2026	Date of last audited annual statement	CARE – 29 Sept 2025 / GCA – 17 Feb 2026 / The Earth – 29 Sept 2025