 CARA ANNUAL REVIEW

Title: Climate Action for a Resilient Asia (CARA)
Programme Value £ (full life): £274,000,000		Review date: April 2026
Programme Code : [AMP ID#] / 301000	AMP start date: 23/02/2022	AMP end date: 31/03/2031

Summary of Programme Performance
Year	2022	2023	2024	2025	26	27	28	29	30	31
Overall Output Score	A	A	A	A+
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003635.odt
DevTracker Link to results framework:	CARA LF (Published Oct 2025)

# A. SUMMARY AND OVERVIEW

Across Asia and the Pacific, climate disruption is evident and accelerating. Extreme heat, severe drought, toxic air, more intense storms and rainfall, rapid biodiversity loss and rising seas threaten the lives of over a third of the world’s population. Climate impacts undermine economic growth, destabilise supply chains, and fuel conflict, instability and distress-driven migration. These risks are intensifying. Yet, the global gap between adaptation needs and actual investment and implementation of measures to build resilience, remains vast.[1]
[1] Adaptation Gap Report 2025 | UNEP - UN Environment Programme

Climate Action for a Resilient Asia (CARA) is the UK government’s key climate adaptation programme building resilience across South Asia, Southeast Asia and the Pacific islands.

## Description of programme
CARA is designed to achieve and sustain impact at scale over the medium to long term – operating across all ODA-eligible countries in South Asia, Southeast Asia, and the Pacific, and deploying tailored solutions for this vast region at risk. CARA works with governments, regional institutions, cities, vulnerable communities, and the private sector to: (i) increase the resilience of economies and vulnerable communities to climate change, (ii) improve the health of natural ecosystems; and (iii) promote low carbon growth.
Seven interlinked components, delivered through five main implementing partners, combine Technical Assistance (TA) with capital investments to tackle the full scale of the adaptation challenge. Overall, CARA’s unique selling points lie in its geographic breadth as well as sectoral depth, and its regional approach.

1. World Bank (WB) – Resilient Asia Programme (RAP) – to strengthen climate resilience through better climate change policy, planning, and investment.
2. International Centre for Integrated Mountain Development (ICIMOD) – Himalayan Resilience Enabling Action Programme (HI-REAP) – to support scaling of Nature-based Solutions for more resilient livelihoods and ecosystems and to improve air quality across the Hindu-Kush-Himalayan (HKH) region.
3. United Nations Development Programme (UNDP) – Climate Finance Network (CFN) – to provide technical assistance to governments on innovative climate finance approaches and mainstream climate change into governance and public financial management.
4. The UK Met Office – Weather and Climate Information and Services (WISER) - Asia-Pacific – to improve people’s resilience to weather extremes and climate change with enhanced weather and climate information.
5. Asian Development Bank (ADB) – Community Resilience Partnership Programme (CRPP) – to scale-up investments in climate adaptation at the community-level, that explicitly address the nexus between climate, poverty, and gender.
6. ADB – Urban Resilience Trust Fund (URTF) – to support resilience projects and build the capacity of cities and urban agencies, communities, and private sector entities to integrate climate resilience into their policies and planning as well as rolling out large-scale resilience investments.
7. Local Level Adaptation Fund (LLAF) – demand-responsive fund managed by the FCDO to enable UK Embassies and High Commissions across Asia and the Pacific to respond to what countries need to build climate resilience and support emerging priorities and work increasingly alongside local partners including civil societies on climate adaptation.
## Summary of key achievements over the review period.

CARA has achieved an overall score of A+ in this Annual Review, which is defined as ‘Outputs moderately exceeded expectations.’ The review team scored the outputs strictly based on the evidence of what has been delivered by December 2025, against the set output milestones. In addition, the review took account of the delivery context over the past year, including budget uncertainty, the extent to which CARA implementing partners were able to absorb and deploy funding at pace, and organisational-level changes within the FCDO and across implementing partners.
Outlined below are some of the top results from this year of the programme by component stream. Thematically, this year, CARA has increased climate finance for adaptation, mobilising a total of $6.8 billion in climate finance through a combination of linked, additional, and leveraged finance – this is the first time CARA has reported this result. CARA has improved both regional and country-specific hydro-meteorological services; increased meaningful cooperation across the Hindu Kush-Himalaya region, including on air quality and water management; unlocked financing for infrastructure, rural resilience and transport projects across the region, and fostered GEDSI and improved reporting for climate adaptation projects across the board – something it can continue to do over the next few years.
### Top results by component stream:
CFN functions as a catalytic policy and financing platform that enables governments to move from ambition to bankable, investable financing frameworks for climate action. Working through UNDP's strong country and regional architecture, this year, CFN has:
1. Supported national and regional climate finance strategies. This includes adoption by the cabinet of Sri Lanka’s National Climate Finance Strategy (2025–2030)
2. Widened engagement with domestic capital markets. In Bangladesh, CFN supported conditions for green bond issuance, which provides the flexibility and structures required to leverage private financing
3. Expanded private sector engagement and blended finance mechanisms, launching the multi-partner Climate Venture Scaler, a regional pipeline-building initiative to accelerate growth-stage climate ventures across Southeast Asia.
4. Advanced multi-window financing mechanisms such as the Pacific Resilience Facility (PRF) to mobilise finance from a range of stakeholders.
WISER Asia-Pacific (AP) is informing the decisions farmers make, the warnings governments issue, and the systems that national meteorological services use – across three large sub-regions simultaneously. The programme moved from inception to implementation: core regional partnerships were established, multi-year activities were developed, and delivery progressed well across all Asia and the Pacific.
1. Through the partnership with CIMMYT, approximately 860,000 farmers received early warning alerts on wheat disease across Bangladesh, Nepal and Bhutan. Of these, 780,000 changed their behaviour by adjusting cultivation practices, applying fungicides appropriately, and switching to resistant crops – this equates to 90% of the people contacted taking action.
2. WISER-AP helped strengthen the weather-and-climate information value chain by co-producing impact-based or risk-based services with partners, building sustained institutional capability, and ensuring inclusive uptake and use of services for resilience decision-making – in both South Asia (via SAHF), in Southeast Asia (via the AHA Centre and MRC) and the Pacific regions (via SPREP)[2]
  [2] WISER’s delivery model in Asia-Pacific is driven by regional partnerships. SAHF is the South Asia Hydromet Forum (SAHF); AHA Centre is the ASEAN Coordinating Centre for Humanitarian Assistance on disaster management; MRC is the Mekong River Commission; and SPREP is the Secretariat of the Pacific Regional Environment Programme.
RAP links trust-funded technical work to a large pipeline of World Bank operations and uses the Bank’s convening power to strengthen regional cooperation on cross-border risks that no single country can tackle alone.
1. The World Bank enabled more effective transboundary air quality cooperation across the Indo-Gangetic Plain–Himalayan region. For example, RAP-supported dialogues led to agreement among countries on a shared roadmap and targets for reducing air pollution – this is also a strong example of cross-CARA coordination as the World Bank has been working in partnership with ICIMOD and the ADB for air quality management (AQM)[3].
  [3] AQM is the coordinated use of monitoring, evidence, policies, and targeted emission-reduction actions—often across sectors and national borders—to reduce harmful air pollutants, protect human health, and deliver climate and development co‑benefits at local, national, and regional scales.
2. In India, RAP analytics shaped World-Bank lending operations in Bihar Haryana and Uttar Pradesh (approved in December 2025). In Bangladesh, RAP’s evidence directly informed the National Air Quality Management Plan and played a critical role in shaping the World Bank–financed Bangladesh Clean Air Project, leveraging US$290 million in investment.
3. RAP has demonstrated strong traction in mobilising and shaping large‑scale World Bank investments for climate adaptation, with links to 16 operations[4], worth about US$3.49 billion.
  [4] 10 active, 2 completed, and 4 pipeline projects
URTF demonstrated strong delivery momentum and catalysed large-scale climate‑resilient investment in infrastructure, transport and solid waste management across Asia and the Pacific. With a total portfolio of $48 million, URTF has helped unlock over $1.02 billion in downstream financing.
1. Three new projects alone leveraged more than $709 million—including $241.7 million in Bangladesh for the Khulna Water Supply Project, $317.6 million for Cambodia’s Liveable, Resilient & Water‑Secure Cities programme, and a planned $150 million ADB loan in Nepal for river-related support, demonstrating URTF’s effectiveness in shaping bankable, resilience‑focused pipelines at scale.
2. URTF-supported events and forums strengthened partnerships with national governments, British Embassies, and other partners including UK institutions (such as UK universities, Clean Air Fund, Ricardo and Arup).
CRPP has demonstrated momentum in scaling pro-poor, gender-responsive, community-level adaptation through government systems, particularly in Southeast Asia.
1. Two large investment projects approved by the ADB in 2025 used funding from the CRPP Trust Fund (CRPPTF) to design and prepare loans/investments or implement specific adaptation interventions. These include: the Green Primary Care Project (Lao PDR $41 million); and the Building Resilience and Reducing Rural Poverty Project (Lao PDR).
2. The programme also made significant progress at the policy level – the Cabinet approval of Bangladesh’s ‘National Framework for Locally Led Adaptation’, plus revisions to Bangladesh’s ‘Employment Generation for the Poorest’ guidelines that expand climate-resilience functions and strengthen provisions for women’s participation and digitised payments. CRPP technical assistance contributed to the Bangladesh’s new LLA framework through targeted research, structured consultations, and sustained dialogue with government officials and development partners, helping to build collective ownership around the framework.
HI-REAP built on earlier work on water security, Nature-based Solutions (NbS), air pollution and addressed gaps in the entrepreneurial ecosystem of the Hindu Kush Himalaya (HKH)[5] around nature‑based, climate‑resilient business models in the last one year. Implemented by ICIMOD, which is a neutral, intergovernmental convenor for eight countries[6] in the HKH region, the institution is South Asia’s only functioning regional body that plays a critical role in water security, air pollution, and conserving ecosystems. The HI-REAP programme bridges a complex geopolitical landscape by translating shared science and evidence into joint policies and programmes. For example:
[5] HKH includes 8 countries and is the source of 10 major Asian river systems (Afghanistan, Bangladesh, Bhutan, China, India, Myanmar, Nepal, and Pakistan).
[6] Bhutan, Bangladesh, Nepal, India, Pakistan, Myanmar, Afghanistan, China
1. HI-REAP has achieved progress towards addressing water insecurity in the HKH region by scaling-up the revival of drying springs through Nature-based Solutions, especially in Nepal and India.
2. Evidence shows that HI-REAP's support to 41[7] business enterprises on climate-smart solutions has helped generate larger investments, create jobs, build resilience, and foster innovation in the region. HI-REAP's grant funding served as a catalyst for entrepreneurs to secure follow-on investment from other sources.[8]
  [7] 12 from HI-REAP's HKH ICE-Phase 1; 20 startups received seed funding and guidance through Green, Inclusive, and Resilient Entrepreneurial Ecosystem (GIREE); 9 enterprises supported through incubation and acceleration programme in Bhutan through GIREE.
  [8] For e.g. Mangala Herbaceuticals securing USD 0.5 million loan, and Khaalisisi partnered with Google to convert waste into reusable and recyclable products.
CARA’s Local-Level Adaptation Fund (LLAF) spans projects covering ecosystem restoration, climate risk governance, sustainable livelihoods, innovative finance, and policy support, but have, in all cases, been co-developed with UK Posts in response to adaptation and resilience gaps not covered by other CARA work in countries, but complementary to it, and with potential to scale. So far, 14 LLAF projects have been completed, and an additional 34 projects are ongoing (see Annex 3). Although they all have relatively modest funding and short timelines, these projects have contributed to CARA’s outputs and outcomes to date. The activities under this component have generated momentum for policy-level changes, improved knowledge and capacity among participants, and have already shaped decisions, strengthened local capacity, and laid the foundations for long-term adaptation. Key examples this year include:
1. The FAO project in Thailand developed guidelines on Climate-Smart Agriculture (CSA) and built the capacity of Thai government officials, enabling them to integrate climate change adaptation priorities into local planning and implement provincial plans. The guidelines will be adopted nationwide by PoNRE[9] offices and help local agencies design CSA project proposals for fiscal budgeting and climate finance applications.
  [9] Provincial Office of Natural Resources and Environment
2. With the State Government of Tamil Nadu (via World Resources Institute), CARA has established the first Heat Resilience Centre for an Indian state to coordinate multi-sectoral initiatives on heat and access funding at scale for building resilience, launched by Minister for the Indo-Pacific Seema Malhotra in November 2025. This could provide a model for other states in India and beyond.
## Summary supporting narrative for the overall score in this review
Given CARA’s complexity and the challenging operating context, overall programme risk remained Major throughout 2025, but stable and within risk appetite. Delivery across seven components was strong in 2025–26, with resilient partners, timely reporting, effective oversight, robust commercial performance, and audited financial assurance despite budget reductions over the years. In addition, the team took several actions over the course of the year to steadily improve risk mitigations and reduce several risks.
Due to these actions, the CARA team assess that, for the FY 2026-27, the overall risk profile of the programme is better reflected now by a Moderate assessment, rather than Major. During FY 2025-6, the actions taken to reduce risks included:
- Reducing residual (Public service delivery and operational) risks, due to strengthened programme management controls, closer partner and post engagement, improved financial oversight, enhanced MEL systems, and clearer communication.
- Political volatility, and ODA‑related financial risks persist, although several have eased following the programme’s official extension to 2031, clarity over the next three years of budgets, and improved re‑forecasting.
In addition, fiduciary and safeguarding risks remain Moderate to Low.

Major risks are likely to persist throughout 2026-27. The most significant of these are:
- External – geopolitical risks, due to political instability in several regions (Russia-Ukraine, and the Middle East wars) and their knock-on effects on global supply chains, economies and politics, and
- Internal, operational – the ongoing restructuring of the FCDO and related staff/resource cuts and slowness of internal operating systems.
The CARA team is able to manage the impact of external risks to a certain extent through increased preparation, by regular discussions with IPs and the development of differing/contingency scenario plans and budgets. The internal risks remain, but several changes to the CARA team’s resourcing in 2025-26 have now completed (including loss of some staff) and so we expect this risk to reduce somewhat in 2026-27 or remain stable.

All this has led to CARA overall programme risk moving from Major to Moderate in the current FY.
## Major lessons and recommendations for the year ahead
Building on lessons and recommendations from the last CARA Annual Review 2024/25, the CARA team has strengthened the programme’s communications, MEL, and coordination between partners to amplify impact. Specific actions taken for each recommendation from the 25/26 Annual Report are detailed in Annex 1.
Overall, Financial Year 2026-27 will be a year of transition for CARA, in line with FCDO’s management of a significant reduction in ODA budgets, and re-prioritisation of countries; development of new Country Business Plans; and the FCDO-wide development of new Communities of Expertise.
The CARA team will review the following recommendations 6 months after this Annual Review and consider progress against them to ensure action is on track. These overall recommendations are based on, and summarise by theme, all the sub-recommendations laid out in the Output Level Assessment below - but the CARA team will work on and assess progress against all the top level and sub-level recommendations.
Lesson 1 - Sustainability of pilots and innovative approaches: Considerable effort needs to be invested in terms of monitoring, evaluating, and communicating successful pilot activities (e.g. in HI-REAP's Nature-based Solutions, or enterprise support[10]) and innovative tools (such as the development of a new climate finance mechanism like CANOPI) to relevant stakeholders. Pilots also need to have strong partnerships, sustainability and scalability plans to ensure the proven approaches become embedded in policy and decision-making of line ministries, or else they risk discontinuity after CARA support ends.
[10] Support for Small and Medium-sized Enterprises to: Help strengthen market linkages between producers, enterprises, and buyers; business incubation; mentoring and coaching; grant funding; technical support such as financial literacy, market testing and product validation etc.
Recommendations:
1. Component leads to discuss pilot work with CARA’s Implementing Partners (IPs), ensuring all this year’s workplans include specific and detailed plans for the sustainability and scalability/replicability of pilots, including having financing options, and links to subnational/national policy processes clearly articulated. The Communications and Engagement Lead should also advise, to ensure impact/adoption by others, as relevant. This applies to all components, but particularly for CFN, HIREAP and RAP component leads.
2. The CARA team, in collaboration with the MEL provider and IPs (CFN should help lead) should complete a systems assessment/report in 1-3 priority countries, focusing on the effectiveness of systems for planning and financing climate investments. This should draw on lessons from CARA to date, including the MDB Trust Funds and CFN, and identify any gaps which CARA is helping to fill or should focus on in the future.
3. Prioritise an enabling environment for adaptation deal-making (policy, institutions, pipelines) and hold focused conversations synchronised with British International Investment, Private Infrastructure Development Group, MOBILIST (Mobilising Institutional Capital Through Listed Product Structures) and other growth-focused UK vehicles to ensure learning from CARA is factored into workplans where possible, and over the longer term, support to mobilise and crowd-in investment at scale using CARA’s learning and pipelines. These conversations should be held and reported by end of quarter 2.
4. FCDO to work with CARA Implementing Partners on jointly identified opportunities that call for enhanced support this over the course of the year including: (i) early budget confirmations; (ii) more timely feedback on submissions; (iii) multi-year agreement structures; (iv) targeted capacity-building for smaller partners; and (v) streamlined communication to avoid duplication.
Lesson 2 - Approach to regional work: Over the life of CARA, the utility of technical assistance and the effectiveness of regional and national dialogues will be contingent on sustained follow-up by the IPs and government counterparts, as well as alignment with existing regional initiatives and policy priorities. Evidence-based influence depends not only on the quality and rigor of the evidence, but also on deliberate efforts to influence take-up with government stakeholders to embed findings into programming, strategies, and policy processes. The effectiveness and sustainability of regional cooperation through dialogues, flagship reports, and internal knowledge-sharing mechanisms have not always been clear to date.
Recommendations:
1. To ensure that CARA’s regional work achieves impact over the life of the programme, the MEL team and Comms/Engagement lead should ensure that specific evidence regarding regional work is captured, then factored into ongoing work and influencing plans for each component with the component leads, to ensure that policy influence is achieved. This could also be disseminated to other programmes or via the new Community of Expertise. This applies to all components, but specifically CFN, HI REAP, WISER.
2. Work on effective mechanisms for building planning and climate‑investment financing systems should be documented. Over next year, a note on evidence from CARA to date on this topic (tailored pathways needed to deliver finance goals and sustain cooperation beyond one‑off events) should be produced by the MEL team and Comms/Engagement lead in discussion with component leads, and specific actions agreed regarding future workplans and wider dissemination of findings.
3. Recognising that the results of regional initiatives take time to materialise and are often complex, nonlinear and cumulative, and that convening is not a one-off activity, CARA should regularly assess ongoing regional dialogues and prioritise a portfolio of dialogues that demonstrate progress over time, while retaining space for a limited number of new, strategically selected dialogues. Longer-term follow up of priority dialogues, where possible, will be factored into CARA’s workplans from 2026 by the IPs and CARA team.
Lesson 3 - Capacity building: Trainings and awareness raising events have helped contribute to climate adaptation pathways (as described in Output Section). To ensure it is linked to lasting organisational change, there is a need to focus not only on training/awareness events but also on system change and strengthening the conditions that make capacity development sustainable such as leadership commitment, incentives, and institutional processes. Additionally, capacity strengthening in poor and vulnerable communities cannot be delivered through short-term or standardised training models and needs to be reinforced through repeated engagements and peer learnings; it requires substantial upfront investment in orientation, translation, trust-building, and facilitation to ensure it is as participatory and community-led as possible.
Recommendations: Activities need to shift from ‘service delivery’ to ‘system support’ by helping countries build their governance systems. This should be reflected by IPs in their workplans this year. All component leads and the SRO to agree on approach by Q2 2026.
1. In 2026 workplans, CARA IPs (e.g., CFN, HI REAP, LLAF leads) will be required to set out specific and measurable actions focused on strengthening institutional ownership and follow‑through mechanisms.
2. Capacity building for vulnerable communities needs to be framed as a long-term process rather than a discrete output, moving beyond one-off trainings toward sustained transfer and adoption of skills at both sovereign and sub-national levels.
Lesson 4 - Outcome and impact reporting: Programmes like WISER and CRPP have developed a systematic process and rigorous methodologies to account for and report on long-term results such as ‘increased resilience of vulnerable populations’. These processes can support CARA’s long term influence and impact, ensuring lessons are captured. This approach could be replicated across the other CARA components.
Recommendations: Given the programme has completed its fourth year of implementation, the CARA team and the external MEL supplier will discuss with all CARA IPs on how to ensure comprehensive and relevant outcomes and impact-level reporting, following methodological guidance by Q2/Q3 2026.
Specific consideration should be given to how the required reporting against the wider ICF indicators can also be supported through this process. Additionally, there is a need to prioritise field visits to track progress against milestones, specifically for components like CRPP.
Lesson 5 -Annual Milestones: Progress on some output indicators was significantly higher than the corresponding annual milestones and, in some cases, exceeded annual targets. This may indicate that annual ambition was set conservatively. This is partly explained by the CARA target-setting process: once workplans with Implementing Partners (IPs) are finalised, annual milestones are derived from those plans and are typically locked within the first half of the financial year. During the year, however, some IPs that did not originally expect to contribute to certain indicators subsequently delivered activities and reported results against them. In addition, a small number of IPs received additional funding later in the financial year, allowing them to undertake further activities and generate additional results.
Recommendations: Once annual workplans for each CARA Implementing Partner (IP) are finalised, the CARA team should discuss deliverables and milestones with each IP and seek to strengthen ambition; milestones are set to be finalised latest by September 2026. The quarterly review discussion should allow milestones and targets to be formally adjusted where additional funding materially change delivery expectations, ensuring that the ambition remains realistic and proportionate.
Lesson 6 - Delivery via Trust Funds: Performance of the CARA Trust Funds has in general been strong, with the ADB demonstrating flexibility in response to uncertainty over funding, but also through their efforts to renew focus on the Pacific (through opening new offices in the region) and supporting local planning. However, in some cases, specific workstream delivery via the Trust Funds has been slow to start or progress – for example, the development of the SHARPER biodiversity platform in the RAP, or transboundary cooperation between India and Bangladesh on the Sundarbans. This is for a range of reasons, including geopolitical (for example, political upheaval in Bangladesh and Nepal), and as such, beyond the scope of partners’ ability to influence.
Recommendation: Where workstreams under the TFs have not progressed as planned over the last year, a discussion should be held by the CARA SRO and leads, and IPs, to examine whether the workstream remains valid, if UK funding is providing the catalytic support needed, or if other partners can be found. Where it is not, that workstream can be removed from the CARA workplan this year, given the reducing ODA context.
# B. THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

CARA has five outcome-level goals to deliver and uses a mix of UK ICF and non-ICF indicators (included in the ToC in) to measure progress against these goals. CARA’s Theory of Change is designed to address five broad barriers to building the resilience of people and nature to climate change impacts in the Indo-Pacific. This section describes the progress made against the five key outcome indicators in the 2024-25 period, outlines the key challenges, and provides an overview of cross-cutting themes.
Pathways to impact include a very wide array of workstreams delivered through seven components, (six CARA IPs and LLAF). The workstreams and activities are delivered across a range of levels, areas, and sectors to produce the intended outcomes and impact. These are captured in the programme’s overall or portfolio level results framework through six thematic output areas (included in section C of this Annual Review). Progress against each output is reported through one or multiple composite indicators that combine data from relevant contributing indicators drawn from CARA IP’s results frameworks (each six CARA IP has its own standalone results framework). Weightage to is applied to each CARA Output depending on the expected contribution of the respective output towards achieving the CARA programme Outcome. Equal weightage was applied to all outputs this year, with the exception of the LLAF component. This distinction was made because LLAF projects differ from the other six CARA components, being smaller scale, shorter timeline, and with reduced resource requirements. However, the Results Framework (RF) will be revisited in Q2 2026 in case the weightage needs to be revised.
## Outcome 1: Climate adaptation is integrated or mainstreamed into government policies and plans (national, sub-national and sectoral)
The portfolio has made credible, evidence‑based progress in embedding adaptation and climate finance into public systems and sector policies across Asia and the Pacific. This is visible in cabinet‑level approvals, endorsed regional strategies, and institutionalised tools that governments now own and operate, aligning with the CARA Theory of Change (ToC) pathway. Across the CARA portfolio, building on work from the past four years, the programme has helped integrate or mainstream climate adaptation into at least 44 national, sub-national and sectoral policies and plans over the past one year.[11] Some of the examples are mentioned below:
[11] CFN= 12; WISER= 6; HI-REAP= 18; CRPP=2; RAP= 3; LLA=3
- The CFN programme has developed an “ecosystem” of resilience finance tools that can support green finance and PFM policy reform at both national and sub-national levels. It enabled Sri Lanka to integrate climate change into a new Cabinet-approved financing strategy led by the Ministry of Finance. Sri Lanka has included climate into its budget call circular, paving the way for climate-integrated budgetary proposals. In Bangladesh and Cambodia, after mainstreaming climate change into the budgeting process, CFN is integrating climate change into the public investment management process in road infrastructure, agriculture and energy sectors. In Solomon Islands, the vulnerability assessments helped the Ministry of Agriculture and Livestock reallocate internal funding to re-establish a nursery and model farm in Western Province, translating climate risk evidence into on-the-ground investments that strengthen food security and community resilience. CFN’s engagement through apex ministries (including ministries of finance) is helping embed this support within core public finance systems. For example, the digital public finance infrastructure tool, CONNECT, hosted in Indonesia’s Ministry of Finance, provides training to officials across the country. In Thailand, the capacity building support to the Thai Parliament in 2024-2025 contributed to the successful preparation of the first draft of the Climate Change Act. There is also emerging evidence in the Maldives, Tonga and the Philippines that their ministries of finance will use the analysis from the modelling tool on the economic costs and impact of climate to inform climate change-related investments.
- The WISER programme helped institutional integration and resource decisions in Nepal and Bangladesh to strengthen wheat disease surveillance, monitoring systems, and early warning dissemination through the International Maize and Wheat Improvement Center (CIMMYT) Phase 2 project. Similarly, the Department of Agricultural Extension in Bangladesh has increased the Wheat Variety Extension and doubled the funding for high yielding blast/rust resistant wheat variety programme. This is a result of the prior work in disease surveillance, advisory dissemination and awareness raised through the WISER project. Based on trainings provided through the CARA programme, local governments of Nepal’s mid and far western regions are now funding themselves to train and improve seed production and build capacity. These measures are helping improve preparedness and protect agricultural productivity. This demonstrates greater institutionalisation occurring across Nepal, which should lead to further mainstreaming of best practice.
- Evidence from HI-REAP's Nature-based Solutions (NbS) workstream such as springshed management, agroecology, and rangeland restoration, has informed policy development and scaling initiatives. To address water security by reviving drying springs, HI-REAP supported Manipur’s Forest Department (India) to integrate and approve GESI-responsive Springshed Management (SSM) into the state-level roadmap, and helped nine municipalities prepare springshed action plans (Nepal). HI-REAP, in collaboration with the Government of Bhutan, developed Natural Capital Accounting (NCA) to integrate ecological wealth into national plans, secure more funding for conservation, and promote sustainable livelihoods. In Nepal, HI-REAP helped embed NbS-based agriculture into the Karnali province strategy, Nepal’s agroecology roadmap, and development plans for four municipalities. HI-REAP's NbS-based agriculture has also been adopted and scaled-up by various organisations establishing 60 Community Learning Centres[12] across Nepal.
  [12] CLCs are demonstration/knowledge sites where farmers learn, test, adopt, and scale-up sustainable practices or technologies like improved soil management, water harvesting, and pest control to improve livelihoods and food security. (Aasman= 50 CLCs; Oxfam= 5 CLC; JWAS =5 CLCs).
- ADB’s CRPP Trust Fund (CRPPTF)[13] helped develop and support the Bangladesh Cabinet’s approval of a National Framework and Action Plan for Locally Led Adaptation. Through the CRPPTF co-financed Technical Assistance (TA) linked to the Second Strengthening Social Resilience Policy Based Loan, the Ministry of Disaster Management and Relief approved the revised guidelines of the Employment Generation for the Poorest Programme, which will provide paid employment to poor rural households during lean seasons.
  [13] Between 2021 and 2025, the CRPP TF was supported by the Agence Française de Développement (AFD), the Nordic Development Fund (NDF), and the UK Foreign, Commonwealth, and Development Office (FCDO).
- The World Bank’s RAP-supported Air Quality Management analytics helped develop state-level airshed plans for two large states in India (Uttar Pradesh and Bihar), helping states to move from fragmented city-level interventions to more comprehensive airshed management approaches. RAP’s TA and dialogues facilitated the explicit inclusion of regional cooperation and climate adaptation targets in revised National Biodiversity Strategy and Action Plans (NBSAPs) in four countries - India, Nepal, Bangladesh, and Bhutan. India’s NBSAP now features a dedicated “Regional Cooperation” section, and similar language has been adopted by neighbouring countries, committing to joint monitoring, technology transfer, and capacity building for climate resilience.
- URTF support is actively shaping policy and planning instruments such as Cambodia’s risk‑sensitive urban planning and building codes (drafting and adoption supported), Jakarta’s carbon pricing framework, Metro Manila’s ‘Pasig River open‑space’ framework, and curriculum‑aligned resilience modules in Indonesia - positioning these for formal uptake in the next reporting periods.
- Under the LLAF component, UNDP’s waste management circular economy project in Samoa influenced the National Waste Management Strategy 2025–2029. In Solomon Islands, the United Nations Capital Development Fund (UNCDF) pilot both created and tested insurance products for vulnerable communities and partnered with the Central Bank of Solomon Islands (CBSI) and other key partners[14] to successfully launch the nation’s first parametric insurance product. The initiative received strong support from the CBSI, who accepted and approved Transpacific Assurance Limited’s product through their regulatory sandbox. This is the first time such an insurance product has been approved in the country, setting a new precedent for disaster risk financing – and is also an example of market-building from community level.
  [14] Trans-Pacific Assurance Limited (TPAL), the Solomon Islands National Provident Fund (SINPF), M-SELEN.
## Outcome 2: Capacity of, and access to, resources and weather and climate information for vulnerable communities is improved to strengthen their resilience against climate change.
Across CARA’s components, it is estimated that approximately 28 million people will benefit once the approved and committed large ADB or WB investment grants, loans, or projects are completed. These investments typically follow long project cycles, with implementation lasting two to five years, and in some cases a decade or more.[15]
[15] Of these, ~19 million is estimated to reach through URTF, CRPP, and CFN activities, and the remaining ~9 million people are expected to benefit when the RAP investment projects are complete.
- During 2025, CFN supported efforts in Thailand to strengthen the resilience of 5.3 million residents (directly and indirectly) in Bangkok to the negative effects of extreme heat, with delivery prioritised to achieve results by the end of 2026. In the Pacific, building on work from the past four years, as a result of CFN work, climate-resilient infrastructure has been supported in over 200 climate-resilient community projects in 2025, including 80 projects supporting climate-resilient water infrastructure and 70 projects supporting small-scale infrastructure, including bridges, community halls and access roads. Similar results are being achieved in Bangladesh with the support to 100 Micro, Small, and Medium Enterprises in the most vulnerable areas as measured by the Climate Vulnerability Index.
- RAP has delivered a number of project development studies linked to World Bank projects in India (urban heat and river management) and Bangladesh (coastal resilience and river management), with the potential to reach over 10.5 million beneficiaries in total. The World Bank-supported Uttar Pradesh Clean Air Management Programme (approved in 2025, $585 million), in India is using a mix of outreach, gender-segregated datasets, and capacity building to ensure greater participation of women in providing sustainable public transport solutions across the state. The $560 million Haryana Clean Air and Sustainable Development Operation (approved in 2025) explicitly promotes women’s engagement and leadership. The operation mandates that over a third (35%) of the committee positions are reserved for women, while also providing training for female committee members to enable them to carry out their roles and responsibilities effectively.
- URTF has focused on facilitating infrastructure with a strong climate resilience component in projects. This includes Bangladesh (a project in Khulna to improve water supply to areas where salination is a problem), Cambodia (to support resilience plans for many secondary cities), Nepal (to work on a major river in Kathmandu to tackle wastewater and solid waste challenges as well as flooding and ecological decline), India and Solomon Islands (urban solid waste management), Palau (improving sanitation and wastewater treatment), and Tuvalu (floating solar renewable energy will both supply domestic energy and use electricity to regenerate a coral reef which also has a storm resilience function, which is highly innovative).
- WISER supported the Weather Ready Pacific (WRP), which is a Pacific-led, 10‑year programme of investment to reduce the human and economic costs of severe weather, water and ocean events across Pacific Island communities with an emphasis on strengthening how warnings are communicated and delivered to end‑users, and ensuring inclusion of vulnerable and marginalised groups. Through its collaboration with the South Asia Hydromet Forum (SAHF), WISER AP supported regional events that strengthened institutional capacity and political commitment, endorsed strategic roadmaps on Observational Networks, Numerical Weather Prediction (NWP) and Impact-Based Forecasting (IBF), and established a new Climate Services working group.
- CARA’s LLAF project in Timor-Leste (implemented by World Vision) demonstrated women-led financial governance by establishing savings groups with 141 active members (including women and persons with disabilities); within a year, the group saved $10,000 and disbursed $9,940 to expand access to micro-investment for climate-resilient livelihoods such as horticulture, agriculture inputs, school/health needs. Unlike the other six CARA components, this was delivered as a one-off single activity for a year with a small amount of CARA resources.
## Outcome 3: Large-scale investments for climate adaptation action are realised and implemented
So far, CARA has mobilised a total of $6.8 billion in climate finance through a combination of linked, additional, and leveraged finance, and this is the first time CARA has reported this result.[16] Mobilised finance is funding from other public or private organisations that (i) is additional and (ii) can be causally linked with confidence to CARA/ICF support. The table below provides a breakdown of the three types of financing (linked, additional, leveraged) that contributed to the mobilised figures.
[16] URTF accounts for $1.17 bn across 7 investments; CRPP contributes $0.39 bn across 5 investments, and RAP contributes $1.88 bn across 6 investments, reflecting the scale of approved investment lending supported through these windows. CFN $3.40 bn across 3 initiatives, driven primarily by leveraged finance (USD 3.2bn) alongside additional finance (USD 200m) and a smaller amount of linked finance. ICIMOD contributes USD 0.96m through one leveraged initiative, demonstrating smaller but catalytic mobilisation alongside the larger investment platforms.
- Linked finance is a larger investment (often an MDB/ International Financial Institutions loan or project) that CARA-funded work is connected to, i.e., CARA helped generate evidence, designs, pipelines, or enabling work.
- Additional finance is the extra money on top of the main (linked) package—i.e., a clear “top‑up” that increases the total funding available for the climate investment, and which would not have happened without the intervention.
- Leveraged finance is money attracted from investors/financial institutions (often private finance) because a specific structure or instrument was set up (e.g., blended finance facility, green bond, guarantee), bringing in funding beyond the programme’s own “catalyst” investment.
Types of financing /investment	Amount (in billion USD)
Total Linked finance	3.43
Total Additional finance	0.21
Total Leveraged finance	3.20
Total Climate Finance Mobilised	6.84

CARA’s components such as URTF, CRPP and RAP are oriented towards responding to the immediate needs of governments and operations staff; it is therefore a challenge to initiate more institutionally novel ways of mobilising climate finance beyond the linking of outputs to existing project pipelines. This has constrained work around mobilising “additional” public finance or “leveraging” private finance for climate action. URTF is, however, looking at supporting public-private partnerships (PPPs) in the waste sectors and buildings / housing sectors which should bring in new capital streams, and is also actively reaching out to potential UK investors.
ICIMOD has been able to mobilise additional funding from governments and donors as well as leverage finance from the domestic private sector. The amounts mobilised remain relatively small compared to the scale of the financing required, however, encouraging results from HI-REAP are emerging. Following the first cohort of business enterprises that were supported through HI-REAP’s challenge fund, the programme mobilised $1.1 million by leveraging investment from the private sector, including Google. HI-REAP supported 12 mountain-based climate enterprises, successfully demonstrated the potential of enterprise-led adaptation pathways and access to private finance, in countries where access to climate finance is limited.
## Outcome 4: More regional cooperation mechanisms are in place for collaborative, transboundary action to address climate change impacts in Indo-Pacific sub-regions
All programmes have undertaken productive and important regional events as mechanisms for strengthening regional cooperation. However, mechanisms that build effective systems for planning and financing climate investments have yet to be demonstrated, and this is a key lesson for the programme’s future. This need is captured in Lessons 1, 2 and 3 (sustainability of innovative approaches, approach to regional work and capacity building) in general, and under Lesson 1 in particular.
- URTF shared learnings on responding to climate change in urban settings regionally to inform approaches of countries in Asia.
- CRPP has mainly focused on promoting cooperation on community resilience within ADB across the Asia-Pacific region.
- RAP has contributed to a series of regional dialogues and Knowledge Product launches as a mechanism to promote regional cooperation around tackling heat stress.
- CFN has been promoting regional cooperation on the development of strategies on adaptation finance across the Indo-Pacific region.[17]
  [17] Bhutan, Cambodia, Vietnam, Malaysia, Indonesia and Tonga
- HI-REAP programme is engaging with country governments to strengthen regional cooperation on AQM and NbSs. High-level engagement with environment ministries led to a regional call for action on air quality and climate-resilient development.
- WISER is working towards strengthening regional cooperation by promoting shared forecasting systems and frameworks. For example, the development of a Pacific Integrated Forecasting Platform and a regional framework for IBF in South Asia will establish common approaches to hazards and forecasting, strengthening collaboration and coordination across countries.
- Through the LLAF, the UK has become a Development Partner of the Mekong River Commission, and is further supporting river monitoring for heavy metal pollution related to mining activity, as this poses a significant health threat to the resilience of the ecosystem and human health.
CARA’s regional dialogues and partnerships demonstrate strong convening power; as the programme progresses, there needs to be tailored pathways to deliver the finance goals and to consolidate and sustain the cooperation mechanisms beyond individual events.
## Outcome 5: Protection and conservation of nature and natural biodiversity is improved
This is the first time the CARA programme has reported against this outcome, and discussions with the CARA implementing partners need to begin on reporting against the relevant ICF indicators for this outcome from next year onwards to ensure evidence of progress is captured.
- CFN has successfully incorporated instruments for nature / natural biodiversity protection (natural capital accounting, carbon markets, sustainable tourism levies) into Sri Lanka’s Climate Finance Strategy to mobilise public and private finance for biodiversity protection. This initiative has potential for wider replication across the region, but needs further support to be influential. CFN has also supported the institutionalisation of NbS into sub-national financing plans and budgets to combat coastal erosion, salination and marine systems in Pattani (Thailand), which again is a potential model for other Southeast Asian countries and provinces.
- HI-REAP has made progress on strengthening the policy and institutionalisation of NbS in the HKH. Guidance on prescribed‑burning for Bhutan is now used by forestry, livestock and local authorities to plan, approve and safely implement controlled burns for rangeland/habitat management. NbS (springshed management, agroecology) is mainstreamed into Bhutan’s university curriculum, and Nepal’s provincial plans and university curricula. HI‑REAP helped establish eight tripartite Access Benefit Sharing (ABS) agreements amongst companies, community groups, and government in Bhutan and has been working towards translating ABS policies into practice. The ABS agreements formalise harvesting rules to avoid exploitation of natural resources, custodianship and benefit‑sharing so communities are recognised partners, not just raw‑material suppliers. Currently eight private enterprises or companies now source raw materials through formal ABS agreements with communities and government and 5% of net profit returns to Bhutanese communities.
- An LLAF project on circular economy and waste management in Samoa implemented by UNDP diverted 6.63 tonnes of plastic waste from landfills and prevented waste from polluting ecosystems.
- RAP has supported the development of national biodiversity strategies for India, Nepal, and Bangladesh, and for the South Asia Platform for Ecological Resilience as part of the enabling framework for biodiversity protection. However, progress on SHARPER, a platform for biodiversity conservation, has been slow to establish itself over the last two years.
# C. DETAILED OUTPUT SCORING

Output Title	Filling key knowledge gaps to facilitate adaptation action: Knowledge is produced & used to strengthen adaptation enabling factors, adaptation policy making & implementation.
Output number:		Output 1	Output Score:	A+
Impact weighting (%):		18%	Weighting revised since last AR?	No

Indicators	Milestone(s)	Progress (till Dec 2025)
1.1 No. of Knowledge Products (KPs) developed by five CARA IPs.	61 / CRPP= 9; URTF= 8; CFN= 10; RAP= 17; WISER= 8; HI-REAP= 9	77 / CRPP= 16; URTF= 8; CFN= 6; RAP= 19; WISER= 12; HI-REAP= 16
1.2 No. of countries that directly benefited from the knowledge products.	42 / CRPP= 9; CFN= 10; RAP= 4; WISER= 17; HI-REAP= 2	58 / CRPP= 10; CFN= 10; RAP= 4; WISER= 30; HI-REAP= 4
1.3 No. of officials/people who accessed and used the KPs developed by CARA IPs in their work demonstrate improved skills in and knowledge or No. of downloads, views, or citations of the KP.	400t / CFN= 400	4069 / CFN= 1700; URTF= 902; HI-REAP= 1467
1.4 How did the KPs developed by CARA's IPs help beneficiaries, institutions or countries a) benefit and adopt information from the KPs; b) improve skills and knowledge to work on climate-related issues	N/A since it is qualitative evidence	N/A. Information is provided below

The targets for Output 1 have been exceeded, and is strategically relevant to achieving CARA’s long-term adaptation outcomes. There is strong evidence emerging in the early or immediate uptake of the Knowledge Products (KP), particularly through downloads, views, policy engagement, integration into other programmes, and government-led application. The KPs have enabled stronger climate risk understanding, improved planning and policymaking, and enhanced capacity to mobilise adaptation investments.
The KPs produced by the CRPP component are informing choices, re‑allocating resources toward adaptation, and strengthening the enabling environment through practical design features and capacity building rather than stand‑alone guidance. CRPP’s KPs are being taken up by decision‑makers and are shaping climate adaptation programmes and investments. In Lao PDR, the Ministry of Health used CRPP resources to conduct consultations and surveys on climate‑linked vulnerabilities among border and migrant communities; these findings are guiding the design of community‑based adaptation and risk‑reduction measures and are positioned to be implemented through the ADB approved $41 Million Green Primary Care project. CRPP produced a KP to support India’s Ministry of Rural Development (MoRD)’s Rural Prosperity and Resilience Programme (RPRP); findings from the report informed MoRD’s initial design discussions by embedding adaptive and shock-responsive social protection, climate-resilient livelihoods, and institutional capacity building. Information and evidence generated from CRPP informed the design of Smallholder Resilient Economic Development Project (Cambodia), a c.$100M pipeline with an expected c.$70M in adaptation finance that aims to enhance climate-resilient agriculture and rural livelihoods.
CFN’s climate–economy modelling tools are influencing strategic budgeting in Maldives, informing regional training priorities in the Philippines, and shaping the evidence base for Viet Nam’s Nationally Determined Contributions (NDC) 3.0 update.
Under WISER, seasonal climate outlooks from ASEANCOF‑24 and SASCOF‑31 were directly used by participants from National Meteorological and Hydrological Services (NMHSs), Regional Climate Centers (RCCs), agencies, and academic institutions to integrate seasonal forecasts and enhance preparedness, particularly for agriculture and disaster management.[18]
[18] ASEANCOF: ASEAN Climate Outlook Forum; SASCOF: South Asian Climate Outlook Forum
KPs focused on South Asia and the Pacific are used to initiate policy dialogue and identify operational opportunities in the focus countries. These studies fill critical knowledge gaps and provide concrete actionable recommendations that can be presented to governments for their consideration as well as inform conversations with operations colleagues at ADB to identify suitable entry points in new or existing projects and programmes in these countries.
Lesson (Volume of KPs, timing and dissemination gaps): Some KPs are either too recent to show clear evidence of utilisation or have been finalised but not officially disseminated, limiting the ability to capture the evidence on the uptake and utilisation of the KPs. As the portfolio grows and volume of KPs grow, the marginal value of stand‑alone analytical products falls unless they are actively curated, synthesised and repackaged into user‑oriented formats that respond to the needs of the audience.
Recommendation: During the monthly catch-up meetings with each IP, the CARA team will discuss the dissemination of KPs (e.g. target audience and channels). When IPs submit annual workplans for approval, the CARA team will ensure that any KP-related activity clearly outlines dissemination strategies. In resource-constrained contexts, prioritise realistic actions from the MEL/Comms/KM strategy, such as basic audience mapping and mandating dissemination plans to accompany publication of key KPs.
Lesson (Country-driven, context-specific frameworks accelerate adoption): While regional KPs help harmonise approaches and enable cross-border coordination, country-specific co-creation with governments and synchronisation with national planning cycles and priorities supports faster uptake and helps move products from knowledge to action.
Recommendation: CARA team to ensure that the CARA IPs coordinate and collaborate with government stakeholders to ensure in-depth, country-level relevant information and evidence emerges from the KPs. This will be integrated into IP workplans by end of Q1, with the relevant evidence subsequently captured under Indicators 1.3 and 1.4.

Output Title	Convening for Adaptation: Events and dialogues are held that contribute to a range of adaptation pathways, including generating policy and political will and momentum, sharing of learning, and creating buy-in for adaptation from key stakeholders.
Output number:	Output 2	Output Score:	A+
Impact weighting (%):	18%	Weighting revised since last AR?	No

Indicators	Milestone(s)	Progress (till Dec 2025)
2.1 No. of events held to increase awareness, share evidence, or build sub-national, national or regional collaboration on climate adaptation and transboundary climate action.	47 / CRPP= 11; URTF= 11; CFN= 5; RAP= 6; HI-REAP= 14	103 / CRPP= 15; URTF= 11; CFN= 14; RAP= 8; HI-REAP= 55
2.2 No. of concrete commitments / joint initiatives agreed or made by governments, institutions, or private sector entities that have taken place in the past twelve months as the result of the regional or national event or replicated by other countries because of lesson sharing.	2 / CFN= 2	7 / CFN= 2; / HI-REAP= 5
2.3 Feedback from the participants on the relevance of the event and how they used or plan to use the information and collaboration formed in their country’s programmes and policies.	N/A since it is qualitative evidence	N/A. Information is provided below
2.4 How have the forums, platforms, cooperation mechanisms, partnerships etc. contributed to or will contribute towards achieving CARA outcomes (existing and new partnerships, including collaboration amongst CARA IPs).	N/A since it is qualitative evidence	N/A. Information is provided below

The CARA programme delivered 103 events across five IPs that contributed to a range of adaptation pathways such as generating policy and political momentum, sharing of learning, and creating buy-in for adaptation from key stakeholders, and strengthened collaboration on climate adaptation at sub‑national, national, and regional levels (N=3,813 participants). The output has met the planned annual milestones and remains on track to hit end‑of‑programme targets.

This Output acts as a ‘knowledge‑to‑action bridge’, moving insights from evidence-based information into policy conversations, unlocking partnerships, and developing large investment projects. Knowledge products developed through CARA’s support (Output 1) were disseminated through events to reach a wider audience, promoting the uptake of findings in policy discussions and larger investment project design and created opportunities for collaboration and knowledge exchange that can inform future policies and programmes HI-REAP conducted events to prepare national-subnational roadmaps in India and Nepal on springshed management to revive drying springs; help allocate provincial and municipal budget for scaling agroecological practices and scale-up CLCs in Nepal and Bhutan; support the initiation of national clean air strategies in Nepal and Bhutan. Post-CRPP event survey reported that revealed that the CRPP Forum increased participants' awareness of building climate resilience through urban development programs and financial inclusion, with 94% reporting an increased awareness. Participants who attended the forum primarily mentioned that they plan to use the knowledge and skills to design and implement programmes.

Lesson (Capacity and continuity at institutions): Staff turnover, especially in government agencies, slows translation from evidence to decisions and actions.
Recommendation: CARA IPs to build repeat touchpoints and refresher sessions (e.g., periodic follow-ups, re-orientation for new officials, and short “booster” engagements) to sustain momentum and institutional memory.
Lesson (Regional versus country-specific events): Regional collaboration works best when tightly coupled to national ownership—country coalitions gain traction when regional insights feed directly onto domestic reform agendas and financing instruments. Regional efforts strengthen coordination, multiply impacts, and build momentum for regional agendas, particularly in dynamic operating environments or when asymmetric capacities exist (AQM, heat stress/sustainable cooling).
Recommendation: CARA team to coordinate with all CARA IPs to ensure regional platforms (e.g., AQM, South Asia HydroMet Forum) are explicitly linked with, and work in parallel with, national entry points—by translating regional outputs into country-specific roadmaps, policy asks, and financing/institutional pathways that have clear domestic owners.
Lesson (Causality from convenings/events to outcomes): As a majority of CARA’s resources are spent on events, technical assistance, workshops, etc., it is critical to assess whether and how these are helping the programme move towards achieving outcomes. This year, new quantitative and qualitative indicators were added to CARA’s Results Framework to provide insight on uptake of outputs, decisions, and changes in procedures/practices. Additionally, a few targeted case studies were conducted to triangulate information and clarify the pathway to achieving outcomes.
Recommendation: CARA team’s MEL Advisor, in collaboration with the MEL supplier and CARA IPs will discuss and agree actions including timelines in the annual in-person partners meeting, ways to strengthen evidence of contribution to outcomes by systematising and tracking the pathways of change following the delivery of an output through MEL tools such as key informant interviews or collect light-touch follow-up evidence at set intervals.

Output Title	Training & other capacity building support for effective adaptation action: Capacity building support, particularly critical training, is delivered to key stakeholders in governments and civil society, enabling adaptation action, adaptation policy making, its implementation, and monitoring.
Output number:	Output 3	Output Score:	A+
Impact weighting (%):	18%	Weighting revised since last AR?	No

Indicators	Milestone(s)	Progress (till Dec 2025)
3.1 Number of training / capacity building sessions on climate adaptation-related topics.	22 / URTF= 3; CFN= 2; RAP= 6; HI-REAP= 11	32 / URTF= 6; CFN= 5; RAP= 3; HI-REAP= 18
3.2 No. or % of participants who report improved capacity and skills on climate-related topics or application of information / skill gained in the capacity building sessions-measured through follow-up surveys.	215 / CFN= 40; WISER= 175	304[19] / CFN: 41; WISER= 263
3.3 Insights from the participants on the usefulness and relevance of the events. And how they used or would like to use the information and collaboration formed in their country’s programmes and policies.	N/A since it is qualitative evidence	N/A. Information provided below
[19] CFN: 41 participants attributed changes in their knowledge, skills, capacity directly to the training. HI-REAP: 75% reported improved capacity and skills after the training, and confidence in the understanding of complex topics, e.g. natural capital accounting, developing water and Protected Areas accounts in Bhutan and Forests in Nepal. WISER: 263 participants of which 90% agree the training is useful (Men= 149; Women= 114)

Under Output 3, CARA delivered 32 targeted trainings and contributed to key adaptation pathways by strengthening knowledge and skills and bringing behaviour change to design and implement climate adaptation and resilient interventions. Some of the KPs developed in OP 1 were used along with site visits, workshops/events. Qualitative evidence and post-workshop surveys from CARA components demonstrate the workshops contributed to clear evidence of improved skills, confidence, and application of learning among participants, supported climate mainstreaming and in finding bankable projects.
At the request of Ministry of Housing and Urban Affairs (MoHUA), India, RAP conducted a workshop on heat and cooling convened central/state agencies and private operators. Participants co‑identified regulatory and planning barriers. Following the workshop, the MoHUA has requested advisory support and help lay the groundwork for scalable public-private partnership (PPP) models.
Lesson (Capacity building becomes more meaningful when it is practical, contextualised and closely tied to institutional mandates): Training that combined hands-on learning, field demonstrations and problem-solving workshops (e.g., district cooling case studies in India, springshed fieldwork in Nepal, gas analyser calibration in Bhutan and Nepal) was taken up more effectively than conceptual sessions.
Recommendation: CARA team to ensure that some partners’ annual workplans prioritise experiential formats that allow participants to practise real tasks using their own datasets, regulatory processes or project pipelines. Embedding technical training—through follow-up clinics, mentoring and applied assignments—will deepen skill retention and ensure learning feeds directly into institutional workstreams, rather than remaining standalone exposure.
Lesson (Co-design and community-centred approaches lead to stronger ownership and sustained use of solutions): URTF’s school retrofit consultations in Nusantara (Indonesia), farmer-led design of urban agriculture demonstration plots (Nepal), and RAP’s participatory ecological monitoring showed that interventions grounded in lived experience build legitimacy and long-term commitment. Communities were more willing to maintain assets (e.g., demonstration farms or retrofitted schools) when they shaped the design themselves.
Recommendation: Wherever relevant, CARA will champion community based adaptation approaches, and share the lessons learnt widely within FCDO and external stakeholders.
Lesson (Linking training and knowledge to policy processes and investment pipelines strengthens uptake): When training aligns with an ongoing policy priority, it creates momentum for rapid institutional uptake. In several cases, ministries requested additional advisory support, adoption of new protocols, or development of public–private partnership documents as a direct consequence of training dialogue. This alignment helps shift outcomes from general awareness to specific regulatory and budgeting decisions required for adaptation.
Recommendation: Implementing partners to design and deliver capacity‑building activities explicitly aligned to identified policy windows and investment decisions, such as scheduled regulatory revisions, annual budget cycles etc. Training content should focus on the immediate application of tools (e.g., modelling, climate budget tagging, SOPs) required for those decisions. These workshops should be deliberately timed, mapped and framed no later than 3–6 months around concrete policy windows and investment decisions—such as regulatory updates, or upcoming budget cycles. This increases the likelihood that participants apply knowledge immediately into standard operations.
Lesson (GEDSI outcomes improve when barriers to participation are actively addressed, rather than assuming open invitations guarantee diversity): For example, WISER noted high participation by female meteorologists when space was intentionally created; CFN’s modelling and finance sessions were stronger when women’s expertise was explicitly sought; HI-REAP found women’s role in agroecology central when training was held in accessible locations and formats that recognised time constraints. Where inclusion was not deliberately planned, participation in more technical sessions remained low.
Recommendation: The GEDSI strategy is being finalised in coordination with IPs, and will inform all aspects of the programme, including planning, implementation and management, as well as monitoring, evaluation and learning (MEL) approaches, systems and frameworks. All programmes would embed GEDSI principles from the outset, covering the location and timing of events, accessible materials, facilitator selection, and targeted outreach to women, youth, persons with disabilities, and marginalised communities. Furthermore, programmes must not only provide gender-disaggregated data but also articulate how they ensure under-represented groups participate meaningfully and influence decision-making.

Output Title	Investments & Finance for Adaptation Action. Large-scale multilateral Investments with adaptation objectives are enabled (support on design, prep, & implementation), with possible additional finance generating effects.
Output number:	Output 4	Output Score:	A
Impact weighting (%):	18%	Weighting revised since last AR?	Yes, increased from 10% to 18%

Indicators	Milestone(s)	Progress (till Dec 2025)
4.1 No. of new financial mechanisms or instruments introduced (e.g., green bonds, climate funds, insurance schemes).	6 / URTF= 2; CFN= 4	4 / URTF= 1; CFN= 2 complete & 3 ongoing (2 to be complete by mid-2026); / HI-REAP= 1 complete & 1 ongoing
4.2 No. of country government policies and regulations adopted that facilitate climate finance (e.g., tax incentives, regulatory frameworks for green finance).	3 / CFN= 3	4 / CFN= 4 completed & 3 ongoing; URTF= 4 ongoing
4.3 No. of new partnerships formed, or institutions accredited to access international climate finance entities (e.g., GCF, GEF, etc.).	2 / HI-REAP= 1; CFN=1	1 / HI-REAP= 1; / CFN= 1 to be complete by Q1 & 1 by mid-2026
4.4 No. of successful climate finance proposals submitted and approved for international funds (e.g., Green Climate Fund, Adaptation Fund).	1 / HI-REAP= 1	2 / HI-REAP= 1; / CFN= 1
4.5 No. of countries with improved capacity and mechanisms to track and report on climate spending.	2 / CFN= 2	2 / CFN= 2 complete and 3 ongoing
4.6 No. of CARA supported ADB/WB investment projects receiving linked climate finance to help countries mainstream or build resilience or strengthen adaptation.	24 / CRPP= 6; URTF= 6; RAP=12;	33 / CRPP= 9; URTF= 8; RAP=16

Many of CARA’s components have made progress against Output 4 this year in enabling large-scale adaptation finance—exceeding milestones on all but two indicators (scheduled to be complete by early/mid this year). See section on Outcome 3, which differentiates CARA’s role in linked, additional and leveraged finance, as different forms of enabling support.
For CFN, progress is ongoing in some cases. Although there has been some delay in delivering against two indicators, CFN has made strong progress and results by aligning financial instruments, institutional reforms, and expenditure tracking systems, and has helped countries strengthen climate expenditure tracking and fiscal transparency, reduce fragmentation, and strengthen the governance required to absorb and manage large-scale adaptation investments.
The results demonstrate how Output 4 supports CARA’s wider ambition: helping governments move from acknowledging climate risks to financing the solutions - whether by enabling small businesses to adapt to drought, helping countries design national climate‑finance strategies, or reshaping public finance systems to prioritise resilience. This work also strengthens countries’ ability to access international funds, such as the Adaptation Fund and Green Climate Fund, ensuring they can start to mobilise more resources over time. Results against Outcome 3 are demonstrating CARA’s contributions to the financial enabling environment, and work on bids to the Climate Funds is being discussed for future workplans with several IPs (to note, the ADB already has had success in bidding to the GCF for CRPP, the first time the organisation has done this, as outlined in the 2023-4 Annual Review). Linking work through to larger scale results in finance is a top consideration for workplans this year, as outlined in the recommendations.
The programme shifted from exploratory pilots to the development of practical financing mechanisms, partnerships and investment‑readiness systems that countries can use to unlock and manage adaptation finance. CARA also helped governments and partners create new blended finance models, strengthen natural‑capital accounting approaches, develop co‑investment frameworks, and advance clean‑air initiatives with private‑sector involvement.
Lesson (Aligning climate finance TA/work to national budget timelines and systems): When upstream climate finance analytics and credible evidence (e.g., green taxonomies, expenditure analysis, budget tagging) are embedded in strong public-finance systems and aligned to MDB investment cycles, they accelerate government ownership and turn priorities into bankable, scalable operations.
Recommendation: Support a multi-year roll-out of climate-budget tagging, citizens’ budgets and audit guidance through ministries of finance, aligned to the national budget calendar. Build line-agency capability so tagging, reporting and evidence use become routine public-finance practice rather than one-off exercises.
Lesson (Enabling environment efficiencies for blended finance for adaptation): Blended finance guarantees and effective deal-making unlock private capital for adaptation by reducing risk and cost of capital, but they only work when the enabling environment is tailored to country needs and partnerships are structured to mobilise investment at scale.
Recommendation: Prioritise an enabling environment for adaptation deal-making (policy, institutions, pipelines) and hold focused conversations synchronised with British International Investment, Private Infrastructure Development Group, MOBILIST (Mobilising Institutional Capital Through Listed Product Structures) and other growth-focused UK vehicles to ensure learning from CARA is factored into workplans where possible, and over the longer term, support to mobilise and crowd-in investment at scale using CARA’s learning and pipelines. These conversations should be held and reported by end of Q2.

Output Title	Gender and Social Inclusion for Adaptation: All CARA components respond to FCDO’s GEDSI agenda/strategy by incorporating it effectively into their workplans/delivery.
Output number:	Output 5	Output Score:	A+
Impact weighting (%):	10%	Weighting revised since last AR?	No

Indicators	Milestone(s)	Progress (till Dec 2025)
5.1 No. of individuals from vulnerable/ marginalised communities who received training on climate resilience and/or on adaptation.	3399 / CRPP= 1578; URTF= 450; HI-REAP= 1371	3621 / CRPP=520; URTF= 478; HI-REAP= 2623
5.2 No. of tools developed or no. of people from vulnerable/marginalised communities who use or have access to climate or weather information, tools, climate-resilient services, safety and livelihood opportunities or other solutions/services to respond to climate change.	801,002 / CRPP= 100,000; WISER=701,000; HI-REAP= 2	856,875 / CRPP=215[20]; WISER= 856,653; HI-REAP= 7
5.3 No. of initiatives led by women or vulnerable/marginalised community focused on building collective climate adaptation or resilience initiatives.	3 / CRPP=2; HI-REAP=1	4 / CRPP=2; HI-REAP=2
5.4 No. of stakeholders supported (e.g. capacity building) to design, implement or mainstream GEDSI-responsive initiatives (e.g. GEDSI-responsive NbS, GEDSI in WCIS GEDSI responsive policies or financial instruments etc.).	270 / CRPP= 205; CFN=50; WISER=10; HI-REAP=5	1,067 / CRPP= 860; CFN=100; WISER=101; HI-REAP=6
5.5 Insights from beneficiaries on how events or workshops supported or improved their ability/capacity to respond to climate change, adopt practices, or helped them prioritise vulnerable communities in the policies, practices and guidelines.	N/A since it is qualitative evidence	N/A. Information is provided below
[20] Conditional Cash Transfers (CCT) were expected to be disbursed in Q4 in Lao PDR. Once disbursed, the CCTs will reach at least 25,000 women, benefiting approximately 100,000 people

Under Output 5, the CARA programme has exceeded its annual milestones across all the indicators. 3,621 individuals from vulnerable or marginalised communities were trained to respond to climate change against a milestone of 3,399.
Women’s leadership and voice are becoming more visible and influential across CARA components. CRPP, HI-REAP and CFN, for instance, have trained and employed local community members to gather data, empowering local women to become leaders and influence community and local government activities in Thailand, Nepal and Indonesia. Initiatives aimed at building leadership capacity among grassroots women have resulted in the formation of women leadership groups that are increasingly engaging with local government institutions and raising issues affecting women and their communities. Several local agencies have now invited women leaders to train others, signaling growing institutional recognition of their expertise.
CRPP trained 520 community members in climate vulnerable parts of Indonesia and Nepal. Post-trainings survey showed that 73% of the participants were able to interpret rainfall patterns, anticipate risks, apply knowledge to local planning decisions, and translate into behavioural change such adjusting planting schedules; adopting climate-resilient crops; using water-saving techniques like drip irrigation and rainwater harvesting.
CFN supported capacity building for inclusive climate planning in Bangladesh and Thailand on GESI-responsive prioritisation, budgeting, and adaptation planning, strengthened tools and processes for integrating GEDSI into government systems. These activities led to Bangladesh government developing a GESI checklist for the Local Adaptation Plan of Action (LAPA) to embed participation of women, persons with disabilities, and ethnic minorities.
Lesson (Dependence on government systems and timelines): Working through government systems is essential for institutionalisation, scale, and sustainability, but progress can be delayed by government timelines, budget cycles, and procurement—especially in fragile and conflict-affected contexts (e.g., Nepal, Bangladesh, Timor-Leste).
Recommendation: Consider with all IPs (and HI-REAP in particular) where their workplans (due Q2) can support strengthening systems-level linkages between grassroots organisations and government programmes by creating structured mechanisms (e.g., participation in local planning and budget forums, joint working groups, and co-designed implementation plans). This will help align community-led priorities with government budgeting/procurement cycles and reduce delays by embedding activities within formal planning and implementation processes.

Lesson (Localisation and mediation matter): In multilingual settings, connectivity and geography constraints, and the invisibility of some groups can bias assessments and reduce uptake if content and facilitation are not tailored.
Recommendation: The programme can explore ways to move beyond attendance at workshops to include embedded learning arrangements, including working with community leaders. This would be one way of translating learning experience from building capacity in communities, to the government context. Particular attention should be given to lessons from projects under CRPP, CFN and in the Pacific Island Nations.

Lesson (Strengthening the GEDSI “results story” from outputs to outcomes): It is important to ensure the strong GEDSI results CARA has achieved at the output level translate into credible, compelling outcome‑level contributions. For instance:
- How training and empowering marginalised groups increases their capacity to engage in climate adaptation decisions which contributes to improved resilience against climate change (CARA Outcome 2), and
- How community‑led data collection generates locally grounded evidence which informs government planning and investment decisions on climate adaptation at (national, sub-national and sectoral) (CARA Outcome 1).
Recommendation: In the next reporting cycle, the GEDSI strategy will be finalised and agreed by the MEL supplier with IPs in Q2 to provide them a handy tool/guidance on how to mainstream GEDSI in their components. This would strengthen the GEDSI results story by documenting and evidencing causal contribution pathways—showing how improved capacity and empowerment are enabling GEDSI integration into government adaptation planning and influencing climate-adaptation investments. This will include systematically capturing examples of changes in planning decisions, budget allocations, and implementation choices linked to CARA-supported GEDSI work.
Output Title	Small-scale Local Level Adaptation Fund (LLAF) projects that respond to emerging priorities in a flexible manner to respond to climate change and protect nature and biodiversity.
Output number:	Output 6	Output Score:	A+
Impact weighting (%):	18%	Weighting revised since last AR?	N/A

Indicators	Milestone(s)	Progress (till Dec 2025)
6.1 Number of KPs produced to build capacity, develop Guidelines, and fill knowledge gap to respond to climate mitigation or adaptation strategies.	3	13
6.2 Number of events/trainings held to raise awareness, share evidence, foster learning, build capacity or formulate consensus on climate-related issues.	33	31 / N=1299 (Men=806; Women=493)
6.3 Number of physical assets, systems, tool, solutions, equipment/infrastructure or other solutions/services developed or maintained or supported to respond to climate change.	5	9
6.4 Number of partnerships, networks, forums, decision-making platforms and cooperation mechanisms established or strengthened.	5	15
6.5 How have LLAF projects improved the skills, knowledge, ability to adapt and respond to climate change/disaster, protect and manage ecosystems and biodiversity? How are the institutions and beneficiaries adopting knowledge, skills, and information received through the support?	N/A since it is qualitative evidence	N/A. Information is provided below

With the large volume of projects under the LLAF (Annex 3), a new Output (Output 6) was introduced in this year’s reporting to capture and streamline results from the LLAF component. Annex 3 also conveys the breadth of climate adaptation activities undertaken through the LLAF, in response to demand articulated by UK High Commissions and Embassies. Many (47%) of the projects were undertaken by civil society organisations, which helped in delivering results on ground, impacting lives at the community level.
There have been efforts to integrate GEDSI within the LLAF portfolio. Some projects were explicitly women-focused, particularly in livelihood and community resilience initiatives.
GEDSI is a core component of LLAF project proposals and will be assessed in line with the CARA GEDSI Strategy. Building on learning from the previous portfolio, the next LLAF Call for Proposals (Q1) will place greater emphasis on the meaningful integration of GEDSI principles throughout the project cycle—from planning and design to implementation and monitoring. Proposals that demonstrate strong, intentional, and context‑appropriate GEDSI integration will be given due weighting during the assessment process.
Lesson (Capacity-building improves uptake and ownership, but short LLAF timeframes limit sustainability and scale): Investing in local country capacity supports implementation and transfers skills and practices, but one-off trainings/single-year interventions are often insufficient for deeper institutionalisation, behaviour change, and sustained outcomes. Stronger vertical and horizontal linkages are needed to embed pilots within national systems and budgets.
Recommendation: Strengthen vertical/horizontal linkages (community–local–national) and actively connect pilots to relevant government planning, budgeting and implementation processes. CARA will maintain portfolio oversight to identify replication opportunities, strengthen cross-project synergy, and support mainstreaming beyond the LLAF project period. CARA team will be sharing it widely with other CARA IPs and donor partners to ensure sustainability of the projects
Lesson (Challenges with reporting milestones and timelines): Given the nature, budget and timeline of the LLAF component, capturing annual milestones from LLAF projects accurately for CARA’s reporting framework is complicated. This is because milestones provided by all the LLAF projects are overall (i.e. targets that will be achieved at the end of their project), and not annual, whilst CARA’s RF requires annual milestones. Additionally, CARA’s AR process requires reporting against results achieved till December, and almost all the projects under the LLAF component end on different timelines (N >30 projects), making it harder to anticipate results, align targets and milestones, and aggregate and report performance consistently. This challenge will be amplified when the number of projects increases in the LLAF component.
Recommendation: CARA, the external MEL supplier and LLAF IPs will jointly map each project’s timeline, deliverables, indicators (including GEDSI) and milestones and convert them into annualised milestones aligned to CARA’s reporting calendar (including “results-by-December” expectations). This will be supported through an adaptive, flexible reporting approach and a consolidated portfolio tracker to improve consistency as the number of projects grows.

# D. VALUE FOR MONEY

Based on performance against outputs and outcomes, strong alignment with CARA’s ToC, and evidence across all 5Es, the programme continues to deliver Value for Money (VfM). Delivery during this review period was guided by the FCDO's 5Es (see below), with partners embedding VfM considerations in workplans, implementation, and monitoring. In FY26/27, the programme team will develop a detailed VfM strategy with support from the commercial team and the ECD economist to act as guidance for partners to further strengthen procedures to measure and report VfM. Partner‑wise VfM performance against the 5Es is detailed in Annex 4.
## Economy (acquiring inputs at least cost)
The IPs controlled costs through disciplined cost control, competitive procurement and by leveraging existing systems, expertise, and partnerships rather than building new ones from scratch. For example, WISER has built on existing platforms such as the South Asia Hydromet Forum (SAHF), and the Mekong River Commission (MRC), thus minimising new overheads. Similarly, the URTF pooled additional financial resources by adding The Rockefeller Foundation’s $2.57m to the URTF Trust Fund and used advance contracting to control prices and timelines. Many of the staff on the URTF secretariat work part-time – also working for the Spanish trust fund which enables both trust funds to have access to specialists such as the MEL adviser, etc. ADB’s effective use of staff in the region and country also kept travel costs down.
## Efficiency (delivering well and converting inputs to outputs):
Efficiency was strengthened by building on successful projects, scaling-up proven approaches, and integrating workflows across multiple components to avoid duplication. Joint delivery arrangements between implementing partners reduced transaction costs and enabled shared planning, reducing time spent on parallel processes. For example, CARA IPs (WB and WISER) supported and engaged with SAHF on regional hydromet and forecasting platforms to draw upon in‑house capabilities and established partnerships, helping maintain quality at the lowest feasible cost. The CFN’s work sits within and on top of the UNDP country office architecture and other climate finance work and funding streams, creating efficiencies.
## Effectiveness (achieving the right results):
Activities were designed to produce multiple outputs from single investments. For example, using analytical work to inform policy engagement while strengthening institutional capacity. This approach helped convert KPs into practical influence, improved delivery capability in government systems, and leveraged co-financing to expand reach and scale of the programme (HI-REAP, CFN). CARA funding has led to large investments: for example, $4.0 million from URTF has influenced an approved $241.7 million water supply project in Bangladesh, and $3.0 million URTF support contributed to the approved $317.6 million resilient and water-secure cities project in Cambodia.

Equity (reaching people fairly):
As evident through Sections B and C, CARA’s focus on GEDSI is strong and growing. The CRPP programme seeks to address the gender-climate vulnerability-poverty nexus by integrating a set of activities to address structural drivers of women’s inequality, disproportionate vulnerability to climate change, and poverty. Across SA and SEA, the CRPP programme scaled participatory tools, channelled community‑level grants, and designed Technical Assistance to improve the resilience of health workers by placing women and underserved groups at the centre of design and delivery. URTF has held specific events with youth and marginalised river slum communities to help design resilience solutions, and its transport project in India will also look at women’s use of transport and the impact of heat. Equity was mainstreamed throughout the programme by creating a CARA-GEDSI strategy and establishing a Community of Practice (CoP) to ensure the CARA programme’s benefits could reach underserved groups, rather than only better‑resourced institutions. The CoP served as a platform to help the CARA IPs foster collaborative learning, knowledge sharing, help standardise practices, and ensuring the IPs integrate GEDSI in the projects where relevant.
## Cost‑effectiveness (achieving outcomes at reasonable cost):
Cost-effectiveness was maximised by using targeted, catalytic interventions to unlock additional finance, promote scalable solutions, and enhance long-term resilience. The programme team continues working closely with IPs, CARA team, and Department’s Finance Manager to adjust programme deliverables and forecast in line with the available budget constraints, focusing on activities that are likely to result in higher impact. The IPs are regularly and promptly informed of UK’s changing budget situation (e.g. ODA pause, budget cut, additional allocation towards the end of year etc.). All the CARA IPs respond to such evolving situation in the design and implementation of their workplan.
## Key cost drivers and performance:
Key cost drivers included staff/consultant time, technical assistance, travel and events, and knowledge products were managed carefully (through workplans, financial reporting, NPAC and discussions in the regular meetings with the partners), with no material change to their performance over the year. Performance risks were actively managed: ODA uncertainty required re‑prioritisation, and geopolitical sensitivities in multi‑country TAs triggered phased designs and early risk screening.

# E. RISK

Given CARA’s complexity and the challenging operating context, overall programme risk remained Major throughout 2025, but stable and within risk appetite. Delivery across seven components was strong in 2025–26, with resilient partners, timely reporting, effective oversight, robust commercial performance, and audited financial assurance despite budget reductions over the years. In addition, the team took several actions over the course of the year to steadily improve risk mitigations and reduce several risks.
Due to these actions, the CARA team assess that, for the FY 2026-27, the overall risk profile of the programme is better reflected now by a Moderate assessment, rather than Major
## Risk Appetite and Key Trends:
The most material risks continue to relate to:
- Programme delivery and coordination, especially ensuring coherence across multiple implementing partners and regions. The HMG Adaptation Network, improved country‑level coordination, and strengthened MEL systems have helped stabilise this risk at a Major residual level but within appetite.
- Political and contextual risks in partner countries remain dynamic, though overall exposure has decreased due to stabilisation in key countries (e.g., Bangladesh and Nepal). Regular partner updates and flexible programming have helped maintain this risk at a Moderate residual level.
- Financial risks, particularly those related to ODA reductions and sporadic funding in previous years, have reduced following the programme extension to March 2031, timely quarterly financial reviews, and active re‑forecasting. Several risks (e.g., RDEL constraints) have moved from Major to Moderate/Minor residual levels.
- Fiduciary risks involving misuse of funds have been proactively managed through refreshed due diligence (e.g., UNDP) and ongoing updates (ICIMOD, ADB), delivery chain reviews, annual audit requirements, fraud letters, and capacity‑building sessions, which have improved assurance. Findings from the Due Diligence Assessment (DDA) have been incorporated into the programme risk register, with mitigation actions tracked through quarterly meetings and partner reporting.
- Safeguarding risks remain low due to robust partner systems, mandatory safeguarding clauses, partner training, and refreshed awareness sessions planned for March 2026.
Learning from implementation has strengthened confidence in partner governance systems, reducing overall fiduciary and safeguarding risks. Residual risk now sits at Moderate.
## Climate, Environment, Gender, and Equalities Assurance:
In line with the Paris Agreement, climate and environment risks are low, partners are monitored through climate‑aligned workplans, environmental safeguards within DDAs, and regular engagement with posts. A review of the Gender Equality Duty and Public Sector Equality Duty confirms that original assumptions remain valid. No material negative impacts have been identified. Partners continue to report against equality‑related indicators where available, with ongoing efforts to improve sex‑disaggregated data and equitable access across vulnerable groups.

# F. PROGRAMME MANAGEMENT: DELIVER, COMMERCIAL & FINANCIAL PERFORMANCE

Across the seven CARA components, delivery performance in 2025–26 remained strong. Partners demonstrated resilience, effective financial management, and timely reporting despite funding uncertainty and operational disruptions in several countries. Delivery continued broadly on track, supported by strengthened programme management, structured engagement, and proactive risk discussions.
The CARA team has stabilised programme management processes over the past two to three years, culminating in the current level of maturity. Key tools—including the activity tracker (MEL), country briefs (Communications), financial reviews, detailed delivery plans, and the flexible fund tracker—were developed, completed by partners, and progressively refined, stabilised, and streamlined over time. Regular programme management structures are now well established, with monthly meetings held with the seven main partners and quarterly meetings with LLAF partners. These engagements focus on reviewing progress against agreed activities and projects under approved workplans, alongside financial performance and compliance.
Implementing Partner Performance
All delivery partners maintained effective programme management through monthly technical meetings, quarterly financial reviews, and semi-annual reporting cycles. Narrative and financial reports were consistently submitted on time and to a high standard, with clear articulation of progress, risks, and expenditure against plans. Financial forecasting and activity-based budgeting remained accurate, and no procurement or asset management concerns were identified.
Risk dialogue continued to improve across the portfolio, with regular fiduciary, safeguarding, and operational discussions. URTF and ICIMOD effectively applied adaptive management in response to political disruptions, while WISER strengthened scrutiny of partners such as RIMES and SPREP. Delivery chain maps and risk registers were routinely updated.
Implementation Partners identified opportunities for enhanced FCDO support, including: (i) early budget confirmations; (ii) more timely feedback on submissions; (iii) multi-year agreement structures; (iv) targeted capacity-building for smaller partners; and (v) streamlined communication to avoid duplication.
FCDO Oversight and Programme Management
FCDO oversight was maintained through:
- Weekly SRO chaired CARA team meetings
- Monthly ‘Brilliance @ Basics’ compliance reviews and programme Health checks
- Regular meetings with IPs on work plan, finance, SEAH, fraud, and delivery chain.
- Continuous maintenance of the CARA Delivery Plan as a live control tool.

The Annual in-person IP meeting could not be held in 2025 due to uncertainty around budgets and strategic direction, though routine assurance and engagement remained strong.
Commercial Performance
Triple Line, contracted under the Global Evaluation and Monitoring Framework Agreement (GEMFA) framework, complied fully with contractual requirements, MEL obligations, transparency standards, and supply partner expectations.
Financial Performance:
Financial reporting remained robust across all partners with partners demonstrating strong forecasting accuracy and great flexibility across changing budget scenarios.
The reporting period (for the actuals) considered is for the financial year ending 31 March and was supported by audited financial statements that provided assurance of accuracy and probity. A comparison between Business Case budgeted numbers and the actual to date is as follows:

In UK Financial Year 26/27, CARA’s budget will be reduced as a result of ODA reductions. The CARA team will continue to regularly interact with IPs, including for more granular financial narratives to link expenditure with impact, to highlight programme effectiveness. Regular engagements with IPs’ finance teams help track spending and ensure financial compliance.
# G. MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
In 2025-26, CARA continued to use a multi-pronged monitoring strategy to ensure a clear view of the quality and pace of delivery across its seven components. The programme continues to use this approach to inform various decisions, including future workplans and focus areas. CARA team members undertook a series of field visits, covering projects from groundwater management (in Sri Lanka) to various LLAF projects in Southeast Asia and Pacific Island Countries (PICs). The team visited LLAF projects in Laos, Fiji, Timor Leste, delivering a variety of sectoral issues: community led adaptation, NbSs, water management, and flood control.
The team also participated in various CARA IP hosted events and interacted with event participants, community members, country office staff, ADB/WB staff, government officials and CARA project beneficiaries such as business entrepreneurs etc. To ensure VfM, CARA programme leveraged FCDO’s in-country posts to undertake field visits for LLAF projects, where post-based colleagues conducted visits to CARA-supported activities in their host countries to monitor delivery and provide on-the-ground assurance.
To date, no monitoring field visits have been undertaken for the CRPP; given CRPP has delivered a series of community-level consultations and trainings in Nepal, Indonesia and Laos, and has begun implementing conditional cash transfers in Nepal and Indonesia, it is now imperative to schedule MEL field visits.
For this annual review, a few changes were made at the output level in CARA’s portfolio-level Results Framework (RF) to better capture activities delivered across the seven components and, therefore, the pathways to desired change. Last year’s RF (i.e. 2024-25) had an output indicator on assets and tools[21]; to avoid having too many outputs and overlap with other indicators, this output was dropped in this Year’s RF (2025-26) and was replaced with a new output on the LLAF (OP 6). This was done since the nature and delivery of LLAF is different from other CARA components, and to ensure that progress and results are systematically captured.
[21] Develop, maintain or support tools, mechanisms, instruments, procedures, or systems (soft & hard) that strengthen capacity of govt. or non-govt actors across a range of adaptation/resilience related pathways, such as mobilisation of climate finance, governance of climate finance, production and delivery of weather and climate services and so on.
CARA is in its fourth year of implementation, and the programme is now generating evidence related to how “upstream” investment work contributes to outcomes and impact on the ground. The CARA team, in collaboration and coordination with the external MEL supplier and CARA IPs revised CARA’s portfolio-level results framework (RF) in 2025 to track the progress against the various stages of investment. This year’s RF (2025-26) has an emphasis on documenting the evidence on the uptake and utilisation of various deliverables such as TA, equipment (bought with CARA resources). This was done through a mix of quantitative and qualitative surveys to address the evidence gap on how well the upstream support is translating into downstream effectiveness to produce outcome-level results. Additionally, the CARA MEL Supplier conducted external case studies on the CFN and HI-REAP components. Information from the case studies is incorporated in this report and will guide future strategies and planning for the CARA programme.
# Annexure
## Annex 1: Lessons and recommendations from last year’s annual review and progress made against them
Lessons and recommendations from last year (2024/25)	Progress made in 2025/26
Lesson: Despite an increasing rate of output delivery over this year, current monitoring and annual reporting of the three Trust Funds - RAP, URTF and CRPP. Together, URTF, CRPP, and RAP will approximately use 60% of CARA’s resources. - largely capture the upstream Technical Assistance (TA) support provided, with little focus on the progress of investments after implementation. This is needed for continual assessment of potential impacts, to adjust the projects where required, and to support efforts to attract further sources of finance. / Recommendation: CARA’s MEL team, along with the MEL Supplier, to work with the IPs of the three multilateral Trust Funds, to develop an approach to track progress of investment projects. Proposed approaches to be shared with the IPs before August 2025.	CARA team, in collaboration and coordination with external MEL supplier and CARA IPs revised CARA’s portfolio-level results framework (RF) in 2025 and added new indicators to track the progress against the various stages of investment. Additionally, an Excel tracker sheet was developed for all the CARA programmes to routinely monitor and update the status on a quarterly/biannual basis.
Lesson: The Flexible Fund (FF) has delivered strong results to date and demonstrates the value of demand-led work on adaptation. However, after nearly two years of operation, the approach and results from the FF need to be more closely integrated into CARA’s wider portfolio level results framework, reflecting progress and learning to date. / Recommendation: FCDO to develop a Theory of Change (ToC) for CARA’s Flexible Fund component and a monitoring mechanism that is integrated into the programme’s portfolio level results framework, by July 2025. This will make reporting and assessment of impacts easier and clearer, and support development of future projects based on outcomes.	The CARA team developed the Theory of Change (ToC) for the Flexible Fund (LLAF) and a set of indicators, which were subsequently incorporated into CARA’s portfolio-level results framework (RF). The team also developed an annual progress reporting template and a project completion report template to capture and standardise information.
Lesson: Mobilising finance for adaptation, resilience and nature is very difficult. Unsurprisingly, CARA is achieving more success in influencing finance flows, and shaping investments for delivering adaptation objectives, from existing MDB funds, compared to mobilising additional finance from sources beyond MDBs. / Recommendation: By the end of July 2025, the CARA team will develop separate indicators for influencing, shaping, and mobilising, finance, to monitor progress.	In addition to revising CARA’s portfolio-level RF by adding new indicators to reflect the stages of capturing finance mobilisation, an Excel tracker sheet was developed for all the CARA programmes to routinely monitor and update the status on a quarterly/biannual basis.
Lesson: Gender Equality, Disability, and Social Inclusion (GEDSI) integration into CARA’s indicators and workplans requires further focus and refinement. There is also a need to account for disability indicators as well as gender. However, work has already begun via a Community of Practice (CoP) group, which meets regularly to develop a CARA-wide GEDSI strategy. / Recommendation: The CARA MEL team to work with the MEL Consortium to finalise and implement the CARA-wide GEDSI strategy, by July 2025. The team will also work with the IPs to i) refine their MEL frameworks, (ii) agree on the final CARA GEDSI strategy, (iii) GEDSI integration into CARA’s indicators and workplans, (iv) harmonisation with overarching ToC.	CARA team advanced the CoP by having regular interactions with CARA’s six IPs. This CARA-GEDSI CoP held deep dive sessions during 2025-26 which covered topics ranging from gender inclusive climate finance, impact of climate change on violence against women and girls, child protection and climate change, mainstreaming gender in infrastructure projects and working with grassroots women’s organisations to promote climate resilience. The first part of a Draft CARA-GEDSI strategy was developed in 2024-25 and this year, CARA’s MEL partner, Triple Line further worked on co-developing the operational part of the strategy through a consultative process with each component partner. The team also delved deep into developing qualitative indicators for GEDSI which have been incorporated in the revised Results framework of CARA. The GEDSI strategy is expected to be finalised mid-2026.
Lesson: As a longer-term programme, CARA is a valuable tool for building adaptation and resilience, as climate adaptation efforts take time to show significant impact and require long-term support. However, CARA also needs to demonstrate intermediate outcomes and impacts to ensure good engagement and cooperation with key stakeholders, and multiply possibilities to influence. / Recommendations: CARA IPs should prioritise tracking progress and the intermediate changes arising from projects on the ground, allowing for a clearer demonstration of progress toward outcomes and, eventually, impacts. Likewise, the CARA team will need to develop and strengthen mechanisms that incentivise IPs to improve their focus on the dissemination and engagement around outputs such as knowledge products, and, track the uptake and use of these output level products and services, rather than only monitoring the volume quantity (e.g. numbers of events, numbers of people attending, etc.) of those products. / IPs leads should work with the Communications and Engagement Officer and MEL Consortium on increasing strategic influence over the next six months. Dissemination efforts do not achieve impact without targeted stakeholder engagement, and so communications and engagement work should not just focus on distributing Knowledge Products (KPs), but develop plans for specific changes. These changes will require sustained engagement in priority areas to influence policies or implementation efforts.	Over the past year, the CARA team worked with Triple Line to conduct a survey with all IPs and prepare a tailored knowledge management strategy. This surfaced gaps in current practices and offered specific recommendations on how partners could shift away from quantity-based reporting toward capturing uptake and use. / In addition to periodically populating the CARA website, the CARA team also developed dedicated trackers for publications, events and progress of LLAF projects to improve oversight of outputs and enable more systematic monitoring of progress. / The team also worked to embed impact storytelling across partner communication (working with WISER to document impacts of their wheat disease work, guiding CRPP to report their activities more regularly, working with CFN and HI-REAP to jointly curate events and participants, and providing editorial and design support to smaller LLAF partners) and prepare thematic notes for targeted stakeholder engagement at major regional events. Efforts also extended to influencing institution-wide processes with multilateral partners, with ADB’s central communications division formally listing strengthening communications and donor visibility as a key priority in their start-of-year newsletter.
Lesson: There are many challenges involved in translating national level climate policies and changes into sub-national implementation plans, requiring targeted support. Many CARA interventions and engagements to date have focused on national government engagement, however, it is equally important to engage and build the capacity of local governments, institutions, communities and civil society organisations to enhance the effectiveness of adaptation processes and interventions, ensuring that they are more inclusive, context-specific, and sustainable in addressing local challenges. / Recommendation: IPs to consider the links between their national level initiatives and translating these to subnational level in their workplans for the next year, by the end of July. CARA team and IPs to work together to identify priority areas.	CARA IPs will identify few areas to link between their national level initiatives and translating these to sub-national level in their workplans for 2026/27 and the workplans is expected to be submitted in the end of April 2026.
Lesson: IPs are already coordinating workplans and collaborating in certain areas of their programmes. For example, RAP and WISER on weather and climate services. However, a greater focus on coordination will arise as CARA’s implementation continues to ramp up (against an increasingly challenging fiscal environment), to ensure efficiency and maximise impacts. / Recommendation: In 2025-26, CARA IPs will continue to synergise their efforts and coordinate approaches wherever feasible, to maximise efficiency and increase effectiveness. This should also include ways of creating a more enabling environment that fosters and encourages private sector and other alternate sources of financing for climate adaptation.	CARA team had regular (monthly) catch-up call with each of the six CARA programmes and quarterly calls with the LLAF IPs to ensure synergies and coordination.

## Annex 2: CARA programme’s Theory of Change (ToC)

## Annex 3: List of all the LLAF fund projects[22]
[22] Projects in Blue cells are currently active projects, while the ones in Green are completed projects.

No.	Country	Partner Name	Project Name
1	Bangladesh	United Nations Development Programme (UNDP)	Next-Generation Urban Resilience: Leveraging Locally Led Adaptation (LLA) and Nature-based Solutions (NbS) for Shaping Sustainable and Adaptive Cities in Bangladesh.
2	India	British Geological Survey (BGS)	Recharge for Resilience: Understanding the evolving nature of groundwater recharge for adaptation and resilience of Agriculture and Water Supply in North-West India
3	India	World Resources Institute India	Strengthening heat resilience in Tamil Nadu through building technical capacities and identifying channels for mobilising finance
4	Indonesia	UNDP	Leveraging Village Funds for Climate Action in Indonesia
5	Laos	Clovek v Tisni, O.P.S (People in Need)	Building Climate Resilience through Scalable Early Warning System
6	Laos	World Wildlife Fund for Nature (WWF) Laos	Safeguarding the Mekong: Advancing sand governance and biodiversity protection for climate resilience in Laos
7	Malaysia	British Geological Survey	Trigger Index for Rainfall‐Induced Landslide Risk Assessment for Enhanced Resilience (TRIGGER)
8	Malaysia	Forever Sabah	Tackling the climate-poverty nexus in palm oil: Co-designing a scalable transition to beautiful, bountiful and resilient agroforestry with smallholders in Sabah, Malaysian Borneo
9	Malaysia	Monash University Malaysia	Building Climate-Resilient Communities through Integrated Water-Energy-Food-Environment Nexus
10	Malaysia	UNDP	Scaling Climate Adaptation Financing in Malaysia
11	Maldives	UNDP	Transforming the Blue Economy with Maldives MSME Empowerment and Blended Finance: Phase 2
12	Myanmar	WWF Myanmar	Accelerating Bottom-up Climate Action Through Community Empowerment
13	Papua New Guinea	Baluan Development Association (BDA)	Using the climate-smart landscape approach for building climate-resilient agriculture & forest ecosystems in Baluan Island, Manus Province, Papua New Guinea
14	Papua New Guinea	Conflict Islands Conservation Initiative (CICI)	Empowering Community Conservation Rangers: Advancing Protected Area Development and Climate-Resilient Conservation in Papua New Guinea
15	Papua New Guinea	International Organisation for Migration (IOM)	Strengthening Community Resilience and Climate Adaptation through Inclusive Agricultural Value Chains in the Atolls of the Autonomous Region of Bougainville
16	Philippines	Catholic Relief Services	Climate-resilient Cities - NURTURE: Nature-based Urban Resilience Through Unifying and Responsive Engagement (CRC- NURTURE)
17	Philippines	UNDP	Climate Resilience in Action: Strengthening National Systems for Impact: A Strategic Initiative to Support the Philippines’ Role in Global Climate Governance and Hosting of the Fund for Responding to Loss and Damage
18	Regional – Indo-Pacific	Asian Development Bank (ADB)	UK ADB Partnership Nature and Food Partnerships under the CARA Programme
19	Regional - Pacific	Conservation International	Sustainable Blue Pacific Initiative - Supporting Pacific Island Countries to Sustainably Manage and Protect their Oceans
20	Regional - Pacific	UNDP	Governance for Resilient Development in the Pacific (Gov4Res)
21	Regional - Pacific	WWF Fiji	Resilient Communities: Nature-based Solutions as adaptation strategies strengthening community food systems and livelihoods
22	Regional - South Asia	Conservation International	Mountains to Mangroves Atlas: Nature Restoration & Conservation Mapping for Climate-Resilient Eastern Himalayas
23	Regional - South Asia	ICIMOD	Promoting Resilient Agroecological Systems (PRAS) in Western Nepal and the HKH
24	Regional - South Asia	United Nations Economic and Social Commission for Asia and the Pacific (UN-ESCAP)	Risk and Resilience Portal: Multi-hazard Coastal Analysis and Adaptation
25	Regional - South Asia	UN-ESCAP	Enabling Urban Action to Enhance Climate Resilience in Asia
26	Regional - South Asia	Women's FUND Asia	Advancing climate resilience & adaptation through a gender equality lens in Asia
27	Regional - Southeast Asia	Mekong River Commission (MRC)	UK MRC Partnership
28	Solomon Islands	Secretariat of the Pacific Regional Environment Programme (SPREP)	PRISMSS Natural Enemies – Natural Solutions (NENS) for the Solomon Islands
29	Solomon Islands	World Vision Solomon Islands	Building Climate-resilient Communities in Solomon Islands
30	Sri Lanka	International Water Management Institute (IWMI)	Improving groundwater management in the Jaffna Peninsula – Phase 2
31	Thailand	Food and Agriculture Organisation (FAO)	Localisation of adaptation priorities including Nature-based Solutions (NbS) and strengthened climate and disaster risk finance in climate-vulnerable areas of Thailand
32	Timor-Leste	World Vision New Zealand	Building Resilience and Assets for Food Security Systems (BRASS) Phase 2
33	Vietnam	British Red Cross / Viet Nam Red Cross Society (VNRS)	Strengthen inclusive climate resilience and disaster response through access to blended and climate finance
34	Vietnam	UK Met Office	Co-production of localised climate risk profiles for sustainable climate adaptation
35	Vietnam	United Nations Children Fund (UNICEF)	Climate-Smart Evacuation Centre : Advancing Child-Centred Climate Resilience in Viet Nam
36	Timor-Leste	Adventist Development & Relief Agency (ADRA)	Revitalising Ecosystems & Village Inclusion for Vulnerability Elimination (REVIVE)
37	Regional - Southeast Asia	UNDP	Analysis of impact of CC on unpaid care workers
38	India	British Geological Survey (BGS)	Potential research study on extreme flooding events and groundwater implications
39	Regional- Pacific	United Nations Capital Development Fund (UNCDF)	Climate Disaster Risk Insurance
40	Regional- Pacific	Mulberry Leaf	Scoping study- 'UK Strategy on Disaster Risk Finance in the Pacific'
41	Regional- Pacific	Talanoa Consulting	Capacity Building Workshop in Proposal Writing
42	Regional- Pacific	Secretariat of the Pacific Regional Environment Programme (SPREP)	Invasive species management and habitat restoration projects
43	Nepal	ICIMOD	HI-REAP will contribute to CARA outcomes through inclusive and climate-resilient communities.
44	Papua New Guinea	Baluan Development Agency (BDA)	Water storage for secondary use
45	Samoa	UNDP	CERO waste
46	Sri Lanka	International Water Management Institute (IWMI)	Improving Groundwater Management in the Jaffna Peninsula, Sri Lanka
47	Thailand	Food and Agriculture Organisation (FAO)	Strengthened capacities and local-level plans for climate change adaptation in agriculture in Thailand
48	Thailand	UNDP	Blended Finance Activity - CFN
49	Timor-Leste	Adventist Development & Relief Agency (ADRA)	Improve community resilience and climate adaptation utilising NbSs and participatory processes.
50	Timor-Leste	World Vision	Building Resilience and Assets for Food Security (BRASS)
51	Tonga	Red Cross	BRICS - TRC

## Annex 4: Value for Money

During the review period, the programme continued to represent strong Value for Money (VfM) across all pillars of the FCDO 5E framework. Evidence shows that programme resources were used economically, efficiently, and equitably to achieve high‑quality climate resilience outcomes at scale. VfM was assured through disciplined cost control, strategic use of technical expertise, and deliberate alignment with national priorities, regional platforms, and multilateral investments.

1. Economy / Across delivery partners, inputs were procured at the right price and quality while keeping administrative costs low. Overall, inputs were procured economically while safeguarding the quality of technical outputs.	ADB–URTF controlled costs through reliance on ADB’s staff and systems, limiting Secretariat expenditure to $1.66M cumulative while ensuring high-quality design support. / ADB–CRPP used competitive procurement, pooled resources across the Trust Fund and Investment Fund, and leveraged ADB’s financial management and technical systems to minimise duplication. / ICIMOD HI-REAP used competitive bidding, combined events (e.g., GIREE Summit + Investment Dialogue), and adopted IFRS-based cost controls to avoid unnecessary expenditure. / UK Met Office/WISER AP maintained strong budget control, with most activities under budget and substantial co‑financing from WMO, CREWS, IMD, and the World Bank. / World Bank RAP ensured cost-conscious procurement by combining international expertise with in‑house technical capabilities, minimizing consultant time while maximizing precision. / CFN (UNDP) kept costs low by leveraging UNDP core staff, economist networks, and retainer experts, significantly reducing reliance on external consultancy spending.
2. Efficiency / Delivery systems converted inputs to outputs with high productivity. / Across all partners, efficiency was strengthened through partnerships, co‑financing, harmonized systems, and deliberate design choices that produced multiple outputs from single investments	URTF integrated fully into ADB’s business processes, used framework agreements to reduce transaction costs, and strengthened funding review processes to ensure readiness. / CRPP achieved efficiencies by aligning the Trust Fund and Investment Fund under one facility, enabling seamless programming and strong co‑financing ratios (IF ratio 1:5.8). / ICIMOD achieved efficiency through strategic partnerships (Helvetas, CEAPRED, LI‑BIRD) and co‑financing (USD 22,000), enhancing delivery without proportional cost increases. / WISER AP leveraged regional platforms and partner contributions, delivering activities quickly and cost‑effectively despite budget uncertainty. / World Bank RAP maximised efficiency by integrating workshops with policy dialogues and coordinating travel with operational missions. / CFN ensured efficiency by aligning with related UNDP regional programmes and co‑financing (Sida, DFAT), streamlining analytical work and accelerating implementation.
3. Effectiveness / The programme demonstrated strong progress in converting outputs into outcomes, with several partners exceeding annual targets. Effectiveness was strengthened through policy influence, capacity building, catalytic programming, and integration into large-scale investments.	URTF ensured upstream resilience integration; its $48.02M in commitments leveraged $1.02B in downstream investments. / CRPP exceeded its 2025 financing mobilisation target ($273M), influenced major policy reforms (e.g., Bangladesh locally led adaptation framework), and strengthened design quality across ADB’s portfolio. / ICIMOD achieved durable policy uptake (e.g., Nepal’s Karnali Agriculture Strategy; Bhutan Rangeland Guidelines) and embedded NbS into academic curricula. / WISER AP met or exceeded all 2025 targets, establishing foundational regional partnerships (RIMES, AHA Centre, MRC) that enable future transformational impact. / World Bank RAP informed $3.49B in World Bank investment projects, shaped national action plans, and catalysed regional cooperation on air quality, biodiversity, and cooling. / CFN translated analytical work into practical financing strategies and institutional reforms, supporting adaptation finance, climate budgeting, and gender-responsive planning
4. Equity / Equity—including gender equality, disability inclusion, youth, and marginalised groups—was embedded across all programmes. / Programme benefits were distributed fairly and equitably, strengthening resilience for the most vulnerable	URTF institutionalised GESI integration and delivered targeted initiatives such as ASPIRE (women in public service) and participatory design with youth in the Nusantara GREEN project. / CRPP performed strongly, with all projects meeting GEN/EGM criteria, pilots through the Gender Window, and systematic disaggregation of beneficiary data. / ICIMOD ensured inclusive participation of women, youth, and marginalised groups, supported women-led enterprises (HKH‑ICE), and embedded equity in all NbS pathways. / WISER AP intentionally designed projects to reach women, youth, and people with disabilities, with GEDSI central to future planning. / World Bank RAP embedded gender-sensitive approaches in biodiversity, air quality, and livelihoods, ensuring equitable participation and more inclusive policy outcomes. / CFN integrated equity into climate finance systems, enabling gender-responsive budgeting, women-led climate MSMEs, and inclusive investment frameworks.
5. Cost-Effectiveness / Across the portfolio, modest FCDO investments unlocked multi-million-dollar policy, financing, and institutional outcomes with high leverage and catalytic effects.	URTF: $48M in support leveraged $1.02B downstream (over 1:20 leverage). / CRPP: small TF allocations catalysed large-scale investment (e.g., $613k → $70M in Cambodia). / ICIMOD: co‑investment models and private sector contributions (e.g., Bhutan heating pilot) reduced programme costs. / WISER AP: high-reach activities and regional platforms magnified impact beyond project budgets. / World Bank RAP: linked analytical work to $3.49B in WB investments and unlocked additional funding (e.g., CREWS $5.25M; Swiss $9.5M). / CFN: amplified FCDO resources through UNDP core financing, Sida, and DFAT support, enabling system-level reforms at low marginal cost.