## Annual Review 2025

Title: Local Infrastructure Support Programme (LISP) Transition/Initial Implementation
Programme Value £ (full life): £98.1m		Review date: September 2025
Programme Code : 301010	AMP start date: 17 March 2023	AMP end date: 30 September 2029

Summary of Programme Performance
Year	2024	2024 (refresh)	2025
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004648.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004584.xlsx

## A. SUMMARY AND OVERVIEW
The Local Infrastructure Support Programme (LISP) is the British Embassy Kathmandu (BEK)’s initiative to support the Government of Nepal (GoN) to enhance the capacity of its sub-national governments to deliver resilient, inclusive, and sustainable infrastructure. The programme’s goal is to empower local and provincial governments to effectively respond to citizens' demands for local infrastructure, thereby increasing their legitimacy and accountability. A strong focus is placed on empowering women and marginalised communities, creating green recovery jobs, stimulating the local economy, and building climate resilience into all projects
[note] LISP currently features three components: Technical Assistance and Innovation, Evidence and Learning (IEL) – led by DT Global; and IVQA (Independent Verification and Quality Assurance), an independent technical verification and quality assurance component implemented by Pegasys.
LISP is jointly implemented by the GoN and BEK under an MoU signed on 16 March 2023. With a planned total value of £98.1 million in grant support to Nepal under LISP over the period 2023-2029, the programme was expected to provide both technical assistance (TA) and performance-based financial aid (FA) to the GoN until 2029, with a focus on local governments (LGs). Target LGs are expected to co-finance up to 40% of the capital infrastructure cost, a key component for building ownership and sustainability.
LISP delivers its objectives by providing a combination of TA and performance-based FA for local infrastructure. The programme strategically utilizes existing government systems. LISP incentivizes LGs to improve their performance in infrastructure service delivery by strengthening existing government systems, adopting systems-building approaches, and fostering innovation and learning to enhance national and local policy and practice. This approach aims to create green recovery jobs, stimulate local economies, and build climate resilience across the country.
LISP has followed a carefully phased implementation strategy to facilitate iterative learning and scaling:
- Design and Pilot (November 2021 – June 2023): Focused on programme design and initial piloting in 15 LGs in Karnali.
- Transition Phase (July 2023 – July 2024): Aimed at deepening learning in the same 15 LGs in Karnali and preparing for comprehensive scale-up.
- Full Implementation Phase (from July 2024): The current phase and object of this review: this phase focuses on comprehensive roll-out based on lessons learned from the preceding phases, and transitioning both in terms of TA arrangements (from the previous TA supplier WFP to a new supplier – DT Global) and with respect to the introduction of a full GoN-embedded financing modality through FA channeled through the treasury.
This annual review covers the first year of the full implementation phase, aligned to the GoN fiscal year (FY) that runs from mid-July to mid-July each year. While the current Nepali FY started in July 2024, construction cycles normally start during the autumn (September) and run till the end of the FY (July), depending on subnational seasonal variability. The review hence focuses on the period September 2024- August 2025, with most data updated up to August 2025.
During this period LISP transitioned to an on-budget / on-treasury funding mechanism (via FA), which institutionalizes its financial flows within the GoN's system. The programme successfully onboarded a new primary TA supplier, DT Global, in partnership with CARE International, and an Independent Verification and Quality Assurance (IVQA) supplier, Pegasys. Over the review period, the geographical reach of LISP expanded from 15 LGs in Karnali Province to 35 LGs across both Karnali and Lumbini provinces for F/Y 2024/25 activities. In addition, LISP supported Ministry of Federal Affairs and General Administration (MoFAGA) to select addition 15 LGs (5 in Karnali and 10 in Lumbini) for F/Y 2025/26. The 35 LGs for F/Y 2025/26 and additional 15 LGs for F/Y 2025/26 were selected through a transparent, evidence-based "opt-in" process that balanced vulnerability and capacity. During this review period the LISP-TA team engaged with 50 LGs at settlement, ward, and LG level in the planning process for FY 25/26.
During the transition of TA delivery from the World Food Programme (WFP) to DT Global, WFP provided support to direct project planning and engineering assistance to ensure continuity, to March 2025. From April 2025, DT Global assumed formal responsibility, with a broader mandate that extends beyond engineering to include strengthening systems, governance, inclusion, climate resilience, disaster risk reduction, and public financial management. The Innovation, Evidence and Learning (IEL) component within DT Global also played a crucial role in shaping the programme's direction. In parallel, the IVQA supplier conducted three stages of independent verification, adding a further layer of accountability and quality assurance.
Local Context
Under LISP governance arrangements with GoN, the Secretary at MoFAGA chairs the LISP Steering Committee (SC), while the Provincial Principal Secretaries chair the LISP Provincial Coordination Committees (PCC). For most of the review period, the political environment in Karnali and Lumbini remained largely stable, allowing LISP to operate smoothly. While Karnali experienced some protests by government employees and routine staff transfers, these did not significantly disrupt programme activities. In a few LGs, by-elections temporarily shifted local leaders’ and LG staffs focus on campaigning, requiring LISP to adopt a flexible and adaptive delivery approach. Overall, this stability enabled the continuation of technical support and capacity-building initiatives.
A major challenge across both provinces—particularly in Karnali—has been the acute shortage of human resources at the local level. High turnover and frequent vacancies in key positions such as Chief Administrative Officers (CAOs) and engineers have slowed project planning, procurement and implementation in some areas. These gaps have directly impacted the preparation of Detailed Project Reports (DPRs), bid evaluations and construction supervision, contributing to suboptimal infrastructure choices in some LGs and, to some extent, lower capital budget execution rates (though the issues causing this are multifaceted). In some LGs, tensions between political leaders and government staff further weakened institutional capacity. To mitigate these issues, LISP provided embedded technical support to fill critical gaps and sustain project delivery, though long-term solutions are still needed to address systemic staffing shortages.
In Karnali, GoN reconstruction efforts following the November 2023 Jajarkot earthquake were slower than expected due to delayed reconstruction funding disbursements from FGs/NRA, administrative bottlenecks and new documentation requirements for fund distribution. Many households remain in temporary shelters as detailed damage assessments and beneficiary identification processes continue. However, LISP reconstruction interventions were successfully completed. Despite the pressure to address affected communities’ needs, earthquake-affected LGs (Aathbesakot, Nalgad, Shivalaya) maintained their co-financing pledges to the main LISP component, demonstrating strong ownership and commitment to programme objectives.
At the national level, LISP has contributed significantly to policy development, providing technical assistance to MoFAGA in completing the Nepal Local Infrastructure Sector Assessment, drafting a revised national infrastructure policy (though its progress to policy has stalled under shifting MoFAGA leadership) and supporting the development of GoN-owned LISP Operating Procedure. This reflects LISP’s positive influence in shaping infrastructure governance and aligning local development with Nepal’s federal constitutional framework.

Recent political turmoil
On 8 September, the killing of dozens of ‘GenZ’ protesters opened the door to two days of intense protests in Kathmandu and in other areas of the country, causing the PM’s resignation and leaving over 70 killed and over 1000 injured. Damage to property and infrastructure alone is estimated to cost up to $1 billion.
Following this swift revolt, the establishment of an interim government creates a different, more protracted and less clear state of crisis, dominated by uncertainty on how the context will evolve until and beyond new federal elections on 5 March 2026.
The interim government faces significant challenges, ranging from the operational and financial challenges of reconstruction and the organisation of elections, high expectations from “Gen Z” and other segments of the population in terms of change (especially against corruption), backlash from traditional parties, and shielding the economy from potential long-term consequences.
While the troubles have mostly concentrated in Kathmandu and larger cities across the country, they might have implications for LISP. The delivery of LISP requires stable administrative functions, timely intergovernmental transfers and functional administrations at the local level. Early assessment indicates near-to-normal circumstances for LISP delivery (and known systemic issues), but BEK will need to monitor the evolving context up to and after the March elections to promptly identify and manage emerging risks (see Section E for details or Risk Management).

UK and International Context
Over the past year, Nepal—like many countries dependent on international aid—has faced major disruptions due to shifting donor priorities and declining global aid flows. In early 2025, the abrupt termination of 34 USAID-funded projects by the US government severely impacted programmes in infrastructure, energy, agriculture and disaster resilience. Local governments were left scrambling to secure alternative funding for ongoing development efforts. While LISP delivery was not directly affected, the loss of USAID support reduced opportunities for collaboration at the local level and weakened broader development support available to the GoN, particularly in infrastructure.
Soon after, the UK’s decision to reduce its ODA allocation from 0.5% to 0.3% of Gross National Income (GNI) by 2027 triggered a global contraction in FCDO’s bilateral aid portfolio. In Nepal, this led to a 15% budget cut in the current fiscal year, reducing LISP programme scope and funding. Further reductions were expected in FY 2026/27, and given LISP’s large scale and cost, the British Embassy Kathmandu (BEK) has decided to phase out LISP by March 2027. This decision reflects a broader shift in UK aid strategy in Nepal, focusing limited resources on green growth, climate and resilience, and human capital – with a focus on urban areas – as drivers of economic transformation.
Other donors are also reprogramming toward narrower, results-based support. The Swiss Agency for Development and Cooperation (SDC) has withdrawn from direct bridge and road support, creating potential gaps in donor financing for local infrastructure. However, multilateral institutions like the Asian Development Bank (ADB), World Bank (WB), and the European Union (EU) remain active in large-scale infrastructure—particularly in roads, bridges, urban development, and agriculture—though their focus is less on community-driven, local infrastructure. LISP will capitalise on opportunities to align with these initiatives, drawing on their technical expertise to strengthen its delivery and inform its transition and exit strategy.
In summary, the combined impact of USAID’s exit, UK’s ODA cuts, Switzerland’s strategic shift, and evolving donor priorities has reshaped Nepal’s infrastructure funding landscape. Provinces like Karnali, where local infrastructure needs are high, face a turning point. While LISP has shown strong local ownership and alignment with federal priorities, Nepal now relies on loans for up to 70% of its foreign aid, with concerns about its ability to meet Sustainable Development Goals (SDGs) and graduate from Least Developed Country (LDC) status by 2026. Novel climate finance instruments offer promising paths forward. Success will depend on Nepal’s ability to strengthen governance, secure such financing and ensure infrastructure investments are resilient, inclusive, and locally-driven.

Summary supporting narrative for the overall score in this review
LISP is a high-risk, high-impact programme that just entered its main implementation phase in early 2025. Despite the inherent challenges of transitioning both capital funding (from WFP-controlled mechanism to FA through Nepal’s intergovernmental fiscal systems) and technical support (from WFP to a new supplier in DT Global – see section E), the programme is on track to deliver most of its logframe objectives for this review period, hence justifying the overall score of ‘A’.
Given mobilisation delays and modality changes, LISP has demonstrated significant performance and resilience. The difficult but relatively successful transition to the main implementation phase—marked by the onboarding of DT Global in late 2024 / early 2025 and expansion to 20 additional LGs and an entirely new geographical area (Lumbini province)—were major milestones. The programme’s ability to maintain good levels of output delivery and a focus on institutional strengthening during this complex shift reflects its robust design and adaptive management approach, which included flexible contract management (see section E). Most of the overarching recommendations from the previous Annual Review were geared towards continuously guiding the LISP throughout the phase, and most recommendations remain valid and are in progress
Field visits throughout the spring 2025 and then again in August 2025 confirmed positive trends around improved deliberative processes and inclusive planning in target LGs. Conversations with local authorities and communities validated the shift toward strategic infrastructure selection and reduced planning biases. These insights underscore the programme’s early successes in promoting institutional change at the local level
Summary progress against Outputs
- LISP successfully achieved all targets under Output 1, demonstrating effective institutionalisation of improved systems and processes for local infrastructure governance, as demonstrated by the formalised adoption of bespoke infrastructure governance guidelines at municipal level approved by local executives (see section C for details). This has created the enabling policy environments for stronger local ownership and practices in targeted LGs, although improving operational uptake is the key future challenge for LISP.
- Progress against Output 2 (capacity building) is good. All targeted LGs prioritized larger-scale (relative to past practice), labour-intensive, disaster and climate-resilient infrastructure projects in FY 2024/25. Officials also received technical support to enhance inclusive planning and infrastructure management. There is still major scope for improvements, as shown under the lessons and recommendations below.
- Progress against Output 3 (on budget and spend improved) is positive, with most targets achieved or slightly exceeded, with the significant exception of budget absorption in co-financed infrastructure projects, which has proven lower than expected.
- Output 4 milestones were well achieved, with 302 infrastructure schemes constructed or rehabilitated across 35 LGs in FY 2024/25—exceeding the annual target of 287. Of these, 81% incorporated climate resilience and DRR features, and 44% included GEDSI elements. In addition to these results, 60 reconstruction projects were support under the LISP-REDI sub-component in response to the Jajarkot earthquake.
- Good progress has been made against Output 5 in employment generation, with significant numbers of workdays created for poor women and disadvantaged groups, though collecting job-related data has proven more complex than anticipated.

Major lessons and recommendations for the year ahead
The following lessons and recommendations are crucial to consolidate the gains from this review period and ensure the programme's long-term sustainability and impact.
Risk Management
While most risks identified under LISP have been adequately managed so far, fatal incidents in Humla and Jumla during the review period highlighted serious gaps in safety awareness and implementation, underscoring the inadequacy of current measures. Enforcement of health and safety measure at the local level remains weak due to the absence of localized tools, ineffective enforcement mechanisms and a loose safety culture, with safety considerations often treated as secondary rather than being integrated throughout the infrastructure cycle.
[note] June 2025, two tragic incidents occurred at separate LISP supported project sites in Humla and Jumla districts of Karnali Province, resulting in one fatality at each location and several injuries. In the first accident, an unregistered substitute worker died due to injuries caused by a sudden slope failure during trench excavation for a gabion retaining wall, which also cause one severe and four minor injuries (all recovered). The second incident involved a tractor used to carry stones losing control and slipping off the edge of a narrow road and falling approximately 40 meters down a slope. registered UC worker, suffered a fatal head injury after being struck by the tractor, while one other person was injured. These accidents prompted an immediate reassessment of existing safety protocols, operational practices and mitigation planning that are being integrated into the upcoming infrastructure cycle, both within revised LISP Operating Procedure and in practical toolkits.
LISP TA team was tasked to develop simple, ready-to-use tools and training materials in local languages and support regular safety training. As a follow up, LISP (DT Global) must provide continued support towards strengthening local enforcement and promoting a culture of safety to prevent future incidents and ensure safer infrastructure delivery (throughout the construction cycle). Additionally, health and safety considerations should be formally included within LISP Operating Procedure that is currently revised by MoFAGA / GoN (October 2025).

Novel Contextual Risks
Nepal’s interim government and upcoming elections pose risks to LISP delivery, including delays in budget approvals, procurement restrictions and reduced responsiveness from local governments, which may risk disrupting infrastructure timelines and financial aid disbursements for this upcoming construction cycle.
Key LISP actors can mitigate these risks through bespoke measures: MoFAGA should issue temporary operational guidance to LGs; DT Global should fast-track procurement and strengthen contingency planning; BEK should provide political monitoring support to promptly identify deterioration in the operating context. Early works initiation and clear communication with communities will help maintain delivery and safeguard programme integrity.

Financial and Fiduciary Risk
Given the size of FA relative to other programme’s expenditures (ratio of 3:1 in the BC), and the operating model channelling capital funds through the Nepal’s Treasury systems, fiduciary risk management is a fundamental element within the broader risk management systems of LISP.
As the programme approaches the milestones for disbursement, it’s critical that all stakeholders (LISP TA/DT Global, IVQA/Pegasys, MoFAGA/GoN and BEK) adhere to the mitigation measures detailed in the 2023 LISP Fiduciary Risk Assessment (FRA) and the associated Fiduciary Risk Management Implementation Plan (FRMIP). An Annual Statement of Progress (ASP) is currently being carried out to inform FRMIP improvements going forward, and the Memorandum of Understanding (MoU) between the UK and the GoN governing LISP foresees a bespoke review of LISP by the Office of the Auditor General (OAG) audit mechanisms to enhance accountability.

Programme delivery
The current cluster team deployment model appears insufficiently sized to provide the required level of support, given the insights the local capacity assessment carried out in June 2025 (see section C), thus limiting capacity support coverage and responsiveness and reducing quality of outputs (especially, quality of infrastructure choices). DT Global should review their TA operational modality that is adaptive to LG needs. Options like the integration of “surge engineers” and “surge governance specialists” was widely appreciated by LGs and could be part of a systemic, revised approach to responsive, flexible TA support.
Based on lessons learned, DT Global must revise their operational strategy to prioritise equitable and consistent TA presence across all LGs (October 2025), hence improving the quality of local infrastructure delivery. Such revised operational modality should also promote more interactive peer-to-peer collaboration and coordination across LGs and other key stakeholders, to foster stronger relationships, shared understanding of the programmes’ goals and locally driven changes in practice related to local infrastructure development.

Evidence-based and deliberative decision-making
LISP’s support has significantly improved infrastructure planning processes by promoting scoring tools at the local settlement and ward levels, leading to the selection of fewer but larger (and in general) more sustainable projects that benefit more people. However, challenges remain in the final stage of the 7-steps planning process—particularly within municipal assemblies—where final project selection often lacks transparency. As programme winds down in the fall of 2025, LISP (through DT Global) should focus its closing TA support to encourage needs-based and scoring-driven project prioritization, including thorough the promotion of transparent project banks, sector-specific master plans and flexible budgeting process (June-September 2026).

Moreover, LISP TA, in collaboration with BEK and relevant government counterparts, should fast-track analytical work to inform improvements in deliberative decision-making processes before the next planning cycle (before March 2026). The focus should be on enhancing evidence-based procedures and expanding deliberation beyond the early planning phases. A set of learning papers should be prepared and disseminated to inform the GoN and key technical assistance suppliers.

Intergovernmental coordination
While there’s a reasonably positive relation between MoFAGA and LGs, provincial governments represent an underutilized tier in supporting local infrastructure development. The level of coordination, collaboration and engagement with provincial governments for their support in LISP's planning and implementation has not been as strong as initially anticipated. Linkages between LISP and the Provincial and Local Government Support Programme (PLGSP), including their supported Provincial Centre for Good Governance (PCGGs), have not materialized as envisioned in LISP’s Business Case due to both LISP’s progress and, more critically, the reset of PLGSP into a second phase (PLGSP-II), not yet fully active. This represents a missed opportunity for synergy and mutual reinforcement of efforts to strengthen sub-national governance.
LISP should use its final year to promote engagement between LGs and provincial governments, extending beyond bureaucrats to include political leaders, to foster a more strategic collaborating framework around capital investment planning. LISP should also consider expanding its technical assistance support to provincial ministries to help bridge the emerging gap left by donor withdrawal (e.g., through seconding technical advisors, supporting policy shaping and strengthening subnational coordination mechanisms).

Capacity Building
During the AR field visits in both provinces, LGs expressed a strong need for capacity building support, particularly in implementing the LSIP improved modality and making infrastructure projects climate-resilient, sustainable and inclusive. Local governments face major shortages in qualified and experienced personnel, resulting in delays and suboptimal performance across basic steps of the construction management cycle (selection influencing, design, procurement, oversight). These gaps often undermine the appropriateness of infrastructure investment choices.
LISP (through DT Global) should prioritise a refined version of its structured training and mentoring capacity-building approach, focusing on sustainable, inclusive and resilient infrastructure development. More relevant to institutional capacity, LISP should encourage PGs and LGs to adopt such approach and allocate budget for regular capacity building, peer-to-peer learning and collaboration with technical institutions (academia, professional councils and private sector entities).

Crosscutting (Climate, Social and Economic Impact)
LISP has demonstrated a strong commitment to promoting social inclusion and gender equity, for instance through the active participation of women and marginalised communities in Users' Committees and the implementation of equal wage policies, providing women and marginalised communities access to job opportunities and pathways to improve their income and lives (feedback shared by women’s groups during AR visits). However, beneficiaries have expressed concerns about the sustainability of these benefits and the short-term nature of these changes.

LISP (through DT Global) should identify options to integrate strategies for long-term livelihood generation pathways into project design and implementation (e.g., hands-on training in construction-related skills; reliance on local, sustainable materials and technologies linked to local markets). While LISP might not be able to do this at scale within the current phase-out context, the programme might be able to help GoN’s relevant technical entities to revise local infrastructure policy aligned with the above ambitions.
Besides socio-economic considerations, climate resilience and inclusivity are cross-cutting issues, yet policies, codes and standards for climate- and disaster-resilient and inclusive infrastructure development remain limited and vary across sectors, resulting in inconsistencies in joined-up strategic planning, application and compliance.
To promote sector-wide harmonization, LISP could test the appetite for supporting federal and provincial authorities in developing and disseminating harmonized sector-wide policies, codes, and standards for climate- and disaster-resilient infrastructure across sectors (though cognizant of the new programme timelines and the mid-term implications of the recent political crisis).

Evidence & Learning
LISP’s multi-layered monitoring, evidence generation and learning systems (see section G) enabled real-time learning, revealing the value of adaptive, locally grounded approaches to infrastructure governance and inclusive development, as well as the extent of the challenges and obstacles to change.
BEK should turn LISP programme closure into a learning opportunity by promoting a structured, multi-stakeholder process to capture, synthesize and share lessons across government, partners and within BEK itself, informing future policy and programming.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
The LISP Theory of Change (ToC) postulates that by providing specialised technical assistance in key areas of infrastructure governance, incentivising rational investments in local infrastructure and mentoring local leaderships, local stakeholders (communities, bureaucrats, technical staff and local leaders) will be better equipped to plan, deliver and manage demand-responsive infrastructure that is inclusive and climate- and disaster-resilient, eventually improving legitimacy of government.
LISP ToC translates into a set of concrete output-level results that can be used as proxy of success, indicatively listed below – as per MoU and Programme Design Document (PDD) agreed with the GoN:
- Up to 1.7 million people with improved access to sustainable infrastructure services.
- 80- 100 LGs with improved capacity to undertake planning, budgeting, deliberative decision making, expenditure and delivery on local infrastructure services based on local level priorities.
- Creation of up to 6 million person-days of employment in support of Nepal’s Green Recovery and COVID-19 recovery.
- Improved use of evidence and innovation in local government planning, investment and delivery.
- Up to 1,800 resilient infrastructure assets resilience developed by local governments.
- Up to 630 projects supported directly to provide resilient infrastructure services to remote, disadvantaged and vulnerable communities.
- An agreed national framework for the Provincial and Local Infrastructure Sectors to support local infrastructure investment by development partners to guide a significant proportion of investment in sector (percentage to the be defined by the GoN).
- Improved cooperation and coordination between the Local, Provincial and Federal Governments in the three identified provinces, and lessons sharing among local governments with enhanced intergovernmental relationship to deliver infrastructure services at the local levels.
These results have been the basis of the logframe that, with a few minor iterative changes, has been used since the beginning of the programme. In the most recent iteration, the first result above was moved at the outcome level, as a proxy of improved access to quality infrastructure. There have not been any other changes in the outcome indicators during the review period. However, given the recent decision at post to close LISP and phase it out by March 2027, it’s unlikely that many of the outcomes will be achieved, and a full review of the logframe is being carried out by BEK in coordination with LISP implementing partners (likely to be finalised by December 2025).

A visual representation of LISP’s ToC (as per Business Case) is shown on page 8. It should be noted that, while not captured in the original ToC, LISP had significant climate finance targets (16.6% of revised prospective budget - £15 million out of £98.1 million), with associated markers. As a result of specific infrastructure choices (types of projects, construction methods and choices of materials), it’s estimated that up to 40% of final LISP spend could be classified as International Climate Finance (ICF).
[note] Rio Markers: climate adaptation: Principal at 80%; climate mitigation: Significant, at 20%; biodiversity and desertification both at Significant.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
LISP has been implemented under a transitional setup since 2023 (through WFP), and it has been operating in its intended form (i.e. through TA-enhanced government systems, including funding through Nepal’s Treasury) only since the beginning of 2025. This implies that many of its original assumptions remain untested. Therefore, while there has been promising progress across a range of output and outcome areas, it would be too early to definitively assess whether the programme is contributing to its expected outcomes and impacts.

ADDED: climate adaptation and mitigation outcomes as part of climate financing commitments under FA capital funds to rural areas
As mentioned above, the decision to close LISP in March 2027, after just two cycles through government operational and financial systems (as opposed to five as originally planned), fundamentally changes the basis for programme achievements by the closure. Many governance-related outcome areas originally envisioned for LISP—such as strengthening deliberative decision-making in local governments, improving intergovernmental and intersectoral coordination, enhancing transparency in infrastructure financing, and advancing gender equality and social inclusion in planning—are unlikely to fully meet the ambitions set out in the original design. Nonetheless, meaningful progress remains achievable in terms of identify viable pathways for change, and using lessons learned to inform future UK’s work in these areas. Similarly, economic outcomes linked to stimulating rural economic activity and leveraging major infrastructure investments are now expected to fall short of initial projections. Instead, efforts will focus on developing scalable pathways to help the Government of Nepal align local infrastructure choices with relevant market, economic and industrial policies, while also delivering localised income and employment benefits through infrastructure works planned for the upcoming construction season.
.

As such, the programme outcome rating for LISP will move to Red. This reflects the acknowledgement that, despite meeting most output indicators under this review (thus justifying the A score), the original longer-term ambitions of LISP are no longer expected to be fully achieved. However, with an orderly phase-out and transition, LISP has the opportunity to deliver immediate, tangible benefits for thousands in underserved LGs and marginalised communities that had made commitments to the programme, while also securing lasting gains in infrastructure governance and policy reform. This will help establish a positive legacy of good governance and accountability, aligned with Nepal’s evolving priorities, and offer valuable insights to inform BEK’s broader portfolio. The transition will also ensure the UK’s financial commitments to the Government of Nepal for the current fiscal year are upheld, supporting the upcoming construction cycle and safeguarding both value for money and the UK’s reputation as a dependable partner. Moreover, LISP’s final phase can serve as a strategic platform for BEK to integrate its portfolio enabler functions into Nepal’s next budget planning cycle, as identified during the recent ODA reset.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As previously described BEK, has recently decided for responsible exit of LISP, ensuring that remaining financial commitments towards the GoN will be met during the Nepali FY 2025/26. BEK, in collaboration with LISP stakeholders, will develop an exit plan for transition out of the programme, with a focus on the widespread LG and central government buy-in to document proven models and inform the GoN on possible sustainability pathways.

## C. DETAILED OUTPUT SCORING

This Annual Review updates on the relevant achievements in the first year of the main implementation against targets set in the most recent LISP Logframe (see attachment). As a general note that cuts across Logframe choices, BEK will have to review, in collaboration with LISP suppliers DT Global and Pegasys, the programme outputs in advance of the next AR and the Programme Completion Review (PCR) to reflect the impact of early closure.

Output Title	Palikas supported to improve systems and processes in Karnali, and Lumbini Provinces.
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Previous	Target(s)	Progress
Output Indicator 1.1 / No of LGs that show: / Development or adaptation of policies, legislative instruments and operational frameworks related to local infrastructure governance to institutionalize the improved local infrastructure management practices (e.g., LG guidelines). / Other localised improvements may include: / Adoption of institutionalised and informed decision-making on construction modality selection for each local infrastructure. / Alignment of annual plan with Periodic Plan, Infrastructure Sector Development Plan and MTEF for FY 2024/25 / Effective operationalisation of LG-level community feedback and response mechanism.	15 / (Karnali)	35 / (20 Karnali, 15 Lumbini) / (qualitative disaggregation across areas)	35 / (formalised legislation and guidelines on improved local infrastructure modalities) / 7 / (enhanced & more coherent MTEF) / 22 / (feedback mechanisms – varying degree of implementation

Briefly describe the output’s activities and provide supporting narrative for the score.
Before the Local Infrastructure Support Programme (LISP), infrastructure projects in Nepal were typically small-scale and implemented through a uniform approach dominated by User Committees, often led by local elites. This limited equitable participation and undermined the decision-making authority of Local Governments (LGs), contrary to the principles of federalism. LISP introduced a transformative shift by promoting participatory planning and project selection under the Local Government Operation Act (2017), and by supporting LGs to adopt technically sound criteria aligned with Public Procurement Regulations. This enabled more rational, transparent, and inclusive infrastructure delivery.
During the review period LISP, supported 35 LGs in Karnali and Lumbini Provinces to improve systems for infrastructure governance (including 15 existing LGs in Karnali, as well as five and 15 newly enrolled LGs in Karnali and Lumbini respectively). All 35 LGs adopted one of the three prescribed implementation modalities, enhancing transparency and accountability. Of the 304 schemes initiated, 301 were completed, with a significant number implemented through improved User Committees and others via contractor modalities aligned to Public Procurement Regulations (e.g., using e-Procurement platforms). The revised User Committee approach promoted inclusive participation and shifted procurement responsibilities to LG engineering or procurement units, with the aim of eliminating rent-seeking incentives and enabling direct payments to workers through bank accounts.
To institutionalize reforms, LISP TA supported 15 new LGs in Lumbini and five in Karnali to develop five key local procedures covering: infrastructure management, environmental and social risk screening, monitoring, maintenance, and grievance redressal (based on models tested during the pilot phases by WFP). These have strengthened LG operational capacity and embedded good practices in service delivery. While all 35 LGs had annual plans, the quality of Medium-Term Expenditure Frameworks (MTEFs), Periodic Plans, and Sectoral Plans varied. LISP TA addressed this by supporting seven LGs in developing enhanced MTEFs to improve long-term budgeting and strategic alignment.
Additionally, LGs set up varied grievance redressal mechanisms—hotlines, helpdesks, feedback boxes, SMS platforms, and social media— with the aim to enhance accountability and community trust, though operationalisation has been patchy. Broadly, achievements under this output so far depict a viable and scalable model for local infrastructure governance reform in Nepal.
Planning and selection support was provided for the last construction cycle (Nepali FY 2024/25 – see output 4 for details on the actual infrastructure assets). For the upcoming construction cycle (Nepali FY 2025/26), FA and TA support expanded to 50 LGs, including 10 new ones in Lumbini and five additional ones in Karnali. Across all LISP LGs, the programme supported / facilitated 502 settlement-level and 170 ward-level consultations, ensuring the introduction of inclusive prioritization approaches with targeted outreach to generally sidelined and marginalised groups (women and adolescent girls; Dalits, Badi community). All 50 LGs finalized infrastructure plans and budgets for FY 2025/26, with 40 selecting larger-scale schemes for LISP co-funding as intended.
These results across LGs demonstrate point to relatively positive performance trends despite delays in contract mobilisation and suppliers’ onboarding, showing a potentially sustainable and scalable model for local infrastructure governance reform in Nepal.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No major changes were included under this output, though some indicators that less under the control of LISP programme have been included as “secondary results”, given the likely localised nature of achievement in very diverse LG settings. These secondary results will become the focus of the next review period, with a specific attention to quality of operationalisation and delivery, now that formal local legislative and policy processes are established across all 50 LGs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from the 2023/24 AR under this output include the following:
WFP should assess the extent of effective participation of the most marginalised communities and help LGs develop more inclusive access to infrastructure and job opportunities through analysis of their beneficiaries’ datasets and the production of a summary paper with findings and recommendations.
Partially completed: This recommendation was not fully acted upon as per original expectations. Some findings were shared as part of AR cycles and final reporting processes by WFP, as well as handover workshops, though mostly in a light-touch qualitative (often anecdotal) way. While these insights were still useful for recent implementation, LISP would still benefit from a more granular analysis around LISP effects on local participation and inclusion, to inform transition and dissemination of learning to government counterparts.

WFP should consolidate the processes and guidelines into standardised operating procedures to prepare for LISP scale-up and potentially help LGs manage other non-LISP infrastructure investments
Completed: This recommendation was acted upon as per original expectations. LISP Operating Procedure was approved by MoFAGA in February 2025 and are currently guiding the implementation of LISP through government systems. The Procedure is currently being revised (as expected each year) based on lessons learned from the last implementation cycle. However, considerations should be given to the extent of review given the early closure, trying to avoid nugatory review for areas that are no longer relevant (for instance, changes in LG selection processes in future years).

Lessons and recommendations for the year ahead rotate around the following areas:
Sectoral Imbalance in Infrastructure Prioritization: Despite LISP TA’s efforts to institutionalize participatory planning and prioritization tools LGs have continued to overwhelmingly favour road projects. In the FY 2024/25 construction cycle completed in July 2025, roads accounted for 60% of LISP co-financed projects. A similar proportion (63%) came out from the FY 2025/26 processes (but as high as 73% in Lumbini Province). Some LGs indicated that co-financing roads through LISP allows them to redirect local budgets to smaller projects. However, current programme-level analysis hasn’t been able to clearly interpret whether this reflects genuine community needs (which might indeed be the case) or is influenced by political interests or lower co-funding requirements.
Recommendation: LISP TA should assess whether road projects, and more broadly infrastructure choices, genuinely align with local priorities and evaluate the inclusiveness of current selection practices (October 2025). Based on findings, LISP TA should support LGs and MoFAGA in refining current selection tools and criteria in ways that promote more balanced sectoral prioritization, ensuring infrastructure investments respond to the needs of poor and marginalised communities.

Balancing Project Scale and Inclusivity: LGs implemented an average of 8.7 LISP co-financed projects in FY 2024/25, and over seven in FY 2025/26, many significantly larger in scale and financing than previously practiced. This indeed align with LISP’s ambitions and the assumption that fewer, larger, more strategic projects are more cost-effective, have higher population impact and reduce the politization of local choices (as opposed to small, scattered projects that follow localised Ward-level politics). However, field visits surfaced local community concerns that providing benchmarks for larger projects and limiting their numbers led in some cases to the unintended exclusion of vulnerable communities. Larger projects often benefit more populous areas / wards, which also tend also to be the ones politically more influential. In several local conversations, LG authorities emphasized that smaller projects, while having potential pitfalls in terms of cost-effectiveness, can be also more inclusive and responsive to local needs.
Recommendation: LISP TA should help GoN (MoFAGA) refine infrastructure prioritisation approaches through formal intergovernmental guidance to promote a more nuanced set of inclusive criteria, that includes but does not overweight considerations around projects’ sizes and costs. TA teams should facilitate discussions on trade-offs and support LGs in making informed, inclusive decisions that reflect community-level priorities. (continuous across the remainder of the programme – but focus on planning season: March-May 2026)

Strengthening Transparency in Municipal Assemblies: While LISP TA has promoted participatory planning at settlement and ward levels, its influence at the LG level—particularly within municipal assemblies and executive decision-making platforms—remains limited, reflecting the traditional limitations faced by the public. These assemblies, which approve infrastructure projects, often operate with minimal transparency. Meetings are closed, minutes are not publicly shared and decisions may be politically driven, undermining participatory principles.
Recommendation: MoFAGA should use LISP catalytic efforts to demand greater transparency and accountability in Municipal Assembly proceedings, as a model for conditional co-financing in infrastructure. This includes mandating LGs to publish meeting minutes on executive decisions and allowing community observers or representatives to participate. Enhancing transparency is critical to reinforcing participatory governance and ensuring infrastructure investments are equitable and community-driven.

Output Title	Capacity and delivery improved in targeted Palikas through strong and sustainable local government capacity building (with focus on infrastructure governance), evidenced by the indicators below
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Previous (cumulative)	Target(s)	Progress
Output Indicator 2.1 / No. / proportion of LGs that have prioritized large-scale infrastructure which are labour intensive, disaster risk reducing, climate resilient (in FY24/25 construction season & cumulatively).	15	35	35
Output Indicator 2.2 / No. of LG’s officials capacitated in deliberative and inclusive planning and management of local infrastructure	83	150	163

Briefly describe the output’s activities and provide supporting narrative for the score
During the review period, LISP help strengthening the institutional capacity of 50 Local Governments (LGs) across Karnali and Lumbini Provinces, including 15 newly selected LGs for FY 2024/25 and, more recently, LGs participating in the upcoming FY2025/26 construction season (both refer to Nepali fiscal years). The programme supported LGs in adopting participatory planning approaches and a scoring-based project prioritization tool, which translated broad central guidance into a practical method for inclusive and deliberative decision-making.
For the construction cycle of Nepal’s FY 2024/25, all 35 target LGs applied the tool with some degree of success, prioritizing larger-scale infrastructure schemes in line with the programme’s requirements (with the implications around inclusion trade-offs highlighted above). For the upcoming FY 2025/26 construction cycle, 40 out of 50 LGs selected comparatively large-scale projects, with 86% opting for high-value schemes—indicating that most LGs adopted a strategic shift from fragmented investments to more impactful infrastructure planning.
Targeted training was delivered to key officials, including mayors, chairs, chief administrative officers, engineers and other LG representatives. Two-day orientation sessions were held in both provinces (including LGs officials), fostering shared understanding of planning steps, policy frameworks and strategies for inclusive and climate-resilient infrastructure. These sessions, involving 204 participants (chairpersons, chief administrative officers, engineers, accounting officers), also supported peer learning (with lessons learned shared by established LISP LGs to onboarding LGs) and covered topics such as project selection, procurement, GEDSI integration and grievance handling.
Basic engineering training was prioritised and provided to all technical staff present in LGs, enhancing skills in project design and cost estimation. This has improved the confidence and technical capacity of LG engineering teams in preparing detailed plans and ensuring quality infrastructure delivery. Overall, a total of 163 LG engineers were provided a range of training offers around inclusive infrastructure planning, delivery and management. These efforts have strengthened LGs’ ability to engage communities, apply technical criteria and integrate resilience and equity into infrastructure governance.
Describe any changes to this output during the past year, and any planned changes as a result of this review
This is an output that replicates the language in the LISP PDD agreed with the GoN. No changes were applicable, and LISP TA are reviewing the results framework. As per suggestion in the past AR, the third indicator originally included under this output (related to repair and maintenance financing) was removed and integrated into output 3. The title was also modified to reflect the broader scope of collaboration beyond PLGSP.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from 2023/24 AR under this output have been mostly acted upon:
WFP should suggest contextualised approaches for embedding TA staff at LG level for each of the 15 target LGs in Karnali, including an analysis of advantages and disadvantages of various modalities (fully LG-embedded, clustered, roving) to inform future expansion.
Partially Completed: WFP shared lessons related to the model used during the early phases (full embedding within LGs), but did not engage in or piloted other models, and therefore could not provide a comparative analysis of advantages and disadvantages of different approaches. See below for more insights on the DT Global clustered model implemented during the last construction cycle.

WFP should engage with LGs during the FY24/25 annual planning and budgeting processes to continue to improve scoring-based prioritisation tools and help them prioritize climate-resilient local infrastructure.
Completed, with caveats: While improved prioritisation tools were used during the selection phase of the last construction cycle (2024/25), visits to the field showed varying degrees of adoption. At times (while still a minority of cases), projects selected through relatively representative prioritisation processes at settlement and Ward levels were subsequently deprioritised within the executive assemblies’ final budgetary allocation processes. This has been a relevant, if minority, trend during the most recent selection process for the upcoming 2025/26 construction cycle.

BEK and MoFAGA should capitalise on the early successes for their engagement with new LGs (both in Karnali and Lumbini) during the expansion phase.
Completed: BEK and MoFAGA (supported by DT Global) maintained good engagement with subnational levels, building on early LISP lessons to organise several in-depth orientation and peer-learning events, bringing together target LGs and provincial representatives (political and technical officials), to improve understanding of best practices in local infrastructure delivery.

Lessons and recommendations for the year ahead include:
Strengthening the Planning and Decision-Making Processes: Despite visible improvements in participatory planning, project selection still lacks the level of transparency expected after the introduction of prioritisation tools aligned official policy, and these choices remain too often influenced by political interests with a bias toward road projects.
Recommendations: LISP TA should revise TA deployment to ensure consistent support at the LG level, and provide practical tools to improve planning, prioritisation and oversight during the next planning cycle (Jan-May 2026). This should include bespoke engagement and tools to promote the establishment of transparent proceedings by municipal assemblies and set conditionalities on funding based on community-led, scoring-based prioritisation that align investments with community needs. At the federal level, LISP TA and BEK should work with MoFAGA to improve and promote harmonised guidance and policies that link up to grants’ conditionalities before the next planning cycle (December 2025).

Foster Inclusive Engagement and Coordination Across Levels: While LISP focused (as per business case) on promoting larger infrastructure projects with the aim of reducing politicised fragmentation and inefficient, dispersed infrastructure spending, conversations with communities highlight the need for more localised and inclusive approaches. Despite good intentions, oftentimes larger infrastructure serves by default larger, more densely populated and connected Wards. This creates an unintended risk that by putting efficiency and strategic “population impact” front and centre (as per scoring-based tools), smaller and more marginalised communities and Wards won’t benefit from smaller, but locally relevant infrastructure projects that respond to their needs.
Recommendations: LISP core actors (LISP TA, MoFAGA and BEK) should work together to improve project selection processes (including formal scoring-based tools) by rebalancing the relative weighting of projects size, remoteness and marginalisation traits. This process improvement, to be finalised and implemented before during the prioritisation process (April-May 2026), would support deliberative processes that reflect community priorities rather than relying on crude efficiency measures.

Output Title	Local infrastructure budget and spend improved
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Previous (cumulative)	Targets(s)	Progress
Output Indicator 3.1 / Amount of LG/public finance and LISP co-finance (GBP) mobilized for resilient local infrastructure development	£6.1M / (LGs: £2.5M)	£6.6M / (LG: £2.6M) / Cumulative: Total £12.7M / LGs: £5.1M	£6.47M / (LG: £2.47M) / Cumulative: / Total: £12.57 / LGs: $4.97M
Output Indicator 3.2 / Amount of budget (GBP) allocated by Municipal Council for the O&M fund in FY 2023/24.	£410K	Not defined	Unclear
Output Indicator 3.3 / Year-on-year percentage increase in LGs’ investment in co-financed sustainable and resilient local infrastructures (co-financed) in FY 2023/24 compared to FY 2022/23	N/A	40%	34%
Output Indicator 3.4 / Budget absorption for co-financed infrastructure projects	N/A	90%	81%

Briefly describe the output’s activities and provide supporting narrative for the score.
During the review period, LISP supported 35 LGs in Karnali and Lumbini Provinces to significantly improve the mobilization, allocation and management of public finance for resilient infrastructure development. All targets under this output were slightly underachieved.
LGs and LISP jointly mobilized a total of £6.47 million for infrastructure projects, slightly below the target of £6.6 million expected under Output Indicator 3.1. In this year, LGs allocated approximately GBP £2.47 million (NPR 434.3 million) in co-financing for infrastructure projects. Compared to Nepali FY 2023/24, this collective allocation by the GoN represented an increase of approximately 34% from the year’s allocation (£.1.84 million), against an expected target of 40% given the increase geographical scope. While this demonstrates growing ownership and commitment towards infrastructure investment.
Budget absorption for co-financed infrastructure projects was lower than expected, at 78% in FY 2024/25, a mix of underspend against FA (81%) and own LGs’ funding (72%).
When analysis some of the underlying trends behind lower-than-expected achievements against targets under this output, a few factors include:
Propensity for selection of roads projects: While a trend most visible in Lumbini, in both provinces road rehabilitation and upgrade projects made for most selected projects (nearly 70% in Lumbini and over 40% in Karnali). This might reflect a range of incentives:
- Roads, along with infrastructure focused on climate resilience and renewable energy, are the only types eligible for 80% co-financing from FCDO’s FA under the MoU and PDD with the GoN (compared to 60% for other projects). This policy aimed to steer LGs toward upgrading existing roads rather than building new ones, but it has unintentionally led LGs to favour projects with higher UK co-financing, road upgrading and rehabilitation being the simplest and least contentious within LGs’ decision-making processes.
- Upgrading and rehabilitating roads—especially larger, strategic schemes—often require contracts rather than Users’ Committees. Contracts are easier for LGs to manage and support more efficient mechanized approaches. Moreover, due to average quality of procurement processes and reliance on unrealistic official rates, contractors tend to underbid, resulting in actual project spending falling well below approved budgets.
- Project feasibility and completion issues: Some projects selected during prioritisation were later found unfeasible after appraisal. Due to delays outlined in Output 4, the timeline from prioritisation to delivery was compressed during the last construction cycle, leaving LGs little time to replace discarded projects. Additionally, procurement delays—such as lack of bids or unsuitable bidders—led to decisions to cancel projects when no contractors were available, and no other timely option was feasible. These issues mainly affected larger, costlier rural projects, impacting budget absorption more than the total number of projects delivered.
- Efficiencies in project delivery: Linked but somewhat separated from the above, contracting modalities (reliance on relatively transparent e-procurement), larger scale, rationalised design, materials choices and operational efficiencies are likely to have generated important efficiencies, thus resulting in savings on budgets.
Overall, this projects a mixed picture of well-intentioned approaches to transparency and efficiency, but at times with limited adaptability or inflexible / tight timelines, which coupled with operational and administrative realities and inherent programme incentives, resulted in excessive savings on UK grants, and a missed opportunity to expand further on the impactful projects highlighted under Output 4.
Besides these aggregate metrics, LISP TA provided substantial TA to LGs in financial planning, budgeting and expenditure tracking (broadly under the banner of improve PFM practices, but with an eye on fiduciary risk management for UK’s FA). LGs were encouraged to integrate infrastructure priorities into their annual budgets and MTEFs, set up enhanced accounting mechanisms for tracking infrastructure spend (based on existing accounting systems), and align spending with inclusive, sustainable and climate-resilient development goals.
When it comes to encouraging LGs to dedicate own fundings to operation and maintenance (O&M) budgets, a more in-depth analysis put into questions figures identified in the last AR (approximately £410,000). No formal target was set for this year, but LISP TA was required to better understand the O&M funding landscape given inconsistencies identified over the last year during field visits. DT Global identified a range of issues that complicate the identification of O&M funds allocated by LGs (based on the review of “Red Books” from 11 LGs). The review found that there’s no consistency in how O&M is treated across LGs: some LGs report on O&M as a budget category, some as projects in their own right, and some include O&M in other line items. At times all of the above are present in the same budget, and O&M can also consist of various types of scheduled maintenance that cut across a range of assets (e.g., cumulatively for things like infrastructure assets, vehicles, etc).
[note] In one extreme example in Dullu Rural Municipality (Karnali), O&M budgets are reflected against three accounting codes at municipal level, and five additional accounting codes at the ward level (in one instance, two different codes for the same label), for a total of eight different O&M lines with varying degree of flexibility.
The insights provided indicate that, in their current form, the data analysis on O&M would be labour intensive and the quality of data variable and questionable, relying on “judgement calls” on what constitutes O&M. What is clear however is that all 50 LGs have dedicated O&M budgets, the challenge in the future is to try to streamline, simplify and harmonise a system that looks overly complex, cognizant that changes in practices and behaviours take time to be embedded. As such, any LISP contribution to O&M, within its new timelines, is likely to be modest.
In summary, Output 3 underperformed (for most indicators, slightly) key financial mobilization and investment targets, to some extent because of justified contextual and operational factors. The increase in LG contributions—but preference for specific types of projects requiring less co-financing; the prioritization of high-value projects—but relying on contracts instead of labour-intensive projects; operational and administrative delays both within FCDO instruments and GoN fiscal transfer, resulted in financing targets not being fully achieved, justifying a score of “B” in this annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Changes in this output (besides numbering, from 4 to 3) include a) the implicit integration of geographical dimension of O&M (n. of LGs) within the explicit budget analysis, given the early finding that all LGs have some form of O&M budgets that touch on infrastructure; and b) a clearer reference to budget absorption trends. The integration of the former indicator appears questionable within the new programmatic context, and going forward O&M qualitative insights might be best integrated within the broader governance improvement framework under outputs 1 and 2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations from previous AR for this output are being actioned. The status of the recommendations are as follows:
WFP should carry out detailed analysis of the robustness of infrastructure budgeting and the participating LGs’ capacity to improve spend (and quality of spend), to provide learning for scale-up to other LGs (draft by July 2024; final report by September 2024)
Incomplete: this recommendation could not be completed for two reasons: BEK requested WFP to refocus workload towards the FY24/25 construction cycle planning given aforementioned delays in mobilisation of DT Global contract; and b) delays in intergovernmental decisions around LG selection, allocations and development of the LISP Operating Procedure, which required extensive policy work. The role to work on extensive PFM and LG capacity analysis was moved to the new TA supplier DT Global, also to ensure ownership of findings and solutions.
As the new TA suppliers starts its inception phase, they should explore with LGs options for bulk procurement across projects managed by Users’ Committee, starting with piloting annual infrastructure procurement plans with a few test LGs. –
Likely small scale: in some LGs DT Global have been able to identify, as part of their TA presence, negative examples of split procurement that could have benefited from consolidation and streamlining (e.g., PPEs split by infrastructure scheme rather that procured in one single procurement exercise), as well as positive examples of LGs rationalising their options. Findings have been shared recently with the LISP FRMIP Task Team within MoFAGA as part of the lessons from the financial monitoring exercise, and will be included in the updated FRMIP actions. However, given the time remaining under the programme, it’s unlikely that the scale of improvements will go beyond small pilots in the upcoming construction cycle.
WFP to develop standard guidelines on use of operation and maintenance funds based on the best practices and lessons on applicability during both Pilot and Transition phases (October 2024) and produce a briefing note on how these funds could be set up and effectively utilised (November 2024), as part of their documenting and learning tasks.
Completed: the LISP Operating Procedure was approved by the GoN’ Cabinet in early 2025, setting the framework for the various phases of LISP implementation (EoI-based LG selection; granting mechanisms; monitoring requirements; local policy requirements; infrastructure planning and prioritisation approaches, among the areas covered by the Procedure, along with roles and responsibilities of various stakeholders and tiers of government).
WFP should detail specific case studies of intergovernmental collaboration in infrastructure and BEK and its TA suppliers should showcase these during their provincial engagement in LISP target provinces as promising good practice (September 2024)
Incomplete: LISP facilitated the development and endorsement of the Infrastructure Sector Co-Financing Procedures 2023 in Karnali. This landmark policy was meant to establish a clear framework for joint implementation and financing between provincial and LGs, promoting alignment with federal mandates and minimizing duplication. However, political changes in provincial government leadership and reduction in its funding late in the FY23/24 construction cycle, coupled with tight timelines for the FY24/25 cycle, meant that there was no successful case of implementation of jointly financed projects (with the exception of one scheme in Kharpunath Rural Municipality, in Karnali – a road rehabilitation project co-funded by the province).
The following lessons and recommendations were identified:
Field-level Procurement Realities: Shifting procurement responsibilities from Users’ Committees to LGs, following formal public procurement rules, has reduced corruption and fiduciary risks. However, some LGs experienced construction delays due to a lack of bidders when market prices for key materials exceeded official district estimates. LGs that conducted their own rate analysis and used timely bulk procurement avoided these issues.
Recommendation: LISP TA should help LGs develop their own rate analysis, encourage early bulk procurement and promote the use of local materials and climate-smart construction methods (starting from the design phase within the new construction cycle – October 2025). These steps will support project sustainability, local employment, and reduce environmental impact.

Public Procurement and Financial Management (PPFM): Many LGs face significant capacity gaps in financial management, procurement, and contract administration, affecting transparency and effective use of funds. While LISP TA’s PPFM component is meant to support these areas, it has mostly focused on accounting (supporting UK’s fiduciary risk management requirements), with limited early-stage support for the PPFM cycle. While this is due to underlying programme pressures (including multifaceted contextual delays in programme delivery that in part originated from FCDO), this is an area that required increased focus going forward, within the limitation of the new realities of a closing programme.
Recommendation: LISP TA teams should engage with LGs from the start of budget and procurement planning, providing continuous guidance throughout the project cycle. This will improve transparency, efficiency, and LGs’ confidence in managing projects. Concretely, this means providing hands-on design and procurement support to all 50 LGs (according to a recently revised and agreed TA Approach) starting early during the upcoming construction cycle (from October 2025).

Co-funding constraints: The most rural LGs have struggled to secure co-funding for infrastructure projects due to reduced equalisation grants, in case having the unintended effect of LISP co-funded projects displacing relevant smaller projects for underserved communities. However, there is strong interest from provincial governments to co-finance projects that use LISP improved modalities, and a provincial co-financing guideline has been drafted for Karnali. There’s also a clear recognition at the federal level (especially during review conversations with MoFAGA) that LISP approach provides a positive framework for more trustworthy channels to fund infrastructure through more flexible granting approaches based on local priorities, while still allowing for a reasonable degree of transparency and accountability.
Recommendation: LISP TA should enhance their work with Provincial Governments to formalize and test co-financing mechanisms at subnational level, especially in resource-constrained areas. Cognizant of the political uncertainties over the next six months, this work should take a patient approach and likely use the next planning season (post March 2026 elections) to engage more meaningful and in a structured way with provincial governments. At the same time, BEK with the support of TA should focus the remainder of the programme implementation in strengthening coordination across all government levels will help ensure more sustainable and inclusive local infrastructure policy and fiscal environment.

Strategic Operation & Maintenance: Introducing a policy requirement for LGs to allocate dedicated funds for infrastructure O&M has been positively received and is a promising step toward sustainable infrastructure management. Despite this, many LGs struggle with unwieldly legacy accounting systems, coupled with the challenge of securing adequate and sustainable O&M funding, mainly due to limited local revenue and heavy reliance on central government transfers. LG leaders highlighted the importance of properly estimating and integrating O&M costs during the planning and design stages of infrastructure projects, something LISP TA could potentially support.
Recommendation: LISP TA should help LGs institutionalize O&M planning by ensuring costs are estimated and included from the outset of each project, while also providing practical guidance on budgeting for O&M. Efforts should also focus on strengthening LGs’ capacity to generate local revenue and exploring allocative efficiencies, co-financing or matching fund options to reduce reliance on central transfers. Establishing a baseline for O&M funding, tracking allocations and monitoring progress will be essential for measuring impact and improving sustainability. Finally, clear guidance should be shared with all LGs, and ongoing reviews should enhance how O&M and overall infrastructure sustainability are tracked and reported (continued proportionate support from October 2025).

Output Title	1,800 infrastructure assets with increased resilience and sustainability
Output number:		4	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?

Indicator(s)	Previous (cumulative)	Target(s)	Progress
Output Indicator 4.1 / No of productive, protective, climate-resilient and employment generating assets (co-financed) built, restored, or maintained, by type and unit of measure in FY 2024/25.	233	287 / (cumulative: 520)	302 / (plus 60 schemes from LISP-REDI)
Output Indicator 4.2 / No of the co-financed projects directly provide resilient infrastructure services to remote, disadvantaged and vulnerable communities.	59	Not defined	GEDSI responsive: / 134 of 302 (44%) / GEDSI accessible: / 22 of 302 (7%) / Climate & Disaster: / 244 of 301 (81%)

Briefly describe the output’s activities and provide supporting narrative for the score.
During the construction cycle 2024/25, a total of 302 infrastructure schemes were constructed or rehabilitated across 35 LGs, exceeding the annual target of 287 schemes set under Output Indicator 4.1. The target of 287 reflected the prioritisation and selection process by LGs. Originally, 325 schemes were identified by LGs, however only 287 were included in the final LISP co-financing selection on the basis of affordability (with committed FA ceiling), eligibility (as per LISP PDD) and feasibility. Due to cost savings and efficiencies generated from competitive contract bidding (as mentioned under previous output), an additional 26 “Priority 1” schemes were added from prioritised LGs’ lists (project banks) and implemented using surplus funds.
The schemes constructed include various types of infrastructure authorised under the PDD, for the most part rural roads (rehabilitation and upgrades), water supply and sanitation, and irrigation, plus a handful of other projects across seven eligible categories (e.g., transport, energy, urban development, social infrastructure and waste management). The completed infrastructure schemes improved access to essential services for an estimated 572,377 people, and they are summarised in the tables below. The detailed breakdown of these schemes is provided in Annex A.
KARNALI PROVINCE

SN	Typology of Projects	Infrastructure		Actual Expenditure (Typology wise)
		No. of Projects	%	Total / GBP value	UK Financing		LG Financing
					GBP value	%	GBP value	%
1	Irrigation	27	16%	£379,174.31	£237,290.12	13%	£141,884.18	13%
2	Rural Transport	103	60%	£1,900,452.67	£1,128,849.75	62%	£771,602.92	68%
3	Small and Alternative Energy	1	1%	£3,716.17	£2,435.93	0.1%	£1,280.24	0.1%
4	Social Infrastructure	18	11%	£257,855.94	£181,274.42	10%	£76,581.51	7%
5	Waste Management	8	5%	£127,621.38	£69,198.01	4%	£58,423.37	5%
6	Water Supply and Sanitation	14	8%	£249,577.04	£187,573.90	10%	£62,003.13	6%
7	Other			£28,410.42	£16,866.98	1%	£11,543.43	1%
	Grand Total	171	100%	£2,946,807.92	£1,823,489.12	100%	£1,123,318.80	100%
					61.9%		38.1%

LUMBINI PROVINCE

SN	Typology	Infrastructure		Actual Expenditure (Typologywise)
		No. of Projects	%	Total / GBP Value	UK Financing		LG Financing
					GBP value	%	GBP value	%
1	Irrigation	13	10%	£146,133.84	£86,417.56	6%	£59,716.28	9%
2	Rural Transport	87	66%	£1,476,315.14	£1,044,195.01	73%	£432,120.13	67%
3	Social Infrastructure	15	11%	£257,916.64	£179,620.68	13%	£78,295.96	12%
4	Waste Management	1	1%	£11,600.68	£6,960.41	0%	£4,640.27	1%
5	Water Supply and Sanitation	15	11%	£190,587.15	£116,843.86	8%	£73,743.30	11%
	Grand Total	131	100%	£2,082,553.46	£1,434,037.52	100%	£648,515.94	100%
					68.9%		31.1%

Out of the 302 schemes:
- 244 schemes (81%) incorporated climate resilience and disaster risk reduction (CR & DRR) features: specifically, this meant supporting LGs in conducting basic environmental and social risk assessments and integrating climate-resilient design features during the planning and design stages. These assessments helped identify site-specific vulnerabilities and guided the adoption of appropriate mitigation measures. Nature-based and climate-smart techniques were applied in various scheme types, including bioengineering for slope stabilization, improved RCC drainage systems for rural roads, and source protection for irrigation and water supply schemes. All schemes were jointly verified by TA teams and LG engineers to ensure compliance with existing climate-resilient standards.
  [note] Reinforced cement concrete.
- 134 schemes (44%) included gender equality, disability and social inclusion (GEDSI) elements: this reflects the attempt to steer the prioritisation process (including through scoring-based prioritisation tools) towards target areas, where possible, that include marginalised communities and vulnerable groups in the decision-making processes, or deliberately target underserved or remote localities / settlements prevalently inhabited by marginalised communities (and often both). These efforts ensure that amongst the 572,377 people reached above, 297,636 were women (52%) and 286,108 individuals (just under 50%) from marginalised groups. This directly contributes to Output Indicator 4.2, which tracks the number of co-financed projects delivering resilient infrastructure services to remote, disadvantaged and vulnerable communities (see Output 5 for details on job-related results).

Most of the LISP work in this area was jointly delivered by DT Global and WFP, with WFP providing transitional support from January to March 2025. During this period, WFP led the initial orientation and prioritisation, helping identify ineligible projects and guiding local engineers through feasibility appraisals and design processes. These efforts showcased approaches that LG staff could later replicate (with DT Global offering quality assurance).
From April onwards, as DT Global staff were fully onboarded, they assumed full responsibility for technical assistance to LGs and MoFAGA. This included regular on-site mentoring and occasional knowledge-sharing events to build LG staff capacity and strengthen local ownership of infrastructure planning and delivery.
Support areas included design follow-up, preparation of bills of quantities and project reports (with fully costed designs), procurement (e.g., improving User Committees or navigating public procurement rules), and enhancing site inspection quality. While LGs previously supported by WFP had largely adopted these frameworks, newer LGs in Lumbini and five additional ones in Karnali required more direct coaching—especially on formalised systems like e-procurement and e-payments. As noted in earlier Annual Reviews, these digital tools aimed to ensure fair payment practices, particularly benefiting women and marginalised members of User Committees who were often excluded under informal wage systems.

Besides LISP main schemes, during the review period 60 reconstruction schemes were supported by WFP (completed in December 2024) in response to the 2023 Jajarkot earthquake.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Based on suggestions from the Annual Review 2023/24, Output 6 from the previous logframe (looking specifically at infrastructure delivered to marginalised communities) has now been integrated under this output as a qualitative appraisal of the degree of inclusiveness and climate/disaster resilience across the infrastructure assets co-funded by LISP. As part of this change, Indicator 6.1 in the previous logframe has been integrated under this output as Indicator 4.2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations from previous AR for this output are being actioned.
WFP should disseminate best practices and showcase evidence about economies and efficiencies to other non-LISP LGs, either through lessons-sharing sessions or by engaging with organisations like NARMIN and promoting these approaches at provincial level
Completed: WFP supported the dissemination of lessons in its target LGs to other LGs (both in Karnali and Lumbini) as part of the EoI orientation events in Karnali and Lumbini before the scale-up of LISP in FYU24/25. These events brought together representatives of all rural municipalities interested in attending and applying to the EoI process, as well as representatives of NARMIN and MuAN (as spokespersons for the urban municipalities) and provincial governments.
The new TA supplier should explore opportunities to link sectors at the local level, in the first instance by activating the LISP Provincial Coordination Committee
Unlikely to proceed: This would have been a long-term focus of LISP, with the aim of systematising infrastructure planning approaches by bringing together sectoral economic analysis and infrastructure choices. LISP PCCs were indeed established, with several meetings organised over the last year, but with a narrow focus on supporting the basic LISP scale-up architecture. Given the shortened life of the programme, it’s unlikely that LISP will be able to meaningfully prioritise sophisticated economic sector-matching in its list construction cycle, relative to other more urgent exit and transition priorities.
It is recommended that the full programme retains the current 15 target LGs for the next few years, limiting new EoI processes to newcomers, thus ensuring the longer-term household and community benefits of the improved infrastructure
This recommendation was followed through and all original 15 LGs retained. This should have been the last season for the original 15 LGs, with the plan to shift to new areas. Given LISP early closure, there will be no new EoI to enrol additional LGs. Any remaining TA (to support planning and early infrastructure prioritisation in 2026) will only be offered to existing LGs, with no additional FA.
WFP should track the details of the 15 LGs’ infrastructure maintained through the dedicated maintenance and repair funds (e.g. number, results, jobs and system changes).
Completed: WFP supported LGs technically to use their own O&M funds to repair/rehabilitate 135 schemes, including by helping calculating depreciation and amortization (D&A) costs and workdays requirements for repairs and rehabilitation works.

The following lessons and recommendations were identified:
Climate Resilience and Local Appropriateness: Climate resilience is still narrowly defined, focusing on isolated types of physical infrastructure and mostly using non-local materials. This approach overlooks the ecological, social and institutional dimensions of resilience, resulting in interventions that are often unsustainable and disconnected from local realities.
Recommendations: LISP TA should use the last construction and planning cycles before programme closure to promote the adoption of a holistic resilience framework for local infrastructure, based on the “4R” principles and aligned with national climate policies and international best practices (throughout the current construction cycle and the upcoming planning cycle). On projects’ sites, LISP TA should promote – from the design stage – the use of locally available, environmentally friendly and culturally appropriate materials and technologies to enhance sustainability and community ownership (October-November 2025).
[note] Robustness, Redundancy, Resourcefulness and Responsiveness. See World Bank’s The Adaptation Principles.

Inclusive and Resilient Infrastructure Planning: Climate resilience, DRR and GEDSI principles are inconsistently applied across project stages due to limited shared understanding, local capacity and lack of practical tools. This leads to missed opportunities for inclusive and sustainable infrastructure development.
Recommendations: LISP TA should support the development of new or the operationalisation of existing standardized checklists, templates and design guides that integrate climate resilience, DRR and GEDSI principles throughout the project cycle. This should include targeted, context-sensitive on-the-job training to LGs and TA teams to ensure consistent and effective application of these principles (early phases construction cycle – October 2025 – January 2026).

Construction Quality, Safeguarding, and Implementation Modalities: Poor workmanship, weak safety protocols and inadequate supervision within LGs’ systems risk compromising infrastructure quality and worker safety. The review process found that several projects faced challenges such as low bidding, site abandonment and excessive subcontracting, which affected quality and timelines. Even in well performing sites, insufficient inspection and performative adherence to health and safety procedures (focused on wearing protective equipment rather than site-wide risk management) create unwarranted preventable hazards, as witnessed during two tragic accidents in the last construction cycles.
Recommendations: LISP TA should use the upcoming and last infrastructure cycle to help strengthen LGs’ supervision systems and accountability frameworks, including on rational procurement, safety protocols and technical audits, in collaboration with LG monitoring teams / oversight committees. Specific to the LISP co-funded project, LISP TA should expand support to LGs and Users Committees in procurement, supervision and quality assurance. Efforts should specifically focus on ensuring clear communication on payment modalities and project scope; promoting regular community consultations; and systematically supporting Operational Health & Safety training coupled with adequate PPE and awareness materials (throughout the FY25/26 construction cycle).

Technical Support and Local Engagement: The “cluster approach” tested for the first time under LISP by DT Global showed its limitations during the early handover phases, linked to a mix of limited local technical capacity and operational challenges around securing consistent presence in remote locations. Key gaps included insufficient numbers of DT Global engineers (but also other staff) relative to the scope, and inconsistent support from provincial and central TA teams (impacting on resource planning and understanding of local conditions). Surge engineering teams agreed with BEK and embedded in LGs provided responsive, tailored support during the tail end of the last construction cycle, which allowed to fast-track delivery, but at the same substituting, to some extent, LG teams and hence partially undermining a patient capacitation approach.
Recommendations: LISP TA should revise TA operational strategies to ensure equitable and consistent practice-oriented presence across LGs (by September 2025). This should also include the provision of platforms to promote regular peer-to-peer collaboration over the infrastructure cycle, and deeper engagement with local realities to improve learning, coordination and support delivery.

Seasonal and Operational Planning: In Nepal, the construction season typically runs from October to the start of the next monsoon (summer months). In the mountain regions, this window is further constrained by harsh winters and the Yarsa Gumba harvesting season, compressing the effective construction period to just a few months. Without adaptive planning, infrastructure delivery risks delays and compromised quality.
[note] Yarsa Gumba is a rare caterpillar-fungus prized in traditional medicine. Found in Nepal’s high Himalayas, its lucrative market value diverts local labour from farming, herding and other local jobs (including infrastructure) to seasonal harvesting, reshaping rural economies and livelihoods.
Recommendations: LISP TA should develop a seasonally adaptive project implementation calendar (October 2025) in collaboration with LGs and communities, providing targeted training to field engineers, Users Committees and contractors on rapid mobilization, efficient resource management, timely procurement and contingency planning to maximize productivity during the short working season.

Local Capacity for Inclusive, Climate-Resilient Infrastructure: Local governments face persistent local capacity challenges in designing infrastructure that is both inclusive and climate-resilient, due to limited technical capacity and frequent staff turnover that undermine technical soundness of decision-making processes, and low risk awareness at the community level. Learning on past lessons, the current phase focusing on feasibility appraisals for selected projects is already testing and integrating community consultative processes that undertake locally-led environmental and social risk identification, but capacity enhancements must be integrated along the whole infrastructure cycle.
Recommendations: LISP TA should continue deliver regular structured training AND on-site mentoring on sustainable infrastructure (both to political decision-makers and LGs’ technical staff across all relevant infrastructure governance processes (prioritisation, feasibility appraisal, design, procurement and construction monitoring – ongoing, with expanded support from October 2025)

Output Title	6 million employment days created for poor women and disadvantaged groups
Output number:		5	Output Score:	A (likely)
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Previous (cumulative)	Targets(s)	Progress
Output Indicator 5.1 / No of wage employment days created for poor women and disadvantaged groups.	549,903	296,000 / Cumulative: 845,903	323,001 / Cumulative: / 872,904
Output Indicator 5.2 / No of local unemployed, disadvantaged, poor HHs/people received wage employment through local infrastructure development.	14,384	7,400	14,220
Output Indicator 5.3 / Number of unemployed and poor HHs identified and registered in the database of unemployed/poor HHs who can access the wage employment opportunities in local infrastructure works (strengthening PMEP's EMIS to avoid creating a parallel system)	47,140	Not defined	TBD
Output Indicator 5.4 / Total wage amount (GBP) directly paid to the workers through LG-contracted financial service providers (LG + LISP co-financing).	£3.06M	£1.4M	£1.7M / (estimate)
[note] Provisional, could be higher. Jobs-related data are to collect. Contracts in particular provide cost per unit of work, and LG contractors are not required to report wage information – DT Global is currently collating available information from contractors and finalising aggregation of paid work information from UCs, but given the late completion of the last construction cycle, these data will be available beyond the AR submission deadlines.
[note] Over 43% of the schemes (by value) were delivered through Users Committees, which are notoriously labour-heavy. The total wage paid under UCs is approximately £1.04M. Contracts also employ significant labour (20-40% of total costs) under the types of projects co-funded by LISP. Assuming conservatively that 25% of total schemes delivery through contracts were wages, this would amount to nearly £700,000. The estimated total, approximately £1.7M, would thus exceed estimated targets.

Briefly describe the output’s activities and provide supporting narrative for the score.
Given gaps in data, this output is provisionally scored at B, though this is likely to be an understatement of the likely achievement. LISP TA has a clear job-generating goal. While many of the jobs generated through LISP co-financed infrastructure are short term, for many employees (especially in remote rural areas) these are critical income-generating opportunities and allow local communities to benefit from local jobs and rely less on in-country and international migration.
To promote inclusive community participation, LGs ensured that at least 50% percent of User Committee members involved in this F/Y 204/25 schemes were women. LISP also advanced financial inclusion by mandating, as in previous years, that all wage payments be transferred directly into workers’ bank accounts. This approach reduces the risk of labour exploitation by linking verified site attendance to guaranteed wage payments, and reduces practices such as wage discrimination (unequal wages for equal work) and failure to comply with minimum wages.
The construction of the 302 assets from FY24/25 generated 323,001 person-days of employment, of which 132,430 days (41%) were delivered by women and people from marginalised communities, contributing to inclusive economic opportunities.
To improve the quality, safety, and efficiency of construction work, basic construction skills were provided to all workers through pre-construction training. This training equipped them with essential knowledge for various tasks, while on-the-job learning allowed them to apply and refine these skills in real construction settings. This practical approach not only improved current project outcomes but also prepared unskilled workers for future employment opportunities. Given that, on average, 30-50% of local LGs’ budgets are allocated to infrastructure development annually, these skills are in high demand and enable beneficiaries to contribute to a wide range of construction activities supported by LGs, beyond what is funded by development partners.
Going forward, we will work with LGs to adapt standard contracts to include this requirement, and to ensure that there is monitoring of compliance by contractors for paying minimum wage as There is emerging data from our field visits showing that this might not always be done. This is a learning point

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This slightly revised output brings together job-related dimensions both in terms of numbers of people / wage-days as well as value of wages supported through LISP. No changes were applicable, and a review of the results framework will be facilitated by LISP TA.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations from previous AR for this output are being actioned.
In the longer term, the main TA supplier should aim to increase employment opportunities for these [marginalised] groups by helping LGs refining how target communities are selected and ensuring that infrastructure investments systematically benefit marginalised communities and minorities.
Ongoing – LISP TA is providing support to all target LGs to analyse data and increase employment opportunities for women and marginalised communities: this is a continuous process that relies on regular peer-learning engagement events that bring political leadership (mayors / deputy mayors), chief administrative officers and engineering staff from different LGs together to absorb lessons learned and share practices by counterparts.
WFP should prepare a comparative analysis between LISP target LGs and other LGs in Karnali on the inclusion aspect of the programme, to gain early insights on the programme’s inclusion outcomes to inform the main implementation phase (November 2024)
Not completed: This activity was abandoned due to displacement of WFP resources and a staff towards reconstruction efforts post Jajarkot earthquake and extended support to LISP planning phase due to delays in contract mobilisation for the new supplier (DT Global).
BEK should ensure that future TA build a qualitative body of evidence on the evolving role of women in infrastructure –
Ongoing: likely scale reduced due to early closure, but learning and evidence remain a critical part of the IEL strategy under LISP.
WFP, as part of their learning, should provide evidence and advice on how to increase employment days per worker without increasing financing burden and renouncing the performance-based approach in labour-based infrastructure delivery work by LGs.
Dropped: local realities suggest that there are irreconcilable tensions between expanding labour-intensive infrastructure choices and reducing financial burdens, including: a) high wages (especially if using official minimum wages); b) logistical challenges -- especially in remote areas; c) timeliness of delivery and related efficiencies; d) oversight and quality of delivery. This then becomes a local policy choice in terms of how local leaderships prefer to prioritise efficiency and timeliness (and often quality) of asset delivery (doing more with less) with job-creating and sustainability objectives within their constituencies. LISP can help LGs navigate these trade-offs and support more rational, data-based approaches to support local choices.

The following lessons and recommendations were identified:
Communication and Labor Management in UC-led Construction: Field visits revealed that poor communication around payment modalities and project scope led to confusion and mismanagement in UC-led infrastructure projects. Workers were often unaware of wage rates and payment structures, resulting in scheduling issues, underpayment, and occasional conflict between User Committees (UCs) and labourers. Delays in material delivery from Local Governments (LGs) further exacerbated these challenges.
Recommendations: LISP TA should support LGs and UCs in improving communication by providing clear, non-technical explanations in local languages. TA should also assist UCs in labour resource planning and work scheduling to enhance transparency, reduce misunderstandings, and ensure fair wages.

Equity and Inclusion in Contractor-led Construction: Contractor-led projects often lack mandatory provisions for hiring local labour, especially from disadvantaged groups. Employment decisions are left to contractors’ discretion, resulting in limited opportunities for women and marginalised households. While projects led by Users Committees generally uphold equal pay for equal work, from field observations some wage gaps persist, particularly in contractor-led initiatives, raising concerns about fairness and inclusivity.. These disparities were acknowledged by both LGs and contractors.
Recommendation: LISP TA should conduct an evidence-based assessment of hiring practices in contractor-led projects and propose alternatives to institutionalize equity. These (to be ideally introduced within the upcoming construction cycle, with estimated procurement timelines starting in November 2025) could include:
- Mandating Community Benefit Agreements in contracts.
- Developing model clauses for bidding documents that enforce local hiring quotas, monitored by LG’s Project Liaison / Oversight Committees.
- Integrating inclusion criteria into bid evaluation and monitoring.
- Providing contractor orientation on inclusive practices, drawing from UC-led models.
- Collecting disaggregated data on employment practices by contractors.

More broadly, LISP TA should work with LGs to enforce gender wage equality through regular wage monitoring, transparent payment tracking and awareness campaigns / knowledge-sharing workshops targeting all stakeholders.

## D: VALUE FOR MONEY

The following summary articulates early Value for Money (VfM) analysis across FCDO VfM pillars: Economy, Efficiency, Effectiveness, Equity and Cost-effectiveness.

Economy
As the major cost driver besides FA, LISP TA has demonstrated strong economy in its delivery. Between November 2024 and August 2025, the programme incurred £2.91 million in total costs, with 89% (£2.58 million) attributed to expert fees and 11% (£334,668) to reimbursable costs. Strategic cost containment measures yielded £373,000 in savings, including:
- Transparent procurement of laptops, motorbikes, and servers.
- Use of vehicles from other FCDO-funded projects and DT Global’s fleet.
- Leveraging CARE’s lower-cost human resources.
- Hosting meetings in government and partner facilities to avoid venue hire.

Fee rates were benchmarked against RAP3 and inception baselines, with international LTTA rates reduced from £703 to £621 and STTA from £703 to £696. National rates increased modestly due to inflation, reflecting equitable pay practices. Notably, national staff accounted for 95% of expert days and 80% of costs—exceeding RAP3 benchmarks and demonstrating economical resourcing.

For the other major cost-driver—FA—more analysis is required, but transparent procurement practices (coupled with exchange rate fluctuations) resulted in significant economy against original FA commitments (£3.27M spend pre-identified against £4M FA commitments – though this is still pending agreements on currency exchange rates and auditing processes). At any rates, the preliminary figures point to potential savings of approaching £750,000.

Efficiency
Efficiency is evident in LISP TA’s rapid transition from inception to delivery. During the inception phase, the team established relationships with 35 LGs and developed governance, project management and monitoring systems. These foundations enabled tight control over activities, results and spending.

LISP supported the construction or rehabilitation of 302 infrastructure assets, including site inspections, fiduciary risk management and support for e-procurement and e-payment systems. Embedded TA staff provided on-the-job mentoring, enhancing LG capacity and reducing reliance on external contractors, thus creating process efficiencies within LGs. As mentioned above, there were significant savings against FA commitments, while at the same time LISP supported co-financing for more projects than originally planned and using saving to expand reach.

LISP reduced the number of small, scattered projects, enabling LGs to invest in more strategic, impactful schemes. Cost per beneficiary dropped from £23 to £15, and direct bank payments to workers improved transparency and reduced fiduciary risks.

Effectiveness
LISP exceeded several of output indicators. Key achievements include:
- Completion of 302 infrastructure schemes (vs 287 planned).
- Creation of 323,001 person-days of employment (vs. 296,000 planned), with 41% delivered by women and marginalised groups.
- Improved access to infrastructure for 572,377 people, way in excess of original estimates (also because of increased numbers of schemes: disaggregate data show that 52% of those benefitting from these schemes were women, and just under 50% originating from marginalised communities.
- Support to 50 LGs in project prioritization and budget finalization for FY 2025/26.
- Identification of 371 assets for construction in the upcoming construction cycle through scoring-based tools.
Most LGs have shown meaningful appetite to adopt improved modalities for infrastructure governance (though degrees of implementation and compliance vary), including evidence-based planning, scoring-based prioritization, and institutionalised maintenance frameworks. LGs systematically allocate budget to O&M (though somewhat inconsistently) and provincial co-financing took place under a few of the schemes.

LISP TA also supported the development of environmental and social risk screening tools, monitoring guidelines, and complaint mechanisms, contributing to improved infrastructure quality and governance.

Equity
Equity is central to LISP’s approach. The programme mainstreamed CR&DRR and GEDSI across all stages of infrastructure development, with varying degree of success. Achievements for the review period include:
- 244 assets (81%) with CR&DRR features (though a more refined disaggregation is expected in the upcoming review period).
- 134 assets (44%) with GEDSI features.
- 132,430 person-days (41%) of employment for women and marginalised groups.
- 297,636 women (52%) and 286,108 marginalised individuals (nearly 50%) gaining improved access to infrastructure.
- 502 settlement-level and 170 ward-level consultations to ensure inclusive asset prioritization.

Revamped / improved Users’ Committees were expanded onto newly joining LGs, to support the inclusion as workers of actual beneficiaries, with the aim to replace traditional elite-led structures. Equal pay policies and direct bank transfers have improved transparency and reduced exploitation. However, some wage gaps persist in contractor-led projects and further efforts are needed to institutionalise equity through Community Benefit Agreements and enforceable local hiring provisions.

Cost-Effectiveness (Emerging)
While a full cost-effectiveness analysis is planned for programme completion, early indicators suggest strong performance:

For TA, broadly:
- High ratio of national to international expert inputs.
- Significant savings reinvested into delivery.
- Strong alignment of costs with outputs and outcomes.
- Use of existing public infrastructure and partnerships to reduce overheads.

For FA and the broader programme:
- Linkages between infrastructure to economic activities like agriculture or trade, enhancing long-term value.
- Application of LISP methodologies to non-LISP projects, indicating progressive (if still relatively localised) systemic change.

Conclusion
Despite operating in a challenging rural context, facing funding constraints, political instability and operational challenges, LISP TA has delivered encouraging results across all VfM pillars. Given the recent shifts in delivery modality through FA and the complexity to track government-owned data, it’s early to provide a comprehensive VfM, which is likely to become available only at the time of the next Annual Review. However, early quantitative and qualitative appraisals demonstrate early signs of:
- Economical use of resources, with competitive fee rates and strategic partnerships.
- Distributed efficiencies across TA and FA outputs.
- Effective trajectory towards outcomes, including infrastructure delivery, job creation and improved access.
- Equitable impact, with inclusive planning and benefits for marginalised groups.

These achievements position LISP as a model for scalable, sustainable and inclusive infrastructure governance reform in Nepal. As the programme moves towards an early closure just as it started its main implementation phase, continued emphasis on cost-effectiveness, inclusion and institutional strengthening will be key to sustaining and expanding its early successes within government systems.

## E: RISK

Overview of risk management
Overall risk rating is: Major
Overview of programme risk
In general, the overall risk rating for LISP during the review period was considered Moderate (especially given that the actual transfer of FA through government systems hasn’t started yet). However, beyond the review period, and in light of the implementation (scale) and contextual (political) changes highlighted above, it’s likely that the risks will increase in ways that are still difficult to project, and for this reason the overall residual risk for the project is considered to remain Major. There is now a clear risk that the longer-term impact, VfM and outcome-level ambitions of the programme will not materialise given the proposed early exit. BEK and suppliers are currently working on a “soft-glide” transition and exit plan that is meant provide meaningful VfM and achieve at least some positive and lasting changes across some of the outcome areas of infrastructure governance and delivery. This will be the basis of final contract amendments with key suppliers to be finalised before the end of calendar year 2025.

Delivery Risks (spilling over into Reputational Risks)
Most of the risks identified under LISP have, to date, been effectively managed, with mitigation measures proving particularly successful in areas related to programme delivery. The programme has also made progress in raising safeguarding awareness, in line with recommendations from previous Annual Reviews. However, recent fatal incidents in Humla and Jumla (as detailed in Section A) have exposed serious gaps in safety awareness and the implementation of health and safety protocols. These events underscore the inadequacy of current measures and highlight the urgent need for more robust safeguards.

While national policies on workplace safety exist, their enforcement at the local level remains weak. This is largely due to the absence of contextualised tools, ineffective or non-existent enforcement mechanisms, and a lack of a strong safety culture within local infrastructure delivery. Safety planning and training are limited, and safety considerations are often treated as secondary—rather than being integrated throughout all phases of infrastructure development. As a result, risks to workers and communities persist, particularly in remote and high-risk environments.

In addition to these operational risks, a new delivery risk has emerged, linked to broader contextual developments. The establishment of an interim government and the upcoming federal elections scheduled for March 2025 may introduce significant operational, fiscal, and logistical challenges. These include potential disruptions to local administrative functions, delays in fiscal transfers that could affect Financial Aid (FA) disbursement, and restrictions on procurement and contracting activities—particularly during the 40-day purdah period preceding the election. These developments could impact programme continuity and require proactive planning and coordination to mitigate risks and maintain momentum.

Recommendations:
- LISP TA should develop clear, user-friendly safety tools and training materials in local languages, and support regular safety training for engineers, contractors, and workers. Safety planning and auditing must be integrated throughout all project phases—from design to construction—so it is not treated as an afterthought. TA should also help strengthen local enforcement and promote a culture of safety to prevent future incidents and ensure safer infrastructure delivery.
- MoFAGA and BEK should establish a stronger operational health and safety framework at the local level. This includes revising the LISP Operating Procedures, Local Infrastructure Management Directives, and Improved Modality Guidelines. They should also promote earlier initiation of works to avoid time pressures and adopt phased disbursement of Financial Aid (FA) to ensure safety measures are applied systematically and not delayed.
- To address delivery risks linked to recent political developments, including the interim government and upcoming federal elections, BEK and LISP suppliers must closely monitor critical risk areas and their operational implications. Key mitigation actions include fast-tracking procurement before the election purdah period, coordinating with subnational governments to monitor operational security, and maintaining regular engagement with MoFAGA, the LISP Programme Coordination Unit (PCU), and the FRMIP Task Team to identify and respond to any emerging issues around intergovernmental fiscal transfers.

Fiduciary risks
Given the scale of FA within LISP—three times larger than other programme expenditures, fiduciary risk management is central to the programme’s overall risk framework. LISP channels capital funds through Nepal’s Treasury, but disbursements have yet to occur. Payments follow a reimbursement model, triggered only after asset completion, verification of physical progress and financial reporting.
With hundreds of infrastructure schemes across multiple LGs, the risk of misuse is inherent. To mitigate this, a comprehensive Fiduciary Risk Assessment (FRA) was completed in 2023, followed by a Fiduciary Risk Management Implementation Plan (FRMIP). BEK and DT Global work closely with MoFAGA to update FRMIP actions, and an Annual Statement of Progress (ASP) is underway to guide future improvements. Additionally, LISP is subject to bespoke audits by Nepal’s Office of the Auditor General (OAG), as part of UK’s MoU with the GoN, further enhancing accountability.
LISP also promotes e-bidding during procurement, and supports LGs in using improved User Committee models, where LGs handle procurement and committees manage labour. Despite these safeguards, recent reviews of the 302 schemes revealed some irregularities. These include misallocation of LISP funds to contingency budgets, purchases of non-infrastructure items, premature contractor payments, and discrepancies between contracted and paid amounts.
Once identified, such expenses are flagged as ineligible or pending justification. MoFAGA has cooperated fully, confirming that BEK is not liable for these costs. Overall, preliminary financial review of all 302 schemes show that about 0.5% of total expenditures was deemed ineligible, and 1.5% requires further review. This amounts will not be reimbursed during the first planned FA disbursement, planned in November 2025, pending OAG audit findings in early 2026. The findings from our reviews, the ASP and the OAG audit will inform updates to the FRMIP, helping strengthen financial oversight and reduce future risks.
The table below provides a summary of key risks identified during the FY24/25 document review, and associate recommendations:
Procurement Management and instances of non-competitive procurement	Plan procurement in advance and adequately space procurement process, promoting and overseeing competitive procedures to ensure value for money.
Lack or inadequate Insurance of Workers	Ensure worker insurance is arranged in advance and covers all workers (including prospective rosters), in both User Committees and contractor projects.
Errors contracting and during Accounting & Reporting	Verify payments against engineer-certified bills and ensure accuracy of contract agreements and records.
Gaps in Supporting Evidence	Require contractors to submit complete invoices for all items before acceptance of expenditure.
Failure to meet Cofinancing Commitments	LGs should fulfil agreed co-financing commitments; regular follow-up and dialogue recommended and non-compliance promptly escalated to MoFAGA.
Non-completion of works Physical Progress	Ensure timely completion of projects within fiscal years through regular reviews, surge support and follow-up actions.

Context Risks (political, spilling over into Delivery Risks)
Recent political developments in Nepal—including the formation of an interim government and the upcoming federal elections in March 2025—pose significant contextual risks that could spill over into both security and operational delivery challenges for local infrastructure programmes like LISP. While Nepal’s federal structure provides constitutional clarity, the practical functioning of intergovernmental relations can be disrupted during political transitions.
LISP’s delivery model relies heavily on functional local administrations, timely intergovernmental fiscal transfers and uninterrupted access to construction sites across multiple provinces. Political uncertainty may lead to delays in local budget approvals, disruptions in fiscal flows and temporary (likely localised) paralysis of local decision-making processes. The 40-day purdah period preceding elections could restrict procurement and contracting activities if not completed in time, affecting infrastructure timelines and FA disbursements. Additionally, heightened political tensions may compromise operational security in some areas and reduce LGs’ responsiveness to programme needs.
These risks are compounded by the reliance on coordinated action between federal, provincial (to a limited extent) and local governments: any breakdown in these relationships could undermine infrastructure planning, execution and oversight. Without proactive mitigation, LISP may face delays, cost overruns and reputational risks, especially if infrastructure works stall or safety standards are compromised.
Recommendations
Many of the recommendations around mitigation of delivery risks apply here. Additionally, MoFAGA and BEK should explore issuing temporary operational guidance for LGs during the election period, clarifying permissible activities and ensuring continuity in infrastructure delivery. This could include pre-approved procurement packages, flexible disbursement schedules and delegated authority for urgent decisions.
To safeguard infrastructure works and maintain momentum, LISP TA teams should also:
- Strengthen local contingency planning, including site-level risk assessments and alternative scheduling options (in collaboration with LG technical teams).
- Promote early initiation of works in the construction season to reduce exposure to political disruptions.
- Ensure transparent communication with LGs and communities, reinforcing trust and programme legitimacy during uncertain periods.
These measures will help LISP navigate political transitions while maintaining delivery standards and safeguarding its inclusive infrastructure agenda.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

LISP has so far utilised two main funding instruments for the delivery of LISP: a technical assistance MoU with WFP (up to March 2025), and a drawdown contract under the Global Development Delivery (GDD) commercial framework with DT Global (the main TA supplier). Moreover, LISP has included small contracts with Adam Smith International (ASI) to produce the FRA and FRMIP; Yale University for early learning support; and has an ongoing contract for independent verification and quality assurance (IVQA) with Pegasys Limited.

WFP
The LISP Pilot (and early transition) Phase concluded in July 2024, with the MoU going through multiple amendments to adapt to evolving piloting realities and delays in mobilisation of commercial TA suppliers. A fifth and last amendment extended WFP’s support to provide handholding guidance to the new TA provider DT Global (onboarded in November 2025) until March 2025. The total amended MoU budget reached £6,698,883, including £1,375,333 spent through a legacy project (RAP3) during the Pilot Phase. WFP utilised nearly all committed budget by March 2025, with the reimbursement of a small unused amount being currently finalised.

During the pilot / early transition phase, WFP signed MoUs with 15 target LGs in Karnali. LISP co-financing allocations were integrated into each LG’s SuTRA system and reflected in annual plans and budgets. Disbursements followed a performance-based reimbursement model, triggered by verified documentation and expenditure reports. LGs maintained separate records for LISP funding.

A separate MoU was signed for the LISP Recovery of Earthquake-Damaged Infrastructure (LISP REDI) in Karnali, following an earthquake in early November 2023 that caused widespread destruction in Jajarkot district. Running from 3 May 2024 to 31 March 2025, with a total budget of £4.2 million, the initiative supported resilient recovery and reconstruction across three LGs already enrolled under LISP. Initially, staffing overlaps with the main LISP workstream caused delays, but dedicated personnel with defined roles were later deployed, improving efficiency. The project was completed on time, with full budget utilisation.

WFP implemented adequate safeguarding and risk mitigation measures across both MoUs. However, field visits revealed gaps in beneficiary understanding of safeguarding policies—largely due to language barriers—highlighting the need for clearer communication by WFP staff.

WFP submitted all required reports, including the Project Completion and Learning Report on 1 August 2025. Project assets (mainly laptops) were transferred to DT Global as per FCDO guidance. All due diligence actions were completed.

LISP TA (DT Global)
A contract was signed with DT Global on 13 November 2024 (with end date on 13 August 2029) to deliver technical assistance for the main LISP implementation phase, in partnership with Care International (as sub-contractor).

Following contract signing, the DT Global started onboarding relevant staff, and LISP TA team started deploying at the subnational level at the start of 2025. Stakeholder mapping and coordination were initiated with BEK, MoFAGA, provincial governments in Karnali and Lumbini, and the IVQA team. This included active participation in LISP Steering, Technical Coordination, and Provincial Coordination Committees.

LISP TA collaborated closely with WFP during the handover phase (until 31 March 2025), initially shadowing delivery before assuming full responsibility from 1 April 2025. DT Global provided TA to all 35 LGs, supporting the 2024/25 construction cycle. For the upcoming construction cycle, DT Global expanded planning and project prioritisation support to 15 additional LGs, bring the total LISP geographical coverage to 50 LGs across the two provinces. An engineering internship programme was also launched in the spring to support delivery while also create local capacity for Nepali engineers.

A set of early amendments reflected changes in operational realities (including the integration of delivery activities during the inception period to compensate for mobilisation delays) and emerging ODA constraints, reducing the ceiling for the UK FY24/25 by approximately 8%. While at times imperfectly organised (also given the additional delivery pressures by BEK during inception) and tending towards risk-averse decision-making, DT Global have broadly shown commendable commitment to delivery of additional interventions outside the original contractual outlines, within extremely tight deadlines and through budget uncertainties—all during a major programmatic shift from partial direct (if government-centred) delivery by WFP, to a completely untested model fully owned by GoN (with FA through treasury and delivery through intergovernmental systems and procedures, with TA as a supporting and facilitating functions). This has required DT Global to learn and adapt in real time during delivery of several hundred infrastructure schemes and against an uncertain policy framework.

Coordination with BEK has been positive, with regular monthly and ad-hoc meetings covering programme updates, financial progress and policy issues. While communication and reporting have generally been strong, peer-to-peer technical collaboration between DT Global and BEK advisors has been less effective. The central DT Global team has likely reacted to heavy delivery pressures by focusing heavily on high-level solutions, relying on one-door communication approaches and restricting broader engagement with BEK technical teams and with subnational stakeholders. This hierarchical setup, while potentially explained by delivery priorities, has also reduced opportunities for meaningful interaction with subnational stakeholders (evidenced by limited subnational travel), hindering a full understanding of on-the-ground realities. Recent exchanges have encouraged a shift toward a more practical and context-sensitive approach—one that prioritises local-level challenges and tailors support accordingly, rather than over-relying on standardised, top-down strategies. This change is expected to improve collaboration, responsiveness and relevance of technical assistance across all levels of programme delivery, despite the reduced ambition following the decision to close LISP earlier.

DT Global has shown a calm and pragmatic approach in dealing with the two serious fatal incidents occurred in the second half of June 2025, acting immediately investigate the causes and propose short-term solutions and longer-term recommendations. A rapid Health and Safety risk assessment was conducted, with a final report shared with BEK and MoFAGA on 31 July 2025. Recommendations on health and safety are included elsewhere in the document (see sections A, C and E).

The Inception Period successfully concluded on 30 May 2025, with all deliverables—including the Inception Report—completed. The total TA expenditure during the review period is £2,913,653.

IVQA
The IVQA contract with Pegasys Limited currently runs from 16 October 2024 to 16 June 2028. As the expanded acronym entails, the contract covers independent verification and quality assurance of LISP-funded infrastructure. The IVQA team submitted the required inception phase report and a range of verification reports, but timeliness and quality have been a regular concern. The first verification report had significant quality issues (especially around generic findings and recommendations, and gaps in evidence showcasing) that required several rounds of comments to be finalised. The subsequent verification reports were much improved in terms of content and readability, but there is still space for improvement in future products to make findings and recommendations specific, useful to and actionable for LISP stakeholders (BEK, DT Global and GoN counterparts).

Forecasting and invoicing have been coordinated between the BEK LISP Programme Manager and the Pegasys Limited Programme Manager, who have working closely to ensure alignment between budgets and delivery. To date, IVQA has incurred expenditures totalling £137,532.

YALE and ASI
Both these smaller instruments have closed before the review period. Please refer to previous AR for details.

BEK performance
The BEK team was stretched during the review period due to multiple supplier transitions (closures, mobilisations, contracting) and staff changes that created uneven workloads and delivery pressures. Initially, the LISP team included a Senior Responsible Owner (SRO), a Senior Programme Manager/PRO, a Programme Officer and an Infrastructure Adviser. Over time, the team experienced several shifts: the departure and replacement of both the Infrastructure Adviser and Programme Officer, a long-term absence of the new Programme Officer, and the onboarding of a new Social Sectors Governance Adviser—all coinciding with the mobilisation of new suppliers and the peak of the construction season.

Despite these challenges, the team maintained strong support for LISP delivery, holding regular meetings with suppliers to track inception phase progress, overseeing infrastructure implementation in LGs, managing programme risks, and sustaining positive engagement with federal and subnational counterparts.

However, the unstable team structure somewhat affected cross-supplier coordination and limited collaboration and learning across BEK’s wider programme portfolio. As the team stabilises and LISP’s future becomes clearer, it is expected that workloads will balance and opportunities for joint learning and collaboration will expand.

The Governance and Social Development Group Head, SRO, advisors, and programme managers were also heavily involved in responding to the two serious incidents, reporting to HQ on reputational risks and pressing DT Global for appropriate follow-up actions.

Governance
The LISP Steering Committee (LSC), chaired by the Joint Secretary of MoFAGA, provided strategic guidance on the overall direction of the programme and endorsed key decisions. These included the approval of the LISP Implementing Guideline, the selection of 15 additional Local Governments (LGs), and the allocation of budget, as recommended and supported by the LISP Technical Coordination Committee (LTCC).

During the reporting period, two LSC meetings and four LTCC meetings were held. Additionally, two Provincial Coordination Committee meetings were conducted in each of the Lumbini and Karnali provinces to facilitate engagement and share updates on LISP.

A dedicated LISP Programme Coordination Unit (PCU) has been established within MoFAGA during review meeting, to provide operational coordination for the programme. The PCU works closely with LISP TA and BEK to plan and support the implementation of LISP infrastructure activities. It plays a leading role in organizing steering and technical committees and FRMIP Task Team meetings, tracking progress, reviewing and improving the policy framework, and conducting joint field visits to monitor progress. The PCU also provides timely feedback to ensure corrective actions are taken as needed.

Financial Overview of LISP
The table below summarises the financial position for the programme at the time of this review:
Components	Budget	Spend / (August 2025)	Balance	Remarks
Karnali Pilot / LISP Transition with WFP / 301010-401	£5,323,549	£5,322,703	£846	Actual WFP MoU commitment from BEK is £6,698,883 including RAP3 contribution of £1,375,334 during LISP Pilot Phase.
PFM/FRA DT Global / ASI / 301010-402	£161,298	£161,298	0	Contract ended in Jan 2024
LISP TA DT Global / 301010-404	£19,386,335	£2,913,653	£16,472,682
LISP FA Capital Fund / 301010-404	£66,000,000	0	£66,000,000
LISP IVQA / 301010-407	£1,499,925	£137,532	£1,362,393
LISP REDI / 301010-408	£4,200,000	£4,200,000	0	Completed in March 2025
LISP Learning with YALE / 301010-409	£114,897	£114,897	0	Completed in February 2025
LISP PFP for Social Sector, Governance and Infrastructure Advisory Support / 301010-110	£600,000	£38,935	£561,065
LISP Mid Term Review and Unallocated Fund	£813,996	0	£813,996

Total	£98,100,000	£12,889,864	£85,210,136

A MoU between the Government of Nepal (GoN) and the UK Government was signed through the Ministry of Finance (MoF) in March 2023, accompanied by the approved Programme Design Document (PDD). These documents establish the financial assistance ceiling that the Local Infrastructure Support Programme (LISP) will provide to the GoN over the programme’s duration, totalling £66 million.

Of this amount, £4 million has been earmarked to reimburse completed local infrastructure schemes by July 2025. As finalisation of Financial Monitoring Reports (FMRs) will require approximately two months, the corresponding payments will be released based on actual expenditures in October 2025.

## G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
During the reporting period, LISP employed a comprehensive four-pronged monitoring and evaluation approach to ensure programme accountability, learning, and adaptive management. First, the internal monitoring mechanism led by the LISP TA provincial and cluster team enabled continuous tracking of progress through field visits and engagement with local stakeholders. Second, local-level monitoring was conducted through Monitoring Committees led by the deputy chair at the local government level as per the Monitoring guidelines developed by the local government, which facilitated participatory oversight and community feedback. Third, the Independent Verification and Quality Assurance (IVQA) team completed all three stages of verification, providing an external layer of assurance on infrastructure quality and compliance with standards. Fourth, the British Embassy Kathmandu (BEK) conducted regular monitoring visits, offering strategic oversight and direct engagement with implementing partners and beneficiaries. Together, these mechanisms informed programming decisions, supported course correction, and strengthened the credibility and effectiveness of LISP’s delivery model.

Evidence
During this reporting period, evidence was generated through three key activities: analysis of the LISP Phase 2 selection process, IVQA verification, and the LG-level Political Economy Analysis. The Phase 2 selection process provided critical insights into how capacity and vulnerability intersect in targeting decisions. It highlighted that while the LG opt-in approach improved transparency, political pressure continues to influence infrastructure prioritization and the composition of user committees, often at the expense of inclusion. The IVQA verification, conducted in three stages, validated infrastructure quality and governance indicators, revealing disparities in implementation performance across LGs. These disparities were often linked to political settlements, with LGs exhibiting extractive tendencies showing weaker compliance and oversight.

The PEA profiles further reinforced these findings, showing that patronage politics and informal arrangements remain pervasive, particularly in LGs with weak horizontal checks or where mayors are in their second term. Election-related risks are rising, with evidence suggesting that programme resources may be diverted for political gains ahead of the 2027 elections. While the breadth of evidence is strong, combining qualitative and quantitative sources, gaps remain in disaggregated monitoring data. There is limited systematic tracking of inclusion by age, sex, disability, and geography, which constrains the programme’s ability to assess progress against the Leave No One Behind agenda. Strengthening inclusive data systems and aligning future evaluations with the Inclusive Data Charter will be essential to ensure that infrastructure investments are equitable and responsive to the needs of marginalised groups.

Learning
As mentioned above, LISP has employed a combination of structured learning processes to capture and share lessons, new evidence, and operational know-how during this reporting period. These processes were complemented by ongoing engagement with TA teams, LGs, and provincial stakeholders. The field visits, in particular, provided valuable real-time feedback on implementation challenges, local perceptions of the LISP approach, and the effectiveness of TA support.

Key lessons for the programme include the need to strengthen the integration of governance and GEDSI principles into infrastructure planning and delivery. While LGs have shown improved understanding of LISP procedures, many still treat it primarily as an infrastructure programme, rather than a governance initiative. Tools such as O&M, EIA/IEE, and grievance handling are being applied to LISP projects but not mainstreamed across broader LG functions. The IVQA and PEA findings reinforce this, showing that political settlements and informal arrangements continue to shape infrastructure outcomes, often at the expense of inclusion and transparency. The field visit also highlighted the trade-offs between prioritizing large, LG-level projects versus smaller, ward-level ones underscoring the risk of marginalizing vulnerable communities when project selection is driven by scale or political influence.

For FCDO and broader development work, the learning points to the importance of adaptive programming that responds to local political dynamics and capacity constraints. It also emphasizes the need for inclusive data systems and proactive engagement strategies that go beyond compliance to foster genuine ownership and accountability. The programme must prioritize capacity building, especially in climate resilience and GEDSI-sensitive design, and reassess TA deployment models to ensure equitable and timely support across LGs. Strengthening provincial engagement and cross-learning among TA teams will be critical to sustaining momentum and scaling good practices.

Looking ahead, the programme’s learning aims to understand how LGs developed their infrastructure project pipelines, who was included or excluded in the process, and whether the selected projects reflect climate resilience and GEDSI priorities. This study will generate actionable insights to inform future TA strategies, improve community engagement, and guide LGs in aligning infrastructure investments with inclusive development goals. It also reflects MoFAGA’s and BEK’s shared priorities for evidence-based decision-making and adaptive programming. In addition to this, the upcoming sensemaking workshop planned for November 2025 will be a key milestone to revisit learning priorities and co-agree future IEL study topics to capture lessons learned.

### Annex A – List of infrastructure schemes for the review period
### (see Excel annex)

### Annex B – Summary of LISP Critical Risks and Mitigation Approaches
### (cfr. Risk Register on AMP)

Risk Description	Risk Category	Likelihood	Impact	Gross Rating	Mitigation Actions
The transition of the programme from WFP to the new supplier (DT Global), along with the introduction of financial aid (through the on-budget & on-treasury mechanism) across a larger geographical scope, including Lumbini Province as a new LISP area, could result in stretched financial oversight, leading to potential financial mismanagement or misuse of funds, thereby increasing the risk.	Financial & Fiduciary	Possible	Major	Major	Develop, implement & adequately resource financial oversight including implementation of the FRMIP recommendations & appropriate PPFM QA. / Continuous review of risk & implementing relevant mitigating measures, with adequate escalation frameworks for subnational teams.
Limited awareness and poor enforcement of health and safety standards among construction workers, contractors, and local governments—especially in hazardous environments and extreme weather—pose serious risks of injury, fatalities and property damage.	Safeguarding	Likely	Severe	Severe	Develop and enforce a standardised health and safety framework across all project phases. / Ensure mandatory safety training and provision of protective equipment for all workers. / Integrate gender-sensitive safety measures and insurance into project planning and contracts. / Embed health and safety protocols into LISP’s infrastructure design, procurement, and supervision systems. / Strengthen monitoring and accountability mechanisms at LG level to ensure compliance.
Political influence over infrastructure decisions and worker selection may undermine transparency and limit inclusion of vulnerable and marginalised groups, despite safeguards introduced by LISP’s opt-in processes and improved operational modalities	Strategy & Context	Likely	Major	Major	TA to ensure the improved modality is effectively followed & implemented, establishing clear & transparent criteria for selecting & prioritising infrastructure projects, construction workers, & user committee members. / Targeted training & awareness programmes to be conducted for LG officials & stakeholders, emphasising the importance of equity, inclusion, & merit-based selection based on the Formation of User Committee Guidelines.
Insufficient technical capacity and staffing gaps—especially among newly qualified LG engineers and overstretched rural teams—risk poor infrastructure design, weak compliance with standards, and reduced sustainability. These limitations also constrain LISP TA’s ability to scale delivery and build lasting local capability.	Policy & Programme Delivery	Highly Likely	Major	Major	Provide targeted technical support and mentoring to LG engineers and contractors throughout the infrastructure cycle. / Develop and share practical guidance tailored to LISP standards. / Align project planning and budgeting with available technical capacity. / Facilitate peer learning and collaboration across LGs. / Coordinate with government institutions to strengthen engineering capacity and address staffing gaps
The on-budget and on-treasury funding modality is new to most LISP-implementing LGs, there may be gaps in capacity and understanding to fully comply with its requirements. This poses risks of ineligible expenditures, weak budget execution and challenges in meeting fiduciary standards. Delays in budget release, poor reporting systems, and political influence over project selection further increase the risk of non-compliance and may affect LISP’s infrastructure targets and reimbursement processes.	Policy & Programme Delivery	Highly Likely	Major	Major	Support LGs in adopting policies and procedures aligned with LISP’s financial modality. / Provide targeted training and on-site assistance to strengthen planning, budgeting, and implementation. / Monitor delivery and offer corrective guidance to ensure compliance with LISP standards. / Coordinate with MoFAGA and LGs to uphold fiduciary safeguards, conduct financial reviews, and enable timely fund release and reporting.
The September 2025 political crisis, followed by the formation of an interim government leading to federal elections in March 2026, may disrupt administrative continuity, delay intergovernmental fiscal transfers and restrict procurement and contracting activities—especially during the pre-election purdah period. These disruptions could affect LISP’s infrastructure planning, execution and FA disbursement timelines, potentially undermining programme delivery and value for money.	Strategy & Context	Possible	Major	Major	Fast-track procurement and contracting activities before the purdah period to avoid delays. / Coordinate with MoFAGA and LGs to issue temporary operational guidance for LGs during the election period, clarifying permissible activities. / Promote early initiation of infrastructure works to reduce exposure to political disruptions. / Strengthen contingency planning at LG level, including alternative scheduling and site-level risk assessments. / Maintain regular engagement with MoFAGA, the Programme Coordination Unit (PCU), and the FRMIP Task Team to monitor and respond to emerging risks. / Ensure transparent communication with LGs and communities to reinforce trust and programme legitimacy during uncertain periods.