# Wajibika Programme in Tanzania Annual Review

Title: Wajibika Programme in Tanzania
Programme Value £ (full life): 15m by FCDO / An additional £10.625m by the Swiss Embassy in Tanzania		Review date: 10/05/2025
Programme Code : [AMP ID#] 301011	AMP start date: 18 July 2023	AMP end date: 31 March 2030

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007234.xlsx

## A: SUMMARY AND OVERVIEW
## Description of programme

The Wajibika business case was approved in June 2023. The vision for the Wajibika programme is that it uses a flexible, adaptive, issue-based, coalition-led approach to support civil society organizations and media to help Tanzania move further in the direction of a more "Open Society." Promoting an open societies agenda in Tanzania will contribute to an improved policy environment for reform e.g. on the business environment and education, both which are top UK priorities for Tanzania - and facilitate more open Tanzanian relationships with key partners, including the UK. The Wajibika Programme is a new flagship programme for FCDO Tanzania. Wajibika is consistent with FCDO Minister for Africa, Lord Collins speech he made during the International Human Rights Day, December 2024…. “Human rights and the rule of law are the basic building blocks of sustainable economic growth, stable societies, and humane migration policies. My 5 priorities to help deliver the key missions of the government: defending civic space and fundamental freedoms; Upholding the rule of law; champion equal rights for all; Support accountable, effective & inclusive institutions; and prioritise human rights and governance principles
## Summary supporting narrative for the overall score in this review

The actual Wajibika programme implementation is yet to start. The main achievement during the period under review was a successful design and implementation of inception phase that has allowed a consortium of partners (national and international) to successfully and efficiently finalise the design of Wajibika and set up required structures and systems for successful delivery of the programme. Through Wajibika component three (Governance Innovation Facility - GIF Component) Wajibika was able to support Tanzania Vision 2050 as well as this year’s World Media Freedom Day. Key achievements delivered during the period under review include:

Successful designing of Wajibika Component Strategies: these strategies were designed. They set overall frameworks on how Wajibika programme will be delivered. They included: a) Civic Space Strategy which sets a framework for how Wajibika will contribute towards building: an enabling environment for civic engagement; provide flexible support to Civil Society Organizations (CSOs) towards solving policy problems in a way that delivers tangible benefits for citizens; and to strengthen civil society effectiveness; b) The Media Strategy which proposed a two-pronged approach towards working and supporting media: working with existing media coalitions and other actors to bolster efforts at countering disproportionate regulation of the media sector; and providing support to targeted sections of the media to enhance professionalism and the capacity to undertake quality journalism; and c) GIF Strategy which sets a framework for how Wajibika will deliver flexible approach to provide targeted technical assistance to the GoT to support governance reforms that are consistent with Wajibika objectives.

Completed Political Economy Analysis (PEA): undertakings of regular PEAs will ensure the programme is ‘working and thinking politically’. These PEAs will be undertaken six monthly. During inception phase, PEAs completed were: a) An Opportunity Assessment PEA. By working on carefully selected issues with motivated civil society partners, Wajibika aim is to help secure improvements to policy (and its implementation); prove the value of civil society to the government; and defend and expand civic space (the goal of the programme). In selecting the policy areas to focus on, Wajibika is emphasising the idea of ‘sweet spot’ issues. These are issues where there is a good combination of: the potential for a positive development outcome; clear demand or interest from government; and the prospect of assembling a coalition of motivated civil society partners. Demonstrating civil society’s ability to contribute constructively to areas that ‘go with the grain’ of government interests and motivations can help earn the trust and confidence of the administration, which may be necessary in order to undertake more challenging reform issues further down the line. Through this PEA analysis, initial ‘sweet spot issues’ identified are: youth employment, skill development and livelihoods; health sector reform (including universal coverage, health insurance, health security, quality of services); women’s political inclusion and empowerment; and b) Civic Space and Media PEAs. These PEAs have enabled the inception team to identify niche areas where the programme can initially focus towards addressing specific civic space and media freedoms through Wajibika support.

Completion of Programme Management Frameworks: these included: value for money (VFM) framework; Wajibika Monitoring, Evaluation, Adaptation and Learning (MEAL) Strategy; Wajibika Adaptive Results Framework; Wajibika Risks Management Strategy; Wajibika Operations Manual (Finance, Procurement, DSA Policy, Governance Arrangements); Wajibika Grants Management Framework; Wajibika Gender, Equality, Disability and Social Inclusion (GEDSI) strategy, GIF Strategy and Manual.

Completion of Programme Team Deployment and Office Set Up; by the end of inception phase the following full-time members of Wajibika Team has fully been deployed and based at DSM – Programme Director, Deputy Programme Director, Technical Leads for Civic Space, Media, GIF, Programme Manager, Finance and Administration Lead, MEAL Lead. Wajibika office is co-located with OPM Tanzania office at Dar es salaam.

Provided Technical and Coordination support to the National Planning Commission on Vision 2050. Through this support, Wajibika was able to deliver the following products:
  - Developed a “financing TDV2050” options paper
  - Supported National Bureau of Statistics to ensure aligned for V2050 Workstream 3 on Data and Information Systems
  - Developed draft Human Capital Development strategy for TDV2050
  - Finalized deep dive analysis of Oil and Gas - Liquified Natural Gas (LNG) project.
  - Finalized V2050 Multidonor Support - Legal & Governance Structure Options

- World Press Freedom Day in Arusha this year, Wajibika, in collaboration with UNESCO, Jamii Africa, Nukta Africa and the University of Dar es Salaam, coordinated three plenary sessions:
  - The Future of Media Sustainability
  - Misinformation and fact checking: The Role of AI and Emerging Technologies
  - 2025 General Elections: The news and media- what journalists want

A total of 103 journalists, including presenters, programme managers, and station managers, received training on election reporting. This training focused on critical areas that are often inadequately covered by the news media. The training benefited 52 local radio stations.
## Major lessons and recommendations for the year ahead [1/2 page]
Wajibika inception phase was intentionally long (up to seven months) to allow sufficient time for programme team to fully mobilize, undertake political economy analyses and carry out external consultations to ensure identified issues and strategies are context specific and relevant for Tanzania. External consultations involved donors, government and non-government actors. Within civil society groups, consultations included NGOs, faith-based organizations, academia, thinktanks, and grassroots organizations. UK, Swiss and other donors were consulted to help ensure Wajibika design is both complimentary and adds value and is not duplicating what other donors are planning to do in the civil society and media freedom landscape in Tanzania. Overall, these consultations were of good quality, thorough and well structured.
Wajibika inception and design has been informed by lessons from the Swiss’ Social Accountability Programme (SAP, 2019–2022), and FCDO Accountability in Tanzania Phase 2 programme (AcT, 2015–2022). These lessons included:
SAP and AcT both highlight the importance of integrating political economy analysis and ‘thinking and working politically’ approaches. A major challenge in both programmes was the perception by government that donor-funded CSOs were advancing external interests. To navigate this, Wajibika will focus on locally identified pressure points that resonate with citizen needs, and that are in less sensitive political areas. This will allow civil society partners build confidence and capacity to address pertinent issues, before addressing more challenging issues that constrain civic space.

Lessons from both SAP and AcT highlight the importance of political economy analysis to align programme expectations with realities. A key finding from SAP was that donors expected sudden and sweeping political change after President Samia Hassan came to power in 2021. However, insights from the SAP’s political economy analysis suggested that change would be more gradual. Wajibika will undertake PEA every six months to ensure key issues are identified

Developing a programme that is responsive to citizens’ priorities will strengthen engagement and promote greater accountability in government. Findings from SAP indicate that for the average citizen, issues of democracy, accountability, and good governance are often subsumed by more immediate needs, such as an adequate water supply, food shortages, and infrastructure issues. Focusing on these pressure points resonates with citizens and enables CSOs to demonstrate their value in a tangible way. Similarly, a recommendation from the SDC Media support programme as the need for media outlets to actively engage their audiences and provide relevant content to gain patronage.

Civil society programmes need to explore how to ensure their long-term sustainability. Lessons from AcT and SAP show that many larger CSOs continue to rely heavily on donor funding, driven both by a challenging civic space, and a lack of knowledge on how to access funds from alternative funding sources, such as social enterprise funds and foundations. Wajibika will explore ways to strengthen the long-term sustainability of the CSOs and media. This has been factored into the design of the programme.

Results from civic space interventions can be slow to materialise. AcT found that allowing time and space to identify politically viable pressure points led to more sustainable results, even if immediate results were not always evident. By providing long-term support to CSOs, AcT enabled them to identify areas where they could work more effectively and take risks to address politically sensitive issues. Some AcT successes only became apparent after the programme concluded, highlighting the need for a long-term perspective.

Balancing short-term wins with long-term strategies is critical. While short-term flexible funding helps CSOs achieve small-scale successes, sustained support is required to build their confidence in addressing deeper structural issues. Wajibika is a six-to-eight-year programme. Wajibika will ensure good balance between short term vs long-term strategic support to CSOs and media to ensure successful delivery.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
## Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The Theory of Change (ToC) for Wajibika is built around three building blocks (pathways) – Convening, Catalysing, and Influencing. Many of the outputs and outcomes to be delivered by Wajibika are mutually reinforcing. The more CSOs and media coordinate effectively to influence government on civic space, the more margin they have to demonstrate their value to government and citizens and thus become more influential actors.

The ultimate Outcomes Wajibika aims to contribute to are in the following domains: a) Strengthened Civic space: CSOs develop stronger connections to the public, effectively deploy evidence to demonstrate their value to government, and challenge disproportionate regulation. Coalitions (CSOs, media, faith-based organisations) are strengthened to promote inclusive politics and engage citizens – particularly women - in the democratic process; b) Media freedom and access to information: media challenges disproportionate regulation, including of the online space, and grows its capacity for public interest journalism; c) Government service delivery: Government and key actors are supported to explore new solutions to tackle longstanding service delivery challenges.

Building blocks for Wajibika’s Theory of Change
Wajibika as convener: Wajibika will convene alliances across CSOs, media and stakeholders (on both the demand and supply side, including donors) to address salient issues around inclusion, civic space and democratic rights. This responds to an observable lack of such convening and coordinating mechanisms among existing civil society actors. Where such alliances are particularly underdeveloped, Wajibika will support the early stages of their development including through political economy analysis, stakeholder identification and strategic design. Emphasis will be placed on sustainable collective organising which creates networks between organisations which can be activated and repurposed as necessary according to the key issues of the day. Wajibika will also facilitate learning and sharing of best practice to support the use of an adaptive flexible programme approach.

Wajibika as catalyst: Wajibika will make use of small grants as a mechanism to support CSOs, media and other key actors in their efforts for systemic change. Seed and catalytic funding will be targeted towards issues that are strategic in that they enable civil society to better function as a whole in a sustainable way, rather than purely focusing on any one thematic issue. This could include political economy analysis; technical assistance (TA), pilot projects, and meetings/conferences. Wajibika will seek to be a co-creator of these initiatives, helping CSOs develop ideas rather than doing grant making.

Wajibika as influencing vehicle: Wajibika will be grounded in the development concept of ‘thinking and working politically’. It will focus on issues where the political conditions exist for change. Wajibika’s influencing strategy will be multi-pronged. CS and media partners will be supported to effectively design influencing strategies that are regularly reviewed and updated. CS and media partners will be supported to better understand influencing strategies, individually and collectively, across informal or formal, inside track or outside track activities. The FCDO will also be an influencing actor itself, where it can add value through lobbying and public diplomacy activity. The Governance Innovation Fund (GIF) component of Wajibika is designed strategically as an incentive to influence government in support of Wajibika’s goals, as well as providing practical support to delivery.

By implementing these strategies, Wajibika will seek to open, or at least help protect, Tanzania’s civic space and increase the effectiveness of the use of the space, even with its current restrictions, to the benefit of citizens. That, in practice, means:

- Expanding inclusiveness: Including a range of actors beyond traditional NGOs and CSOs, such as women’s groups, FBOs, social movements, academia and representatives of the private sector.
- Collective action for the benefit of the wider ecosystem: Bringing diverse groups together to further shared interests and ideas, beyond individual organizational interest.
- Connecting activity explicitly to citizens’ priorities: Enabling civil society actors to gain greater credibility with the public by representing their concerns.
- Delivering results with accountability, in tangible and constructive ways.
- Working in politically smart ways with government, to build trust and influence.
- Building resilience and sustainability, to thrive in the face of shocks.
## Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The actual Wajibika programme implementation is yet to start.

The intended impact (“Impact”) of the Wajibika is a more open and inclusive society in which government demonstrates greater accountability to, and collaborates with, civil society to find innovative public service solutions that better meet the needs of citizens. An interim outcome for Wajibika during the inception phase was: Stronger and more effective civic and media space, including through more accountable and responsive Government.

During the inception phase, there were good examples of the programme contributing to more accountable and responsive Government. These will contribute to improved policy, strategy and service delivery. Wajibika supported GoT Development Vision 2050. Tanzania is currently formulating its strategic Vision 2050 and accompanying technical Long Term Perspective Plan. These strategic planning statements are on a 25-year cycle, replacing Vision 2025. As such their content and the process for formulating them is completely different from that for annual and medium-term plans – these are not about funding trade-offs and implementation plans, they are a strategic beacon which can guide those shorter-term implementation plans for many years.

The responsible agency for managing the Government’s role in delivering TDV2050 is the National Planning Commission under the President’s office. Its role takes on a number of high-level functions including the oversight and delivery of TDV2050; provide economic policy; conduct economic management and research and develop strategies for development. Wajibika provided direct technical support to the PC on financing strategy for the V2050; V2050 human capital strategy, natural gas deep dives, Vision 2050 Multidonor Support - Legal and Governance Structure Options. Wajibika has also supported donor coordination for V2050 to ensure coherence and avoid duplication. The overall Wajibika support to DV2050 was built on clear theory of change that if …the Govt. of Tanzania is able to develop its national vision, strategy, and family of economic plans through a credible process….and ..if Tanzania is able to build its strategic management capabilities that convert vision and plans into actions and impact via 5-year implementation plans…then Tanzania increases the chance of creating a more inclusive growth model in the years up until 2050

In addition, in March 2025, during the World Press Freedom Day (WPFD) in Arusha, Wajibika, in collaboration with UNESCO, Jamii Africa, Nukta Africa and the University of Dar es Salaam, delivered three plenary sessions: The Future of Media Sustainability; Misinformation and fact checking: The Role of AI and Emerging Technologies; and 2025 General Elections: The news and media- what journalists want. Over 250 participants from Government, media and CSOs attended the above sessions. The Wajibika support also helped cover the costs of the WPFD Keynote Speaker - Aidan Eyakuze, Chief Executive Officer, Open Government Partnership (OGP). Through the WPFD engagement and contribution, Wajibika was able to contribute to shaping the discourse among media, civil society, and development partners on tackling media sustainability issues in the digital era and devising strategies to counter digital mis/disinformation. At the UDSM session, journalists were encouraged to actively uncover and report instances of political interference in the media in order to strengthen public accountability. The goal was to foster a critical discussion on pressing media challenges including and the growing threat of misinformation and disinformation while exploring sustainable models for a resilient and independent digital future.

In the year ahead, full implementation of Wajibika will begin. Wajibika will continue to undertake regular PEAs and work with coalition partners to deliver the ambition of the programme.
## Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio . Wajibika responds toUK Minister for Africa Lord Collins speech which he made during the International Human Rights Day, December 2024…. “Human rights and the rule of law are the basic building blocks of sustainable economic growth, stable societies, and humane migration policies. The intended impact (“Impact”) of the Wajibika of a “more open and inclusive society in which government demonstrates greater accountability to, and collaborates with, civil society to find innovative public service solutions that better meet the needs of citizens” remains relevant to Tanzania.
## Wajibika’s ‘sweet spot’ approach is timely and appropriate, especially in Tanzania, where civil society, and media, faces several significant challenges and restrictions. Demonstrating civil society’s ability to contribute constructively to areas that ‘go with the grain’ of government interests and motivations can help earn the trust and confidence of the administration, which may be necessary in order to undertake more challenging reform issues further down the line, for a more open civic space.

## C. DETAILED OUTPUT SCORING

Output Title	Effective inception period for procurement (used for 2023-24 and 2024-25 only)
Output number:		1	Output Score:	A
Impact weighting (%)		75% (in Years 1 and 2) 0% (future years)	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Inception and procurement completed effectively and on time to enable successful programme set up.	Inception report completed and approved, including an agreed workplan, Political economy analysis, theory of change, results framework.	The following inception milestones have been completed and approved: / Wajibika Component Strategies for Civic Space and Media Freedoms / Wajibika Theory of Change / Wajibika MEAL Strategy / Wajibika Results Framework / Wajibika Value for Money Framework / Wajibika Grants Making Strategy and Manual / Wajibika GEDSI Strategy / Wajibika Risks Management Framework / Wajibika Communications Strategy / Wajibika Operations Manual (Finance, Procurement) / Wajibika Travel, Accommodation and DSA Policy / Wajibika GIF Strategy and Procedure Manual / Workplan for Year 1 of Implementation including: Implementation Milestones and Annual Forecast / Service Credit (Key Performance Indicators) KPIs tracking tool. / Transparency Key Performance Indicators (T- KPIs) / Transparency Key Performance Indicators (T-KPIs) / Exit Strategy that addresses what will be done in the event of closure or termination of the services under this Contract

## Briefly describe the output’s activities and provide supporting narrative for the score.

Wajibika inception phase period was seven months. It was intentionally long to allow sufficient time for programme team to fully mobilize, undertake political economy analyses and carry out external consultations to ensure identified issues and strategies are context specific and relevant for Tanzania. External consultations involved government and non-government actors in Dar, Dodoma, Mwanza, Zanzibar and Kilimanjaro – representing different zones across the country. Within civil society groups, consultations included NGOs, faith-based organizations, academia, thinktanks, and grassroots organizations. FCDO, Swiss and other donors were equally consulted to help ensure Wajibika design is both complimentary and adds value and is not duplicating what other donors are planning to do in the civil society and media freedom landscape in Tanzania. Overall, these consultations were of good quality, thorough and well structured.

OPM deployed a mix of international and national expertise to ensure strategies and issues selected are informed with local context and political underpinning in the country. The role of national expertise cannot be overemphasised. Wajibika full-time technical Team is formed of technical advisors drawn from within Tanzania and in the region. This is very important as they bring deep historical and contextual underpinnings.

Completed inception deliverables have complied with FCDO requirements. FCDO cross-cutting advisors were pro-actively engaged to ensure both compliance and quality are fully met. FCDO cross-cutting advisors that reviewed these deliverables included FCDO Advisors/Leads on: Results, Value for Money, Safeguarding, Political, Programme Risks Compliance, Finance and Procurement. In addition, Swiss Embassy advisors in Finance, Governance and Political Teams were also part of the quality assurance who provided extensive review and comments to ensure deliverables meet Swiss compliance requirements.

FCDO Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO) were responsible to ensure Wajibika design complies with aspirations set in the business case, meets UK and Swiss standards and on day-by-day basis, were responsible towards holding the supplier accountable to ensure smooth and successful delivery of the deliverables.

## Describe any changes to this output during the past year, and any planned changes as a result of this review.

## This was an interim output. New Wajibika outputs have now been finalised and will inform next year’s annual review.
## Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key actions/recommendations for the year ahead:
The year ahead marks the beginning of implementation cycle for Wajibika programme. All new strategies and frameworks will be rolled out to inform programme implementation. The following actions/recommendations have been agreed with Wajibika Team:
By Aug/Sept 2025, Wajibika Team to finalize and submit all logframe refinements (milestones, targets, % weighting) as well as clearly defining all the indicators and case studies methodologies. In addition, OPM will set milestones for 2026 and set milestones and targets for future years.

Issued-based approach: Wajibika will continue to use political economy analysis to identify ‘sweet spot’ issues that resonate with citizens and attract support from civil society, media, and government. By Jan 2026, Wajibika Team will undertake PEA to assess emerging GoT priorities post-elections to identify ‘sweet spot’ issues that resonate with the new government.

Elections-specific risks: given the upcoming elections in October 2025, Wajibika Team will carry out an election-specific risks analysis that identify key risks and challenges during the pre-and-post election period and identify implications for the programme.

Options for adapting the programme to respond to emerging UK priorities in Tanzania: FCDO is currently reviewing their priorities for Tanzania. Following these reviews, Wajibika team will develop a clear plan and strategy to pivot the programme to adapt to the new priorities.

Output Title	Improved capability of Government or civil society aimed at strengthening civil society and media, and improving accountability and responsiveness of GoT
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number and description of activities to improve civil society and media voice or strengthen accountability and responsiveness of government.	4 studies or activities completed / (2) Civil Society and Vision 2050 Governance Innovation Fund studies completed, with positive feedback on quality, timeliness and value from lead advisers / Yearbook publication and effective dissemination: 2024 yearbook published, including one special research report; at least 100 citations in media or academia, 300 copies distributed, 1 presentation outside Tanzania. / Impactful yearbook training and use: Four media houses trained in 2024; training of trainers conducted twice a year; accreditation of trained trainers once a year; 2 workshops a year with universities and colleges on use of quality criteria	Technical support to Vision 2050: / Analysis and producing a High-level commentary of the TDV2025 / Producing a Revised Macro Policy Framework / Quality assurance and peer review of TDV 2050 Revised draft 1 / An analytical framework and the Terms of Reference for individual studies required to take the development of TDV50 to the next stage / Developed ToRs to deliver selected deep dives i.e. human development strategy’ / Produce Workplan & Roadmap to deliver the work through Parliament in June / Produced a fundable Project document for supporting PC to produce and implement TDV2050 / Support coordination of development partners’ support of the 18 analytical deep dives and L-T Perspective Plan in 2025 until the end of the Parliamentary process. This includes updating the Heads of Agency DPG when required / Finalized V2050 Multidonor Support - Legal & Governance Structure Options / Liquid Natural Gas Deep Dive (report, PowerPoint, workshop) / Accountable Grant to University of Dar (UDSM), School of Journalism / Yearbook Report 2024 published and disseminated. 172 participants attended Yearbook 2024 launch. / 400 yearbook reports have been distributed to journalists, media houses, training institutions, media organisations, regulatory bodies, international organisations / 103 journalists 37 female & 66 male) from 52 local radio stations trained on election reporting. This training focused on critical areas that are often inadequately covered by the news media. / World Press Freedom Day (WPFD) in Arusha this year, Wajibika, in collaboration with UNESCO, Jamii Africa, Nukta Africa and the University of Dar es Salaam, coordinated 3 plenary sessions: / The Future of Media Sustainability / Misinformation and fact checking: The Role of AI and Emerging Technologies / Media and the 2025 General Elections during the national conference on World Press Freedom Day (WPFD) 2025.

## Briefly describe the output’s activities and provide supporting narrative for the score.

During period under review, Wajibika, supported activities that helped to improve civil society and media voice as well as strengthen accountability and responsiveness of government.

Wajibika provided Technical Assistance (TA) support to the Planning Commission (PC) that is providing vital and acknowledged support towards the wider V2050 processes. These efforts are contributing to:

- V2050 Analysis, Strategy, and Plans: providing analytical foundation to support the Vision, the Strategy, and the suite of plans that will drive the delivery of Vision 2050. These analytical products will inform that 5-Year Development Plan, a key socio-economic policy framework
- V2050 Coordination and Financing: The initial TA support has focused on supporting the coordination and mobilization of donor financing for Vision 2050, including the development of Trust Fund proposals. These efforts aim to foster a conducive environment for funding the Vision, reinforce government ownership, and strengthen alignment and buy-in from both government stakeholders and development partners
- V2050 Data and Information Systems. This includes exploring alternative approaches for developing Data and Management Information Systems to support the Planning Commission in monitoring and evaluating national projects.
On support to media: Wajibika in collaboration with Nukta Africa, UNESCO, and Jamii Africa co-hosted two key sessions at WPFD event in Arusha. These sessions were attended by over 200 participants including from the government of Tanzania and addressed some of the most pressing issues facing the media in Tanzania and across the region. Over the two-day gathering, one message came through loud and clear, journalists need to be protected, especially during the period leading up to the next elections to ensure they are not exposed to threats, harassment, or violence. Under the theme “Reporting in the Brave New World: the Impact of Artificial Intelligence on Press Freedom and the Media” WPFD events in Arusha was a timely platform for examining the role of the media in strengthening transparency, accountability, and civic engagement as Tanzania enters a political period ahead of Presidential Election in October 2025. On media sustainability, speakers highlighted the urgent need for innovative business models and a policy environment that supports freedom of expression and protects the role of the media as a democratic watchdog.

Through the WPFD engagement and contribution, Wajibika was able to contribute to shaping the discourse among media, civil society, and development partners on tackling media sustainability issues in the digital era and devising strategies to counter digital mis/disinformation. The Yearbook Report documented positive and negative trends in media coverage and reporting of the civic elections. UDSM works closely with both the GoT and media organizations to implement recommendations. During WPFD event, the UDSM led a session that encouraged journalists to actively uncover and report instances of political interference in the media, a key to strengthening public accountability.

## Describe any changes to this output during the past year, and any planned changes as a result of this review.

This was an interim output. New Wajibika outputs have now been finalised and will inform next year’s annual review.

## D. VALUE FOR MONEY
## Key cost drivers and performance

The focus during inception period, was to complete a Wajibika Value for Money (VfM) framework in alignment with FCDO VfM guidance on adaptive programmes. This task has been completed. During inception phase, key cost drivers where fees for long- and short-term technical team that delivered the inception deliverables. The quality and timeliness of delivery were all good. There was a good mix of national and international expertise which balanced well and ensured that the design of Wajibika is relevant to the in-country context.

Wajibika is an adaptive programme which tests various pathways to change through initiatives which are structured as projects. The VFM framework’s definitions of the ‘Es’ recognise the centrality of learning and adaptation. Wajibika VfM framework uses the OPM methodology following the guidance in the Wajibika business case and supported by OPM experience of its suitability in other adaptive FCDO governance programmes. The OPM methodology uses a framework of performance criteria and performance standards to provide an agreed transparent basis for interpreting the evidence and arriving at well-reasoned judgements:

VfM criteria defines what is meant by each of economy, efficiency, effectiveness, equity, and cost-effectiveness.
Performance standard	Definition
Excellent	The intervention is meeting and, in some cases, exceeding all reasonable expectations/targets and/or is showing exceptional progress overall.
Good	The intervention is generally meeting reasonable expectations/targets and/or is showing good progress overall.
Adequate	The intervention is fulfilling minimum ‘bottom-line’ requirements and/or is showing acceptable progress overall.
Poor	The intervention is not fulfilling ‘bottom-line’ requirements and/or is not showing acceptable progress overall.

VfM dimension	Wajibika-specific definition
Economy	Wajibika’s team manages programme resources to a high standard, procuring inputs of appropriate quality for a reasonable price. Appropriate resources are procured for speedy and effective adaptive management.
Efficiency	Wajibika’s management processes comply with good practice and deliver good quality, timely outputs. Its adaptive management processes quickly deliver / high quality, actionable adaptive management outputs.
Effectiveness	Wajibika’s project change strategy progress markers specify meaningful changes to which the project contributes.
Cost-effectiveness	Wajibika’s project change strategy progress markers relate the cost of project inputs to meaningful changes.
Equity	Wajibika ensures equitable processes and contributes to equitable outcomes

VfM standards (rubrics) provide defined levels of performance (excellent, good, adequate, and poor) for each of the criteria; they describe what the evidence looks like. Standards may include ‘indicators but the sense is wider than that: a level of performance may for instance be evidenced by a narrative. The complete set of indicators, which will include project and partner level VfM will be developed once coalitions of CSOs and media are up and running and have specified their target output and outcome results.

Wajibika VfM framework is designed to generate data for both learning and accountability. Data that will inform both the adaptive management process and for the annual review’s assessment of programme VfM. The VfM framework effectiveness measures are defined by reference to the MEAL framework’s progress markers; thus, the same data-gathering exercise underlies both outcome tracking (in the MEAL framework) and VfM assessment. The VfM framework will entail a combination of assessments at both the programme and individual project levels. The following table summarises the methodology that Wajibika will adopt:
## VfM performance compared to the original VfM proposition in the business case.

A full VFM strategy for Wajibika programme has now been completed as part of inception phase interventions. It includes metrics covering economy, efficiency, effectiveness, equity and cost effectiveness, as defined in FCDO’s Approach to Value for Money.

Wajibika will VfM lens throughout the Wajibika life cycle. At the outset, programme management systems and processes will be scrutinized to ensure economy, efficiency, and equity; at year-end they will be assessed, providing examples of good practice. (Some CSO and media partners may trigger criteria for partner economy and/or efficiency scrutiny and assessment.) At the start of each accountable grant, stakeholders usually in coalitions will devise progress markers that meet MEAL/VfM criteria; and quarterly or half-yearly project reviews against their progress markers will be input to the adaptive management resource re-allocation process, shifting resources to better performing projects.

At year-end, projects will be assessed against their progress markers and rated using the VfM scoring system to obtain their VfM effectiveness rating (including the equity of outcomes), and against their budget utilization to obtain their VFM cost-effectiveness rating. The project VfM ratings will then be selected and weighted to obtain component and programme VfM effectiveness and cost-effectiveness ratings, for submission to the annual review.

E: RISK

The Wajibika Programme operates in a complex and politically sensitive environment, requiring a robust and adaptive approach to risk management. The overall risk remains Major and has not changed since the business case was approved. A detailed Risk Register is attached at Annex A.

Trends and Key Risk Drivers
The main risk trends this year have been shaped by Tanzania’s political landscape, including upcoming elections, civic space restrictions, constraints on freedom of expression, and donor funding cuts. Safeguarding and SEAH risks remain a priority, with no major incidents reported.
Risk Monitoring
The UDSM Yearbook Project identified several political and operational risks, including potential boycotts of Local Government Elections (LGEs) due to dissatisfaction with new electoral laws, and the suspension of local radio stations involved in programme monitoring. Press freedom remains a concern, with high risks of self-censorship and perceived media bias. A number of these risks were mitigated through journalist training, regulator engagement, and contingency planning. Medium-level risks such as funding shortfalls and possible political interference with the 2024 LGE report launch were addressed through stakeholder engagement and efforts to secure co-funding. While risks remained within appetite, continued monitoring and adaptive management were essential particularly in the context of safeguarding freedom of expression and ensuring neutrality in media reporting.

As part of the inception phase deliverables, our main delivery partner Oxford Policy Management (OPM) designed a robust Risk Management Framework, which is grounded in transparency, proportionality, and accountability. Risk is managed at three levels—programme, project, and downstream partner—through quarterly reviews, six-monthly Political Economy Analyses (PEAs), and regular updates to the risk register. Gender equality and inclusion will be actively monitored through the GEDSI strategy, and all grant proposals will be assessed for “do no harm” and inclusion.

Risk Appetite Review
 Across FCDO’s seven risk categories, the programme over the last year has largely operated within our risk appetite, programme implementation team has highlighted specific risks:
- Strategy & Context: Residual risk remains moderate due to political volatility and civic space constraints. Adaptive programming and trust-building with government have helped manage this.
- Policy & Programme Delivery: Risks are moderate, particularly around coalition effectiveness and delivery capacity. Mitigation includes rigorous partner selection and diversified interventions.
- People: Risks such as staff turnover and underperformance at are moderate and managed through strong HR systems at OPM.
- Safeguarding: Risks are moderate to major, especially in politically sensitive regions. Safeguarding policies and training are fully embedded.
- Financial & Fiduciary: Risks are moderate to major. Due diligence, and financial oversight remain strong, we have planned audits in the pipeline. The planned ODA cuts pose a major risk to the programme from 2026/7 onwards.
- Reputational: Risks are moderate to severe, particularly around partner conduct and government perception. Strategic communications and vetting processes are in place.
- Climate & Environment: While Wajibika does not directly implement environmental interventions, climate sensitivity was considered in the project design. Environmental integrity and climate change resilience underpin the Tanzania Development Vision 2050 as one of its core pillars.

Due Diligence and Partner Risk
All coalition and downstream partners have undergone Enhanced Due Diligence Assessments (DDA). Risks identified—such as weak financial systems or limited delivery capacity—have been addressed through targeted capacity-building. Some DDAs may require refreshing due to time lapse or organisational changes. Overall, partner risk levels have remained stable.
Delivery Within Appetite
The programme has largely delivered within risk appetite. Areas of pressure—particularly safeguarding and reputational risks—have been managed through proactive mitigation. In the year ahead, the focus will be on refreshing DDAs, strengthening climate risk awareness, and maintaining adaptive planning to respond to political developments, particularly around elections.

Update on Partnership Principles [1/2 page]
The BHC conducted a Partnership Principles Assessment (PPA) in July 2024, it found that while some political and media freedom issues have improved over the past 5 years, Tanzania still has notable limits on freedom of expression and political pluralism. Tanzania’s commitment to human rights and civic freedoms remains mixed, with notable gaps in adherence to international treaties and court rulings, particularly concerning media laws and judicial fairness.

Wajibika does not use the Partnership Principles as a formal conditionality for the monitoring of the programme. However, we will use relevant sections of the PPA to guide choices of engagement with relevant public institutions to monitor the progress of the programme. This proportionate approach is appropriate for Wajibika since 20% of the Wajibika programme budget has been allocated towards the Governance Innovation Facility (GIF) which will provide flexible technical assistance (TA) to identified government institutions to contribute towards improvements in accountability and service delivery. Wajibika will not provide direct Financial Aid (FA) to government institutions.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Wajibika is jointly funded by FCDO and the Embassy of Switzerland, with FCDO as the lead partner.
The programme is implemented by the University of Dar es Salaam’s School of Journalism and Mass Communication and Oxford Policy Management. SJMC operates under a short-term accountable grant. OPM operates under a longer-term commercial contract and is the lead partner of a consortium which includes REPOA, Uongozi Institute, ESRF, Inter Religious Council for Peace Tanzania, Media Council of Tanzania, Helvetas, Abt Britan, Kivu and Thomson Foundation. FCDO adopted a proportional approach to managing the two partners, with the bulk of effort spent managing the higher value longer term contract. The programme is monitored through a mix of weekly meetings to discuss activities progress, and formal quarterly steering committee meetings to discuss strategic issues and grant formal approval for work.

In order to ensure successful delivery of all the planned activities and that implementation was of high quality and meets FCDO compliance requirements, SRO and PRO led both the weekly programme management meetings with the OPM senior team as well as the quarterly steering committee meetings which provided overall oversight of the delivery of planned interventions. In addition, as part of ensuring Wajibika is designed in ways that meet both FCDO and Swiss country objectives, a high level meeting between OPM and Heads of Missions (UK and Swiss) was organised to share highlights of the emerging design of the Wajibika Programme whilst giving HoMs opportunities to influence the direction of travel of the new programme.
This Annual Review focuses on the delivery of the inception phase, during which 12 milestone deliverables were completed in order to set up the required strategies, systems, policies and procedures needed to implement the Wajibika programme over the next 6 years.
The Wajibika inception phase was extended up to the end of March, and OPM provided comprehensive insights, produced high quality analysis, detailed reports and strategies on risk, finance, procurement, standard operating procedures, communications, a grants manual, a GIF manual, KPI’s, a VFM framework, a MEAL plan, a payment milestone schedule, component strategies and a workplan for year 1.
The programme applies a proactive, politically informed approach to risk management. Risks are identified and monitored through a rolling Political Economy Analysis and Opportunity Assessment, complemented by insights from partners. There are clear protocols for donor funding changes, including adaptive programming and transparent communication with downstream partners. All risks are tracked through a Risk Management Framework and Register ensuring systematic oversight at programme, project, and partner levels.
Wajibika is jointly funded by FCDO (56%) and the Embassy of Switzerland (44%). FCDO funding was utilised during the inception phase (see financial table below) and continues into implementation, while Swiss funding of CHF 7.8 million will be brought in during the implementation phase.
The implementation partners budget forecasting has remained strong, although minor variances occurred due to the extension of the inception period. The University of Dar es Salaam audit report was delivered on time with a clean opinion, and the Oxford Policy Management audit is scheduled in the next 9 months. Assets were purchased during the inception period, and a detailed register is maintained by the partner as well as FCDO. Asset spot checks are planned for the next reporting period.
FCDO FUND UTILISATION:

COMPONENT	BUDGET	SPENT	BALANCE
Civil Society Support	£8,100,000	£402,915	£7,697,085
Promoting media freedom and access to information	£2,700,000	£267,108	£2,432,892
Governance Innovation Fund	£2,850,000	£268,617	£2,581,383
Design, Evaluation, Results validation costs	£1,350,000	£0	£1,350,000
TOTAL	£15,000,000	£938,640	£14,061,360

Agreements with the SJMC, OPM and the Embassy of Switzerland were signed during the inception phase. We have drafted TORs for the planned Evaluation procurement, as well as the External Audit, updates will be provided as part of the next Annual review.

The next Annual Review will report on implementation of the programme, including performance against KPI’s, compliance with the new cost and transparency requirements and gender equality.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
As part of inception phase, a comprehensive Wajibika MEAL strategy was designed. Wajibika (MEAL) framework seeks to provide evidence in relation to: the operations and management of Wajibika; results of the Wajibika programme and its projects and the changing context which affects Wajibika.

The Wajibika MEAL system focuses on generating evidence for learning and adapting, and includes Political Economic Analysis, Social media listening and civic space diagnostics to monitor trends in civic space and public discourse and provide real-time insights into the evolving political and social landscape. Monitoring activities will include quarterly and six-monthly reviews involving FCDO, implementing and coalition partners, beneficiary feedback surveys and tracking the representation of women, youth, and persons with disabilities in coalitions.

Components of the Wajibika MEAL Strategy:

The results framework is based on the new FCDO adaptative Annual Review process, and is structured around four performance areas — delivery, actionable learning, contribution to meaningful change, and fitness for purpose. The Terms of Reference for an external evaluation has been developed to conduct robust, independent mid and end-of-programme evaluations.

Evidence and Learning

During the inception phase, Wajibika adopted a politically informed approach to issue selection, grounded in a macro-level political economy analysis and an opportunity assessment. This process identified “sweet spot” issues—policy areas combining strong government demand, potential for positive development outcomes, and the ability to convene motivated civil society coalitions. Initial deep dives into priority areas reinforced the importance of starting with issues that align with government interests to build trust and demonstrate civil society’s constructive role. This learning has shaped programming decisions by focusing on coalition-based strategies that can gradually expand civic space while mitigating risk. The evidence base is broad but evolving, and the approach reflects lessons on how to operationalise politically smart programming in restrictive contexts.

One of the key emerging areas for Wajibika to focus on is youth, employment, and security. This area offers significant opportunities for mobilising Wajibika’s resources and coalitions. Two other potential areas include Universal Health Insurance and child sexual exploitation; the latter being seen as a promising entry point for exploring broader criminal justice sector reform.

A post‑election refresh of the Political Economy Analysis will be essential to recalibrate emphasis and ambition in line with evolving political dynamics.

Generating high-quality, contextually relevant evidence and using that evidence within (and when appropriate beyond) this programme is central to Wajibika’s approach. Structured reflection workshops will be held quarterly, involving programme staff, donors and implementing partners. These will review progress, assess context shifts and guide decisions. Learning priorities for the next year include exploring the use of social media analytics, civic space diagnostics and stories of change to better understand influence, space to engage and outcomes.

Date of last narrative financial report	UDSM- March 2025. / OPM- March 2025	Date of last audited annual statement	UDSM: March 2025. OPM – new contract, due in September 2025.