## Annual Review – January 2024

Title: Shifting the Power. Strengthening African Civil Society
Programme Value £ (full life): / FCDO: £30,000,000 / Comic Relief: £30,045,000 / Total £60,045,000		Review date: March 2024
Programme Code: 301034	AMP start date: 31/03/2020	AMP end date: / 9 March 2030

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	B	A
Risk Rating	Moderate	Major	Major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/55428258.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301034/documents

A. SUMMARY AND OVERVIEW

Description of programme:
The ‘Shifting the Power’ (StP) programme is a 10-year partnership between Comic Relief (CR), the Foreign Commonwealth and Development Office (FCDO) and partner organisations, referred to as Anchor Partners (APs), in Zambia, Malawi and Ghana. The programme was announced in March 2020 during CR’s annual televised fundraiser (Sport Relief 2020). In partnership with CR and the British public over five annual televised matched appeals, the programme will invest £60 million in equal amounts to each organisation – (with CR providing an additional £15,000 to each AP in 2023 to support organisations with the rising cost of living globally) – to strengthen the capacity and sustainability of locally-led civil society organisations (CSOs) in Ghana, Zambia and Malawi that are working across priority areas for both FCDO and CR including: Early childhood development, gender justice, enabling peace and security, safe and secure shelter and mental health. In following the principles of the #ShiftThePower movement, local CSOs can identify their own focus areas. For example, the programme in Ghana has included access to public services, whilst in Zambia, the areas of focus have extended to climate justice/environmental degradation.
[note] Anchor Partners are local civil society infrastructure organisation/s with whom Comic Relief partner with to jointly design the programme, and to provide programme management in each country. The Anchor Partners consist of: Zambian Governance Foundation (ZGF) in Zambia, Tilitonse Foundation (TF) in Malawi and Star Ghana Foundation (SGF) and West African Civil Society Institute (WACSI) in Ghana.
[note] The StP programme is part of the broader global Shift the Power Movement. The core principles of the movement, thus the programme, are outlined in the #ShiftThePower: A Manifesto for Change.
The core programme activities will be delivered via three funding streams and a comprehensive package of organisational strengthening for CSOs:
- Fund one: The Catalyst Fund (CF) will provide accessible grant funding to support small grassroots organisations that might not otherwise be able to bid for funding. The purpose was to enable the programme to reach small organisations that are new to FCDO/CR funding and therefore likely to benefit more from organisational strengthening (OS) support and enable them to create positive change in their communities.
- Fund two: The Civil Society Strengthening Fund (CSSF) will provide a mix of core and restricted funding to support CSOs with organisational strengthening and resilience, which is critical to delivering their strategic mission and achieving and overcoming some of the barriers to building organisational sustainability.
- Fund three: The Community Resourcing Match Fund (CRMF) will provide training for CSOs in alternative forms of local income generation, where any income generated locally will be matched by the fund, serving to incentivise income diversification and financial sustainability.
In addition to the above grants, a package of organisational strengthening (OS) support will be provided to CSOs, enabling them to identify and tackle the challenges that hinder them from achieving their mission and organisational sustainability.
The programme aims to begin addressing the negative consequences that short-term, project-focused funding (typically channelled through Northern-based intermediary organisations) can have on the ability of Southern-based CSOs to respond to the priorities of local communities. This includes the power dynamic between the donor and CSO that shapes such funding and weights the donor and International Non-Governmental Organisation (INGO) intermediaries’ priorities above those of local communities.
The intended impact is that CSOs in Ghana, Zambia and Malawi are more resilient, independent, and effective in responding to the priorities of local communities. The programme will deliver on four principal objectives:
- Locally led, Southern based CSOs will be supported to become more effective, sustainable and better able to represent local priorities around key thematic areas in Ghana, Malawi and Zambia.
- The FCDO’s partnership with CR will work more strategically through jointly funding a programme that will span five annual matched appeals (rather than developing a new programme annually) and 10 years of programming.
- Working collaboratively with African storytellers, filmmakers and creatives, this programme will enable CR and FCDO to communicate a progressive narrative to the United Kingdom (UK) public, demonstrating how aid is enabling local communities to pursue their own priorities and to stand up for their rights.
- The programme will be innovative and adaptive. It will generate learning on the efficacy of different interventions, designed to advance organisational capacity and resilience which will be influential in programme design within CR, FCDO, other funders and amongst CSOs themselves.

"The Shifting the Power programme presents an opportunity for us to work with local CSOs in a manner that truly reflects the needs and aspirations of the citizens of Malawi. It responds to the long-standing cry of Malawian CSOs for community defined development agendas and a localized approach that supports people move out of poverty and deprivation!"
Robert White, CEO, Tilitonse Foundation

Summary supporting narrative for the overall score in this review:
The overall score for this review is A and is informed by progress made towards the five outputs of the programme, which have been met, or, in some instances exceeded. Only one output has been partially met scoring a B, which is output four:
‘Local or community philanthropy is supported across civil society’.
The reason for this is that there has been a delay in operationalising the Programme Advisory Panels (PAPs) or their equivalent in Malawi and Zambia, due to AP concerns that the structures are at odds with the locally led decision-making aspect of the programme.
Met - Output one focuses on StP programme partners [CR, FCDO (for this programme), APs] aligning their practices to the #ShiftThePower Manifesto for Change. During this review period CR and APs delivered a programme of work to ensure alignment with the principles and manifesto. Activities included:
- One session on ‘How to operationalise the #ShiftThePower Manifesto in the programme’ at a convening event in Lusaka in April 2023 – the first in-person meeting of APs and CR.
- Participation in several UK and international conferences - both as a participant and speaker - including facilitated workshops and webinars organised by partners in the wider movement such as: the Segal Family Foundation; African Philanthropy Conference, WINGS Forum and the global Shift the Power summit.

At the national level, APs undertook several activities including:
- Zambia – The independent service providers selected by the Zambian Governance Foundation (ZGF) to support with the delivery of OS activities for grant partners underwent orientation on the StP ethos prior to starting the delivery of services to CF partners and CF CSO partners were introduced to the StP community-led development approach.
- Malawi – Organised and delivered a Shift the Power Conference on the StP programme and #ShiftThePower principles to broader civil society and galvanised support for the programme and movement. In line with Shift the Power principles, Tilitonse Foundation (TF) organised a co-creation session to develop application templates for the CSSF. The aim was to ensure that the templates are user-friendly and reflect the needs of the users and facilitate mutual ownership collective drive.
- Ghana – Has made conscious efforts to embed the #ShiftThePower principles through being intentional about demonstrating the key tenets of the StP programme by running every action by the question “How is this shifting power”? Discussions are regularly held with staff for a collective understanding of shifting power and its operationalisation within the programme.

Met - Output two is concerned with evidence and learning from new or different funding models that engage and strengthen some of the key principles of the programme, including: locally led and sustainable development; equitable partnerships and an asset-based approach, and their impact on CSOs. In the year under review, progress has been made through programme learning. The establishment of a StP learning subgroup has entrenched a collaborative and equitable way of working that creates a sense of shared responsibility for the learning, ensuring learning is not purely extractive and is useful for all partners. For example, co-creation and consensus decision-making is now a standardised way of working and is exemplified in the foundational learning documents that have been formulated or reviewed through a co-creative process. Similarly, collective learning events, like the CF and logframe update events, were co-designed and co-led by APs. The StP programme met this output as all milestones have been met.

Exceeded - Output three centres on strengthening authentic representation of how civil society contributes to their communities. In the year under review, delays in the delivery of the CF resulted in challenges to collect and curate stories from grassroots funded partners. Significant progress has been made to ensure collaboration and decision making is undertaken with APs through the creation of the advocacy and comms subgroup and regular bi-weekly meetings. This, in turn, has led to collaborative ideation sessions and a series of activations to showcase the programme, amplify local voices, and highlight learnings and themes linked to the programme’s aims. Finally, CR and APs have established a clearer understanding of the target audiences and recommendations based on findings from an audience insights report, which has allowed CR to influence and secure an extended slot on the Night of TV to showcase creative content via spoken word poetry – produced, written, and inspired by young people living in Ghana, Malawi and Zambia. The Shift the Power programme has exceeded this output as all milestones have been exceeded.

Partially met - Output four relates to local or community philanthropy being supported across civil society. Philanthropy is key to the success of the Community Resourcing Matching Fund (CRMF) which is the next fund to be rolled out after the CSSF. This year sees the start of preparatory work to lay the foundation for the design and implementation of the CRMF with a meeting held earlier in January between the delivery partners (CR and APs) to agree on how best to take this work forward.
The PAPs were to be established in this review period – with Ghana having established its equivalent of the PAP but there have been delays in Malawi and Zambia. The reason for the delay was that APs sought clarity on the role and responsibilities of the PAPs to ensure that these added value to the process, built on the importance of existing governance structures and were overall in keeping with the principle of locally led development and decision-making of #ShiftThePower.
Discussions between the three partners (FCDO, CR and APs) ensued and were completed in October 2023, enabling establishment of the PAPs to commence in Malawi and Zambia. The PAP structure in Malawi and Zambia are expected to be signed off by the end of this review period. This output has been partially met as the milestone to establish PAPs in all three countries has been delayed – whereby they are being created but will not be operational by financial year end as had been planned.

Met - Output five focuses on organisational strengthening (OS) across civil society organisations and StP partners. There is a focus to ensure areas of OS are self-identified by CSOs and partner organisations. Considerable work was undertaken in relation to this output. APs used the OS framework they developed in 2022 to guide their work of OS with the CF grantees. APs also began implementation of their own OS plans. Finally, CR developed its own OS Framework and Principles, based on accumulated learning from many years of successes and challenges in supporting OS. In 2023 the CR framework entered its ‘test and learn’ phase, supporting funded partners across Africa to apply this framework through designated organisational strengthening funding from Red Nose Day (RND) 13, 15 and 19. In early 2023 CR conducted a review to assess the effectiveness of the framework and approach to strengthening civil society organisations to continue to reflect on, and learn from this work both in terms of the experience of participating funded partners and CR’s own funding practice. The output from this exercise is a guidance manual that the StP programme will use to develop a systematic process to ensure learning from this is embedded in the OS work.

Major lessons and recommendations for the year ahead:

Major Lessons:

Building equitable and trust-based partnership working is complex:
Equitable partnerships require a range of characteristics including finding the right partners to work with, time to establish relationships and demonstrate commitment, a culture of trust, open communication, and ways of working that are inclusive, transparent and learning-centred. Much of the initial stages of the programme are centred on co-creation and reimagining systems and processes – an ongoing journey that required significantly more time than originally anticipated. The process has been of equal and sometimes greater value than the final product due to the learnings, reflections and richness of the discussions in an attempt to reimagine how all organisations (FCDO, CR and APs) work in partnership, dismantle traditional 'power centred' relationships and embrace new ways of working that centre the voice, experience and expertise of partners.

The importance of shared understanding of the aims and objectives of the StP programme across all partners on the programme:
The StP programme aims to influence the wider donor sector including funders and organisations of the global north. The aim is to create equitable partnerships and relationships with shared accountability amongst partner organisations. FCDO and CR, as co-funders, recognise and acknowledge the inclusive and revolutionary ways of working on the programme evidenced through the engagement and involvement of APs in overall risk management, inputting into logframe changes and VfM design - elements that have not been done before in other FCDO and CR co-funded projects. For the programme to progress, it is important that there is continued shared understanding of and commitment to the aims and objectives of the programme across all partners and that this tangibly translates into all aspects of the delivery of the programme.
1. Collaboration and shared ownership results in more authentic storytelling and influencing:
   The creation of an advocacy and comms subgroup has been central in ensuring CR and APs work equitably and collaborate in designing collective influencing and communications, delivering authentic, inclusive, and representative content with those with lived experience and closer proximity to the issues.
2. Creating a culture, and ways of working that are inclusive, equitable and locally led takes time to develop, embed and establish and can therefore slow down implementation:
   CR and APs remain committed but realistic in terms of activity planning for the 2024 year and beyond. 2023 was the first year of full programme implementation and this lesson was keenly felt, as both APs and CR underestimated the commitment, time and resources required to deliver the programme in line with the inclusive, equitable and locally led ethos and values of the programme.

Recommendations:
Summary of recommendations for the year ahead	Owner	Completion Date
Equitable partnerships – Using the findings from the partnership assessment, continue to embed the StP principles in the partnership and improve ways of working.	CR/ FCDO/APs	Ongoing - Start next partnership assessment in March 2024
Collaboration across the delivery chain – Further develop inclusive collaborations with all stakeholders in the delivery chain including local CSOs funded and supported through the programme to disseminate the StP principles to the broader CSO sector.	CR/APs	Ongoing
Translate the immeasurable strength of the partnership into tangible activities - including ways of delivery and reporting that ensures partners are all accountable to their audiences.	CR/ APs	Ongoing
Focused learning – Now that the foundations for learning across the programme have been co-created and established, more focused or themed learning is required to capture progress. In the upcoming year, focus will be on learning from future grant funds including the CSSF and the CRMF.	CR/ APs	January 2024 then ongoing for duration of programme
Long-term storytelling - Now that the CFs have been awarded, CR and APs will continue to grow relationships with local content creators, grassroots communities and start designing and curating stories that captures change over the length of the programme. Drawing on the focus from the audience insights and seeing evidence that StP delivers and is value for money is crucial for public comms and strengthening the collective influencing for the programme.	CR// APs	Ongoing
Thematic approach - In 2023 the focus was on establishing the advocacy and comms subgroup, establishing what co-creation of content and collective influencing looks like and looking closer into what works for different audiences. In the next Annual Review, the focus will be to take a thematic approach, create a long-term comms plan and work closer with local communities to ensure they are accurately represented.	CR/ FCDO	Ongoing
Build in the Shifting the principles in the implementation of the PAPs – CR will listen attentively to the perspectives of APs concerning the PAPs and how they are performing to ensure alignment with ethos and values of the programme, taking particular care that PAPs contribute to enhancing governance in APs	CR/ APs	Ongoing
Review the risk appetite – The StP programme has begun work taking into consideration the work completed by RINGO on re-imagining risk.	CR/ FCDO/ APs	Embedding of re-imagining risk to be an on-going part of this programme

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Shifting the Power: Strengthening Civil Society Theory of Change
The StP programme differentiates itself from other programmes as its intentions are to not only impact the organisations and individuals that the programme works with and funds in Ghana, Malawi and Zambia but to also challenge and change donor practices more broadly when funding CSOs including the StP programme funders - CR and FCDO. The theory of change encapsulates the experimental nature of the programme and its intention to generate new learning and insights towards power shifting in international development and donor environment, and on civil society strengthening. Specifically, it highlights the programme’s aims:
- For a more resilient, sustainable and community-led local civil society in Ghana, Malawi and Zambia.
- The change in narrative of the British public on aid to one of empowering local communities and;
- The change in donor practice and culture that is characterised by long-term investments, locally led development, equitable partnerships and collaboration.
The Theory of Change outlines how CR and FCDO will work collaboratively with local APs and appropriate in country governance mechanism's ability to generate funding locally through a ‘Catalyst Fund’, ‘Strengthening African Civil Society Fund’ and ‘Community Resourcing Match Fund’ respectively. The ToC assumes that by identifying and investing in their own organisational strengthening priorities and diversifying their funding models (with support from APs and local providers), CSOs will be better able to develop, and stay true to, their long-term strategies in response to local people’s priorities. Greater flexibility and autonomy afforded by enhanced organisational capability and a more diverse and sustainable funding model will increase CSOs’ effectiveness while reducing reliance on foreign donor funding. Accountability can therefore shift away from distant donors and towards local people, building local trust and engagement.

No changes have been made to the StP Theory of Change. However, CR and APs undertook a thorough exercise to co-create and develop the foundational learning documents of the programme. This exercise included the development of the learning questions that will drive the learning programme, drafting the first programme-wide learning agenda, and reviewing and updating the logframe. The updated logframe now better reflects the theory of change and the activities of the programme. The above-mentioned work was undertaken co-creatively and equitably in partnership with partner organisations in Zambia, Malawi and Ghana.

Value for Money:
The Value for Money (VfM) case for this programme was agreed to not be based on cost per beneficiary calculations, which would be at odds with a theory of change which is seeking to move away from the buying of outcomes through short term project funding and towards strategic investments which will have wider social and economic value which sustains long after funding ends.

This is also in line with CR’s approach to VfM which is defined as:
“To give scope to communities and their partners to define the social change they want to see happen and what success looks like now and moving forward. Our investment goes beyond money to our relationships, models, approaches, expertise and communications. We recognise that we contribute to a bigger picture of social change, alongside other actors.”
The StP Programme continues to offer value for money in terms of effectiveness, equity and economy:
- Effectiveness - Centring learning as a core function of the programme where partners, including local CSOs, APs and funders, asses the changes achieved and identify what could be improved. AP’s growing experience in delivering the required interventions to achieve the short-term outcomes from the planning and delivery of the CF.
- Equity - Equity is fundamentally at the heart of the StP programme, which explicitly seeks to minimise / neutralise inequitable power dynamics both between funders and APs, and subsequently between APs and their funded partners within each country. The partnership assessment conducted in 2023, demonstrated the establishment of trusted relationships across the programme and the areas where the partnership could improve. As programme implementation proceeds, the programme further entrenches a culture across the programme that centres the Shift the Power principles and practices including inclusive language, co-creation, locally led decision-making, and distributed leadership and mutual accountability. The CF enabled organisations who might not otherwise be funded to develop their systems and processes, so they are ready to receive funds. It aims to support organisations to succeed in applying to the CSSF, where each AP’s fund design is specially designed to enable small grassroots organisations to secure CF grants. It was delivered in the context of each AP country with each using different methods to engage with organisations who might not otherwise be funded to develop their systems and processes, so they are ready to receive funds. APs utilised different methods and platforms to engage with local CSOs including radio, road shows to hard-to-reach regions, posters, social media and existing CSO networks.
- Economy - A core principle of the programme is to work collaboratively, transparently and in equal partnership. This is embedded through the co-creation of the programme and component grants, as well as the collaborative approach to find solutions to any challenge. This approach ensures that meaningful engagement with stakeholders is at the centre of the programme’s design, implementation and adaptation. This approach harnesses the vision, resources, energy and skills of all partners and enables more sustainable change through greater ownership and ultimately power to influence change in their communities and in the broader donor environment.
This type of work takes longer than resorting to historic and inequitable funding approaches as it is crucial for these foundations of collaboration, transparency, equity and trust to be in place for this work to flourish and can only occur within a safe space built on mutual trust, shared risk and benefit.

Logframe – Impact
Impact statement	The funding ecosystem is transformed to enable civil society organisations in Ghana, Zambia and Malawi to be more resilient and effective in delivering the priorities of local people
Indicator(s)	Milestone(s) for this review	Progress
1.1 Improvement in civil society organisation sustainability rating in Ghana	N/A	N/A
1.2 Improvement in civil society organisation sustainability rating in Zambia	N/A	N/A
1.3 Improvement in civil society organisation sustainability rating in Malawi	N/A	N/A
1.4 Shifting the Power principles and practices are more prevalent in the UK, Ghana, Malawi and Zambia.	N/A	N/A

Indicators:
There are no milestone targets for the impact indicators for this reporting period. The programme has just begun the delivery phase so measuring any changes in broader civil society this early in the delivery phase would not be attributed to the programme.
During the review of the logframe, the consensus was that capturing the change in broader civil society will have to be further developed and discussed. The current measure is the Civil Society Organization Sustainability Index (https://www.fhi360.org/resource/civil-society-organization-sustainability-index-reports) and the Civicus Monitor (https://findings2021.monitor.civicus.org/). Both were viewed as inadequate measures; therefore, partner organisations will review this in more depth at the next in-person convening event in Malawi in April 2024.
Changes to the Impact indicators
The StP learning subgroup reviewed the logframe in 2023 and the following changes were made to the logframe for this reporting period. Changes to the other milestones beyond milestone 4 can be found in the ‘change frame’ in the updated logframe.
Logframe section	Original / detail of change	Amended statement or indicator	Notes
Impact statement	Civil society in Ghana, Zambia and Malawi organisations are more resilient, independent and effective in delivering the priorities of local people.	The funding ecosystem is transformed to enable civil society organisations in Ghana, Zambia and Malawi to be more resilient and effective in delivering the priorities of local people.
Impact 1, Indicator 4	NEW INDICATOR	StP principles and practices are more prevalent in the UK, Ghana, Malawi and Zambia.'	Milestones to be determined after looking into more suitable measures for this overall impact statement

The Impact statement has been updated to capture the broader impact across the donor ecosystem instead of understanding impact as only in AP countries. The new indicator captures the impact in AP countries and the global north funders.

Logframe – Outcome:

Outcome statement	The funding ecosystem and civil society organisations are better able to respond to the priorities and needs of communities.
Indicator(s)	Milestone(s) for this review	Progress
1.1 Evidence of positive steps towards change in funding practices of FCDO, CR, and APs that have resulted in increased responsiveness to the needs of the communities.	Three case studies from the initial set up of the programme and delivery of the catalyst fund. Each country will appear in at least one case study.	The three case studies have the following themes - / Co-creation/ collaboration of Logframe – #ShiftThePower principle three / Relationship building e.g., convening events - #ShiftThePower principle two. / Authentic story telling – #ShiftThePower principle six
1.2 Evidence of CSOs with improved capacity and financial sustainability through the various forms of funding received through the programme	Examples of how Catalyst Fund has improved capacity of CSOs (annual reports and data monitoring)	Ghana - Care for Society Network International https://fb.watch/pCnSus8RMt/ / Zambia - Nkandabwe Citizen Voice and Action https://youtu.be/cySs_gf6p0U?si=o2855zPkkC1ndAIa / Malawi – See case study in 1.2 below.
1.3 British public better understand and support the need to shift power to communities so that they can lead their own change	Audience insights completed and baseline set	First audience insights completed in 2023

1.1 Evidence of change in funding practices of FCDO, Comic Relief, and APs that have resulted in increased responsiveness to the needs of the communities.
The programme differs in that it goes beyond change in the individuals, communities or countries where funds are spent, but is equally focussed on change in the broader donor ecosystem including change amongst funders including FCDO and CR. All partners aimed to deliver the programme in line with the ethos and values of the programme. The three case studies demonstrate how the initial set up of the StP programme has reimagined traditional ways of philanthropy and how these practices have laid the foundation for the delivery of the programme that is more responsive to the needs of local communities and can demonstrate new ways of working to the broader donor community. The three case studies are each themed on a specific principle that underline the programme and broader movement. They represent ways the programme, in the early stages, has tried to put into practice more equitable, inclusive, local and asset-based approaches to development.
1.2 Evidence of CSOs with improved capacity and financial sustainability through the various forms of funding received through the programme.
During this reporting period, APs designed and delivered the first funding call of the programme. The CF provided small grants to help strengthen small civil society organisations who would normally not receive significant funds from funders. The CF distributed 68 six-to-twelve-month grants ranging in value from £3,275 to £5,000, totalling £260,000 across three countries. Through the CF learning session, APs demonstrated the different methods they used to reach a diverse range of CSOs to ensure an equitable spread of funding. For two countries (Malawi and Zambia) the six-month timeframe to provide organisational strengthening support was extended to better ensure the support would lead to sustainable change in the CSOs. An example of how the CF has improved, or provides an opportunity, to improve capacity of local CSOs is below:
An organisation in the Northern Region of Malawi had been without funding since 2016.
Development partners would not give the organisation any funding because it was not a
registered entity. To make it worse, the organisation was in no position to register as it relied on members to finance its operations and survival from individual giving. Even local district authorities that had worked with the organisation previously, had stopped involving them in their work. The organisation was stuck in limbo, unable to progress or continue in their current state and all programmes and activities had significantly reduced or were discontinued, save for a few community interactions and cost-free activities members would hold from time to time. Seven years later (in 2023), they qualified for the Shift the Power Catalyst Fund. They used the grant to register their organisation with the Non-Governmental Organisations Regulatory Authority and the Council for Non-Governmental Organisations in Malawi. They also strengthened structures and systems such as their Board and their financial system. A month after getting registered, the organization has been granted funding for a multi-year project that they are expected to implement as part of a consortium. From near closure, the organisation has been given a new lease of life.

1.3 British public better understand and support the need to shift power to communities so that they can lead their own change.
In April 2023, CR commissioned the Development Engagement Lab researchers to deliver a piece of research that explored ‘audience insights’ to better understand the British public’s understanding on localisation and aid. The main purpose of this was to explore the British Public’s appeal of and feelings towards charities that provide aid overseas, explain and gauge reactions to the traditional model of aid delivery and understand its perceived strengths and weaknesses. Finally, and perhaps more crucially, to present the Shift the Power model as an alternative to the traditional model and assess if its method and aims are easily understood by donors (British taxpayers).
The approach to the research involved two 90-minute text-based surveys conducted on YouGov and examined how people who donate to international charities felt about the traditional model and the Shift the Power model of aid delivery. The data collected from the UK public was collected in two ways: via qualitative data through focus groups with the demographics of participants being: eight men and 13 women between the ages of 24-72 years old and a mix of ethnicity, social grade and geography. Secondly, by quantitative data via an anonymous survey of 1,000 –10,000 people based in the UK.
In summary, the report found, to shift public perceptions around shifting power, and gain further support for communities to lead their own change; the programme needs to demonstrate the effectiveness of this model through empirical evidence and case studies. It needs to soften the language used in its branding, for example many feel the word ‘Power’ is a politically charged word and focussing on ‘community leadership’ and ‘empowerment’ are alternative ways to make it more palatable. Public communications need to emphasise the skills and expertise held by local communities that enable this model to be successful. Finally, the report concluded highlighting the weaknesses of the traditional model and outlining how StP will help assuage the concerns of those who believe in its effectiveness and may make them more amenable to alternate forms of aid delivery.

Changes to the Outcome indicators:
The StP learning subgroup reviewed the logframe in 2023 and the following changes were made to the logframe for this reporting period. Changes to the outcome statement, indicators and milestones can be found in the ‘change frame’ tab in the updated logframe.
Changes to the outcome statement and related indicators better reflect the change the programme aims to achieve. This includes change in the local CSO sector in the three countries but also change in funders across the donor environment.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track and significant progress has been made across the programme in the period under review, including the recruitment of further StP programme staff team at CR, more established ways of working with the formation of subgroups with delegated responsibility, and key strategic and planning documents co-created. These include the development and amendment of the foundational learning documents (learning questions, learning agenda, updated logframe), and the programme-wide and in-country communication and advocacy strategies. In the year under review, there have been tangible outputs including the first disbursement of the funds to local CSOs through the CF, numerous blogs, vlogs, and social media posts, and two online learning events. These tangible outputs reflect the immeasurable value found across partner organisations including strong inter-personal relationships, a clear and shared purpose, and a culture centred around learning, co-creation, mutual accountability and responsibility, and transparency. This culture has been built over the inception phase through regular online meetings and events and especially through two in-person learning and convening events held in Lusaka, Zambia in April 2023 and Accra, Ghana in October 2023. It is envisaged that these strong relationships and clearer and established ways of working will catalyse the implementation of the programme going forward.
As the programme gathers pace and strong foundations have been laid to ensure inclusive, equitable and shared ways of working embody StP principles, it was agreed that it would be a good point to review the CR StP staffing structure and review the resource and support the programme requires now and, in the future, to ensure it meet its aims and objectives while ensuring it delivers in a way that aligns with the locally led, equitable and revolutionary values of the programme.
In consultation with APs, it was agreed that the CR team would benefit from additional roles including:
1. A Head of StP Programme role - to be based in the UK and to provide ongoing strategic oversight of the programme and deliverables, as well as working closely with our existing Comms and Advocacy Manager to support with influencing and convening of the wider civil society when it comes to rethinking how traditional aid practices can be transformed.
2. A StP Programme Manager - to work in either Ghana, Malawi or Zambia and support with the delivery of the programme alongside the existing StP Lead.
3. A StP Finance Manager - to be based in the UK and work closely with the finance teams across all three APs leading on the financial management of the programme and to explore how StP principles can be applied to financial management.
Between January and March 2024, CR began recruitment for the Head of StP, Finance Manager and for the StP Lead role (as the current post holder is due to leave the role at the end of March 2024). The remaining StP Programme Manager role will be recruited in April/May 2024.
Whilst staffing changes can pose a risk to programme delivery, the changes in motion will support with the programme’s peak stage of delivery and ensure the programme is well resourced from CR, which in turn enables CR to best work in partnership with APs so the programme can continually be truly transformative when it comes to shifting power.
Organisational strengthening activities for the successful CF grant partners commenced as did those of APs in all three countries. Ghana proceeded with an open call for the CSSF and has started the selection process from the 117 applications.
In Malawi, pre-grant processes for the CSSF, such as co-creation of the templates and identification of a team of external experts to sit in the Proposal Review Team has begun but progress was paused at the request of British High Commission Malawi, amid concerns of TF’s capacity to deliver the fund. CR agreed to commission an end-to-end review of the CF to be undertaken by an external review team.
Zambia will begin its CSSF design process in the coming year. The participatory grant-making approach undertaken for the CF, although very innovative and in keeping with the principles of shifting power is very time consuming.
’We have underestimated the time it takes to organise and host the district-level participatory grant-making process, as it required selecting local review panel members, seeking an audience with the local administration, introducing the local review panel to ZGF and the selection process, inviting and hosting CSO applicants and facilitating the selection process itself.
ZGF annual report.

The programme for the year ahead will focus on:
- Delivery of OS for the CSSF grant funders based on the results of the OS assessments of the funded partners. Work on embedding the lessons from the RND13, RND15 and RND19 OS pilot study will continue.
- Roll out of the Community Resource Match Fund (CRMF) towards the end of 2024. Preparatory work for the launch of the CRMF has started with the creation of a subgroup to co-create the terms of references for scoping of community philanthropy in all three countries, which is a starter exercise to provide a baseline.
- Ongoing engagement in external processes for learning and influencing purposes will continue including further attendance at relevant seminars, webinars. CR and APs will also explore new opportunities including, for example, visits to other relevant programmes in other regions.
- Establishment of the PAPs which are in the final stages of being developed. CR will provide continual support to APs in Malawi and Zambia to ensure PAPs compliment and feed into locally led development and decision-making. The year ahead will focus on making the PAPs operational and ensure their manner of operation are consistent with programme’s principles.
- Implementation of APs value for money policies. The development of APs’ value for money policies began with Star Ghana Foundation (SGF) and CR jointly commissioning a consultant to assess current approaches to defining and measuring value for money in social development actions against the principles and ethos of approaches of the StP programme, #ShiftThePower movement, and community-led development. The aim is to develop a value for money strategy for SGF and other APs. This work will also provide input for a development dialogue to influence wider development thinking and practice. All APs are expected to have their value for money policies finalised before end March 2024. The year forward will focus on implementation.
- Review and update the AP contracts to better align them to the equitable, trusting and locally led values of the programme. As the programme began delivery, it became apparent that the AP contracts place significant administrative and bureaucratic burden on APs in conflict to the values of the programme that aims to reduce unnecessary, top-down bureaucracy and reporting. APs, CR and FCDO have already started the process of revisiting risk sharing and compliance management (Reimagining risk) for the programme with the aim to anchor these processes into the programme’s values. In relation to the AP contracts, CR and APs will explore how the contracts can be amended to be more equitable and in line with the programme’s values.

Justification on whether the programme should continue, based on its own merits and in the context of the wider portfolio:
In 2023 the programme moved into the delivery phase with programme implementation and the partnership across all participating organisations in a stronger place. The programme fits squarely within the ambition set out in the UK Government International Development White Paper (November 2023), which establishes mutual respect as the core principle of how the UK partners with others, with a focus on local ownership, mutuality, transparency, and values. It also fits within the FCDO International Development Strategy (May 2022), and Women and Girls’ Strategy (March 2023), particularly through the focus on:
1. Equitable partnerships and a move beyond the outdated ‘donor-recipient’ model
2. Providing women and girls with the freedom they need to succeed, and
3. Taking forward work on climate change, nature and global health.
A patient approach is essential – one which unlocks the power of people, ideas and institutions, and tackles the causes of crises, to deliver lasting growth, stability and poverty reduction. The table below shows how the themes for the programme speak to point (i) and (ii) while point (iii) is spoken to by the overall approach of the programme.

Table one: Anchor Partner themes
Star Ghana Foundation & West Africa Civil Society Institute - Ghana	Tilitonse Foundation	Zambian Governance Foundation
Access to public services	Early childhood development	Early childhood development
Gender justice	Gender Justice	Gender Justice
Food security and livelihoods	Mental Health	Climate Change/environmental degradation
Peace and security	Safe and Secure Shelter

StP has a clear strategic role in the global #ShiftThePower movement, contributing to wider understanding and learning of how a long-term funded initiative built on the principles of the movement works to shift power in an African context.
[note] The #ShiftThePower movement originated at the 2016 Global Summit on Community Philanthropy held in Johannesburg, South Africa. Soon after that Summit, in 2017, CIVICUS convened a meeting of hand-picked philanthropists, foundations, commentators and activists, specifically to discuss the systemic challenges around funding. Comic Relief were present with FCDO where the concept of the StP programme began. The #ShiftThePower movement is now a global movement for fundamental change in the international aid sector centred around the key #ShiftThePower: A Manifesto for Change.

## C. DETAILED OUTPUT SCORING

Output Title	StP partners (CR, FCDO, APs) align their practices to StP principles (#ShiftThePower Manifesto for Change)
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of APs successfully contracted	Three	Indicator not measured in this AR as already completed in 2022. All three APs contracted in 2022 remain in place.
1.2 CSOs feedback that the grant-making process and support was in line with StP principles including demonstrating key outcomes of their work (#ShiftThePower Manifesto for Change)	Three case studies from APs (one per country) that explores both positive and negative feedback from various CSOs and reflections about their use of StP principles.	The themes for the three case studies are: / Zambia: Exploring the effectiveness of Community-led development – #ShiftThePower principle #4. / Malawi: Challenging the notion of one-size-fits-all capacity strengthening initiatives - #ShiftThePower principle #5. / Ghana: Transforming language and practices: a case study on changing the language that enables new ways of working - #ShiftThePower principle #8.
1.3 The partnership between CR/FCDO and APs is assessed and demonstrates change in line with the Shift the Power principles over time	First partnership assessment completed which sets a baseline for how the partnership is functioning at the beginning of implementation	The first partnership assessment was undertaken between March - June 2023.

Briefly describe the output’s activities and provide supporting narrative for the score:
The overall score for output 1 is A. Indicators 1.2 and 1.3 have been met.
Indicator 1.1, Number of APs successfully contracted.
Indicator not measured in this AR as it was completed in 2022.
All three APs successfully completed the Design and Iteration phase and have delivered the CF and are in the process of designing and delivering the CSSF. Their contracts are still in place and agreed to September 2025, to mirror the first contractual break clause CR and FCDO have in place over the agreement to 2030.
One point to note is that in Malawi, there are ongoing concerns raised by BHC Malawi in relation to TF’s current capacity to deliver the CF and future work. An independent end-to-end review has been undertaken to ensure its delivery was in line with the StP principles and aims of the CF. Recommendations from the review will be incorporated into the design and roll out of the CSSF.
Indicator 1.2, CSOs feedback that the grant-making process and support was in line with StP principles including demonstrating key outcomes of their work (#ShiftThePower Manifesto for Change)
Met – The three case studies focus on the following StP principles and themes:
Case study 1 - Zambia
Title: Exploring the effectiveness of Community-led development
#ShiftThePower principle four: Creatively find ways to unlock the inherent power of communities in determining their own development course – however they define it – and let the language of “beneficiaries” and “recipients” be a thing of the past.
ZGF is in its fourth year of testing, adapting and building an evidence base that can prove that CLD is producing more sustainable outcomes. We have successfully introduced CLD in 17 communities across Zambia's Lusaka and Central provinces. Through this case study, ZGF explored the effectiveness of the community-led approach.
Case study 2 – Malawi
Title: Challenging the notion of one-size-fits-all capacity strengthening initiatives.
#ShiftThePower principle five: Move away from “building capacity” as defined by external actors and requirements, towards community organising and movement building, where “capacity” equates to relevance, rootedness and constituency.
This case study highlights how Tilitonse Foundation delivered the Catalyst Fund tailored to the needs of local CSOs.
Case study 3 – Ghana
Title: Transforming language and practices: a case study on changing the language that enables new ways of working.
#ShiftThePower principle #8: Change the language we use so that it enables new ways of working and thinking, rather than constrains them, and challenge the dominance of English.
This case study delves into the transformative journey undertaken by APs in Ghana during the implementation of the CSSP-STP, where a deliberate shift in language use is employed to instigate new ways of working and thinking. The focus extends beyond linguistic changes to map the observed transformations among both anchor and implementing partners over the past 18 months.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Over the last three years, participating partner organisations have developed strong relationships through online and in-person meetings and events, shared vision and goals and established, co-development ways of working. More importantly, there is a high degree of trust, open communication, challenge and dialogue amongst partner organisations that can only be developed over time. The benefits of this will be seen throughout the delivery phase of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The StP programme learning subgroup reviewed the logframe in 2023. The changes to output 1 can be found in the updated logframe’s ‘Change frame’ tab.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

Summary of recommendations from Yr 3 (2022-23)	Progress March 2024
The risk appetite of the programme should be reviewed to ensure due diligence, compliance and reporting procedures do not overwhelm one of the programmes’ central aims of improving accountability to local people and their priorities.	In addition to completing a programme risk appetite, it was agreed to introduce latest thought leadership on ‘Reimagining Risk’ alternately during the six-weekly risk register meetings between FCDO, APs and CR. First session on re-imagining risk was due to take place on 19th January 2024 but needed to be re-scheduled to later in 2024.

Major lessons and recommendations for the year ahead:

Lessons learned this year.
Building equitable and trust-based partnership working is complex:
Equitable partnerships require a range of characteristics including finding the right partners to work with, time to establish relationships and demonstrate commitment, a culture of trust, open communication, and ways of working that are inclusive, transparent and learning-centred. Much of the initial stages of the programme are centred on co-creation and reimagining systems and processes - a process that requires significantly more time than originally anticipated. The process has been of equal and sometimes greater value than the final product due to the learnings, reflections and richness of the discussions in an attempt to reimagine how individuals and organisations work in the partnership, dismantle traditional 'power centred' relationships and embrace new ways of working that centre the voice, experience and expertise of APs and local CSOs.

The ability to shift power among co-funders across governance, finance, safeguarding and contractual functions requires further time that may not keep in pace with the programme:
APs, who have experienced a history of top-down, funder driven decision-making, found some of the programme delivery replicated and reinforced existing power structures. For example, the split of APs’ contracts into three phases instead of a single contract to 2030 as originally envisaged, some of the compliance requirements in the contracts and the ongoing challenges raised concerning the delivery of the CF in Malawi reinforced current systems of power, control and decision-making by donors towards APs. Moving forward, all partners, including funders, need to be conscious of this and to ensure the StP programme centres and embeds the community-led, equitable and localised ways of working across the programme while ensuring partners are equally accountable to each other, local communities and the British public and taxpayers.

Intentional efforts need to be made to communicate and disseminate the key principles of the programme around locally led development and decision-making and engage local CSOs in the broader #ShiftThePower movement:
A key learning from the delivery of the CF is the importance to promote, communicate and operationalise the ethos and values of the programme with the onward funded CSOs that APs work with. APs found that local CSOs supported were less knowledgeable or aware of the underlying principles of the StP programme. While this is expected early in the implementation phase, intentional efforts need to be made to influence the broader CSO sector in Malawi, Ghana and Zambia.

The importance of shared understanding of the aims and objectives of the StP programme across all partners on the programme:
The StP programme aims to influence the wider donor sector including funders and organisations of the global north. The aim is to create equitable partnerships and relationships with shared accountability amongst partner organisations. FCDO and CR, as co-funders, recognise and acknowledge the inclusive and revolutionary ways of working on the programme evidenced through the engagement and involvement of APs in overall risk management, inputting into logframe changes and VfM design - elements that have not been done before in other FCDO and CR co-funded projects. For the programme to progress, it is important that there is continued shared understanding of and commitment to the aims and objectives of the programme across all partners and that this tangibly translates into all aspects of the delivery of the programme.

Recommendations for the year ahead:
Recommendation	Responsibility	Completion date
Equitable partnerships – Using the findings from the partnership assessment, continue to embed the StP principles in the partnership and improve ways of working.	CR/ FCDO/APs	Ongoing - / Start next partnership assessment in March 2024
Collaboration across the delivery chain – Further develop inclusive collaborations with all stakeholders in the delivery chain including local CSOs funded and supported through the programme to disseminate the StP principles to the broader CSO sector.	CR/APs	Ongoing

Output Title	Evidence and learning from new or different funding models that engage and strengthen Shift the Power principles and their impact on CSOs
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Learning agenda developed and iterated in collaboration with programme stakeholders	Initial learning agenda developed	The learning agenda was co-created by the StP learning subgroup.
2.2 Learning products disseminated and produced based on the evidence and learning from new funding models that leverage Shift the Power principles and strengthen impact of CSOs	One learning product focussing on learning in the Catalyst Fund	In September 2023 and January 2024, the StP Learning Subgroup hosted learning sessions to share learning from the planning and delivery of the programme so far. The first session on the CF where each AP presented their model of delivering the fund, their learning, and the challenges in delivering the fund. The second, in January 2024, a CSSF design learning session was held to share learning and progress on the design and implementation of the CSSF.
2.3 Equitable and high-quality learning collaborations formed on key programme components	Two examples (Learning coordinator model determined, and recruitment process/ToR started, additional bespoke research designed)	Learning coordinator ToR co-created and circulated for recruitment. The Learning Coordinator will be recruited by March 2024. / Two learning and convening events held – one in Zambia in April 2023 and one in Ghana in October 2023 / Logframe update completed collaboratively amongst APs and funders.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 2 is A. All the indicators have been met.
Indicator 2.1, Learning agenda developed and iterated in collaboration with programme stakeholders.
Met – Through a co-creative process amongst partner organisations, the foundational learning documents have been formulated or reviewed. The learning subgroup developed the learning questions, programme related definitions, and updated and amended the logframe. These combined, forms the broader StP learning agenda. This is a long-term programme with new and emerging findings so the learning agenda is a live document that will be adapted and regularly reviewed as the programme progresses.
Indicator 2.2, Learning products disseminated and produced based on the evidence and learning from new funding models that leverage Shift the Power principles and strengthen impact of CSOs.
Met – Two collective learning events have been held amongst partner organisations to share learning from the delivery of the programme. This included a session on the learning from the delivery of the CF. The event was captured in the event recording and three country presentations. The presentations demonstrated how the Catalyst Fund was delivered differently, was in line with the StP principles, and demonstrated what worked and did not work with their new or innovative approaches to deliver the fund. The second session was held in January 2024 about the design and implementation of the CSSF. Each country shared what they had learned from the CF and how they would utilise it in the design of the CSSF. Ghana provided additional learning as SGF and West African Civil Society Institute (WACSI) have already started to roll out the CSSF. Like the first session, the presentation and recordings have been shared more widely.
Indicator 2.3, Equitable and high-quality learning collaborations formed on key programme components.
Met – The StP learning subgroup has led to collaboration, co-creation, and shared responsibility on the learning across the programme. The subgroup has collaborated on key documents listed in indicator 2.1 that was the start of building. The subgroup also co-created the terms of reference for the learning coordinator and have equitably shared the responsibility to recruit the role including shortlisting, drafting of the interview questions and the interview process. Similarly, the subgroup, along with FCDO, collaborated on the review and update of the key programme component - the logframe. During the review, the subgroup recommended a move away from the logframe in the medium term to a process of reporting that centres shared learning, equitable partnerships and mutual accountability in line with the StP principles. The partner organisations will continue to review and reflect on all aspects of the programme to ensure it is equitable, transparent and mutually accountable. The accumulation of this way of working is an intangible and additional benefit unique to this programme compared to other FCDO and CR co-funded programmes. The culture and ways of working is more trusting, equitable, transparent and collaborative. The indicator has been met in part to both the tangible outputs and activities delivered by the learning subgroup and the intangible culture, relationships and ways of working that are firmly entrenched around learning with the StP learning subgroup.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The formation and establishment of a dedicated StP learning subgroup has contributed to the embedding of learning across all partners and a range of opportunities for peer-to-peer learning. There is equitable and shared ownership of the learning agenda and a mutual accountability to ensure any requests and reporting functions are for the benefit of all partners. The approach to learning is itself an opportunity to learn and share this way of working to influence other programmes that the partners participate in and with the wider donor community. The inclusive process of updating the logframe not only led to a more representative logframe but also sparked engaging discussions and ideas including moving away from a logframe model of accountability to one that better encompasses the StP principles that centres learning, shared and mutual responsibility and accountability, and changes in the overall approach to measurement and the notion of success.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The StP programme Learning Subgroup reviewed the logframe in 2023 The changes to output 2 can be found in the updated logframe’s ‘Change frame’ tab.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
Summary of recommendations from Yr 3 (2022-23)	Progress March 2024
Protect time for collective learning as part of the formal learning agenda, alongside other routine operational meetings	A culture of collective learning has been established across partners. This has been done through: / The establishment of a more focused learning subgroup. / bi-weekly subgroup meetings. / Co-created programme-wide learning events, and / the co-creation of the foundational learning documents including the learning agenda, learning questions and logframe review. / Now that the equitable learning culture has been established, the group has agreed to alter the purpose of the group to shift from solely decision-making group to one where tasks are divided amongst members and the group oversee the delivery of a broad range of learning activities.

Major lessons and recommendations for the year ahead
Lessons learned this year.
The emergence of joint ownership and shared responsibility:
One of the key benefits of collaboration, co-creation, and shared decision-making, is an increased sense of shared ownership and responsibility amongst partners. The long-term nature of the programme has allowed for the opportunity to develop relationships and to instil the principles through a process of learning, unlearning and relearning ways of working and thinking. A simple example of this is the co-creation of the learning questions. The original questions were drafted by external, global north consultants. The subgroup, initiated by CR, had just formed and there was hesitance to critique the learning questions as they were created and paid for from the global north funder and consultants. The review of the questions took up multiple subgroup sessions and it took time to breakdown the perceived hierarchies and power dynamics and build trusting relationships across CR and APs. The direct benefit was a significantly amended set of learning questions that better reflect the programme’s aims and objectives but also a way of working, thinking and challenging that is more equitable, balanced and constructive.

There is no one size fits all:
The learning from the delivery of the catalyst funds demonstrated that there is no one size fits all approach. APs shared how they designed and delivered the Catalyst Fund in a way that was in line with their context and community needs. For example, two of the three APs (in Malawi and Zambia) set up open calls for CF applications across a range of in-person, online and media outlets. In contrast, in Ghana, it was decided to do a closed call due to the size of the country and larger civil society sector. By doing a closed call, it was felt they could better reach those organisations who would most benefit from the CF instead of attracting the ‘usual suspects.’ Future funding always needs to reflect this nuance and differences in operating context.

Thinking outside of the box:
By working equitably and collaboratively with a focus on learning, partners have the space to think innovatively and broadly about solutions and delivery. There is space to try new things, make mistakes and to share experiences, both good and bad, with other partners without fear of consequence or rebuttal.

Recommendations for the year ahead
Recommendation	Responsibility	Completion date
Translate the immeasurable strength of the partnership into tangible activities - To translate the immeasurable strength of the partnership into practical delivery of the programme including ways of delivery and reporting that ensures partners are all accountable to their audiences.	CR/ FCDO/ APs	Ongoing
Focused learning – Now that the foundations for learning across the programme have been co-created and established, more focused or themed learning is required to capture progress. In the upcoming year, focus will be on learning from future grant funds including the CSSF and the CRMF.	CR/ APs	Ongoing

Output Title	More authentic representation of how civil society contributes to their communities
Output number:		3	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Equitable and high-quality collaborations with APs, funded partners and communities to enhance their work	Two examples of influencing	Attendance to, and participation in the following: / Development Engagement Lab Conference / High-level reception event / World Vision Panel / Segal Foundation Annual Conference / #ShiftThePower Conference
3.2 Authentic content created or co-created and produced with African content creators and influencers	Two pieces of StP programme wide content developed or in production. / Two pieces of in-country programme content from each AP country (6 in total)	Co-created content includes: / Comic Relief: / Spotlight videos launch – Twitter / International Women’s Day blog 2023 / Segal Family Foundation blog and vlog / World Literacy Day blog / Red Nose Day activation Poem and Film (in post-production) / Star Ghana Foundation: / Launched a forum on StP. / Delivered a Shift the Power survey and webinar. / Tilitonse Foundation: / 23 grant partners supported to strengthen their comms, storytelling and visibility. / Supported 9 local organisations to showcase accurate content that reflects the community and further amplified this in TF newsletter and various social media channels. / Zambian Governance Foundation: / Supported 405 local organisations on comms and local storytelling. / Co-created a webinar with WACSI and TF as part of the weaving conversations in the lead up to the Shift the Power summit. / ZGF has created and shared stories from the local community on various social media channels.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 3 is A+. All the indicators have been exceeded.
Indicator 3.1, Equitable and high-quality collaborations with APs, funded partners and communities to enhance their work.
Exceeded - The advocacy and communications subgroup was formed in May 2023 and meet bi-weekly to ensure there is equitable, high-quality collaboration with APs, funded partners and communities to build our external influencing. At a national level, CR’s STP Communications and Advocacy Manager delivered a presentation at the Development and Engagement Lab Conference on: ‘Shifting Power: Can we bring the public along’ and shared insights in to the StP programmes transformative aims to co-share decision making, move towards trust-based philanthropy and amplifying community voices with the general public. This led to discussions and opportunities to influence other donors, thought leaders and UK based CSOs interested in the StP Model.
In November 2023, CR organised and held a Shifting the Power high-level reception in Whitehall to showcase the flagship StP programme. The primary objectives of this event were to inform and influence MPs, CSOs, funders, philanthropic partners, board members and high-level ministers on the importance of shifting power, what it means to local organisations and how local civil society are transforming their communities. During the event attendees heard from Robert White, CEO of the Tilitonse Foundation one of the APs based in Malawi and Melinda Bohannon, Director General, Humanitarian and Development at the Foreign Commonwealth & Development Office (FCDO). The event was attended by 60 guests and one of the attendees shared:

"The Shift the Power event was terrific; through music, poetry and thought-provoking speeches, it highlighted new possibilities that exist in how we fund and also how we tell stories about that work to fundraisers."
Event attendee

In December 2023, CR and SGF presented the StP programme to World Vison UK as a direct outcome of the high-level event. During the panel discussion CR and Star Ghana Foundation shared the overall aims and objectives of the programme, the #ShiftThePower principles and how devolved grant-making, trust-based collaboration and equitable partnerships empowers and gives local organisations agency to work with grassroots communities. This has led to a meeting in March 2024, with the communications team at World Vision UK to share and explore the findings of the Audience Insights report and influence ways in which locally- led initiatives are communicated through stories and communications with their audiences.
In July 2023, APs and CR attended and participated at two high-level international conferences focussed on localisation and the Shift the Power movement. The Segal Foundation conference held in Kigali provided an opportunity for the team to learn more about participatory grant-making, best practices, challenges and lessons from funders and local organisations. The Summit provided a platform for the team to amplify learnings from the programme, specifically the catalyst fund and the different approaches and adaptations APs made when faced with specific challenges.
In December 2023, APs, CR staff and a Trustee attended the #ShiftThePower global summit in Bogota, Colombia. The summit connected and united changemakers and trailblazers from around the world who are committed to disrupting and challenging traditional power dynamics in international development, philanthropy and civil society systems. The conference gave everyone an opportunity to explore the possibilities in the face of crisis, reforming and transforming the current international funding system and provided lessons and insights in to equipping ourselves for the journey towards change. The summit was a significant moment to connect with ‘shining light’ actors and present via a presentation the findings from the audience insights research, comms and wider learning. The demand to hear more about the research was high and Comic Relief will continue with influencing by developing action learning sets for bilateral funders and the wider sector to test messaging around localisation and locally led initiatives.
The StP programme has developed a collective influencing strategy to bring all the partners of the programme together around some specific influencing aims and tasks. The strategy aims to influence actors to fund locally led development more directly. The strategy outlines two ways to do this: 1) By influencing more traditional actors to change who they fund and how they fund; 2) To work with ‘shining light’ actors to amplify and showcase their work in order to demonstrate the effectiveness of shifting power and funding locally-led development (and further convince traditional actors and the public of its value).
Indicator 3.2, Authentic content created or co-created and produced with African content creators and influencers.
Exceeded- During the reporting period Comic Relief wider comms exceeded this output with the creation of five pieces of content that have been co-created and produced with local communities, African content creators and influencers. This included three spotlight videos posted on CR and FCDO Twitter channels and produced with APs – this content gained 13,376 views and a 1.4 % engagement rate this is an average score as CR aims on average for a 2% engagement rate and 2,000 views on Twitter. However, CR faced some challenges and received racist negative responses and online trolling. This led CR to test other social media platforms such as Facebook and LinkedIn.
On International Women’s Day 2023, CR shared a blog which featured an interview with two female influencers and leaders who are shifting power and narratives in Africa (please note that this is being reported on this year as the content came outside of last year’s reporting period). Comic Relief typically aims for a 5% engagement rate on social media so anything at 5% and above is strong. The International Women’s Day LinkedIn post received a 2.38% engagement rate, 4,756 views and CR had 13 reposts. Following CR and AP attendance at the Segal Foundation summit in July 2023, CR and APs co-wrote a blog and posted a vlog highlighting and sharing some of the learnings from the summit – this received a 5.25% engagement rate, 2,816 views and 15 reposts which is strong. On International Literacy Day, CR collaborated and amplified an opinion piece with WACSI, again, this received high engagement rates on LinkedIn with a 13.41% engagement rate and 1,834 views which is again very strong.
For Red Nose Day 2024 (RND24) CR and APs launched a creative call out for poem submissions on the theme ‘Climate’. (NB Climate has been identified as a key priority area for APs, CR and FCDO). The call out specifically targeted a young audience with an age range of 15-30 years old. CR created supportive materials and information including a webpage, poster with a QR code and a clear and accessible brief. CR will shortlist poems and coordinate a virtual meeting between finalists and renowned artist, George the Poet to discuss and explore themes and lines from their poems as inspiration for a longer poem written by George.
The poem will form part of CR’s largest fundraising campaign – Red Nose Day, where CR partners with BBC Studios for a Night of TV on BBC 1 & BBC 2 – some of the largest broadcast channels in the UK. This content item for RND24 is a celebration and thank you for the FCDO project. The key final assets (in post-production) will be an original spoken word poem about climate change, written and performed by George the Poet, inspired by, and supported by poems from young people in Ghana, Malawi and Zambia. This activation also involves working with Beautiful Stories a film production company who are based in Ghana. They will film the finalists in Ghana, Malawi, Zambia, and George the Poet in the UK. They will direct, edit, and share a one-minute film on the Night of TV and across CR, FCDO and APs’ digital and social platforms.
Although this was primarily for RND24 the content gathered will provide the opportunity to tailor and share longer content for various platforms and occasions e.g., Africa Day, International Youth Day, and World Poetry Day.
Anchor Partner Comms outputs:
Star Ghana Foundation: Launched a forum on Shifting the Power to 140 participants. This was hybrid and included 80 people attending in-person and 60 people joining virtually. The purpose of the forum was to launch the Civil Society Strengthening Fund and share learning from the StP programme. As part of the weaving conversations for the #ShiftThePower summit, SGF also delivered and hosted a Shift the Power survey and webinar with 131 organisations participating in the survey (100 male respondents and 31 female respondents) The purpose of this survey was to understand local civil societies’ knowledge on shifting power and locally led initiatives.
Tilitonse Foundation: Worked with 23 grant partners to improve their organisational advocacy and visibility by reviewing their work and providing support and guidance for consistent visibility and communication. Nine local grassroots were supported to create content showcasing the capacity development they were undertaking during and outside monitoring to learn visits. This support has amplified the profile of grant partners on platforms such as the TF quarterly newsletter, LinkedIn, YouTube, Spotify, Twitter and Facebook.
Zambian Governance Foundation: worked with 405 local organisations on communications and local story telling. The foundation has engaged in various spaces, sharing their learnings from the STP programme and fostering links with other organisations and individuals who are shifting power (Lusaka and Ghana AP events, Segal Family Foundation event and #ShiftThePower global summit, amongst others). ZGF have also been able to ignite a conversation around shifting power among local CSOs and INGOs, albeit to some limited extent, working in the country. They have participated at various webinars (weaving conversations organised by Global Fund Community Foundations, WACSI or TF) and conferences (Malawi #ShiftThePower convening and WINGS Forum), amongst others. Many of the content created with local communities and organisations has been shared via their social media pages (Facebook, Twitter, and LinkedIn) and has amassed 43,900 engagement rates – this is a high engagement rate for ZGF.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Establishing the comms and advocacy CR and AP subgroup has contributed to ensuring content gathering considers local expertise and is a true reflection of the communities APs are seeking to amplify. This collaboration has led to upcoming content for Red Nose Day 2024 being inspiring and community driven. The role local poets have played to support and guide with poetry submissions has helped ensure authentic and creative inputs have been made that reflect and are true to local contexts. Collaboration, working with local partners and experts has been crucial in ensuring the stories highlighted and amplified are authentic and driven by the community. Therefore, value for money has been about recognising the value of strengthening relationships, working with local expertise and amplifying local voices.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The StP programme learning subgroup reviewed the logframe in 2023 The changes to output three can be found in the updated logframe’s ‘Change frame’ tab.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Summary of recommendations from Yr 3 (2022-23)	Progress March 2024
Communicating a progressive narrative that enables those most affected to tell their own stories. This will require: / Building relationships with African film makers and other creative story tellers	Poetry - Over the last year CR has communicated and tested various narratives that enable people to share their own stories. Most recently CR has worked with APs to deliver a public poetry call out on the theme ‘Climate’ and is in the early stages of working with a film production company based in Ghana who will be delivering a short film to be shown on the BBC as part of Red Nose Day 2024 and beyond.
Development of an advocacy plan for the influencing of donor funding practices towards #ShiftThePower principles.	Influencing strategy – Both a national and collective (CR and APs) advocacy plan for influencing donor funding practices has been developed. In 2023, CR and APs have begun implementing their influencing objectives by connecting with other ‘Shining the light’ actors, holding influencing events and sharing learnings and insights at global summits and conferences. Next year, CR hopes to design and run webinars, and deliver workshops to Directorates within CR and with others who are part of the #ShiftThePower movement.

Major lessons and recommendations for the year ahead:
Lessons learned this year.
Collaboration and shared ownership lead to more authentic storytelling and influencing:
The creation of an advocacy and comms subgroup has been central in ensuring CR and APs work equitably and collaborate in designing collective influencing and communications delivering authentic, inclusive, and representative content with those with lived experience and closer proximity to the issues.

External facing communications:
The UK public do not have strong or clear views on power within the aid system. However, through testing on platforms and looking at the data from CR audience insights, we know the public respond better to the core elements of shifting power. Showcasing and emphasising locally led decision making, self-sufficiency, sustainability and capacity through story telling will lead to positive and stronger engagement from the UK public.

Language is important:
When communicating shifting the power narratives, softer language needs to be used. For example, many of the UK public feel the word ‘Power’ is politically charged and language that focused ‘community leadership’ and ‘shared decision-making’ are alternative ways to communicate how the programme seeks to empower, enable and support communities. Jargon, technical terms and donor language also need to be reduced when communicating stories. It is inaccessible to many and often makes it difficult to inform, connect or inspire others who are less familiar with the aims of the programme.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
Long- term storytelling - continue to grow relationships with local content creators, grassroots communities and start designing and curating stories that captures change over the length of the programme. Drawing on the focus from the audience insights and seeing evidence that StP delivers and is value for money is crucial for public comms and strengthening the collective influencing for the programme.	CR/ FCDO/ APs	Ongoing
Thematic approach - the focus will be to take a thematic approach, create a long-term comms plan and work closer with local communities to ensure they are accurately represented.	CR/ FCDO	Ongoing

Output Title	Local or community philanthropy is supported across civil society
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 A Community Resourcing Match Fund is established	Programme Advisory Panels (PAP) or equivalent are recruited and inducted in Ghana, Zambia and Malawi	Ghana equivalent of a PAP is operational and was involved in the selection of CF grantees. / Zambia and Malawi processes for establishing PAPs currently underway. PAPs expected to be in place and inducted in both countries by end March 2024.
4.2 CSOs receive support on promoting community philanthropy including income generation	N/A	No milestones for 2023/24
4.3 Proportion of CSOs who have initiated community philanthropy initiatives to address the salient needs of the community	N/A	No milestones for 2023/24

Briefly describe the output’s activities and provide supporting narrative for the score:
The overall score for output 4 is B due to one of the activities from the workplan not being met and the delay in operationalising the PAPs in Malawi and Zambia.
Indicator 4.1, A Community Resourcing Match Fund is established:
Partially met – One of the milestones for this output was the establishment of PAPs. Ghana established its equivalent of the PAP which has played a positive role in the delivery of the Catalyst Fund and the Civil Society Strengthening fund. There was a delay in Malawi and Zambia in the establishment of the PAPs. The reason for the delay was that APs sought clarity on the role and responsibilities of the PAPs to ensure that this added value rather than undermine existing governance structures and were overall in keeping with the #ShiftThePower principles. Discussions between the three partners (FCDO, CR and APs) ensued and were completed in October 2023 enabling establishment of the PAPs to commence in Malawi and Zambia. PAPs are expected to be inducted end March as per milestone.

"The conditionalities imposed as to the mandate of the PAP might change the StP programme’s DNA going forward. We will continue challenging Comic Relief and FCDO."
AP annual report

Indicator 4.2, CSOs receive support on promoting community philanthropy including income generation:
N/A - There is no milestone for this year. The CRMF will not roll out until 2024/25.
Indicator 4.3, Proportion of CSOs who have initiated community philanthropy initiatives to address the salient needs of the community:
N/A - There is no milestone for this year. The CRMF will not roll out until 2024/25.
The workplan in the year under review includes the following activities:
- Scoping of Community Philanthropy in countries (Development of Terms of reference). The process to co-create the TORs has commenced and will be completed by end March 2024. The scoping exercise will provide baseline for the CRMF.
- Consultancy of specialist provider in match funding and community philanthropy to develop methodology. This activity will take in the next reporting period.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
The Investment in this programme is guided by CRs value for money framework which goes beyond money to focus on relationships, models, communications and leaning on local expertise. Value for money is therefore fundamentally about recognizing the value of strengthening relationships and social cohesion beyond funding transactions. Support for local or community philanthropy is across civil society and the action of establishing the PAPs is firmly within the span of relationship building and recognition of local expertise. Supporting local or community philanthropy gives strength and independence as it promotes their resilience and sustainability as they reduce their dependency on foreign donor funding. The PAPs are comprised of a cross section of representatives in each country from civil society, private sector, public sector, experts by experience, and academia provide independent, specialist and strategic guidance to all aspects of programme design.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The StP programme learning subgroup reviewed the logframe in 2023 The changes to output four can be found in the updated logframe’s ‘Change frame’ tab.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:

Summary of recommendations from Yr 3 (April 2022- March 23)	Progress March 2024
CR working with APs should invest in alternative forms of financing including those promoting local philanthropy, matching funds etc. This will require learning from other funders that are already have this support in place and from APs such as WACSI who are the forefront of promoting this endeavour.	Co-creation of the Terms of Reference for the Scoping of Community Philanthropy in countries exercise done

Major lessons and recommendations for the year ahead:

Lessons learned this year.
Tension between creating the PAPs and the #ShiftThePower principles:
The design of the programme was that the grant application process for applicants will be jointly managed by APs and overseen by Comic Relief. However, to ensure that decisions effecting local people are being taken by local people national PAPs would be established in each of the three countries with the aim that they will eventually select winning grants. The panel would include a place for the FCDO country office representative whose role on the panel would be advisory, not decision-making.
The tension arose because the APs already have established boards and grant making committees made up of local people already playing the role envisaged for the PAPs and therefore there was confusion concerning where power and ultimate decision making would sit and how this aligned with the values of the programme. Compromise was reached to have PAPs established as fully advisory bodies. Nonetheless, unease remains with this arrangement amongst some of the APs. A prime example of this tension is that ZGF has sadly decided to remove innovative participatory grant-making element from the upcoming grant selection phase and return to the conventional method of grant selection. They took this decision because the participatory grant making approach that ZGF has adopted is a very good example of innovation and in keeping with the ethos of shifting the power, it is also very time consuming. The inclusion of the PAP has added an additional step in the timeline, impacting programme delivery timeframes.
The board of directors of ZGF has requested for dialogue with more senior staff of CR on the role of the PAP.

1. Different understandings between partners around risk and accountability:
   APs rightly had expectations of approaches to risk and compliance consistent with #ShiftThePower principles. For example, adopting an approach that explores risk sharing and compliance management in ways that are more, trust-based, empowering, less risk averse and equitable. APs view of risk in line with the RINGO new approach to risk sharing and compliance management which amongst others advocates for co-creation of partnerships of genuine solidarity between international actors and local civil society, where risk is shared and continuously navigated and negotiated by all stakeholders, including funders. Improvements so that the system is less transactional and reflects proportionately local needs, and risks, alongside donor needs for accountability. In this programme, the risk register was developed by the funders before APs came on board and although subsequently included in the meetings to review the risk register, they have been brought into an already defined framework (FCDO) and content to which they have to react rather than to co-create in line with #ShiftThePower principles. Accountability is hierarchal with lines of power clearly determining lines of reporting. The higher up this hierarchal chain the less reporting or accountability there is to other partners in the programme.
2. Co-creation and the need to ensure the programme is delivered along the #ShiftThePower principles can slow down implementation:
   Our commitment to the principles of the #ShiftThePower remains strong and as calendar year 2023 was the first year of full programme implementation, it was a great lesson learned in terms of needing to be realistic when planning deliverables and activities. The StP teams within APs and CR were overwhelmed due to the commitment to ensure co-creation and other StP principles are embedded in the way the programme was delivered that honoured the values of the programme.

"The CF CSO partners have been introduced to the STP/community-led development approach, and the organisations have expressed an understanding of what that entails. However, the CF CSO partners are comfortable operating within the parameters of traditional aid and therefore tend to concede power; hence, the CF CSO partners need constant reminders of their powers. Along that same line, the CF CSO partners need continuous support on what it means to adopt the STP ethos in their work and their stakeholder relationships.”
AP annual report

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
Review the risk appetite – The StP programme has started this process taking into consideration the work being done by RINGO on re-imagining risk.	CR/ FCDO/ APs	Embedding of re-imagining risk to be an on-going part of this programme

Output Title	Civil society organisations identify their priorities for organisational strengthening.
Output number:		5	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 An organisational strengthening framework is adapted in each country to support funded partners to identify and prioritise development needs.	i) CR OS learning study is completed and disseminated. / ii) OS Framework for Malawi, Ghana & Zambia operational.	i) The CR OS study report was completed and disseminated in February 2024. / ii) The OS Framework for Malawi, Ghana and Zambia was applied to the Catalyst Fund grantees.
5.2 Funds (CF, CRMF, CSSF) provided to support civil society organisations in their identified priority areas.	Catalyst Fund operational in Ghana, Malawi and Zambia.	Catalyst fund operationalized in Ghana, Malawi and Zambia. / End to End review of Catalyst Fund process undertaken in Malawi.
5.3 Number of funded partners who have completed assessment of OS priorities.	OS priorities assessed for 60 CSOs funded by Catalyst Fund.	68 CSOs assessed.
5.4 Number of CSOs who have implemented their OS plans (future indicator).	N/A	No milestone in this reporting period.

Briefly describe the output’s activities and provide supporting narrative for the score:
The overall score for output 5 is an A. All the output indicators have been met and indicator 5.3 slightly exceeded because 8 additional CSOs were selected for the Catalyst Grant than originally planned.

Indicator 5.1, An organisational strengthening framework is adapted in each country to support funded partners to identify and prioritise development needs.
Met - CR OS learning study is completed and disseminated: The intention of this milestone was to promote cross learning within CR. Comic Relief (CR) commissioned a review of its Organization Strengthening (OS) work at the end of 2022, focusing on three FCDO funded programmes: ‘All in All Learning’, ‘Maanda’ and ‘Mental Health In Kenya’. The funded partners (FPs) in these programmes (in Uganda, Kenya, Malawi, Sierra Leone and Tanzania) were piloting CR’s ‘OS Framework and Principles’, developed in 2020 from several years’ learning of OS work. The review sought to:
- Further develop CR’s OS Framework and Principles.
- Surface learning in real time to inform our resourcing of civil society OS.
- Understanding how funded partners experience our OS support.
- Showcase what our OS support has enabled for funded partners.
Galvanizing Africa Consult (GAC) worked with the FPs over a period of one year, during which time online conversations were had as well as face to face meetings to understand every aspect and experience of the FPs OS journey. In considering how best to document the learning study to build on the successes and learning of the OS pilot, CR and GAC agreed that an operational guidance outlining how CR should manage OS grants at each stage of the grant making process, would enable good practice to be more consistently embedded.
Key findings of the study included:
- The importance of context in shaping how OS funding was perceived and operated.
- FPs who understood OS as holistic and of intrinsic value to their development, reported more sustainable outcomes than FPs who perceived OS support to be more of a donor-compliance driven process.
- FPs reported that improved internal systems and the increased visibility they experienced through the OS process, has made them more attractive for bigger partnerships with other likeminded actors, including international NGOs.
The StP programme will embed the lessons learnt from this study into its OS work.

Met - OS Framework for Malawi, Ghana & Zambia operational:
The work plan commitment to the OS framework being operational in all three countries was met. APs first developed their individual OS frameworks in 2022. These were applied in their OS work with the Catalyst Fund grantees.

Indicator 5.2, Funds (CF, CRMF, CSSF) provided to support civil society organisations in their identified priority areas:
Exceeded - The catalyst fund was operationalised in all three countries. The target number of organisations was provisionally set at 20 per country or total amount capped at £100,000 in cases were organisations received less than £5,000. All countries capped the total amount to £100,000 and some organisations received less than £5,000 therefore enabling 68 to be selected. The end-to-end review of the CF in Malawi was not a milestone neither was it in the workplan, but it was significant work that was delivered.
In Ghana, a closed call for organisations to apply for the CF led to 29 applications. Out of this, a total number of 20 were successfully awarded from different regions of the country. Ghana launched and disseminated nationwide call for the CSSF through print and social media. A total of 117 organisations responded to the call. All 117 applications were assessed by staff and external persons in line with a set assessment criterion and are to be reviewed by the Project Steering Committee who will advise and make recommendations to the grants committee.
In Malawi, a total of 237 applications for the CF were received through an open call, and 23 were approved from across all regions of the country. In the activities which the grant partners organized under the CF grants, a total of 2,035 individuals were reached (1,068 males and 967 females). Among them, there were 161 Persons with Disabilities (PWD).
In Zambia a total of 178 civil society organisations (CSOs) responded to the CF call, 25 CSOs (5 from each district) were selected as recipients of the CF grant. ZGF innovated by accepting calls in forms other than written application, audio and video applications were also accepted. ZGF chose a geographical specific focus of five of the districts in the country most affected by climate change/environmental degradation. A participatory grant-making approach was adopted by ZGF with a local review panel in each district selecting the successful applicants.
Pre-grant processes for the CSSF commenced in Malawi and included activities such as co-creation of the templates and identification of a team of external experts to sit in the Proposal Review Team.

Indicator 5.3, Number of funded partners who have completed assessment of OS priorities.
Exceeded – In total, 68 CSOs across Ghana, Malawi and Zambia have completed OS assessments - 20 organisations in Ghana, 23 in Malawi and 25 in Zambia completed the assessment. Each CSO selected needed to complete an OS assessment. The milestone was exceeded because it was possible for additional CSOs to be selected within the overall allocated budget.

Indicator 5.4, Number of CSOs who have implemented their OS plans (future indicator)
No milestones for this reporting period.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year:
Both the CF and CSSF are central to the programme’s ambition to move away from short term project funding and towards strategic investments which have wider social and economic value long after they end. This is central to the programmes approach to value for money.
At the same time, the programme is investing in organisational strengthening for APs enhancing the funding’s contribution to sustainable social benefits.

Describe any changes to this output during the past year, and any planned changes as a result of this review:
The StP programme learning subgroup reviewed the logframe in 2023 The changes to output five can be found in the updated logframe’s ‘Change frame’ tab.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
Summary of recommendations from Yr 3 (April 2022- March 23)	Progress March 2024
Build in key learning from the OS pilot study and partner experiences to ensure OS within the programme is offered, and perceived to be offered, as funded partner led and of intrinsic value to funded partners.	The output from OS pilot study conducted for the RND 13, 15 & 19 had been completed. / The output will be an operational guidance manual on how CR can better support OS such that it is more valuable to FPs and less about donor compliance and readiness. Building in the learning from this will commence when the manual is delivered.
"Cocreate with the Anchor Partners best practice governance structures for devolved grant making that balance governance as envisaged within the Business Case and existing practices within the Anchor Partners by June 2023	This action was tied into the discussion on the PAPs and as such there was no separate discussions or activity pertaining to this recommendation

Major lessons and recommendations for the year ahead:
Lessons learned this year.
Lessons learnt from the OS pilot study will be embedded in the StP programme and include:
- Donors should reflect on and be clear on their position on the ‘donor compliance’ to ‘funded partner owned’ OS journey, before considering the operational details of how they fund OS work. This should be clearly and authentically communicated to FPs to ensure mutual understanding and alignment on the meaning and purpose of OS.
- Donors, and individual staff members, should be aware of the real or perceived power they have in different contexts, during the OS funding process. Where this is not feasible, working through local grantmakers should be considered.
- Regular interrogation and reflection on approaches to funding OS is critical to ensure OS funding is supporting FPs as intended.
Recommendations for the year ahead:
Summary of recommendations for the year ahead	Owner	Completion Date
Lessons learnt from the OS study will continue to be embedded in the StP OS work.	CR/ FCDO/ APs	Ongoing

D: RISK

Overview of risk management
The overall residual risk was moderate and remains moderate. In the period under review, the major risks to the programme were:
- Further tightening of civic space.
- Cost of living crisis exacerbated by global events, debt and fluctuations in exchange rates.
During the period under review CR continued to monitor the risks facing the programme using a programme level risk register. The risk register was updated by CR, submitted to FCDO and jointly reviewed quarterly in the first half of the year. However, the frequency was increased to six-weekly and the local FCDO offices and APs also included in the meetings. In addition, it was agreed that the meetings alternate between reviewing the risk register and discussions on re-imagining risk.
Work was undertaken by all the partners to reduce the number of risks on the register to determine the key ones for prioritisation and focus.
APs reported on risk and mitigation in the reports submitted to CR in October and January 2024. They also fed into the risk register updates that CR submits to FCDO.
In addition, CR continuously monitors the context in Ghana, Zambia and Malawi and includes insights from in-country APs. CR’s Funding Team, which oversees all CR investments, updates its risk register each quarter. This is reported to CR’s Executive Leadership Team and Audit and Risk Committee on a quarterly basis. CR also has an Assurance function which oversees the management of risks across all CR’s work.
It was recommended last year that the risk appetite of the programme be reviewed to ensure due diligence, compliance and reporting procedures do not overwhelm, the programmes’ central aims of improving accountability to local people and their priorities. Discussions were held within CR, concrete work on this will begin on 22nd March 2024 and will therefore continue into next year.
The work to embed the RINGO re-imagining risk and compliance prototype into the programme recommended to be done by December 2023 did not begin until January 2024 due to the high burden of work in the programme.
Tables below record key risks against each of FCDO’s risk categories over the reporting period and also provides comment on current residual risk rating and analysis of trends. The three tables breakdown into table 1 which carries the general risk across all countries. Table 2 and 3 are specific to Ghana and Malawi. Zambia does not have risks specific to it.

Table 1: StP programme risk register
Category	Residual risk rating	Update
Strategy and External context	Moderate - The residual risk is moderate trending towards major because of tightening civic space in all countries as elections loom.	The risks related to this category are: (i) Attacks on civil society and closing civic space (moderate), / Mitigation Measures / APs involvement in risk identification and management, informed by local knowledge and mitigation strategies. / Regular engagement with in-country partners and an adaptive approach to programme design and management. / Phased implementation and data-informed design allows for changes in scale of roll-out, tailored approach per context and change in country (if necessary). / (ii) Project activities in projects funded under this programme are delayed or scaled-back (Minor) / Mitigation Measures / APs report Comic Relief in March, October and January and note any changes in context that are impacting on their organisation, or its ability to deliver the funded project. / If funded projects face significant delays or need to make major changes to their project design owing to changes in context. Comic Relief requests a revised project plan (including revised targets) and a revised budget for approval. / If changes to targets need to be made, the programme logframe is updated and changes agreed with FCDO. / Mitigated through no cost extensions and adaptive programming and grant management
Financial and Fiduciary	Moderate - This remains moderate however the impact of global events on currency depreciation, cost of living, etc is constituting a substantial risk to the economic value of grants provided to partner CSOs in the local currency. In November 2023 for example, Malawi’s currency was depreciated by its central bank by over 40%.	The risks related to this category are: / (i) Global political, wars & natural disasters lead to increased costs (moderate). / Mitigation Measures: / APs budgets are held in £GBP rather than local currency. / The financial health of APs will be subject to ongoing monitoring as currency depreciation may overtake these gains. / (ii) Funds not used by CR and/or grant holders for the intended purposes, and/or are not properly accounted for (Moderate). / Mitigation Measures: / Comic Relief employs a thorough assessment of all projects prior to funding being awarded, including an in-person assessment of grant holders' and their partners' governance, financial health and financial management. / APs holders report to Comic Relief on regular basis and grant managers can assess compliance with Comic Relief's Conditions. / Should performance or compliance concerns arise, additional learning and support calls will be scheduled. / Comic Relief conducts learning and support visits to all its funded partners. The grant manager will complete an assessment of the financial systems and processes being used, use and control of assets purchased with project funds, and will also complete spot-checks of expenditure. / Comic Relief Assurance Team have dedicated and experienced counter fraud staff who will train staff/grantees, devise and oversee the implementation of policy, (e.g., fraud response plan), and investigate any alleged fraud/corruption/mismanagement incident and inform FCDO of all major incidents as per our agreed reporting protocol. / An Internal Audit function is in place which will examine the control framework across Comic Relief, including the Impact & Investment, Finance and Assurance Teams. This will review safeguarding, mismanagement & risk controls. / (iii) Substantial flows of funding into APs inflate annual budgets & create dependency on STP Portfolio (Moderate) / Mitigation measures / Budgets are scrutinised when assessing proposals and during assessments before grants are awarded to ensure sustainability. / Financial reports, budget changes, and variances from budget are carefully reviewed every six months and wider income sources and sustainability are monitored closely. / As part of this programme OS support will be delivered to APs to strengthen their organisational systems and processes, consequently leading to them being more viable and attractive for other funders.
Policy and Programme Delivery	Moderate (i-iii and v) / Major (iv) - The residual risk rate is maintained at moderate. Effective mitigation measures in place to manage these risks.	The risks related to this category are: / (i) Power relations between APs & funded partners affect how local organizations are engaged (Moderate) / Mitigation measures / APs are committed practitioners of the StP ethos and leaders in the #ShiftthePower movement and have time evidenced this commitment. / On going consultations at all levels to achieve consensus, ownership and co-creation of pathways of change (between CR partners, and between APs and funded partners). / Horizontal accountability mechanisms being developed. / (ii) Slow roll out of programme as APs strengthen own capacities (moderate) / Mitigation measures / Support APs organisational strengthening of their processes, staffing and systems. / Regular monitoring of grants and other systems through in person and online visits and reports. / Roll out partner orientation early on, and accompany partners based on their needs. / (iii) Insufficient internal capacity to effectively oversee implementation (Moderate) / Mitigation measures / Comic Relief is an experienced grant maker and has worked in partnership on co-funded programmes with FCDO since 2009. / This Programme is managed by an experienced team under the Funding Directorate which is dedicated to managing all FCDO co-funded programmes and is supported by Comic Relief's Assurance and Finance teams. / Comic Relief is committed to a strong, collaborative working relationship with FCDO which fosters mutual accountability and learning. / Consistent oversight from the Funding Directorate Leadership team (supported by Comic Relief's Trustees and Executive Leadership) is ensuring capacity remains at the level needed to ensure FCDO co-funded programmes are delivered effectively. / All CR staff receive regular supervision, including check ins on capacity and objectives. / (iv) Grant holders delivering complex, or innovative projects expected results are not met (Major). / Mitigation measures / Comic Relief employs a thorough assessment of all projects prior to funding being awarded, including an assessment of project design and grant holders' and their partners ability to deliver the proposed work. / Grant holders complete a capacity assessment of all implementing partners as part of the application process which are also assessed. / A portion of every grant is dedicated to the organisational development of the grant holder and its partners, informed by their own analysis and recommendations from the assessment. / Grant holders report to Comic Relief every six months and grant managers assess progress toward agreed outcomes and monitor partners' ongoing capability to deliver. Areas for development are identified and updates sought from grant holders. / Guidance and support are provided by grant managers through regular grant management and monitoring visits. / (v) Funds used by CR and/or grant holders do not achieve value for money (moderate) / Mitigation Measures / Budgets are scrutinised when assessing proposals and during assessments before grants are awarded to ensure they provide reasonable VfM. / Financial reports, re-budgets, and variances from budget are carefully reviewed annually to ensure funded partners continue to deliver value for money throughout the life of the programme. / APs are developing value for money policies.
Public Service delivery and Operational / Miti	Severe - The residual risk for this category remains at severe. This is because cuts to the UK aid budget which impacts on the StP would be profound as it could result in a loss of 50% of the overall budget.	The risks related to this category are: / (i) Cuts to the UK aid budget (Severe) / Mitigation Measures / FCDO and Comic Relief work collaboratively to ensure necessary assurance on the value of the programme is communicated and accepted. / Programme and budget adjusted for implementation into three phases up to 2030. / Comic Relief engages with other trusts, foundations and institutions to explore the possibility of co-investment into the programme. / (ii) FCDO (and/or CR) compliance requirements constrain ability to honour the programme’s values of shifting accountability away from Northern donors towards local communities (Major) / Mitigating Measures / Comic Relief & FCDO are committed to delivering the Business Case and staying true to the programme's underlying values. / Both partners' risk appetite continues to reflect the more experimental, iterative nature of the programme. / Regular meetings provide space for honest, open dialogue between FCDO and Comic Relief, rooted in the values of the programme. / Senior stakeholders on both sides are bought-in to the programme and its aims and regular communication and engagement maintains support. / CR and FCDO commit to championing a change in internal financial and assurance processes that are centred around shifting power and more equitable partnership values.
Safeguarding	Major - The residual risk for this remains at major. Safeguarding must feature highly in all our work since power and how that is used and, in some cases, abused is inherent is pervasive in the aid sector. Although there have been no reports of this received in this programme, delivery partners cannot be complacent because of the power imbalances in the relationships in this programme between several layers of funders and funded partners and ultimately the people at community level impacted by this.	The risks related to this category are: / (i) Failure to protect people from harm as a result of engaging in the programme. Local people engaged in programme are not adequately protected from harm by partners engaged by CR. / Mitigation Measures / APs' approach to safeguarding (policy and practice) assessed as standard as part of Comic Relief's tendering process. / Contracted partners are supported by CR to strengthen safeguarding policy and practice where needed. / Reporting protocol between local people, local partners, Comic Relief and FCDO established as part of programme design as part of wider framework for community engagement.
Reputational	Moderate - The residual rate is moderate	The risks related to this category are: / (i) The credibility of CR, FCDO and/or its grant partners is damaged as a result of the behaviour/actions of CR or its partners (moderate) / Mitigation measures: / Prior to grants being awarded, the reputational risk is assessed as part of the assessment phase for all potential projects. Mitigating actions are recommended by the assessor. / When a grant has been awarded, Comic Relief's Conditions of Funding sets out the expectation for grant holders to notify Comic Relief of any major changes to the project, the delivery organisations and includes any allegations made against them or negative publicity received. / Through ongoing grant management (including learning and support visits), grant managers identify any potential for reputational risk to the grant holder, their partners, Comic Relief or FCDO and support them to mitigate the risk. / Internally, Comic Relief has sound organisational policies in place, as well as appropriate levels of training and guidance available to staff, to ensure no reputational risks arise from actions of staff. This includes risk assessments for all overseas trips whereby all guest travellers are briefed before undertaking any activity/trip with Comic Relief in order to clarify expectations of behaviour (e.g., on social media, photography etc) & protect both staff, visitors and individuals. / If a reputational risk materialises, Comic Relief has a dedicated resource to manage any issues. This included a dedicated Assurance Team with experienced risk management staff as well as a Head of Strategic Communications & Public Affairs who leads on the reputational risk management, planning and response. / (ii) Poor public perception of the programme and international aid (minor). / Mitigation measures / FCDO and Comic Relief work collaboratively to ensure necessary assurance on the value of the programme is communicated publicly. / Proactive communications work pursued by Comic Relief. / Outcomes and indicators will be carefully developed to demonstrate impact and value of work. / Comms work will demonstrate impact and value of the programme to the general public. / The thorough selection of APs has led to a partnership of strong mature organisation, who are keen to coordinate their work well and with integrity. / Story communications work demonstrating impact and value of the UK public and beyond.
People		None

Table 2: risks specific to Ghana.
Category	Residual risk rating	Update
Policy and Programme Delivery	Moderate	Relationship within Ghana consortium (SGF and WACSI) is disrupted. / The residual risk remains moderate trending towards minor. SGF and WACSI’s working relationship precedes the StP and built over several years. They are both strong and mature organisations who work in a mutually respectful way. For example, early in 2023 they conducted a joint implementation staff onboarding for the StP which was convened to: / Build a collective understanding of Shift the Power and its operationalization within the programme. / Strengthen WACSI/STAR-Ghana working relationship; and / Create collective understanding towards WACSI/SGF’s contractual obligations. / All of which led to improved communications and strengthened coordination between them.

Table 3: Risks specific for Malawi
Category	Residual risk rating	Update
Policy and Programme Delivery	Major	End-to-End Review (EER) worsens relationship between Tilitonse Foundation and BHC Malawi (Major) / The residual risk remains major. The EER of the CF delivery process - conducted by local, external consultants - was fraught with complex difficulties. This mainly came from the consultants’ lack of understanding of the contextual and conceptual foundations of the broader #ShiftThePower movement and the StP programme. This lack of understanding meant the consultants omitted, or did not consider, details which would have strengthened the understanding of TF's process. This led to conclusions and recommendations in the report shared with BHC Malawi - a considerable number of which CR and Tilitonse Foundation disagreed with - that did not accurately reflect how the CF was implemented by TF, did not consider the ethos and values that underlie the programme, and contradicted CR’s long term experience of working with TF on the programme.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Quality and timeliness of narrative reporting and audited financial statements:
The StP narrative reporting to FCDO was until recently six monthly and annually. The frequency has been increased to quarterly because of slowness of delivery and to ensure that deliverables/milestones are on track. The first quarterly report will be for the period October 2023 to December 2023 to be delivered in February 2024. During the period under review one six monthly report for the period 1st April to 30th September 2023 was delivered on time.
CR conducts full and comprehensive audits annually and these are submitted timely. The audit includes a review of all individual fund balances and checks all grant agreements to ensure that spending complies with conditions of grant from funders including FCDO. In the accounts, CR has a separate line for FCDO funds in note 20 which is the restricted funds note. This line includes all income from FCDO in the year and all expenditure against those funds. This is signed off by the auditors.
APs provide six month and annual narrative and financial reports. They also provide annual audited accounts. In the period under review the above reports were provided in a timely manner. The first ever six-month report was submitted in October 2023 and the annual report on 15th January 2024. The reports are overall of high quality, review and feedback have been given on the six-monthly report. The review of the annual reports will provide CR with more detailed information and analysis on the performance of APs. Overall financial reporting provided was satisfactory. However, their forecasting was off target. This is attributed to this year being their first year of operation, with a heavy implementation schedule and many variables in terms of how plans are realised in practice still unknown.

Proactive dialogue on risks and updating of delivery chain maps:
As outlined in sections above a comprehensive risk register is in place to monitor risk. Meetings to discuss risks and update the risk registers are held with participants drawn from FCDO (UK and country offices), APs and CR. A reporting protocol is in place at CR for reporting serious incidents and concerns to FCDO and an agreed approach to investigation and reporting thereafter. During this period, allegations were received of abuse and fraud, which were thoroughly investigated and found to be unsubstantiated. However, there are always lessons to be learned and this provided an opportunity for CR, APs and FCDO to review current practice and strengthen where appropriate. An up-to-date delivery chain map has been submitted with this annual review.

Quality of financial management:
Key cost drivers in order of highest expenditures are:
- Partner grants:	71%
- Management costs:	12%
- Knowledge, Evaluation and Learning:	9%
- Communications and Advocacy:	9%
At the start of the review period, the forecast of spend of the FCDO contribution (which includes partner grants, MEL, comms and advocacy, and management costs) was £3,607,480.
The actual amount disbursed during this period was £1,781,863 which is a variance of 51%. The difference in actuals against the forecast resulted from:
      1. The slower than anticipated implementation pace by the AP.
      2. The omission to make the necessary adjustment to the Annual forecast in a timely manner.
	Forecast	Actual
April to June 2023 Q1	£1,195,943	£1,221,779
July to September 2023 Q2	£ 194,402	£ 96,655
October to December 2023 Q3	£ 2,070,533	£128,031
January to March 2024 Q4	£ 146,602	£335,398
Total	£3,607,480	£1,781,863

Asset monitoring and control:
All assets under the StP programme are funded from Comic Relief’s contribution and therefore followed Comic Relief’s asset management policy. In line with Comic Relief policy, where capital expenditure by funded partners is approved, it must be clearly demonstrated that any assets acquired will be used during and at the end of the grant on activities in the spirit of the original grant agreement.
During monitoring visits, spot checks were undertaken to confirm existence of assets reported to have been bought and entered into asset registers.

Learning and Support activities:
Monitoring progress by APs is done through:
1. Desk review of the reports submitted.
2. Verbal/ virtual updates and
3. Physical visits.
Regarding the latter, three learning and support visits were undertaken: two to TF (Malawi) and one to ZGF (Zambia). Details of these visits have been provided to FCDO. These learning and support visits help in relationship building, deepening understanding of the programmes’ country context, opportunities, challenges and progress being made in implementation and overall assist CR in improving its response to the partners.
As part of their annual reporting to CR, APs also reflect on changes as a result of their work. Given the nascence of the programme monitoring and capturing of change at outcome and impact level has not begun. Focus right now is on the output level.

Value for money:
The VfM case for this programme was agreed to not be based on cost per beneficiary calculations, as that would be at odds with a theory of change which is seeking to move away from the buying of outcomes through short term project funding and towards long term strategic investments which will have wider social and economic value which sustains long after funding ends. This is also in line with CR’s approach to VfM which is defined as:
“We want to give scope to communities and their partners to define the social change they want to see happen and what success looks like now and moving forward. Our investment goes beyond money to our relationships, models, approaches, expertise and communications. We recognise that we contribute to a bigger picture of social change, alongside other actors.”
The StP Programme continues to offer value for money in terms of effectiveness, equity and economy:
Effectiveness - Centring learning as a core function of the programme where partners, including local CSOs, APs and funders, asses the changes achieved and identify what could be done better. AP’s growing experience in delivering the required interventions to achieve the short-term outcomes from the planning and delivery of the CF.
Equity - Equity is fundamentally at the heart of the StP programme, which explicitly seeks to minimise / neutralise inequitable power dynamics both between funders and APs, and subsequently between APs and their funded partners within each country. The partnership assessment conducted in 2023, demonstrated the establishment of trusted relationships across the programme and the areas where the partnership could improve.
Economy - A core principle of the programme is to work collaboratively, transparently and in equal partnership. This is embedded through the co-creation of the programme and component grants, as well as the collaborative approach to find solutions to any challenge. This approach ensures that meaningful engagement with stakeholders is at the centre of the programme’s design, implementation and adaptation. This approach harnesses the vision, resources, energy and skills of all partners and enables more sustainable change through greater ownership and ultimately power to influence change in their communities and in the broader donor environment.

Date of last narrative financial report	28 November 2023	Date of last audited annual statement	22 February 2024

Annex 1: Theory of Change

## Annex 2: Acronyms

AP	Anchor Partner
CF	Catalyst Fund
CR	Comic Relief
CRMF	Community Resourcing Match Fund
CSO	Civil Society Organisation
CSSF	Civil Society Strengthening Fund
EER	End-to-End Review
FCDO	Foreign and Commonwealth Development Office
FP	Funded Partners
GAC	Galvanizing Africa Consult
INGO	International Non-governmental Organisation
OS	Organisational Strengthening
PAP	Programme Advisory Panels
RND	Red Nose Day
RINGO	The RINGO Project: Re-Imagining the INGO and the Role of Global Civil Society
SGF	Star Ghana Foundation
StP	Shifting the Power
TF	Tilitonse Foundation
ToC	Theory of Change
VfM	Value for Money
UK	United Kingdom
WACSI	West African Civil Society Institute
ZGF	Zambian Governance Foundation

## Annex 3: #ShiftThePower: A Manifesto for Change

The StP programme forms part of a broader movement built around the #ShiftThePower: A Manifesto for Change. The manifesto states:
If we want to create a genuine alternative to existing ways of deciding and doing, we need to:
1. Embrace a vision of a “good society” built around core values of equality, democracy and sustainability and a set of organizing principles based on global solidarity and distributed leadership.
2. Cast off the restrictive framework of “international development,” which is defined by money and power which creates artificial barriers between communities and movements in the global north and south.
3. Move away from a system that is preoccupied with quick “solutions,” and is premised on and organized around the transfer of funds. Change how we approach, and seek to measure, the notion of success.
4. Creatively find ways to unlock the inherent power of communities in determining their own development course – however they define it – and let the language of “beneficiaries” and “recipients be a thing of the past.
5. Move away from “building capacity” as defined by external actors and requirements, towards community organizing and movement building, where “capacity” equates to relevance, rootedness and constituency.
6. Ensure that external funding recognizes, respects and builds on local resources and assets, rather than over looks, undermines or displaces.
7. Expand our horizons beyond money as the central driver of change, and place greater value on other kinds of infinite non-financial assets and resources (knowledge, trust, networks etc)
8. Change the language we use so that it enables new ways of working and thinking, rather than constrains them. And challenge the dominance of English.
9. Change ourselves. We need both humility and boldness, and to be ready to challenge our own power and to listen to and work with others.
In short, we want a future that is negotiated, participatory, and widely owned, and which is developed through values and processes based on movement generosity rather than the success or failure of one organization over others.