Annual Review – January 2023

Title: Shifting the Power. Strengthening African Civil Society
Programme Value £ (full life): / FCDO: £30,000,000 / Comic Relief: £30,000,000 / Total £60,000,000		Review date: March 2023
Programme Code: 301034	AMP start date: / 31/03/2020	AMP end date: / 9 March 2030

Summary of Programme Performance
Year	2021	2022	2023
Overall Output Score	A	A	B
Risk Rating	Moderate	major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/55428258.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301034/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The ‘Shifting the Power’ programme is a 10-year partnership between Comic Relief and the Foreign Commonwealth and Development Office (FCDO). The programme was announced in March 2020 during Comic Relief’s annual televised fundraiser (Sport Relief 2020).
By partnering with Comic Relief and the British public over five annual televised matched appeals,
the programme will invest up to £60 million (in equal amounts from each organisation) in strengthening the capacity and sustainability of locally-led civil society organisations (CSOs) in Ghana, Zambia and Malawi that are working across areas that are a priority for both FCDO and Comic Relief: early childhood development, gender justice, climate change, enabling peace and security, safe and secure shelter and mental health.

The core programme activities will be the delivery of two funding streams for civil society and organisational strengthening:
- One fund will provide a mix of core and restricted funding to support organisational strengthening and resilience which is critical to delivering their strategic mission and achieving and overcoming some of the barriers to building organisational sustainability
- A second fund will provide training for CSOs in alternative forms of local income generation and will match the resulting revenue that they generate to incentivise income diversification and financial sustainability.
- Organisational strengthening facilitation will be provided to support CSOs in identifying and tackling the challenges that hinder them from achieving their mission and organisational sustainability.

The programme aims to begin addressing the negative consequences that short-term, project-focused funding (typically channelled through Northern intermediary organisations) can have on the ability of Southern-based CSOs to respond to the priorities of local people. This includes the power dynamic between the donor and CSO that shapes such funding and weights the donor and International Non-Governmental Organisation (INGO) intermediaries’ priorities above those of local people.

The intended impact is that civil society organisations in Ghana, Zambia and Malawi are more resilient, independent, and effective in delivery the priorities of local people. The programme will deliver four principal objectives:

- Locally led, Southern based CSOs will be supported to become more effective, sustainable and better able to represent local people’s priorities around key thematic areas in Ghana, Malawi and Zambia.
- The FCDO’s partnership with Comic Relief will be placed on a more strategic footing by jointly funding a programme that will span five annual matched appeals (rather than developing a new programme annually) and 10 years of programming.
- Working collaboratively with African storytellers, filmmakers and creatives, this programme will enable Comic Relief and FCDO to communicate a progressive narrative to the UK public demonstrating how aid is empowering local people to pursue their own priorities and to stand up for their rights.
- The programme will be innovative and adaptive. It will generate learning on the efficacy of different interventions designed to advance organisational capacity and resilience which will be influential in programme design within Comic Relief, FCDO, other funders and amongst CSOs themselves.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Staff recruitment challenges experienced in 2021 through to 2022 and Comic Relief’s internal restructuring and staff changes in 2022 has created challenges in delivering the programme. From February 2023, all key programme staff have been recruited and in post to deliver this programme. The programme nonetheless made every effort to implement the planned activities where possible, as evidenced by the achievements outlined in the detailed output scoring.

Clear progress was made in many areas. The three Anchor Partners were selected in March 2022. This was followed by a series of inception workshops and the process to contract them to the programme. The inception workshops focused on ensuring clarity was achieved by all parties in terms of objectives and deliverables for the Development and Iteration phase (also referred to as the interim phase) from May to September 2022. In the spirit of the programme, it was essential to work with Anchor Partners to co-design many of these areas.

During the interim phase (May to September 2022) the Anchor Partners undertook the following activities:
- Developed a self-assessment tool to be used by ‘Catalyst Fund’ grantees in the development of their full Strengthening Civil Society Fund proposals.
- Co-designed the funds - Strengthening Civil Society Fund; including a ‘Catalyst Fund’ for small grants to support the development of proposals.
- Mapping the local and national market of organisational strengthening support services and groups for CSOs (as determined by the Organisational Strengthening Framework).
- Developed country specific ‘Organisational Strengthening Frameworks’.
- Country scoping exercise - Updated the country socio-economic and political contextual analysis of the key issues including a mapping of the main national actors working in these areas with an emphasis on civil society actors and recommendations for which thematic area (s) will focus on.
- Governance - Design of the governance processes for grant decision making.
- Plans and budget - Develop a full delivery plan and budget for the long-term phase of the programme.
- Organisational Assessment - Analysis of the anchor partner’s organisational strengthening needs.
- Liaison with other Anchor partners contracted for the development and iteration stage to ensure delivery plans are complementary and dovetail well.
- Due diligence - Support the due diligence processes Comic Relief needed to make decisions on the long-term investment.

Anchor Partners were selected through a closed call and a rigorous process of assessment and due diligence to deliver the long-term phase of the programme. They are extremely well placed in their specific civil society contexts to deliver the programme well. Good relationships have been built with the Anchor Partners providing the basis for strong partnerships. The work of defining this partnership is ongoing and it will culminate into the development of partnership agreements that reflect the shifting the power principles. Contracting the three Anchor Partners for the long-term phase took far longer than expected. More implementation activities would have been achieved in the year had there not been delays to the contracting. During the process of contract negotiation for the long-term phase from September to December 2022, the Anchor Partners undertook a limited number of other activities carefully negotiated with them as there was no contract during this period to guide the relationship:
- Participation in a learning and sharing session on the Catalyst Fund. The purpose of the session was to enable further reflection on this fund since it was the first for implementation among the core activities of the programme
- Engaged in reflections on the Programme Advisory Panels. Prototypes for the Programme Advisory Panels were explored and developed to be further iterated and discussed by all the partners. Given their pivotal but debated role in the programme it has been important to do this collaboratively.
- Two of the Anchor Partners CEOs met in London with senior staff and board members of Comic Relief and senior members of FCDO.

This programme is committed to embedding learning in all it does. Considerable effort has been invested in this with regular learning sessions with Anchor Partners and within Comic Relief being held in the year under review. Progress has been made towards the development of the learning strategy and is to be finalised in April 2023 during the meeting to be held in Lusaka.

Major lessons and recommendations for the year ahead [1/2 page]

Major lessons for year ahead

In the year under review progress was made in building good relationships and developing a more equitable way of working with the Anchor Partners. However, building more equitable partnerships requires time and a fundamental review of internal practices as funders (Comic Relief and FCDO). Most of our agreements, reporting processes and other ways of working are based around contracting organisations to deliver specific programme; as opposed to this new partnership we are establishing with Anchor Partners, based around devolved grant making, more trusting ways of working and horizontal accountability amongst all partners in the programme. So, Comic Relief have had to make sure these systems and practices are not unnecessarily burdening Anchor partners and are appropriate for a programme that is aiming to shift power. In addition, Comic Relief have then had to discuss if they put unnecessary paperwork or controls in place for the partners they go onto fund; and taking time away from them addressing the priorities of those most impacted upon by poverty and injustice. During the contracting phase Anchor Partners expressed concern about certain provisions in the agreements:
    1. Clauses related to digital spend requiring notification each time there is spend on this category
    2. Several provisions requiring Anchor Partners to provide varied information in various clauses in the agreements.

The information requests can be a burden on the Anchor Partners leading to diversion of focus from them and their funded partners from their mission of tackling poverty and injustice.

The level of complexity planned into this programme has taught us that decision making/governance requires depth of thought and measured consideration. A one size fits all approach will not work because of the multiple accountabilities that stakeholders in the programme have and for the governance structures developed to reflect the shifting the power principles.

1. The risk appetite of the programme should be reviewed to ensure due diligence, compliance and reporting procedures do not overwhelm, with one of the programmes’ central aims of improving accountability to local people and their priorities. Examples of risk aversion include requirements in the agreements such as:
  1. Clause 5.1 (d) you have all necessary resource and expertise to deliver the Activities; This clause does not take it account that the Anchor Partners have capacity needs of their own which have to be addressed.
  2. Clause 5.1 (f) you and any person, organisation, company or other third-party representative engaged in the Activities will comply with all applicable laws, regulations (including the laws of England & Wales and any other jurisdictions in which you undertake Activities), rules, codes of practice and the Policies; The concern with this is how organisations operating outside of England and Wales are expected to be fully knowledgeable of laws in a jurisdiction they are not resident in.

Communicating a progressive narrative will require us to enable those most affected to tell their own stories. This will require building relationships with African film makers and other creative story tellers and learning from them the types of narratives they want to tell.

When developing the advocacy plan for the influencing of donor funding practices towards shifting the power principles, central to this is exploring the distinct role and added value Comic Relief and FCDO can bring to the burgeoning movement of funders looking to shift power in their grant making practices.

Comic Relief working with the Anchor Partners should invest in alternative forms of financing including those promoting local philanthropy, matching funds etc. This will require learning from other funders that are already have this support in place and from Anchor Partners such as WACSI (who are working in partnership with Star Ghana Foundation to deliver this programme) who are at the forefront of promoting this endeavour within the shifting the power movement.

Protect time for collective learning as part of the formal learning agenda, alongside other routine operational meetings.

Build in key learning from the organisational strengthening pilot study and partner experiences to ensure organisational strengthening within the programme is offered, and perceived to be offered, as funded partner led and of intrinsic value to funded partners.

Recommendations for the year ahead

Summary of recommendations	Owner	Completion date
Cocreate with the Anchor Partners best practice governance structures for devolved grant making that balance governance as envisaged within the Business Case and existing practices within the Anchor Partners.	Comic Relief	June 2023
Embed the RINGO re-imagining risk and compliance prototype into the programme.	Comic Relief	December 2023
Review the risk appetite of the programme to meet one of the programmes central aims of improving accountability to local people and their priorities.	Comic Relief and FCDO	September 2023
Protect time for collective learning	Comic Relief	To be done as part of annual work plan by 31st March 2023
Communicating a progressive narrative that enables those most affected to tell their own stories	Comic Relief	During Red Nose Day and other times to be determined by the Comms strategy
Development of an advocacy plan for the influencing of donor funding practices towards shifting the power principles.	Comic Relief	May 2023
Participation and shifting power in grant making require Comic Relief plan carefully to enable sufficient time for processes to be truly representative and meaningful, particularly where co-design is involved	Comic Relief	This an approach and not an event will therefore be ongoing
Build in key learning from the OS pilot study and partner experiences to ensure OS within the programme is offered, and perceived to be offered, as funded-partner led and of intrinsic value to funded partners.	Comic Relief	Ongoing

Update on last years’ recommendations
The March 2022 review made several recommendations to deal with the lessons learnt. Progress was made as follows:
- Ensure specialist technical input – The programme incorporated external assessors and experts by experience in conducting assessment of the proposals submitted by the Anchor Partners. Consultants associated with the Shifting the Power movement have been used to provide input into various aspects of the programme.
- Ensure resource for remote processes – Comic Relief worked remotely and successfully with the Anchor Partners and access to Internet and IT equipment was not a barrier.
- Organisational Strengthening (OS) Learning Study – Comic Relief is piloting an Organisational Strengthening (OS) framework and principles in three other FCDO funding portfolios and weaving the learning into the Shift the Power programme to ensure OS is offered and perceived as funded-partner owned and driven and not as donor-compliance.
- Risk Register – Comic Relief continued to maintain a live risk register that is reviewed quarterly with FCDO.
- Learning Strategy – to test community accountability impact on assurance – The testing will begin as soon as the learning strategy is finalised and implementation of the strategy begins.
- Build in additional time and use a breadth of platforms for staff recruitment, which seeks staff who are multi-specialists in a number of intersecting areas. – This was undertaken and successfully completed whereby from 1 February 2023 the programme will be at full staff capacity.
- Consult with Anchor Partners in advance of recruitment – Consultations with Anchor Partners led to the abolishment of the position of Comic Relief in-country programme managers (CPMs). It had been envisaged that CPMs would be recruited for this programme, but on closer discussion with the Anchor Partners it was difficult to ascertain the specific added value of these roles that couldn’t be undertaken by either the Anchor Partners or other CR programme staff. CRs other programmes support partners in many countries’ programmes in Africa and elsewhere and that has not necessitated residency in those countries. The issue of closer oversight was discussed as one of the advantages of the role of the CPMs but it was concluded that with oversight being provided by Anchor Partners own governance structures, the PAPs and CR programme staff, there is sufficient oversight. There was clear potential for the CPMs to add an additional layer of complexity to an already complex management structure for the programme.
- Participation and shifting power in grant making – Comic Relief ensured that Anchor Partners lead in the various processes and design of the components of the programme through continuous engagement, building meaningful and not tokenistic relationships with them
- Review programme risk appetite – Yet to be done
- Test repayable finance internationally as a potential route to sustainability for some local CSOs. Lessons learned to feed into the work on alternative financing which the Shifting the Power Portfolio is due to explore.
- Define programme logframe output, outcomes and impact milestones through to the end of 2030 - Considering the phased approach to funding, milestones are defined through to the end of the period of funding granted (2025). In line with shifting power principles and working with grant-making anchor partners, these are predominantly qualitative and not include numbers of people benefiting.

During the period January to March 2023 the Anchor Partners are working on the following:
- Preparing for the launch of Catalyst Fund (CF) activities;
- Conducting promotional activities and workshops with local CSOs so that they know about the availability of the CF and the requirements for applying to the fund;
- Learning and sharing meetings for CSO applicants to share their Catalyst Fund ideas for cross-fertilisation;
- Launch of calls for the Catalyst Funds;
- Providing technical support to partners to develop concept notes/ proposals (accompaniment, reviews of proposals and budgets);
- Facilitating review of capacity assessments from the CSOs that have applied to the CF;
- Conducting selection process to determine successful applicants to the CF;
- Orientation session for selected Community Based Organisations / Civil Society; Organisations under the Catalyst Fund Component;

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The development of the programme Theory of Change (ToC) was led by Comic Relief during the initial design phase of the programme in 2020 and was informed by engagement from civil society leaders and thinkers from each of the programme countries; African sector-wide experts; Comic Relief and FCDO. It underpins the Business Case and frames the ongoing programme, demonstrating how the programme will approach working collaboratively with Anchor Partners to design and implement appropriate in-country governance mechanisms and grant making in support of the programme’s intended impact: that civil society organisations in Ghana, Zambia and Malawi are more resilient, independent and effective in delivery the priorities of local people.

The Theory of Change outlines how Comic Relief and FCDO will work collaboratively with local ‘Anchor Partners’ and appropriate in country governance mechanism's ability to generate funding locally through a ‘Catalyst Fund’, ‘Strengthening African Civil Society Fund’ and ‘Community Resourcing Match Fund’ respectively. The ToC assumes that by identifying and investing in their own organisational strengthening priorities and diversifying their funding models (with support from Anchor Partners and local providers), CSOs will be better able to develop, and stay true to, their long-term strategies in response to local people’s priorities. Greater flexibility and autonomy afforded by enhanced organisational capability and a more diverse and sustainable funding model will increase CSOs’ effectiveness while reducing reliance on foreign donor funding. Accountability can therefore shift away from distant donors and towards local people, building local trust and engagement.
[note] Anchor Partners are local civil society infrastructure organisation/s with whom Comic Relief will partner to jointly design the programme, and to provide programme management in each country.

The theory of change encapsulates the experimental nature of the programme and its intention to generate new learning and insights towards power shifting in international development, and on civil society strengthening.

During this period, implementation has focused primarily on activities relating to the design and initiation of the Catalyst and Strengthening African Civil Society Funds (SACS); organisational strengthening frameworks by the Anchor Partners; and development of both learning, and communications and influencing strategy.

Both the Catalyst and SACS funds were designed as part of the Design and Iteration phase. The Catalyst Fund has also been the subject of learning and reflection between the Anchor Partners and Comic Relief, alongside other dedicated learning conversations including ‘shifting the power in reporting’, which has fed into the grant management design to ensure shifting the power principles are adhered to. For example, this learning reflected that grant-makers should stop a ‘one-size-fits-’ll' approach to monitoring, evaluation and reporting, and be more flexible in enabling funded partners to tell their stories of change. Another example arising from the learning sessions was the challenge to the pre-determination of all thematic areas for focus in the business case. This led to changes to flexibility to themes to ensure that those that are priority to each country context are included.

The Value for Money (VfM) case for this programme was agreed to not be based on cost per beneficiary calculations, which would be at odds with a theory of change which is seeking to move away from the buying of outcomes through short term project funding and towards strategic investments which will have wider social and economic value which sustains long after funding ends. The programmes ToC offers VfM in relation to effectiveness and equity as follows:

Effectiveness
- Comic Relief’s long expertise as a grant maker.
- Comic Relief’s communications expertise including large multimedia public appeals; content production which reaches, challenges and influences a broad UK audience, all contribute to effectiveness towards the outcomes of this programme.
- Comic Relief is now working with Anchor Partners with expertise in delivering the required interventions (designing and implementing the three grant-making programmes) to achieve the short-term outcomes anticipated from the Catalyst and Shift the Power funds (for example setting organisational development priorities).
- The programme is investing in organisational strengthening for both Anchor Partners and their funded partners, in line with the organisational framework and principles co-developed with FCDO in concurrent programmes with Comic Relief; Maanda (RND13), All in All Learning (RND15) and Mental Health in Kenya (RND19). This investment ensures both Anchor Partners and the CSOs they support are supported on a path to sustainability, enhancing the funding’s contribution to sustainable social benefits even after funding ends.
- The programme implementation and adaptation continue to be informed by knowledge, evidence and learning from within the programme itself, and from FCDO funded Maanda (RND13), All in All Learning (RND15) and Mental Health in Kenya (RND19). This learning also generates additional VfM by influencing more effective civil society programming in programme countries, as well as improving funding practice for Comic Relief, FCDO and other donors.

Equity
- Equity is fundamentally at the heart of the Shift the Power programme, which explicitly seeks to minimise / neutralise inequitable power dynamics both between funders and Anchor Partners, and subsequently between Anchor Partners and their funded partners within each country.
- The Catalyst Fund seeks to enable organisations who might not otherwise be funded to develop their systems and processes, so they are ready to receive funds. It seeks explicitly to support organisations to succeed in applying to the SACS Fund, where each Anchor Partner’s fund design is specially designed to enable marginalised organisations to secure Catalyst Funds. Those targeted include organised and less organised groups, media organisations, civic networks and coalitions at community, regional and national levels. CSOs that are based in communities or supporting but not necessarily located in the community affected by climate change and / or environmental degradation. Underserved communities including women, youth, children and persons with disabilities in programme areas will be the ultimate beneficiaries of the programme.

Economy
Anchor Partners were assessed for economy during assessment– for example exploring procurement policies, financial management systems and skills, programme scoping and project planning to ensure that robust checks and balances are in place. The programme works to ensure that as much resource as possible accrues to Anchor Partners and onwards to their local civil society partners.

No changes have been made to the theory of change in this period, but it’s anticipated that, during the long-term partnership phase starting from December 2022, reflecting on and iterating the theory of change will become part of the programme’s learning agenda and it’s anticipated that changes may take place as reflection and learning are built into the programmes approach and activities. These will be confirmed in the learning agenda but are likely to include regular reflection sessions with Anchor Partners and other programme stakeholders.

In the business case for the programme the FCDO and Comic Relief agreed to a set of design principles, one of which is to seek to shift power closer to people with experience of poverty and injustice and be rooted in a feminist analysis of power and equality. Guided by this principle the application process and proposal assessment for the long-term phase of the programme ensured inclusion of often marginalised groups and geographies. Anchor Partners in their long-term proposals have as their targets underserved populations such as children, youth, persons with disabilities, women and communities affected by climate change and / or environmental degradation.

A core principle of Comic Relief’s engagement with Anchor Partners has been to work collaboratively and in equal partnership. This is embedded in the approach to codesign the programme and component grants, as well as to work together to find solutions to any challenges arising. We are learning that such collaboration requires time and commitment to open conversation and can only occur within a safe space built on mutual trust, shared risk and benefit. This period has focused on building such a relationship with Anchor Partners through conversation, open dialogue, reflection on each partner’s practice and commitment to identify and change practice to intentionally put shifting the power principles into practice. Working collaboratively and consciously like this takes longer than resorting to historic and inequitable funding approaches and has contributed to some of the delays in achieving programme objectives as it is crucial for these foundations to be in place for this work to flourish.

Our original timeline for the programme did not sufficiently accommodate the time this would take and this has caused some work to take longer than expected, but Comic Relief believes this focus on creating a more equitable relationship with Anchor Partners is fundamental to achieving success for the programme in the long term. It directly reflects the programme’s commitment to both shifting power and the ‘Leave no one behind’ agenda. It ensures that meaningful engagement with local stakeholders, and their onward engagement with their constituents, are at the centre of the programmes design, implementation and adaptation.

In addition, the programme will co-design Anchor Partner reporting templates to Comic Relief and consider approaches to reporting of the funds within the programme. However, counting ‘people benefitting’ would be at odds with a theory of change which is seeking to move away from short term project funding and towards strategic investments which will have wider social and economic value.

Finally, the learning agenda under development in this and the next phase of the programme will outline strategies for and learning from engaging constituent communities directly.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Comic Relief completed grant making to the three Anchor Partners in December 2022, marking the beginning of the confirmed commitment to a long-term partnership phase of the programme. An in-person convening of partners in April 2023 is planned and will be an opportunity to consolidate and build on the work to date both operationally (e.g., Catalyst and SACS fund design and management) but also to bring organisations and individuals together and strengthen connections. It is the primary stated objective of each partner that this convening opportunity focuses more on relational aspects and partnership building, true to power shifting principles of creating a more equitable collaboration, with the intention that this will ease and catalyse the implementation of the programme going forward.

The programme for the year ahead will focus on:
- Delivering the SACS and Community Resourcing Match Funds
- Delivering organisational strengthening for both the Anchor Partners and their funded partners
- Progressing the communications and advocacy work, including conducting research into UK audiences view on shift the power, the development of a joint Comic Relief and FCDO communications plan that will d engage with African filmmakers and other creatives.
- Developing with Anchor Partners in-country communications and advocacy strategies/plans
- Strengthening Comic Relief’s participation in the shifting the power networks and movements.
- Resolving the role of the PAPS and the overall governance structure for the programme
- Co designing with the Anchor Partners, their value for money policies
- Co creating with FCDO and the Anchor Partners risk sharing and compliance management that is anchored in the shift the power principles

While we will be able to more fully report on the impact of the programme in later years, we believe the programme is on track. There have been delays in implementing some activities leading to the programme progressing slower than it should be. Some of these were practical due to staff recruitment issues, but also some of this was because we wanted to take the time to invest in the co-design of work with the anchor partners and in developing equitable relationships with them that reflect the shift the power principles of the programme. We do believe however given the long-term nature of the programme we are on track to achieve expected outcomes and impact. However, this will require some mitigation measures being put in place including:

- Adequate staffing at CR – This has now been achieved but it requires to be maintained and ensure back up is available should shortage of staff at CR occur. CR has for back up a number of consultants who have worked with the organisation for a long time, know the organisation well and are therefore able to fit in quite quickly should need arise.
- Work with Anchor Partners on their capacity development, so they are able to deliver effectively and efficiently.
- Streamlining comic reliefs operational systems so that wherever necessary repetition, duplication etc are removed and they are in line with shifting the power principles.
- Expanding the Operational Working Group (OWG) of the shifting the Power programme to include people from the operational side of the organisation such as legal, finance, risk & assurance. Currently the OWG is made of core programme team (MEL, Comms, programme lead and the head of the Poverty and Injustice Unit of the Funding Directorate). The group meets monthly to consider operational issues affecting the programme to find solutions. The operational colleagues are consulted as per need. But we believe having them in the room as challenges are being diagnosed will bring about greater appreciation on their part and overall, the ability to resolve things quicker.
- Recognising that cocreation takes time, planning of activities should take that into careful consideration and monitoring processes should expect and accommodate change.
- Following the organisational restructuring at CR has now stabilised and this too will assist in overall effective implementation.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Comic Relief believes that the programme represents good value for money, is making clear progress and should continue.

The focus of the work to date has been building stronger, more equitable partnerships and improving Comic Relief’s collaboration practices, and this has had implications for operational timelines as originally envisaged. In the next period, with the recent grant commitment to the long-term partnerships with Anchor Partners in place, Comic Relief will catalyse implementation of Catalyst and SACS funds, from a much stronger and more equitable foundation.

The work has been adapted but this has always been based on learning. The programme is committed to the centrality of collaboration and adaptation, and the continual learning and adaptation is an embodiment of the principles and aspirations as stated in the Business Case.
Comic Relief’s recently launched its Strategy to 2025 that has been strongly influenced by this programme. Principals such as working with those closest to the issues including organisations with knowledge of and credibility with the communities they serve; supporting partners to tell powerful, dignified stories about the impact of poverty and climate crisis – and their solutions are central to the new strategy.

The strategy also recommits to public engagement to raise awareness and building understanding (key to this programme’s objective); to funding organisations, not just projects; and to convening and networking in support of learning, movement building, and fundamental shifts in practice, which remains crucial to FCDO Single Departmental Plan, both in supporting priority outcome one – supporting sustainable development, and in committing to a diverse range of global partnerships.

C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Comic Relief grant making and management supports anchor partners to deliver their planned activities
Output number:		1	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of Anchor Partners successfully contracted	Three	All three anchor partners (including WACSI, working in partnership with Star Ghana Foundation) were contracted for the Design and Iteration phase in May for Zambia and Malawi and June for Ghana. Final grant Conditions of Funding were completed in Dec 2022 for the long-term partnership.
1.2 Number of projects in the AP portfolio that receive a high-quality review	Two	Catalyst Fund disbursements are due to start in March 2023 and as such, no reviews have taken place during this reporting period.
1.3 [indicator to be finalised on Comic Relief’s-Anchor Partner relationship satisfaction]	Tool developed and baseline collected	Comic Relief and Anchor partners collectively agreed a tool to use for the partner relationship satisfaction, and subsequently took time to find a partnership broker in line with Shift the Power programming, so requiring exploration of new consultant networks in partner countries. These were achieved within the reporting period and Comic Relief has contracted an accredited Partnership Broker to support work between Comic Relief and Anchor Partners to embed partnership working within the programme. / However, in order to ensure quality engagement and data, the consultant will use the face-to-face meeting in April -2023 to initiate the assessment using the Learning Loop approach, resulting in a ‘score’ that will act as a baseline for the programme.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output relates to the Design and Iteration phase, as well as the transition to the long-term partnership grant.

Indicator 1.1, Number of Anchor Partners successfully contracted
Met but delayed – All three Anchor Partners successfully completed the Design and Iteration phase, which was contracted in May 2022. Contracting of the Anchor Partners for the long-term phase was due to be completed in late October to early November 2022 but was finalised in December 2022. The long-term contract was phased into three parts. the first phase of the longer-term partnership, is up to September 2025 and was confirmed subject to availability of funds and other conditions) and a commitment to in principle to funding of two phases up to September 2023. The decision for phasing was made because Comic Relief felt unable to make a long-term commitment given the substantial amounts involved which it does not have upfront and is dependent of the outcome of future fundraising.

Indicator 1.2, Number of projects in the AP portfolio that receive a high-quality review

Not met – Catalyst design and testing was originally planned to take place in April to June 2022, and catalyst grants awarded in Ghana and Zambia in July/August 2022. However, due to the delays in contracting the Anchor Partners for the long-term phase the Anchor partners will begin to build their portfolio this year with Catalyst Fund disbursements All Anchor Partners have advertised the call for proposals for the catalyst funds and started the vetting processes. As such, no reviews have taken place during this reporting period.

Given the aforementioned delays to implementation work on the Community Resourcing Match Fund has not begun as envisaged. Comic Relief will work with the Anchor Partners to determine new timelines for this taking into account that this component of the programme is a new way of working for both Comic Relief and the Anchor Partners and also very significant to the overall impact of the programme. We want to make sure that it is carefully planned and implemented.

However. Comic Relief and Anchor Partners have initiated exciting conversations about different approaches to assessing the quality of the funder – funded partner relationship. These seeks to directly feed into the programme’s aim to shift power, dismantle inequitable power imbalances and re-frame the relationship as one of equality of risk, benefit, resource and expertise.

While Indicator 1.3 outlines this in more detail, it’s envisaged that this initial partnership assessment between Comic Relief and the Anchor Partners will also model a new approach to ‘reviewing’ funded partner projects and progress in the longer term. This is therefore on-track to hit current log frame targets to March 2025.

Indicator 1.3, [indicator to be finalised on Comic Relief’s Anchor Partner relationship satisfaction].
Partially met during the period of this review. Comic Relief and Anchor Partners considered options and approaches to a partnership assessment in depth, and came to an agreed way forward, within the period under review. It was agreed to delay the implementation of the assessment until the April convening on the basis that this would result in better quality engagement and ultimate baseline.
Comic Relief and Anchor Partner learning sessions have explored equitable partnership approaches and power shifting throughout 2022, culminating in a review and shortlisting of partnership assessment tools that would help produce an annual assessment or score of the quality of the partnership, but also support and strengthen the relationship with Anchor Partners by creating an open and safe space to explore power, decision-making and risk within the programme. For this reason, finite quantitative surveys and approaches to measure the Anchor Partners’ satisfaction have been excluded and Comic Relief and Anchor Partners have collaboratively agreed to work with an independent partnership broker to provide objective, neutral and independent guidance, as well as ensure that the partnership is given due attention alongside the programme implementation. They will use the Learning Loop approach which is directly in line with the programme’s ambition and learning agenda on shifting power and changing practice and is on-track to for 2025 logframe indicators. The Learning Loop has both qualitative and quantitative components and supports mutual discussion and feedback, rather than unilateral 'scoring' of either funder or funded partner. Anchor Partners will have their own means for assessing the performance or relationship satisfaction of their onward grantees, under indicator 1.2, but these will be shared and reflected upon in relation to ‘shifting the power’ as the programme progresses.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Comic Relief and the Anchor Partners all bring deep experience in grant making and community philanthropy which significantly contributes to the effectiveness of this programme. The ambitions of the programme require radical honesty from all co-funders and funded partners to reflect on organisational practices and be open to challenge and change. This will ensure grant making practices will be iterative, implementing learning and good practice in pursuit of the programme’s anticipated impact.

 Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no changes to the output during the review period. Since we anticipate a baseline in March 2023, we anticipate a second assessment in Jan / Feb 2024, in line with the existing logframe and workplan. With learning and iteration are embedded in this programme, we therefore cannot completely rule out having to make changes in response to contextual or situational matters that might arise.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Summary of recommendations from Yr 2 (2021-22)	Progress March 2023
Participation and shifting power in grant making require Comic Relief to: plan carefully to enable sufficient time for participative processes to be truly representative and meaningful, particularly where co-design is involved.	Comic Relief and Anchor Partners continue to work collaboratively to codesign programmes activities, which has led to revised delivery schedules to accommodate participation and shared decision making. / Additionally, the approach to and process for codesign continues to improve as personal and individual relationships strengthen and enable open dialogue that moves away from tokenistic engagement. / Comic Relief has initiated a conscious ‘partnering lens’ to the programme to directly address power imbalances and better enable all stakeholders to be meaningfully engaged.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons learned this year
In the year under review, progress was made in building good relationships with the Anchor Partners. However, building equitable partnerships requires time and a fundamental review of systems and practices of funders (Comic Relief and FCDO) so that the same are not unnecessarily burdening partners and drawing them away from achieving their missions and meeting the priorities of those most impacted by poverty and injustice. A start has been made with the Anchor Partners reviewing the signed agreements to indicate those clauses which contribute to making the partnership unequal. Ideally in a shifting the power partnership a contract is cocreated, which unfortunately was unable to happen in this case. Although the Anchor Partners were given some time to review the draft agreements and give input, this process was hindered by insufficient time and the fact that some of the clauses in the contracts are non-negotiable given the legal and accountability requirements of both Comic Relief and FCDO. Further discussions will be held within Comic Relief and with FCDO on the submission made by the Anchor Partners to determine where there is flexibility to vary some of the clauses deemed onerous with the intention to make amendments wherever possible.

Furthermore, the programme has been divided into three phases in order to ensure Comic Relief has the full amount to commit to partners ahead of the next phase. The first phase is ending in 2025 which provides an opportunity for review of contract templates and efforts to make them more equitable in nature.

Recommendations for the year ahead
Recommendation	Responsibility	Completion date
The risk appetite of the programme should be reviewed to ensure due diligence, compliance and reporting procedures do not overwhelm one of the programmes central aims of improving accountability to local people and their priorities.	Comic Relief /FCDO	Ongoing

Output Title	Evidence and learning on how to build organisational capacity and resilience in Southern led civil society
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Learning strategy developed and iterated in collaboration with programme stakeholders	Initial learning strategy developed	Learning Sessions between Comic Relief and the stakeholders have gathered significant detail on each stakeholder’s existing and future learning ambitions. These have been aggregated and will be formalised into a formal learning agenda and implementation plan during and following the April convening.
2.2 Knowledge and learning products are produced in line with the learning strategy and disseminated through networks	In line with learning strategy	Pending the collaboratively agreed Learning Agenda, various learning products and events have taken place in this period. / Comic Relief and WACSI staff were panel members for an INTRAC discussion on shifting the power in monitoring, evaluation and learning. / Comic Relief has held internal learning sessions reflecting on putting shifting the power principles into practice.
2.3 Equitable and high-quality learning collaborations formed on key programme components	n/a	Each partner continues to foster learning collaborations independently, while the Learning Agenda will more formally identify opportunities for new collaborations, specific to the programme’s learning ambitions

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Indicator 2.1, Learning strategy developed and iterated in collaboration with programme stakeholders.
Partially met - Collective learning sessions, started during the design and iteration phase, have ranged from having a specific focus on existing partner Monitoring, Evaluation, Research and Learning (MERL) activities and ambitions, to broader and more exploratory considerations of learning potential from this programme. From March 2023, these will feed into the development of a tangible, costed activity-based learning agenda, which partners did not feel was possible until long term grants were made, which were made to the Anchor Partners in December 2022. In part, it was difficult to prioritise or commit to longer terms learning ambitions prior to grant commitments, but it also wasn’t practical before clarity on available budgets for learning held by each partner. This is therefore on-track to hit year 4 milestone.

Indicator 2.2, Knowledge and learning products are produced in line with the learning strategy and disseminated through networks.
Partially met – due to the delay in the learning agenda (indicator 2.1) being developed, pending clear articulation of desired learning products in the learning agenda, each partner has shared learning and insights from the programme to date according to their own learning approaches. For Comic Relief, this has included participating in a panel discussion on shifting the power in monitoring, evaluation and learning; internal staff sessions reflecting on learning from the programme (for example, on the role of operations – risk, compliance and finance – in enabling Comic Relief to ‘walk the talk’ of power shifting). This is therefore on-track to hit year 4 milestone.

Indicator 2.3, Equitable and high-quality learning collaborations formed on key programme components.
Not met - The Learning Agenda will formally bring together the learning ambitions, and learning networks, of each of the programmes’ partners. This will enable articulation of appropriate approaches to forming learning collaborations, for example with academic or research institutions, through commissioning research and evaluations or through informal learning with others operating in this space. Signing of research contracts with a university, think-tank or academic institute was originally planned to start in October 2022 but has been deferred to March 2024.

In anticipation of the start of the research, Comic Relief has already mapped out each partner’s learning collaborators and began thinking about equity in research and learning partnerships, drawing on the experience and learning from the ‘Understanding and Improving Equitable Research Partnerships’ Initiative. This is therefore on-track to hit end-of-year 5 targets in 2025.

The learning component of the programme directly speaks to both efficiency and effectiveness of the programme. Continual learning and adaptations, informally during this period, but increasingly formalised through the Learning Agenda in the next period, ensure ‘inputs and activities are appropriate, timely and informed by best practice to ensure anticipated outputs are efficiently reached.

This same learning builds on progress towards the programme outcomes in relation to the theory of change and logframe, to ensure effectiveness.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes during the review period. Subsequent years’ plans are dependent on the learning strategy and therefore we don’t anticipate further changes to the logframe indicators. However, learning and iteration are embedded in this programme, we therefore cannot completely rule out having to make changes in response to contextual or situational matters that might arise.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Summary of recommendations from Yr 2 (2021-22)	Progress March 2023
Participation and shifting power in grant making	As with output one, the commitment to ensuring meaningful participation in promoting and building in learning to the programme, has required time to build a strong foundation between Comic Relief and Anchor Partners.
Define programme logframe output, outcomes and impact milestones through to the end of 2030	Since progressing with the long-term partnership grants in phases, rather than the envisioned single long-term grant, Comic Relief has reflected this time period in the programme logframe. / In keeping with the shifting the power principles, embedding of of learning and iteration, Comic Relief commits to revising these milestones where the programmes experience and consensus with Anchor Partners suggests that a different approach will more effectively achieve programme outcomes.

Lessons learnt this year
It has been challenging to protect time for collective learning and reflection on funding practice while all partners have been focussed on operational matters relating to agreements and grants in this period. While the designated learning sessions have been consistently well attended and received good feedback, they have also had to be co-opted at times in order to enable group conversations about operational matters. This has been a pragmatic approach to ensure partners’ time is used efficiently, and it is anticipated that learning spaces will be better protected in the next period to reflect and learn from the programme’s implementation, rather than to discuss and plan for it.

Recommendations for the year ahead
Recommendation	Responsibility	Completion date
Protect time for collective learning as part of the formal learning agenda, alongside other routine operational meetings	Comic Relief and Anchor Partners	Ongoing

Output Title	More empowering representation of civil society
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Equitable and high-quality communications collaborations in the Shift the Power and Community Philanthropy Space	one example	none
3.2 Stories (including user-generated content) produced which are informed by local voices and or key elements of community philanthropy	Approach to communications and influencing developed	The communications and influencing strategy was developed during this reporting period in a process within CR. The draft is to be further iterated and finalised with input from Anchor Partners at the in-person meeting in April 2023. This will also allow APs begin to develop in-country strategies

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 3.1, Equitable and high-quality collaborations in the Shift the Power and Community Philanthropy space

Not met – With challenges in hiring high quality staffing for the communications and influence strand of the programme, and pending final granting for the long-term partnership, progress has been slow. The Advocacy and Communications Manager has now been recruited and will work with the Anchor Partners, in developing their own in-country advocacy and comms plans. This work will progress in the next phase and is on-track to hit end-of-year 5 targets in March 2025.

Indicator 3.2, Stories produced which are informed by local voices and or key elements of community philanthropy
Partially met - Work on communications and influencing has been slow to progress due to recruitment challenges both for the programme itself and for Comic Relief’s audience insight and communications team. Comic Relief has faced challenges in recruitment of high-quality staff in what turned out to be a sector wide problem faced by charities in the UK. This problem is attributed to the disruptive impact of Covid 19. However, there is now a team in place and in the next reporting period (April 2024 – March 2025), they will develop a joint communications strategy with FCDO. Anchor Partners will develop their own in-country advocacy and communications plans which will use assets informed by local voices and or key elements of community philanthropy. This work will progress in the next phase, and this is on-track to hit end-of-year 5 targets in March 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no changes to this output during the reporting period. No changes anticipated for the output indicators as a result of this review. However, learning and iteration are embedded in this programme, we therefore cannot completely rule out having to make changes in response to contextual or situational matters that might arise.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Summary of recommendations from Yr 2 (2021-22)	Progress March 2023
Consult with Anchor Partners in advance of recruitment to interrogate which roles are most appropriately held in a country of operation, which are best suited to being embedded within Anchor Partners and which (for strategic / influencing reasons) are best suited to being located in the UK.	Consultations were conducted with Anchor Partners as per recommendation from year 2 leading to a management decision by Comic Relief to not go ahead with recruiting the position of Country Programme Managers. The funds allocated to these positions were reallocated to the Anchor Partners for their organisational strengthening.
Participation and shifting power in grant making require Comic Relief to plan carefully to enable sufficient time for participative processes to be truly representative and meaningful, particularly where co-design is involved	This is a core value of the programme. With a strong commitment to ensuring meaningful participation, Comic Relief has been intentional in creating dedicated time to build a strong foundation in the relationship with Anchor Partners.
Build in additional time and use a breadth of platforms for the recruitment required under this programme, which seeks staff who are multi-specialists in a number of intersecting areas	Recruitment of high-quality staff has been a challenge for Comic Relief. This is because this programme requires staff who are experienced in shifting the power - a relatively new approach requiring people who are multi-specialists. Progress has been made with recruitment of the Communications and Advocacy Manager and from 1st February 2023, the programme will have full staff compliment.

Lessons learnt for this year

Insufficient work was done in the area of comms and advocacy from which to draw lessons from.

Recommendations for the year ahead

Recommendation	Responsibility	Completion date
Communicating a progressive narrative that enables those most affected to tell their own stories. This will require: / Building relationships with African film makers and other creative story tellers	Comic Relief/Anchor Partners	On-going
Development of an advocacy plan for the influencing of donor funding practices towards shifting the power principles.	Comic Relief/Anchor partners	July 2023

Output Title	Funded Partners are supported to generate income from local or community philanthropy
Output number:		4	Output Score:	C
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 A community resourcing match fund is established	Programme Advisory Panels (PAPs) or equivalent are recruited and inducted in Ghana, Zambia and Malawi	Design of the PAP structures have been undertaken in all 3 countries, who will feed into the design of the community resourcing match fund.
4.2 Funded Partners receive support on diversifying income, including from community philanthropy	n/a for this period
4.3 Proportion of funded partners who have initiated alternative income generating activities	n/a for this period

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 4.1, A community resourcing match fund is established
Not met - An issue has arisen as to how PAPs fit into the existing governance structures of Anchor Partners. Therefore, Programme Advisory Panels (PAPs) or equivalent have not been recruited and inducted in Ghana, Zambia and Malawi. This relates to the recommendation in last year’s report: “Enable locally based grant makers to design, commission and lead on in country governance structures (or repurpose existing successful governance structures where they exist) rather than imposing externally designed structures that are likely to be inappropriate / ineffective”. It is the view of some of the Anchor Partners that their already existing grant making structures are sufficient for decision purposes. To enable thorough and in-depth discussions given the complexities of the n this programme, a review of the governance arrangements was undertaken, and a draft paper produced. This paper seeks to set out in one place how and where decisions will be made - what is often called the governance arrangements of a funding programme and it sets out a series of recommended actions that would need to be made to ensure that this governance structure works well. This draft is feeding into the ongoing reflections with Anchor Partners on this matter. Once progress has been made and the PAPs confirmed, Comic Relief is confident of being on-track to hit end of year 5 (2025) targets around the delivery of the community resourcing match fund.

Indicator 4.2, Funded Partners receive support on diversifying income, including from community philanthropy
Not measured in this AR - In line with the planned implementation schedule for this programme, the Community Resourcing Match Fund has not yet started and there are no milestones anticipated for this period.

Indicator 4.3, Proportion of funded partners who have initiated alternative income generating activities
Not measured in this AR - In line with the planned implementation schedule for this programme, the Community Resourcing Match Fund has not yet started and there are no milestones anticipated for this period.

Ongoing discussions about the most appropriate governance structure have caused some delays in confirming the governance approach for each of the funds. However, Comic Relief sees both the process and content of these discussions as central to living the principles of the programme, and a key source of learning. Therefore, the resulting governance structure will ultimately be stronger and more effective than the PAPs as originally envisaged in the Business Case and reflect more equitable funding practice.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Summary of recommendations from Yr 2 (2021-22)	Progress March 2023
Participation and shifting power in grant making require Comic Relief to: plan carefully to enable sufficient time for participative processes to be truly representative and meaningful, particularly where co-design is involved;	There has been and continues to be ongoing discussion about governance structures within the programme’s grant making, and how to find the best practice balance between the governance as envisaged within the Business Case and existing practices within the Anchor Partners.
As implementation begins review programme risk appetite and review the risk register	The Programme Lead participated in the RINGO Risk and Compliance Group. This was seeking to re-imagine risk and compliance so that power imbalances, and the lack of mutual trust and understanding which currently permeate the current system are reformed into funding practices that lessen the burden of risk and compliance requirements from local CSOs to a more equitable system. A prototype was developed. / The RINGO project under which, the prototype was designed, came to end last year and is now held by WACSI for this programme. Over the next year, Comic Relief and Anchor Partners will focus on how to embed the prototype into the programme.

Lessons learnt for this year
The complexity of this programme has taught that decision making/governance is equally complex. A one size fits all approach will not work because of the multiple accountabilities that stakeholders in the programme have and for the governance structures developed to reflect the shifting the power principles. However, the overall good relationships build with Anchor Partners provides a good starting point to resolve this matter.

Recommendations for the year ahead
Recommendation	Responsibility	Completion date
Comic Relief working with the Anchor Partners should invest in alternative forms of financing including those promoting local philanthropy, matching funds etc. This will require learning from other funders that are already have this support in place and from Anchor Partners such as WACSI who are the forefront of promoting this endeavour.	Comic Relief/ Anchor Partners	On-going

Output Title	Civil society organisations define their priorities for organisational strengthening (OS)
Output number:		5	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 An organisational strengthening framework is adapted in each country to support funded partners to identify and prioritise development needs	Pilot OS framework in existing portfolios; / OS learning study commissioned	Comic Relief's Organisational Strengthening framework is currently being piloted through grant top ups for 19 funded partners of previous FCDO and Comic Relief co-funded programmes. / Comic Relief has commissioned Galvanising Africa Consult (GAC) to work with these funded partners to evaluate the framework and Comic’s application of it.
5.2 Catalyse funding provided to support civil society organisations in bid development	Catalyst Fund design initiated	Each Anchor Partner completed the design of their Catalyst Funds during the Design and Iteration phase [May to September 2022].
5.3 Number of Funded Partners who have completed assessment of OS priorities	Strengthening African Civil Society (SACS) Fund designed	Each Anchor Partner completed the design of their SACS Funds during the Design and Iteration phase [May to September 2022].

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Indicator 5.1, An organisational strengthening framework is adapted in each country to support funded partners to identify to prioritise development needs.
Met - Each Anchor Partner has their own approach to supporting funded partners to identify their OS needs. These approaches will continue to be iterated and developed within the programme and throughout Catalyst Fund cycles. Comic Relief has commissioned Galvanising Africa Consult (GAC) to evaluate Comic Reliefs OS framework and learning from this will also feed into these iterations and as such, are on track to achieve end-of-2025 targets.

We propose that output 5 has provided rich ground on which to really explore the issues and values of the Shift the Power programme, and that, while we have achieved the milestones for this period, in fact the activities contributing to this achievement have enabled more fundamental progress towards the programme’s ultimate impact of a more resilient national civil society.
The conversations Comic Relief and Anchor Partners have had to date on approaches, principles and power relations around supporting organisational strengthening – moving away from donor compliance and readiness, and towards holistic and intrinsically valuable organisational resilience-building - have been fundamental to deepening the trust and depth of our relationships. Underlying the achievement of this output, the discussion on approaches to organisational strengthening in the context of each country has enabled, and required conversations at new levels of honesty and humility about the role of funders, both ‘Northern’ and national Anchor Partners. These have set a precedent for how we intend to work together to shift power in support of civil society strengthening in each programme country, and as such we feel will catalyse progress and momentum in all communications and strategic decision-making going forward.

Indicator 5.2, Catalyse funding provided to support civil society organisations in bid development
Partially Met - The Catalyst Funds, co-designed this year between Anchor Partners and Comic Relief. Anchor Partners were given feedback bilaterally from Comic Relief on the Catalyst Fund design, but also discussed Catalyst Funds in relation to power shifting in a series of dedicated learning sessions. These included discussions on criteria for success for the Catalyst Fund, means of progression to the Strengthening African Civil Society (SACS) fund, implications of eligibility criteria for the fund (e.g., registered and unregistered organisations) and practical design features of the fund to ensure it reaches ‘beyond the usual suspects’ to civil society organisations who may often be excluded from such funding opportunities. Therefore, Comic Relief is on track to hit end-of-year 5 targets in 2025.

In terms of grant making for the CF, each Anchor Partner has outlined this process in the design developed during the interim phase and as expected the process is different and specific to each context. We have ensured that the process/system put in place is in conformity with the business case which reads “Though Comic Relief and / or the anchor partners may initially have oversight of grant decisions, we aim ultimately to allow a panel of local people to make the final decision on successful grantees from a shortlist of fundable partners”. As the issue of governance/PAPs is being resolved, Anchor Partners will have initial oversight to get this core activity going and by the time we get to disbursements of the larger SACs funds this issue will have been resolved.

Indicator 5.3, Number of funded partners who have completed assessment of OS priorities
Met - Learning sessions have also begun to explore the SACS Funds and transition from the Catalyst Funds in relation to power shifting in a series of dedicated learning sessions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Both the Catalyst and SACS Funds are central to the programme’s ambition to move away from short term project funding and towards strategic investments which have wider social and economic value long after they end. This is central to the programmes approach to value for money.

At the same time, the programme is investing in organisational strengthening for Anchor Partners enhancing the funding’s contribution to sustainable social benefits.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output in the review period. Because learning and iteration are embedded in this programme, we therefore cannot completely rule out having to make changes in response to contextual or situational matters that might arise.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Summary of recommendations from Yr 2 (2021-22)	Progress March 2023
OS Learning Study: ensure that learning from the OS Learning Study accompanying current test and learn phase of the Organisational Strengthening Framework informs ongoing design of the Strengthening African Civil Society Fund.	The consultant leading the OS study with other FCDO funding cohorts received information about this programme and its commitment to organisational strengthening as part of their context to the evaluation, and would revisit opportunities to share learning between the programmes on an ongoing basis. / Additionally, the same Comic Relief staff are involved in both the OS study and this programme’s implementation and are well placed to share learning and insight between the two. / Finally, the OS study is due to provide final learning in December 2023, such that further iterations of the Catalyst Fund can build this directly into their design.

Lessons learnt for the year
As recognised and reflected in Comic Relief’s Organisational Strengthening Principles, it is challenging for funders to move away from ‘OS as donor-readiness' and towards framing it as of intrinsic value to funded partners and led by them. This will take ongoing work for Comic Relief and FCDO to unlearn existing practices and re-learn, for funders and funded partners, how to ensure authentic organisational strengthening approaches that do not rely on power imbalance or external drivers to define and implement organisational strengthening plans.

Recommendations for the year ahead
Recommendation	Responsibility	Completion date
Build in key learning from the OS pilot study and partner experiences to ensure OS within the programme is offered, and perceived to be offered, as funded-partner led and of intrinsic value to funded partners.	Comic Relief	March 2024

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

A programme level risk register is in place (informed by risks identified in the Business Case and current in-country and global political, economic contexts and events such as the Covid 19 pandemic, the Russian/Ukraine war etc) and is reviewed with FCDO on a quarterly basis. Comic Relief continuously monitors the context in Ghana, Zambia and Malawi and includes insights from in-country anchor partners. In addition, Comic Relief’s Funding Department (formerly the Impact and Investment Department), which oversees all investments, updates its risk register each quarter. This is reported to the Executive Leadership Team and Audit and Risk Committee on a quarterly basis. Comic Relief also has a strong internal Assurance unit which oversees the management of risks including safeguarding, financial, governance, legal and reputational risk among others, across all of Comic Relief’s work.

As the severity of illness caused by Covid 19 waned, travel restrictions were lifted and COVID ceased being the major risk to the programme as it was the prior years.

In the year under review, the major risk to the programme were internal to Comic Relief leading to delays in implementation. This was compounded by the organisational restructuring which by its nature is a disruptive process. Some key staff with the institutional memory of the programme left the organisation. Other staff departures in finance were registered though not related to the restructuring process.

Further delays to implementation arose because of the long process of contracting. Shifting the Power is a new concept and practice for Comic Relief and therefore the process of contracting was not a straightforward one. Significant amount was taken to agree internally on the contents of the contract. Then more time was needed for discussion and negotiation with the Anchor Partners over the contract. The Anchor Partners had a number of concerns with the contract, although they ultimately signed, they did so and highlighted the concerns they had and requested discussion and hoped for resolution. It was agreed that a review of these would be done to undertake wherever possible amendments to facilitate ease of implementation by the APs and compliance with shifting the power principles of the programme.

The overall risk rating during the reporting period is moderate. Now that implementation procedures and processes have been developed with Anchor Partners, the risk appetite and risk register will need to be reviewed.

The table below details the key risks each of FCDO’s specific risk categories. It should be noted that the risk levels are post mitigation.

Category	Residual risk rating	Update
Operational	Major	1. Insufficient internal capacity (moderate) at Comic Relief (in teams and in systems) linked to staff turnover, parental leave and ill health to effectively oversee implementation of the Programme of work and ensure its objectives are met. Mitigation measures include: / A pool of consultants with a history of working on the programme from which Comic Relief draws upon to fill in gaps / This Programme is managed by an experienced team under the Funding Directorate which is dedicated to managing all FCDO co-funded programmes, and is supported by Comic Relief's Assurance and Finance teams. / iv. Consistent oversight from the Funding Directorate Leadership team (supported by Comic Relief's Trustees and Executive Leadership) is ensuring capacity remains at the level needed to ensure FCDO co-funded programmes are delivered effectively. v. All CR staff receive regular supervision, including check ins on capacity and objectives. / This risk was introduced during the year under review.
Strategy and context	Moderate/Minor/major	1. Attacks on civil society and closing civic space (moderate) also pose contextual risks. This programme has limited this risk by selecting countries where civic space is relatively challenged (Ghana) or is narrowing (Zambia and Malawi), rather than closed. However, significant escalation of legislative or regulatory actions to restrict civic space could limit the programme’s ability to achieve outcomes and put funded partners at risk. This risk will be mitigated over the coming year through regular engagement with in-country partners and an adaptive and flexible approach to programme design and management. / The residual has moved in this review period from major to moderate. This is because although the threat persists there has been no escalation to suggest a worsening situation in any of the countries. The one significant development was the passing of the NGO Act March 2022 of Malawi. It was welcomed by the umbrella membership coordinating body; the Council of Non-Governmental Organisations in Malawi (CONGOMA) who stated that “it will result in improved regulation and coordination of the NGO sector, hence bringing more benefits to NGOs” – https://allafrica.com/stories/202204080263.html / 2. Political context/civil unrest (minor) is a potential risk to the programme. Project activities in projects funded under this programme could be delayed or scaled-back owing to shifts in political context or civil unrest resulting in expected project results or outcomes not being met, and programme outcomes compromised as a result. Pockets of unrest were experienced in Ghana and Malawi in protest against the escalating costs of living, but these were not sustained and had no impact on the programme. Comic Relief will continuously monitor the situation in all three countries through regular engagement with in-country partners and being kept update on the situation through news channels. / This risk is a new one added during the year under review. / 3.FCDO (and/or Comic Relief) (Major) compliance requirements constrain Comic Relief’s ability to honour the programme’s values of shifting accountability away from Northern donors towards local communities (major). Mitigating actions are: Comic Relief and FCDO’s commitment to delivering the Business Case and staying true to the programme's underlying values and both partners' risk appetites continue to reflect the more experimental, iterative nature of the programme. Comic Relief’s Trustees are bought-in to the programme and its aims and have contributed to the development of the programme’s Business Case. Lastly, regular meetings between FCDO and Comic Relief will provide space for honest, open dialogue, rooted in the values of the programme. / The residual risk for this remains major.
Financial and Fiduciary	Major/ Moderate/ Moderate	1. The primary fiduciary risk during the programme delivery phase is that funds are not used for the intended purposes or accounted for properly (moderate) by Comic Relief and/or Anchor Partners. Mitigation actions include: Thorough assessments were undertaken before awarding the long-term grants to the Anchor Partners of their governance, financial health, and financial management. Reports by Anchor Partners to Comic Relief and monitoring visits will enable assessment of compliance. In line with programme objectives, Comic Relief will explore how contracted partners and grant holders can be supported to strengthen policy and practice where necessary. / The residual risk remained at major / 2. Impact of global events moderate) such as political turmoil, natural disasters, and war may lead to increased costs for funded partners to deliver their intended projects. Mitigation actions include: Comic Relief will continue to have a supportive and flexible approach with the funding, working with partners to revise project plans and budgets when budgets are significantly impact by exchange losses, inflation etc. Comic Relief will provide the necessary ongoing support to partners. / This risk was introduced during the period under review, residual risk stands at moderate. / 3. Creation of Dependency (moderate) Substantial flows of funding into the Anchor Partners has the potential to inflate annual budgets and create dependency on Shifting the Power Portfolio. Mitigation actions include: scrutinised budgets during assessment of proposals awarded to ensure the organisations sustainability is not compromised when the programme ends. Financial reports, re-budgets, and variances from budget are carefully reviewed every six months and organisational support will be delivered to partners to strengthen their organisational systems and processes, consequently leading to them being more viable and attractive for other funders. Comic Relief will work with Anchor Partners on measures including exit strategies to promote their financial sustainability beyond this funding. / This risk was introduced during the year under review. Residual risk is moderate.
Policy and Programme Delivery	Moderate/Major/Moderate	1. Failure to secure strong Anchor Partner(s) (moderate) in Ghana, Zambia and Malawi to co-design the delivery phase of the programme, or positive working relationship fails to be established, results in poor or delayed programme outputs and outcomes. Strong partners were secured in all three countries: STAR-Ghana Foundation in collaboration with the West Africa Civil Society Institute (WACSI), Zambian Governance Foundation (ZGF) and Tilitonse Foundation for Ghana, Zambia and Malawi respectively. Positive working relationships have been established with all the Anchor Partners. A bi-weekly remote learning and sharing forum has been established and other communication and engagement are held whenever necessary. Other mitigation actions include; regular in person visits starting from May 2023, calling upon FCDO Country Offices to provide in-person support if required, and, including break clauses in with the Anchor Partners’ contract to enable partnerships to cease if poor performance persists as a last and final resort. / Residual risk stands at moderate from major in the last review. This has changed because strong Anchor Partners were secured. / 2. Complexity and innovation (major) - Owing to grant holders delivering especially complex, or innovative projects, expected project results or outcomes are not met, and programme outcomes are compromised as a result. / This is a new risk introduced during the year under review. mitigation measures include: a thorough assessment of all projects prior to any funding being awarded, including an assessment of project design and grant holders' and their partners ability to deliver the proposed work. / 3. Delays in recruitment of high-quality key personnel leading to delay in delivery of some programme outputs. / The risk materialised and there have been delays to developing the Communications Influencing strategy. There was a change in this risk in the latest risk register with impact moving from major to moderate to reflect mitigation measure of putting in place, consultants to fill in the gap. By year end 2022 recruitment was concluded for all vacant posts. The Comms and Advocacy Manager began in their post on 18th January 2023. / The residual risk has remained at major since the last review.
Public service delivery and Operational	Severe	1. Cuts to the UK aid budget (Severe) could pose a major threat to the scale, scope and ultimately impact of the programme. Mitigation actions include: Commencement of UK public education on the value of this programme during Red Nose Day and other times. Comic Relief has adjusted programme implementation and budgets across three phases up to 2030. Comic Relief is engaging with other trusts, foundations and institutions to explore the possibility of co-investment into the programme. / The residual risk for this remains severe.
Safeguarding	Major	Failure to protect people from harm as a result of engaging in the programme. Local people engaged in programme are not adequately protected from harm by partners engaged by Comic Relief to (co)lead programme owing to insufficient safeguards and reporting measures in place. Mitigating actions are: Comic Relief has a comprehensive safeguarding policy, approach and practice, led by a Safeguarding Lead supported by designated Safeguarding Leads at Executive Director and Trustee levels. Comic Relief will assess prospective partners' approach to safeguarding – both their policy and practice as part of the tendering process and contracted partners will be supported by Comic Relief to strengthen safeguarding policy and practice where needed. Comic Relief’s safeguarding lead will begin work with all three Anchor Partners this year to help build and support local and cross Africa safeguarding networks. The programme design process will develop a reporting protocol between people participating in the programme design, local partners, Comic Relief and FCDO. / The residual risk remains at major.
Reputational	Moderate	1. Poor public perception of the programme and international aid by the UK public who through Red Nose Day are a major provider of funding and other support to Comic Relief generally and to shifting the power specifically. Poor perception would lead to fall in income and pressure on the government for reduced support to the programme or cut in funds for the programme. Mitigation measures include: FCDO and Comic Relief work collaboratively to ensure necessary assurance on the value of the programme is communicated publicly, proactive comms work undertaken by Comic Relief and SMART Outcomes and indicators will be carefully developed to demonstrate impact and value of work. / This is a new risk introduced during the year under review. / 2. The credibility of Comic Relief, FCDO and/or its grant partners is damaged as a result of the behaviour/actions of Comic Relief or its partners, including poor project management, the misuse of funds, a failure to safeguard people intended to benefit from the Programme or other issues compromising the successful delivery of the Programme. Mitigation strategies are in place to deal with reputational risks proactively and reactively: Prior to grants being awarded, the reputational risk is assessed as part of the assessment phase for all potential projects. Mitigating actions are recommended by the assessor. Through ongoing grant management (including monitoring visits), grant managers identify any potential for reputational risk to the grant holder, their partners, Comic Relief or FCDO and support them to mitigate this risk. Internally, Comic relief has sound organisational policies in place, as well as appropriate levels of training and guidance available to staff, to ensure no reputational risks arise from actions of staff. If a reputational risk materialises, Comic Relief has a dedicated resource to manage any issues. This included a dedicated Assurance Team with experienced risk management staff as well as a Head of Strategic Comms & Public Affairs who leads on the reputational risk management, planning and response. / This is a new reputational risk introduced during the year under review. Residual risk is moderate.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

The start of the programme was delayed by Covid 19 and the subsequent staff recruitment challenges. In the year under review progress was made in identifying the Anchor Partners in all 3 countries and implementation of the development and iteration phase begun. This was a short-term phase focused on designing the various components of the programme before embarking on the long-term phase from 2022 to 2030. The long-term phase itself is being implemented in 3 phases with the first being up to 2025. This is in mitigation of the unknown outcome of the UK governments spending review. The selected anchor partners were assessed comprehensively on several parameters to determine their readiness to be partners conceptually and in practice in terms of the shifting the power principles as well as in terms of their organisational capacities. The process of contracting of Anchor Partners for the long-term phases took longer than anticipated, which has led to delays in implementation of catalyst and SACs grant funding.

The programme’s key cost drivers will be the grants programme, including the grants made to participating CSOs, as well as the agreements with Anchor Partner(s) and costs relating to Programme Advisory Panels or other appropriate governance structures in country. There are a variety of costs that will drive each individual grant and are based on the country context.

Proactive dialogue on risks and updating delivery chain maps
Comic Relief has a reporting protocol in place for reporting serious incidents and concerns to FCDO and an agreed approach to investigation and reporting thereafter. Comic Relief and FCDO are committed to ensuring that their funded partners are protecting the people whose lives they intend to benefit. As set out in Section D, a comprehensive risk register for the Shifting the Power programme is in place and reviewed on a quarterly basis with FCDO. An up-to-date delivery chain map has been submitted for this Annual Review.

In the year under review Comic Relief has submitted to the FCDO a six-monthly progress report of good quality and in a timely manner and it has maintained proactive dialogue with FCDO on risks and other pertinent issues.

Quality of financial management
Comic Relief’s finance team supports the programme to ensure the quality of financial management is good. However, until the long-term Anchor Partner budgets were finalised and agreements awarded in December 2022 the accuracy of forecasting was challenging this year. The delay of MEL and Communications and Advocacy activities also impacted on the programme forecast. At the start of the year the programme was forecasting spending £1,487,139, which has now reduced to £940,998. To date, as set out in the table below, £788,748 of the estimated £940,998 forecast has been spent. Figures for Q4 will not be available before this report is finalised and will be reported on in the next annual review.

In addition to uncertain Anchor Partner budgets, the introduction of a new finance system at Comic Relief and the changeover of financial staff in November 2022 has led to challenges in receiving timely accurate financial reporting, particularly in the last quarter of the year. It is expected there will be an improvement in next year's financial reporting

Forecast and Actuals for period April 2022 to March 2023
	Forecast	Actual
April to June 2022 (Q1)	£85,442	£84,876
July to September 2022 (Q2)	£1,189,961	£59,575
October to December 2022 (Q3)	£ 1,262,081	£644,297
January to March 2023 (Q4)	£ 152,251

Figures for Q3 have yet to be finalised so the actual Q3 is not yet available. Forecast for Q3 and Q4 are from the Q2 forecast.

Complementing the grants programme is investment in Evaluation and Learning. This programme is designed to be innovative and will test several new interventions and approaches. Learning from what works, and what doesn’t, is identified as an important output which will contribute to the overall impact of changes in donor and CSO behaviour as intended in the Theory of Change. Investment in Communications intends to shift the narrative about aid in the UK through content produced by African film-makers and creatives and progressive messaging from the perspective of people in the programme’s target countries and the organisations working alongside them.

Comic Relief is investing significantly alongside FCDO in both grant funding and programme monitoring, learning and evaluation and management costs. This funding structure represents an exciting opportunity for FCDO to invest in an experienced grant-making and managing organisation to implement this large and complex programme.

The programme’s management costs continue to offer good value for money to the FCDO. Programme management has been designed to build capacity in country and as such, management costs help to contribute to an improved civil society ecosystem and hence programme outcomes. As the Business Case notes, the adaptive management approach means that the actual programme costs could rise should programme learning recommend changes to the implementation approach; this would be offset by the longer-term impact of contributing to the sustainability of civil society organisations.

This programme is situated within Comic Relief’s Funding Directorate alongside Comic Relief’s other programmes including those co-funded with FCDO. This enables it to benefit from good practice in grant making and management generated from across the department, as well as learning from other relevant work. Comic Relief’s commitment to learning means that budgetary resources are committed for dissemination of learning with the aim of influencing decision makers and promoting replication by others.

Asset monitoring and control
No assets have been purchased yet as no grants have been awarded this year.

All assets will be funded from Comic Relief’s contribution to each grant and therefore funded partners follow Comic Relief’s asset management policy. In line with Comic Relief policy, where capital expenditure by funded partners is approved, it must be clearly demonstrated that any assets acquired will be used during and at the end of the grant on activities in the spirit of the original grant agreement. Funded partners must have an asset procurement and management policy in place and must be able to show that no conflicts of interest exist between the parties acquiring or providing the assets, and that they comply with relevant national laws and guidelines on the disposal of assets. As part of project monitoring visits, procurement and management of assets is discussed and evidence is sought of how assets are being used and logged. Comic Relief’s Monitoring Visit guidance includes points on assessing policies and practices relating to procurement and managing assets, ensuring that project staff are confident in using these policies and procedures and that there is evidence of these being followed.

Monitoring Activities
Agreements signed with the Anchor Partners during the interim period (May to September) had very clear deliverables and provided for Anchor Partners to give a monthly update on progress being made. These updates included progress made towards the activity/deliverable and any issues, challenges and opportunities that occurred. The reports also include sharing reflections on lessons learnt in the process of execution; the focus of which could be about efforts to shift power away from donors, about grant making and fund design, about community philanthropy or anything else Anchor Partners wanted to share. The Anchor Partners were also asked to give feedback about Comic Relief by reflecting what is working well and/or not working well, and make suggestions for improvement in terms of the support being given. Depending on the issues raised this would be followed up with calls to the Anchor Partners or discussed as part of the bi-weekly meetings. This was to ensure that learning was embedded as per the programmes aims.
The agreements signed with the Anchor Partners for the long-term phase including reporting schedules as:
- 31st January to 31st March of each year
- 10th October of each year
These are timed to fit in with the reporting schedule to FCDO from CR, so that there is alignment in the reporting process and frequent requests of information/reports from Anchor Partners are curtailed and allows more focus on activities key to making impact.
The agreements signed for the long-term phase have clearly outlined monitoring processes and include:
- Commitment by both parties to embed effective learning, and to establish transparent monitoring and reporting processes.
- The Anchor Partners will take all reasonable steps to ensure any Sub-Funding is appropriately and responsibly managed and monitored in line with shifting the power principles
- Meaningful assessment of how the specific needs of girls, women, boys and men are considered, take account of the voices of both women and men.
- Work with, through and represent the diversity of communities in order to respond to their needs more effectively and strengthen accountability.
- On reasonable notice, provide access to relevant personnel, premises and records solely for the purpose of monitoring and evaluating the use of the funding.
- On the basis of the above, the shifting the power principles and the learning strategy working with the Anchor Partners, a monitoring and evaluation plan will be developed which ensures:
- The voices of those most impacted upon by poverty and injustices are heard.
- Monitoring is in keeping with Shifting the power principles and therefore
  - uses tools such as “outcomes harvesting” which are more appropriate and fitting
  - measures only what matters.
Collects only the data needed, so keeping the system simple and easy to use.
It is expected to have this in place by end August 2023. Meanwhile, monitoring will take place through reports provided by Anchor Partners and through in person visits expected to commence in May 2023.

Date of last narrative financial report	1 March 2023	Date of last audited annual statement	7 March 2023