## Annual Review Template – September 2020

Title: Shifting the Power. Strengthening African Civil Society
Programme Value £ (full life): / FCDO: £30,000,000 Comic Relief: £30,045,000 / Total £60,045,000		Review date: March 2025
Programme Code: 301034	AMP start date: 31/03/2020	AMP end date: / 9 March 2030

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	B	A	A
Risk Rating	Moderate	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/55428258.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301034/documents

A. SUMMARY AND OVERVIEW

Description of programme
The ‘Shifting the Power’ (StP) programme is a 10-year partnership between Comic Relief (CR), the Foreign Commonwealth and Development Office (FCDO) and partner organisations, referred to as Anchor Partners (APs), in Zambia, Malawi and Ghana.
[note] Anchor Partners are local civil society infrastructure organisation/s with whom Comic Relief partner with to jointly design the programme, and to provide programme management in each country. The Anchor Partners consist of: Zambian Governance Foundation (ZGF) in Zambia, Tilitonse Foundation (TF) in Malawi and STAR Ghana Foundation (SGF) and West African Civil Society Institute (WACSI) in Ghana.

The programme will invest £60 million in equal amounts to each organisation – (with CR providing an additional £15,000 to each AP in 2023 to support organisations with the rising cost of living globally) – to strengthen the capacity and sustainability of locally-led civil society organisations (CSOs) in Ghana, Zambia and Malawi. This support will focus on CSOs that are working across priority areas for both the FCDO and CR including: early childhood development, gender justice, enabling peace and security, safe and secure shelter, and mental health, but each AP has identified additional own focus areas. For example, the programme in Ghana has included access to public services, whilst in Zambia, the areas of focus have extended to climate justice and environmental degradation. Malawi remains committed to supporting CSOs working with communities on Early Childhood Development, Gender Justice, Mental Health and Safe and Secure Shelter.

The programme was borne out of and is grounded in the #ShiftThePower movement, a global mobilising force comprised of hundreds of organisations around the world seeking to tip the balance of power in the development sector. This programme enables Comic Relief and FCDO to practically support and model the impact of funding in a different - and more equitable - way, together with the Anchor Partners. By contributing to and being part of a global movement of change makers, programme partners are able to amplify messages, share learning and learn from other system change advocates and initiatives, and influence change at a scale beyond that of one single programme.

The Shifting the Power programme looks to the #ShiftThePower manifesto as a set of guiding principles (referred to as the ‘STP Principles in the report) and recommendations to the wider sector, providing value-based structure to the way that we work and engage with communities. The #ShiftthePower movement manifesto can be seen in Annex 2.

The core programme activities will be delivered via three funding streams and a comprehensive package of organisational strengthening for CSOs:
- Fund one: The Catalyst Fund (CF) has provided accessible grant funding to support small grassroots organisations that might not otherwise be able to bid for funding. The purpose was to enable the programme to reach small organisations that are new to FCDO/CR funding and therefore likely to benefit more from organisational strengthening (OS) support and enable them to create positive change in their communities.
- Fund two: The Civil Society Strengthening Fund (CSSF) is providing a mix of core and restricted funding to support CSOs with organisational strengthening and resilience, which is critical to delivering their strategic mission and achieving and overcoming some of the barriers to building organisational sustainability.
- Fund three: The Community Resourcing Match Fund (CRMF) will provide training for CSOs in alternative forms of local income generation, where any income generated locally will be matched by the fund, serving to incentivise income diversification and financial sustainability.

In addition to the above grants, a package of organisational strengthening (OS) support is being provided to CSOs and Anchor Partners, enabling them to identify and tackle the challenges that hinder them from achieving their mission and organisational sustainability.

Through these streams of work, the programme aims to address some of the negative consequences that short-term, project-focused funding can have on the ability of Southern-based CSOs to sustainably respond to the priorities of local communities. This includes the unequal power dynamic between donors and funded CSOs that shapes such funding and weighs the donors’ priorities above those of local communities.

The intended impact is that CSOs in Ghana, Zambia and Malawi are more resilient, independent, and effective in responding to the priorities of local communities. The programme will deliver on four principal objectives:
- Locally led, Southern based CSOs will be supported to become more effective, sustainable and better able to represent local priorities around key thematic areas in Ghana, Malawi and Zambia.
- The FCDO’s partnership with CR will work more strategically through jointly funding a programme that will span five annual matched appeals (rather than developing a new programme annually) and 10 years of programming.
- Working collaboratively with African storytellers, filmmakers and creatives, this programme will enable CR and FCDO to communicate a progressive narrative to the United Kingdom (UK) public, demonstrating how aid is enabling local communities to pursue their own priorities and to stand up for their rights.
- The programme will be innovative and adaptive. It will generate learning on the efficacy of different interventions, designed to advance organisational capacity and resilience which will be influential in programme design within CR, FCDO, other funders and amongst CSOs themselves.

‘This funding I would call it a miracle. It’s a game changer for our organisation because in as much as we had the idea of a project, we didn’t know how to run our finances effectively… But through the Catalyst Fund, our capacity has been built”
(Interview, Executive Director, Zambia, 16th July 2024).

Summary supporting narrative for the overall score in this review
The overall score for this review is A, which is informed by progress made towards the six outputs of the programme, the majority of which have been substantially exceeded, exceeded and met. Only Output 6 was substantially not met, scoring a C, with further detail provided below.
Exceeded – Output 1 (StP partners (CR, FCDO, APs) align their practices to StP principles (#ShiftThePower Manifesto for Change): The Catalyst Fund (CF) implementation mostly took place in the previous reporting period, but the impact, reflections and lessons learned from the process have been realised in this reporting period. The CSOs in all three countries funded through the CF had positive feedback about the nature of the grant-making process, which they regarded as in line with StP principles, and eight case studies have been provided which describe this feedback. Two reflection sessions, one in Malawi and one in the UK, also revealed an improvement in partnership dynamics between the FCDO, CR and the three contracted APs.
Exceeded – Output 2 (Evidence and learning from new or different funding models that engage and strengthen Shift the Power principles and their impact on CSOs): The learning agenda was thoroughly reviewed and updated; and valuable learning products produced across partners including bespoke research reports, learning briefs and online learning sessions held within each country and across the programme. The indicator captures nine of these learning products. Unlike other programmes that use traditionally extractive monitoring and evaluation methods with upward accountability, StP is a learning programme that centres collaboration and equity across partners. This is exemplified this year in the collaborative approaches to the recruitment of the in-country research partners, the design and co-creation of convening sessions, the shared responsibility and decision-making of the learning subgroup and the special bilateral learning visits between Anchor Partners.
Substantially Exceeded – Output 3 (More authentic representation of how civil society contributes to their communities): A long-term joint communications strategy was developed, and we have provided examples of five high quality collaborations between APs, funded partners and communities, including a Shifting the Power UK Parliamentary reception. A substantial amount of authentic content has been created or co-created with African content creators and influencers this year, using community voices in formats ranging from poems to articles in national newspapers, with 16 examples shared in the report.
Met – Output 4 (Local or community philanthropy is supported across civil society): There were no milestones for this review period for Output 4 – around local or community philanthropy being supported across civil society. However, we provided an update on last year’s milestone and have therefore graded this as Met.
Met – Output 5 (Civil society organisations identify their priorities for organisational strengthening): All three APs continue to regularly review and revise their OS frameworks. The CF has been completed in all three countries, with more CSOs supported through organisational strengthening than originally planned; and the CSSF is making excellent progress but is at slightly different stages of implementation in each country, due to a focus on shifting power and commitment to quality, rather than speed, as required in each different context.
Substantially did not meet – Output 6 (StP programme financial forecasting improves): This was not met this year for a number of reasons. The key reason is that the initial annual financial forecast was developed using a planning approach that has since been updated and improved amongst programme partners. Partners have since agreed steps to improve financial forecasting with strong links to programme planning and updating payment schedules accordingly, however the impact of these improvements will only be felt in future years as the indicator and targets are based on the initial annual forecast and could not be adjusted during the year. Additionally, there have been slight delays with the roll out of the CSSF in Malawi and Zambia. However, the variance between forecast and spend has already improved compared to the previous reporting year (30% compared to 51%), and plans are in place to further improve this output in the next reporting year, with a prioritisation to holding regular finance sub-group meetings, joint financial and workplanning across the programme and closer accompaniment from CR programme and finance colleagues.
Major Lessons:
1. Lesson 1 (from Output 1): It is important when implementing a capacity strengthening and sustainability initiative, such as the CF, that an exit strategy with a defined plan and process is put in place so that the APs are able to continue supporting funded partners as needed, whether through the CSSF or more informally, and funded partners are in a more sustainable place than when they first received funding from the CF.
2. Lesson 2 (from Output 2): Bringing a new way of thinking and doing development and humanitarian work has not been easy. One of the key challenges faced has been the lack of understanding of the power shifting approaches and principles by the various players and stakeholders. These include internal staff members of the partner and donor organisations, trustees, government institutions and ministries, civil society organisations, CBOs, the private sector and communities. It is important to continue to capture how this programme has influenced different levels of understanding of the Shift the Power principles and what it means for the sector at various levels (local, national and international), including through key learning opportunities such as the mid-term review.
3. Lesson 3 (from Output 3): As the programme enters its fifth year, the programme has expanded both in terms of its staffing (particularly on the Comic Relief side) as well as the scope of work. New staff have identified new needs in the programme, such as a Community of Practice on grantmaking and organisational strengthening, and the need for more regular communication between partners. As groups form and new focal points come into the programme, maintaining clear and consistent communication about actions, goals, outcomes, and progress throughout the year is critical to preventing miscommunication and avoiding siloed work.
4. Lesson 4 (from Output 5): The diverse nature of the CSSF partners in all three countries means there is a wide range of needs and requests which require personalised support, and managing this diversity has been a challenge in ensuring that each organisation receives the attention necessary for their growth.
5. Lesson 5 (from Output 6): While resource led solutions like new finance staff and reporting templates are important, improving financial forecasting across multiple partners in an equitable and partner-led manner requires time to embed changes and build mutual understanding of each partner's financial processes and address challenges.
Recommendations:
Summary of recommendations for the year ahead	Owner	Completion Date
1. Recommendation 1 (from Output 1): Develop an after-care process in the programme and consult partners intentionally and with sufficient time.	CR, APs	March 2026
2. Recommendation 2 (from Output 2): As the programme enters the midpoint, it is important to capture the learning so far and to share this learning with local communities, CSOs, delivery partners, broader civil society, government and the private sector in all participating countries and as part of the broader Shift the Power movement. This will be through internal convening events, existing Shift the Power events, global or regional conferences and events, blogs, infographics and social media.	CR, APs	March 2026
3. Recommendation 3 (from Output 3): Initiate and deliver an internal STP newsletter to share updates, progress and opportunities. This newsletter will serve as a regular tool to keep all subgroups and partners informed and aligned throughout the year.	APs, CR	July 2025
4. Recommendation 4 (from Output 5): SGF will establish learning hubs, grouping partners based on shared needs and locations, to encourage peer learning, collaboration, and targeted support, allowing partners to benefit from collective resources while still addressing their unique requirements effectively. If successful, this approach could also be rolled out in Malawi and Zambia	SGF	March 2026
5. Recommendation 5 (from Output 6): Leverage the finance sub-group to develop context-specific forecasting approaches that balance accuracy with partners' operational realities and programme challenges and strengthen communication and planning between finance and delivery teams.	CR, APs	Sept 2025
6. Recommendation 6 – Co-design a shared programme strategy with all partners to ensure collective buy-in, input and strategic steer to the programme, as well as developing a document that clearly articulates and captures the up-to-date programmatic approach	CR, APs	Dec 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

No changes have been made to the StP Theory of Change during this reporting period; however the Mid Term Review is now underway, which may lead to changes to the ToC and logframe during the next financial year.

Logframe – Impact

Impact statement	The funding ecosystem is transformed to enable civil society organisations in Ghana, Zambia and Malawi to be more resilient and effective in delivering the priorities of local people
Impact Indicator(s)	Milestone(s) for this review	Progress
1. Civil society organisations engaged in the StP programme in Ghana demonstrate greater resilience and effectiveness.	Include in the mid-term report baseline longitudinal Indicators developed collaboratively and captured to track resilience and effectiveness over the remainder of the programme.	Expectation State has been contracted to independently conduct the mid-term review, to be completed by May 2025 with subsequent follow up collaborative work with Expectation State and partner organisations to develop longer term indicators for remaining five years of the programme.
2. Civil society organisations engaged in the StP programme in Zambia demonstrate greater resilience and effectiveness.	Same as above milestone 1	Same as above progress 1
3. Civil society organisations engaged in the StP programme in Malawi demonstrate greater resilience and effectiveness.	Same as above milestone 1	Same as above progress 1
4. Shifting the Power principles and practices are more prevalent in the UK, Ghana, Malawi and Zambia.	N/A	N/A

Indicators:

Impact Indicators 1, 2 and 3: Civil society organisations engaged in the StP programme in Ghana / Zambia / Malawi demonstrate greater resilience and effectiveness.
The mid-term review will be conducted between December 2024 and May 2025. It will collect qualitative and quantitative data through a mixed-methods approach, with emphasis on participatory evaluation techniques. While the overall evaluation framework will ensure consistency and comparability across countries, the methodology allows for adaptation to local contexts and priorities. Following completion, Comic Relief, Anchor Partners and the independent consultants will collaborate to develop a framework that balances program-wide impact measurement with country-specific indicators of resilience and effectiveness. This will enable measurement of both immediate and longer-term impacts on CSSF grant recipients, while exploring potential wider effects on civil society strengthening across Ghana, Malawi and Zambia.

Impact Indicator 4: Shifting the Power principles and practices are more prevalent in the UK, Ghana, Malawi and Zambia.
There are no milestones for this reporting period, as shifting the power principles and practices take time to become more prevalent, so these will be assessed in Year 6. The first of the three grant funds, the Catalyst Fund, has just finished and anecdotally, participating CSOs and Anchor partners view the Catalyst Fund and the Shifting the Power programme as ‘a game changer for the civil society sector’ in Malawi, Zambia and Ghana. The next action is to carry out a landscape mapping of donor practices in line with StP principles in the UK, with potential to expand to the programme countries. This will provide insights into the current state of buy in for, and adoption of, the StP Principles amongst donors.

Changes to the Impact indicators
The StP learning subgroup reviewed the logframe in August and September 2024. The new version was agreed and finalised with FCDO in October 2024. The following changes were made to the logframe impact indicators for this reporting period. Changes to the other milestones can be found in the ‘change frame’ in the updated logframe.
Logframe section	Original / detail of change	Amended statement or indicator
Impact indicator 1	Improvement in civil society organisation sustainability rating in Ghana	Civil society organisations engaged in the StP programme in Ghana demonstrate greater resilience and effectiveness.
Impact indicator 2	Improvement in civil society organisation sustainability rating in Zambia	Civil society organisations engaged in the StP programme in Zambia demonstrate greater resilience and effectiveness.
Impact indicator 3	Improvement in civil society organisation sustainability rating in Malawi	Civil society organisations engaged in the StP programme in Malawi demonstrate greater resilience and effectiveness.

Logframe – Outcome:

Outcome statement	The funding ecosystem and civil society organisations are better able to respond to the priorities and needs of communities.
Outcome Indicator(s)	Milestone(s) for this review	Progress
1 Evidence of positive steps towards change in funding practices of FCDO, CR, and APs that have resulted in increased responsiveness to the needs of the communities.	3 case studies from the delivery phase including the Catalyst Fund and set up of the Civil Society Strengthening Fund (CSSF). Each country will appear in at least one case study	Exceeded. 5 case studies drawn from learning and practice papers around the CF and CSSF: / Ghana - Peer review mechanism to make decisions on transition of CSOs from CF to CSSF / Malawi - TF’s evolving approach to shifting power / Ghana - SGF’s evolving approach to shifting power. / Zambia - ZGF’s evolving approach to shifting power. / Case study on how Comic Relief’s delivery of the StP programme has laid the foundations for shifting power to local actors.
2 Evidence of CSOs with improved capacity and financial sustainability through the various forms of funding received through the programme	Examples of how the different funds have improved capacity of CSO (annual reports and data monitoring)	Met. 7 examples/ case studies from bespoke Catalyst Fund research: / Ghana - Improved Capacity of the Nabaans Foundation / Ghana - CELDAR Foundation / Zambia - Change through Collective Action is Attainable / Zambia - Breaking the Chains of Menstrual Poverty in Petauke / Ghana - report on Organisation Capacity Assessment of Catalyst Fund Partners (SGF) / Malawi - Positive Stories of Change / Malawi - Delivery of the Catalyst Fund in Malawi
3 British public better understand and support the need to shift power to communities so that they can lead their own change	Audience insights report completed / Share insights with the sector, funders and other institutions.	Exceeded: / Audience insights report was completed. / Insights shared with funders, the wider sector and other institutions through webinars. / In addition to this CR created and launched a comms lab to directly engage other funders and INGOs in testing and utilising the insights, which goes far beyond only sharing insights.

Outcome 1: Evidence of positive steps towards change in funding practices of the FCDO, Comic Relief, and APs that have resulted in increased responsiveness to the needs of the communities.
Exceeded. The programme exceeded the required three case studies, and presents five case studies which show the progress towards changing funding practices and increased responsiveness to community needs, drawn from the Catalyst Research Fund grant partners, which are summarised here, and provided in full in Annex 4:

Ghana - Peer review mechanism to make decisions on transition of CSOs from CF to CSSF
SGF’s standard granting process involves bringing in consultants to make funding decision recommendations, and SGF would make the final decision. However, with the decision on which CF grantees to support to move to the CSSF grant, they tested out a peer review mechanism. Peer organisations that shared similar characteristics with the funded partners formed teams and met with the potential partners to understand their history and progress, then informed SGF whether they felt that organisation was ready to transition to CSSF or not. SGF expanded their grants committee to include CSOs to share in this decision-making process. This approach increased the acceptance of the outcome, particularly for those who were not selected to transition into the CSSF.

Malawi - TF’s evolving approach to shifting power
TF made significant changes this year in how it collaborates with CSO partners by embracing the StP principles. These changes emphasise equitable partnerships and co-creation in all stages of intervention. It represents a shift from the traditional model, where stakeholders are mere recipients of interventions, to one that promotes shared decision-making. Key challenges included stakeholders’ limited understanding of these principles, scepticism, resistance, and slow uptake, particularly among communities accustomed to conventional development projects. To address these issues, TF engaged stakeholders through presentations, social media publications, materials sharing, and participation in regional and international conferences. During the operationalisation of the CSSF, TF established platforms for stakeholder engagement, enhancing collective ownership and bridging the gap between CSOs and communities.

Ghana - SGF’s evolving approach to shifting power
SGF has continued to shift power in its funding practices to help CSOs better meet community needs. Examples of power shifting this year include devolving decision-making on the CF partners transitioning to the CSSF to a participatory peer review panel; introducing a funded four-month design phase to support CSSF partners in consulting stakeholders/communities and developing sustainability plans; and engaging partners in a co-creation process, starting with an inception workshop and a learning café to clarify sustainability goals.

Zambia - ZGF’s evolving approach to shifting powe
ZGF adopted a participatory approach across its programs, emphasising the StP principles to foster collaboration with local communities and empower them in participatory organisational strengthening, grant-making and project design processes. Asset-based community development (ABCD) approaches promoted community ownership and accountability, while strengthening ZGF’s responsiveness to local needs.

Case study on how Comic Relief’s delivery of the StP programme has laid the foundations for shifting power to local actors
The two case studies highlight how Comic Relief’s work on the StP programme has planted the seeds for positive change across the partnership. The first case study highlights how reimagining value-for-money, developing a learning centred approach and creating a trust-based culture has given delivery partners the freedom to deliver the grant funding in a way that is more responsive to the needs of communities. The second highlights how Comic Relief’s StP team has made strides individually and collectively to influence other parts of the organisation to become more power aware and supportive of shifting power and community-led work, thus increasing responsiveness to these communities. Comic Relief is now trying to change perceptions of “needs in the community” from the historically paternalistic narratives defined and described by the north to more authentic, nuanced community perspectives.

Outcome 2: Evidence of CSOs with improved capacity and financial sustainability through the various forms of funding received through the programme.
Met. The following outlines seven examples that show the improved capacity and financial sustainability drawn from the Catalyst Fund grant partners, which are either linked or provided in full in Annex 4:

Ghana - Improved Capacity of the Nabaans Foundation
This video features Nabaans Foundation in Eastern Ghana, outlining their story of organisational strengthening through the CF and the positive impact they have had so far on a local school, including provision of computers, library books, blackboards, water and linking them to electricity. The case study concludes that the support provided by SGF and West African Civil Society Institute (WACSI) under this programme is “testament to the boundless potential of CSOs when equipped with the right tools and support”. Note: this video was captured during a Comic Relief and British Airways visit to Ghana, as a supporter of Comic relief.
[note] Visit to Nabaans Foundation https://www.youtube.com/watch?v=IMEZVodqQkw

Ghana - CELDAR Foundation
The CELDAR Foundation, also based in Eastern Ghana, tells the story of the capacity strengthening support they received through the CF, which has positioned the organisation to be “legitimate and relevant”, with a 5 year strategy, and able to explore new opportunities.
[note] Learning event with CF partners https://www.facebook.com/watch/?v=7782192745230775

Zambia - Change through Collective Action is Attainable
[note] Change through collective action is attainable https://mailchi.mp/zgf/lets-strive-for-zero-hunger-news-for-from-civil-society?e=3d85726727&fbclid=IwY2xjawG9CfpleHRuA2FlbQIxMAABHX-KmtIKS39WVRqxlHwAfj0wAZG1TBkFKFNWCjogKJ7-u5hhmAhsB77fxg_aem_GPK3HDH_JE5h8cFXMAlrug
Kaingo ka Nyalungwa, a community-led CSO in Chimazi village, Nyimba District, was formed in 2022 by 34 residents to address local challenges. They focus on early childhood development, environmental conservation, water scarcity, educational barriers, and deforestation. They have been supported by ZGF through the Catalyst Fund. In embracing the StP ethos, Kaingo ka Nyalungwa prioritises community ownership and decision-making. By empowering community members to lead project initiatives, the organisation fosters sustainable change and long-term development aligned with community needs and aspirations.
Through strategic guidance and support from ZGF's Catalyst Fund, the organisation evolved from an informal community group into a fully registered entity with robust governance structures, including a functional board and comprehensive internal management systems.
The organization's enhanced institutional capacity enabled it to effectively manage diverse programmes addressing local challenges in early childhood development, environmental conservation, and education. Their growing organisational sophistication is evidenced by their successful implementation of multiple concurrent initiatives, including an environmental conservation project that planted over 1,000 trees to combat deforestation, and a sustainable school feeding program at Kaingo ka Nyalungwe community school.
Demonstrating increased resource mobilization capabilities, the organisation has established international partnerships, securing support from Swiss supporters who provided educational materials for their community school. This diversification of funding sources beyond the initial ZGF support indicates growing financial sustainability and reduced donor dependency. The transformation from an unregistered community group to a formally recognised institution with adequate organisational systems positions Kaingo ka Nyalungwa for continued growth and impact in Chimazi village.
Zambia - Breaking the Chains of Menstrual Poverty in Petauke
[note] Breaking the chains of menstrual poverty in Petauke https://mailchi.mp/zgf/petauke-youths-on-a-mission-of-impact-news-for-from-civil-society?e=3d85726727
Petauke Youth Bakers, a youth-led group in Petauke District, Zambia, was founded in 2022 by 21-year-old Hellen Manda and her friends, after they were introduced to sexual and reproductive health and rights through Plan International’s "Break Free!" project. Their mission is to combat teenage pregnancies, child marriages, and menstrual poverty. Petauke Youth Bakers provides menstrual products, including washable pads made from local Chitenge materials, and conducts sensitisation programmes. Due to limited resources and institutional capacity, they have faced challenges in sustaining their activities and meeting demand. For instance, they relied on hand-sewing the pads making the process labour intensive and slow. Being selected as one of five emerging CSOs for the Catalyst Fund, the support has enabled them to buy sewing machines and durable materials to expand their impact, ultimately empowering young girls to break “free from the chains of adversity”. The group has made remarkable progress, simply by the acquisition of their sewing machines. This equipment has significantly improved their production of menstrual pads, dramatically reducing the time previously spent on manual production.

The additional institutional capacity support through the Catalyst Fund - including full registration, improved financial management, updated board policies and structures, and improved community engagement & advocacy initiatives - has further enhanced their sustainability and capacity. Their improved organisational structures and increased production capacity has attracted the attention of the Petauke District Health Office, which is currently in discussions with them regarding potential supply of hospital linens and fabric materials. Furthermore, the support from the Catalyst Fund has catalysed membership growth, attracting more community members interested in developing their sewing skills to enhance their livelihood opportunities. By providing a range of support that both increased their ability to implement and deliver their services (sewing machines) and improved their overall structures (institutional capacity support) the Petauke Youth Bakers has been able to access new opportunities for the organisation for the benefit of its members and broader community.

Ghana - report on Organisation Capacity Assessment of Catalyst Fund Partners (SGF)
WACSI conducted an evaluation to compare the pre and post-capacity strengthening support outcomes to assess the impact of the organisational strengthening support. The partners assessed themselves on seven thematic areas: Leadership Structure, Working Practices, Human Resources, Finance, Community Engagement, Partnerships, and Sustainability. The tool enabled the CSOs to identify their current organisational stage, starting from lowest capacity to highest:
0-29% (Critical)	26-50% (Striving) 51-75% (Thriving) 76-100% (Viable)

There was significant progress between the baseline and endline assessment scores, revealing a significant improvement in organisational capacity. For example, of the 11 partners who were at the Striving stage at baseline, 10 advanced to the Viable stage by the endline after 12 months. At endline, all partners were either Thriving, or Viable, with none scoring low enough to be either Critical or Striving. This progress can be attributed to the partners' progress in all the thematic areas because of the capacity strengthening received, their ability to meet their targets and their successful development and institutionalisation of all the policies and procedures outlined in their priority action plan. A few of these partners have begun experiencing impact/change stories, as a result of participating in the CF project. Full results are presented in the case study. These efforts have increased the legitimacy and credibility of partner organisations, thereby positioning them for partnerships with new funders, including private sector organisations. As of July 2024, 30% of CF organisations reported progress towards broadening their funding base and increasing their financial sustainability. For example, Dynamic Works Foundation (DWF), a CF partner, secured its first major grant from KGL Foundation to support teenage mothers’ re-entry into schools in the Oti region; and FoRD Ghana has signed a service contract with Catholic Relief Services for a period of 5 months, but likely to be renewed for 3 to 5 years.

Malawi - Positive Stories of Change
Five positive stories of change from CSOs who received CF funding are included in this umbrella case study, covering:
1. Mutisunge AIDS and Community Development Support Organisation, who had an inactive Board, had not received funding since 2017 and minimal engagement with the district council due to lack of ongoing activities. The CF enabled them to strengthen their organisation and formally register, becoming active again, joining a project consortium with other CSOs, receiving funding from AIDSFONDS in the Netherlands.
2. Kachila Youth Initiative, who used the CF to transform their policies and financial management, and formally register, carry out community and stakeholder mapping. As a result, they received a grant from Amplify Change to implement a sexual and reproductive health rights (SRHR) project worth over £71K.
3. Neno Active Youth in Development used the CF to address major governance and technical skill gaps, including proposal writing; and transformed their policies. This resulted in a substantial grant from Save the Children, showcasing their newfound ability to navigate complex due diligence processes.
“The Catalyst Fund is essential for small grassroots organizations, offering vital resources and support to enhance our capabilities. Continuing the Fund will help more organizations gain the training and tools needed to expand their impact and drive sustainable change in their communities.” - Moses Chabuka, NAYODE’s Executive Director.
1. Concerned Youth Organisation was able to formally register through the support of the CF. They also created a strategic plan and boosted their financial and safeguarding policies and protocols. As a result, they negotiated a five-fold increase in their annual grant amount from their usual donor, Commonwealth of Learning. They then secured funding from OXFAM for a five-year project, Save the Children for an 18-month project and IM Swedish Development Partner for a one-year project.
2. Umunthu Radio Station used the CF to set up their operations and structures, hire their first Finance Officer and began collaborating with the District Health Office to compile and update relevant mental health data. They have also secured grants from Amplify Change and Share Net International on menstrual hygiene and safe abortion, respectively.

Malawi - Delivery of the Catalyst Fund in Malawi
TF provided grants of up to GBP 5,000 to 23 CSOs for six-month organisational strengthening funds through the CF. The grants were able to help local CSOs develop effective proposals for further funding and strengthen their capacity to access support from other development partners. Key achievements included the legal registration of ten organisations; helping organisations to establish governance systems, financial procedures and strategic plans; the supported CSOs were able to secure additional funds from other sources, leveraging improvements in financial management and improved systems; and engage with local communities in collecting data and designing projects, to ensure their needs were met.

The results of Outcome indicator 1.2 demonstrate effectiveness and excellent value for money, particularly given that support from the CF enabled some funded CSOs to leverage additional funding from other donors, which will have a positive impact on their financial sustainability.

Outcome 3. British public better understand and support the need to shift power to communities so that they can lead their own change.
Exceeded. Audience insights report was completed, and insights were shared with funders, the wider sector and other institutions through webinars and presentations and the programme took one step further through engaging other INGOs to test how to adapt their messaging through a bespoke communications testing lab.
Following the delivery of the audience insights research in the previous financial year – which presented a detailed examination of the British Public’s understanding on localisation and aid – Comic Relief looked at ways to disseminate this research as part of its broader influencing aims of bringing the wider sector, funders, and other institutions along on this journey.

In July 2024, Comic Relief hosted a 2-hour webinar with the audience insights researchers from the Development Engagement Lab (University College London (UCL) and University of Birmingham). The researchers presented findings on how to communicate the "Shift the Power" message to the UK public and Comic Relief shared how these insights informed the Red Nose Day 2024 Campaign. Over 30 funders, including Gates Foundation, Eleanor Crook Foundation, FCDO and Chanel participated in the session, which offered research-backed insights to help funders communicate development issues differently to the public.

As part of our post evaluation, attendees shared, “This session was incredibly informative. It has made us think about how we can tell stories and the frames we might need to use to do so." Another funder stated,"It is fantastic that a high-profile funder like Comic Relief takes the lead on this kind of work. Communication and storytelling are not our bread and butter, so seeing Comic Relief begin to work in this way gives us confidence to try!"

In November, Comic Relief presented the research findings at an event hosted by the Gates Foundation, during which Comic Relief shared the results of the original research, outlined the challenges Comic Relief faced in communicating STP messaging to the British public, and demonstrated how Comic Relief applied these insights and recommendations in last year’s Comic Relief Red Nose Day Night of TV content. The event was attended by senior policy and communications officials from the FCDO, senior staff at the Gates Foundation, and representatives from 45 UK-based NGOs. The presentation was well-received and sparked numerous follow-up conversations. Notably, Save the Children was inspired by the presentation to join the STP Communications Lab, detailed in the following paragraphs.
Beyond simply sharing insights with the sector, Comic Relief took proactive steps to drive meaningful action. In November 2024, Comic Relief launched a step-up initiative, actively engaging six leading NGOs—WaterAid, Christian Aid, Plan International UK, Save the Children, ADD International, and HelpAge—in a hands-on testing initiative: the ‘Shifting the Power Communications Lab.’ Rather than just presenting findings, Comic Relief incentivised these organisations to put the audience insights into practice. Through this initiative, participants were encouraged and supported in testing new, innovative ways of communicating aid and development narratives with their own audiences, ensuring real-world application and impact.
Each participating organisation received up to £5,000 in funding, alongside coaching support and opportunities for peer collaboration, to test messaging and content with their audiences. Comic Relief is also participating in the lab, which moved into the delivery phase following design workshops held in December. Between January and May 2025, participants will focus on designing and delivering their content. In the summer, all participants will reconvene to share their findings and present their tests, which will then be shared more widely across the sector.

Comic Relief also welcomed the H&S Davidson Trust as a new partner in the lab, supporting our broader efforts to reform international development (note: their funds will be used to cover additional communications initiatives to disseminate their work and learnings).

Changes to the Outcome indicators:
There are no changes in the outcome indicators for 2024.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to contribute to the expected impact and outcomes. The Logframe Impact indicators are on track, with strong signs that civil society organisations engaged in the StP programme in Ghana, Zambia and Malawi will demonstrate greater resilience and effectiveness. APs and Comic Relief will be working with the mid-term review consultants to develop baseline longitudinal indicators and strengthening programme delivery and approaches based on recommendations. The Logframe Outcome indicators are also on track, with case studies showing evidence of change in the funding practices of CR and APs that have increased responsiveness to the needs of communities provided; numerous examples of CSOs with improved capacity and financial sustainability as a result of the programme; and good progress towards influencing British public about the need to shift power through the programme's communications and influencing how other key NGOs and donors communicate about their work.

In this reporting year, three new CR roles for this programme were successfully recruited, a Head of StP Programme, a StP Finance Manager, both based in the UK; and a StP Programme Manager who was based in Malawi (but resigned at the end of 2025; recruitment for her replacement is complete and they are set to join in April 2026). Following the departure of the previous Programme Lead in early 2025, a new Lead, based in Zambia, also joined the team. Together this has resulted in a more robust programme and financial management team to support the APs and the wider programme objectives.

Actions planned for the year ahead include:
- Continued roll out of CSSF across all AP countries. Capacity strengthening work will continue through the CSSF to ensure that CSOs increase their resilience and effectiveness.
- Feedback from the sector, funders and other institutions on the Audience Insights Report, which was compiled by CR, will be used to continue with proactive communications to enable the British public to better understand the need to shift power to communities.
- Research into community philanthropy and other resource generation models in preparation for CRMF.
- Co-design of a programme strategy following MTR recommendations to strengthen and further refine programme approach and delivery with all programme partners.

Justification on whether the programme should continue, based on its own merits and in the
context of the wider portfolio

CR and the APs recommend that the programme continues, based on the fact that all of the Outcome indicator milestones have been met or exceeded in this reporting period, with many positive changes in funding practice documented in the learning and practice papers from the CF; evidence of improved capacity and financial sustainability in supported CSOs; and dissemination and utilisation of the audience insights report, which is an important step towards the British public supporting the need to shift power to communities. Further achievements are outlined in the following section on Detailed Output Scoring, which provide substantial additional justification for the continuation of the programme.

## C. DETAILED OUTPUT SCORING

Output Title	StP partners (CR, FCDO, APs) align their practices to StP principles (#ShiftThePower Manifesto for Change)
Output number:		1	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of APs successfully contracted	Three	Met. Three APs are still contracted.
1.2 CSOs feedback that the grant-making process and support was in line with StP principles including demonstrating key outcomes of their work (#ShiftThePower Manifesto for Change)	6 case studies from Anchor Partners (2 per country) that explores both positive and negative feedback from various CSOs reflections about their use of StP principles	Exceeded - 8 case studies provided: / Ghana: Shifting Power in Grantmaking: Experiences with Design Phase Grants / Ghana: Positive Feedback about the Grant-Making Process and support through the CF was in line with StP principles. / Malawi/Zambia: CSO Feedback that the grant-making process and support through the CF was in line with StP principles. / Zambia/Malawi: Feedback from CF partners that the self-assessment tool was in line with StP principles / Ghana: Cashew Watch Ghana / Zambia: The Healing Balm Foundation / Malawi: Concerned Youth Organization / Zambia: Feedback from CSOs during Expectation State research
1.3 The partnership between Comic Relief/FCDO and Anchor Partners is assessed and demonstrates change in line with the Shift the Power principles over time	Reflection session on partnership (FCDO, CR, APs) and how the partners are working together including power dynamics in the partnership. Feedback indicates improvement in partnership dynamics.	Exceeded. The partnership went beyond conducting one reflection session and conducted two as well as developing a partnership health check methodology which provides rigour and structure to the sessions and enables progress to be tracked over time. / The partners reflected on what equitable partnerships looks like for the StP programme at the Malawi convening event. The session utilised the partnership assessment to gauge how the partnership had progressed and areas of improvement. / The partnership health check at the UK convening showed how the StP principles are being used to change power dynamics in the partnership. There were also very high scores overall from the pulse survey check, indicating that this milestone has been exceeded.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 1 is A+. Indicator 1.1 has been met, 1.2 has been exceeded and 1.3 has been exceeded, giving an overall score of Exceeded (A+).

Indicator 1.1, Number of APs successfully contracted

Met. There are three Anchor Partners still in place - Zambian Governance Foundation (ZGF), Tilitonse Foundation (TF), and STAR-Ghana Foundation (SGF). Notably, in Ghana, SGF collaborate with the WACSI, who serve as the organisational strengthening lead, and collaborate equally as an AP in the design, learning and communications work of the programme. Contract amendments are expected to be completed shortly (March/April 2025) to make some of the contract requirements more enabling of or easier to understand by APs. Comic Relief has also amended the language of the contract to provide more assurances to the APs of the grant commitment to 2030, giving them more confidence to provide longer term grants under the CSSF to their funded CSO partners based on 5 year-long organisational strengthening plans. Comic Relief is also voluntarily transferring over an increased share of its budget to APs to hold for enhanced local decision making, e.g. budget line for in-country learning research partners and external influencing.

Indicator 1.2, CSOs feedback that the grant-making process and support was in line with StP principles including demonstrating key outcomes of their work (#ShiftThePower Manifesto for Change)

Exceeded. Eight case studies are provided, above the six case studies required, which demonstrate the StP-principled grant-making process and key outcomes of the CSOs’ work:

Ghana: Shifting Power in Grantmaking: Experiences with Design Phase Grants
In 2024, SGF piloted a 4-6 month design grant with 26 CSOs to provide financial resources to CSOs at the stage of developing and planning their projects. Some CSO partners used this grant to convene internal and external discussions, hold workshops or expert consultations. Others used it to commission studies and scoping analysis into sustainability strategies they could pilot. Others used it to support board and team reflections to come up with sustainability roadmaps. SGF found that supporting CSOs with funding to cover their costs during the planning and design phase is key to enabling power shifting in grantmaking, as it gave them the time and resources to collectively diagnose their situations, generate solutions and co-design their projects with their constituents. A CSO representative reflected “Unlike most restricted funding opportunities that already come with fixed frameworks of objectives and focus areas, this was more relaxed and open and ensured that organisations designed interventions they needed and not to necessarily design interventions to fit into the already designed framework which on grounds may not yield the needed impact. Indeed, it was a significant shift of power to growing organisations to position themselves much better in the development landscape”.

Ghana: Positive Feedback about the Grant-Making Process and support through the CF was in line with StP principles.
When the CF work ended, SGF held a feedback and evaluation session with CF partners. This information has been captured in a learning event report. CSOs shared examples from the CF of how the principles of StP have been employed within their organisations, for example enhancing ownership of the newly developed or revised policies which were co-created; supporting communities to identify the resources they possess and building on local resources and assets; and challenging the dominance of English and using first languages to enhance the understanding and participation of communities. The learning event itself also increased their knowledge around the StP principles and approaches used by other organisations.

Malawi/Zambia: CSO Feedback that the grant-making process and support through the CF was in line with StP principles.
Bespoke research was carried out by the Kabod Group in Ghana, who are aligned to the StP principles. The aim of the research was to carry out a study on the experiences, innovative practices, successes, challenges and key lessons learnt from implementation of the Catalyst Fund (CF), using structured interviews with grant partners and APs. Throughout the report, each STP principle was referenced as the researchers used a #STP lens to assess the CF. They found that the CF was instrumental in shifting power towards grant partners, through co-creation and equitable decision-making, changing the approach from “due diligence” to “knowing your partners”; through the languages adopted by the APs in communicating with partners; a focus on strengthening organisational capacity of grassroots organisations; shifting power within grant partners’ organisations, and also in shifting power from the partners to the communities through their active participation in decision-making processes.

Zambia/Malawi: Feedback from CF partners that the self-assessment tool was in line with StP principles
Funded CSOs under the CF in Zambia and Malawi provided positive feedback about the organisational capacity self-assessment tool, which they found to be highly aligned with StP principles. CSOs conducted self-assessments of their organisational capacity and financial management using provided tools. These self-assessments then formed the basis for in-person meetings between the CSOs and AP staff for a joint organisational capacity assessment, prioritising mutual learning and the creation of an honest, thorough, and CSO-owned document. These collaborative assessments, conducted at the CSO's premises to foster a comfortable environment, facilitated discussions about the organisation's systems, resources, and activities. This process allowed the APs to gain a deeper understanding of the CSOs’ self-perception while prompting the CSO to reflect on its actual capacity through the APs’ questions and input. CSO partners expressed appreciation and satisfaction with the opportunity to identify their own OS needs through self-assessment tools.
Ghana: Cashew Watch Ghana
Cashew Watch Ghana (CWG) was a loose network who advocated for the rights and livelihoods of cashew farmers. The CF enabled them to formally register as a legitimate entity in Ghana and strengthen their capacity and governance, which in turn has enabled them to reach the cashew farming community with training and support around financial management and resource mobilisation. CWG has been able to influence policy decisions and shape sectoral discourse in the cashew sector in Ghana; if successful this will ensure the needs of cashew farmers are addressed in national development plans.

Zambia: The Healing Balm Foundation
The Healing Balm Foundation (HBF) focuses on amplifying citizens’ voices in public resource management and addressing social issues through innovative inclusive initiatives, with a focus on climate change. The CF provided the HBF with training on advocating effectively, identifying allies and ensuring meaningful community participation; financial management; proposal writing; and M&E. The CF transformed the HBF into a more empowered effective entity, and it has been successful in obtaining a large grant from GIZ and the EU as a result. HBF’s inclusive approach to projects has led to a more meaningful participation of community members in identifying and addressing the challenges they face.

Malawi: Concerned Youth Organization
The Concerned Youth Organisation (CYO) is focused on empowering marginalised children, youth and women in Malawi, but lacked proper systems and policies, and relied on small grants which only enabled them to undertake short term projects with minimal impact. The CF enabled CYO to undertake a comprehensive self-assessment using the Organisation Capacity Assessment (OCA) tool, and as a result develop policies including safeguarding, equal employment opportunity and sexual harassment, and systems that they didn’t have previously. This strengthened CYO’s credibility with donors and they have since received a significant five-year grant from Oxfam, as well as grants from IM Switch Development Partners and Save the Children. Before receiving the CF, CYO were reaching around 1000 people; they have now been able to expand their reach to 4000 people.

Zambia: Feedback from CSOs during Expectation State research
ZGF employs innovative mechanisms to enhance community participation. For instance, CSO staff provided feedback on how simplified application processes—such as accepting proposals in local languages—have made funding more accessible to grassroots organisations. Additionally, researchers found the approach enables CSOs to allocate funds based on local priorities rather than donor mandates. Such flexibility represents a significant shift toward empowering communities as decision-makers. However, CSOs provided feedback on the lack of bridging support if they did not progress on to CSSF, and it was clear there is a need to address resource dependency amongst CSOs during this programme.
Indicator 1.3, The partnership between Comic Relief/FCDO and Anchor Partners is assessed and demonstrates change in line with the Shift the Power principles over time

Exceeded. The programme was borne out of and is grounded in the #ShiftThePower movement, a global mobilising force comprised of hundreds of organisations around the world seeking to tip the balance of power in the development sector. The Shifting the Power programme and all programme partners look to the #ShiftThePower manifesto as a set of guiding principles (referred to as the ‘STP Principles in the report) and recommendations to the wider sector, providing value-based structure to the way that we work and engage with communities. The #ShiftthePower movement manifesto can be seen in Annex 2. The principles were used as a guiding structure to assess the partnership within this programme.

The programme held its 3rd convening event in Malawi in April 2024 and the 4th convening event in London in October 2024. The convenings are critical opportunities for programme wide reflection, strategic thinking and planning, and relationship building across all partners. Each convening has been hosted by one of the Programme partner organisations and reflects the programme’s intention to promote and demonstrate equity. Beyond the work that is being done, the distribution of hosting responsibilities reflects the way the APs and Comic Relief are working intentionally as equal partners.

The programme partners utilise the convening events as opportunities to regularly reflect on the partnership. At the Malawi convening event, the partnership reflected on what equitable partnerships looks like for the StP programme, in line with the StP principles mentioned above. The session utilised the partnership assessment to remind attendees of where the partnership strengths and challenges were in 2023 and to gauge how the partnership had progressed since then. As part of this review, Comic Relief and Anchor Partners conducted a ‘start, stop and continue’ exercise to highlight ways to further entrench equitable ways of working and partnership, which the partners continue to track over time.

During the October 2024 convening the partners agreed to dedicate a half day to the partnership, facilitated by an accredited Partnership Broker. The broker worked collaboratively with all of the partners to co-design a partnership health check survey built upon the partnership attributes that all partners felt were important to reflect upon and built upon the reflections from the Malawi convening. The survey was carried out in advance of the convening event, with responses from 13 APs and 7 funded partners. The survey results demonstrated high scores overall, with little variation between each area. The highest scores were for meeting participation, commitment to mutual support and outcomes for communities. The lowest scores were on listening, governance system, and the partnership reflecting the principles of #StP; but all still scored above 6.4/10.

During the convening session the partners gathered in three groups to discuss how to strengthen the partnership across three areas they collectively agreed to be of greatest importance or need to strengthen:
  - Power dynamics & challenging ‘status quo’ approaches
  - Listening & ensuring people feel heard
  - Communication frequency & content

The groups developed key takeaways and actions, such as co-designing a programme strategy document that reflects the AP’s contextualised vision for the programme; addressing the biggest blockers to change, such as stringent compliance requirements; developing a log of feedback to improve transparency; streamlining communications requests; and creating an internal newsletter to share information. The key outcome was that the partners agreed that the health check is a valuable exercise and have committed to do this regularly, which will not only ensure that the programme partners dedicate effort to ensuring the quality of the partnership but also can track changes to the quality of the partnership over time.

Comic Relief has taken several other steps to increase its accountability to the APs and actively foster an equitable partnership dynamic. This includes inviting AP representatives to sit on interview panels when recruiting CR staff working on the StP programme and inviting AP staff to take part in 360 performance review feedback for CR StP staff. Furthermore, through participatory decision making and consultative approaches, Comic Relief and the APs agreed on moving the management of certain budget lines, for example to fund the in-country research partners, from CR to the APs’ budgets. This decision was taken by the Strategy and Governance Sub-Group, a StP sub-group composed of the AP CEOs and deputies, CR Head of the StP programme and Programme Lead. This sub-group features a rotating chair and decision making by consensus, ensuring that APs have equitable decision making over key programme decisions.
Additionally, Comic Relief has amended its reporting templates to enable space for formal feedback on the partnership. The following details some of the written feedback from Anchor Partners to Comic Relief in their reports. SGF shared that “We co-lead with CR on many aspects of the programme delivery. An example is the sub-groups, where APs play influential leading roles, alongside CR. We have also shared spaces with CR to engage other stakeholders on this programme, an example is the APs and CR session at the 2024 African Philanthropy Assembly. Again, for the first time in the partnership, we co-created the 2024 annual report. In every step of this partnership is evidence of improvement in co-leadership and learning.”

TF’s feedback on the partnership with CR was “Over the reporting period, the power dynamics in the partnerships with Comic Relief and FCDO have evolved positively. The continued engagement and information sharing, alongside joint efforts in co-creating templates and documents for the CSSF, efforts to collaboratively work to roll out the CSSF have all fostered a more friendly, collaborative and engaging environment. The Foundation's active involvement in recruitment for key staff positions for Comic Relief such as the Programme Lead, Programme Manager and Project Manager, and consultations on important programmatic matters such as the development of the programme strategy have contributed to a stronger sense of ownership and partnership in the programme.” Specific practices that have helped build more equitable relationships in the Malawi programme include the regular updates, critical friend reviews, and joint decision-making processes on key matters such as budgeting, risk management, and safeguarding. These practices have ensured that all parties have an equal say in shaping the programme and its implementation, fostering a sense of shared responsibility.

Like TF, ZGF welcomed the opportunity to be more involved in the recruitment of CR consultants and staff. ZGF also found that the regular communication from CR regarding various influencing opportunities and networking spaces, as well as regular convenings and subgroup meetings, were all helpful for building more equitable relationships. They felt the Strategy and Governance sub-group, which is now holding regular meetings, has helped in clarifying aspects of partnership effectiveness and decision making.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output demonstrated equity by supporting CSOs through grants and organisation who might not otherwise be funded to develop their systems and processes, which is likely to result in greater impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output during the past year, and none planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
Equitable partnerships – Using the findings from the partnership assessment, continue to embed the StP principles in the partnership and improve ways of working.	The partnership assessment, started in March 2024, was used to guide the Malawi convening discussion focusing on equitable partnerships. / Building on the Malawi convening, during the London convening, the partners underwent a partnership health check, guided by findings from a partnership survey completed prior to the convening. Details on these sessions and improvement in partnership dynamics are outlined above in Output 1, Indicator 1.3
Collaboration across the delivery chain – Further develop inclusive collaborations with all stakeholders in the delivery chain including local CSOs funded and supported through the programme to disseminate the StP principles to the broader CSO sector.	This recommendation crosses over with how APs have adapted to have CSOs more involved in all funding processes. / The learning report on the Catalyst Fund highlighted that the APs' approaches were very enabling and inclusive towards local grantees in line with StP principles. Furthermore, the CF enhanced or enabled organisations to involve and engage community members in project design and implementation. In the words of one grantee, through the CF, they "engage the communities and ensure that their interests are paramount in what [they] are doing. [They] have now made localisation or locally led development a core approach in [their] work’’. / In Ghana, throughout the partnership process, SGF have been making efforts to ensure StP principles underline the programme. In the report template at the end of a partnership or phase report, SGF asks how CSOs are incorporating StP principles into their work.

Major lessons and recommendations for the year ahead:
Lessons learned this year.
1. Lesson 1 – It is important when implementing a capacity strengthening and sustainability initiative, such as the CF, that an exit strategy with a defined plan and process is put in place so that the APs are able to continue supporting funded partners as needed, whether through the CSSF or more informally, and funded partners are in a more sustainable place than when they first received funding from the CF.
2. Lesson 2 – It is important to recognise, as funders and APs, that there are other programmes besides the StP programme, and time allocation to other activities should be mutually respected to ensure that the work does not negatively impact on the other work/programmes of partners.
3. Lesson 3 – It is important to manage expectations as shifting power takes time and there will not be immediate results. In the meantime, there may be small wins, there may be no wins at all and/or there will be a more sizeable change over the medium to long term.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
Develop an after care process in the programme and consult partners intentionally and with sufficient time.	CR, APs	March 2026
To ensure that partners are encouraged to give honest constructive feedback about the partnership, structured feedback mechanisms should be introduced, including bi-monthly meetings and anonymous surveys.	APs, CR, FCDO	March 2026
Utilise bi-annual programme-wide convenings to document incremental changes in power dynamics and organisational strengthening	CR, APs, FCDO	Convening dates tentatively scheduled for May 2025; Nov 2025

Output Title	Evidence and learning from new or different funding models that engage and strengthen Shift the Power principles and their impact on CSOs
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Learning agenda developed and iterated in collaboration with programme stakeholders	Learning agenda reviewed and updated with learning collaborators	Met. The entire learning programme was reviewed and updated with the learning collaborators at the Ghana learning event from 10-11 February 2025.
2.2 Learning products disseminated and produced based on the evidence and learning from new funding models that leverage Shift the Power principles and strengthen impact of CSOs	5 learning products e.g. research report and blogs about learning through the programme (to be determined by learning agenda)	Substantially Exceeded. 9 learning products provided: / Catalyst Fund Evaluation / CR’s position in the Shift the Power ecosystem research / Malawi - Patsinde event of the CF. / Ghana - Report on baseline and endline analysis of Catalyst Fund Partners. / Ghana - Assessment Report of the CF Partners Initiative / Zambia - Blog: Lessons from the Catalyst Fund / CR: Blog: “Walking the talk on Shifting Power: why and how change is possible” / London convening summary report / APN Convening blog
2.3 Equitable and high-quality learning collaborations formed on key programme components	4 examples (Learning coordinator appointed, bespoke research completed, and additional research collaboration formulated)	Substantially Exceeded. 7 examples provided: / Catalyst Fund Research Management / Recruitment of in-country research partners / Inclusive practices for the midterm review / Convening sessions Co-Created by CR and the APs / Learning Sub-Group Convening in Ghana / Ongoing Learning sub-group co-created meetings (9 online, 2 in person) / Chipata meeting between ZGF and TF

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 2 is A+. Indicator 2.1 was Met, and Indicators 2.2 and 2.3 were substantially exceeded, giving an overall score of Exceeded (A+).

Indicator 2.1 Learning agenda developed and iterated in collaboration with programme stakeholders
Met. In February 2025 the StP Learning subgroup convened in Kasoa, Ghana for two days. Ten colleagues from the five delivery partner organisations (2 per organisation) came together, along with the learning coordinators from the Kabod Group, to review and update the learning agenda and activities across the programme and plan the learning activities for the second half of the programme. A specific session was held with the Comms and advocacy subgroup to explore ways to further enhance collaboration and to intentionally embed ways of working across the two subgroups. The comms and advocacy strategy highlights that the ‘Comms and Advocacy Subgroup will collaborate with the Learning Subgroup to draw out evidence, case studies and material to ensure our communications has a strong evidence base. The Learning Sub-Group will also support in developing approaches to monitor and learn from the effectiveness of the communications outputs.

Indicator 2.2 Learning products disseminated and produced based on the evidence and learning from new funding models that leverage Shift the Power principles and strengthen impact of CSOs
Substantially Exceeded. The learning products reflect the diverse and broad scope of the StP programme, capturing the broader learning across the UK, Zambia, Malawi and Ghana, and the more specific in-country learning across the four countries.

Catalyst Fund Evaluation Report
Conducted by the learning coordinators for the StP programme - Kabod Group - the evaluation drew out the successes and challenges of the Catalyst Fund and provided recommendations for future, similar intervention. The report summary was shared with programme partners at the London convening event. Additionally, the research case studies were used in the ‘Shifting the Power’ booklet distributed at the high-level event in London, UK and will be used as subsequent advocacy opportunities such as conferences and workshops.

CR’s position in the Shift the Power ecosystem research
This research looks at the landscape of donors working on shifting power or localisation initiatives and then focuses on analysing Comic Relief’s Shifting the Power programme team. It reflects on the way the team works and how these fits in the context of the localisation and Shift the Power movements. It has found that there are many different ways that Comic Relief’s StP team have planted the seeds of shifting power with programme partners, within Comic Relief and in the sector. The report will be shared across partners of the StP programme and a session will be hosted by the researchers to discuss and work through the findings and recommendations in March and April 2025 and used by Comic Relief in particular to improve its ways of working.

Malawi: Patsinde learning event
Patsinde is TF’s learning platform. The Patsinde event was a review of the Catalyst Fund process with TF, alongside the CF awardees, local CBOs, and other stakeholders. CF funded CSOs held various speaking slots during the event. For example, the Sacramento Sisters of Bergamo in Mangochi reflected that TF wanted to see them and hear from them directly, rather than just reading their proposal; they found TF’s power-shifting approach to be friendly and encouraging. TF shared and captured the experiences from the Patisnde learning event on multiple Facebook posts including videos that captured the experiences of CF partners. Below are quotes from just two of the 12 TF Facebook video posts.

“Their (TF) approach built trust and we really carried out our deliberations with confidence because their approach was friendly and they were encouraging us.“ Sr. Florence M’meta, Sacramento Sisters

“After we started the Catalyst Fund, we also managed to get about three grants from different donor communities…..The £5,000 from the Tilitonse Foundation has helped us to generate over £100,000” Edward Kuwacha, Umunthu Radio Station

Ghana - Report on baseline and endline analysis of Catalyst Fund Partners
WACSI conducted a baseline and endline analysis of CF partners using the self-assessment tool, which is one of tools used by the programme to shift power from the APs to the CF partners. Completing the self-assessment tool enabled them to assess their technical and organisational strengths and influence. This self-administered tool provided a comprehensive picture of the partners' organising capacity, operational resilience, and sustainability. By completing the self-assessment tool, WACSI understood the capacity needs of these partners and designed well-tailored capacity-strengthening sessions to address these needs, rather than imposing generic training on them. The comparison between the baseline and endline assessment scores reveals a significant improvement in organisational performance. More details on the results of this report in terms of improvements in capacity and financial sustainability are described under Outcome 2, case study 5.

Ghana - Assessment Report of the CF Partners Initiative
Star Ghana contracted two separate, independent consultants to assess 19 CSOs who participated in the Catalyst Fund (nine in Central, Greater Accra, Eastern and Volta regions, and 10 in Northern, Upper East, Ashanti, Bono, and Savannah regions). Each produced a summary report for their respective cohort of CSOs and insights on each CSO in detail.

In the cohort of nine:
- 62 new policies, manuals, guidelines and measures were produced.
- 100% of the products the CSOs committed to in their performance plans were completed with 95% found to be satisfactory or sufficient. Three CSOs produced additional products above and beyond the performance plans.
- All the nine organisations have formed, revised or reconstituted functioning boards.
In the cohort of 10:
- 9 out of 10 of the CSOs became fully registered CSOs.
- The CSOs constituted new governing boards or revamped existing bodies through the Catalyst Fund support.
- All 10 CSOs developed key organisational policies and procedure manuals with support from the Catalyst Fund including Strategic Plans, Financial Manuals, Safeguarding Policies, Monitoring and Evaluation Manuals, Code of Conduct Manuals, Board Charters, and Constitutions.

Both independent assessments showed significant improvement for all participating CSOs. The reports were used to help inform which CSOs had the capacity and potential to continue to the second fund - the Civil Society Strengthening Fund (CSSF). Combined, ten CSOs were recommended for transition to the CSSF.

Zambia - Blog: Lessons from the Catalyst Fund (yet to be published)
ZGF’s M&E Specialist reflected on the lessons learned in a blog post. Themes explored in the blog include: the power of time, or the lack of it; breaking language barriers; when local communities invest, sustainability thrives; procurement is a necessary but frustrating process; and trust in the selection process of CSOs.

The key takeaways highlighted in the blog include to allow more time for implementation to reduce partner fatigue and continue language inclusivity to empower local organisations. Furthermore, to encourage local financial contributions to enhance sustainability, streamline procurement processes to avoid unnecessary delays, and strengthen selection processes to build trust and transparency.

CR: Blog: “Walking the talk on Shifting Power: why and how change is possible”
[note] https://www.linkedin.com/pulse/walking-talk-shifting-power-why-how-change-possible-tania-cheung-qfqje/
CR’s Head of the STP programme wrote and disseminated a blog reflecting on the learning from the London convening on LinkedIn. The blog includes reflections on the impact of the CF, the partners’ challenging questions to further their commitment to shifting power, and reflections on how to genuinely create an equitable partnership dynamic. The blog quotes one of the convening participants: “To realise genuine change, a shift in power must happen at an atomic level, within all of our organisations, throughout the hierarchy of our institutions, across organisational culture, and within every individual.”

London convening summary report
The summary report reflects the activities, discussions, reflections and learning from the convening event held in the UK. The report has been circulated to all convening event participants.

African Philanthropy Network blog
In November 2024, Comic Relief and Anchor partner representatives attended the Africa Philanthropy Network Assembly in Victoria Falls, Zimbabwe. The Assembly aims to ‘facilitate the sharing of experiences, new knowledge, and collective reflections on the development of Africa’ and to ‘collectively promote the voice and action for African philanthropy.’ The Shifting the Power Programme hosted a community dialogue session at the assembly exploring what it looks like to upturn traditional power structures in funding relationships, the challenges in navigating funding structures while maintaining core principles and integrity, and the work that is still needed to achieve transformative change. Partners interacted with participants attending the assembly and raised awareness of the good work that is in progress.’ The Shifting the Power Programme Lead at Comic Relief summarised and shared learning from the assembly and the event on a LinkedIn blog here. Her key reflection was that “when we talk about #ShiftThePower as a movement, we need to look beyond formal power structures to address informal rules and dynamics that shape how resources flow and decisions are made”.
[note] Reflecting on Power Dynamics in Development - When Movement Building Meets #ShiftThePower https://www.linkedin.com/pulse/day-three-apnassembly2024-reflecting-power-dynamics-henry-hgyse/

Indicator 2.3 Equitable and high-quality learning collaborations formed on key programme components
Substantially Exceeded. The Shift the Power principles form the core ways of working across the programme including the Learning subgroup, which includes at least one representative from each AP organisation and CR. Throughout the year, the Learning subgroup has worked on a range of activities collaboratively, inclusively and equitably. These include:

Catalyst Fund Evaluation Research Management
The Catalyst Fund evaluation was collectively steered by all the APs and CR.

Recruitment of in-country research partners
At the Malawi convening event in April 2024, the learning subgroup reviewed the overall budget and allocated resources for a local, in-country research partner in Malawi, Ghana and Zambia. The subgroup co-created the terms of reference to ensure continuity but also included minor amendments to fit the local context in each country. Each country used their own, internal recruitment methods and processes to fit their local contexts. Originally, the budget was held by Comic Relief, but after consultations at the UK convening event, the decision was made for each Anchor Partner to oversee and manage the budget and contract in-country, reflecting the flexibility of the programme and ability to shift resources and decision-making more locally. There was a collaborative approach to recruitment of research partners.

Inclusive practices for the midterm review
Anchor Partners have been involved in the design and delivery of all aspects of the midterm review, As of February 2025, this includes:
- The terms of reference were co-created with Anchor Partners
- The shortlisting and interview panels included representatives from three Anchor Partners and Comic Relief
- The drafting of the interview questions were agreed upon collectively by the interview panel
- The inception report included input from all partners equitably

In practice, the current delivery of the midterm review reflects the collaborative, inclusive, democratic and equitable way Comic Relief and Anchor Partners aim to deliver the programme learning. The focus of the midterm review goes beyond a funder’s reporting requirement with the hope that the outputs will be useful for all partners in the programme, for local CSOs and communities, and for the broader influencing of the INGO sector.

Convening sessions Co-Created by CR and the APs
At the two StP convening events, the learning sub-group planned and delivered various sessions. This included sessions at the Malawi convening event around equitable partnerships and sessions at the UK convening reflecting on the Catalyst Fund and looking forward to the CSSF.

Learning Sub-Group Convening in Ghana
In February 2025, the learning sub-group convened in Kasoa, Ghana. At the UK Convening event in October 2024, the learning sub-group highlighted that more in-person collective work was needed to review, update and progress on the learning agenda. In Kasoa, the 10 representatives from the five delivery partners reflected on the programme learning so far. The group workshopped ways to better capture and embed learning within each country and across the programme and how to capture this learning effectively. A set of 27 actions and priorities were agreed on centred around three themes - learning, coordination and visibility/support to the broader StP programme.

Ongoing Learning sub-group co-created meetings (9 online, 2 in person)
These meetings are structured to ensure equitable ways of working including rotating chairs and open agendas, and co-creation and shared delivery of the learning sessions at the convening events. Equally important is the collaborative and democratic practices of decision-making. These sessions are opportunities for subgroup members to interrogate different learning activities and decide collectively on a way forward.

Chipata meeting between ZGF and TF
In 2024, ZGF and TF convened in Chipata, Zambia. Titled the Chipata Accord, this collaborative initiative provided an opportunity for the two partners to share the challenges, successes and learning from the delivery of the Catalyst Fund. At the Chipata Accord, participants discussed and workshopped themes around the development of a participatory monitoring and evaluation model, how to address local language challenges, development of their advocacy and communications work, how to develop greater staff reflection on context and deeper issues of communities, and how to creatively use feedback mechanisms. ZGF and TF used the learnings from the accord in the current design and implementation of the CSSF.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The StP programme learning subgroup reviewed the logframe in 2024. The changes to output two can be found in the updated logframe’s ‘Change frame’ tab and were approved by FCDO in October 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
Translate the immeasurable strength of the partnership into tangible activities - To translate the immeasurable strength of the partnership into practical delivery of the programme including ways of delivery and reporting that ensures partners are all accountable to their audiences.	The CF Evaluation Report captures strong aspects of the partnership and the practical elements that contributed to it, including APs taking time to co-design programmes with grantees. / The APs are involved in writing and directly delivering the six-month presentation for FCDO as well as shaping the Annual Review via a “writeshop”. The APs also create their own case studies.
Focused learning – Now that the foundations for learning across the programme have been co-created and established, more focused or themed learning is required to capture progress. In the upcoming year, focus will be on learning from future grant funds including the CSSF and the CRMF.	The CF Evaluation was completed. / Additionally, in-country learning partners have been recruited. The research partners will focus on gathering learning related to specific principles within the StP manifesto, which will feed into a wider piece of learning by the Learning Coordinator. The in-country learning partners are: / Zambia - Laria Consultancy / Ghana - Bureau of Integrated Rural Development (BIRD) / Malawi - Institute of Public Opinion and Research / The process of translating CF learning to CSSF is underway, as a result of bespoke CF research and bespoke funder research. In 2025-6 the research thematic focus will be on studies to inform the design of the CRMF.

Major lessons and recommendations for the year ahead:
Lessons learned this year.
1. Lesson 1 The importance of intentional and embedded learning practices - The programme is now entering the peak delivery phase. This phase is where significant learning and adaptation will take place. It is important to ensure the learning is captured, shared and the programme adapted in a timely manner and to embed learning across the programme.
2. Lesson 2 The understanding of Shift the Power principles and practices varies - Bringing a new way of thinking and doing development and humanitarian work has not been easy. One of the key challenges faced has been the lack of understanding of the power shifting approaches and principles by the various players and stakeholders. These include internal staff members of the partner and donor organisations, trustees, government institutions and ministries, civil society organisations, CBOs, the private sector and communities. It is important to continue to capture how this programme has influenced different levels of understanding of the Shift the Power principles and what it means for the sector at various levels (local, national and international), including through key learning opportunities such as the mid-term review.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
Build in more opportunities to share and capture programme wide learning within each partner organisation, in each country and across the programme.	CR, APs	Jan 2026
Generate more outward facing outputs. As the programme enters the midpoint, it is important to capture the learning so far and to share this learning with local communities, CSOs, delivery partners, broader civil society, government and the private sector in all participating countries and as part of the broader Shift the Power movement.	CR, APs	March 2026

Output Title	More authentic representation of how civil society contributes to their communities
Output number:		3	Output Score:	A++
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Equitable and high-quality collaborations with APs, funded partners and communities to enhance their work	Long-term joint comms strategy developed / 3 examples of collaborations (tbd once the long-term joint comms strategy work plan is finalised)	Exceeded: Long term joint comms strategy developed, and 5 examples of collaborations, including: / Bi-weekly Sub-Group Meetings / Scottish International Development Alliance Spring Conference / Catalyst Fund Close Out Event / African Philanthropy Network Conference / Shifting the Power UK Parliamentary Reception
3.2 Authentic content created or co-created and produced with African content creators and influencers	2 pieces of content produced (tbd once the long-term joint comms strategy work plan is finalised) / 2 pieces of in-country programme content from each Anchor Partner country (6 in total)	Substantially exceeded. 16 pieces in total: 3 pieces of content from CR, 3 from TF, 6 from ZGF and 4 from SGF. / Comic Relief: / Red Nose Day 2024 Social Media Posts / Blog by CR on StP Learning convening in Malawi / Programme-wide STP Programme Handbook / Malawi: / Catalyst Fund Articles / Catalyst Fund Success Stories (Videos) / UNIMA Theatre Festival / Zambia: / Climate Change Poet spotlight / Newsflash Articles / Catalyst Fund in Daily Nation Newspaper / Media Engagement / Shifting the Power Cafes / Documentaries on Catalyst Fund Success / Ghana: / CSSP/ STP Fact sheet / Mini docuseries on Catalyst Fund Success / Social media engagement on STP / STP Poem, launched at the STP parliamentary reception

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 3 is A++. Indicator 3.1 was exceeded, and Indicator 3.2 was substantially exceeded.

Indicator 3.1 Equitable and high-quality collaborations with APs, funded partners and communities to enhance their work

Exceeded

Bi-weekly subgroup meetings: The Communications and Advocacy subgroup has continued its bi-weekly meetings, a routine firmly established. Following the Malawi Learning Convening in May 2024, the group co-created an agenda and introduced a rotating chair system. This has bolstered its governance, equity, and collaboration, fostering shared responsibility for chairing, coordinating, and working towards shared goals. The Terms of Reference (ToR) for the Communications and Advocacy subgroup was also co-created, drafted, and finalised. 18 online sub-group sessions and two in-person sessions all chaired and organised collectively.

Scottish International Development Alliance Spring Conference: In April 2024, Comic Relief’s Communication and Advocacy Manager and the Executive Director of WACSI attended the Scottish International Development Alliance (SIDA) Spring Conference in Edinburgh where they participated in a panel on locally led approaches to global justice. They discussed decentralising power, money, and resources in development, while highlighting key learnings from the StP programme. After the event, organisers expressed appreciation for Comic Relief and WACSI’s contributions, noting the eye-opening insights shared –‘Thank you for your excellent contribution to our panel on locally led development. The eloquent exposition of the journey that Comic Relief has made was eye- opening for many in the room and very much appreciated.’

Catalyst Fund Close Out Event: The Communications and Advocacy subgroup successfully hosted and delivered a ‘Catalyst Fund Close-Out’ event, which showcased learnings and achievement from the Catalyst Fund. The team co-created the agenda, guest list, and presentations, while giving a platform to Catalyst Fund partners to present and share their stories of change, impacts made and reflections. The event featured contributions from Anchor Partners, Comic Relief, and Kabod Group including for the first-time presentations from Catalyst Fund grantees. The event was attended by 96 people.

African Philanthropy Network Conference: During the APN Conference hosted in Zimbabwe, Comic Relief and Anchor Partners successfully hosted and facilitated a session exploring the question: ‘is it possible to dramatically change deep-rooted inequities in the philanthropy ecosystem, dominated by major power brokers?’ The panel included representatives from SGF, WACSI, TF, ZGF and CR. The group offered diverse perspectives from funders, intermediary organisations, and local civil society organisations. The discussion contextualised the StP programme's learnings to exemplify broader themes in shifting power dynamics in development funding. By focusing on the concrete experiences and learnings from the StP programme, this session provided tangible insights and sparked broader discussions about transforming power dynamics in development funding.

Shifting the Power Parliamentary Reception: Comic Relief hosted a StP parliamentary reception in London to celebrate, amplify and hear directly from the local leaders at the heart of the programme. This event was an opportunity to reflect on the progress made, share the key learnings and recommendations from the first four years, and celebrate the impact of over 69 grassroots organisations. With Ministers, local leaders, funders and global development advocates in attendance, the evening marked a critical moment in advancing sustainable development and promoting community-led solutions. Comic Relief CEO, Samir Patel, emphasised that this programme “disrupts the status quo, shifting resources and decision-making into the hands of those who understand their communities best.”

International Development Minister Anneliese Dodds delivered the keynote address, stating, “It’s incredibly important that the voices of communities are always heard. Partnership must be genuine and based on respect, especially with people in the Global South. We need to make sure that we truly shift the power in the direction of supporting communities globally.” The AP CEOs were encouraged by the Minister's support and prioritisation of locally-led development.

The event featured poetry, music, and art created by local communities in Malawi that captured the essence of the StP movement and brought to life the programme’s core themes of empowerment, resilience, and community leadership. It was a vivid reminder that development is not just about funding—it’s also about human stories. The interactions throughout the evening fostered important discussions about the future of localisation and how we can continue to drive progress over the remaining six years of the programme.

Indicator 3.2 Authentic content created or co-created and produced with African content creators and influencers

Substantially Exceeded

Comic Relief:
Red Nose Day 2024 Social Media Posts: In March 2024, Comic Relief received strong public reception for the George the Poet climate film produced and edited by African content creators Beautiful Stories. The film aired on the BBC on March 15th, garnering 4.1 million views (the highest viewing ratings) during the "Thank You" moments. The film’s success stemmed from its authentic portrayal of community stories, in line with audience insight recommendations. On LinkedIn, the film received 3,022 impressions, 151 engagements (67 likes, 10 reshares, 74 clicks), and a 5% engagement rate—exceeding CR’s internal benchmarks. On Instagram, it achieved 3,913 views, 108 engagements (101 likes, 6 saves, 1 comment), and a 2.6% engagement rate—again, close to CR’s internal benchmark of 3%. (Please note this content was published and aired after the submission of the previous Annual Report, but the outcomes and statistics were not available prior to the previous Annual Report submission)

Blog by CR on StP Learning convening in Malawi: The blog was published and featured in TF’s quarterly newsletter and shares insights into the learnings and reflections shared by partners, as well as authentic content which included a spotlight on CF partner visits. Link to blog here.
[note] Community Governance Action, A Tilitonse Foundation Newsletter: Issue 8, 2nd Quarter 2024 https://drive.google.com/file/d/1TCcuY3h4WsizjV5lREqUHthRzD1tgg29/view

Programme-Wide StP Programme Handbook: The StP programme handbook was developed collectively with the Communications and Advocacy subgroup, steered by Comic Relief, and highlights the collective efforts and outcomes of the StP programme. The handbook offers a comprehensive overview of the programme, showcasing its objectives, progress, and impact. It features a profile of all partner organisations involved, underscoring the strength and diversity of our collaboration. The handbook outlines the milestones achieved and issues a powerful collective call to action, urging stakeholders across sectors to support localised approaches in humanitarian efforts. This call emphasises the necessity of shifting power dynamics to create more equitable and effective responses. Three case studies from the CF are spotlighted featuring images taken by local photographers; these case studies demonstrate how targeted funding, and local leadership can yield significant, scalable outcomes. The handbook concludes with actionable recommendations derived from the programme's experiences and building on those within the #ShiftThePower movement. These recommendations serve as a guide for policymakers, donors, and practitioners to continue supporting and scaling the StP model. The handbook was launched and unveiled at the StP Parliamentary reception and has been disseminated both digitally and via hard copy format. It has also been presented at key forums such as the African Philanthropy Network Conference and in partner countries, ensuring wide reach and engagement. This handbook is a testament to our collective journey and a blueprint for future initiatives aimed at shifting power to local actors.

Malawi:
1. Catalyst Fund Articles: “The Catalyst Fund: Experiences from Malawi”, a feature article that was published in the two main daily newspapers in Malawi and two main weekend newspapers. The article was authored by Robert White, CEO of TF and gave an overview of the CF and its impact. Link to article here.
  [note] The Catalyst Fund: Experiences from Malawi https://tilitonsefoundation.org/storage/2024/08/Tilitonse-Foundation-newspaper-article-ver3.pdf
2. Catalyst Fund Success Stories (Videos): TF produced documentary video footage collected from visits to CF grant partners. The videos focus on the partners’ experience rolling out the CF, some of which are featured in the case studies for Outcome 1.2.
3. UNIMA Theatre Festival: Tilitonse has been intentional in collaborating with local artists and storytellers to advocate for community-driven philanthropy, mindset shifts, and systems change, all with the goal of achieving sustainable, locally led development in Malawi. Recognising the unique power of the arts in addressing complex and contemporary issues, the Foundation is exploring innovative ways to use creative storytelling to communicate ideas about power dynamics, development, and aid in an accessible and engaging manner for local communities. Tilitonse supported the University of Malawi’s (UNIMA) Theatre Festival in November 2024, and the CEO of Tilitonse delivered a speech about the Shifting the Power programme and principles emphasising the importance of local stories that authentically represent local communities. The festival brought together diverse participants, including secondary school drama groups, college performers, and professional acts, alongside visual artists, storytellers, and musicians from across the creative arts.

Zambia:
1. Project Dreamworld Poetry Competition Feature: Building on the success of the Project Dreamworld poetry competition last year—highlighted by the inclusion of a poetry film during Red Nose Day 2024— in March 2024 ZGF followed up with a special feature celebrating Tendy Heaven, the winning poet from Zambia. In their weekly Newsflash, ZGF conducted an intimate conversation with Tendy, delving into her experience with the competition, her journey as a poet, and her reflections on climate change and the role of young people as leaders in addressing global issues. [Link to Newsflash article] (Please note this content was published after the submission of the previous Annual Report)
  [note] Meet Tendy Heaven: Our poetry competition winner https://mailchi.mp/zgf/serving-the-earth-knowing-its-worth-news-for-from-civil-society?e=%5BUNIQID%5D&fbclid=IwY2xjawG9CbRleHRuA2FlbQIxMAABHZuKTjzViL199Lik6cHPSsPqv0DZRFyii9oNSVtRn7Uc6gLGMBJiO-868w_aem_Z7bQhxgTiUwvzPT69AIh7w
2. ZGF Newsflash Articles: Wrote and published articles in the newsflash about the work of Catalyst Fund partners and how they are actively contributing to development in their local communities. The newsflash is ZGF’s flagship weekly newsletter which features news for and from civil society, sharing analysis on important topics affecting civil society as well as updates on events and opportunities. These features have highlighted the impact of the Catalyst Fund on local grassroots organisations, such as the Healing Balm Foundation in Zambia, which leveraged the Fund to attract additional funding. This is an example of a Newsflash Article here. The ZGF newsflash is currently Zambia’s leading CSO newsletter.
  [note] Change through collective action is attainable https://mailchi.mp/zgf/lets-strive-for-zero-hunger-news-for-from-civil-society?e=3d85726727&fbclid=IwY2xjawG9CfpleHRuA2FlbQIxMAABHX-KmtIKS39WVRqxlHwAfj0wAZG1TBkFKFNWCjogKJ7-u5hhmAhsB77fxg_aem_GPK3HDH_JE5h8cFXMAlrug
3. Catalyst Fund in Daily Nation Newspaper: ZGF published an article about the CF in Zambia's Daily Nation newspaper. This increased visibility and understanding of the CF's role in supporting local CSOs. Link to article here.
  [note] 25 Zambian CSOs in £4,000 boost from UK https://www.pressreader.com/zambia/daily-nation-newspaper/20240126/281509346062186?srsltid=AfmBOoq6lZfCbEnAw-JI08a1lvngxhvm4Rtyxgp7bjtrPp0vX5V9B-te
4. Media Engagement: ZGF organised a media breakfast and engaged various media outlets including newspapers, TV stations, and radio. The event introduced local media to the programme and helped them gain an understanding of how to tell authentic, community-driven stories. Stories were featured in major outlets like Times of Zambia, Zambia Daily Mail, Daily Nation, The Mast, KBN TV amplifying the visibility of the Shifting the Power programme and the importance of the approach.
5. Shifting the Power Cafes: ZGF has been hosting Shifting the Power Cafes which are lively and interactive pop-up stands to communicate shifting power with locals through informal discussions and Q+As, quizzes and sharing scenarios and stories of change. ZGF ran these cafes at national events in Lusaka including the Conservation Careers Fair 2024. Through the cafés, over 50 young people were engaged, raising awareness of the programme, and encouraging youth involvement in advocacy for shifting power. This involved working on a partnership with the Southern African Leadership Centre to introduce Shifting the Power to youth.
6. Documentaries on Catalyst Fund Success: ZGF produced a series of documentaries showcasing the progress of organisations benefiting from the CF. This provided authentic, visual content that highlighted the positive outcomes and real-world impact of the fund on local CSOs.

Ghana:
1. CSSF/STP Fact sheet: This fact sheet was developed to demystify the StP programme. It discusses the StP concept, why it matters, how StP principles influence programme delivery, and examples of shifts in power within SGF’s partnerships. See link here.
  [note] STAR Ghana Foundation Shifting The Power Programme Fact Sheet https://drive.google.com/file/d/1G4dVPCC-WQFeO1ARu2qeGHIzOpG6Cu5H/view
2. Mini docu-series on Catalyst Fund Success: SGF developed compelling documentaries that showcased the achievements of organisations supported by the CF. These authentic visual narratives highlighted the fund's tangible impact on local CSOs and their communities, emphasising positive outcomes and success stories. Examples can be found here.
  [note] Visit to Nabaans Foundation https://www.youtube.com/watch?v=IMEZVodqQkw
3. Stories of change and marking of programme milestones: SGF and WACSI gathered inspiring success stories and articles showcasing authentic content from CSSF/STP partners’ interventions and collective learning. These stories highlight the creativity, resilience, and unique perspectives that drive impactful narratives across Ghana. Examples can be found here, here and here.
  [note] CSSP-StP Partners Thrilled by Progress of Joint Endeavours in Ghana https://wacsi.org/cssp-stp-partners-thrilled-by-progress-of-joint-endeavours-in-ghana/
  [note] Ghanaian CSOs Strengthen Resilience and Sustainability at WACSI and STAR-Ghana Learning Café https://wacsi.org/ghanaian-csos-strengthen-resilience-and-sustainability-at-wacsi-and-star-ghana-learning-cafe/
  [note] CSSP Partners inception meeting - Shifting the Power for collective impact https://www.star-ghana.org/latest-news/628-cssf-partners-inception-meeting-shifting-the-power-for-collective-impact
4. Amplifying local voices and learning on Social Media: In the past year SGF and WACSI have amplified stories of change, spotlighted funded partners and shared learning from the programme across a range of different social media platforms. This included showcasing compelling documentaries that illustrated the achievements of organisations supported by the Catalyst Fund. In addition to this, SGF and WACSI also shared inspiring success stories and articles showcasing authentic content from partners interventions. These stories highlight the creativity, resilience, and unique perspectives that drive impactful narratives across Ghana. The posts have had positive engagement, with over 500 likes, 100+ comments, 90+ reshares and has surpassed internal benchmarks indicating a strong rise in engagement on Shifting the Power content. Examples can be found on Facebook and LinkedIn.
  [note] CSSP-StP_Learning Event, Kumasi, WACSI Facebook https://www.facebook.com/watch/?v=1668057560665380&rdid=OsvOUBkzvDWCxzva
  [note] WACSI Linkedin https://www.linkedin.com/posts/wacsi_civil-society-strengthening-fund-orientation-activity-7234568414424424448-iDFb/?utm_source=share&utm_medium=member_desktop
5. STP Poem launched at the STP parliamentary reception: Developed and performed a poem at the Shifting the Power UK Parliamentary Reception to echo and bring to life the Shifting the Power principles and our call to action. See link here.
  [note] The Change We Want: A ShiftThePower Manifesto Poem https://www.youtube.com/watch?si=Ho25hM680uK1kmyB&sfnsn=wa&v=eP-19XaF4IU&feature=youtu.be

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output strongly demonstrates the effectiveness of communications created by programme partners and co-created with community voices.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the past year, and there are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
Long- term storytelling - continue to grow relationships with local content creators, grassroots communities and start designing and curating stories that captures change over the length of the programme. Drawing on the focus from the audience insights and seeing evidence that StP delivers and is value for money is crucial for public comms and strengthening the collective influencing for the programme.	Building on the audience insights work, the StP programme has launched a 'Shifting the power Comms Lab' to develop new narratives around aid and its work and actively apply the research. This initiative will partner with leading UK INGOs to enable them and CR to test new ways of communicating with the public and storytelling; with a learning report to capture and disseminate findings. As part of the long-term comms strategy, we will continue to build relationships with local content creators to support with spotlighting and showcasing stories of change.
Thematic approach - the focus will be to take a thematic approach, create a long-term comms plan and work closer with local communities to ensure they are accurately represented.	The Advocacy and Communications subgroup developed and launched a collective influencing brief and a long term comms plan in 2025. The communication strategy included a thematic approach to showcase stories, content and messaging to wider audiences.

Major lessons and recommendations for the year ahead:
Lessons learned this year.
1. Lesson 1 - Effective storytelling can resonate deeply with communities and reflect their unique cultural contexts, ensure that their stories feel relevant to local audiences, giving partners a sense of ownership and pride as they express their struggles and celebrate their triumphs.
2. Lesson 2 - As the programme enters its fifth year, the programme has expanded both in terms of its staffing (particularly on the Comic Relief side) as well as the scope of work. New staff have identified new needs in the programme, such as a Community of Practice on grantmaking and organisational strengthening, and the need for more regular communication between partners. As groups form and new focal points come into the programme, maintaining clear and consistent communication about actions, goals, outcomes, and progress throughout the year is critical to preventing miscommunication and avoiding siloed work.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
1. Continue to develop relationships with local content creators to showcase/ amplify authentic stories of progress and/ or change.	CR, APs	Jan 2026
2. Initiate and deliver an internal STP newsletter to share updates, progress and opportunities.	APs, CR	July 2025

Output Title	Local or community philanthropy is supported across civil society
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 A Community Resourcing Match Fund is established	N/A	There are no milestones for this review period, however, the milestone for this indicator (“Programme Advisory Panels or equivalent are recruited and inducted in Ghana, Zambia and Malawi”) which was not achieved in the previous reporting period has now been fully achieved in all three countries, so we have given an output score of A.
4.2 CSOs receive support on promoting community philanthropy including income generation	N/A	N/A
4.3 Proportion of CSOs who have initiated community philanthropy initiatives to address the salient needs of the community	N/A	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 4 is A. Indicators 4.1 will be reported on in Year 7, Indicator 4.2 will be reported on in Year 6, and Indicator 4.3 will be reported on in Year 9. The Output is on track to be achieved in the latter half of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
Build in the Shifting the Power principles in the implementation of the Programme Advisory Panels (PAPs) – CR will listen attentively to the perspectives of APs concerning the PAPs and how they are performing to ensure alignment with ethos and values of the programme, taking particular care that PAPs contribute to enhancing governance in APs	PAPs have been engaged at different levels during CF and CSSF roll out and implementation in all three countries. CR has been proactively engaging with APs to understand their perspectives on PAP performance in relation to the CF and CSSF, seeking feedback on PAPs' contribution, assessing PAP composition and procedures, identifying areas for improvement, and exploring collaborative ways of developing strategies to strengthen alignment.
Review the risk appetite – The StP programme has started this process with the legal team of CR to address this matter of reviewing CR/APs contracts taking into consideration limitations arising from the MOU between FCDO and CR. The work being done by RINGO on re-imagining risk should be an important part of this review and to include review of the SR 20 risk register.	Following discussions with the new Strategy and Governance sub-group, contracts have been amended to make some of the contract requirements more enabling of or easier to understand by APs, expected to be signed in March/April 2025. In particular, the amendments include changes to the language of the grant to provide more assurances to the APs of the grant commitment to 2030, giving them more confidence to provide longer term grants under the CSSF to their funded CSO partners based on 3-5 year long organisational strengthening plans. / The partners will launch a series of workshops to prompt deep reflection on reimagining risk within the programme, with the aim of ensuring the programme has an appropriate balance of whose risks are being prioritised and mitigated, and how they are being managed.

Major lessons and recommendations for the year ahead:

Recommendation	Responsibility	Completion date
1. Continue work across CR, APs and FCDO to reimagine how risk is analysed, managed and reported against within the programme.	CR, APs, FCDO	Jan 2026

Output Title	Civil society organisations identify their priorities for organisational strengthening
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – from 30% to 20%

Indicator(s)	Milestone(s) for this review	Progress
5.1 An organisational strengthening framework is adapted in each country to support funded partners to identify and prioritise development needs	OS frameworks are reviewed and revised based on learning (continue throughout programme)	Met. / All three countries are regularly reviewing and revising their OS frameworks to help them identify priorities.
5.2 Funds (CF, CRMF, CSSF) provided to support civil society organisations in their identified priority areas.	Catalyst Fund completed in Ghana, Malawi and Zambia. CSSF fund operational in Ghana, Malawi and Zambia. Approximately 20 CSOs in each country selected for the CSSF	Overall: Met / Catalyst Fund Completion (Exceeded): / The Catalyst Fund (CF) has been successfully completed in all three countries, surpassing the original targets for CSO support: / Ghana: Supported 20 CSOs / Malawi: Supported 23 CSOs / Zambia: Supported 25 CSOs / CSSF Implementation Status (Met and in progress of being met): / Ghana: Exceeded target with strong progress / 36 partners onboarded to CSSF programme / 24 agreements formally signed by end of 2024 / Significantly above the 20 CSO milestone target / Malawi: On track / CSSF call for applications launched in September 2024 / Know Your Partner field visits completed for 43 potential applicants, with 35 assessment reports submitted to PAP for review. / Grants Committee will review on March 12th, with board approval expected on March 13th. / Contracting to begin immediately thereafter. / Expected to meet the 20 CSO target by end of March 2025. / Zambia: Progressing in phases / First round: 11 CSOs successfully selected / Second round of selection planned to reach 25 CSO target to be completed by end of July 2025.
5.3 Number of funded partners who have completed assessment of OS priorities.	OS priorities continue to be monitored through CSSF	Met. Across the three countries: / Ghana: CSSF partners have completed their OS priority assessments and are being actively monitored through the CSSF framework / Zambia: ZGF are implementing the CSSF through a phased approach to ensure they reach their target of 25 partners. CSSF1 has successfully onboarded 11 partners who have completed assessment of organisational priorities. CSSF2 has just been rolled out to target the remaining 14 partners. The complete onboarding process, including all capacity assessments to inform OS priorities, is scheduled to be completed by July 2025. / Malawi: Partners are in the process of being onboarded to CSSF, with OS priority assessments scheduled to be completed as part of the onboarding process by end of March 2025.
5.4 Number of CSOs who have implemented their OS plans (future indicator).	N/A	No milestone in this reporting period - Future indicator to be measured once implementation begins. / While implementation of OS plans has begun in (as noted in 5.2), this indicator measures full implementation of OS plans. No CSOs have yet completed full implementation of their OS plans in its entirety. Progress on this indicator as currently phrased will be formally measured and reported once CSOs reach completion milestones in their implementation journey. / Note: We recognise the need to review and amend this indicator to allow for more meaningful tracking of incremental progress rather than waiting for complete implementation before reporting any achievements.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 5 is A, with APs and partners firmly focused on carrying out self-assessments and identifying their priority areas. While there are some minor delays, this output is on track to be fully achieved during the lifetime of this programme. This year, Indicators 5.1, 5.2, 5.3 have been met. There is no milestone for Indicator 5.4 in this reporting period.

Indicator 5.1 An organisational strengthening framework is adapted in each country to support funded partners to identify and prioritise development needs.
Met. The Organisational Strengthening (OS) frameworks have been reviewed and revised based on continuous learning and feedback throughout the programme in Ghana, Zambia, and Malawi. Key points regarding this process, with specific examples from each country, include:

1. Joint Organizational Capacity Assessment (JOCA): In Zambia, the ZGF team conducted JOCA to refine the OS frameworks. This involved assessing the organisational strengthening needs of the CSOs and adapting the frameworks accordingly. The insights gained from these assessments informed the revisions of the OS frameworks to better align with the actual needs of the organisations. In Malawi, the JOCA process also facilitated the identification of specific capacity-strengthening priorities among local CSOs, which were then integrated into the OS frameworks.

2. Peer Learning and Sharing: The programme facilitated peer-to-peer learning among CSO partners in Ghana, Zambia, and Malawi, allowing for the sharing of insights and strategies for community development. This collective knowledge generation contributed to the ongoing refinement of the OS frameworks, as lessons learned from one organisation could be applied to others across these countries.

3. Engagement with Programme Advisory Panels (PAP): In all three countries, the PAP was involved in reviewing applications and providing technical guidance, which helped ensure that the OS frameworks remained relevant and effective. Their feedback on the proposals and the overall approach to organisational strengthening was taken into account during the revision process.

4. Adaptation to Contextual Changes: The OS frameworks were also revised in response to changes in the operational context of the countries involved. For instance, in Zambia, the ZGF grants committee reviewed the alignment of intended actions and budgeting with local development priorities, ensuring that the frameworks remained responsive to the evolving needs of the CSOs. In Malawi, the frameworks were adapted to reflect the unique challenges faced by local organisations, particularly in areas such as advocacy and community engagement.

Indicator 5.2 Funds (CF, CRMF, CSSF) provided to support civil society organisations in their identified priority areas.

Met

1.	Catalyst Fund Completion:

- Ghana: The CF successfully supported 20 civil society organisations, meeting the target effectively.
- Malawi: A total of 23 CSOs received support, surpassing the initial target and demonstrating strong engagement with local organisations.
- Zambia: The CF supported 25 CSOs, exceeding the target and showcasing the fund's impact on strengthening civil society.

The Catalyst Fund was a strategic component of the Shifting the Power programme designed to support civil society organisations (CSOs) in developing high-quality proposals for capacity development funding. During the programme's implementation phase, the fund provided small grants (up to £5,000) to help organisations strengthen their bid development capabilities.
This Annual Review reports on the Catalyst Fund this year to document the learning and outcomes from this innovative approach, noting that most of the grants concluded at the end of the last reporting period. This retrospective analysis provides valuable insights into how targeted, small-scale support can help local CSOs strengthen their organisational capacities.
The Catalyst Fund supported a total of 68 CSOs across Ghana, Zambia, and Malawi, with a focus on critical thematic areas such as gender justice, early childhood development, mental health, and safe shelter. These grants were instrumental in enabling organisations to invest in consultation, external capacity assessments, and proposal design workshops.
The CF’s most significant achievement lies in its transformative approach to organisational development that enables organisations to target their own priorities, increasing ownership and buy in for the process. For example:
- In Malawi 91% of participating organisations achieved official legal registration, up from just 65% at the programme's outset. This legal formalisation is crucial, as it provides CSOs with greater credibility, access to additional resources, and a stronger foundation for long-term sustainability.
- In Zambia, all 25 CSOs that participated in the Catalyst Fund demonstrated improved financial management. The Financial Management Assessment tool was used to capture financial management capacity in participating CSOs over the course of the Catalyst Fund delivery. In June 2023, 20 CSOs (80%) were scored as high risk. By February 2024, only one (4%) was high risk (but still demonstrated significant improvement) while 22 (88%) had improved to medium risk. This demonstrates improved financial management capacity in a relatively short period of time of the Catalyst Fund.
- In Ghana, CSOs showed marked improvements in organisational self-assessment in all thematic areas. For example, average scores from participating CSOs saw increases in financial management (52% to 88%), human resources (64% to 86%) and leadership structure (68% to 94%).

Financial sustainability emerged as a key focus area, recognising that long-term impact requires more than just project funding. The Malawi cohort demonstrated this approach most definitively, with 35% of participants successfully securing alternative funding sources. This achievement represents a fundamental shift from donor dependency to a more resilient funding model, empowering organisations to chart their own financial futures.

The #ShiftThePower principles were evident throughout the Catalyst Fund's implementation. By prioritising local leadership, supporting organisational self-determination, and focusing on building genuine capacity rather than imposing external frameworks, the programme demonstrated a radical reimagining of development support. As one Zambian CSO representative eloquently stated, "These skills aren't just for the Catalyst Fund project; they're helping us become a stronger organisation overall."

Challenges were not overlooked. Participants consistently noted the compressed implementation timeframe (6 months - 1 year) as a significant constraint, with organisations struggling to balance comprehensive capacity strengthening alongside their existing project activities. This feedback is invaluable, providing critical insights for future iterations of the StP programme. Strategically, the Catalyst Fund served as a crucial preparatory phase for the CSSF, creating a pipeline of more robust, capable organisations. By investing in governance, legal formalisation, financial management, and strategic planning, the fund ensured that participating CSOs were not just recipients of aid, but active architects of their own development trajectories.

The quantitative and qualitative outcomes across Ghana, Malawi, and Zambia tell a compelling story of institutional transformation. From improved board structures and policy development to enhanced fundraising capabilities and legal recognition, the Catalyst Fund has laid a robust foundation for a more resilient, independent, and locally driven civil society ecosystem.

As the programme moves forward, the lessons learned from the Catalyst Fund will be crucial. The success demonstrates that true development support is not about dictating solutions, but about creating the conditions for local organisations to identify, articulate, and pursue their own visions of change. This approach represents a profound shift from traditional donor-recipient relationships towards a more equitable, collaborative model of social development.

2.	CSSF Implementation Status:

APs have progressed with implementation of the CSSF across Ghana, Malawi, and Zambia, with each country either exceeding or working towards exceeding its initial target of supporting approximately 20 CSOs.

Ghana

The CSSF in Ghana has shown exceptional progress, with the fund being effectively operationalised through SGF and WACSI, who have completed rigorous processes for partner selection and grant making. Specifically:

- The fund has exceeded its target by onboarding a total of 36 partners
- This includes 12 CSOs transitioning from the Catalyst Fund (CF) and 24 new CSOs
- Formal agreements have been established that outline clear expectations, resource allocations, and accountability frameworks
- The fund is working to strengthen institutional systems in key areas including:
  - Governance
  - Financial capacity
  - Safeguarding
  - Monitoring and evaluation (M&E)
- This structured engagement of partners helps ensure effective implementation of the fund's objectives around strengthening civil society capacity and sustainability

Malawi
The CSSF in Malawi commenced in September 2024, with the aim to support 23 CSO organisations. TF encountered significant challenges that resulted in delays, most notably due to negotiations between TF, FCDO Malawi and FCDO in the UK. TF received approval to proceed in September 2024, and since then they have completed the following actions:
Assessment report has been submitted to the Grants Committee, with final Board approval pending
- Invested time in developing a robust organisational strengthening framework tailored to the local context
- Maintained transparency with funders through detailed assessment reports
Malawi expect to complete selection and onboarding of CSSF partners by end of March 2025.

Zambia
The CSSF in Zambia demonstrates a strategic and methodical approach through phased implementation. So far ZGF have:

- Due diligence completed for 13 organisations - 11 approved, 1 deferred, 1 rejected
- A second round planned to select a total of 25 CSOs by July 2025
  - ZGF will conduct a second round of the CSSF to expand and refine the programme's partner selection process.
  - Recognising that the initial cohort of partners may not fully represent the diverse civil society landscape, the mapping of CSOs across nine districts will provide critical insights into local organisational capabilities, needs, and potential impact.
  - This comprehensive approach ensures a more targeted and effective partner selection process, allowing the programme to identify organisations that are best positioned to contribute to the programme's objectives of strengthening local civil society. The selection process will be aligned with the landscape mapping, which starts in March 2025.
The consistent progress across all three countries, despite varying timelines and approaches, demonstrates the Anchor Partners' ability to implement the programme while maintaining focus on its core objectives of strengthening civil society organisations in their identified priority areas in line with StP principles.

Indicator 5.3 Number of funded partners who have completed assessment of OS priorities.

Met. In Ghana, SGF and WACSI have made significant strides in ensuring that onboarded CSSF partners have completed their OS priority assessments. The assessments have been instrumental in identifying key areas for improvement, enabling the CSSF to provide targeted support that aligns with the unique contexts of each partner. Furthermore, these assessments are actively monitored, ensuring that progress is tracked and that organisations receive ongoing guidance and resources to address their identified priorities.

In Malawi and Zambia, the onboarding process for partners is currently underway. In Zambia ZGF has completed OS priority assessments of the first selected 11 CSOs partners, with funding disbursements planned for Feb/March 2025. In Malawi the OS priority assessments are planned to take place prior to the end of March 2025.

OS assessments take place at the very beginning of the granting process, ensuring that all partners are equipped with a clear understanding of their organisational needs before fully engaging with the CSSF. This proactive approach not only facilitates a smooth transition into the program but also ensures that the support provided is relevant and impactful from the outset.

Indicator 5.4 Number of CSOs who have implemented their OS plans (future indicator).

While there is no milestone for this reporting period, Indicator 5.4 remains an important future measure of the programme's effectiveness in strengthening civil society organisations. This indicator will track how CSOs move from planning to implementation and review of their organisational strengthening priorities identified through the CSSF. Note: We recognise the need to review and amend this indicator to allow for more meaningful tracking of incremental progress rather than waiting for complete implementation before reporting any achievements.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Both the CF and CSSF are central to the programme’s ambition to move away from short term project funding and towards strategic investments in civil society which have wider social and economic value long after they end. This is central to the programme’s approach to value for money. At the same time, the programme is investing in organisational strengthening for APs, enhancing the programme’s contribution to sustainable social benefits.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the last year, and none are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
Lessons learnt from the OS study will continue to be embedded in the StP OS work.	The programme has made significant progress in shifting from donor compliance to funded partner-owned OS through: / Clear communication with funded partners about OS expectations and objectives / Working through local Anchor Partners to reduce power imbalances / Regular reflection sessions to ensure OS funding meets partner needs / Adjusting OS frameworks based on partner feedback and local context

Major lessons and recommendations for the year ahead:
Lessons learned this year.

Lesson 1 - The diverse nature of the CSSF partners in all three countries means there is a wide range of needs and requests which require personalised support, and managing this diversity has been a challenge in ensuring that each organisation receives the attention necessary for their growth.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
To overcome the challenge of the diverse needs of the 36 CSSF partners, SGF will establish learning hubs, grouping partners based on shared needs and locations, in order to encourage peer learning, collaboration, and targeted support, allowing partners to benefit from collective resources while still addressing their unique requirements effectively. If successful, this approach could also be considered in Malawi and Zambia.	SGF	Jan 2026

Output Title	StP programme financial forecasting improves
Output number:		6	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes – new output

Indicator(s)	Milestone(s) for this review	Progress
6.1 The variance between forecast and actual spend up to end of each Financial Year.	StP programme achieves a 5% or less variance between forecast and actual spend up to end of Financial Year. (From set baseline figure at start of year)	Expected variance based on forecasts received will be around 30%.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for output 6 is C. Indicator 6.1 has not yet been achieved.

Indicator 6.1 The variance between forecast and actual spend up to the end of each Financial Year.
Substantially Not Meet. For the previous reporting period (programme year 2023-2024), the variance between forecast and actual spend was 51%.

For 2024-2025, the programme has taken several steps to improve financial management and forecasting, including:
- Recruiting a Finance Business Partner at Comic Relief, whose time is 40% dedicated to financial management of the StP programme.
- A finance sub-group was created, which first met in November 2024. This group is made up of finance and delivery teams from all partners. The aim of the group is to share good practice, co-produce a standardised financial reporting template so information can be shared easily between all parties, also look at challenges and blockers faced collectively or by organisation (e.g managing exchange rates and fluctuations).
- Pro-active programme and finance planning with each AP and CR monthly. APs and CR will be meeting approximately every two weeks, and finance will be part of the monthly agenda so challenges can be flagged up sooner and discussed to mitigate and manage possible impact to forecasts.
- Streamlining financial reporting from APs by co-producing standard reporting template, aligning payments to APs cash forecasts and more forward planning of programme-wide cash flow.

However, it takes time to embed change in systems and processes across this number of partners, particularly in a participatory manner that is true to the Shifting the Power principles. The variance was further exacerbated by the fact that a large payment was made by Comic Relief to Anchor Partners at the beginning of the financial year in April based on original payment schedules rather than financial forecasts (a process no longer in place), which meant that most Anchor Partners have not required additional payments during the year, particularly due to delays to CSSF rollout in Malawi and Zambia, as mentioned under output 5.

Finally, all the proactive financial changes took place during the reporting period after the yearly financial forecasts were already set, which determined the target for this indicator, and payments already made to Anchor Partners. As such this indicator was unlikely to be met without dramatically changing the granting process which would have been to the detriment to the relationship between Comic Relief and Anchor Partners, and between Anchor Partners and their funded CSO partners.

Despite these challenges, the programme has seen improvements in variation between the annual forecast and spend, at 30% in 2024-5. Comic Relief are aiming to reduce this variance further for the programme year 2025-2026. The majority of the positive impact from the work conducted this year will only be perceived during the next reporting year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output is a new output for this reporting period. Variances are expected to reduce now that a Finance Business Partner, based at CR is in place and has developed supportive relationships with AP finance colleagues.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Summary of recommendations from Yr 4 (2023-24)	Progress March 2025
N/A

Major lessons and recommendations for the year ahead:
Lessons learned this year.
Lesson 1 - While resource led solutions like new finance staff and reporting templates are important, improving financial forecasting across multiple partners in an equitable and partner-led manner requires time to embed changes and build mutual understanding of each partner's financial processes and address challenges.

Recommendations for the year ahead:

Recommendation	Responsibility	Completion date
Leverage the finance sub-group to develop context-specific forecasting approaches that balance accuracy with partners' operational realities and programme challenges and strengthen communication and planning between finance and delivery teams.	CR, APs	Sept 2025

D: VALUE FOR MONEY

Value for Money Policies and Strategies

In 2024, each AP either drafted or finalised, respectively, their context-specific Value for Money (VfM) Strategy/Policy. SGF’s VfM strategy acknowledges that their work is complex and results in social change that cannot necessarily be captured in a linear way or within an average 2–4-year project timeframe, so they plan to explore approaches to estimating long-term outcomes from proxy indicators. They also want to ensure the perspectives of local communities are at the core of the VfM framework, with an approach rooted in the principles of locally led and community-driven development, recognising both monetary and non-monetary resources.

SGF are pursuing a twin track approach of Reform (building on and expanding the definition of Equity in the 4Es framework) and Transformation (collaboratively piloting and testing approaches with organisations to inform a more transformative change in VfM practice in the long term). ZGF’s VfM Policy outlines their guiding principles (accountability, adaptiveness to change, responsiveness to needs, resourcefulness and collaboration) which generates the 4Es and transparency in decision-making processes including resource allocation. Their VfM policy outlines operational strategies and practices, how these will be monitored and evaluated, and serves as a guiding framework that aligns the organisation's actions with its core mission of strengthening local communities and civil society, fostering sustainable development, and ensuring that every resource is optimised for the benefit of all stakeholders. The Anchor Partners all completed their Value for Money (VfM) policies by October 10, 2023, which was the original deadline. Comic Relief has also reviewed and updated its VfM framework this year, and all Anchor Partners are now in the process of reviewing and updating their policies to ensure alignment with programme objectives and emerging best practices.

Effectiveness

This programme has been designed with effectiveness at its heart. In particular, the long duration of the programme allows effective programme partnerships to be built, lessons to be learned and fed back into programming, and effective communications to be created using community voices. By centering learning as a core function of the programme partners, including local CSOs, APs and funders, have been able to critically assess their work, impact achieved and identify what could be improved. For example, the Malawi and London cross-programme convening events provided an opportunity for collective reflection on programme achievements, and cross-country sharing of lessons learned from the CF, which will improve the effectiveness of the CSSF (and later the CRMF) and other aspects of programming. There were discussions on how to integrate different programme components for maximum effectiveness, and how to effectively strengthen African civil society through programme outcomes. This collaborative approach has reinforced the programme's commitment to shifting power dynamics while building a stronger, more sustainable African civil society sector.

The leading role for APs further enhances the programme’s effectiveness by leveraging local knowledge, particularly as the APs are committed to ensuring the voices of community members are heard and gaining their buy-in and contributions to the projects. Each AP has adapted the programme to their local context while maintaining core principles. Local approaches reflect different civil society landscapes and needs across the three countries. Implementation strategies demonstrate flexibility while ensuring consistent programme objectives.

The commitment by CR and FCDO to covering the core costs and management costs of the APs also means that over the last year, APs have been able to fully focus on organisational strengthening (OS) (through the CF, and now the CSSF), which have been highly effective initiatives, and are fully described in this report under Outcome 1.2 (Evidence of CSOs with improved capacity and financial sustainability). In addition, being able to focus on OS, without the distraction of fundraising to cover core costs and management costs, will ultimately ensure that the APs are more effective in meeting their objectives in strengthening local civil society.

Equity

Equity is fundamentally at the heart of the StP programme, which explicitly seeks to minimise or neutralise inequitable power dynamics both between funders and APs, and subsequently between APs and their funded partners within each country.

The CF also enabled organisations who might not otherwise be funded to develop their systems and processes, so they are ready to receive funds from the programme’s other streams of funding or other donors. In doing so, the APs have improved the diversity of applicants which is likely to result in greater impact and the equity of the programme by increasing reach beyond the usual organisations who are eligible for this type of funding. APs utilised different methods and platforms to engage with local CSOs including radio, road shows to hard-to-reach regions, posters, social media and existing
CSO networks. The type of work being implemented through the StP programme with equitable funding approaches is time consuming, as it is crucial for the foundations of collaboration, transparency, equity and trust to be in place for the relationships and programme to flourish but is critically important.

Economy
It was agreed that the VfM case for this programme would not be based on cost per beneficiary calculations, which was previously a common measure of economy, as that would be at odds with a theory of change which is seeking to move away from the buying of outcomes through short term project funding and towards long term strategic investments which will have wider social and economic value which sustains long after funding ends. This is also in line with CR’s approach to VfM which is defined as:

“We want to give scope to communities and their partners to define the social change they want to see happen and what success looks like now and moving forward. Our investment goes beyond money to our relationships, models, approaches, expertise and communications. We recognise that we contribute to a bigger picture of social change, alongside other actors.”

However, there are numerous other key measures of economy which the programme is demonstrating. Firstly, the partnership between CR and FCDO ensures that FCDO’s financial contributions were matched by donations from annual televised fundraising appeals, which represents excellent VFM as it effectively doubles FCDO’s investment. Comic Relief provides a unique combination of local grant management, public matching and communications expertise that this programme requires to achieve its stated objectives and deliver value for money. Comic Relief’s grant management staff have been provided with training and renewed guidance on how to embed this across the grant making cycle. The long duration of the StP programme offers greater economy by reducing programme costs per year. Also, FCDO committed to meeting the true cost of delivery in the 2016 Civil Society partnership Review which it links to CSO sustainability; this promotes organisational resilience, which represents economy.

Working with local anchor partners to deliver the programme ensures that as much of the benefit of undertaking programme management accrues to local civil society as possible, ensuring that how we deliver programme management also contributes to the intended outcomes of the programme in relation to local civil society capacity; this will ensure added economy. Knowledge, evidence and learning within the programme are feeding into ongoing programme design and adaption as well as generating additional VfM by influencing more effective civil society programming in FCDO and other donors. Comic Relief and the APs engage regularly, both online and at least once per year in person. In-person engagements include an opportunity to assess VfM, including budgeting processes, financial systems, and MEL practices (as part of a broader review of performance, compliance and learning). In turn, the APs also engage frequently with and provide specific support to the CSOs funded through the CF and CSSF and guide them on the importance of value for money, something which is also considered at the grant-making stage.

In terms of examples of economy and efficiency within individual countries:

Efficiency

The long-term duration and strategic nature of the funding for the StP programme allows CSOs the time they need to plan strategically and institute real organisational change and as such represents enhanced efficiency in programme management and change, as opposed to short term grants which end before genuine cultural shifts can take place in an organisation.

Specific country approaches to VfM

Ghana

Over the past reporting year, SGF have continued to deliver the Ghana programme in line with their procurement policies, ensuring value for money in service provider costs. For example, in sourcing service providers for conducting ‘know your partner’ exercises, they engaged only consultants who have been pre-qualified and registered on their vendor list, with agreed rates for their services, which are competitive compared to the market rates. SGF have also encouraged partners to do the same. Programme delivery is broadly on schedule, with minor delays to some plans. Now that the CSSF is operational, this will improve accuracy of forecasting in the next reporting period.

The CSSF in Ghana demonstrates an innovative and inclusive approach through its support of 36 diverse partner organisations. These partners span a spectrum of civil society organisations - from small grassroots groups to large established institutions, operating at both national and sub-national levels across different regions of Ghana. Their work focuses on critical issues including reducing inequalities, addressing marginalisation, and combating various forms of exclusion.

A significant innovation in Ghana's implementation was the introduction of a funded four-month design phase for CSSF partners, inspired by CR's iterative approach at the program's start. This phase represented a marked departure from traditional funding approaches in order to ensure effectiveness by:
- Enabling organisations to engage in meaningful consultations with their constituents and peer organisations about sustainability pathways
- Supporting internal organisational discussions for more effective strategic planning
- Funding research and delivery plan development
- Covering consultation costs during proposal development - traditionally an unfunded burden on organisations, allowing CSOs to focus on effectiveness

To maximise programme effectiveness while accommodating the design phase, SGF implemented a flexible staggered implementation approach. This allowed:
- Organisations to begin implementation as soon as their plans were finalised rather than waiting for all partners
- Partners to start priority activities while continuing to refine other aspects of their delivery plans
- Maintained programme momentum while ensuring strategic alignment of activities

Feedback from a survey on the design phase's effectiveness revealed that organisations particularly valued:
- The ability to conduct truly participatory planning with constituents
- Opportunities for meaningful stakeholder engagement
- Support for making their programmes more equitable and effective through proper consultation

The diversity of participating organisations combined with their varied focus areas suggests strong potential for value for money through effectiveness, as the programme can:
- Impact multiple levels of civil society simultaneously
- Address interconnected development challenges
- Build capacity across different types of organisations
- Create opportunities for peer learning and collaboration
- Reach communities through organisations that understand local contexts

Out of the 19 CF partners in Ghana, less than 5 had ever received donor funding for projects, let alone for institutional funding. Working with these partners will improve effectiveness due to their focus on local grassroots issues with community buy-in. Through this enhanced approach to grant-making and capacity strengthening, Ghana's CSSF implementation exemplifies key principles of shifting power by providing organisations with both the resources and flexibility to determine their own development priorities and pathways to sustainability.

Malawi

TF has systems in place to ensure value for money and fair competition when selecting providers of services and suppliers of goods. Specification of goods to be procured, or Terms of Reference (TORs) for services to be acquired, are developed on which goods suppliers or service providers respectively are requested to base their quotation on. Specifications and quality of items being procured are key considerations, in addition to cost. Inspection of goods ensures quality and economy, and monitoring of service delivery ensures efficiency.

A major risk to the programme’s value for money is a requirement by the new Foreign Exchange Regulations 2024 by the Government of Malawi. The regulation requires that NGOs and CSOs that receive funding in foreign currency should convert 70% the funds received into local currency within 2 days of receiving the funds. Failure to do that, the commercial banks are mandated to affect the conversion. The volatility of the Malawi Kwacha in terms of losing value against the foreign currencies means that once the foreign currency is converted, the value cannot be maintained over time. This is happening against a poor forex situation in the country and high price volatility. TF has participated in activities under the National Advocacy Platform and Council for Non – Governmental Organization of Malawi (CONGOMA) regarding this position on foreign currency. TF made a presentation on the likely effects of the regulations at a meeting with the central bank. There is also an injunction which Commercial Banks in Malawi have obtained from the High Court for a judicial review on this regulation from Government. TF also welcomes support from FCDO and the British Government on this issue. TF and Comic Relief are working on practical ways to help mitigate the impact of this regulation on the programme, for example through more regular but smaller payment tranches

During this reporting period, Tilitonse Foundation (TF) demonstrated VfM through a highly effective comprehensive three-stage selection process for the CSSF:
1. Preparatory Support
  1. Conducted preparation workshops for potential applicants ahead of the funding call, and provided technical guidance on proposal development, to ensure high-quality applications, and a commitment to equitably reaching organisations who would not previously have been able to apply
  2. Implemented targeted outreach to ensure diverse geographical and organisational representation and equity
2. Expert-Led Selection
  1. Established an independent expert review panel to evaluate applications and integrated local expertise to ensure context-appropriate decision-making
  2. Applied standardised assessment criteria to ensure fairness and transparency
  3. Prioritised alignment with key thematic areas: Early Childhood Development, Gender Justice, Mental Health, and Safe and Secure Shelter
3. Accountability Mechanisms
  1. Established a dedicated complaints review team, and implemented clear procedures for handling and responding to complaints
  2. Created feedback channels for unsuccessful applicants to strengthen future applications

This structured approach also helped ensure efficient use of resources while maintaining very effective high standards for partner selection. The process demonstrates TF's commitment to both rigorous assessment and inclusive equitable support for potential funded partners, balancing the need for due diligence with accessibility for emerging civil society organisations.

Zambia

To increase the impact of their programmes in Zambia, ZGF have invested in their staff through upskilling them using low-cost platforms like Humentum for training, and introducing low-cost wellness programmes such as aerobics to improve employee health resulting in increased productivity. They have also met economy dimensions of VfM, for example using technology to automate repetitive financial processes, which reduces the costs of purchasing paper and toner, and maintenance of printers and scanners; and using solar energy to reduce electricity bills. Finally, ZGF’s programming has been efficient, for example programme activities are aligned with organisational strategic goals, because of work planning focused to reflect bench marked impact.

ZGF has also demonstrated strong value for money through their commitment to effectiveness and equity through implementation of the CF and beginning of CSSF. Their approach prioritises communities facing significant environmental challenges, including those affected by climate change, natural disasters (e.g. drought and flooding), mining activities, and environmental degradation, or they may be hard to reach, for example the CF partner Kakuntha Multipurpose Cooperative is based in a remote part of Nyimba. Key demonstrations of their value for money approach to effectiveness and equity this reporting year include:

1. Targeted Programming: Resources are directed to areas with the highest levels of deprivation and need, while considering practical feasibility to ensure efficient implementation.
2. Community-Led Decision Making: Unsung heroes from local communities are actively involved in determining how granted funds should be allocated, ensuring investments align with genuine local priorities and needs.

E: RISK

Overview of risk management
The overall risk profile remains largely stable, with most risks maintaining their previous levels. The overall residual risk remains at a moderate level. In the period under review, the major risks across the three countries in the programme were:
- That compliance requirements constrain the ability to shift accountability to local communities.
- Safeguarding (failure to protect people from harm during programme engagement)

During the period under review CR continued to monitor the risks facing the programme using a programme level risk register. APs report on risk and mitigation in the reports they submit to CR and feed into the risk register updates that CR submits to FCDO. The risk register is updated by CR’s Funding Team, submitted to FCDO and jointly reviewed quarterly. This is reported to CR’s Executive Leadership Team and Audit and Risk Committee on a quarterly basis. CR also has an Assurance function which oversees the management of risks across all CR’s work. In addition, CR continuously monitors the context in Ghana, Zambia and Malawi and includes insights from in-country APs. It remains a priority to ensure that reporting procedures do not overwhelm the programmes’ central aims of improving accountability to local people and their priorities.

The main changes to risks during the reporting period, and how they are being mitigated, are as follows:

Strategy and External Context
There were/are political tensions ahead of elections in Ghana (2024), Malawi (2025) and Zambia (2026), which may tighten civic space in all countries and distract key stakeholders from the StP movement and programme. Mitigation includes revising context analyses, regular engagement with in-country partners, and phased, data-informed implementation approaches.
Overall Residual Risk: Major (Increased from Moderate due to escalating situation in Malawi)
The residual risk has increased in this category primarily due to the upcoming elections in Malawi in 2025. While Ghana successfully navigated its December 2024 elections with the programme maintaining political neutrality (Moderate residual risk, unchanged), the situation in Malawi has deteriorated. The likelihood of political interference in Malawi has increased from "Possible" to "Likely" and the impact has been elevated from "Moderate" to "Major," resulting in an overall residual risk of "Major" (increased from Moderate).
This escalation reflects the increasing proximity to Malawi's September 2025 elections and heightened potential for political interference. Despite strengthened mitigation measures including Tilitonse Foundation's intensified sensitisation efforts with CSOs and the establishment of a Complaint Redress Mechanism team with representatives from the Malawi Human Rights Commission, Office of the Ombudsman, and Anti-Corruption Bureau, the pre-election environment presents significant challenges that justify the elevated risk assessment.

Financial & Fiduciary
There were no incidents of fraud identified in this reporting period. There is a risk around balancing financial management standards with CSO autonomy in the StP programme. Mitigation includes the implementation of tiered reporting systems, capacity-building initiatives, and collaborative review processes with partners. In addition, the impact of global events on currency depreciation, cost of living, etc is constituting a substantial risk to the economic value of grants provided to partner CSOs in the local currency.

The risk of Anchor Partners' financial sustainability being compromised by overreliance on the STP Portfolio (SR20-15/FCDO F7) remains rated as Moderate for Q4 2024-25. The risk of AP funding dependency decreased from moderate to minor in Ghana, because of these mitigating actions: scrutinised budgeting, regular financial report reviews, organisational strengthening support, and development of comprehensive resource mobilisation strategies. However, recent developments require attention. Both TF (Malawi) and ZGF (Zambia) have identified potential shifts in their funding landscapes that may affect long-term sustainability. Both APs are exploring new funding opportunities and also monitoring implications of aid funding stop orders from the USA and UK aid funding cuts. These developments will be closely monitored, as they may necessitate adjustments to risk ratings and mitigation approaches in the coming financial year.

Policy and Programme Delivery
The risks related to this category include three new risks in this reporting period, given that implementation is now fully underway. Firstly, imposing financial management standards on Southern based CSOs undermines efforts to allow organisations to set their own priorities and skews accountability to distant donors and away from local communities. The mitigation strategy now includes a commitment to regularly review the impact of financial management requirements on CSO autonomy and local accountability, to maintain an appropriate balance.

Residual Risk: Moderate (Unchanged)

The second new risk is that CSOs fail to generate significant new income streams despite receiving training and support through the CRMF, potentially compromising their long-term financial sustainability and the programme's objectives. Mitigation measures include thorough needs assessment, ongoing mentorship, peer learning networks to facilitate knowledge sharing, adapting training and tiered support with more intensive assistance for those CSOs who need it.

Residual Risk: Moderate (Unchanged)

The third and final new risk is that milestones identified within the capacity development framework in areas identified by CSOs themselves are not met by a significant number of funded partners. Mitigating measures include regular process reviews and an early warning system and proactive support, and flexible budget allocation systems, amongst others.

Residual Risk: Moderate (Unchanged)

A new risk in Ghana is the potential for disruption in consortium partner relationships. Mitigation involves regular engagement and adaptive programme management approaches and ensuring that the partnership is engaged as one unit and communication and feedback between them is kept open, with CR facilitating regular joint update meetings between SGF and WACSI and encouraging alignment on programme objectives.

Residual Risk: Moderate (Unchanged)

There were also concerns that the End-to-End Review (EER) might worsen the relationship between TF and FCDO Malawi, but significant progress has been made in strengthening the relationship between TF and FCDO Malawi, effectively mitigating this risk. The increased engagement and positive feedback from FCDO confirm that the EER’s recommendations are being addressed effectively, and the programme is moving in a positive direction with FCDO's support.

Residual Risk: Moderate (decreased from Major)
Rationale for Change: The significant improvement in relationship quality and strategic positioning suggests the original risk has been effectively mitigated, warranting a reduction in both likelihood and impact ratings.

Public Service Delivery and Operational
During Q4 2024-25, we have reintroduced and updated a significant risk related to potential UK Aid budget cuts (SR20-1/FCDO C1) which had been previously closed. This decision follows recent UK Aid budget announcements that have raised concerns about future funding stability for development programmes.The reinstated risk addresses potential reductions in the UK aid budget that could compromise the Shifting the Power programme's scale, scope, and long-term sustainability. Such reductions would threaten our ability to achieve the intended transformative outcomes related to civil society strengthening in Ghana, Zambia, and Malawi.The risk has been assessed as Major (combination of Possible likelihood and Major impact). We have developed a comprehensive mitigation strategy and anticipate the residual risk as Moderate. The programme team will closely monitor budget announcements and maintain regular communication with FCDO to identify early warning signs of potential funding changes.
Safeguarding
In this reporting period, two safeguarding incidents were reported and investigated in Zambia. One was a communication issue which was addressed through formal apologies, additional training and improved communication protocols. The other was a misconduct case and future engagements with the service provider involved have been discontinued. Both cases are now closed. These incidents were the only two reported over the period.

Each AP during the period has identified a Safeguarding Focal Point for the programme and this has enabled the safeguarding sub-group to be formed. The group is now solidified and meeting regularly allowing for peer support, and, for the partners as a group to think together about how safeguarding should look across the programme and more broadly within the StP space. Each organisation now has a robust safeguarding policy which is being utilised in practice. The sub-group has identified that it would like for each organisation to work to move beyond practice in order to make each of their organisations truly safeguarding focussed.

The sub-group has also been able to embed reporting procedures within the program and are considering how to adopt this with their onward funded partners. For example, in Ghana, SGF held an introductory session on safeguarding for the new CSSF partners, which revealed that 5 out of 23 did not have safeguarding policies and reporting mechanisms; they will be supported to develop these. Each member of the sub-group has also begun to create a list of consultants who they are able to draw upon should Safeguarding investigations arise. The Safeguarding Lead at Comic Relief has also undertaken the Humentum Investigations training so is able to provide support in this regard at present if necessary. At the next Safeguarding sub-group meeting the team intend to agree a way forward in terms of commissioning a consultant to support the process of identifying a strategy and workplan for the sub-group.

Reputational
There was a major reputational risk in Malawi regarding public perception of the programme; mitigation has included thorough pre-grant assessments, ongoing monitoring, and dedicated resources for managing reputational issues. A multi-faceted mitigation strategy has been implemented in response. At its core, FCDO and Comic Relief have established strong collaborative mechanisms to ensure effective public communication about the programme's value and assurance measures. This is complemented by Comic Relief's proactive communications work and carefully developed SMART outcomes and indicators to demonstrate tangible impact.

During this period, the TF has also increased its visibility and improved relationships with key stakeholders in Malawi. TF has been engaged and involved in activities with the British High Commission in Malawi, including being invited by the British High Commissioner to a Principals Engagement Breakfast in November 2024, co-chaired by herself and her Deputy, which provided an update on the British Government directions on international aid and cooperation with the coming in of the new Labour Government. This high-level event involved around 25 institutions including UN family members, World Bank, the key development partners in Malawi (USAID, Norwegians, EU) and other multilateral institutions. TF was the only local CSO present.

In December 2024, TF also was invited to a dinner organised by the British High Commission for the visiting Minister for Development Anneliese Dodds. Discussions focused on the economic situation in Malawi, corruption and the general governance challenges Malawi is facing. TF highlighted the work of the Shifting the Power Programme, which the High Commissioner acknowledged in her remarks, and emphasised the importance of strengthening support for civic engagement and localisation.

Comic Relief has taken an active role in reviewing both Tilitonse Foundation (TF) and Shifting the Power (StP) Communications and Advocacy strategies specifically for Malawi, aiming to enhance implementation effectiveness. The programme is also exploring the adaptation of Institute for Voluntary Action Research’s (IVAR's) open and trusting practices principles into grant-making processes in Malawi, which should improve partner relationships and programme outcomes. A proactive media engagement strategy has been developed to showcase positive programme impacts.

Recent developments have shown encouraging progress, with TF and Comic Relief actively identifying success stories from Catalyst Fund projects. The focus has notably shifted from managing implementation delays to showcasing tangible community-level impacts.

The mitigation strategy continues to evolve, with new specific actions being incorporated around public engagement and grant-making transparency. This adaptation reflects both the changing nature of public perception risks and emerging opportunities for positive engagement. Regular monitoring of these measures' effectiveness is ongoing, with particular attention to impact demonstration and stakeholder engagement. The comprehensive approach appears to be yielding positive results in managing reputational risks while building public confidence in the programme's value and impact.
Reworded Risks and Rationale
As part of our continuous effort to refine our risk management framework, CR and partners have updated the wording of several risks in our risk register. The following highlights the key changes made to the risk descriptions, along with the rationale behind these updates:
1. SR20-14 (FCDO F1)
Original Risk Description: Funds are not used by Comic Relief and/or grant holders for the intended purposes, and/or are not properly accounted for, a risk heightened by global events (e.g., political turmoil, natural disasters, war) and economic pressures (e.g., cost of living crisis, exchange rate fluctuations) that increase costs and complicate financial management for programme implementers.
Updated Risk Description: Funds Misappropriation Risk: A multi-dimensional risk encompassing potential intentional and unintentional misuse of funds across the Shifting the Power programme.
Rationale for Update: The risk description has been updated to explicitly acknowledge both intentional and unintentional fund misuse. This reflects a more comprehensive understanding of the risks associated with fund misappropriation, allowing for more targeted monitoring and mitigation strategies.
2. SR20-15 (FCDO F7)
Previous Risk Description: Substantial flows of funding into the APs inflate annual budgets & create dependency on STP Portfolio.
Updated Risk Description: APs' financial sustainability may be compromised by overreliance on STP Portfolio as primary funding source.
Rationale for Update: The risk description has been rephrased to better reflect concerns about avoiding APs' overdependence on STP funding. This new wording underscores the importance of sustainability in financial planning and encourages diversity in funding sources.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Quality and timeliness of narrative reporting and audited financial statements:
During the period under review one six monthly report for the period 1st April to 30th September 2024 was delivered by CR and APs to FCDO on time.

CR conducts full external audits annually and these are submitted by the statutory due date required by UK Companies House. The audit includes a review of all individual fund balances and checks of all grant agreements to ensure that spending complies with conditions of grant from funders including FCDO. As required by Charity SORPs, in the accounts, CR has a separate line for FCDO funds in note 20 which is the restricted funds note. This line includes all income from FCDO in the year and all expenditure against those funds. This is sampled, checked and signed off by the auditors. The final set of accounts are presented to CR’s Board of Trustees, signed and filed at Companies House.

APs provide six monthly and annual narrative and financial reports. They also provide annual audited accounts. In the period under review the above reports were provided in a timely manner. The reports are overall of high quality and provide CR with more detailed information and analysis on the performance of APs. Overall financial reporting provided was satisfactory. Forecasting has improved in this reporting year, but efforts are still underway to reduce the variance further. It is anticipated that variances against budget will reduce in the next reporting period, with the support of the CR Finance Business Partner.

Risk Registers have been updated by APs and CR and submitted quarterly to FCDO.

Proactive dialogue on risks and updating of delivery chain maps:
As outlined in sections above a comprehensive risk register is in place to monitor risk. Meetings to discuss risks and update the risk registers are held with participants drawn from FCDO, APs and CR. A reporting protocol is in place at CR for reporting serious incidents and concerns to FCDO and an agreed approach to investigation and reporting thereafter. During this period, two safeguarding cases were investigated, resolved and closed. No allegations were received of fraud. Safeguarding remains a major priority for risk monitoring and the emphasis this year is on improving practice, especially amongst CSSF partners. An up-to-date delivery chain map has been submitted with this annual review.

Quality of financial management:
Key cost drivers in order of highest expenditures are:
- Partner grants:	83%
- Management costs:	10%
- Communications and Advocacy:	4%
- Knowledge, Evaluation and Learning:	3%

Financial management has improved, due to a combination of more accurate forecasting by APs and recruitment of the Finance Business Partner. Variance against forecast has reduced from 51% in 2023-24 to a forecast of 30% in 2024-25. Description of the challenges faced in addressing variance is detailed under Output 6.

	Forecast	Actual
April to June 2024 Q1	£980,217	£1,891,479
July to September 2024 Q2	£1,384,240	£114,971
October to December 2024 Q3	£1,250,099	£489,755
January to March 2025 Q4	£944,995	£686,781 (forecast)
Total	£4,559,552	£3,182,986

Asset monitoring and control:
All assets under the StP programme are funded from Comic Relief’s contribution and therefore followed Comic Relief’s asset management policy. In line with Comic Relief policy, where capital expenditure by funded partners is approved, it must be clearly demonstrated that any assets acquired will be used during and at the end of the grant on activities in the spirit of the original grant agreement. Asset registers are regularly updated by each AP.

Learning and Support activities:
Monitoring progress by APs is done through:
1. Desk review of the reports submitted.
2. Verbal/ virtual updates and
3. Physical learning and support engagement.

Report submission: As part of their annual reporting to CR, APs also reflect on changes as a result of their work. Focus remains on the output level, although there is now also some early programme monitoring and capturing of change at outcome and impact level too.

Verbal/virtual updates: CR and AP programme teams meet generally on a biweekly basis, with finance joining monthly, touching on topics across the entire programme to break down silos. Detailed technical discussions take place in sub-groups, for example the Learning and the Advocacy & Comms sub-groups meet roughly on a biweekly basis, but with gaps during busy periods such as in person convening and the Strategy & Governance sub-group meets once a quarter. Further, ad-hoc meetings take place on a regular basis, based on needs.

Physical learning and support engagement:
Learning and support visits to each country took place at least once in this reporting period. In May 2024, the team visited Zambia to support the ZGF with the implementation of their safeguarding policy; and Malawi to support the TF on grant making approaches ahead of planning roll out of the CSSF and engaged with the British High Commission (BHC) Malawi to address challenges and support recruitment of the in-country Manager for the StP programme. In September 2024 the team returned to Malawi to support TF in rolling out the CSSF, forging new relationships with BHC Malawi and supporting induction of the StP Programme Manager. With the new Programme Lead being based in Zambia, there is consistent engagement and support through regular in-person meetings in Zambia. Ghana also received a partnership support visit in February 2025. Details of these visits have been provided to FCDO and included as an annex. These learning and support engagement help in relationship building, deepening understanding of the programmes’ country context, opportunities, challenges and progress being made in implementation and overall assist CR in improving its response to the partners.

During this reporting period the programme partners organised two convening events, one in Malawi focused on equitable partnerships in April 2024, and one in London focused on learning, partnerships and strategic direction in October 2024. More information is shared under Output 1.3 above.

Date of last narrative financial report	31 January 2025	Date of last audited annual statement	November 2024

Annex 1: Acronyms

ABCD:	Asset-Based Community Development
AP:	Anchor Partner
APN:	African Philanthropy Network
BC:	Business Case
BHC:	British High Commission
CBO:	Community Based Organisation
CEO:	Chief Executive Officer
CF:	Catalyst Fund
CR:	Comic Relief
CRMF:	Community Resourcing Match Fund
CSO:	Civil Society Organisation
CSSF:	Civil Society Strengthening Fund
CYO:	Concerned Youth Organisation
CWG:	Cashew Watch Ghana
DWF:	Dynamic Works Foundation
EER:	End-to-End Review
EU:	European Union
FCDO:	Foreign and Commonwealth Development Office
HBF:	Healing Balm Foundation
IVAR:	Institute for Voluntary Action Research
JOCA:	Joint Organizational Capacity Assessment
M&E:	Monitoring and Evaluation
MEL:	Monitoring Evaluation & Learning
OS:	Organisational Strengthening
PAP:	Programme Advisory Panels
SGF:	Star Ghana Foundation
SIDA:	Scottish International Development Alliance
SRHR:	Sexual and reproductive health rights
StP:	Shift/ing the Power
ToC:	Theory of Change
ToR:	Terms of Reference
TF:	Tilitonse Foundation
UCL:	University College London
UK:	United Kingdom
USAID:	United States Agency for International Development
UNIMA:	University of Malawi
VfM:	Value for Money
WACSI:	West Africa Civil Society Institute
ZGF:	Zambia Governance Foundation

Annex 2: #ShiftthePower manifesto