## Annual Review Template

Title: Combatting International Illicit Finance: Accelerating the 2030 Agenda
Programme Value £ (full life): £39.34m		Review date: 27/06/25
Programme Code : 301035	AMP start date: 27/03/2024	AMP end date: 31/03/2029

Summary of Programme Performance
Year	24/25
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301035
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301035 Documents

## Scoring your programme
## The Annual Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.
Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

Ideally changes should not be made to any targets or indicators less than six months before review, unless agreed with the Head of Department.

A. SUMMARY AND OVERVIEW

Description of programme

The Combatting International Illicit Finance: Accelerating the 2030 Agenda programme represents an evolution in FCDO capability to tackle international illicit finance (IF). Informed by a comprehensive consultation, it has two, complementary components designed to address existing HMG capability limitations. Component 1 establishes a new International Centre of Expertise on Illicit Finance (ICE) to enhance HMG and FCDO’s understanding of, and responsiveness to, the complex international IF dynamics which undermine the UK’s international interests. ICE pools specialist resource, creating an in-house expert consultancy generating research products, monitoring, evaluation and learning services, and advice and short-term catalytic deployments for posts, FCDO thematic teams, and Other Government Departments (OGDs) to enhance the impact of their counter IF efforts. It works closely with existing, cognate HMG capabilities such as the National Economic Crime Centre (NECC) and FCDO’s Research and Evidence Division.

Component 2 supports FCDO’s international influence with emerging and established -financial centres to combat IF challenges. It does so through funding FCDO’s network of IF policy advisers (known as ‘IF leads’) in ODA eligible priority jurisdictions. IF leads develop HMG understanding of IF vulnerabilities in jurisdictions and build trusted networks across host governments, the private sector and civil society to incentivise them to strengthen resilience to IF. The programme also equips IF leads across the network with an ODA and non-ODA funded ‘Resilience Fund’. The purpose of this fund is to galvanise action against IF in partner jurisdiction through short-term and small-scale catalytic projects and activities. Towards the end of the performance period, an additional output was added via an addendum - funding towards a Pacific World Bank (WB) Correspondent Banking Relationship (CBR) Multi Donor Trust Fund (MDTF) project. This arose due to an opportunity to join likeminded international donors such as the US, Japan, and Korea to co-fund a WB project which aims to address the withdrawal – the fastest withdrawal in the world - of CBR in the Pacific region.

Collectively, the two components aim to enhance resilience against the international IF which most undermines the UK and its international interests.

Summary supporting narrative for the overall score in this review

The programme has performed well in its first year, scoring an A for its overall output score. Across four realistic, albeit stretching outputs, almost all indicators were either solidly met or exceeded. Output 1, which focusses on establishing the key personnel, systems and processes required to deliver both ICE and the IF policy advisor network’s goals, was achieved at pace, scoring an A. This set the stage for successful programme delivery under outputs 2-4. Output 2 assesses performance of ICE’s analytical function, which has produced various, largely well-received product types to enhance understanding of IF issues, such as a horizon scanning threat assessment, and a collaboration with the NECC. This output received an A. Output 3 covered ICE’s response-orientated capability, the impact of the IF Resilience Fund, and the overall policy and strategy impact of ICE products. ICE research products received customer feedback that considerably exceeded expectations while a high percentage of Resilience Fund projects produced the intended catalysing effect on anti IF activity in partner jurisdictions. The output therefore scored an A+. Output 4 addresses ICE’s monitoring, evaluation and learning offer. Clear progress has been made in demonstrating ICE’s capability across these three areas, including demonstratable thought leadership on an innovative IF measurement project. This scored an A. In line with best practice, outcomes were also measured (to provide baselines for future annual reviews and against identified targets where possible). Clear impact was found against both programme outcomes. The baselining exercise will enable more stretching outcome targets to be set for the next performance year.

Major lessons and recommendations for the year ahead

Following a strong inaugural year, the programme should prioritise demonstrating full delivery of its ‘stage one’ (of three ambition stages) targets as per the business case, then seek senior approval to transition to the next stage. If the programme continues on its current trajectory, and with sufficient supporting central capacity, this should be feasible within its next performance year. Consideration should also be given to which programme outputs can be expedited to support the Foreign Secretary’s Campaign on IF. While conducting the AR, there was a notable difference in the balance of indicators across the network and ICE branches of the programme. Network indicators were fewer and were more outcome related. ICE had more indicators, with many of these covering activity or output level work. This imbalance should be resolved going forward. Various minor lessons are also offered under each output e.g., adding an output to the log frame to guide the programme’s contribution to the WB MDTF project should be prioritised and a more granular, activity or output level indicator to assess IF lead effectiveness in addition to outcome harvesting would also be beneficial.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Combatting International Illicit Finance: Accelerating the 2030 Agenda’s business case outlines that the programme’s intended impact is to ‘enhance international system resilience to illicit finance that undermines UK and developing countries’ interests’. This long-term change is to be delivered through two outcomes which can be summarised as improving understanding of IF issues and enhancing global responses:

- Improved, shared, UK and partner understanding of, and preparedness for, international illicit finance dynamics, risks and vulnerabilities.
- Improved UK response, and support to international partners’ responses, to international illicit finance.
In the detailed theory of change (ToC), Six outputs flow into these two outcomes:
- ICE established, piloted, and four-year strategy developed
- ICE research, analysis, horizon scanning, and response products delivered and used to inform UK and our partners’ policymaking and responses
- ICE monitoring, evaluation and learning function delivers high quality evidence on effective approaches to IF and informs iterative, adaptive management of ICE
- Creation, development and mobilisation of ICE partnerships with think tanks, academia, NGOs, and the private sector across ICE’s products
- Expanded network of illicit finance leads delivers partnerships, political engagement and policy influencing
- ICE advisory support and expert deployments, and IF leads funded activities, provide nimble and targeted expertise to FCDO and UK partners
During the mobilisation phase of the programme, a logframe was created to guide delivery against the programme’s ‘stage one’ ambition targets. This level of ambition prioritises establishing necessary personnel, implementing governance and quality assurance systems, and establishing proof of concept across key programme functions with FCDO and HMG colleagues. It is the first of three levels of ambition set out in the business case (e.g., external ICE partnerships with the private sector are proposed as a high ambition phase target). As part of the logframe development process, the business case’s impact statement and outcomes have been slightly reworded to enhance their clarity. The importance of a harms-based approach towards prioritisation, consistent with HMG’s conceptual approach to prioritisation, has also been emphasised. Nonetheless, it remains consistent with the original ToC while outputs have also been consolidated from six into four to better align under each outcome.

The rephrased impact statement and outcomes are:

Impact: enhanced UK and UK partner resilience to the illicit finance which most harms UK international interests
Outcome 1: Improved UK and partner understanding of IF dynamics, enabling effective prioritisation and targeting of IF and enhanced preparedness to respond
Outcome 2: More, and more effective UK and partner anti IF interventions which reduce IF risk factors associated with the greatest harms to UK international interests

The evidence underpinning the programme, and its theory of change remain valid. The Integrated Review (IR) presented IF as one of the ‘transnational challenges of the decade’, and a compelling Foreign Affairs Committee report outlines the breadth and magnitude of harms caused and enabled by IF to the UK’s international interests: ‘[it] undermines our national security by supporting corrupt and autocratic regimes around the world, subverts our rule-of-law systems to hide and protect ill-gotten assets, deprives the world’s poorest communities of resources, prices citizens out of our housing market and infiltrates our academic and democratic institutions’.

In the year since the programme was launched, IF continues to pose a major threat to a wide range of UK domestic and international interests. Moreover, the multilateral architecture designed to combat illicit finance has come under increasing strain. To buttress global action and ensure that the UK is playing a leading role, the Foreign Secretary has also launched a campaign to ‘clamp down on corruption and illicit finance’[1]. This will entail a greater effort across HMG and FCDO posts to address global and regional IF issues.
[1] https://www.gov.uk/government/news/uk-cracks-down-on-dirty-money-with-fresh-sanctions

Two gaps in UK capability were identified by the programme design consultation with OGDs, civil society, and the private sector: 1) detailed, shared understanding of IF issues; and 2) effective HMG and partner country response capability. Both remain challenges to addressing IF globally and to delivery of the Foreign Secretary’s vision. Accordingly, the two main programme outcomes: 1) enhancing the UK and our partners’ understanding of IF and 2) improving the collective ability to effectively respond to IF, continue to act as clear lodestars for ongoing programme delivery.

The addition of the £500,000 MDTF project via an addendum late in Q4 is consistent with both the programme’s outcomes. The MDTF project has three major outputs. The first output isa feasibility study to inform the design of the regional Pacific payments aggregation mechanism, with the aim that this will provide a more medium-term, sustainable solution to the challenge of reduced Correspondent Banking Relationships (CBRs) in the Pacific. This output aligns closely with outcome one in the ToC. The second output is technical assistance to support Pacific Island Countries (PIC)s and eligible financial institutions to improve compliance with international AML/CFT standards, and to help them access the CBR services under the project delivered by World Bank experts. The third output is investment in payment system infrastructure. The MDTF project contributes to outcome two and work to incorporate these into the Theory of Change and develop a log frame output is underway.

In terms of stakeholder engagement, for the ICE programme component, a cross HMG reference group with representation across HMG has been established to ensure ongoing alignment with other HMG capabilities and to seek feedback on ICE outputs. A survey was also conducted with reference group members to inform ICE’s strategic direction for this annual review. Customers of ICE products also provide feedback via a project completion feedback process. There is also comprehensive internal quality assurance process for each product. IF leads have distinct groups of stakeholders per jurisdiction, so do not have a single reference group, but do each own a Country Action Plan (CAP) co-created and discussed with relevant cross HMG stakeholders at Post.

ICE and the IF Network do not engage directly with children or vulnerable groups. However, for each ICE and Resilience Fund agreement with an external partner, their commitment to safeguarding has been scrutinised at the enhanced due diligence and selection stages and will be kept under regular review throughout the delivery of the programme. In terms of Public Sector Equality Duty, there has been no impact on protected characteristics because ICE, the IF Network and IF Resilience Fund focus on generating analysis, evidence, and lessons, and influencing reforms and political will.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is delivering well against all four output indicators (with a fifth in development to cover the MDTF project), while making clear progress against outcomes. While more ambitious quantitative and qualitative targets will need to be assigned for the new performance year, the programme appears fully on track to deliver its ‘stage one’ targets.

Feedback on ICE from Reference Group stakeholders validates the view that ICE is increasing HMG understanding and preparedness, with all respondents signalling, in response to a 5-point Likert scale, that ICE adds either a great deal, or a lot of value to HMG’s IF capability. Illustrative qualitative and constructive feedback includes: ‘doing a top job already, do teach-ins / lunch and learn sessions’ and ‘ICE is blossoming in its professionalism… That said, I believe there is scope to harness a wider contributor pool, across government and academia, to both exponentially increase your outputs and decrease pressure on your immediate team when it comes to delivering updates at such meetings and wider engagement’. Aligned to such feedback, for next year, the ICE team also intends to increase external engagement through more open procurement and the delivery of public good research. At outcome level, 70% of ICE projects were found to have impacted policy, strategy or programming. And the overall customer satisfaction score was 83% across all completed, assessed products.

The network is making a considerable contribution to outcome two, and the programme’s overall impact via IF lead influencing in host jurisdictions and impact from Resilience Fund projects. An outcome harvesting exercise conduced for the Annual Review assessed examples of evidencable ‘real world’ changes due to IF lead activity. It found seven clear cases, across Kenya, Nigeria, Mauritius, Moldova and Cyprus of IF leads collaborating with stakeholders to contribute to tangible changes in this performance year which have increased the resilience of partner jurisdictions against IF. Rated on a 3-point scale, with 3 representing likely significant, sustainable changes, to 1 representing limited and/or unsustainable changes, two of these examples were graded as ‘3’ - significant and sustainable, with the remaining five scoring a ‘2’. Examples include the IF lead covering Cyprus being integral to the creation of a National Sanctions Implementation Unit to tackle IF associated with Russia, the IF lead in Mauritius supporting reforms required to enable a formal application to accede to the OECD Working Group on Bribery (WGB), and the IF lead covering Moldova securing UK expertise to support Moldovan partners investigate illicit finance issues related to cryptocurrencies. Seven of eight Resilience Fund projects were also found to have made a clear, attributable impact in galvanising anti IF activity in partner countries. For the coming year, this IF lead outcome harvesting exercise sets a benchmark for the network to exceed, and there are plans to raise the profile of the Resilience Fund among IF leads in non-ODA eligible jurisdictions to further increase its impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue based on its own merits and considering the wider strategic and political context, including that it provides an anchor for the Foreign Secretary’s IF campaign. It delivered well against log frame targets during its inception year, which have guided the programme to establish necessary personnel and systems, demonstrate proof of concept across its various functions, and drive international influencing activity in key ODA eligible jurisdictions.

Now that all baseline capabilities have been effectively established, focus should be on conclusively demonstrating full, high-quality delivery of all ‘stage one’ delivery targets over the performance year. Indeed, expedited programme progress to meet stage two targets may be advisable given likely increased demand on programme services due to the Foreign Secretary’s IF campaign.

## C. DETAILED OUTPUT SCORING

Output Title	Delivery of Key Personnel, Systems and Processes
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
1.1 Staffing Recruited	8 ICE team members recruited, 2 additional network posts	Moderately exceeded. A full ICE team of 8 individuals, covering various ICE functions, has been established. This consists of staff migrated from predecessor programming, internal FCDO recruitment and external recruitment. 2 new IF lead roles were created, recruited and deployed to South Africa and India during review period.
1.2 HMG Reference Group Established	Group convened by September 2024	Achieved. The first cross HMG reference group meeting was held in August 2024 with two subsequent meetings. All have been well attended with representatives from HMT, Home Office, National Crime Agency, HMRC and OGDs. Members have been surveyed with all respondents indicating that they find the Group value-adding and that ICE adds constructively to HMG’s IF capability.
1.3 Identify preferred ICE expert deployment scale up delivery option	Option identified by end March 2025	Achieved. ICE has successfully identified and implanted a preferred delivery option method for scaling up expert deployments. Alongside continuing to utilise the existing option of the Conflict Stabilisation Group (CSG) expert deployment roster for certain time sensitive projects, ICE has also developed its own External Partnership Function with 50 experts (both individuals and firms) within the non-HMG community to provide expert competition for delivery of ICE products.
1.4 Enhanced reporting tools developed and piloted with network leads	Enacted by end March 2025	Achieved. A new outcome harvesting approach, which collates and measures real world changes in host jurisdictions, has been introduced for programme funded IF leads. This approach draws on lessons learned from relevant programming such as the Combatting Illicit Economies Programme. This has enabled a baselining exercise to inform next year’s targets.

Briefly describe the output’s activities and provide supporting narrative for the score.

The purpose of this output is to stand up the necessary personnel, systems and processes to deliver against the stage one targets set out in the business case, primarily pertaining to the ICE programme component due to it being a new capability. The pace and quality of progress was therefore a prerequisite for broader delivery. In its initial year, the programme has performed well against output 1., establishing a full ICE team covering the various planned functions, expanding the IF network into two new jurisdictions/emerging financial centres, and establishing effective governance and monitoring systems to inform ongoing strategic direction and performance of the IF network.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output Adjustment. For ICE, a staffing baseline has now been achieved. However, for the IF lead network, there will be a greater effort over the coming year to expand it into new jurisdictions. The programme could consider adjusting the indicators and weighting of this output to prioritise an expanded and strengthened IF lead network over the new performance year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Ongoing Network Reporting Improvements. The new outcome harvesting reporting system delivered through output 1.4 is an improved way to assess the performance of the IF lead network compared to the previous reliance on the End of Year process. However, the programme may want to consider moving beyond annual outcome harvesting to also include activity/output level reporting. As an example, IF leads reporting their progress against newly developed jurisdiction specific campaign delivery and engagement plans could be incorporated into the log frame. Political access and influencing reporting mechanisms could also be explored to capture the type of activity conducted by network leads. This will also help balance the notable difference between outcome focused indicators for network delivery, and the more activity focused indicators relating to ICE outputs.
While only certain ODA funded roles are currently funded by the programme, there would also be merit in the whole network, rather than simply programme funded members of the network participating in activity level reporting systems to ensure ongoing assessment of the whole network’s operational performance in addition to its outcomes

Network Upscaling. In addition to funding the existing network in ODA eligible jurisdictions, progress has been made in recruiting and deploying IF leads to two new jurisdictions identified as emerging financial centres – India and South Africa - in this programme year. However, the programme business case outlines 5 additional IF leads in total as the lower level of ambition goal to ensure that IF has nowhere to hide. Progress towards this goal should be expedited given the long lead time between advertising and deployment of overseas roles, though it is recognised that the pace will depend on central staffing capacity to manage the process to identify new jurisdictions and consequent HR processes.

Reviewing Governance Arrangements.
The overall strategic and governance context framing IFAC’s agenda has changed since the programme’s design. ICE is now docked into the SCS IF campaign board which is a positive step. It The programme may also want to consider alignment with planning for future xHMG FS IF campaign and Anti-Corruption Strategy 2 governance to complement the ICE reference group which serves primarily as a venue for communications on the development and findings of ICE products.

Consideration should be given to broader IF network governance. IF leads in non-programme funded network, Tier 1 jurisdictions currently benefit from a dedicated working group and an SCS sponsor that monitor progress against CAPs. Programme funded IF leads, and other non-Tier 1 IF leads, could potentially also benefit from more systematic HMG oversight and performance assessment of their CAPs. Across the whole network, consideration should be given to defining and monitoring network contributions to the FS campaign.

In terms of the Resilience Fund, presently, the programme SRO considers individual proposals on an ad hoc basis. Rather than the SRO reviewing and approving requests on a rolling basis, considerations could be given to establishing an internal Resilience Fund Board and a formal call-for-proposal windows for Fund bids to ensure more strategic oversight of, and consistent approach to the Fund’s use.

Output Title	Value-adding evidence products produced by ICE and effectively disseminated to inform the UK and our partners' policymaking and response and in-depth analysis of priority country dynamics by IF leads
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
2.1 Internally delivered on demand products	4	3. Target moderately underachieved. These were either delivered or managed by Analysts within ICE: / ‘In-depth assessment of IF risks in India to UK interests’, delivered internally Customer: SOCnet regional coordinator. 90% product satisfaction. / ‘Nigerian crypto market analysis’, delivered in collaboration with an external consultant Customer: Nigeria IF lead. 60% product satisfaction. / ‘Illicit Finance Threat to UK interests in Western Europe’ delivered by RUSI’ Customer: SOCnet Regional Coordinator. 85% product satisfaction.
2.2 Horizon scanning products	1 delivered by end March 2025	2. Target moderately exceeded. A comprehensive ‘IF Trend Analysis’, developed through surveys and workshops with OGDs was completed. This identifies ongoing and emerging IF trends which impact on UK international interests. / A second project ‘Illicit Finance’ Data Mapping Project was conducted with the FCDO’s Global Insights Unit to build ICE and HMG stakeholders understanding of the illicit finance data landscape.
2.3 Collaborative projects with the NECC	1 delivered by end March 2025	2. Moderately Exceeded. The ‘International Illicit Finance Strategy Threat Picture was delivered in partnership with the NECC. The FCDO contribution drew on international trends identified as part of the IF Trends Analysis, with the NECC providing content drawn from operational intelligence. A second collaboration with the NECC assessment on Serious and Organised Crime and state threats’ risks posed by the Central Bank Digital Currencies (CBDC), a precursor for an ICE Alternative Payment system impact assessment.
2.4 Average cumulative customer approval score	>70%	Moderately exceeded 78%. There was also evidence of customer satisfaction with the overall process of commissioning ICE products, with an average score of 83%.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output establishes ICE’s analytical capacity and demonstrates proof of concept to HMG stakeholders and customers across a range of products while fostering collaboration with relevant HMG capabilities. Examples included collaborations with the NECC and customer led, ‘on-demand’ products. In the programme’s first year, delivery has largely met quantitative expectations with the successful delivery of a variety of product types across different issues (both IF typologies and geographies). Customer feedback, which assessed product satisfaction out of 100%, on average, has surpassed service quality aspirations. There was however one exception – the Nigerian crypto market analysis report - which was assessed below the target feedback level, with both the content and project process e.g., a lengthy procurement negotiation receiving constructive criticism

There is mixed evidence of the demonstrable impact of some ICE analytical products significantly informing UK and our partners' policymaking and responses on IF. This partly reflects challenges tangibly measuring the impact of enhanced understanding and has partly been outside the control of the team e.g. the International Illicit Finance Strategy Threat Picture was commissioned for a cross HMG strategy which was later paused however it has subsequently influenced the Anti-Corruption Strategy. In contrast, the IF Trends Analysis report which whilst an integral step in developing ICE’ horizon scanning and internal ICE prioritisation processes, it has not yet materialised demonstrable impact on policy, programming or strategy. Likewise, there is no clear evidence of the Data Mapping Project producing a tangible impact (albeit this is viewed as a preparatory project for later collaborations).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Clarify inhouse vs. externally delivered targets. The original intention was for all 2.1 products to be delivered by FCDO staff to showcase internal capability. Due to the highly specialised subject matter of one product i.e., Nigerian crypto market analysis, and capacity constraints when an additional product enquiry was received (Illicit Finance Threat to UK interests in Western Europe) two products under this output were delivered via delivery partners with oversight and input from ICE analysts. These have been included within output 2.1 due to it being the most relevant output for their inclusion.

There is merit in deploying external support where appropriate. However, if ICE does intend to develop a more comprehensive, externally delivered offer (albeit overseen by ICE analysts), it would be advisable to produce a new log frame output dedicated to those products to ensure clarity over what is being measured.

Evaluate analytical product impact. Currently the impact of analytical projects is captured in output 3.5, along with all other product types (i.e., respond orientated and MEL outputs) A standalone output reflecting the policy and programmatic impact of analytical products may also add value. Furthermore, given the inherent difficulties of attributing policy impact to analytical products, an output focused on measuring the extent to which analytical outputs have increased customer and stakeholder understanding could also be considered. Finally, all products are given a total feedback score by customers. Most feature considerable inputs from both ICE’s ‘understand’ analysts and ‘respond’ governance advisers. It may be advisable to ask customers both the degree to which the product increased their understanding of IF issues, and the extent to which it prepared them to combat IF. This would enable more accurate performance evaluation of the two services provided by ICE.

Horizon Scanning product impact. Horizon scanning products are, by definition, speculative. As such, they will typically not have the same immediate impact nor customer base as on-demand products. Nonetheless, going forward, consideration should be given to ensuring that 1) horizon scanning products are prioritised and resourced according to likely impact, 2) sufficient effort is spent after project completion in promoting product findings and their utilisation e.g., influencing future ICE project selection and 3) development of a meaningful feedback process for non-customer led products which do not have an easily identifiable customer upon which scores would be provided.

IF Lead Contribution to Output 2
The output description refers to ‘in-depth analysis of priority country dynamics by IF leads’. This is captured in Country Action Plans. It is not however measured via an output indicator. To that end, either it should be removed from output description or formally incorporated.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Delivery partner selection. Customer satisfaction with products delivered via consultants was notably lower than that of products delivered inhouse (largely driven by a 60% score for the Nigeria project).
Interviews with ICE analysts highlight that the team has considered how to respond to this feedback and is more likely to rely on the new ICE external partnerships’ framework or open procurement in future to draw on a wider pool of delivery partners.

Furthering intra HMG collaboration. The initial NECC collaborations served to build relationships and clarify remits. Further collaborations on joint products with clear customers would be beneficial. A proposed NECC liaison in the business case should also be a priority to deepen institutional relationships.

Output Title	HMG better prepared to address IF challenges with actionable recommendations, action plans etc., and successful enabling actions (e.g., small-scale catalytical projects) to galvanise longer term partner commitment.
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
3.1 Internally delivered advisory inputs	2	3. Moderately exceeded. ICE’s response team provided advisory input on: / Advisory: The British Embassy Baghdad (BEB)’s programme footprint and engaged with consultants conducting a political economy analysis. / Customer: Programme Manager, BEB. / Advisory: The British Office Sudan (BOS) requested advice on their approach to illicit finance and the functioning of the war economy within the Sudanese conflict. / Customer: Private Sector Development Advisor, BOS / Advisory: British High Commission Dhaka’s plans to support an independent Financial Intelligence Unit in Bangladesh. Customer: Governance Adviser, British High Commission Dhaka.
3.2 External expert support /deployments	2 by end March 2025	2. Achieved: / Project: utilising key subject matter experts, support the British High Commission Nairobi to navigate a key window for anti-corruption reform by developing a series of proposals on anti-corruption (delivered by Deployable Civilian Expert) Customer: IF Lead, British High Commission Kenya. 85% product satisfaction score. / Project: steer the FATF-style regional body for Eastern and Southern Africa to develop innovative and credible options for a training and technical assistance offer, with the core analysis (delivered by a PwC project team). 70% product satisfaction score. Customer: IF lead in Mauritius and the Seychelles. / [@Arthur to decide on Bahamas] / There are also two ongoing deployments which will be accounted for in the next annual review.
3.3 Internally delivered on demand products	2	2. Achieved: / Recommendations for the Iran Unit to strengthen their response to Iranian-linked illicit finance. Customer: Head of Programming, Iran Unit. 90% product satisfaction score. / A desk-based assessment of the potential illicit finance insurance risks in Bermuda. Customer: IF lead for Bermuda, Cayman, BVI. 100% product satisfaction score.
3.4 Average cumulative customer approval score	>70%	87%Substantially exceeded. [need to double check this if we use the products above] / External support/deployments: average 78% / Internally delivered products: average 95%
3.5 % of ICE projects shown to have influenced policy, strategy or programming	>70%	70%. For this output, completed horizon scanning, on demand products, NECC collaborations and external support/deployments were reviewed according to customer feedback. This was based on a feedback form which asked customers directly whether the product influenced policy, strategy and programming and ICE product lead interviews. Of 10 completed projects, 7 produced a clear, demonstrable impact. / On demand 4/5 Product Impact 80% / Horizon Scanning 0/2 Product Impact 0% NECC collaboration 1/2 Product Impact 50% External support deployments 2/2 Product Impact 100%
3.6 % of IF resilience projects shown to have catalysed anti IF activity (based on qualitative case study annual assessment)	>70% TBC	88%. Substantially exceeded. Eight Resilience Fund projects were delivered over the review period. Seven were funded (another two remain live) and one non-ODA project. In total, seven of these projects made an attributable, catalysing impact within their contexts. / A £3,000 project explored the current state of play of cryptocurrencies in Moldova and examined the last few months for changes which could indicate interference. This enabled Moldova to successfully investigate strands of election interference. / A £20,000 project to a supplier to assess the Somali financial sector and outline options for unlocking international payments and international investments across the Somali and international financial ecosystem. This project will closely inform the design of a new FCDO economic governance programme, which will aim to strengthen Somalia’s fiscal sustainability by supporting domestic revenue mobilisation and public financial management and targeting the most pressing barriers to investment, trade and growth. / A £53,000 project supported an external expert to embed within the Mauritius Financial Crimes Commission (FCC) to support the successful transition of the new organisation from the Independent Commission Against Corruption (ICAC). This galvanised interest from the Attorney General for a further project outlining law enforcement reform options. / A £21.000 non-ODA project to fund a multi-stakeholder roundtable on Illicit Gold at the Prospectors and Miners Association of Canada (PDAC) Annual Convention. This roundtable fostered new conversations between HMG, and organisations and individuals active in the gold industry and in combatting illicit gold. The result was to deepen HMG engagement on gold with the United Nations Office on Drugs and Crime (UNODC), strengthen the relationship with SwissAid and increase HMG’s profile in the illicit gold space. This has accelerated work towards establishing a new public-private partnership on gold, primarily between the UK Government and UK gold industry but with input from international banks and with engagement on international issues / Two projects were conducted in Nigeria: / Seed funding (£19,000) to FinTech Nigeria contributed to establishing a good legal framework for Virtual Asset Service Providers in Nigeria through the passage of the Investment and Securities Act and underlying regulations. / A £25,300 project to recruit a DCE enabled the development of a monitoring and accountability framework for the cross-government AML/CFT Inter-Ministerial Committee.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on ensuring that HMG is better prepared to respond to IF challenges though the delivery of high quality, advisory response, and via Resilience Fund projects generating sustainable action in partner countries. ICE has delivered well against outputs, with customer feedback significantly above target expectations across the different service types. There is also clear evidence, drawn from customer feedback, of ICE research and deployment recommendations influencing policy, strategy or programming. For example, the Kenya deployment also informed Government of Kenya priorities in response to protests and will inform future HMG programming. Iran Unit customers also report that the recommendations had a strong impact on the programming for the forthcoming year. The Resilience Fund has also exhibited clear evidence of ‘on-the-ground’ value-add, although almost exclusively in ODA eligible jurisdictions. By supporting a wide variety of short-term interventions aimed at galvanising sustainable domestic action, it has compounded IF lead impact in an efficient and cost-effective manner.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Multi Donor Trust Fund (MDTF) project. The programme team should prioritise developing indicators to assess the effectiveness of funding towards the World Bank Multi Donor Trust Fund (MDTF) project.

IF lead reporting. In addition to an outcome level output, the programme could consider the merits of including an output which assesses IF leads’ influencing effectiveness at activity level. This could relate to existing country action plans, or a new measure of political access and influencing.

Impact specification. As per output 2., a dedicated output covering the impact of respond products would be advisable.

Advisory input feedback. Advisory inputs do not currently receive formal feedback. It is important to not overburden customers, but a short feedback template could help produce customer feedback.

Resilience Fund: Output 3.6 could be disaggregated to cover the two sides of Resilience Fund – ODA and non-ODA funding – to better capture and assess how the Fund is used in different jurisdiction typologies e.g. established vs emerging global financial centres.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Resilience Fund Call for Proposals. To-date, the process to secure Resilience Fund support has been through submitting bids to the SRO on a rolling basis. Establishing a Resilience Fund board and formalising a regular call for proposals window could provide more strategic oversight of the Fund Fund, while increasing improved predictability on its financial forecasting. There could also be targeted communications to IF leads in non-ODA eligible posts raising the profile of the non-ODA dimension of the Resilience Fund. This may help rebalance the current discrepancy whereby all but one Resilience Fund projects were ODA funded.

Importance of identifying customers with policy ownership. The Iran product was commissioned by a policy stakeholder rather than a policy owner. This has limited the impact of the product. A general lesson can be drawn for future products regarding the benefits of securing policy owner buy-in from the outset.

Route to market. Due to the specialised nature of the FATF-style regional body for Eastern and Southern Africa project, a decision was made to recruit an external delivery partner at pace through FCDO’s Expert Advisory Call Down Service (EACDS) procurement framework. ICE’s initial understanding of the EACDS framework was that it would allow for a high degree of flexibility in choosing the composition of the delivery partner’s team. However, in practice, there was limited scope to change the team once the project was initiated. Despite the project meeting customer satisfaction expectations, aided by considerable input from ICE advisers, a general lesson – akin to the experience with the Nigeria crypto market project – has been drawn that open tender is a better means of procurement.

Importance of investing in load bearing, long-term relationships with wider xHMG stakeholders. For same project as the above recommendation, a key advantage was that HMT supported IFAC in attending an ESAAMLG plenary, in exceptional circumstances, which improved upon the outcome of the project significantly. The reason HMT were willing to make an exception was because of strong working level relationships. Another key advantage was strong relationships with key members of the ESAAMLG Secretariat and Membership, which ensured, in a light touch way, that the recommendations of the consultancy team were politically informed and politically viable.

Output Title	Enhanced Monitoring, Evaluation and Learning on IF issues across FCDO and HMG
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
4.1 Project to develop HMG and donor community approach to IF reporting measuring and monitoring	1 by end March	1. Achieved. After evaluating options, ICE has initiated an innovative project delivered as a collaboration between University of Sussex and Tax Justice Network titled ‘A Dynamic Global Dashboard of Illicit Finance Vulnerabilities’. / The purpose of this project is to advance outcome and impact level measurement of IF and its enabling factors e.g., regulatory environments. The intended project impact is that HMG, and other donors pivot towards the use of proxy-based measures to target and monitor bilateral IF risks. The project should also contribute to assessing the effectiveness of IF interventions. / To increase the likely impact, a relevant internal customer has been identified for this project who will provide feedback upon its completion.
4.2 On demand projects/advisory inputs	3	3. Achieved. In addition to output 4.1., three on demand projects/advisory products were initiated or delivered. The first is complete, whereas the latter two were initiated in quarter four and are ongoing: / Advisory: Recommendations for the Central Asia team on programming priorities Customer: programme manager, Central Asia Development and Programme Team / Advisory: A performance management framework for the IF campaign Customer: Head of Strategy, Illicit Finance and Anti-Corruption Department. / Project: Mapping HMG’s IF/AC Footprint. Customer: Head of the Tackling Illicit Finance and Corruption Programme, Integrated Security Fund
4.3 Develop IF Learning Offer	By end April options agreed	Achieved. In response to departmental demand for a more comprehensive learning offer on IF technical skills, ICE developed a range of options with a preferred recommendation for a new departmental ‘Capability’ focused learning and development programme. / This has garnered support from the senior management and the wider department and is in the process of being rolled out as part of the department’s new L&D strategy It will feature ICE specifying the technical expectations of IFAC policy advisers, signposting and generating training content to ensure upskilling against these skills, and the creation of a dedicated community of practice centred on collective capability development. / Various user-friendly learning tools have also been developed including an ‘Explainer’ tool which was circulated to all FCDO posts., and an ‘Understanding and Responding to Illicit Finance How to Guide step by step guide to tackling IF which has received positive feedback from stakeholders and has been used to guide in-country analysis.
4.4 Seminars exploring understanding, respond and MEL themes.	3	3. Achieved. ICE facilitated seminars on: / ‘The work of the IF Laboratory’ delivered by Dr Matt Collin / ‘Illicit Finance Threats in Western Europe’ delivered by the Royal United Services Institute / ‘Iranian cryptocurrency activity’ by Chainanalysis
4.5 Average cumulative customer approval score	>70%	N/A. As all products are currently in development or finalisation stages, there is no average score yet.

Briefly describe the output’s activities and provide supporting narrative for the score. Following recruitment of a MEL adviser in July, this output has focused on addressing wide-ranging MEL requirements of the HMG community and the broader donor landscape. Despite being a challenging policy area to conduct MEL activities due to issues with measuring IF itself, progress has been made on all the outputs indicators. The most ambitious project, conducted against under output 4.1, demonstrates proactive ICE thought leadership in tackling the perennial limitations of IF policy and programmatic monitoring and evaluation. By novelly combining two previously unconnected estimation methods i.e., proxy-based methods., and actor focused FDI analysis., it should generate a much clearer picture of the nature and scale of IF flows while generating clear indicators which the donor community can aim to address. This will illuminate connections between the IF network jurisdictions and beyond. The proposal and agreement for a new department wide learning and development approach is also a notable advance on existing training provision.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Clarify target expectations. The log frame could be clearer on whether targets are intended to be completely or simply initiated per performance year (a point of clarification which other quantitative outputs would also benefit from). Given this was the programme’s inaugural year, and that the overall output was ambitious for one member of staff recruited in July, both completed and ongoing projects and advisory inputs have been included under output 4.3. For future years., the log frame should specify a target timeframe.

Differentiate advisory and project targets. There may also be merit in separate outputs for advisory inputs and on demand projects. There is a significant difference in the time, and cost of projects and advisory support, which justifies evaluating delivery of each individually.

Seminar feedback mechanism. As ICE continues to mature its seminar offer, a qualitative feedback mechanism for stakeholders to provide input on the value-add of different seminars would be helpful.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Resource. This output is delivered by one MEL Adviser. This creates a natural resource bottleneck and raises risks around sustainability. The programme could consider increasing staff resources dedicated to this function via recruitment and/or dedicating a percentage of other members of staff towards MEL activities as ICE continues to expand.

Prioritise learning and development offer. There is clear demand for an enhanced learning and development offer on IF within FCDO. This will likely increase as the Foreign Secretary Campaign evolves. ICE should prioritise delivering the agreed upon capability offer across the department, while ensuring it is available to other interested colleagues more broadly across FCDO.

## D: VALUE FOR MONEY

Key cost drivers and performance

There have been three main cost drivers during the first year of implementation. The first is the project funded posts charged to the programme, which are essential for its delivery and offer better value for money than outsourced alternatives. These roles are managed within the Workforce Spending Target agreed by HMT and are consistent with the future workforce needs of both FCDO and the Illicit Finance and Anti-Corruption Department. The roles include 8 project funded posts within ICE, as well as 7 overseas project funded posts within the Illicit Finance Network.

The second cost driver is delivery of various projects across the IF Resilience Fund and ICE. These projects have been implemented to help enhance the FCDO country network and FCDO policy teams’ ability to further understand and deliver impact on illicit finance. As outlined in outputs 2 and 3, these projects have delivered a wide range of products which have met or surpassed the majority of expectations.

The final cost driver was a contribution towards the World Bank Pacific Correspondent Banking Relationships (CBR) Multi-Donor Trust Fund. This contribution was not part of the original business case, but the initiative presented both strategic and technical merit. It will help mitigate various political risks (e.g. China’s growing influence), builds FCDOs diplomatic credit in the Pacific region, and can be showcased as an early deliverable under the Foreign Secretary’s Illicit Finance campaign.

Cost Drivers in FY24/25 –

Project funded posts - £1,217,956.48
ICE ODA Projects - £338,329.62
ICE non-ODA Projects - £154,320.93
IF Resilience Fund ODA Projects- £299,861.17
IF Resilience Fund Non-ODA Projects - £21,600
World Bank Strengthening Pacific Correspondent Banking Trust Fund - £500,000

Total – £2,532,068.2

VfM performance compared to the original VfM proposition in the business case

There have been no changes to the original business case cost drivers or the cost of major inputs during the first year of implementation, other than taking on the additional contribution towards the World Bank Strengthening Pacific Correspondent Banking Trust Fund. The VfM performance of the programme has met the original VfM proposition in the business case.

Inhouse delivery has proven an effective, and cost-effective approach towards delivery. The original business case argued that due to the sensitive nature of the topic, the need for access to high side systems, and the avoidance of external mark-up, a Centre of Expertise comprised of specialist HMG staff would deliver the best value for money. High customer satisfaction scores validate that decision.

As ICE was a new HMG capability offering an important, on-demand service to HMG customers, the original VfM proposition also argued that it would be prudent to take a phased approach to developing its capability. This was a sensible decision, as it has driven an adaptive, iterative approach towards programme delivery with three clear stages to provide programme checkpoints. This enables the programme to be adjusted accordingly, dependent on levels of demand and learning accrued during the first level of ambition.

This flexible approach has seen the programme begin to successfully scale through its stage one targets during Year 1. On the ICE side, all necessary personnel have been recruited across the programme, while good progress is underway to expand and strengthen the IF lead network. Systems and feedback systems have also been established while delivery has been impressive across ambitious qualitative and quantitative targets on both ICE and Resilience Fund products. More recent VfM considerations have informed a sensible decision to recruit country-based staff to support IF leads in key priority jurisdictions. Using their local knowledge and expertise, these roles will help to maintain networks across government, civil society and the private sector – and they will undertake programmatic activity, provide reporting and conduct research in country.
These activities will complement the work of IF leads, while also releasing more time for IF leads to focus on influencing key interlocutors to drive tangible on-the-ground impact and deliver the Foreign Secretary’s IF campaign priorities.

Assessment of whether the programme continues to represent value for money
Based on the above analysis there is clear evidence that the programme continues to represent value for money and that the programme should continue. Indeed, in the context of the Foreign Secretary campaign on IF and dirty money whereby the whole HMG system, including FCDO posts is being steered to raise ambition further on IF, the programme, if it continues to perform, should deliver more value for money than originally assumed by catering to increased demand and opportunity from the more favourable operating context.

E: RISK

Overview of risk management

The programme has been able to deliver comfortably within an overall moderate risk appetite. There have not been any areas of pressure to that appetite. The programme does not engage directly with children, vulnerable groups, climate, and environment, nor does it have a significant gender equality aspect. In terms of monitoring risk, the programme risk register and overall risk appetite has been reviewed monthly by the Programme Responsible Officer, Head of ICE, and Senior Responsible Officer throughout the year. These regular reviews have allowed both the monitoring and mitigation of current risks, as well as allowing the assessment of newly identified risks. Throughout the year no new risks have been identified and no initial risks upgraded.

There have been no significant risks identified through the various partner due diligence assessments, either in the initial assessments or through the due diligence refresh processes. During Year 2 of the programme, all current due diligence assessments should be reviewed and updated where necessary to ensure that the assessment is still proportionate and provides assurance to the risks of the programme. Any new risks identified should be responded to and included with the risk register to help inform the overall risk assessment of the programme.

Programme funds are not being provided directly to partner Governments. However, dependent on ICE and the Illicit Finance Network’s development and future opportunities identified throughout the lifecycle of this programme, opportunities may arise to work closely with partner governments to help identify and tackle illicit finance. In these instances, funding may be delivered through third parties such as private sector organisations or think tanks. As such, when new interventions are identified the SRO for the programme will exercise their judgement on a case-by-case basis to determine what role, if any, the partnership principles should play in the management and monitoring of the intervention, in line with the PrOF Guide on Partnership Principles.

Protection of the people involved in FCDO programmes and projects, including those with protected characteristics, and of our funds, is a collective responsibility of all FCDO staff and our partner organisations. Safeguarding is integral in the delivery of ICE and the Illicit Finance Network. As such, requisite focus has been placed on the prevention of social, sexual, and environmental abuse-prevention. ICE has followed the FCDO do no harm policy and ensured that safeguarding plays a role in promoting sustainability and good VfM. ICE and the network have not engaged directly with children or vulnerable groups.

For each agreement with an external partner, whether that be a supplier sourced through the ICE External Partnership Function or a supplier identified through low value procurement their commitment to safeguarding has been scrutinised at the due diligence and selection stages and will be kept under regular review throughout the delivery of the programme. When ICE has used the Civilian Stabilisation Group roster, safeguarding has already been checked by FCDO’s Office for Conflict and Stabilisation (OCSM).Lastly, data used to further mitigate risk includes partner due diligence assessments, delivery risk chain mapping, the ICE feedback function which gathers information from FCDO teams or posts on ICE external partners, alongside this annual review process. Delivery partners have been required to provide full financial statements. Additionally, throughout the lifecycle of the programme, data will be used to inform its financial management and ensure that programme funds are monitored and managed effectively.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

ICE and the IF Resilience Fund has utilised five specific delivery routes throughout the year:

- procurement through FCDO Framework Agreements (FA)
- low value procurement (below Delegated Threshold currently £138,760 including VAT)
- delivery through a third party such as a multilateral or civil society organisation, utilising the FCDO standard Accountable Grant
- delivery via The Civilian Stabilisation Group (CSG) roster which has provided the option to utilise Deployable civilian experts as consultants.
- Programme funded staff in ICE and in the IF network
The volume of contracts and grants awarded has gradually increased during the review period, particularly as ICE and its core team has increased in size and ambition. Across both programme components (for ICE and the network), the programme has spent £814,111.72 ODA and non-ODA on delivering commercial projects. Additionally, the programme has more recently contributed £500,000 ODA to the World Bank Strengthening Pacific Correspondent Banking Trust Fund. Lastly, and key to the delivery of the programme, the project funded roles across both ICE and the IF Network have cost £1,217,956.48. Total delivery and commercial spend is therefore £2,532,068.20 for FY24/25.

There have been no issues in terms of suppliers honouring the Terms and Conditions within contracts, or with partners[2] submitting requests for payment on time. Overall, the quality of partner performance alongside the timeliness and quality relating to reporting has been very good albeit with exceptions. All delivery partners across the programme have correctly submitted accurate statements of expenditure and have provided detailed accounts of actual expenditure incurred against the approved project budgets.
[2] Delivery partners – Conflict Stabilisation Group, Chainalysis, Hook Tangaza, Fintech Association of Nigeria, Resolve, Philip Corper Consulting, Rudich Advisory, Royal United Services Institute, Threat Finance Intelligence Solutions, PricewaterhouseCoopers (PwC), Phil Mason, Global Initiative Against Transnational Organized Crime (GI-TOC), Swiss Aid, Tax Justice Network, World Bank

During the lifetime of all the projects initiated by both ICE and IF Resilience Fund, partners have been required to report directly to either a dedicated ICE Project Lead or IF Lead. This oversight has included the requirement that all projects have key reporting and delivery milestones, regular weekly/monthly update meetings (and ad hoc follow-up discussions when needed), mid-point presentations and substantive status updates, and a presentation of key findings and recommendations on completion of the project. This important process has allowed the programme to closely monitor supplier performance and delivery at regular intervals.

Via this feedback and oversight process, several lessons learned were accrued throughout the year with regards to the programme's delivery partners. For instance, we have seen minor delays with three of ICEs delivery partners around submitting final reports across three different projects. These delays were well managed by the ICE team without needing to revert to the Terms and Conditions of the contract. Clear deadlines were re-negotiated with the partners in a timely manner, which included time built in for FCDO to proofread the final report and the partner to re-draft if necessary. All payments to partners were paused pending final delivery.

One, expensive ICE experienced a lengthy negotiation period around the partner’s proposal for delivering the project. When this project finally launched, the project lacked clear direction and grip from the project team that had been proposed by the partner. This lack of direction had a material impact on the timeliness of the project. Several challenges with the project delivery team who were subcontracted by the partner also materialised, including inflexible responses to FCDO comments on the project direction. Unfortunately, FCDO had limited leverage over the sub-contractor and the partner did not meaningfully mitigate the performance issue.

Only through extensive input from the ICE Lead and IF Adviser did the project remain on track and ultimately deliver a set of strong outputs (product impact rating 80%), substantially mitigating the issues posed by the subcontractors. A specific lesson learned from this project is that ICE is inclined to not use the supplier again because of those issues experienced with the downstream subcontractor and the lack of leverage FCDO had around influencing the sub-contractors, even though the contract was awarded via a tender process and included break clauses in the contract.

A further lesson learned came from feedback provided by an early ICE customer, which has helped refine the bidding process for single source work. Significant delays occurred due to the consultants’ concerns around duty of care arrangements contained in the low value procurement contract, as well as the fee rates proposed by ICE for completing the project. There was also an issue negotiating with the consultant on the number of days required to complete the project.

The feedback from the customer indicated that this back and forth with the consultant before ICE agreed the number of working days to complete the project could have been better managed, which would have produced a more timely product. These delays occurred even though the consultant was engaged by ICE on the basis that fixed rates were already in place (ICE fee rates sit in line with the Expert Advisory Call Down Service Framework rates for consultants) and that the contractual duty of care arrangements were clearly explained to the consultant during the process.

ICE projects now require the potential partner to formally submit a proposal for delivering the project in response to a Terms of Reference developed by ICE. These Terms of Reference contain specific reference to fee rates and also clearly outline duty of care arrangements. Additionally, ICE has now commenced invite to tender processes for particular projects where it is felt that a competitive process would produce a more substantial partner driven proposals towards delivering the project.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
A wide range of activities were undertaken to inform this review. These include:
- Surveys conducted across the Illicit Finance and Anti-Corruption Department, and Reference Group participants to seek views on ICE value-add and product feedback.
- Interviews held with ICE staff and customers
- Outcome harvesting undertaken with IF leads
- Interviews with users of the Resilience Fund to assess the real-world impact of projects, and identify lessons learned.

All product feedback forms, and minutes from ICE product stock take meetings were also considered. Collectively, this provided the reviewer with a considerable amount of evidence to conduct the review.

Evidence
There have been no significant changes in the evidence base underpinning the programme since it was launched.

Learning
As outlined, ICE has a rigorous process for evaluating both the quality of each project process and product outputs. This concludes with a detailed feedback form for each product. This has generated various lessons covered in the outputs and value for money section of this review, including:
- The importance of clarifying customers with policy leadership from the outset
- The importance of getting the procurement framework right to deliver external projects; and
- Clarifying inhouse vs. externally delivered targets.

All project lessons are shared with reference group members for discussion and dissemination.

For the next year, two main learning related recommendations are:

Expedited delivery of the ‘IF Learning Offer’ to ensure ICE is responsive to clear demand within the department, and wider HMG, for more formalised, structured learning and development. This will be important against the backdrop of the FS’ campaign and address a need clearly signalled in IFAC staff surveys.

A learning tool, the ‘Understanding and Responding to Illicit Finance How to Guide’ has been designed by ICE to provide a best practice outline of generic steps that should be taken to understand and address IF challenges. Following IF lead feedback, this could be complemented with more formalised, contextual learning on what has worked most effectively to build strong partnerships against IF at the country level among IF leads. While the challenges in each context will differ, there will likely be generalisable insights based on existing IF lead experience which new leads, and the wider organisation may benefit from.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A