## Annual Review Template

Title: Partnership for Agile Governance and Climate Engagement (PACE)
Programme Value £ (full life): £38.8 million		Review date: March 2025
Programme Code: 301036	AMP start date: 18/10/2023	AMP end date: 19/09/2028

Summary of Programme Performance
Year	2024	2025	2026	2027	2028
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004382.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301036 Documents

A. SUMMARY AND OVERVIEW

Description of programme

This Annual Review (AR) covers the period from May 2024 to April 2025, which saw the completion of the procurement process across various programme components, the finalisation of the programme inception period, and the start of the implementation phase.

Partnership for Agile Governance and Climate Engagement (PACE) is a 4-year £38.8 million programme supporting more accountable and inclusive institutions to respond to Nigeria’s interrelated governance and climate change challenges. Between 10% to 30% of the programme is UK International Climate Finance (ICF) eligible.

PACE is implemented in three states in Northern Nigeria (Kaduna, Kano and Jigawa), with targeted strategic engagement at Federal or regional level. The programme is designed to: (1) support coalitions to influence government to resolve climate and governance problems affecting the poorest and most vulnerable Nigerians and hold government accountable; (2) increase state government income from internally generated revenue; (3) mainstream climate action in the centre of state government policy, planning and budgets; and (4) strengthen democratic institutions.

PACE delivers through five components:

- Component 1. Issue-based coalitions - under this component, the programme facilitates coalitions of reformers in government, civil society, the private sector, politicians, and others who have an interest in positive change on governance, climate mitigation, adaptation and resilience, rapid population growth and service delivery problems. The focus is on issues or real-life problems that matter to a sufficient number of stakeholders who can mobilise and drive change.
- Component 2. Core governance capability and accountability – the programme provides technical assistance to State governments. To complement support to government, the programme builds transparency and accountability by working with civil society, the media, and communities to strengthen citizen engagement.
- Component 3. Fair power structures – this component supports democratic institutions as a central way to achieve fairer power structures and more accountable governance, and, in turn, provision of public goods and a more effective response to climate change. The programme takes an electoral cycle approach to strengthen state and non-state institutions and processes in between elections, including support to delivery of off-cycle elections between 2023 and 2027.
- Component 4. Research, evidence and learning – support through this component ensures that investments are underpinned by analysis and evidence, improving their likely effectiveness.
- Component 5. Strategic Opportunities Fund - a small portion of the PACE budget is set aside as a ‘Strategic Opportunities Fund’. This will enable the programme to flexibly respond to political opportunities as they arise. This is a flexible resource where there is a clear added value that cannot be delivered through other components.

The sourcing strategy in the PACE business case envisaged:
- A commercial supplier/consortium for components 1, 2, 4 and 5. Progress on this is described in Output 1.
- An MoU with USAID (now terminated by USAID), an Accountable Grant with a lead NGO, or a combination of both. This is described in Output 2.
- Flexibility to take advantage of emerging opportunities, as described in Outputs 1 and 2.

The PACE Business Case was approved by DG Africa in February 2023 and received financial approval by the Management Accounts Group in April 2023. The Business Case envisaged a year-long procurement process, and a programme start following completion of procurement. However, to ensure transparent and accountable programme management PACE went live on the date of its financial approval in April 2023 – prior to commencement of procurement. On 17 October 2023, the Development Director approved a no-cost programme extension until September 2028 to adjust for time spent on procurement and to ensure that the programme has four full years of implementation, as envisaged in its Business Case.

Summary supporting narrative for the overall score in this review
This Annual Review (AR) covers the period from May 2024 to April 2025. Progress was assessed against the pre-implementation programme logframe, which considers the procurement process, the inception period, and the start of the implementation phase.
The programme has delivered well, exceeding most expectations. Procurement of the commercial supplier was concluded ahead of schedule, while other planned instruments were signed on time. The programme team managed to onboard additional suppliers (not envisaged but enabled by the Business Case), to respond to BHC priorities.
The Inception Phase saw shifts in HMG policy priorities, which required a rethink in programme strategy and inception deliverables. Implementation of priority activities started ahead of schedule.

Major lessons and recommendations for the year ahead
- PACE needs to maintain readiness for further programme adaptations to respond to new policy priorities and ODA budget adjustments in the coming years. This includes supporting the government of Nigeria to address the institutional barriers that hinder economic growth. Continued scenario planning as well as regular communications with implementing partners and programme beneficiaries will be required to facilitate anticipated adaptations.
- With USAID, one of the key delivery partners for this component, closing its democracy portfolio, the Fair Power Structures (FPS) component of the programme needs to take a strategic decision in its approach to adapting to this reality. Going forward, the programme needs to decide on the scope of the portfolio in the light of this change, including exploring new potential partnerships.
- The FPS component needs to put in place a specific strategy for engagement and support for the 2027 general elections which are now just two years away.
- Changes in the operating environment are likely to test the resilience of the implementing partners and the programme team, requiring sensitive programme management approaches.
- In-programme coherence across components requires constant nurturing, to ensure Value for Money (VfM). Coordination mechanisms were established during the reporting year, and they need to be sustained.
- Programme complementarity across the FCDO Nigeria portfolio has been difficult to achieve. To incentivise suppliers, the PACE team has introduced complementarity targets in its results framework. Advocacy for adoption of such approaches across the wider BHC portfolio needs to continue in the next reporting year.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

As PACE is just about starting, its theory of change has not yet been actively tested. There are no proposed changes to the outcome and impact statements. The only material change concerns the intermediary outcome ‘Strengthened elections delivery and credibility’, which has been reformulated to ‘Strengthened democratic systems, processes and institutions.’ Lessons from PACE’s predecessor programme and the UK’s overall support for democracy in Nigeria over the last decade highlighted the impact of the broader democratic context on the delivery and integrity of elections. An outcome focused on just the delivery and credibility of elections was therefore considered too narrow to contribute to the impact of the programme. This modification provides a more holistic outcome that encompasses both electoral integrity and the wider underlying democratic institutions that are key to a more stable and resilient Nigeria.

The theory of change as set out in the approved Business Case is as follows:

In a context where…
The political settlement, currently sustained through access to and distribution of oil rents, is facing extreme stress because of global economic shocks, the energy transition away from fossil fuels, the impacts of climate change on Nigerian people, and the pressure of rapid population growth.
If …
- States can reduce dependency on oil revenues through increasing internal revenue generation (and access to climate finance) …
- And we support coalitions (private sector, CSOs, communities, legislatures, organisations representing women and vulnerable groups) to come together to influence government and hold them to account for delivery of public goods, including climate adaptation and resilience and social protection …
- And we support delivery and credibility of the electoral process…
- And we support states to strengthen core government processes for a better service delivery, social protection, and response to climate change…
- And we support longer-term reform processes for more inclusive power structures…
Then…
Then we generate impetus for more accountable and inclusive institutions that can respond to Nigeria’s climate change challenges.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
As PACE is in early stages of implementation, it is too early to determine whether it is on/off track to achieve the programme outcomes and impact. The year ahead will see commencement of core activities.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

In the context of the wider portfolio, governance constraints are holding back Nigeria’s ability to deliver inclusive economic growth and respond to the impacts of climate change and support mitigation, adaptation, and resilience. This matters because Nigeria is one of Africa’s largest economies and among the most climate vulnerable countries in the world, the impacts of which are already being felt with increased floods, droughts and reduced agricultural productivity. Together these factors pose a major economic, development and security challenge for Africa’s most populous country, driving instability and tensions the state can no longer contain, and inhibiting sustainable growth and prosperity. This is also a threat to UK interests, given Nigeria’s geopolitical importance and strong links to the UK.

PACE responds directly to FCDO priorities on inclusive economic growth and climate by providing technical assistance and facilitating partnerships necessary to address institutional barriers that hinder Nigeria’s development. In the inception period, the programme has showed its ability to adapt to the changing context and FCDO priorities. The programme inception reports, and work plan have provided clear entry points for FCDO to support public procurement reform, tax administration, climate investment opportunities, and pro-business legislation. For this reason, this review recommends the programme continues.

## C. DETAILED OUTPUT SCORING

Output Title	Procurement phase completed, with service provider for main contract signed, mobilised and delivering
Output number:		1	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.2: Preferred bidder identified through competitive process.	Milestone 2: June 2024 / Bids from interested potential contractors received and evaluated.	Exceeded. Bids were received in April 2024, and the evaluation took place in May 2024.
	Milestone 3: July 2024 / Evaluation completed and implementation contractor selected.	Exceeded. The evaluation was concluded in May 2024 and a DAI Europe-led consortium was recommended.
1.3: Preferred bidder contracted, mobilised and implementing.	Milestone 1: August 2024 / Implementation contractor approved and contract signed.	Exceeded. The Procurement Steering Board approved the Contract Award recommendation report in May 2024. The contract was signed on 25 June.
	Milestone 2: September 2024 / Procurement completed, with contractor mobilised and ready to commence implementation.	Exceeded: The contract start date was 15 July 2024, with contractor mobilised and ready to start work.
	Milestone 3: March 2025 / Inception phase completed with analytical studies, intervention plans, results framework, workplan and strategy finalised.	Met expectations: The final Inception deliverables were approved in March 2025, later than the target date of 15 January. However, the supplier delivered additional priority interventions not originally anticipated in the Business Case.

Briefly describe the output’s activities and provide supporting narrative for the score.

Procurement through FCDO’s Global Development Delivery (GDD) Framework was concluded ahead of schedule, with valuable support from the FCDO commercial and climate change experts. This enabled efficient and effective transitioning from Partnership to Engage, Reform and Learn (PERL), the predecessor governance programme, to PACE.

PACE officially commenced on 15 July 2024. The inception meeting established a framework for regular interaction between FCDO and the DAI Senior Management Team. DAI ensured that all contractual arrangements were in place and finalised at the end of the first month. Additionally, legacy activities from the predecessor programme were also considered, without detracting from the focus on mobilising resources to deliver the inception deliverables outlined in the programme timeline.

As contained in the Invitation to Tender, the DAI Europe team and its consortium members submitted sixteen inception deliverables to FCDO during the inception period. This includes analyses, strategies, diagnostics, workplans and reports and forming the basis for programme engagement during the implementation phase.

Some of these deliverables have required significant revisions due to several reasons. Firstly, PACE has had to undertake extensive internal consultations and coordination with over ten FCDO programmes working on aspects of climate change in Nigeria. After the UK general elections in 2024, PACE has also proactively sought to align its strategy with the missions of HMG, within its Business Case framework. Further, PACE has adopted the new results framework format developed by the Centre for Delivery for adaptive programmes, which required development of new methodologies. Finally, aid cut announcements in 2025 have impacted the finalisation of key deliverables such as strategy and workplans, requiring further prioritisation and scenario planning. All inception deliverables were approved in March 2025.

Overall, delays in the inception deliverable schedule did not have a negative impact on implementation. Priority government requests for PACE to build on the legacy of its predecessor PERL were approved in a contract amendment dated 1st October 2024. Activities started straight away, covering seven strategic areas that align with PACE outputs, as follows:
- The Open Government Partnership, including the thematic working group on Climate Change.
- Central Delivery Coordination Unit (CDCU) to strengthen performance management across thirty-six federal ministries.
- The Office of the Special Adviser to the President (SA) on Policy and Coordination towards strengthening policy capabilities across Ministries, Departments and Agencies (MDAs) while ensuring coherence and effective coordination.
- The Economic and Financial Crimes Commission (EFCC), towards achieving a fit-for-purpose organisation with a clear and structured performance management system.
- Implementing the Draft Climate Change Policy in Kano.
- Institutional assessment of the Association for Local Governments of Nigeria (ALGON).
- State-level Public Financial Management interventions (around the budget cycle).
- Capacity Building Workshop on United Nations Framework Convention on Climate Change (UNFCCC) CoP Negotiations.
The majority of these activities are embedded in the long-term implementation plans of the DAI-led components of the programme.

During the reporting period, PACE also signed a £500k Externally Financed Output, co-financing the World Bank to generate evidence on the delivery and impacts of safety net interventions in Nigeria. This intervention responds to the Business Case requirement for the programme to strengthen state and - where it is strategic - federal level social protection systems, including, potentially, shock responsive social protection.

The Bank are currently concluding the procurement of a large-scale nutrition-related endline survey; and will shortly use remaining funds for a second round of cash transfer surveys, framed as a process evaluation. The evidence generated by the World Bank will inform PACE, broader UK interventions and those of other development partners in the sector from FY2025/26.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR
- A lesson learned during the programme Early Market Engagement event in 2023 was that rigid ‘Payment by Results’ would disincentivise implementing partners from taking calculated risks and innovating to deliver the programme. PACE’s approved sourcing strategy has taken this feedback into account, and the approved payment mechanisms enable greater flexibility and innovation.
- As recommended in the previous annual review, the result framework for PACE’s implementation phase has been updated at the end of the programme inception period to incentivise learning and adaptation.
- Internal coordination mechanisms between the Governance and Climate and Nature teams have been sustained and deepened, allowing for complementarity and better VfM across the portfolio.
Lessons learned this year and recommendations for the year ahead
- PACE needs to maintain readiness for further programme adaptations to respond to new policy priorities and ODA budget adjustments in the coming years. This includes supporting the government of Nigeria to address the institutional barriers that hinger economic growth. Continued scenario planning as well as regular communications with implementing partners and programme beneficiaries will be required to facilitate anticipated adaptations.
- Changes in the operating environment are likely to test the resilience of the implementing partners and the programme team, requiring sensitive programme management approaches.
- To implement a pivot to inclusive economic growth, the DAI-led consortium will need to reassess skillsets and if necessary, amend the programme team composition to ensure that it is well equipped to respond to strategic priorities.
- In-programme coherence across components requires constant nurturing, to ensure VfM. Coordination mechanisms were established during the reporting year, and they need to be sustained.
- Programme complementarity across the FCDO Nigeria portfolio has been difficult to achieve. To incentivise suppliers, the PACE team has introduced complementarity targets in its results framework. Advocacy for adoption of such approaches across the wider BHC portfolio needs to continue in the next reporting year.

Output Title	Component 3 (Fair Power Structures) partner identified and procured
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.2: Progress on drafting of AG/MOU agreement, approval, and AG signing with partner	Milestone 1: July 2024 / Proposal received from partner, assessed, and approved.	Met. Proposal received from PLAC and approved in August 2024. / Two further MOUs (not envisaged in the Business Case) with UN Women and Westminster Foundation for Democracy (WFD) were approved in October 2024
	Milestone 2: August 2024 / Due diligence of partner drafted and approved.	Exceeded. Extant Due Diligence Assessment (DDA) report on PLAC under PERL programme adopted for PACE. DDA for UN Women and WFD completed and approved in October 2024.
	Milestone 3: September 2024 / AG/MOU Letter drafted, Project documents developed, reviewed, and signed with partner.	Met. Accountable Grant (AG) with PLAC signed in October 2024. / MOUs with UN Women and WFD signed in October 2024.
2.3: Partner mobilised and delivering	Milestone 1: March 2025 / Inception phase completed with analytical studies, intervention plans, results framework, workplan and strategy finalised. / Milestone 2: March 2025 / Delivery of substantive activities under all three AG/MOU commenced. (March 2025) / Milestone 3: June 2025 / Proposal for second FPS grant and Women’s Political Empowerment (WPE) AG/MOU received from partner, accessed and approved.	Exceeded. Workplans for PLAC, UN Women and WFD finalised and approved in October 2024. / Delivery of substantive activities commenced in October 2024 and ongoing. / Process for second FPS Accountable Grant Agreement (AGA) commenced but paused pending budgetary allocation for 2025/2026.

Briefly describe the output’s activities and provide supporting narrative for the score.

The strategy for the Fair Power Structures (FPS) component of the programme anticipated two delivery instruments during the inception phase – an Accountable Grant Agreement (AGA) with the Policy and Legal Advocacy Centre (PLAC), and a Memorandum of Understanding with USAID. Both instruments were completed and signed on schedule, with delivery commencing in accordance with the milestones set.

The AGA with PLAC focused on support to the National Assembly and civil society, specifically delivering:

Technical support to priority committees in the National Assembly (NASS). This included work with the Constitution Review Committees of the Senate and House of Representatives. About 113 draft bills for the review process were completed and have gone through second reading in the House. The bills cover key FCDO Nigeria priority issues such as women’s political empowerment, local government reforms, electoral reforms, policing and judicial accountability. Public hearing on the bills is scheduled for the next quarter. PLAC also delivered trainings to the Joint Committee on Climate Change and technical support to the Joint Committee on Electoral Matters leading to the draft of an Electoral Act amendment bill.

Support for civil society advocacy and engagement around the 2024 governorship election in Ondo State by the Nigeria Civil Society Situation Room and its member organisations. This focused on mitigating election violence, civic education/participation, the deployment of election technology and citizen oversight of the process. Through these interventions, 95% of incidences of election-day infractions escalated to INEC were resolved. Kimpact Development Initiative (KDI) – a member organisation of the Situation Room – deployed observers and technology platforms for early warning purposes and coordinated with security agencies to mitigate violence. KDI also facilitated stakeholder engagements, promoted the integrity of the poll by undertaking parallel result tabulation and enhanced civic awareness through an AI powered platform - Naija elections.
The MOU with USAID – delivered by the International Foundation for Electoral Systems (IFES) provided strategic technical support to INEC for the governorship election in Ondo State. It also delivered technical support to six State Independent Electoral Commissions (SIECs) to better deliver local government elections. This led to improvements in key election administration areas during local government elections in Plateau, Kaduna and Akwa Ibom States. It also delivered demand-side engagements by citizens in local government polls in the specified states.

In support of the BHC-wide campaign for women’s political empowerment, a Memorandum of Understanding (MoU) was signed with the Westminster Foundation for Democracy in October 2024. To date, the project has successfully supported the Inter-Party Advisory Council’s (IPAC) to adopt a new a constitution providing a robust governance framework and strengthening inclusion in political life, including: 1) The establishment of Directorates for Women, Youths, and Persons with Disabilities; 2) Clear guidelines for conducting elections at the National, State, and Local Government Area levels, and 3) A mandatory requirement for the inclusion of women in leadership positions within the Council and member political parties.
Further, an MoU was signed with UN Women to advance Nigeria women’s political empowerment in October 2024. The project supports awareness raising and public hearings in Nigeria’s constitutional amendment process for the introduction of parliamentary gender quotas. The activities of the project, including media campaigns and preparation for public hearings, are shaping conversations on the proposed Special Seats Bill as constitutional reform conversations gather momentum.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Since the last AR, the following changes were made:
Indicator 2.2:
- Milestone 1 changed from February to July 2024
- Milestone 2 changed from March to August 2024
- Milestone 3 changed from April to September 2024
- Indicator 2.3:
- Milestone 2 changed from October 2025 to March 2025

These changes were necessary to bring the timeline for completion of these milestones in accordance with the approved strategy for the FPS component. Whilst the initial timelines were put in place in accordance with the general timeline of the PACE Programme, these updated timelines take into consideration the fact that the FPS component would not go through the same procurement process as the other components of PACE. The core of the interventions under the component would be delivered until the end of PERL in September 2024. The processes for securing the delivery instruments and commencement of implementation under the FPS component of PACE were therefore designed to commence around the end of the PERL Programme. This also enabled alignment with the conclusion of the longer procurement process for the other components of PACE.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned this year and recommendations for the year ahead
- The establishment of a framework for internal coordination for Component 3 and the other components of the programmes has been instrumental to enabling key programme outputs during the inception phase of the programme. Two illustrations of this include the development of a joint results framework for the programme, and agreement on a strategy for engagements with the legislature. Building on these coordination and information sharing efforts will be beneficial to delivery as the programme goes into full implementation in the next financial year.
- With USAID, one of the key delivery partners for this component, closing its democracy portfolio, the FPS component of the programme needs to take a strategic decision in its approach to adapting to this reality. Going forward, the programme needs to decide on the scope of the portfolio in the light of this change, including exploring new potential partnerships.
- The FPS component needs to put in place a specific strategy for engagement and support for the 2027 general elections which are now just two years away.
- The programme needs to rationalise its general approach, and the pivots needed to align with FCDO’s thematic priorities of economic growth and security.
- FPS component should develop its VFM and MEL strategy/framework to ensure consistent VFM assessment and MERL reporting.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The PACE theory of change is based on proactive flexible and adaptive programme management enabling activities to change to deliver VFM.

As PACE is just out of its Inception Phase and not yet fully operational, there is no change in the value for money proposition as outlined in the Business Case, or the prospective key cost drivers. The programme value for money propositions might need to be reviewed in light of the forthcoming budget adjustments. Some illustrations of the programme VfM performance in these early stages are provided below:

Economy:
- DAI-led components: The DAI-led components of the programme made considerable savings due to co-locating with the PLANE programme in Abuja. Cost-sharing arrangements include utilities, rent, office supplies, and other general expenses estimated to be approximately £12,500. In Kaduna, Kano and Jigawa, no rental costs were incurred, as the offices are situated in government facilities. The programme also leveraged the use of the PERL assets for its operations, minimizing procurement costs.
- Fair Power Structures: Long standing engagement of our partner PLAC with particular hotel in Abuja, has resulted to considerable discounts at the range of £40,000 - £51,000 annually.
Efficiency: All programme components leveraged existing partnerships between civil society organizations and government ministries, departments, and agencies to enhance collaboration, fast track reform, streamline processes, and reduce duplication. This allowed the programme to hit the ground running and implement priority activities during its inception phase, including:
- DAI-led components supported the development and cross-government validation of a Policy Management Framework for the Federal Government, expected to improve the quality of policymaking nationwide.
- PLAC’s influencing strategy at NASS resulted in the Committees of the Senate and House adopting joint sessions on Constitutional Review and Electoral Matters. These efforts promote collaboration and reduce the amount of time required to harmonize different versions of the draft legislation.
- During the period, PLAC’s work with the National Assembly in analyzing bills at a reduced or no cost to FCDO, this has been made possible through enhanced capacity within PLAC, gained over years in working with the institution. The savings of what would have been used in contracting consultants is estimated at £4,800. Further, the Situation Room (a CSO network supported by PLAC) delivered train-the trainer sessions to grassroots CSOs in proximity to election sites, reducing the cost of observation monitoring.
Effectiveness, Equity and Cost Effectiveness: As PACE is still in the initial stages of implementation, it is too early to determine its Effectiveness, Equity and Cost Effectiveness. The programme will monitor a select number of SMART indicators, both qualitative and quantitative, as part of future annual reviews. Emphasis will be given to understanding drivers of effectiveness.

E: RISK

Overview of risk management
PACE is a major risk programme as approved by Ministers when the Business Case was signed-off. This level of risk signifies a receptive tolerance level which aligns with the FCDO Nigeria overall risk appetite. Risk management follows the PROF guide, and BHC’s internal risk management approach, including at minimum quarterly reviews of risk registers, risk escalation when needed to SRO, ISDU, Development Director, SLT, and Directors. Due to the adaptive nature of the programme and the fluidity of the context, PACE’s risks are a standing agenda point in every programme management meeting and are discussed on an ad hoc basis if circumstances require.

To effectively manage risk across the programme, FCDO facilitated capacity building sessions on financial and risk management, empowering delivery partners with essential skills for developing robust risk framework and to ensure that programme delivery remains within risk threshold.

At 1 April 2025, PACE had 12 live risks, 2 of which are severe, 6 major, and 4 moderate. Following mitigation these have been reduced to 2 major, 7 moderate, and 3 minor. Below is a summary review of PACE’s risk appetite for each of the six risk categories, residual risk exposure and the most significant challenges over the last year:

Strategy and context: Risk appetite was maintained as ‘receptive’/’major’. A key risk was posed by the new aid policy of United States Government and the termination of the USAID-FCDO co-funding arrangement. This may have a negative impact on the delivery of electoral support, with a ‘severe’ gross risk rating. The risk was mitigated to ‘major’ through identification of two alternative delivery options. Further, the worsening security situation in the northwest was assessed as a ‘major’ gross risk, mitigated to ‘moderate’ by ongoing political analysis and coordination with conflict/security experts at post.

Policy & Programme Delivery: During the reporting period, the risk appetite was set at ‘eager’/’severe’. The gross risk of the reduction of UK ODA to 0.3% was assessed as ‘severe’. The residual risk was assessed as ‘major’, with key mitigation approaches included communication internally and with partners, strategy refresh and scenario planning. The financial stability of key implementing partners due to reduction of aid flows was assessed as a major gross risk. Measures to address included coordination and information sharing with commercial colleagues at post and in HQ, and regular communication with partners. However, the residual risk is maintained as ‘major’.

Safeguarding: PACE risk appetite was ‘moderate’/’cautious’. A key gross risk, assessed as ‘major’, was that inadequate analysis of climate and politically sensitive interventions could inadvertently do harm. The risk is mitigated to ‘minor’ as a result of ongoing political economy and conflict analysis, as well as the conflict sensitivity strategy developed during inception.

Reputational: Risk appetite was ‘moderate’/’cautious’. Sensitivities around foreign interference in the country’s internal affairs were assessed as a gross ‘major’ risk. Mitigation to ‘moderate’ includes careful management of the public profile of PACE, working politically, and adopting a locally-driven partnership approach.

Financial & Fiduciary: Risk appetite was ‘moderate’/’cautious’, with an identified ‘major’ gross risk covering foreign exchange rates, and fuel prices. This was mitigated to ‘moderate’ through due diligence assessments, raising awareness and building capacity of partners, and close monitoring of implementation.

People: Risk appetite was ‘cautious’/’moderate’. A key risk, assessed as ‘major,’ was staff resilience and welfare due to the uncertain budget situation and perceptions of job insecurity. Transparent internal communications and work on alternative scenarios brought the residual risk down to ‘moderate’.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Commercial
FCDO has a contract with DAI for £26m (July 2024 - July 2028) to provide technical assistance to government and civil society partners. The contract was approved on 24 June 2024 before the commencement of the inception phase. A Contract Amendment 1 (CA1) was approved to enable the supplier to respond to government priorities. The supplier has successfully completed the inception phase and is currently in the programme implementation phase. Three other agreements were approved during the inception period; 1) Accountable Grant Agreement with PLAC, 2) MoU with Westminster Federation for Democracy (WFD) both on the 11th October 2024 and 3) MoU with UN Women approved on 25th October 2024.

Programme finances
The total programme budget for PACE is £38.8m (from 18/10/2023 to 19/09/2028). As of 31 March 2025, £3,681, 939.07 (99.7%) has been expended. The forecast for 2024/25 was £3,693,392. The programme achieved 99.9% budget utilisation.

Programme management
During this reporting period, FCDO established a functional programme management system including routine fortnightly meetings and monthly engagement at the start of the implementation phase. PACE achieved its financial forecast and delivered zero variance of projected expenditure.

FCDO team established internal programme coordination across components to improve coordination and identify opportunities for regular collaboration between partners (PLAC, DAI, UN Women and WFD) and alignment with FCDO priorities. PLAC and DAI for example formalised their partnership on National Assembly through a framework on ways of working.

At cross-mission level, Governance Advisers are collaborating with relevant teams (e.g. climate change, local government) to pull resources and adapt approaches. For example, the team held technical sessions with UK NAIF, SPRING, PropCom+, Lafiya and UK-PACT to understand the respective programme’s focus areas and explore potential areas of complementarity for climate change action. Further, PACE is working with PLANE to coordinate engagement with partner states Kaduna, Kano, and Jigawa and Federal partners on the Eligibility Criteria (EC) and Disbursement Linked Indicators (DLIs) for the World Bank Human Capital Opportunities for Prosperity and Equity (HOPE) Program. HOPE is expected to support improvements in the strategic allocation and expenditure of resources for basic education and primary health.

Partner performance
DAI: DAI has established a functional programme management system. The partner submitted detailed narrative reports, forecasts, and expenditure reports as scheduled. All 16 inception deliverables were delivered, though some required significant revisions due to the need to coordinate across the mission, respond to HMG policy pivots, and strengthen the approach to climate governance. All inception deliverables were approved in March 2025. DAI’s first contract amendment enabled the PACE team to respond to BHC’s policy priorities and extend technical support to the federal government on performance management.

PLAC: PLAC has performed well as outlined in its inception deliverables: supported FCDO to navigate our partnership with the National Assembly and delivered grants management to downstream partners. Their coordination of other CSOs through the ‘Situation Room’ has enabled FCDO to reach a broach range of subnational and national CSOs and helped the coalition of CSOs to demand for accountability in the management of elections. PLAC has also helped the NASS to build capacity of the legislature especially on NASS legislative reform agenda.

USAID: The co-funding arrangement with USAID ended with the suspension of funding to Nigerian partners. A refund from the US government is expected, however parameters for the refund are yet to be established due to challenges in official communication with USAID counterparts. FCDO programme team is actively monitoring the situation in consultation with the Integrated Strategy Delivery Unit (ISDU).

UN Women, WFD and WB manage small grants that is supporting our campaign on social protection and women’s political empowerment. Progress reporting has been delivered as planned, and regular engagements have enabled FCDO to assess performance and emerging risks.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

In line with the Business Case, PACE finalised its Results Framework and monitoring, evaluation and learning strategy during inception. Programme assessment against this framework will be undertaken in the next annual review, which will be the first year of implementation.

PACE is by design an adaptive programme, making it challenging to assess progress against standard logical frameworks. In response to this, the team worked with implementing partners and FCDO’s Centre for Delivery (CfD) to adopt an alternative approach that scores the programme against the following areas: 1) Delivery, which looks at quality, timeliness and appropriate use of resources; 2) Actionable Learning, which assess how progress is made through testing and learning, identifying what works and what does not and why; 3) Contribution to Meaningful Change, which is demonstrable evidence of progress towards targeted outcome-level change, and 4) Fitness for Purpose, which is the evidence of how the design and delivery approach are appropriate to reach set goals and continue to be relevant in an evolving context.

The alternative approach developed by CfD was deemed more appropriate for PACE as it incentivises a more explicit focus on monitoring progress towards outcomes during the life of the programme. It ensures the programme is assessed on the quality of its adaptation to the shifting political-economic context based on actionable learning – which is key to PACE’s continued relevance in Nigeria and embodied in the Theory of Change set out in the Business Case.

Following consultations with colleagues from the ICF HQ team, PACE also developed an ICF methodology, which allowed in to embed ICF-relevant indicators at output, outcome and impact levels of the Results Framework. This also provided useful guidance to implementing teams on designing interventions in line with the HMG ICF methodology.

Date of last narrative financial report	Not Applicable at this stage	Date of last audited annual statement	Not Applicable at this stage