Basic Information

Programme name	The Partnership for Agile Governance and Climate Engagement programme (PACE)
Programme number	6121
Programme description	The Partnership for Agile Governance and Climate Engagement programme (PACE) is a 48-month Foreign Commonwealth and Development Office (FCDO) funded programme, aiming to support coalitions to influence government to resolve climate and governance problems affecting the poorest and most vulnerable Nigerians, and hold them accountable for climate change objectives. The programme will support state governments to increase income from internally generated revenue; mainstreaming climate action in the centre of state government policy, planning and budgets; and strengthening election delivery and credibility. This will be achieved working with civil society organisations, the private sector, progressive state governments, and the Federal Government. Also, Thinking and Working Politically (TWP) Approach will aid in navigating complex power dynamics, interest and influence in the governance space, and using applied political economy analysis tools to understand the context to effectively engage the political and social processes and shape interventions development for the PACE programme. The beneficiaries of the programme are citizens through support provided to government institutions, civil society organisations, research institutions and private sector organisations both at the federal and sub national levels in PACE focal locations.

Impact

Impact statement	Indicators	Definition	Source	Baseline	Target [2028]
A more stable and climate resilient Nigeria	1. Target state scores TIWs on center for Fiscal Transparency and Integrity Watch (CeFTIW) variables: / Citizen Engagement and / Fiscal Transparency	The Transparency and Integrity Index (TII) initiated by the CeFTIW seeks to monitor the compliance of government agencies with information disclosure, as mandated by national laws and international conventions. CeFTIW assesses MDAs according to six criteria: / 1. Website Integrity. / 2. Fiscal Transparency. / 3. Open Procurement. / 4. Citizen Engagement. / 5. Human Resources. / 6. Anti-corruption.	The Transparency and Integrity Annual Report / https://www.fiscaltransparency.org/	Transparency and Integrity Index 2022 / Overall states ranking / Kaduna – scored 58.32% and ranked 2nd / Kano- scored 52.08% and ranked 5th / Jigawa scored 42.58% and ranked 18. / Fiscal transparency/financials. / Kano scored 43.75 and ranked 14 / Kaduna scored 43.73 ranked 15 / Jigawa 37.46 ranked 23 / Citizen’s engagement / Kaduna scored 100 and ranked 1st / Jigawa scored 66.67 and ranked 3rd / Kano scored 66.67 and ranked 3rd	States score improved/sustained for at least 2 out of the 6 variables of the Transparency and Integrity Index.
	2. Progress towards selected Climate Change Index & ICF KPI 15: / Climate Change Performance index (CCPI) ranking.	The CCPI measures Nigeria’s climate protection performance using four criteria namely, GHG emissions, renewable energy, energy use and climate policy. The overall climate change performance index is used to account for respective scores of each country (in this case Nigeria).	Nigeria - Climate Performance Ranking 2025 | Climate Change Performance Index.	2025 CCPI report / Score of 59.16	Moderate improvement in the CCPI score
	Subnational Climate Governance Performance rating and ranking	The Climate Governance Performance Rating and Ranking is aimed at producing a comprehensive single ranking of climate governance and actions in states based on internationally recognized criteria for measuring the quality of climate governance at subnational levels with the objectives of highlighting good practices and efforts, spotlighting gaps, and ultimately drawing stakeholders’ attention to where more efforts and collaborations are necessary.	Subnational Climate Governance Performance Ranking Report - Society for Planet and Prosperity	Climate Governance Performance rating and ranking of Nigeria’s 36 States report / Kaduna - 16th / Kano – 35th / Jigawa – 33rd	Improvements on the subnational CGPI variables.
	Extent to which ICF interventions are likely to lead to Transformational Change	From the nine criteria under ICF 15, seven have been selected to report on in the PACE Programme. The seven criteria selected cover the three levels of the TOC for transformational change that has drivers, mechanism, and enablers.	PACE ICF KPI 15 Annual report	0	Improvement in each state on selected indicators
	3. Score on citizen-centric Governance and Public Service Delivery (GPSD) Index using following pillars / Access. / User-centered Service Delivery and Responsiveness.	PACE will use a citizen-centric governance index to assess the quality of governance and public service delivery in KKJ states. Citizen here refers to all people in a society in an inclusive and non-discriminatory way. The four pillars include access; user-centeredness and responsiveness; quality and reliability of service delivery, and public sector integrity. The access pillar will track issues such as affordability, geographic proximity, and accessibility of information. The responsiveness pillar will include topics such as the citizen-centric approach, the matching of services to special needs, and timeliness. The pillar of reliability and quality includes issues regarding the effective delivery of services and outcomes, the consistency of service delivery and outcomes, and security and safety. Lastly, public sector integrity pillar will assess whether or not the citizens feel they are treated fairly and equitably.	Governance and Public Service Delivery (GPSD) Index Report		Improvement in scores across indicators on access, user-centred and responsiveness.
	4. Nigeria’s ranking on Worldwide Governance Indicators (WGI): / Voice and Accountability rank / Government Effectiveness rank	The WGI indicators offer a comprehensive dataset that encapsulates six governance dimensions, including voice and accountability, political stability, and absence of violence, government effectiveness, regulatory quality, rule of law and control of corruption	The Worldwide Governance Indicators Annual Report / https://www.worldbank.org/en/publication/worldwide-governance-indicators / Interactive Data Access | Worldwide Governance Indicators	2023 WGI Nigeria ranking. / Voice and Accountability ranked 35% / Government Effectiveness rank ranked 20%	Improvement in at least 2 out of the 6 WGI ranking.
	5. NOI Polls’ annual assessment & Mo Ibrahim Foundation index / Performance score of democratic institutions (NASS, INEC etc.).	The NOI polls will capture public perception of governance and performance of democratic institution such as the National Assembly and INEC. It will also assess areas such as security, rule of law, participation, economic opportunities and human development.	NOIPolls Limited | Research | 1107 Kabir Rabiu Rd, near Trinitate international school, Abuja, Nigeria	NOI Polls 2024 assessment of the NASS performance as of Dec 2024: / Senate 35.9%. / House of Reps 42.3%	NOI Polls assessment of the NASS in 2028 (1% increase annually = 4% by 2028) / Senate: 39.9% / HoR: 46.3%
	Citizens' opinion on the state of democracy in Nigeria.		Ibrahim Index of African Governance (IIAG) | Mo Ibrahim Foundation	NOI Polls assessment of INEC performance during 2023 general elections were: / V. good/good 38%. / Average 26%. / V. poor/poor 36% / Overall Governance: 2023 rank, 10-year change & trend (2014-2023). Nigeria ranked 33.	NOI Polls assessment of INEC in 2028 / (1% increase annually = 4% by 2028) / V.good/good= 42% / Average = 29% / V.poor/poor = 32% (Very poor is calculated using decreasing indices to show improvement).

Outcome / More accountable and inclusive institutions that responds to Nigeria’s interrelated governance and climate challenges

Outcome statement(s)	Indicators	Data Source/MoVs			Unit of measurement	Baseline	Targets 2028[1]
Outcome 1. / Institutional and legal reform processes support more inclusive power structures and better response to governance and climate challenges	1.1 Evidence of targeted (institutional and legal reforms) and other stakeholders becoming more responsive to governance and climate challenges.	Synthesis of PACE MSC case studies.			Qualitative	0	At least 3 PACE Most Significant Changes that have advanced to outcomes showing enhanced inclusivity in decision-making and improved governance mechanisms for addressing climate challenges, with evidence of active participation from citizen groups.
	1.2 Evidence of multisectoral approaches in addressing governance challenges and climate risks issues.	Synthesis of PACE MSC case studies.			Qualitative	0
Outcome 2: / Coalitions of citizens influence government to resolve climate/governance/social protection/problems and hold government accountable	2.1 Evidence of state and non-state actors demonstrating improved awareness, knowledge and capabilities as a result of PACE technical assistance.	Synthesis of PACE MSC case studies.			Qualitative	0	At least 3 PACE Most Significant Changes that have advanced to outcomes demonstrating evidence of citizens influencing government decisions or policy implementation related to climate, governance, or social protection
	2.2 Extent to which non-state actors (including marginalised groups) are active and influencing governance reforms.	Synthesis of PACE MSC case studies.			Qualitative	0
Outcome 3: / Strengthened state planning, budgeting and policies for better service delivery, social protection and response to climate risks and impacts	3.1 Improved Federal, Kaduna, Kano & Jigawa governments expenditure on climate adaptation, resilience, & disaster risk reduction.	Synthesis of PACE MSC case studies.			Quantitative and Qualitative	2025 approved budgets for Climate adaption, resilience and disaster reduction.	At least 3 PACE Most Significant Changes that have advanced to outcomes demonstrating improved planning, budgeting, or policy mechanisms—evidenced by the adoption of climate-responsive budgets, integrated social protection strategies, or service delivery frameworks that incorporate climate risk assessments.
	3.2 Extent to which actions effectively address service delivery blockages in selected sectors at Federal, Kaduna, Kano and Jigawa state level.	Synthesis of PACE MSC case studies.			Qualitative
Outcome 4: / Increased state government revenue generation and preparedness to access climate finance	4.1 Existence of functional policies and frameworks for leveraging climate finance.	Synthesis of PACE MSC case studies.			Qualitative and Quantitative.	Climate Change policies / Climate change Act	At least 3 PACE Most Significant Changes that have advanced to outcomes demonstrating improved revenue generation strategies and established climate finance readiness plans or mechanisms, in readiness to access national or international climate funding sources
	4.2 Year-over-year change in revenue generated	Synthesis of PACE MSC case studies.			Quantitative	Kaduna – N62.42bn (2023) / Kano – N40.51bn (2023) / Jigawa – 11.68bn (2023)
Outcome 5: / Strengthened democratic systems, processes and institutions	5.1 Evidence of targeted reforms from PACE resulting in improved functionality of democratic institutions’ systems and processes.	Synthesis of PACE MSC case studies.			Qualitative and Quantitative.	Published 10th NASS Legislative Agenda (Senate & House of Rep) / Published CSO Credibility Thresholds to monitor INEC/SIEC functionality for the 2023 General Elections	At least 3 reform initiatives undertaken by NASS (Senate and House combined) as a result of PACE C3 partners’ technical support.At least 5 reform recommendations adopted and implemented by INEC/SIEC for general and off-cycle elections between 2024 and 2027.
	5.2 Extent to which civil society is holding democratic institutions to account.	Synthesis of PACE MSC case studies.			Qualitative	N/A	6 strategic CSO platform to hold democratic institutions accountable at national and sub-national levels. / MSCs in three to four thematic areas (aligned with subgrants and work of KDI) showing positive change in democratic processes and systems at national and sub-national levels).
Outcome to impact assumptions
[1] For consistency in interpreting progress vis-a-vis the PACE Results Framework and PACE MSC, “advancement to outcomes” refers to demonstrable changes that aligns with the relevant Rubric in tables (1 – 9) of the MSC Template that covers the 9 criteria. This denotes that the change has moved beyond the “high level output to High outcome Levell”, which may occur over a multi-year timeframe. Reviewers/users should refer to the MSC criteria to assess whether the documented results meet the outcome threshold.

Performance Areas/Outputs

Performance Area statement(s)		Indicators	Source	Unit of measurement	Frequency of data collection & reporting	Responsible PACE component	Baseline [2024]	Milestone [April 2025 to March 2026]
	Delivery (Weight: 50%) Year one
1. Coalition of state and/or non-state actors that work together effectively to tackle democratic governance issues		1.1 Evidence of active coalitions of state and non-state actors informing government plans, policies and budgets.	PACE MSC case studies	Qualitative	Annually	PACE component 1,2,4 & 5 partners.	Coalitions of states and non-state actors has informed govt policies, plan budget. / NAP I-III / Tax reform Bills/laws / MTEF and budgets / Kaduna SAP I-III / Kano SAP I-II / Jigawa SAP I / Coalitions have also influenced State budgets in KKJ.	Coalitions of state & non-state actors to influence at least 3 govt policies, plans or budgets in KKJ States
		1.2 Evidence of issues identified and engaged including social protection and governance	PACE MSC case studies	Qualitative	Annually	PACE component 1,2,4 & 5 partners	Three (3) governance and 1 Climate Change issue identified and being implemented in FKKJ.	At least 1 out of the 4 issues identified in FKKJ is being addressed with clear implementation strategies for addressing the remaining issues.
		1.3 Evidence of key accountability actions taken by civil society to improve democratic governance.	PACE MSC case studies	Qualitative and Quantitative	Annually and quarterly	PACE component 3 partners	50 public engagements conducted by CSOs in 2024 / 30 CSOs supported to take actions in 2024 / 28 SR members sub-granted to implement actions at the subnational level in 2024 / 2,600 CSO election observers deployed nationwide for the 2023 General Elections / 20,000,000 people reached in 2024 through various CSO accountability actions	At least 20 key accountability actions taken by civil society to improve electoral and democratic governance processes / At least 3 digital accountability platforms established / At least 12 Subgrants to civil society to undertake accountability interventions/issue-led advocacy implemented at the subnational level
2. Government capability and accountability to citizens to tackle democratic governance issues increased		2.1 Extent to which government periodic plans, policies, systems and budgets are realistic and responsive to governance and social protection issues.	PACE MSC case studies	Qualitative and Quantitative	Annually	PACE component 1,2,4 & 5 partners	2025 Climate budget tagging in PACE locations. / • Kaduna –NGN113.34bn / • Kano - NGN32.24bn / • Jigawa State - NGN50.98bn / Budget allocation for social protection	Improved alignment between plans and budgets that are addressing governance and social protection priorities in at least 2 out of the 4 PACE locations
		2.2 Evidence of relevant and functional accountability mechanisms and engagements (around governance issues) established and/or sustained in PACE locations.	PACE MSC case studies	Qualitative	Annually	PACE component 1,2,4 & 5 partners	There is a functional climate focused accountability mechanism in Kaduna “Network of Civil Society in Environment championing advocacy/engagements on climate issues. There is no structured and climate-focused coalition in Kano and Jigawa.	At least 1 climate-focused accountability mechanism/coalition established in any of the three PACE locations.
		2.3 Evidence of relevant legislative and other institutional functions/activities taken to improve democratic systems and processes.	PACE MSC case studies	Quantitative and Qualitative	Annually and quarterly	All PACE components	Relationships established and support provided to 12 priority committees of NASS in 2024 / 40 retreats and 70 capacity-building training conducted for NASS in 2024 / Needs/capacity assessment conducted for 36 SHoAs in 2024.	12 priority committees of NASS continue to receive technical support / 15 legislative retreats/oversight actions and 15 training capacity-building sessions / Completed framework of engagement with selected SHoAs agreed and adopted.
3. Govt capability & accountability to manage internal revenue increased through collaboration with relevant programs /institutions		3.1 Evidence of functional and transparent revenue management systems and processes in Kaduna, Kano and Jigawa.	PACE MSC case studies	Qualitative and Quantitative	Annually	PACE component 1,2,4 & 5 partners	Availability of fiscal instrument such as Medium-Term Revenue Strategies in KKJ to support revenue Administration / Functional Tax Networks/coalitions in place in KKJ / Institutional capacity of revenue agencies enhanced.	Implementation of revenue strategies & integrate technology in revenue management, providing tools & systems that enhance decision-making and efficiency in revenue administration across PACE locations.
		3.2 Extent to which revenue generated is improving social contract and tax for service in Kaduna, Kano and Jigawa.	PACE MSC case studies	Qualitative and Quantitative	Annually	PACE component 1,2,4 & 5 partners	States IGR performance / Kaduna – N62.42bn (2023) / Kano – N40.51bn (2023) / Jigawa – 11.68bn (2023)	Moderate improvement in service delivery expenditure leading to improved compliance to tax provisions.
4. Actions taken to strengthen the climate governance systems in KKJ		4.1 Extent of preparedness/ readiness to access climate finance in Kano, Kaduna and Jigawa.	PACE MSC case studies	Qualitative and Quantitative	Annually	PACE component 1,2,4 & 5 partners	Kaduna Climate Policy / Kano Climate Policy.	Green Public Financial Management including (PPP, Development Bank of Nigeria, and private sector) readiness assessment conducted in at least 2 out of 3PACE locations to assess the state’s capacity to access climate finance including the HOPE_GOV Project grant.
		4.2 Evidence of government plans under implementation informed by PACE ICF interventions.	PACE MSC case studies	Qualitative and Quantitative	Annually	All PACE components	2024 States Climate policy / 2025 Climate budget tagging for KKJ	At least 1 state implements 35% of climate projects in the approved 2025 budget & contribute to relevant ICF criteria.
		4.3 No of direct and targeted individual and organisational beneficiaries supported by ICF TA	PACE MSC case studies	Quantitative	Annually	All PACE components	0	At least 30 individuals and 4 organisations in FKKJ received targeted technical assistance to respond to climate shocks and disasters.
		4.4 Number of activities e.g. workshops and key publications delivered to disseminate climate resilience measures.	PACE MSC case studies	Quantitative		All PACE components	No records of activities yet.	At least 4 events across FKKJ on the whole of society approach and support to key institutions to respond to governance and climate issues.

`Actionable Learning (Weight: 30%) Year one			Unit of measurement	Frequency of data collection and reporting	Responsible PACE Component	Baseline 2024	Descriptions / scoring for Actionable Learning
5. Learning and evidence inform programme approaches and build the evidence base.	5.1 Evidence of programme & partners undertaking research and generating learning and evidence to inform policy & advocacy and adapt their strategy/intervention.	PACE MSC case studies	Qualitative and Quantitative	Annually	All PACE components	Programme activities yet to start. / Component 3 baseline / 40 policy briefs produced and disseminated on legislative reforms / 4 Research conducted on electoral reforms and outcomes disseminated	A++ PACE programme and partners have effectively generated reliable research and learning that has been used to inform policy decisions, advocacy strategy and adaptation both within and outside the programme footprint. / A+ PACE programme and partners regularly produced research and learning that is used only for the review programme activities and interventions. / A PACE programme and partners have achieved planned research and learning to a good standard with findings available for use / B PACE programme and partners learning and research findings are insufficient to meaningfully guide and inform policy decisions, advocacy strategy and interventions design. / C The PACE programme and partners have not conducted research and learning to guide and inform policy decision/actions.
	5.2 Evidence of PACE/Partners adjusting strategies and intervention designs based on research, evidence and learning generated by the programme.	PACE MSC case studies	Qualitative and Quantitative	Annually	All PACE components	Full implementation will start in Year one	A++ PACE programme and partners have significantly adjusted a number of strategies/interventions design based on research, evidence from learning and testing of high, mid and low levels propositions in the theory Change. / A+ PACE programme and partners have adjusted a few strategies/interventions design based on research, evidence and learning generated. / A PACE programme and partners identified strategies/interventions to be adjusted based on evidence from research and learning supported. / B PACE programme and partners research and learning evidence are insufficient to drive strategies and interventions adjustments and programme broad change. / C The PACE programme and partners have not conducted research and learning, and there is no evidence to inform strategies and intervention adjustment/review.
	5.3 Records of learning events and description of learning products facilitated by PACE’	PACE MSC case studies	Qualitative and Quantitative	Annually	All PACE components	Full implementation will start in Year one	A++ PACE cases of learning on successful reform initiatives facilitated across the eight programme themes addressing governance and climate delivery blockages in Kaduna, Kano and Jigawa including Federal / A+ PACE cases of learning on successful reform initiatives facilitated across the 6 programme themes addressing governance and climate delivery blockages in Kaduna, Kano and Jigawa including Federal / A . PACE cases of learning on successful reform initiatives facilitated across the 4 programme themes addressing governance and climate delivery blockages in Kaduna, Kano and Jigawa including Federal / B PACE cases of learning on successful reform initiatives facilitated across the 2 programme themes addressing governance and climate delivery blockages in Kaduna, Kano and Jigawa including Federal / C PACE cases of learning on successful reform initiatives facilitated in at least 1 programme theme addressing governance and climate delivery blockages in Kaduna, Kano and Jigawa including Federal

Contribution to meaningful change Weight: 20%) Year one					Unit of Measurement		Frequent of Data Collection and Reporting	Responsible PACE component	Basline	Descriptions / scoring for Meaningful Change
6. Sustainable improvements in accountability, inclusion and service delivery.	6.1 Evidence of PACE’s contribution to sustained government responsiveness to service delivery issues and priorities in PACE supported locations.		PACE MSC case studies		Qualitative and Quantitative		Annually	All PACE components	0	A++ Government is more responsive to the demands of stakeholders and prioritising delivery of public goods and services in the focus locations. / A++ Government sustained actions is moderately contributing to better delivery of public goods and services in focal states / A Government is increasingly becoming more responsive to stakeholders by addressing only identified delivery blockages that are related to governance and climate change. / B Government is only responsive to specific governance and climate change issues prioritized by the stakeholders with little or evidence of contribution to the delivery of public good. / C Government do not respond to stakeholder’s demands but prioritized issues on its agenda
	6.2 Evidence of PACE’s contribution to government transparency and inclusive governance process in PACE supported locations.		PACE MSC case studies		Qualitative		Annually	All PACE components	0	A++ PACE technical support is opening and creating spaces for all stakeholders to engage the government for better delivery of public goods and services that is contributing to effective growth and development in PACE focus locations. / A+ PACE technical assistance is creating spaces to a certain range of stakeholders, making government to be more accountable, effective, evidence informed and prioritising sustainable delivery of public goods in focus locations. / A PACE support is opening spaces for a minimal number of stakeholders to effectively address delivery blockages in focal states, on behalf of the citizens including the marginalised groups. / B PACE interventions are creating spaces for stakeholder to contribute and participate in public planning, budgeting and policy formulation processes for better delivery of public goods. / C PACE support is creating little or no spaces for stakeholders to contribute or participate in selected planning, budgeting and policy formulation processes.
	6.3 Evidence of scaling up/replication of PACE supported reforms across sector and/or location.		PACE MSC case studies		Qualitative		Annually	All PACE components	0	A++ PACE cases of learning on successful reform initiatives that has been used, adapted, scaled up, replicated and supported in at least 5 non-PACE locations and/or sectors / A+ PACE cases of learning on successful reform initiatives that has been used, adapted, scaled up, replicated and supported in at least 3 non-PACE locations and/or sectors. / A PACE cases of learning on successful reform initiatives that has been used, adapted, scaled up, replicated and supported in at least 2 non-PACE locations and/or sectors / B PACE cases of learning on successful reform initiatives that has been used, adapted, scaled up, replicated and supported in at least 1 non-PACE locations and/or sectors / C PACE cases of learning on successful reform initiatives that has been used, adapted, scaled up, replicated and supported only in PACE location and not sufficient to replicate.
	6.4 Evidence of collaboration among PACE Partners and between PACE and other sector programmes contributing to service delivery improvements.		PACE MSC case studies		Qualitative		Annually	All PACE components	0	A++ PACE actions and partnerships with sector programmes is contributing to better delivery of public goods and services that leads to inclusive growth and development. / A+ PACE partnerships are making government more accountable, effective, and prioritising sustainable delivery of public goods and services that meets needs of the citizens focus locations. / A PACE partnership with sector programmes is increasingly effective at addressing delivery blockages in governance and climate space in focus locations on behalf of citizens including normally excluded groups. / B PACE Partnership with other programmes is prioritising planning, budgeting and formulating policies for better delivery of public goods and services in focal states. / C Partnerships in focal states/locations do not prioritised planning, budgeting and policy formulation for better delivery of public goods and services
Output to outcome assumptions

Means of Verification (MoVs Log)

Results Level	Key Means of verifications (MoVs)	Other sources supporting Key MoVs
Outcomes	Synthesis of Most Significant Change Case Study (MSCs)	State of the State Assessment -Dashboard/summary findings / National Bureau of Statistics findings. / Readiness Assessment (Climate Finance) - Findings summary/Dashboard / Public Financial Management- Rapid Annual Appraisal (PFM RAA) - Findings summary/Dashboard / NOI polls / Approved budgets / Budget performance reports / Sector implementation reports / Accountant General report
Outputs	Most Significant Change Case Study (MSC)	Budget Performance Reports / Internal Generated Revenue (IGR) reports / Accountant General Report / State of the State Assessment -Dashboard/summary findings / Government records (Annual Budgets, plans, policies & Audited Financial Statements) / Newspaper reports. / Green PFM RAA / Citizen Accountability Report / PACE Partners report / Quarterly Progress report